## Summary
No | Description | Previous Amount | Current Amount | Cumulative Amount
| BOQ | 0 | 21982.4 | 21982.4
[5 empty] | 999150 | 20% | 199830
| Advance Payment | 199830 | 0 | 199830
| Advance Payment Recovery (20%) | 0 | -4396.48 | -4396.48
|  | 199830 | 17585.92 | 217415.92

## BOQ
S.N | Description | Sign Code | Contract BOQ |  |  |  | Quantity Certified |  |  | Total Amount |  |  | Comp (%) | Remarks
|  |  | Unit | Qty | Unit Rate | Amount | Previous | Current | To Date | Previous | Current | To Date
Room Number
| Room Number | 1.1 |  | 229 | 170 | 38930 |  |  | 0 | 0 | 0 | 0 | 0%
| Room Number | 1.1 |  | 0 | 135 | 0 |  |  | 0 | 0 | 0 | 0 | 0%
Door Sign
| Door Sign FOH | 2.1 |  | 263 | 242 | 63646 |  |  | 0 | 0 | 0 | 0 | 0%
| Door Sign BOH | 2.2 |  | 437 | 80 | 34960 |  | 54 | 54 | 0 | 4320 | 4320 | 12.36% | 90% until WIR approval
| Door Sign Picto FOH | 2.3 |  | 26 | 180 | 4680 |  |  | 0 | 0 | 0 | 0 | 0%
| Door Sign Picto BOH | 2.4 |  | 4 | 77 | 308 |  |  | 0 | 0 | 0 | 0 | 0%
| Technical Room FOH | 2.5 |  | 91 | 162 | 14742 |  |  | 0 | 0 | 0 | 0 | 0%
| Technical Room BOH | 2.6 |  | 169 | 120 | 20280 |  |  | 0 | 0 | 0 | 0 | 0%
| Leaf Sign FOH (double sided) | 2.7 |  | 8 | 746 | 5968 |  |  | 0 | 0 | 0 | 0 | 0%
Directional Sign
| Room Directional | 3.1 |  | 37 | 349 | 12913 |  |  | 0 | 0 | 0 | 0 | 0%
| Directional Sign Wall | 3.2 |  | 5 | 1640 | 8200 |  |  | 0 | 0 | 0 | 0 | 0%
| Vehicular Directional Sign (freestanding) | 3.3a |  | 3 | 18181 | 54543 |  |  | 0 | 0 | 0 | 0 | 0%
| Vehicular Directional Sign (Pole mounted) | 3.3b |  | 5 | 21085 | 105425 |  |  | 0 | 0 | 0 | 0 | 0%
| Pedestrian Directional Sign (freestanding) | 3.4a |  | 5 | 12825 | 64125 |  |  | 0 | 0 | 0 | 0 | 0%
| Pedestrian Directional Sign (pole mounted) | 3.4b |  | 2 | 19582 | 39164 |  |  | 0 | 0 | 0 | 0 | 0%
| Car Park Ceiling Directional | 3.5 |  | 8 | 1742 | 13936 |  |  | 0 | 0 | 0 | 0 | 0%
| Wall graphics signs | 3.6 |  | 3 | 987 | 2961 |  |  | 0 | 0 | 0 | 0 | 0%
| Column graphics signs | 3.7 |  | 8 | 498 | 3984 |  |  | 0 | 0 | 0 | 0 | 0%
| Lift Lobby ID | 3.8 |  | 6 | 829 | 4974 |  |  | 0 | 0 | 0 | 0 | 0%
| Integrated Directional | 3.9 |  | 13 | 335 | 4355 |  |  | 0 | 0 | 0 | 0 | 0%
| Floor Graphics signs | 3.1 |  | 1 | 1554 | 1554 |  |  | 0 | 0 | 0 | 0 | 0%
| Column Directional signs | 3.11 |  | 2 | 1310 | 2620 |  |  | 0 | 0 | 0 | 0 | 0%
Directory Signs
| Directory Sign | 4.1 |  | 14 | 2964 | 41496 |  |  | 0 | 0 | 0 | 0 | 0%
| Lift Cabin Directory Hotel | 4.2 |  | 11 | 192 | 2112 |  |  | 0 | 0 | 0 | 0 | 0%
Digital Signs
| Digital Screen Sign | 5.3 |  | 7 | 334 | 2338 |  |  | 0 | 0 | 0 | 0 | 0%
Level Signs
| Level Sign FOH | 6.1 |  | 11 | 190 | 2090 |  |  | 0 | 0 | 0 | 0 | 0%
| Level Sign BOH | 6.2 |  | 123 | 80 | 9840 |  |  | 0 | 0 | 0 | 0 | 0%
| Level Sign BOH / Staircase | 6.3 |  | 172 | 172 | 29584 |  |  | 0 | 0 | 0 | 0 | 0%
Identity Signs
| Monument ID | 7.3 |  | 2 | 36126 | 72252 |  |  | 0 | 0 | 0 | 0 | 0%
| Entrance ID | 7.4 |  | 1 | 673 | 673 |  |  | 0 | 0 | 0 | 0 | 0%
| Car Park Entrance ID | 7.5 |  | 1 | 5785 | 5785 |  |  | 0 | 0 | 0 | 0 | 0%
| Low Level Building ID | 7.6 |  | 1 | 13366 | 13366 |  |  | 0 | 0 | 0 | 0 | 0%
| F&B / Retail ID | 7.7 |  | 28 | 5246 | 146888 |  |  | 0 | 0 | 0 | 0 | 0%
| Desktop Sign | 7.8 |  | 3 | 271 | 813 |  |  | 0 | 0 | 0 | 0 | 0%
| Function ID | 7.9 |  | 4 | 592 | 2368 |  |  | 0 | 0 | 0 | 0 | 0%
| Building Entrance Sign | 7.1 |  | 8 | 673 | 5384 |  |  | 0 | 0 | 0 | 0 | 0%
| Lift Entrance ID | 7.11 |  | 1 | 1133 | 1133 |  |  | 0 | 0 | 0 | 0 | 0%
Elevator Signs
| Elevator Sign FOH | 8.1 |  | 159 | 64 | 10176 |  |  | 0 | 0 | 0 | 0 | 0%
| Elevator Sign BOH | 8.2 |  | 182 | 54 | 9828 |  |  | 0 | 0 | 0 | 0 | 0%
Emergency Signs
| Escape Route Plan FOH | 9.1 |  | 51 | 257 | 13107 |  |  | 0 | 0 | 0 | 0 | 0%
| Escape Route Plan BOH | 9.2 |  | 88 | 172 | 15136 |  |  | 0 | 0 | 0 | 0 | 0%
| Fire Hose Cabinet | 9.3 |  | 52 | 55 | 2860 |  |  | 0 | 0 | 0 | 0 | 0%
Rules & Regulations
| Rules and Regulation Internal | 10.1 |  | 2 | 1394 | 2788 |  |  | 0 | 0 | 0 | 0 | 0%
| Rules and Regulation External | 10.2 |  | 7 | 1923 | 13461 |  |  | 0 | 0 | 0 | 0 | 0%
| Pool Depth Marking | 10.3 |  | 6 | 285 | 1710 |  |  | 0 | 0 | 0 | 0 | 0%
| Assembly Point Sign | 10.4 |  | 0 | 1012 | 0 |  |  | 0 | 0 | 0 | 0 | 0%
Misc. Signs
| Escape Route Plan FOH (guest room) | 9.1 |  | 229 | 229 | 52441 |  |  | 0 | 0 | 0 | 0 | 0%
| Qibla Sign | 12.1 |  | 229 | 75 | 17175 |  |  | 0 | 0 | 0 | 0 | 0%
Preliminaries
| Shop Drawings |  |  | 1 | 14500 | 14500 |  | 0.8 | 0.8 | 0 | 11600 | 11600 | 80% | No supportings (Drawings, drawing refs)
| Project Management & Coordination |  |  | 1 | 7578 | 7578 |  | 0.8 | 0.8 | 0 | 6062.4 | 6062.4 | 80% | No supportings (Staff details, program)
[6 empty] | 0 |  |  | 0 | 0 | 0 | 0
| TOTAL AMOUNT (AED) |  |  |  |  | 999150 |  |  |  | 0 | 21982.4 | 21982.4 | 2.2%