## IPA
| EMPLOYER |  | : | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE |  | : | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER |  | : | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR |  | : | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| PROJECT |  | : | DORCHESTER HOTEL AND RESIDENCES
| KHANSAHEB JOB REF. NO. |  | : | 201A22002
| APPLICATION FOR PAYMENT NO. 14 | [6 empty] | FOR THE PERIOD ENDING: 31ST MARCH 2023
|  | Description |  | Original Contract Value Amount (AED) | Previous (AED) | This (AED) | Cumulative (AED)
|  | Total Value of Workdone |  | 194951734.5 | 195356338.9756 | 22687310.8874 | 218043649.8629
|  |  |  | 0 | 0 | 0 | 0
|  | Total |  | 194951734.5 | 195356338.9756 | 22687310.8874 | 218043649.8629
SUMMARY
| (i) | Total Value of Workdone |  |  |  |  | 218043649.8629 |  |  | 56294044.2448 | -161749605.6182
|  | Sub Total 01 |  |  |  |  | 218043649.8629
4000000
| (ii) | Add Mobilisation Payment 01 & 02 |  |  |  |  | 12000000
| (iia) | Less Advance Recovery |  |  |  |  | -4000000
|  | Sub Total 02 |  |  |  |  | 226043649.8629 |  |  | 68294044.2448 | -157749605.6182
| (iii) | Less Retention @ 10% on Provisional Sums & MEP (Except prelims & OHP ) |  |  |  |  | -10295542.3044 |  | KCE retention | 58595243.124 | -5859524.3124
| (iv) | Less Amount Certified Previously |  |  |  |  | -187380300.4783 |  | KMEP retention | 44360179.92 | -4436017.992
[10 empty] | 102955423.044 | -10295542.3044
| (v) | Amount due for Payment |  |  |  |  | 28367807.0803
226043649.8629
-3191697.0765
-397333
07.04.23
| Signature | [5 empty] | Date
Note: |  | Mobilisation payments (AED 12 million) to be recovered from subsequent payments as LOA clause 30. | [7 empty] | -448628.7596
222005991.0269
130255895.9809
-91750095.046
86791925.909
-139251723.954

## Summary
APPLICATION FOR PAYMENT - SUMMARY
| PROJECT | DORCHESTER HOTEL AND RESIDENCES | [5 empty] | FOR THE PERIOD ENDING: 31ST MARCH 2023
| EMPLOYER | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| CONTRACT NO. | 201A22002
| Item | Contract Amount | Percentage Complete |  |  | Value Complete |  |  |  | 461823.5938
|  |  | Previous Certificate | This Month | To Date | Previous Valuation | This Month | To Date |  |  |  | Total Certified |  | Variance
| Main Contract Value | 194951734.5 | [6 empty] | 6053836.2575 | 1013274.3962
1 | Civil Works
1.1 | Contract Cost - Direct Work |  |  |  |  | 118636881.237 | 14877019.5138 | 133513900.7508 | 48430690.06 | 8106195.17 |  | 56536885.23 |  | -76977015.5208
1.2 | Cost Adjustments |  |  |  |  | -150267.889 | -15156.26 | -165424.149 | -1208 |  |  |  |  | 165424.149
1.3 | Main Contractor OH & Profit (12.5%) |  |  |  |  | 13846790.8905 | 1703745.6557 | 15550536.5462 | 6445740.61 |  |  | 6445740.61 |  | -9104795.9362
( Exc. KID Value )
| Sub Total 1 |  |  |  |  | 132333404.2384 | 16565608.9095 | 148899013.1479 |  |  |  | 62982625.84 | 0 | -85916387.3079
2 | Provisional Sums (excl MEP)
2.1 | Subcontract Cost
2.2 | Main Contractor OH & Profit (12.5%)
| Sub Total 2 |  |  |  |  | 0 | 0 | 0
3 | MEP Works
3.1 | Subcontract Cost (incl KMEP oh&p of 12.5%) |  |  |  |  | 57293577.0337 | 5565183.6163 | 62858760.65 | 55874453.9111 |  | Correction: Apply retention only on KMEP SC works | 30299794.5825 |  | -32558966.0675
3.2 | Main Contractor OH & Profit on MEP (10%) |  |  |  |  | 5729357.7034 | 556518.3616 | 6285876.065 | 5714432.7864 |  |  | 2797241.92 |  | -3488634.145
| Sub Total 3 |  |  |  |  | 63022934.7371 | 6121701.9779 | 69144636.715 |  |  |  | 33097036.5025 | 0 | -36047600.2125
|  | 194951734.5 |  |  |  | 195356338.9756 | 22687310.8874 | 218043649.8629 |  |  |  | 96079662.3425 |  | -121963987.5204
196372661.4008
85904689.09
8106195.17
96079662.3497
0.0072381

## Pre Cert
APPLICATION FOR PAYMENT NO. 14
PREVIOUSLY CERTIFIED AMOUNTS
Certificate No. | Description | Certified Amount (AED)
1 | Payment Certificate 01 | 6000000
2 | Payment Certificate 02 | 6000000
3 | Payment Certificate 03 | 2104452.12
4 | Payment Certificate 04 | 11118319.2
5 | Payment Certificate 05 | 11047382.21
6 | Payment Certificate 06 | 12807977.89
7 | Payment Certificate 07 | 19982204.03
8 | Payment Certificate 08 | 15491078.95
9 | Payment Certificate 09 | 19804921.87
10 | Payment Certificate 10 | 21126467.6392
11 | Payment Certificate 11 | 19971554.879
12 | Payment Certificate 12 | 24211586.93
13 | Payment Certificate 13 | 17714354.76
14 | Payment Certificate 14
15
16
17
18
19
20
21
22
| TOTAL AMOUNT | 187380300.4783

## Cover
201A22002 - DORCHESTER HOTEL AND RESIDENCES
CONTRACTOR
KHANSAHEB CIVIL ENGINEERING L.L.C.
APPLICATION FOR PAYMENT NO. 14
201A22002 - DORCHESTER HOTEL AND RESIDENCES
APPLICATION FOR PAYMENT NO. 14
| Section 1 | Certificate / Summary
| Section 2 | Cost breakdown Summary
| Section 3 | Labour Cost & Backup
| Section 4 | Material Cost & Backup
| Section 5 | Plant Cost & Backup
| Section 6 | Subcontractor Cost & Backup
| Section 7 | Prelim & General Cost & Backup
| Section 8 | Salary Cost & Backup
| Section 9 | Committed Orders
| Section 10 | MEP Payment Application
| Section 11 | Cost Adjustments
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 1
Certificate / Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 2
Cost breakdown Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 3
Labour Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 4
Material Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 5
Plant Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 6
Subcontractor Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 7
Prelim & General Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 8
Salary Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 9
Committed Orders
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 10
MEP Payment Application
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 11
Cost Adjustments

## SC Summary
SUBCONTRACTOR PAYMENT APPLICATION (CIVIL WORKS) - SUMMARY
PROJECT : DORCHESTER HOTEL AND RESIDENCES | [6 empty] | 2023-03-31
EMPLOYER : SKY PALACES REAL ESTATE DEVELOPMENT LLC
MAIN CONTRACTOR : KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
CONTRACT NO : 201A22002
Sl No | Item | Scope of work | Work Approval Amount | Work Approval Reference | Value Complete |  |  | WD inc. Ad R. | Recovery | Advance P |  | Certified- Jan 23 |  | Variance in certifications
[5 empty] | Previous Valuation | This Month | To Date
| Subcontractors ( PS ) | [6 empty] | 0 |  | 0
1 | Watermaster Technical Services LLC | Swimming Pool & Water Feature works | 2128651 |  | 1845601.7 | 114972.23 | 1960573.93 | 1960573.93 |  |  | 0 | 1604579.94 |  | -355993.99
2 | Arcadia Metal Industries | External Metal works | 3330440 |  | 5884284.17 | 266806.38 | 6151090.55 | 6151090.55 | 499566 | 499566 | 0 | 4776873.4 |  | -1374217.15
3 | Dar Al Rokham LLC | Internal Stone works | 4111821 |  | 4611526.42 | 510464.43 | 5121990.85 | 5121990.85 |  | 0 | 0 | 3650150.6857 |  | -1471840.1643
4 | Al Shirawi Contracting Co LLC | Waterproofing works | 1391469 |  | 950831 | 151343 | 1102174 | 1102174 |  |  | 0 | 745737 |  | -356437
5 | Alshafar Interiors Co LLC | Joinery to Guest Rooms | 5919164.28 |  | 4278376.862 | 187253.815 | 4465630.677 | 4355932.757 | 778176.83 | 887874.75 | 109697.92 | 3714462.4673 |  | -751168.2097
6 | Isam Kabbani & Partners | Guniting & Waterproofing works | 1155933 |  | 440809.82 | 0 | 440809.82 | 440809.82 |  |  | 0 | 435538.7332 |  | -5271.0868
7 | Fiona Environs UAE | Soft Landscaping & Irrigation works | 3313028.6 |  | 3624519.627 | 406459.013 | 4030978.64 | 3956576.14 | 87804.3 | 162206.8 | 74402.5 | 2027557.55 |  | -2003421.09
8 | Al Reem Marble & Granite LLC | External Stoneworks | 4556481 |  | 4753446.756 | 1016706.054 | 5770152.81 | 5565124.05 | 138115.39 | 343144.15 | 205028.76 | 4188087.0406 |  | -1582065.7694
9 | Joyz Overseas Technical Services LLC | EIFS works | 1538156.94 |  | 1504561.826 | 230620.054 | 1735181.88 | 1735181.88 | 153815.69 | 153815.69 | 0 | 1305109.3472 |  | -430072.5328
10 | Bond Interiors Design LLC | Fitout of Hotel Lobby, All Day Dining & Spa Works | 4325954.46 |  | 3208319.85 | 303983.99 | 3512303.84 | 3512303.84 |  |  | 0 | 2792023.53 |  | -720280.31
11 | Al Rawda General Maint. & Decoration Co LLC | Partition & Ceiling works | 1954843 |  | 4155461.76 | 840247.18 | 4995708.94 | 4995708.94 |  |  |  | 3134189.6889 |  | -1861519.2511
12 | Joseph Advertisers LLC | Signage works | 999150 |  | 199830 | 21502.4 | 221332.4 | 26878 | 5375.6 | 199830 | 194454.4 | 199830 |  | -21502.4
13 | Joseph Decorative Glass | Internal Glazing works | 1262387 |  | 758829.352 | 0 | 758829.352 | 632939.94 | 126587.988 | 252477.4 | 125889.412 | 636429.304 |  | -122400.048
14 | Walltracts | Wall Coverings | 712173.7 |  | 689333.335 | 35580 | 724913.335 | 442536.395 | 0 | 282376.94 | 282376.94 | 689333.34 |  | -35579.995
15 | Goodrich Global Trading LLC | Carpets to Guest Rooms | 839675.05 |  | 705042.43 | 0 | 705042.43 | 705042.43 |  |  |  | 555878.32 |  | -149164.11
16 | Arabian Profile Company Ltd | GRC Works | 4155655 |  | 1904090 | 778154 | 2682244 | 2682244 |  |  |  | 1444023 |  | -1238221
17 | Glass Line Aluminium LLC | Aluminium & Glazing Façade works | 10273402 |  | 7554148.76 | 1498793.2 | 9052941.96 | 9052941.96 |  |  |  | 5456646.61 |  | -3596295.35
18 | EW COX Middle East LLC | BMU System | 628861 |  | 204605.8 | 0 | 204605.8 | 204605.8 |  |  |  | 204605.8 |  | 0
19 | Mohammed Tayyeb Khoory & Sons | Garbage & Linen Chutes | 287122 |  | 163261.6 | 0 | 163261.6 | 163261.6 |  |  |  | 140609.4 |  | -22652.2
20 | HTS Carpets Trading LLC | Carpets to lift lobbies & Corridors | 356512.42 |  | 261442.45 | 0 | 261442.45 | 261442.45 |  |  |  | 0 |  | -261442.45
21 | Khansaheb Interior DIvision ( KID ) | Restaurant Works |  |  | 7712286.224 | 1231898.008 | 8944184.232 | 5525883.792 | 1105176.76 | 4523477.2 | 3418300.44 | 6349499.176 |  | -2594685.056
| Subcontractors ( PS ) |  |  |  | 55410609.742 | 7594783.754 | 63005393.496 | 58595243.124 | 2894618.558 | 7304768.93 | 4410150.372 | 44051164.3328 | 0 | -18954229.1632
| Subcontractors (Domestic) | [8 empty] | 2781291.73
1 | Blue Sky LLC | Supply of MEP Maintenance team | 1071950 | P-006 | 871553.08 | 42300 | 913853.08 |  |  |  |  | 814292.99 |  | -99560.09
2 | Data Link Technical Services LLC | Wild Air Partitions | 241882.91 | C-006 | 514606 | 23585 | 538191 |  |  |  |  | 485569.8915 |  | -52621.1085
3 | Al Rawda General Maint. & Decoration Co LLC | Ceiling & Partition repairs, painting works | 26960 | P-001 | 45698.1 | 0 | 45698.1 |  |  |  |  | 45448 |  | -250.1
4 | Firestop Middle East | Firestopping works | 441760 | C-001, 002 R1 | 279037.66 | 74168.59 | 353206.25 |  |  |  |  | 224645.3306 |  | -128560.9194
5 | Creative House Scaffolding | Scaffolding | 1931942.08 | C-01 & 02 | 2943129.56 | 41131 | 2984260.56 |  |  |  |  | 2732404.4054 |  | -251856.1546
6 | Corecut Engineering LLC | Coring & Scanning | 383133 | C-015, 016 | 595080.45 | 11194 | 606274.45 |  |  |  |  | 477692.45 |  | -128582
7 | Inventure Façade Contracting LLC | Glass Balustrade works | 2703097 | C-011 | 2407981.72 | 151031.8 | 2559013.52 |  |  |  |  | 2132695.105 |  | -426318.415
8 | TWIC Insulation Materials Supply LLC | Epoxy Coating & Dust Sealer works | 778544.8 | C-015, 16 R1 | 553379.38 | 230726.02 | 784105.4 |  |  |  |  | 419173.1468 |  | -364932.2532
9 | Al Maraya Marble & Granite Factory LLC | Tile Installation | 514481.6 | C-017 | 257226.99 | 0 | 257226.99 |  |  |  |  | 250361.08 |  | -6865.91
10 | German Concrete Works & Building Contracting LLC | Screed & Insulation works | 796114.2 | C-018 R1 | 782684.21 | 48701.17 | 831385.38 |  |  |  |  | 620302.5396 |  | -211082.8404
11 | Greenwood General Trading LLC | Wooden Flooring | 353975.01 | C-005 | 315997.82 | 0 | 315997.82 |  |  |  |  | 285597.815 |  | -30400.005
12 | Al Hayat Fiberglass Ind LLC | GRP Lining works | 313333.4 | C-027 | 131172 | 0 | 131172 |  |  |  |  | 131172 |  | 0
13 | Vulcan Industries LLC | Steel Doors | 685405 | C-032 | 200380.69 | 0 | 200380.69 |  |  |  |  | 194166.7524 |  | -6213.9376
14 | Polaris International Industries LLC | Timber Doors | 1008983.76 | C-029 | 884336.11 | 12154.24 | 896490.35 |  |  |  |  | 722946.6695 |  | -173543.6805
15 | Center Core Professional Technical Services LLC | Slab cutting & strengthening works | 88900 | C-033 | 88900 | 0 | 88900 |  |  |  |  | 88900 |  | 0
16 | Weserve Technical Services LLC | Miscellaneous Steel works | 1147041.3 | C-052 | 923053.53 | 163787.15 | 1086840.68 |  |  |  |  | 631288.2 |  | -455552.48
17 | Venus Engineering LLC | RC column removal & strengthening works | 110965 | C-039 | 415350.4 | -85442.4 | 329908 |  |  |  |  | 396452.15 |  | 66544.15
18 | Global Composites Solutions LLC | GRP Cladding to Planter Wall | 225683 | C-053 | 45136.6 | 0 | 45136.6 |  |  |  |  | 45136.6 |  | 0
19 | Indiga Tech Trading LLC | Steel Doors | 154496.05 | C-047 | 169489.1 | 80795.72 | 250284.82 |  |  |  |  | 76532.8402 |  | -173751.9798
20 | Monrac LLC | Ceiling & Partition repairs, painting works | 918183.61 | PS-021 | 966943.05 | 66429.8 | 1033372.85 |  |  |  |  | 880323.368 |  | -153049.482
21 | Hygenic Solutions LLC | MMA Flooring | 474794 | C-016 | 349597.55 | 66518 | 416115.55 |  |  |  |  | 274195.05 |  | -141920.5
22 | Technical Access Services (L.L.C.) | Scaffolding Works | 1580356.14 | C-065 | 1698664.4 | 195492.46 | 1894156.86 |  |  |  |  | 1346549.53 |  | -547607.33
23 | Progress Fabrication | Metal Cladding Works and Misc Metal Works | 1264100.14 | C-078 | 1074118.98 | 63002.7 | 1137121.68 |  |  |  |  | 503360.2939 |  | -633761.3861
24 | Ferco Shutters LLC | Fire Curtains | 33685 | P-027 | 26948 | 2244.8 | 29192.8 |  |  |  |  | 24590.05 |  | -4602.75
25 | Jeel Alfan Technical Services | Decorative Paint | 128266 | P-015 | 32066.5 | 35437.5 | 67504 |  |  |  |  | 32066.5 |  | -35437.5
26 | Technoserve Technical works LLC | Painting works | 73379.6 | P-012 | 40099.648 | 24189.752 | 64289.4 |  |  |  |  | 27980.7406 |  | -36308.6594
27 | Dormakaba Middle East | Movable Partition Works- AHK Balance | 366250 | PS-025 | 314975 | 0 | 314975 | 205100 |  | 109875 |  | 314975 |  | 0
28 | Khansaheb Joinery DIvision ( KJD ) | Joinery Works- AHK Balance | 2105729.87 | PS-023 | 1609503.654 | 1420597.656 | 3030101.31 | 2608955.34 |  | 421145.97 |  | 917426.9245 |  | -2112674.3855
29 | Al Burhani General Trading LLC | Wooden Flooring & Carpet works- AHK | 133457 | PS-032 | 134374.65 | 38588.77 | 172963.42 | 119960.92 |  | 53002.5 |  | 123336.8617 |  | -49626.5583
30 | Rattan House Factory for Furniture and Decoration | Res Lobbies, Joinery works- AHK Balance | 279759 | PS-044 | 185656.68 | 61014.4 | 246671.08 | 246671.08 |  |  |  | 150072.32 |  | -96598.76
31 | International Foundation Group LLC | Waterproofing Concrete works | 450000 | C-061 R4 | 450000 | 0 | 450000 |  |  |  |  | 450000 |  | 0
32 | X-Calibur Emirates LLC | Stair nosing works | 221889 | C-064 | 173913 | 19045.28 | 192958.28 |  |  |  |  | 173913 |  | -19045.28
33 | Master Rubber Manufacturing | Wall & Corner Guard works | 169068.5 | C-062 | 50720.55 | 0 | 50720.55 |  |  |  |  | 50720.55 |  | 0
34 | DNK Engineering Equipment Trading LLC | Rolling Shutter works | 75530 | C-026 | 89980 | 0 | 89980 |  |  |  |  | 60817 |  | -29163
35 | Vijayraj Contracting Co LLC | Plastering works | 206250 | C-019 | 211400.1 | 0 | 211400.1 |  |  |  |  | 181750.15 |  | -29649.95
36 | Doormax Building Material Trading LLC | Glass Door works | 128000 | C-090 | 101600 | 0 | 101600 |  |  |  |  | 99200 |  | -2400
37 | KTC International Cont LLC | RTA works | 1043942 | C-091 | 292938.4 | 147486.24 | 440424.64 |  |  |  |  | 208788.4 |  | -231636.24
38 | Urban Science Building Contracting LLC | Joinery- Cupboards | 533125 | C-097 | 106625 | 0 | 106625 |  |  |  |  | 106625 |  | 0
39 | Berkeley | Final Cleaning | 993456 | C-067 | 29470 | 32855 | 62325 |  |  |  |  | 16070 |  | -46255
40 | Elite Skills Technical Services LLC | Steel Door Repainting Works | 75430 | C-087 | 151316 | 103140 | 254456 |  |  |  |  | 50274 |  | -204182
41 | Smart Roof Shade Systems LLC | Retractable Pergola System | 400000 | C-104 |  | 200000 | 200000
42 | Terra Firma Trading LLC | Plant Room Acoustics | 51170 | C-099 |  | 10234 | 10234
43 | Total Solution Engineering LLC | Stainless Steel Column skirting works | 133050 | C-102 R2 |  | 13670 | 13670
44 | TJ Technical Services Contracting LLC | Scratch Removal from Glass & Façade |  |  |  | 6080 | 6080
| Subcontractors (Domestic) |  |  |  | 20515104.562 | 3300158.648 | 23815263.21 |  |  |  |  | 16767812.7048 |  | -6817466.5052
| Subcontractors (Domestic & PS ) |  |  |  | 75925714.304 | 10894942.402 | 86820656.706 |  |  |  |  | 60818977.0376 |  | -25771695.6684
Subcontractors ( Labour Only )
1 | Al Qannati Electromechanical LLC | Labour Supply ( Block Works ) |  |  | 984120 | 0 | 984120 |  |  |  |  | 972720 |  | -11400
2 | Focus Power Security Services LLC | Supply of Site Security Service | 252000 | P-004 | 232016.12 | 24500 | 256516.12 |  |  |  |  | 207516.12 |  | -49000
3 | Service plus Technical Services LLC | Cleaning Service | 162400 | P-005 | 146987.96 | 16800 | 163787.96 |  |  |  |  | 130187.96 |  | -33600
4 | Pinewood StarTechnical Services LLC | Labour Supply ( ASI Recovery ) | 74400 |  | 23944 | 66848 | 90792
5 | World Stars Tech Cont LLC | Labour Supply ( Gypsum Carpenters & Painters ) |  |  | 0 | 97846 | 97846
| Subcontractors (Labour Only) |  |  |  | 1387068.08 | 205994 | 1593062.08 |  |  |  |  | 1310424.08 |  | -94000
[7 empty] | 88413718.786 |  |  |  |  | 62129401.1176

## Staff Cost
FOR THE PERIOD ENDING: 31ST MARCH 2023
SALARY COST & BACKUPS
Certificate No. | Description | Applied Amount (AED)
1 | 2022-03-01 | 16639.13 | 16639.13 | 0
2 | 2022-04-01 | 438092.619 | 438092.619 | 0
3 | 2022-05-01 | 772560.2273 | 772560.2273 | 0
4 | 2022-06-01 | 991945.4545 | 981763.6364 | -10181.8182
5 | July-22 | 1042220 | 1030430.5263 | -11789.4737
6 | August-22 | 1160798.7391 | 1137101.7391 | -23697
7 | September-22 | 1257377 | 1228858.1818 | -28518.8182
8 | October-22 | 1266237 | 1236938.0952 | -29298.9048
9 | November-22 | 1303682.27
10 | December-22 | 1299435.18
11 | January-23 | 1372949.59
12 | February-23 | 1403820.5
13 | March-23 | 1297660.4348
14
15
16
17
18
19
| TOTAL AMOUNT | 13623418.1448 | 6842384.1552 | -103486.0148

## Cost Adust't
FOR THE PERIOD ENDING: 31ST MARCH 2023
Cost Adjustments
Certificate No. | Description | Applied Amount (AED)
1 | Petty Cash Gifts to Arjun | -1208
2 | TXM Manpower cost adjustment from material transaction- August 22 | -9071.54
3 | TXM Manpower cost adjustment from material transaction- September 22 | -9384.76
4 | TXM Manpower cost adjustment from material transaction- October 22 | -9051.18
5 | TXM Manpower cost adjustment from material transaction- November 22 | -9951.73
6 | TXM Manpower cost adjustment from material transaction- November 22 | -1583.52
7 | TXM Manpower cost adjustment from material transaction- December 22 | -19197
8 | TXM Manpower cost adjustment from material transaction- January 23 | -18884.76
8 | IT costs adjustment from Overhead transaction for June 22 | -10220
9 | IT costs adjustment from Overhead transaction July 22 | -11760
10 | IT costs adjustment from Overhead transaction August 22 | -12180
11 | IT costs adjustment from Overhead transaction September 22 | -14000
12 | Visa Cost of labours | -2797.41
13 | Visa Cost of labours | -1259.8
14 | Included VAT adjustment | -521.189
15 | TXM Manpower cost adjustment from material transaction- February 23 | -19197
16 | TXM Manpower cost adjustment from material transaction- March 23 | -15156.26
17
18
19
20
| TOTAL AMOUNT | -165424.149

## Com or's
APPLICATION FOR PAYMENT NO. 14
COMMITTED ORDERS
Certificate No. | Description | Total Amount (AED ) | Applied Amount (AED)
1 | Kone (LPO HM-201A22002/0002) - CTU use Lifts (2 Nos)- March. 23 | 160000 | 16000
2 | IT infra-strucure set up to Offices | 10000 | 10000
3 | Kone (LPO HM-201A22002/0048)- CTU use Lifts no 10 & 21 (2 Nos)- March 23 | 128000 | 16000
4 | Al Ihsan Building Materials Trading (LPO HM-201A22002/0056)- Balcony Tiles | 154032 | 30240
5 | Schirmer Safety Consultants (LPO HM-201A22002/0065)- Façade Inspection Services | 11500 | 5750
6 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0069)- Scissor Lift | 72900 | 0
7 | High Glass Decor & Curtain Works LLC (LPO HM-201A22002/0080)- Turkish Acrylic carpet | 19435 | 9717.5
8 | Kone (LPO HM-201A22002/0086) - CTU Lifts (1 Nos)- for March 23 | 64000 | 8000
9 | Indigatech (LPO HM-201A22002/0095)- Fire rated Windows | 91817 | 0
10 | New Era Construction (LPO HM-201A22002/00113)- Cobiax Permanent Formwork | 67371.21 | 51376.14
11 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0117)- Scissor Lift | 72900 | 0
12 | Spider Access (LPO HM-201A22002/0130)- Column rectification & paint Mock up | 15300 | 0
13 | Carpet Land LLC (LPO HM-201A22002/0151) - Carpet | 13790 | 0
14 | Dutco LLC (LPO HM-201A22002/0155) - Modular Seal | 7600 | 0
15 | Master Builders Solutions LLC (LPO HM-201A22002/0159) - Emaco | 8400 | 0
16 | Jabel Ali Tra. LLC (LPO HM-201A22002/0161 ) -Dune Sand | 11110 | 0
17 | Al Najar LLC (LPO HM-201A22002/0162 ) - DC Furniture | 4900 | 0
18 | Osler Access LLC (LPO HM-201A22002/0166 ) - Cradle Works | 12760 | 0
19 | Al Majid LLC (LPO HM-201A22002/0167 ) - GRP Tank | 6500 | 6500
20 | Inter Metal LLC (LPO HM-201A22002/0168 ) - DC Furniture | 5350 | 0
21 | Smart Office LLC (LPO HM-201A22002/169 ) - DC Furnitire | 9742 | 0
22 | Master Builders Solutions LLC (LPO HM-201A22002/0170) - Mater top | 18000 | 0
23 | Consent (LPO HM-201A22002/0172) - Tile & Coping | 166700 | 0
24 | Momentum (LPO HM-201A22002/0179)- Ironmongery | 62299.3 | 4574.5 | Part cost booked.
25 | Indigatech (LPO HM-201A22002/0132)- Window Glass | 42920 | 0
26 | Laidlaw (LPO HM-201A22002/0176)- Ironmongery | 240812.4 | 0
27 | Kone (LPO HM-201A22002/0138) - CTU Lifts (2 Nos)- for March 23 | 96000 | 16000
28 | Fluid Codes Testing- (LPO HM-201A22002/0149) | 28207 | 0
29 | AST Digital Print Centre (LPO HM-201A22002/0037)- Printer charges | 15000 | 3438.16 | Registered Invoice
30 | Golden Ready Mix LLC (LPO HM-201A22002/0023 R1)- Concrete supply | 587200 | 16101.5 | Registered Invoice
31 | AHK Works- Alternatives SC's | 528371.34
32 | Ostermeier- Supply of manhole covers ( HM-201A22002/0277) | 420090 | 3150
33 | Hilti RE 500V4 ( HM-201A22002/0183) | 18900 | 0
34 | Mobility General- Ironmongery ( HM-201A22002/0185) | 150516 | 11129
35 | Osler- Cradle ( HM-201A22002/0188) | 137000 | 0
36 | Momentum- Ironmongery ( HM-201A22002/0192) | 12202 | 1116
37 | Master Emaco ( HM-201A22002/0195) | 9000 | 0
38 | Door Controls Glass Trading( HM-201A22002/0206) | 57018
39 | Osler- Cradle Maintenance ( HM-201A22002/0207) | 14928.57 | 11428.57
40 | Amalgam- Traffic Signs ( HM-201A22002/0210) | 3003 | 0
41 | Al Areej AC- Temp AC's ( HM-201A22002/0216) | 26500 | 0
42 | Mobility General- Ironmongery ( HM-201A22002/0222) | 13640 | 13640
43 | Schirmer- Façade Testing( HM-201A22002/0224) | 5000 | 0
44 | Neotech Engineering ( HM-201A22002/0228) | 8518 | 0
45 | Neotech Engineering ( HM-201A22002/0229) | 2770 | 0
46 | Hilti RE 500V4 ( HM-201A22002/0231) | 31500 | 12600
47 | Styro polystyrene ( HM-201A22002/0234) | 6875 | 3079.99
48 | Arabuild Tiles ( HM-201A22002/0237) | 480000 | 120057.6
49 | Smart Office Furnitures ( HM-201A22002/0240) | 1439 | 0
50 | Doormax Ironmongery (HM-201A22002/0252) | 223860.28 | 0
51 | Betec CAD Louvers (HM-201A22002/0267) | 90586.4 | 0
52 | Mobility General Trading (HM-201A22002/0273) | 17100 | 17100
53 | Doormax Ironmongery (HM-201A22002/0280) | 13148 | 0
54 | Styro Polystyrene (HM-201A22002/0281) | 46000 | 6125.13
55 | Carpets BSH Trading (HM-201A22002/0116) | 98548.1 | 19709.45
56 | Wow Factor- Barrisol (HM-201A22002/0118) | 40786 | 28550.2
57 | Consent (LPO HM-201A22002/0213) - Benches | 237500 | 96730
58 | Consent (LPO HM-201A22002/0242) - Kerbstone | 138000 | 95220
59 | Jebel Ali Transport(LPO HM-201A22002/0244) - Roadbase | 126000 | 49247.8
60 | Fireproof(LPO HM-201A22002/0289) - Palgan | 19000 | 0
61 | Laidlaw (LPO HM-201A22002/0286)- Ironmongery | 13984.5 | 0
62 | Master Builders ( HM-201A22002/0316) | 63900 | 0
63 | Laidlaw (LPO HM-201A22002/0325)- Ironmongery | 35406.19 | 2562
64 | Hilti RE 500V4 ( HM-201A22002/0330) | 19800 | 6600
65 | Laidlaw (LPO HM-201A22002/0331)- Ironmongery | 93046.22 | 11633.02
66 | Consent (LPO HM-201A22002/0345) - Precast | 24996.5 | 0
67 | Mobility General Trading (HM-201A22002/0353) | 25564 | 25564
68 | Laidlaw (LPO HM-201A22002/0355)- Ironmongery | 19038 | 8119
69 | Mobility General Trading (HM-201A22002/0359) | 25040 | 25040
70 | DIgilock (HM-201A22002/0362) | 5403.708 | 0
71 | Fischer Fixing (HM-201A22002/0319) | 2324.1 | 2324.1
72 | Illusionaire Auto Accessories LLC (HM-201A22002/0364) | 17600 | 17600
73 | Mobility General Trading (HM-201A22002/0368) | 20632.35
74 | Momentum- Ironmongery ( HM-201A22002/0369) | 228022 | 57005.5
75 | Stoncor Middle East (HM-201A22002/0385) | 18900 | 18900
76 | Master Builders Solutions LLC (LPO HM-201A22002/0389) | 86000 | 25800
77 | Master Builders Solutions LLC (LPO HM-201A22002/0394) | 29700 | 8910
| TOTAL AMOUNT | 5911703.168 | 892639.16

## K Summary
COINS - FINANCE
Contract Cost Breakdown 201A22002 Dorchester Hotel & Residences
Period March 2023
|  |  | Previous Cum | Current Month
Ledger | Current Period | Total to Date |  |  | Certified
Labour | 2034378.55 | 14945498 | 12911119.45 | -2034378.55 | 7628037.26 | -7317460.74
Payroll | 1828384.55 | 13351010.92 | 11522626.37 | -1828384.55 | 6696259.3
Manual Journal |  |  |  | 0
Purchase Orders |  |  |  | 0
Direct Invoices |  |  |  | 0
Petty Cash Charges |  | 1425 | 1425 | 0 | 1425
Subcontractor Costs | 205994 | 1593062.08 | 1387068.08 | -205994 | 930352.96
Material | 602976.35 | 11335926.48 | 10732950.13 | -602976.35 | 6311690.05 | -5024236.43
Purchase Orders | 178510.87 | 6635055.76 | 6456544.89 | -178510.87
Stock Issues | 414872.61 | 4511489.21 | 4096616.6 | -414872.61
Manual Journals |  | 4371 | 4371 | 0
Petty Cash Charges | 3626.51 | 18237.93 | 14611.42 | -3626.51
Plant Charges | 5966.36 | 166126.36 | 160160 | -5966.36
Direct Invoices |  | 646.22 | 646.22 | 0
Plant | 567678.27 | 4267752.69 | 3700074.42 | -567678.27 | 2300533.63 | -1967219.06
Plant Charges | 545943.97 | 4051488.71 | 3505544.74 | -545943.97
Manual Journals | 20115 | 205124.98 | 185009.98 | -20115
Petty Cash Charges | 701.3 | 701.3 |  | -701.3
Direct Invoices | 918 | 10437.7 | 9519.7 | -918
Subcontractor | 10905092.402 | 86839926.706 | 75934834.304 | -10905092.402 | 41412331.2124 | -45427595.4936
Subcontract Costs | 10894942.402 | 86820656.706 | 75925714.304 | -10894942.402 | 41405911.2124 | -45414745.4936
CVR Items | 0 | 0 | 0 | 0
Purchase Orders | 10150 | 19270 | 9120 | -10150 | 6420 | -12850
Direct Invoices | 0 | 0 | 0 | 0
Manual Journals |  |  |  | 0
Overhead | 208891.86 | 1607009.05 | 1398117.19 | -208891.86 | 973013.62 | -633995.43
CVR Items | 0 | 0 | 0 | 0
Purchase Orders | 34223.1 | 728390.05 | 694166.95 | -34223.1
Direct Invoices | 20572.52 | 154265.35 | 133692.83 | -20572.52
Petty Cash Charges | 3348.75 | 153898.38 | 150549.63 | -3348.75
Manual Journals | 136938.17 | 302613.03 | 165674.86 | -136938.17
Plant Charges | 1274 | 12334 | 11060 | -1274
Stock Issues | 12535.32 | 255508.24 | 242972.92 | -12535.32
Salaries | 1297660.4348 | 13625148.6648 | 12327488.23 | -1297660.4348 | 8251283.44 | -5373865.2248
Payroll Charges | 1297660.4348 | 13623418.1448 | 12325757.71 | -1297660.4348 | 8249552.44
Manual Journals |  | 1730.52 | 1730.52 | 0 | 1731
Direct Invoices |  |  |  | 0
Commited Orders | -739658 | 892639.16 | 1632297.513 | 739658.353
Commited Orders | -739658 | 892639.16 | 1632297.513 | 739658.353 | 2225356.19 | 1332717.03
0
0
Total | 14877019.8668 | 133513900.7508 | 118636881.237 | -14877019.5138 | 69102245.4024 | -64411655.3484
|  |  |  | 0.353 |  | -8051456.9185
-72463112.2669

## Labour
COINS - FINANCE
Labour Cost 201A22002 Dorchester Hotel & Residences
Period March 2023
Payroll
Cost Head | Description |  | Normal Hours | OT Hours | EOT Hours | Current | TTD
10100 | Unskilled labour costs - internal |  | 34601 | 3758 | 5892.5 | 408795.34 | 3289401.9
10200 | Skilled labour costs - internal |  | 28099 | 3199 | 5298.5 | 380216.73 | 2883968.14
10300 | Operators costs - internal |  | 6416 | 664.5 | 1516.5 | 111946.14 | 870275.11
10400 | Tradesmen costs - internal |  | 65060 | 7265 | 12272 | 855470.42 | 5974723.12
10500 | Charge hand labour costs - internal |  | 4786 | 527.5 | 1007 | 71955.92 | 332642.65
Total |  |  | 138962 | 15414 | 25986.5 | 1828384.55 | 13351010.92
Manual Journals
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Purchase Orders
Commodity | Description |  |  | Invoiced | Accrual / Rev | Current | TTD
Total | [5 empty] | 0
Direct Invoices
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Petty Cash Charges
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
10200 | Skilled labour costs - internal | [5 empty] | 1425
Total | [6 empty] | 1425
Subcontract Costs
Cost Head | Description |  |  | Int Ref | Ext Ref | Current | TTD
11400 | Tradesmen costs - external |  |  |  |  | 198025.48 | 2325597.07
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 42680 | 1108356
1108356
| BLUE008 | Blue Sky Middle East Contracting (LLC) |  |  |  | 90101.48 | 814292.99
814292.99
| FOCU003 | Focus Power Security Services (LLC) |  |  |  | 24500 | 232016.12
232016.12
| PINE003 | Pinewood Star Technical Services LLC |  |  |  | 23944 | 23944
23944
| SERV004 | Service Plus Technical Services LLC |  |  |  | 16800 | 146987.96
146987.96
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 198025.48 | 2325597.07
2325597.07
Total | [5 empty] | 198025.48 | 2325597.07

## Material
COINS - FINANCE
Material Cost 201A22002 Dorchester Hotel & Residences
Period March 2023
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
21110A01 | Reinforcement - Bars Mesh Bending Sched |  | 20754.34 | -20754.34 | 0 | 226559.34
| CICO001 | Cicon Building Materials | 20754.34 | -20754.34 | 0 | 226559.34
21110A02 | Reinforcing Sundries |  |  |  | 0 | 12660
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 7250
| MODE002 | Modern Building Materials Trad |  |  | 0 | 1010
| SALA001 | Salam Enterprises LLC |  |  | 0 | 4400
21111A01 | Aggregates |  |  | -999.9 | -999.9 | 7999.2
| JABE002 | Jabel Ali General Transport En |  | -999.9 | -999.9 | 7999.2
21112A01 | Timber/Plywood/Nails |  | 48050 | -41300 | 6750 | 112900
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment | 30000 | -23250 | 6750 | 55500
| ACME001 | Acme Building Materials Trading LLC | 18050 | -18050 | 0 | 51050
| SRRB001 | SRR Building Material Trading LLC |  |  | 0 | 6350
22317A01 | Vehicle Plant and Spares |  | 61333.33 |  | 61333.33 | 472266.97
| KONE001 | Kone Middle East LLC | 61333.33 |  | 61333.33 | 472266.97
22324A01 | Metalwork/Steelwork/Misc Metalwork Items |  | 432020 | -324355 | 107665 | 432020
| DUTC004 | Dutco Tennant LLC | 15080 |  | 15080 | 15080
| OSTE001 | Ostermeier FZE | 416940 | -324355 | 92585 | 416940
22711A01 | Consumable Tooling |  | 10243.52 | -26142.18 | -15898.66 | 90586.22
| ALAB003 | Al Abbasi Fasteners and Hardware |  | -1900 | -1900 | 2619
| DIAM005 | Diamond Tools Trading FZC |  |  | 0 | 1400
| DUTI001 | Dutest Industrial Est |  |  | 0 | 600
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 820
| HILT001 | Hilti Emirates LLC | 10243.52 | -24242.18 | -13998.66 | 78467.22
| NASE001 | Naser Al Sayer & Co (LLC) |  |  | 0 | 6680
23011A01 | Blockwork/Masonry/Mortar |  | 4889.6 | -4889.6 | 0 | 81190
| ARKA003 | Arkan Building Materials Co Arkan PJSC - Dubai Bramch | 3680 | -3680 | 0 | 45310
| MAST005 | Master Builders Solutions Construction Chemicals LLC |  |  | 0 | 8400
| UNIM005 | Uni Mix Block Industry (LLC) | 1209.6 | -1209.6 | 0 | 27480
23011A02 | Blockwork Sundry Material |  | 1843.2 | -1843.2 | 0 | 164205
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 1600
| CORE004 | Core Metallic Ind LLC |  |  | 0 | 23379
| HILT001 | Hilti Emirates LLC |  |  | 0 | 69300
| MODE002 | Modern Building Materials Trad |  |  | 0 | 720
| PALL001 | Palletco LLC |  |  | 0 | 26000
| UNIM005 | Uni Mix Block Industry (LLC) | 1843.2 | -1843.2 | 0 | 43206
23011A03 | Concrete |  |  | -98259 | -98259 | 253783.5
| GOLD026 | Golden Ready Mix LLC |  | -98259 | -98259 | 253783.5
23011A04 | Concrete Sundries |  | 161121 | -160416 | 705 | 438475.84
| ALAB003 | Al Abbasi Fasteners and Hardware | 5160 | -5160 | 0 | 13760
| KING003 | Kingspan Insulation (LLC) | 12000 | -12000 | 0 | 12000
| MAPE001 | Mapei Construction Chemicals LLC |  |  | 0 | 460
| MAST005 | Master Builders Solutions Construction Chemicals LLC | 143961 | -143256 | 705 | 368586
| STYR002 | Styro Insulation Materials Trading LLC | 0 |  | 0 | 43669.84
23011A05 | Plaster Screed Rush Coat |  | 4240 | -6080 | -1840 | 45920
| CONM001 | Conmix Ltd | 4240 | -6080 | -1840 | 45920
23011A06 | Plaster Sundries |  | 2397 | -2397 | 0 | 5103
| CONM001 | Conmix Ltd |  |  | 0 | 2706
| CORE004 | Core Metallic Ind LLC | 2397 | -2397 | 0 | 2397
23011A07 | Precast Concrete |  | 89297.5 |  | 89297.5 | 362790
| ALSE002 | Al Serkal and Assarain Concret |  |  | 0 | 254470
| CONS001 | Consent LLC | 89297.5 |  | 89297.5 | 108320
23012A01 | Road Base |  | 6533.8 | -2496.2 | 4037.6 | 70056
| JABE002 | Jabel Ali General Transport En | 6533.8 | -2496.2 | 4037.6 | 70056
23012A04 | Kerb Stones |  |  |  | 0 | 42780
| CONS001 | Consent LLC |  |  | 0 | 42780
23016A01 | Tiling Material |  | 125969.14 | -67911.54 | 58057.6 | 594035.48
| ALIH002 | Al Ihsan Building Materials Trading |  | -61584 | -61584 | 62208
| ARAB017 | Arabuild LLC | 120009.6 |  | 120009.6 | 336276
| CONS001 | Consent LLC | 3015.54 | -3015.54 | 0 | 188394.48
| MAPE001 | Mapei Construction Chemicals LLC | 2944 | -3312 | -368 | 4232
| MATE005 | Matex Construction Chemicals Manufacturing LLC |  |  | 0 | 2000
| SODA001 | Sodamco Sal Abu Dhabi |  |  | 0 | 925
23019A01 | Formwork/Falsework |  | 2598.36 | -2324.1 | 274.26 | 25970.06
| ALQU003 | Al Quebeisi SGB LLC |  |  | 0 | 111.51
| FISC002 | Fischer Fixing LLC | 2324.1 | -2324.1 | 0 | 5024.1
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  |  | 0 | 15995.07
| RMDK001 | RMD Kwikform Middle East LLC | 274.26 |  | 274.26 | 1339.38
| TRAD004 | Tradex LLC |  |  | 0 | 3500
23019A02 | Formwork Sundries |  | 40441.04 | -20825.52 | 19615.52 | 79331.04
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment |  | -4125 | -4125 | 15000
| ACME001 | Acme Building Materials Trading LLC |  |  | 0 | 23890
| ASCE001 | Ascend Access System Scaffoldi | 40441.04 | -16700.52 | 23740.52 | 40441.04
23121A01 | Painting & Decorating Materials/Sealants |  | 19000 | -24500 | -5500 | 26600
| DUTC004 | Dutco Tennant LLC |  |  | 0 | 7600
| PALG001 | Palgan Insulation Co LLC | 19000 | -19000 | 0 | 19000
| QCON001 | Q Con General Trading LLC |  | -5500 | -5500 | 0
23123A01 | Ironmongery |  | 463980.46 | -495159.29 | -31178.83 | 1359393.96
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 5320
| BETE001 | Betec Cad Industries FZC |  |  | 0 | 90586.4
| DIGI001 | Digilock Europe BV i.o. | 5411.07 |  | 5411.07 | 5411.07
| DOOR001 | Doormax Building Material Trading (LLC) | 169996 | -159030 | 10966 | 169996
| DOOR002 | Door Controls Glass Trading LL | 3860 |  | 3860 | 60878.18
| FINE001 | Fine Tools Trading LLC |  |  | 0 | 840
| LAID001 | Laidlaw Gulf LLC | 260447.39 | -195198.69 | 65248.7 | 798840.33
| MOBI002 | Mobility General Trading LLC |  | -139387 | -139387 | 0
| MOME001 | Momentum Fireguard LLC | 24266 | -1543.6 | 22722.4 | 221321.98
| QUAL010 | Quality Metal Works Manufacturing LLC |  |  | 0 | 6200
23912A02 | Electrical Items |  |  |  | 0 | 16635
| ALBA003 | Al Bajaa Lighting Equipment Trading LLC |  |  | 0 | 6835
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 9800
24713A01 | Cleaning Materials |  |  |  | 0 | 600
| ALBA009 | Al Bariq Equipment LLC |  |  | 0 | 600
29901A02 | Other Consumables |  | 2680 | -5532.9 | -2852.9 | 275046.59
| AJIH001 | AJI Heavy Equipment Rental LLC |  |  | 0 | 1560.5
| ALAB003 | Al Abbasi Fasteners and Hardware | 2680 | -3990 | -1310 | 232157.09
| ALBA009 | Al Bariq Equipment LLC |  |  | 0 | 1700
| ALSH004 | Al Sham Star Trading LLC |  |  | 0 | 945
| ASCE001 | Ascend Access System Scaffoldi |  |  | 0 | 17582
| CHEM001 | Chemex Hygiene Concepts LLC |  |  | 0 | 4642.5
| CRES002 | Crescent Scaffolding Industrie |  |  | 0 | 6600
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 5903.5
| HEPW001 | Corys Piping Systems LLC |  |  | 0 | 2016
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  | -1542.9 | -1542.9 | 0
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 1940
41540A01 | External Works through LPO's |  | 25754.35 | -38450 | -12695.65 | 1438148.56
| ALNA007 | Al Najah Furnishings LLC |  |  | 0 | 4900
| BSHT001 | BSH Trading (LLC) |  |  | 0 | 78838.74
| CARP001 | Carpet Land LLC |  |  | 0 | 13790
| CULL001 | Culligan International Emirate |  |  | 0 | 218423.22
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 5550
| DOST001 | Dosteen Doors and Shutters LLC |  | -36450 | -36450 | 0
| FLUI002 | Fluid Codes DMCC |  |  | 0 | 28207
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 1225
| HIGH009 | High Class Decor & Curtains Works LLC | 9717.5 |  | 9717.5 | 9717.5
| INDI003 | Indiga Tech Trading (LLC) |  |  | 0 | 134737
| INTE009 | Intermetal (LLC) Dubai Br |  | -2000 | -2000 | 5350
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 1248.54
| NATI010 | National Services for Carpet a | 880.59 |  | 880.59 | 3566.79
| OSLE001 | Osler Access Equipment LLC |  |  | 0 | 753260.09
| OSTE001 | Ostermeier FZE |  |  | 0 | 13357
| SANI001 | Sanipex LLC |  |  | 0 | 20401.74
| SCHI004 | Schirmer Safety Consultants |  |  | 0 | 10750
| SMAR015 | Smart Space Office Furniture Trading |  |  | 0 | 11112.39
| TXML001 | TXM Labour Supply LLC | 15156.26 |  | 15156.26 | 111477.75
| WOWF001 | Wow Factor Building Material T |  |  | 0 | 12235.8
Total |  |  | 1523146.64 | -1344635.77 | 178510.87 | 6635055.76
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
21112 | Wood Products |  |  |  |  | 38201.65
| 11121609-A03989 | Plywood - Film Faced - 18Mm - Fsc - Popalr Core |  |  |  | 38201.65
21510 | Fuels |  |  |  | 391269.45 | 4174113.1
| 15101501-A18400 | Fuel - Petrol |  |  |  | 1234.12
| 15101501-A18401 | Fuel - Diesel | ISS |  | 391269.45 | 4172878.98
22210 | Heavy construction machinery and equipment |  |  |  | 21600 | 126000
| 22101701-A04048 | Floor Protection Sheet Polypro Corrugated 4Mm |  |  | 21600 | 126000
22711 | Hand tools |  |  |  |  | 116222
| 22711H02-010001 | Floor Cleaning Machine |  |  |  | 4440
| 27112702-A20393 | Angle Grinder |  |  |  | 27722
| 27112702-A20412 | Concrete Mixer |  |  |  | 2350
| 27112702-A20424 | Drill |  |  |  | 9510
| 27112702-A20470 | Paddle Mixer |  |  |  | 2700
| 27112702-A20504 | Stepdown Transformer |  |  |  | 34875
| 27112702-A20516 | Vacuum Cleaner |  |  |  | 11125
| 27112702-A20520 | Wall Chasing Machine |  |  |  | 23500
24325 | Project IT Infrastructure |  |  |  | 198 | 16249.5
| 24325V01-010001 | Firewall SonicWall TZ400 - New |  |  |  | 3275
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 2598
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  | 198 | 396
| 24325V01-010012 | Aruba Central AP Foundation 1y Subscription - New |  |  |  | 2350.8
| 24325V01-010026 | Ray L2+ Cloud Managed Switch 8 Port - New |  |  |  | 1077
| 24325V01-010029 | Advanced Gateway Security Suite Bundle for TZ400 Series - 1 Yr |  |  |  | 5445.64
| 24325V01-010030 | Sonicwall Network Security Manager Essential with Management and 7-Day R |  |  |  | 1107.06
| 24325V01-020001 | Firewall SonicWall TZ400 - Used |  |  |  | 0
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 24325V01-020007 | Wireless Router D-Link 4G - Used |  |  |  | 0
24618 | Personal safety and protection |  |  |  | 1124.92 | 15925.97
| 46181507-A04452 | Safety Vest 90 Gsm Florescent Green - Large (Rigger) |  |  |  | 102.93
| 46181507-A04459 | Safety Vest 90 Gsm M Green - Staff Vest - 2XL |  |  | 38.97 | 144.53
| 46181507-A04460 | Safety Vest 90 Gsm M Green - 2Xl |  |  |  | 387.51
| 46181507-A04461 | Safety Vest 90 Gsm M Green - Staff Vest - 3XL |  |  |  | 9
| 46181507-A04462 | Safety Vest 90 Gsm M Green - Large |  |  | 318.79 | 1555.47
| 46181507-A04463 | Safety Vest 90 Gsm M Green - Staff Vest - M |  |  | 37.55 | 264.02
| 46181507-A04464 | Safety Vest 90 Gsm M Green - Staff Vest - L |  |  | 75 | 391.66
| 46181507-A04465 | Safety Vest 90 Gsm M Green - Medium | ISS |  | 318.8 | 1233.3
| 46181507-A04466 | Safety Vest 90 Gsm M Green - Staff Vest - XL |  |  | 75.02 | 439.29
| 46181507-A04467 | Safety Vest 90 Gsm M Green - Xl | ISS |  | 212.79 | 1219.6
| 46181507-A20681 | Traffic Marshall Safety Jacket Size- XL |  |  |  | 75
| 46181507-A20695 | Rigger Safety Jacket Size - XL |  |  |  | 37.5
| 46181507-A20696 | Rigger Safety Jacket Size - 2XL |  |  |  | 37.5
| 46181701-A04400 | Safety Helmet For Staff Mk7 | ISS |  | 35 | 3430
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  | 13 | 5954
| 46181701-A04404 | Safety Helmet High Ev Red - 6 Point Textile Tapes System. Slip Ratchet T |  |  |  | 558.66
| 46181701-A04405 | Safety Helmet High Ev White - 6 Point Textile Tapes System. Slip Ratchet |  |  |  | 26
| 46181701-A20074 | Safety Helmet High Ev Green - 6 Point Textile Tapes System. Slip Ratchet |  |  |  | 60
25213 | Window treatments |  |  |  |  | 13724.91
| 52131602-A18941 | Shade Net - 100% new HDPE with UV protection - 285 GSM - 3.66X100Mtr - |  |  |  | 13724.91
25310 | Clothing |  |  |  | 680.24 | 9206.66
| 53101602-A04981 | Shirt Cotton Full Sleeve White - 2Xl | ISS |  | 143.53 | 523.57
| 53101602-A04984 | Shirt Cotton Full Sleeve White - Large |  |  |  | 1200
| 53101602-A04985 | Shirt Cotton Full Sleeve White - Medium |  |  |  | 912
| 53101602-A04986 | Shirt Cotton Full Sleeve White - Small |  |  |  | 1322.96
| 53101602-A04987 | Shirt Cotton Full Sleeve White - Xl |  |  |  | 376.09
| 53101602-A04988 | Shirt Formal Half Sleeve White - 2Xl |  |  |  | 105.56
| 53101602-A04989 | Shirt Formal Half Sleeve White - 3Xl |  |  |  | 360
| 53101602-A04991 | Shirt Formal Half Sleeve White - Large |  |  |  | 298.42
| 53101602-A04992 | Shirt Formal Half Sleeve White - Medium | ISS |  | 198.74 | 305.44
| 53101602-A04993 | Shirt Formal Half Sleeve White - Small |  |  |  | 120.71
| 53101602-A04994 | Shirt Formal Half Sleeve White - Xl |  |  |  | 383.29
| 53103001-A05701 | T-Shirt 220 Gsm Half Sleeve White - 2Xl | ISS |  | 25.97 | 387.13
| 53103001-A05702 | T-Shirt 220 Gsm Half Sleeve White - 3Xl |  |  |  | 52
| 53103001-A05704 | T-Shirt 220 Gsm Half Sleeve White - Large | ISS |  | 104 | 312
| 53103001-A05705 | T-Shirt 220 Gsm Half Sleeve White - Medium | ISS |  | 208 | 1534
| 53103001-A05706 | T-Shirt 220 Gsm Half Sleeve White - Small |  |  |  | 312
| 53103001-A05707 | T-Shirt 220 Gsm Half Sleeve White - Xl |  |  |  | 701.49
60905 | Computers & Accessories |  |  |  |  | 1845.42
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 125
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 55
| 60905V01-010032 | Microsoft Display Adapter 1080p - New |  |  |  | 330
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 652.42
| 60905V01-010043 | Laptop Bag HP - New |  |  |  | 198
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 485
Total |  |  |  |  | 414872.61 | 4511489.21
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
29910 | Internal division - material costs |  |  |  |  | 4371
29951 | Materials cost accruals - CVR |  |  |  |  | 0
Total | [5 empty] | 4371
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
23116 | Hardware |  |  |  | 2949.03 | 17560.45
|  | 27743-CHRIS McCANN-201A22002 | PCP | MAR/12135/16 | 1103.52
|  | 27743-CHRIS McCANN-201A22002 | PCP | MAR/12191/20 | 1845.51
29316 | Clearance on materials |  |  |  | 677.48 | 677.48
|  | 27743-CHRIS McCANN-201A22002 | PCP | MAR/12191/20 | 677.48
Total |  |  |  |  | 3626.51 | 18237.93
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
22711 | Hand tools |  |  |  |  | 2850
| 27112217-A19363 | LT 53/2-Block Cutter |  |  |  | 2850
24619 | Fire protection |  |  |  | 1153.86 | 5128.86
| PTLT150013 | PTLT150013 Fast Vent Exhaust Fan - 9" |  |  | 384.62 | 384.62
| PTLT150040 | PTLT150040 Fast Vent Exhaust Fan - 10" |  |  | 384.62 | 384.62
| PTLT150045 | PTLT150045 Building Dryer Machine |  |  |  | 150
| PTLT150092 | PTLT150092 Ventilation Fan 18" |  |  |  | 315
| PTLT150096 | PTLT150096 Ventilation Fan-20" |  |  |  | 387
| PTLT150097 | PTLT150097 Ventilation Fan 18" |  |  |  | 315
| PTLT150098 | PTLT150098 Ventilation Fan 18" |  |  |  | 387
| PTLT150108 | PTLT150108 Ventilation Fan 18" |  |  |  | 387
| PTLT150113 | PTLT150113 Ventilation Fan 18" |  |  |  | 702
| PTLT150115 | PTLT150115 Ventilation Fan-20" |  |  |  | 387
| PTLT150132 | PTLT150132 Ventilation Fan 12" |  |  | 384.62 | 384.62
| PTLT150142 | PTLT150142 Ventilation Fan 18" |  |  |  | 315
| PTLT150143 | PTLT150143 Ventilation Fan 18" |  |  |  | 315
| PTLT150144 | PTLT150144 Ventilation Fan 18" |  |  |  | 315
29900 | EHD Materials |  |  |  | 4812.5 | 158147.5
| 99000101-A18468 | Pedestrian Barrier Steel Branded (2.5 x 1.2mtr) |  |  |  | 51000
| 99000101-A18474 | Rebar Access mat |  |  |  | 1800
| 99000101-A20672 | Expandable PVC Barrier - 2.5m x 0.960m |  |  |  | 1750
| 99000201-A18478 | Metal Hordings (2.2 x 2 mtr) K standard |  |  |  | 5775
| 99000601-A18491 | TYPE 1 - 3 Cooler Stand |  |  |  | 8612.5
| 99000701-A18494 | Cable Management Stand |  |  |  | 21937.5
| 99000701-A18496 | Cable Management Hooks-double hooks ( type 2) |  |  |  | 3375
| 99000701-A18497 | Cable Management Hooks three hooks ( type 3) |  |  |  | 1600
| 99000801-A18499 | Aluminium Podium Tower 1.00m x 1.30m |  |  |  | 1350
| 99000801-A19933 | Aluminium Podium Tower 1.00m x 1.85m |  |  | 4812.5 | 4812.5
| 99000901-A18510 | Man Basket |  |  |  | 7575
| 99001001-A18505 | Concrete Bucket - 1m3 |  |  |  | 960
| 99001001-A18668 | 1.5 CBM (3T) Tipping skip |  |  |  | 3300
| 99001001-A18669 | 1.5 CBM (3T) Self Dumping Skip |  |  |  | 5500
| 99001101-A18509 | Tripod |  |  |  | 2800
| 99001201-A18840 | EHD Security Cabin |  |  |  | 2600
| 99001401-A18842 | EHD Gas Monitor |  |  |  | 5400
| 99001601-A19775 | Large Industrial Evaporative Outdoor Air Cooler |  |  |  | 28000
Total |  |  |  |  | 5966.36 | 166126.36
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
21510 | Fuels |  |  |  |  | 646.22
| ALFU013 | Al Futtaim Transport and Renta |  |  |  | 646.22
Total | [5 empty] | 646.22
[5 empty] | 602976.35 | 11335926.48

## Plant
COINS - FINANCE
Plant Cost 201A22002 Dorchester Hotel & Residences
Period March 2023
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
30010 | I-Earth moving machinery |  |  |  | 12474.22 | 105328.02
| 2210150902 | Backhoe Loader (3CX) With Operator-Working |  |  |  | 4147
| 2210152614 | Mini Excavator 3 Ton with Breaker-Working |  |  |  | 4950
| P000220110 | P000220110 Case Sr150 Skid Steer Loader |  |  | 2523.46 | 3831.92
| P000220111 | P000220111 Case Sr150 Skid Steer Loader |  |  |  | 560.77
| P000220115 | P000220115 Case Sr150 Skid Steer Loader |  |  |  | 93.46
| P000220119 | P000220119 Case Sr150 Skid Steer Loader |  |  |  | 2710.39
| P000220120 | P000220120 Case Sr200 Skid Steer Loader |  |  | 438.46 | 33615.4
| P000220123 | P000220123 Case Sr150 Skid Steer Loader |  |  | 2243.07 | 19159.62
| P000230121 | P000230121 Avant Compact Loader -Dxb62067 |  |  | 3946.15 | 9938.46
| P000500116 | P000500116 Bomag Rev Compactor Brp35/60D |  |  | 1592.31 | 1592.31
| P000500132 | P000500132 Bomag Plate Compactor Bpr25/50 |  |  | 276.92 | 13223.07
| P000500133 | P000500133 Bomag Plate Compactor Bpr25/50 |  |  |  | 553.85
| P000610012 | P000610012 Sb Hopper Broom Attachment |  |  | 1453.85 | 7538.47
| P000610041 | P000610041 Hydraulic Breaker CB 37S for Skid Steer Loader |  |  |  | 3413.3
30020 | I-Aerial lifts |  |  |  | 38381.62 | 99418.95
| 2210180513 | Operator for Spider Boom Lift - 36 Mtr-Working |  |  | 38381.62 | 99418.95
30030 | I-Building construction machinery and accessories |  |  |  | 18319.5 | 218454.98
| KSFT000027 | KSFT000027 Diesel Storage Tank 1800 Ltrs(Original) |  |  |  | 138.48
| P000090078 | P000090078 Diesel Tanker- Dorchester Hotel & Residences (Completion Works) Scania Fuel Tanker |  |  |  | 1044
| P000490100 | P000490100 Livers Hf 4Kva Converter |  |  | 1093.5 | 11785.5
| W000020068 | W000020068 Diesel Tanker 9/68 Mercedes Fuel Tanker - DXB64273 |  |  | 16704 | 28710
| W000020069 | W000020069 Diesel Tanker - 9/69 - Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB63219 |  |  |  | 61596
| W000020070 | W000020070 9/70 Diesel Tanker Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB65028 |  |  | 522 | 92394
| W000020071 | W000020071 Mercdes Water Tanker - DXB64272 |  |  |  | 6945
| W000020072 | W000020072 9/72 Sweet Water Tanker 1-Trip Mercdes Water Tanker - DXB62723 |  |  |  | 10674.5
| W000020073 | W000020073 9/73 Sweet Water Tanker 1-Trip Mercedes Water Tanker-DXB62979 |  |  |  | 5167.5
30100 | I-Lifting equipment and accessories |  |  |  | 292757.76 | 1750018.53
| 2410160302 | Forklift - 5 Ton With Operator-Working |  |  |  | 20460
| 2410160315 | Forklift 3 Ton With Long Fork-Working |  |  | 19969.73 | 153326.91
| 2410160401 | Monorail - 20 Mtr with Special Clamp & 2nos.Winches-Working |  |  | 20561.62 | 43407.87
| 2410160402 | Mast Climber (Model: MSM SUPER)-Working |  |  | 54154.24 | 176847.62
| 2410161705 | Electric Scissor Lift - 5.9 Mtr-Working |  |  | 12320 | 23210
| 2410161727 | Electric Scissor Lift - 5.9 Mtr-Working |  |  | 4569.66 | 14657.92
| 2410162301 | Operator for Derrick Crane - 2 Ton-Working |  |  | 6092.43 | 6853.98
| 2410162302 | Derrick Crane 2 Ton-Working |  |  | 20307.93 | 22846.42
| 2410162303 | Derrick Crane |  |  | 28854.05 | 454259.81
| 2410162304 | Derrick Crane - 12 Ton |  |  | 33846.58 | 280290.62
| 2410162402 | Mobile Crane - 50 Ton-Working |  |  |  | 2640
| 2410162404 | Mobile Crane - 70 Ton With Fly Jib & Skidding |  |  |  | 21450
| 2410162405 | Mobile Crane - 100 Ton-Working |  |  |  | 12650
| 2410162406 | Mobile Crane - 100 Ton-Working |  |  |  | 3850
| 2410162414 | Mini Crane (JEKKO SPX532) - 3.2 Ton With Operator-Working |  |  | 2200 | 143099.67
| 2410162415 | Jekko Mini Picker-1000kg-Working |  |  | 31794.29 | 59632.81
| MOB001 | 3rd Party Certification & FamiliarizationTraining Charges For 8nos. Operators.Familiarization Charges AED-200X8 = 1,600/-Certifications Charges AED-350X8 = 2,800/-Total AED = 4,400/- |  |  | 44110 | 178970
| P000210110 | P000210110 Manitou Mt-X 1840 Telehandler |  |  |  | 3576.93
| P000210112 | P000210112 Manitou Mt-X 1840 Telehandler |  |  |  | 6080.77
| P000250049 | P000250049 Liebherr Mobile Crane-55 Ton(1055-32) |  |  |  | 1246.15
| P000260029 | P000260029 Skyjack 8841Rt Scissor Lift |  |  |  | 211.54
| P000260048 | P000260048 Scissor Lift Electric- 8m |  |  | 1269.3 | 1269.3
| P000260049 | P000260049 Scissor Lift Electric- 8m |  |  | 2200 | 21318.9
| P000260050 | P000260050 Scissor Lift - 8m |  |  | 2284.74 | 11677.56
| P000260081 | P000260081 Scissor Lift Electric- 8m |  |  | 2284.74 | 22170.44
| P000260082 | P000260082 Scissor Lift Electric- 8m |  |  | 2200 | 20884.93
| P000260087 | P000260087 Nano Lift 4.5 Meter |  |  | 1246.15 | 11676.91
| P000260088 | P000260088 Nano Lift 4.5 Meter |  |  | 1246.15 | 10984.6
| P000260092 | P000260092 Nano Lift 4.5 Meter |  |  | 1246.15 | 11446.14
| W000180010 | W000180010 Moffett Forklift M4 - DXB43955 |  |  |  | 654.23
| W000180014 | W000180014 TCM Forklift - DXB 41076-Working |  |  |  | 8366.5
30110 | I-Passenger motor vehicles |  |  |  | 57834.18 | 505241.65
| 2510150704 | Pick Up - 3 Ton Double CabinWithout Driver-Working |  |  | 6092.43 | 59591.53
| 2510150705 | Recovery Vehicle 3 Ton |  |  |  | 3850
| P000080658 | P000080658 Ashok Leyland Bus - Dxb 73025P |  |  |  | 1680
| P000080660 | P000080660 Ashok Leyland Bus - Dxb 92791Q With IVMS |  |  | 336 | 1176
| P000080661 | P000080661 Ashok Leyland Bus - Dxb 36303H |  |  |  | 1512
| P000080664 | P000080664 Ashok Leyland Bus - Dxb 52753J |  |  | 5110 | 38724
| P000080666 | P000080666 Ashok Leyland Bus - Dxb 53795I |  |  |  | 168
| P000080667 | P000080667 Ashok Leyland Bus - Dxb 51596J |  |  | 4872 | 13006
| P000080681 | P000080681 Ashok Leyland Bus - DXB 86848H |  |  | 5110 | 44506
| P000080682 | P000080682 Ashok Leyland Bus - DXB 87476H |  |  |  | 840
| P000080683 | P000080683 Ashok Leyland Bus - DXB 15614M |  |  |  | 1176
| P000080684 | P000080684 Ashok Leyland Bus - DXB 15497M |  |  |  | 1680
| P000080685 | P000080685 Ashok Leyland Bus - DXB 86783H With IVMS |  |  | 5110 | 31696
| P000080686 | P000080686 Ashok Leyland Bus - DXB 15496M |  |  |  | 1848
| P000080687 | P000080687 Ashok Leyland Bus - DXB 85148H |  |  | 4536 | 52738
| P000080690 | P000080690 Ashok Leyland Bus - DXB 15611M |  |  | 5110 | 56098
| P000080692 | P000080692 Ashok Leyland 59 Seat Bus-DXB 72359 W |  |  |  | 184.44
| P000080694 | P000080694 Ashok Leyland 59 Seat Bus-DXB 72356 W |  |  | 737.75 | 737.75
| P000080696 | P000080696 Ashok Leyland 59 Seat Bus-DXB 72353 W |  |  | 5610 | 42989.51
| P000080701 | P000080701 Ashok Leyland 71 Seat Bus |  |  | 5850 | 56881.23
| TA00033100 | TA00033100 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4680 | 13822.03
| TA00033109 | TA00033109 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4680 | 53787.95
| TA00043000 | TA00043000 TOYOTA HIACE 13 SEAT BUS |  |  |  | 26549.21
30120 | I-Product and material transport vehicles |  |  |  |  | 16019.78
| P000320042 | P000320042 Thwaites Dumper - P 22157 |  |  |  | 16019.78
30130 | I-Specialized and recreational vehicles |  |  |  | 30538.68 | 266695.76
| P000100022 | P000100022 Nissan Truck With Hiab Crane With IVMS |  |  | 770 | 2310
| P000100023 | P000100023 Mercedes Truck With Crane With IVMS |  |  | 620 | 3100
| P000100025 | P000100025 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000120019 | P000120019 12/19 Skip Truck 1-Trip ( 51762 ) Isuzu 12Ton Truck - Dxb 83254O |  |  | 12012 | 95462
| P000120020 | P000120020 1 Trip 12/20 Skip Truck ( 59844 ) Hino 13.5 Ton Skip Truck |  |  | 1092 | 18846
| W000030018 | W000030018 Nissan Truck with Hiab Crane With IVMS |  |  | 3087.68 | 12584.76
| W000030019 | W000030019 Nissan Truck with Hiab Crane With IVMS |  |  |  | 3465
| W000030020 | W000030020 Nissan Truck with Hiab Crane With IVMS |  |  | 2310 | 10010
| W000050017 | W000050017 12/17 Skip Truck 1-Trip ( 59984 ) Isuzu with Hiab Skip Loader - Dxb 70086 D |  |  | 10647 | 118438
30140 | I-Truck tractors |  |  |  | 1206 | 6834
| P000170028 | P000170028 Machinery Shifting Man Tractor Head - Dxb 25990-Low Bed |  |  | 804 | 1608
| P000170029 | P000170029 Machinery Shifting Man Tractor Head - Dxb 25988-Low Bed |  |  | 402 | 1206
| W000070021 | W000070021 MAN Tractor Unit - DXB 66748 |  |  |  | 2010
| W000070022 | W000070022 MAN Tractor Unit - DXB 66768 |  |  |  | 2010
30160 | I-Product and material trailers |  |  |  | 744 | 3016
| W000320031 | W000320031 Machinery Shifting Low Bed Semi Trailer 65Ton |  |  | 248 | 744
| W000320032 | W000320032 Machinery Shifting Low Bed Semi Trailer 65Ton |  |  | 496 | 992
| W000320035 | W000320035 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
| W000320037 | W000320037 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
30170 | I-Power generators |  |  |  | 63501.36 | 823576.63
| 2611160108 | Generator - 350 KVA-Working |  |  |  | 17769.86
| 2611160109 | Generator - 500 KVA-Working |  |  | 22154.51 | 254334.41
| 2611160110 | Electric Cable - Single Core 240mm X 40 Mtr-Working |  |  | 41346.85 | 551472.36
30200 | I-Masonry and concrete tools |  |  |  | 115.07 | 115.07
| PTLT590049 | PTLT590049 Power Trowel |  |  | 115.07 | 115.07
30230 | I-Compressors |  |  |  |  | 11894.43
| P000330091 | P000330091 Atlas Copco Air Compressor |  |  |  | 11682.9
| PTLT250022 | PTLT250022 Electric Compressor |  |  |  | 211.53
30510 | I-Plant repair & maintenance |  |  |  | 30071.58 | 244874.91
| K000010027 | K000010027 Eco Cabin Type 1 - Ablution |  |  |  | 6292.17
| KA00010006 | KA00010006 Eco Cabin Type 1 - Ablution |  |  |  | 7625.61
| KVS0010004 | KVS0010004 CAT & Ginny Cable Locator M/Kit |  |  | 486 | 4860
| PTLT260006 | PTLT260006 Floor Polishing Machine |  |  |  | 4440
| PTLT530006 | PTLT530006 Block Cutter |  |  |  | 2850
| S3131298 | S3131298-Fuel RFID Tag Installation |  |  |  | 161
| S3131331 | S3131331-Fuel RFID Tag Installation |  |  |  | 322
| S3131479 | S3131479-Fuel RFID Tag Installation / Metal Jerry Can |  |  |  | 472
| S3131494 | S3131494-Third party inspection & Certification |  |  |  | 100
| S3131597 | S3131597-PAT Test |  |  |  | 1850
| S3131609 | S3131609-Fabrication of Steel Ramp Dorchester Hotel |  |  |  | 7374
| S3131631 | S3131631-Electrical Repairs |  |  |  | 500
| S3131666 | S3131666-Dorchester Hotel -Third party inspection & Certification |  |  |  | 770
| S3131668 | S3131668-Electrical Repairs |  |  |  | 400
| S3131730 | S3131730-Electrical Repairs |  |  |  | 25
| S3131828 | S3131828-Electrical Repairs |  |  |  | 2225
| S3131868 | S3131868-DORCHESTER Hotel - Third party inspection & Certification |  |  |  | 860
| S3131933 | S3131933-Fuel RFID Tag Installation |  |  |  | 161
| S3131942 | S3131942-Electrical Repairs |  |  |  | 1431.19
| S3131975 | S3131975-PAT Test and Plugs |  |  |  | 1020
| S3132009 | S3132009-PAT Test |  |  |  | 350
| S3132054 | S3132054-Electrical Repairs |  |  |  | 1255.29
| S3132108 | S3132108-DORCHESTER Hotel- Water pump Replaced |  |  |  | 581
| S3132186 | S3132186-Electrical Repairs |  |  |  | 2619.96
| S3132199 | S3132199-DORCHESTER HOTEL Third party inspection & Certification |  |  |  | 200
| S3132235 | S3132235-Fuel RFID Tag Installation |  |  |  | 161
| S3132242 | S3132242-Electrical Repairs |  |  |  | 1694.02
| S3132281 | S3132281-Electrical Repairs |  |  |  | 175
| S3132299 | S3132299-DORCHESTER Hotel- Beam Cutting |  |  |  | 5510
| S3132316 | S3132316-Electrical Repairs |  |  |  | 666.32
| S3132327 | S3132327-Electrical Repairs |  |  |  | 1082.53
| S3132436 | S3132436-DORCHESTER Hotel Third party inspection & Certification |  |  |  | 2100
| S3132513 | S3132513-Refurbishment of KA1/6 & KA1/27 Ablution units |  |  |  | 418.8
| S3132579 | S3132579-Electrical Repairs |  |  |  | 1569.31
| S3132712 | S3132712-Electrical Repairs |  |  |  | 421
| S3132715 | S3132715-Electrical Repairs |  |  |  | 183.1
| S3132769 | S3132769-Electrical Repairs |  |  |  | 286.67
| S3132770 | S3132770-Electrical Repairs |  |  |  | 504.57
| S3132873 | S3132873-Electrical Repairs |  |  |  | 199.97
| S3132874 | S3132874-Electrical Repairs |  |  |  | 269.22
| S3132898 | S3132898-Electrical Repairs |  |  |  | 400
| S3132899 | S3132899-Electrical Repairs |  |  |  | 504.57
| S3132900 | S3132900-Electrical Repairs |  |  |  | 1158.48
| S3132901 | S3132901-Electrical Repairs |  |  |  | 1169.59
| S3132903 | S3132903-Electrical Repairs |  |  |  | 1189.12
| S3133002 | S3133002-Signboard Cutting Remove |  |  |  | 640.67
| S3133036 | S3133036-Electrical Repairs |  |  |  | 30.6
| S3133037 | S3133037-Electrical Repairs |  |  |  | 357
| S3133131 | S3133131-Electrical Repairs |  |  |  | 131.81
| S3133139 | S3133139-Electrical Repairs |  |  |  | 400
| S3133140 | S3133140-Electrical Repairs |  |  |  | 268.05
| S3133143 | S3133143-Electrical Repairs |  |  |  | 1346.55
| S3133145 | S3133145-Electrical Repairs |  |  |  | 836.5
| S3133262 | S3133262-Electrical Repairs |  |  |  | 400
| S3133263 | S3133263-Electrical Repairs |  |  |  | 434.9
| S3133265 | S3133265-Electrical Repairs |  |  |  | 354.19
| S3133266 | S3133266-Electrical Repairs |  |  |  | 1293.47
| S3133267 | S3133267-Electrical Repairs |  |  |  | 566.71
| S3133473 | S3133473-Electrical Repairs |  |  |  | 172
| S3133475 | S3133475-Electrical Repairs |  |  |  | 162
| S3133481 | S3133481-Electrical Repairs |  |  |  | 822.69
| S3133483 | S3133483-Electrical Repairs |  |  |  | 362.82
| S3133486 | S3133486-Electrical Repairs |  |  |  | 196
| S3133536 | S3133536-Electrical Repairs |  |  |  | 393.04
| S3133537 | S3133537-Electrical Repairs |  |  |  | 180.55
| S3133538 | S3133538-Electrical Repairs |  |  |  | 530.48
| S3133539 | S3133539-Electrical Repairs |  |  |  | 1486.78
| S3133581 | S3133581-Electrical Repairs |  |  |  | 155
| S3133592 | S3133592-Electrical Repairs |  |  |  | 100
| S3133645 | S3133645-Electrical Repairs |  |  |  | 62.53
| S3133646 | S3133646-Electrical Repairs |  |  |  | 400
| S3133685 | S3133685-Fuel RFID Tag Installation |  |  |  | 161
| S3133755 | S3133755-Electrical Repairs |  |  |  | 50
| S3133756 | S3133756-Electrical Repairs |  |  |  | 65
| S3133757 | S3133757-Electrical Repairs |  |  |  | 325
| S3133780 | S3133780-Light Tool Repair |  |  |  | 655.63
| S3133781 | S3133781-Light Tool Repair |  |  |  | 643.47
| S3133782 | S3133782-Light Tool Repair |  |  |  | 295.49
| S3133827 | S3133827-Electrical Repairs |  |  |  | 65
| S3133858 | S3133858-Light Tool Repair |  |  |  | 55
| S3133859 | S3133859-Light Tool Repair |  |  |  | 55
| S3133903 | S3133903-Light Tool Repair |  |  |  | 132.38
| S3133911 | S3133911-Light Tool Repair |  |  |  | 320
| S3133976 | S3133976-Light Tool Repair |  |  |  | 2095.73
| S3133979 | S3133979-Light Tool Repair |  |  |  | 172.85
| S3134028 | S3134028-Light Tool Repair |  |  |  | 269.31
| S3134029 | S3134029-Light Tool Repair |  |  |  | 201
| S3134080 | S3134080-Light Tool Repair |  |  |  | 492.04
| S3134115 | S3134115-Light Tool Repair |  |  |  | 210.02
| S3134116 | S3134116-Light Tool Repair |  |  |  | 467.97
| S3134118 | S3134118-Light Tool Repair |  |  |  | 504.5
| S3134136 | S3134136-Light Tool Repair |  |  |  | 177.38
| S3134137 | S3134137-Light Tool Repair |  |  |  | 177.38
| S3134138 | S3134138-Light Tool Repair |  |  |  | 177.38
| S3134139 | S3134139-Light Tool Repair |  |  |  | 177.38
| S3134167 | S3134167-Light Tool Repair |  |  |  | 177.38
| S3134168 | S3134168-Light Tool Repair |  |  |  | 77.38
| S3134177 | S3134177-Fuel RFID Tag Installation |  |  |  | 161
| S3134245 | S3134245-Fuel RFID Tag Installation |  |  |  | 161
| S3134274 | S3134274-Light Tool Repair |  |  |  | 214.3
| S3134275 | S3134275-Light Tool Repair / Installation |  |  |  | 525
| S3134278 | S3134278-Light Tool Repair |  |  |  | 174.2
| S3134279 | S3134279-Light Tool Repair |  |  |  | 1166.92
| S3134280 | S3134280-Light Tool Repair |  |  |  | 254.13
| S3134283 | S3134283-Light Tool Repair |  |  |  | 1202.63
| S3134284 | S3134284-Light Tool Repair |  |  |  | 957.33
| S3134320 | S3134320-Light Tool Repair |  |  |  | 386
| S3134352 | S3134352-Fuel RFID Tag Installation |  |  |  | 161
| S3134368 | S3134368-Supply of Safety Net |  |  |  | 800
| S3134413 | S3134413-Third party inspection & Certification |  |  |  | 50
| S3134435 | S3134435-Light Tool Repair |  |  |  | 310
| S3134492 | S3134492-Gas Cutting Work |  |  |  | 2185
| S3134583 | S3134583-Light Tool Repair |  |  |  | 191.79
| S3134585 | S3134585-Light Tool Repair |  |  |  | 465.95
| S3134586 | S3134586-Light Tool Repair |  |  | 100 | 100
| S3134588 | S3134588-Light Tool Repair |  |  |  | 264.28
| S3134606 | S3134606-Light Tool Repair |  |  |  | 1360.96
| S3134607 | S3134607-Light Tool Repair |  |  |  | 12.92
| S3134608 | S3134608-Light Tool Repair |  |  |  | 324.33
| S3134609 | S3134609-Light Tool Repair |  |  |  | 570.66
| S3134653 | S3134653-Light Tool Repair / Pat Test |  |  |  | 5625
| S3134654 | S3134654-Light Tool Repair / Pat Test |  |  |  | 1140
| S3134669 | S3134669-Light Tool Repair |  |  |  | 166.63
| S3134680 | S3134680-Light Tool Repair |  |  | 17.69 | 17.69
| S3134681 | S3134681-Light Tool Repair |  |  |  | 336.41
| S3134682 | S3134682-Light Tool Repair |  |  |  | 236.41
| S3134762 | S3134762-Light Tool Repair |  |  |  | 495
| S3134763 | S3134763-Light Tool Repair |  |  |  | 178.92
| S3134764 | S3134764-Light Tool Repair |  |  |  | 495
| S3134771 | S3134771-Light Tool Repair |  |  |  | 187
| S3134772 | S3134772-Light Tool Repair |  |  |  | 135.52
| S3134773 | S3134773-Light Tool Repair |  |  |  | 187
| S3134774 | S3134774-Light Tool Repair |  |  |  | 377.77
| S3134775 | S3134775-Light Tool Repair |  |  |  | 400
| S3134788 | S3134788-Light Tool Repair |  |  |  | 173
| S3134789 | S3134789-Light Tool Repair |  |  |  | 248.5
| S3134899 | S3134899-Fuel RFID Tag Installation |  |  |  | 161
| S3134958 | S3134958-Third party inspection & Certification |  |  |  | 50
| S3134992 | S3134992-Light Tool Repair |  |  | 187 | 187
| S3134994 | S3134994-Light Tool Repair |  |  | 1179.47 | 1179.47
| S3134996 | S3134996-Light Tool Repair |  |  | 129.24 | 129.24
| S3135058 | S3135058-Light Tool Repair |  |  | 676.07 | 676.07
| S3135092 | S3135092-Third party inspection & Certification |  |  |  | 800
| S3135127 | S3135127-Gas Cutting Works |  |  |  | 1045
| S3135130 | S3135130-Light Tool Repair |  |  | 400 | 400
| S3135133 | S3135133-Light Tool Repair |  |  | 393.07 | 393.07
| S3135136 | S3135136-Light Tool Repair |  |  | 924.94 | 924.94
| S3135137 | S3135137-Light Tool Repair |  |  | 289.71 | 289.71
| S3135138 | S3135138-Light Tool Repair |  |  | 400 | 400
| S3135139 | S3135139-Light Tool Repair |  |  | 2695 | 2695
| S3135141 | S3135141-Light Tool Repair |  |  | 372.92 | 372.92
| S3135142 | S3135142-Light Tool Repair |  |  | 1102.39 | 1102.39
| S3135152 | S3135152-Light Tool Repair |  |  | 492.04 | 492.04
| S3135282 | S3135282-Light Tool Repair |  |  |  | 489.18
| S3135283 | S3135283-Light Tool Repair |  |  |  | 1058.16
| S3135284 | S3135284-Light Tool Repair |  |  |  | 187
| S3135285 | S3135285-Light Tool Repair |  |  |  | 187
| S3135286 | S3135286-Light Tool Repair |  |  |  | 187
| S3135287 | S3135287-Light Tool Repair |  |  |  | 430.5
| S3135289 | S3135289-Light Tool Repair |  |  |  | 1070.09
| S3135306 | S3135306-Light Tool Repair |  |  | 462.16 | 462.16
| S3135377 | S3135377-Light Tool Repair |  |  |  | 332.82
| S3135378 | S3135378-Light Tool Repair |  |  |  | 1179.47
| S3135379 | S3135379-Light Tool Repair |  |  |  | 1114.97
| S3135467 | S3135467-I -Beam Cutting |  |  | 475 | 475
| S3135542 | S3135542-Light Tool Repair |  |  | 187 | 187
| S3135544 | S3135544-Light Tool Repair |  |  | 372.69 | 372.69
| S3135696 | S3135696-Light Tool Repair |  |  | 1604.19 | 1604.19
| S3135766 | S3135766-Supply of Torque Wrench & Torque Multiplier with Calibration Certification |  |  | 575 | 575
| S3135970 | S3135970-Concrete Bucket (KCB-010) Repair |  |  | 300 | 300
| S3136270 | S3136270-Repairing of Concrete Bucket |  |  | 250 | 250
| S3304180 | S3304180-Ac Service & Repair |  |  |  | 5580
| S3304218 | S3304218-Additional Paint Requirement for the New Project - Dorchester |  |  |  | 946
| S3304220 | S3304220-Ac Repairs & Service |  |  |  | 4490
| S3304230 | S3304230-Ac Repair & Service - Client Room |  |  |  | 2220
| S3304236 | S3304236-Third Party Certificate for Concrete Bucket (KCB010) |  |  |  | 50
| S3304239 | S3304239-Ac Repairs & Service |  |  |  | 4400
| S3304272 | S3304272-Ac Repair & Service (Non KCE Asset) |  |  |  | 1830
| S3304302 | S3304302-Ac Repairs & Service (Non KCE Asset) |  |  |  | 1980
| S3304317 | S3304317-Replacement of Asian Ablution ? Bottom and Top (KA1/27) |  |  |  | 834.25
| S3304379 | S3304379-Ac Repairs & Service for client office & KCE office |  |  |  | 1120
| S3304387 | S3304387-AC Repair & Service for client office & KCE office |  |  |  | 2490
| S3304411 | S3304411-AC Repair & Service for Site office. |  |  |  | 8280
| S3304437 | S3304437-Inspection & Servicing of Fire Extinguishers |  |  |  | 6000
| S3304438 | S3304438-AC Units relocation - Sr. Staff office |  |  |  | 16160
| S3304479 | S3304479-Shifting of AC units within offices |  |  |  | 5770
| S3304504 | S3304504-AC Units Shifting from one office |  |  |  | 6270
| S3304536 | S3304536-Forklift Charges - Material Offloading |  |  |  | 65
| S3304579 | S3304579-Forklift Charges |  |  |  | 65
| S3304589 | S3304589-Forklift Charge |  |  |  | 65
| S3304597 | S3304597-Forklift Charge |  |  |  | 65
| S3304599 | S3304599-AC Units Shifting and Repairs |  |  |  | 8260
| S3304601 | S3304601-Forklift Charge |  |  |  | 65
| S3304666 | S3304666-Cubicle Door Locks |  |  |  | 424.08
| S3304667 | S3304667-Urinal Push Tap Leak Rectification |  |  |  | 977.48
| S3304758 | S3304758-Forklift Charge |  |  |  | 65
| S3304849 | S3304849-AC Relocating |  |  |  | 16090
| S3304921 | S3304921-AC Relocation & Maintenance Works |  |  | 3010 | 3010
| S3304948 | S3304948-Rerouting Temporary Air-Conditioner Pipe from Bond Lobby |  |  | 11940 | 11940
| S3304989 | S3304989-Third Party Certiciate for Tipping Skip (KTS009) |  |  | 50 | 50
| T039101439 | T039101439 Grab Prefabricated Concrete |  |  | 1000 | 2460.27
Total |  |  |  |  | 545943.97 | 4051488.71
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
30295 | I-Waste skip |  |  |  | 16627.6 | 173724.18
|  | Waste Management Fine Reversal-March 2023 | JNL | 163016 | -500
|  | Waste Management-March 2023 | JNL | 162993 | 17127.6
30951 | Plant cost accruals - CVR |  |  |  |  | 0
34110 | E-Passenger motor vehicles |  |  |  | 2576 | 19876
|  | P000080667-KCE Salik Month Of March 2023 | JNL | 162635 | 296
|  | P000080664-KCE Salik Month Of March 2023 | JNL | 162635 | 344
|  | P000080687-KCE Salik Month Of March 2023 | JNL | 162635 | 232
|  | P000080685-KCE Salik Month Of March 2023 | JNL | 162635 | 400
|  | P000080690-KCE Salik Month Of March 2023 | JNL | 162635 | 272
|  | P000080681-KCE Salik Month Of March 2023 | JNL | 162635 | 256
|  | P000080694-KCE Salik Month Of March 2023 | JNL | 162635 | 56
|  | P000080696-KCE Salik Month Of March 2023 | JNL | 162635 | 336
|  | P000080701-KCE Salik Month Of March 2023 | JNL | 162635 | 384
34120 | E-Product and material transport vehicles |  |  |  | 911.4 | 11524.8
|  | TA00033100-Salik For February 2023 | JNL | 162633 | 315
|  | TA00033109-Salik For February 2023 | JNL | 162633 | 596.4
Total |  |  |  |  | 20115 | 205124.98
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
30090 | I-Industrial trucks |  |  |  | 701.3 | 701.3
|  | 27743-CHRIS McCANN-201A22002 | PCP | MAR/12135/16 | 701.3
Total |  |  |  |  | 701.3 | 701.3
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
30100 | I-Lifting equipment and accessories |  |  |  |  | 400
| KCEE004 | KCE (LLC) - Equipment Hire Div |  |  |  | 400
34110 | E-Passenger motor vehicles |  |  |  |  | 616.5
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 616.5
34120 | E-Product and material transport vehicles |  |  |  | 918 | 9421.2
| GOLD010 | Golden Palace Heavy and Light |  |  | 918 | 9421.2
|  | Hire Pickup Salik -February 2023 | PINN | 2303PL001213 | 918
Total |  |  |  |  | 918 | 10437.7
[5 empty] | 567678.27 | 4267752.69

## Subcontractor
COINS - FINANCE
Subcontract Cost 201A22002 Dorchester Hotel & Residences
Period March 2023
Subcontract Costs
Cost Head |  | Description |  |  | Int Ref |  | Ext Ref |  | Current |  | TTD
Total
Manual Journals
| Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total
CVR Items
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Purchase Orders
Commodity |  | Description |  |  | Invoiced |  | Accrual / Rev |  | Current |  | TTD
62001A01 |  | Pest control |  |  | 10150 |  |  |  | 10150 |  | 19270
|  | CITY003 |  | City Pest Control and Building | 10150 |  |  |  | 10150 |  | 19270
Total |  |  |  |  | 10150 |  |  |  | 10150 |  | 19270
Direct Invoices
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
41991 |  | Subcontact costs - external backcharge | [8 empty] | 0
|  | ACC |  | Accruals | [6 empty] | -3064627.1
Total | [10 empty] | 0

## Overhead
COINS - FINANCE
Overhead Cost 201A22002 Dorchester Hotel & Residences
Period March 2023
CVR Items
Cost Head | Description |  | Type | Int Ref | Current | TTD
29955 | Profit Abatement-CVR |  |  |  |  | 0
67001 | Remedial Works Provision - CVR |  |  |  |  | 0
Total | [5 empty] | 0
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
25512A01 | Project Sign Boards |  |  | -890 | -890 | 7413
| ABDU011 | Abdulrahman Al Abdooli Advertising LLC |  | -890 | -890 | 0
| AMAL002 | Amalgam Ind. LLC |  |  | 0 | 3003
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 3660
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 750
29901A01 | Small Tools/Equipment |  |  |  | 0 | 9035
| ALJA007 | Al Jas Technical Services LLC |  |  | 0 | 9035
60803A01 | Water and Electricity Charges |  |  |  | 0 | 24200
| DANL001 | Danlesco Gulf LLC |  |  | 0 | 24200
60905V02 | IT Equipment Printer Cameras etc |  |  |  | 0 | 76506.2
| ASTD001 | AST Digital Print Centre |  |  | 0 | 11561.84
| NEOT001 | Neo Tech Engineering LLC |  |  | 0 | 38801.5
| SCRE002 | Screencheck Technology Trading LLC |  |  | 0 | 11300
| SHAR005 | Sharaf DG LLC |  |  | 0 | 2542.86
| ZENE003 | Zener Marine Services LLC |  |  | 0 | 12300
61001A01 | Safety Clothing and Equipment / PPE |  | 1500 | -1500 | 0 | 65324
| AGSO001 | AGS Office Supplies and Trading LLC |  |  | 0 | 250
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 14750
| ALJA007 | Al Jas Technical Services LLC |  |  | 0 | 17490
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 800
| KENT002 | Kent Star General Trading LLC |  |  | 0 | 2000
| SALE001 | Saleem Jacobson Trading | 1500 | -1500 | 0 | 17234
| TULI001 | Tulip Trading LLC |  |  | 0 | 12800
61003A01 | Health and Safety expenses |  |  |  | 0 | 41245.93
| ALAM004 | Al Ameen Pharmacy LLC |  |  | 0 | 8825.93
| ASGC002 | ASGC Trading Building Machines & Equipment Rental LLC |  |  | 0 | 8000
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 600
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 23820
61111A01 | Refreshments (snacks tea coffee etc.) |  | 3806.4 | -3438.4 | 368 | 78318.15
| ALSH022 | Al Shalal Pure Drinking Water LLC | 1444 | -1076 | 368 | 15392
| CHOI001 | T Choithram and Sons LLC | 2362.4 | -2362.4 | 0 | 59111.15
| CLEA003 | Clear Ice LLC |  |  | 0 | 750
| FIND001 | Find General Trading LLC |  |  | 0 | 785
| JACK001 | Jackys Electronics LLC |  |  | 0 | 2280
61441A01 | Site Office Consumables |  | 4500 | -2250 | 2250 | 55742
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 30960
| ALBA009 | Al Bariq Equipment LLC |  |  | 0 | 3832
| MANG001 | Mangal Trading Co LLC | 4500 | -2250 | 2250 | 20950
61511A01 | Laboratory Testing & Calibaration Charges |  | 650 |  | 650 | 9137.75
| ALFA021 | Al Fajer Trading LLC |  |  | 0 | 330
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 6850
| GLOB007 | G Global Technologies LLC | 650 |  | 650 | 1150
| WIMP001 | Wimpey Laboratories LLC |  |  | 0 | 807.75
61521A01 | Rubbish Removal |  | 12398.92 |  | 12398.92 | 185127.88
| ALSH013 | Al Shola Transport Co (LLC) | 7200 |  | 7200 | 7200
| GREE044 | Green Earth Waste Collection & Transportation Services | 5198.92 |  | 5198.92 | 63927.88
| STUR001 | Sturdy Products UAE Limited |  |  | 0 | 114000
61521A02 | Sewage Disposal |  | 840 |  | 840 | 840
| RELI003 | Reliable Transport by Heavy & | 840 |  | 840 | 840
61531A01 | Office & Site Furniture - Including ACs |  | 18215.24 | -5750 | 12465.24 | 100705.24
| ALAR007 | Al Areej AC Units Fix Cont | 10250 |  | 10250 | 41875
| ALNA007 | Al Najah Furnishings LLC | 5750 | -5750 | 0 | 11250
| SABI001 | Sabi Air Conditioning Trading |  |  | 0 | 45365
| SHAR005 | Sharaf DG LLC | 2215.24 |  | 2215.24 | 2215.24
61531A02 | Site Est (Offices Ablutions Stores Etc) |  |  |  | 0 | 22930.5
| ALME003 | Al Mesmar Trading Co LLC |  |  | 0 | 5025
| NATI010 | National Services for Carpet a |  |  | 0 | 10368.5
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 6705
| TULI001 | Tulip Trading LLC |  |  | 0 | 832
61701A01 | Printing and Stationery |  | 6755 | -614.06 | 6140.94 | 51864.4
| AGSO001 | AGS Office Supplies and Trading LLC |  | -614.06 | -614.06 | 16515
| ALWA002 | Al Waha Stamps LLC |  |  | 0 | 670
| ASTD001 | AST Digital Print Centre | 5985 |  | 5985 | 32994.4
| SILV004 | Silver Screen Advertising Gift | 770 |  | 770 | 1685
Total |  |  | 48665.56 | -14442.46 | 34223.1 | 728390.05
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
29955 | Profit Abatement-CVR |  |  |  | 0 | 0
| ACC | Accruals
60624 | Penalties & Violations-Costed to Company |  |  |  |  | 1872
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 1872
60701 | Communication expense - landline and fax usage |  |  |  | 5913.64 | 61345.69
| EMIR032 | Emirates Integrated Telecommun |  |  | 4600 | 57584.76
|  | DU BILL FOR FEB-2023 | PINN | 2303PL000856 | 4600
| ETIS001 | Emirates Telecommunications Gr |  |  | 1313.64 | 3760.93
|  | Tel Cost-0566869731-ROAMING CHARGES-20374--DARREN COOK (FEB-2023) | PINN | 2303PL000785 | 600
|  | Tel Recovery-0566897894-34468-MASCO THANGARAJU (FEB-2023) | PINN | 2303PL001002 | 54.39
|  | Tel Cost-0501894373-201A22002-DORCHESTER HOTEL-DORCHESTER FACE STATION (FEB-2023) | PINN | 2303PL001022 | 129
|  | Tel Cost-0569973359-30882--PRABHAKARAN KUPPUSAMY (FEB-2023) | PINN | 2303PL001012 | 105
|  | Tel Cost-0565456086-201A22002-DORCHESTER HOTEL-HIRED--SANEESH MOHAN (FEB-2023) | PINN | 2303PL001012 | 136.5
|  | Tel Cost-0564162849-MULTISIM-10918--NANJAPPA (FEB-2023) | PINN | 2303PL001012 | 26.25
|  | Tel Cost-0509394368-201A22002-DORCHESTER HOTEL-DORCHESTER FACE STATION (FEB-2023) | PINN | 2303PL001012 | 105
|  | Tel Cost-0505548252-MULTISIM-17748--JAINULABUDEEN (FEB-2023) | PINN | 2303PL001007 | 26.25
|  | Tel Cost-0565498157-MULTISIM-24594--ANOOP R P (FEB-2023) | PINN | 2303PL001007 | 26.25
|  | Tel Cost-0506527308-MULTISIM-18589--ASIF NABI (FEB-2023) | PINN | 2303PL001007 | 26.25
|  | Tel Cost-0566897894-34468-MASCO THANGARAJU (FEB-2023) | PINN | 2303PL001007 | 52.5
|  | Tel Cost-0569910950-MULTISIM-21269--ALBIN BIJESH (FEB-2023) | PINN | 2303PL001007 | 26.25
60703 | Communication expense - internet and data |  |  |  |  | 3750
| EMIR032 | Emirates Integrated Telecommun |  |  |  | 3750
60803 | Utilities - water external supply |  |  |  |  | 13750
| DUBA003 | Dubai Aluminium PJSC |  |  |  | 13750
60901 | Printers & Photocopiers |  |  |  | 14658.88 | 69272.66
| NEWS001 | New Smart Office Automation LL |  |  | 14658.88 | 69272.66
|  | B/W AND COLOR COPY CHGS - FEB'2023 | PINN | 2303PL001804 | 1643.18
|  | B/W AND COLOR COPY CHGS - FEB'2023 | PINN | 2303PL001804 | 2735.25
|  | B/W AND COLOR COPY CHGS - FEB'2023 | PINN | 2303PL001804 | 622.19
|  | B/W AND COLOR COPY CHGS - JAN'2023 | PINN | 2303PL001533 | 3931.25
|  | B/W AND COLOR COPY CHGS - JAN'2023 | PINN | 2303PL001533 | 1933.37
|  | B/W AND COLOR COPY CHGS - JAN'2023 | PINN | 2303PL001533 | 2997.33
|  | B/W AND COLOR COPY CHGS - JAN'2023 | PINN | 2303PL001533 | 796.31
61003 | First-aid and medical expenses |  |  |  |  | 1445
| YORK004 | York Diagnostic Laboratories D |  |  |  | 1445
61201 | Recruitment expenses |  |  |  |  | 2830
| EISA001 | Eisa Travels Agency LLC |  |  |  | 2830
Total |  |  |  |  | 20572.52 | 154265.35
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  | 20 | 55762.52
|  | 04193-N MURALI-P CASH-FEES PAID | PCP | MAR/12142/14 | 20
60811 | Utilities - office and factory electricity and water |  |  |  |  | 46680
61003 | First-aid and medical expenses |  |  |  | 85 | 11155
|  | 18259-VENKATESAN ARUNACHALAM-201A22002 | PCP | MAR/12164/12 | 85
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 1593.75 | 33637.3
|  | 27743-CHRIS McCANN-201A22002 | PCP | MAR/12135/16 | 1580
|  | 27743-CHRIS McCANN-201A22002 | PCP | MAR/12191/20 | 13.75
61131 | COS Staff welfare expense |  |  |  | 1650 | 5963.56
|  | 10676-NISAR AHMED-201A22002 | PCP | MAR/12164/10 | 1650
62001 | Miscellaneous expenses |  |  |  |  | 700
Total |  |  |  |  | 3348.75 | 153898.38
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  |  | 82788.81
60624 | Penalties & Violations-Costed to Company |  |  |  | 49476.25 | 49476.25
|  | Dewa (Violation+Damage) | JNL |  | 49476.25
|  | Dewa (Violation+Damage) | JNL |  | -49476.25
|  | Dewa (Violation+Damage) | JNL |  | 49476.25
60701 | Communication expense - landline and fax usage |  |  |  |  | 25555.04
60703 | Communication expense - internet and data |  |  |  |  | 1079.17
60811 | Utilities - office and factory electricity and water |  |  |  | 86000 | 91064.85
|  | DEWA - Security Deposit | JNL |  | 86000
|  | DEWA - Security Deposit | JNL |  | -86000
|  | DEWA - Security Deposit | JNL |  | 86000
60902 | Specialist Software |  |  |  | 700 | 50400
|  | Microsoft Licences for Client - FEB &MAR 23 | JNL |  | 560
|  | MAIL BOX SERVICES - MAR 23 | JNL |  | 140
61001 | Health and safety - material items |  |  |  |  | 1490
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 761.92 | 2955.59
|  | Unclaimed VAT Jan'23 W/Off | JNL |  | 63.46
|  | Unclaimed VAT Jan'23 W/Off | JNL |  | 178.23
|  | Unclaimed VAT Jan'23 W/Off | JNL |  | 184.31
|  | Unclaimed VAT Feb'23 W/Off | JNL |  | 21.75
|  | Unclaimed VAT Feb'23 W/Off | JNL |  | 80.05
|  | Unclaimed VAT Feb'23 W/Off | JNL |  | 116
|  | Unclaimed VAT Feb'23 W/Off | JNL |  | 118.12
61201 | Recruitment expenses |  |  |  |  | -2830
61311 | Rent - accommodation |  |  |  |  | 533.32
62001 | Miscellaneous expenses |  |  |  |  | 100
Total |  |  |  |  | 136938.17 | 302613.03
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60905 | Computers & Accessories |  |  |  | 1274 | 12334
| ITA0002036 | ITA0002036 Samsung Galaxy Tab Active Pro |  |  |  | 0
| ITA0002123 | ITA0002123 Samsung Galaxy Tab Active Pro |  |  |  | 0
| ITA0002186 | ITA0002186 Samsung Galaxy Tab Active Pro |  |  | 189 | 357
| ITA0003005 | ITA0003005 Face Station 2 - Identification Device |  |  | 217 | 2520
| ITA0003060 | ITA0003060 Face Station 2 - Identification Device |  |  | 217 | 2415
| ITA0003063 | ITA0003063 Face Station 2 - Identification Device |  |  | 217 | 2212
| ITA0003075 | ITA0003075 Face Station 2 - Identification Device |  |  | 217 | 2415
| ITA0003084 | ITA0003084 Face Station 2 - Identification Device |  |  | 217 | 2415
Total |  |  |  |  | 1274 | 12334
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
60902 | Specialist Software |  |  |  |  | 2399
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 2399
60905 | Computers & Accessories |  |  |  | 2639.81 | 28920.98
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 1375
| 60905V01-010008 | Mouse Logitec Wireless Black - New | ISS |  | 50 | 1300
| 60905V01-010011 | Cable HDMI 2m - New |  |  |  | 72.5
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 110
| 60905V01-010019 | Cable Cat6 5m - New |  |  |  | 70.44
| 60905V01-010020 | Cable Roll 305m - New | ISS |  | 1666.97 | 3917.79
| 60905V01-010031 | RJ45 connector - New |  |  |  | 8.26
| 60905V01-010037 | Monitor 24" 1080p E Series - New |  |  |  | 5560.23
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 4566.94
| 60905V01-010041 | Samsung Tablet Case Cover - New |  |  |  | 380
| 60905V01-010043 | Laptop Bag HP - New | ISS |  | 922.84 | 3740.09
| 60905V01-010045 | EVOLIS-YMCKO Color Ribbon - New |  |  |  | 660
| 60905V01-010046 | EVOLIS Smart Cards - Mifare 1K - New |  |  |  | 1120.02
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 582
| 60905V01-010052 | Crucial SSD Hard disk - New |  |  |  | 786.28
| 60905V01-010053 | Bracket for Crucial SSD Hard disk - New |  |  |  | 17.5
| 60905V01-010054 | New Onsite installation of new SSD with OS |  |  |  | 95
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New |  |  |  | 595.93
60906 | Standard Software |  |  |  |  | 8847
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 7197
| 60906V01-010018 | Bluebeam Revu Extreme Annual Maintenance & Support Windows OS |  |  |  | 1650
60909 | Telecomunication Services |  |  |  | 1738.11 | 39656.62
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-010012 | Aruba Central AP Foundation 1y Subscription - New |  |  |  | 3651.91
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 60909V01-010008 | Sim Card Etisalat Standard - New |  |  |  | 0
| 60909V01-010012 | Mobile Handset Samsung A12 Black - New |  |  |  | 4910.1
| 60909V01-010014 | Mobile Handset Samsung A52 Black - New |  |  |  | 1255.24
| 60909V01-010015 | Mobile Handset Nokia 225 - New |  |  |  | 340
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New | ISS |  | 1738.11 | 24301.37
| 60909V01-010019 | Mobile Handset Samsung A53 ? New |  |  |  | 1235
61001 | Health and safety - material items |  |  |  | 6955.9 | 161626.32
| 46181503-A01361 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL |  |  |  | 5475.02
| 46181503-A01362 | Blue Pant/Shirt 180 Gsm Full Sleeve -3XL |  |  |  | 1834.56
| 46181503-A01363 | Blue Pant/Shirt 180 Gsm Full Sleeve -4XL |  |  |  | 387.45
| 46181503-A01364 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | ISS |  | 70.19 | 11605.19
| 46181503-A01365 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium |  |  |  | 26325.93
| 46181503-A01366 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small |  |  |  | 14188.75
| 46181503-A01367 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL |  |  |  | 8250.65
| 46181503-A01383 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - 2XL |  |  |  | 570
| 46181503-A01384 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - 3XL |  |  |  | 114
| 46181503-A01386 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Large |  |  |  | 1026
| 46181503-A01387 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Medium |  |  |  | 1596
| 46181503-A01388 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Small |  |  |  | 114
| 46181503-A01389 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - XL |  |  |  | 342
| 46181504-A20645 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | ISS |  | 1975 | 8237.26
| 46181504-A20646 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | ISS |  | 1974.66 | 25548.7
| 46181504-A20647 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 | ISS |  | 1971.06 | 10684.23
| 46181504-A20648 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 11 |  |  |  | 375
| 46181605-A04415 | Safety Shoe For Staff 59351 Size 38 |  |  |  | 240
| 46181605-A04416 | Safety Shoe For Staff 59351 Size 39 |  |  |  | 80
| 46181605-A04418 | Safety Shoe For Staff 59351 Size 41 |  |  |  | 640
| 46181605-A04419 | Safety Shoe For Staff 59351 Size 42 | ISS |  | 80 | 1200
| 46181605-A04420 | Safety Shoe For Staff 59351 Size 43 | ISS |  | 80 | 1200
| 46181605-A04421 | Safety Shoe For Staff 59351 Size 44 |  |  |  | 560
| 46181605-A04422 | Safety Shoe For Staff 59351 Size 45 | ISS |  | 80 | 320
| 46181605-A04423 | Safety Shoe For Staff 59351 Size 46 |  |  |  | 80
| 46181605-A18968 | Safety Shoe For Staff 59351 Size 40 |  |  |  | 560
| 46181605-A18970 | Safety Shoe for workers Saudi 59102 SIZE 38 |  |  |  | 455
| 46181605-A18971 | Safety Shoe for workers Saudi 59102 SIZE 39 |  |  |  | 2015
| 46181605-A18972 | Safety Shoe for workers Saudi 59102 SIZE 40 | ISS |  | 65 | 5525
| 46181605-A18973 | Safety Shoe for workers Saudi 59102 SIZE 41 |  |  |  | 4030
| 46181605-A18974 | Safety Shoe for workers Saudi 59102 SIZE 42 |  |  |  | 10530
| 46181605-A18975 | Safety Shoe for workers Saudi 59102 SIZE 43 |  |  |  | 4940
| 46181605-A18976 | Safety Shoe for workers Saudi 59102 SIZE 44 |  |  |  | 2275
| 46181605-A18977 | Safety Shoe for workers Saudi 59102 SIZE 45 |  |  |  | 715
| 46181605-A18978 | Safety Shoe for workers Saudi 59102 SIZE 46 |  |  |  | 195
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  |  | 26
| 46181804-A04397 | Safety Goggles - Clear - Globus - Riley - Bm08 | ISS |  | 659.99 | 3530.97
| 46181804-A04398 | Safety Goggles - Grey - Globus - Riley - Bm08 |  |  |  | 65.56
| 46181804-A19383 | Safety Goggles - Clear - Bm10 |  |  |  | 51.47
| 46181804-A19384 | Safety Goggles - Clear - Riley - Pn-RLY00071 |  |  |  | 760.21
| 46181804-A19385 | Safety Goggles - Grey - Riley - Pn-RLY00072 |  |  |  | 509.49
| 46182001-A20175 | Disposable Face Mask Blue 3 Ply (1x50) Local |  |  |  | 4107.88
| 71001Z01-010011 | Fire Extinguisher Inspection Tag |  |  |  | 340
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 1201.5 | 1201.5
| 71111Z01-010001 | Lunch Bag with branding | ISS |  | 1201.5 | 1201.5
61131 | COS Staff welfare expense |  |  |  |  | 12314.32
| 51211706-A00348 | Aqualyte Solution 80Grmx100Satchets/Ct |  |  |  | 230.35
| 51211706-A00349 | Aqualyte Solution 800Grmx10Satchets/Ct |  |  |  | 12083.97
61701 | Stationary |  |  |  |  | 542.5
| 14111509-A19706 | Business Cards |  |  |  | 120
| 71701Z01-01005 | Khansaheb Note Pad A5 |  |  |  | 275
| 71701Z01-01006 | Khansaheb Note Pad A4 |  |  |  | 147.5
Total |  |  |  |  | 12535.32 | 255508.24
[5 empty] | 208891.86 | 1607009.05