## PC FOR ISSUANCE
INTERIM PAYMENT CERTIFICATE
PROJECT: |  | Plot 18, BUSINESS BAY DUBAI, UAE |  | Certificate No: | TSSC-04
|  |  |  | Date of Certificate : | 2023-03-06
| Issued By : | Employer's Representative |  | Invoice No. | TSSC/IPA002
|  | Omniyat Concept Investments LLC |  | Cost Code: | D171
Dubai, UAE
| Company : | Sky Palaces Real Estate Development LLC |  | Contract Start Date : | 2021-12-19
|  | PO Box 12501 |  | Date of Application: | 2023-02-24
|  | Dubai, UAE |  | Period for Works Certified: | Refer the attachment
|  |  |  | Payment Due Date : Prior to | 2023-03-26
|  |  |  | Certificate Currency: | AED
| Contractor : | M/s TSSC Kitchen & Laundry Equipment Trading LLC
|  | P.O. Box 69 |  | VALUE COMPLETE | 24.74%
|  | Dubai, UAE |  | CERTIFIED FOR PAYMENT | 44.84%
|  |  |  | Currency | AED
|  |  |  | Contract Amount | 1023695
|  |  |  | Variation | 2359987
|  |  |  | Current Final Value | 3383682 | 1015104.6
| (A) Contract Advance Payment in this certificate |  |  |  | 764013.6
| Advance Payment |  | 1015104.6 |  |  | 1015104.6
LESS:
| Advance Payment Recovery 30% - Works Completed |  | 251091
| Advance Payment in this certificate |  | 764013.6
| (B) Value of Works Completed To Date (Valuation of Work In Place) |  |  |  | 836970
| (C=A+B) Certified Value - Cumulative |  |  |  | 1600983.6
| (D) LESS Retention (10%) |  |  |  | -83697
| (E) ADD: Release of Retention (50%) |  |  |  | 0
| (F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 1517286.6
| (G) LESS Previous Certified Value |  |  |  | -1170151.8
| (H=F-G) Net Certified for payment |  |  |  | 347134.8
| (I) 5% VAT |  |  |  | 17356.74
| (H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 364491.54
| RESIDUAL ADVANCE VALUE |  |  |  | 0
| LESS Recovery form this Certificate |  |  |  | 0
| RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
| Notes: | This payment certificate is for Delivery of Kitchen Equipment to the site
| Payment Terms: | The Payment shall be released within 30 days of the Payment Application
EMPLOYER'S REPRESENTATIVE CERTIFICATION
We certify that the above to be true and correct.
| For on behalf of OMNIYAT CONCEPT INVESTMENTS LLC |  |  |  | Date
APPROVAL BY EMPLOYER
Employer's approval of the net amount certified.
| For on behalf of SKY PALACES REAL ESTATE DEVELOPMENT LLC |  |  |  | Date

## Plot 18
INTERIM PAYMENT CERTIFICATE
PROJECT: |  | Plot 18, BUSINESS BAY DUBAI, UAE |  | Certificate No: | TSSC-04
|  |  |  | Date of Certificate : | 2023-03-06
| Issued By : | Employer's Representative |  | Invoice No. | TSSC/IPA002
|  | Omniyat Concept Investments LLC |  | Cost Code: | D171
Dubai, UAE
| Company : | Sky Palaces Real Estate Development LLC |  | Contract Start Date : | 2021-12-19
|  | PO Box 12501 |  | Date of Application: | 2023-02-24
|  | Dubai, UAE |  | Period for Works Certified: | Refer the attachment
|  |  |  | Payment Due Date : Prior to | 2023-03-26
|  |  |  | Certificate Currency: | AED
| Consultant : | M/s TSSC Kitchen & Laundry Equipment Trading LLC
|  | P.O. Box 69 |  | VALUE COMPLETE | 24.74%
|  | Dubai, UAE |  | CERTIFIED FOR PAYMENT | 44.84%
|  |  |  | Currency | AED
|  |  |  | Contract Amount | 1023695
|  |  |  | Variation | 2359987
|  |  |  | Current Final Value | 3383682
| (A) Contract Advance Payment in this certificate |  |  |  | 764013.6
| Advance Payment |  | 1015104.6
LESS:
| Advance Payment Recovery 5% - Works Completed |  | 251091
| Advance Payment in this certificate |  | 764013.6
| (B) Value of Works Completed To Date (Valuation of Work In Place) |  |  |  | 836970
| (C=A+B) Certified Value - Cumulative |  |  |  | 1600983.6
| (D) LESS Retention (10%) |  |  |  | -83697
| (E) ADD: Release of Retention (50%) |  |  |  | 0
| (F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 1517286.6
| (G) LESS Previous Certified Value |  |  |  | -1170151.8
| (H=F-G) Net Certified for payment |  |  |  | 347134.8
| (I) 5% VAT |  |  |  | 17356.74
| (H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 364491.54
| RESIDUAL ADVANCE VALUE |  |  |  | 0
| LESS Recovery form this Certificate |  |  |  | 0
| RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
| Notes: | This payment certificate is for Delivery of Kitchen Equipment to the site
| Payment Terms: | The Payment shall be released within 30 days of the Payment Application
INTERNAL CERTIFICATION ONLY
We certify that the above to be true and correct for and on behalf of OMNIYAT CONCEPT INVESTMENTS LLC
| Christopher Thomas |  |  | Peter Stephenson
| Commercial Director |  |  | Managing Director - Development
SKY PALACES REAL ESTATE DEVELOPMENT LLC approval to proceed the net amount certified for approval
Ishan Garga
Managing Director - Corporate Finance & Investments

## BOQ
[7 empty] | Project : Dorchester Collection, Dubai | [14 empty] | Sub Contractor : TSSC Kitchen & Laundry Equipment Trading LLC
[7 empty] | Package : Supply & Installation of Kitchen Equipment | [14 empty] | Document Ref. : DCD/KE/13A22/IC/INV003
[7 empty] | Client : Sky Palaces Real Estate Development LLC | [14 empty] | Date : 13th January 2023
Bill Of Quantities for Kitchen Equipment with claim for work done until 13/Jan/2023
Claim for Materials Delivered & Work Done
‡ - Basis of Cumulative Rate: Advance Payment - 30%, Material On Site - 90 % Installed - 95% & Commissioned Equipment - 100%.
Calc Change | Area | Price Updated | Details Updated | Equipment Category | Area | Composite Item No. | Item No | Qty | Unit | Area / Item Description | Manufacturer | Model | Origin | Unit Rate (UAE Dirhams) | Amount (UAE Dirhams) | MIR # Ref | Invoice Qty | % of Work Completed | Value of Work Completed | Prev. Claimed Amount For Work Complete | Net Current Claim (AED) | Comments
Description Change | [9 empty] | BASEMENT 1
Description Change | [9 empty] | FL.00 FLOWER ROOM
Item No. Change | [6 empty] | FL.01 | 1 | No. | Modular Coldroom complete with | TSSC. | Custom | U. A. E. | 967364 | 967364 | MIR # 008 | 1 | 15% | 142466.33 | 47489 | 94977 | • AED 967,364 X 60% for Panels = 580,418.40 • 90% Upon delivery of above amount = 522,376.56 • For 2 cold rooms out of 22 = (522,376.56/22)*6 = 142,466.33 | 142466.33 | 142466.33
Item No. Change | [6 empty] | FL.01A | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | FL.01B | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | FL.01C | 1 | No. | Remote Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Description Change | [9 empty] | LD.00 LOADING DOCK
Item No. Change | [6 empty] | LD.07 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 001 | 3 | 90% | 1315 | 1315 | 0
Item No. Change | [6 empty] | LD.08 | 1 | No. | Floor drain with stainless steel gratings. 10300 x 500 | PKI / Techsteel | Custom | U. A. E. | 7123 | 7123 | MIR # 001 | 1 | 90% | 6411 | 6411 | 0 | Item deleted
Description Change | [9 empty] | RD.00 RECEIVING & DECANT
Item No. Change | [6 empty] | RD.08 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439 | 439 | 0
Description Change | [9 empty] | RW.00 RAW WASH
Item No. Change | [6 empty] | RW.03 | 1 | No. | Floor drain with stainless steel gratings. 1200 x 300 | PKI / Techsteel | Custom | U. A. E. | 861 | 861 | MIR # 001 | 1 | 90% | 775 | 775 | 0
Description Change | [9 empty] | CS.00 CENTRL FOOD AND BEVERAGE STORES
Item No. Change | [6 empty] | CS.01 | 1 | No. | 5 Compartment Modular Coldroom/Freezer Room Suite Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01A | 5 | No. | Control Panels | TSSC. | Custom | U. A. E. | 0 | 0 |  | 5 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01B | 1 | No. | Evaporator (Vegetable & Fruit Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01C | 1 | No. | Air Cooled Compressor (Vegetable & Fruit Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01D | 1 | No. | Evaporator (Meat Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01E | 1 | No. | Air Cooled Compressor (Meat Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01F | 1 | No. | Evaporator (Poultry Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01G | 1 | No. | Air Cooled Compressor (Poultry Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01H | 1 | No. | Evaporator (Seafood Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01I | 1 | No. | Air Cooled Compressor (Seafood Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01J | 1 | No. | Evaporator (Fish Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.01K | 1 | No. | Air Cooled Compressor (Fish Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.06 | 8 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 3896 | MIR # 002 | 8 | 90% | 3506 | 3506 | 0
Item No. Change | [6 empty] | CS.08 | 1 | No. | 3 Compartment Modular Coldroom Suite Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08a | 3 | No. | Control Panels | TSSC. | Custom | U. A. E. | 0 | 0 |  | 3 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08b | 1 | No. | Evaporator (General Purpose Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08c | 1 | No. | Air Cooled Compressor (General Purpose Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08d | 1 | No. | Evaporator (Beverage Coldroom 1) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08e | 1 | No. | Air Cooled Compressor(Beverage Coldroom 1) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08f | 2 | No. | Evaporator (Beverage Coldroom 2) | LU-VE | - | GERMANY | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.08g | 2 | No. | Air Cooled Compressor(Beverage Coldroom 2) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.09 | 1 | No. | 2 Compartment Modular Coldroom Suite Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.09a | 2 | No. | Control Panels | TSSC. | Custom | U. A. E. | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.09b | 1 | No. | Evaporator (Freezer Room 1) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.09c | 1 | No. | Air Cooled Compressor (Freezer Room 1) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.09d | 1 | No. | Evaporator (Freezer Room 2) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.09e | 1 | No. | Air Cooled Compressor(Freezer Room 2) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.14 | 1 | No. | Modular Coldroom Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.14a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.14b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | CS.14c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Description Change | [9 empty] | P.00 PREPARATION AREAS - Vegetable and Fruit Preparation Area
Item No. Change | [6 empty] | P.09 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 002 | 2 | 90% | 878 | 878 | 0
Description Change | [9 empty] | P.00 PREPARATION AREAS - Meat Prep & Poultry Preparation Areas
Item No. Change | [6 empty] | P.19 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 002 | 2 | 90% | 878 | 878 | 0
Description Change | [9 empty] | P.00 PREPARATION AREAS - Fish and Seafood Preparation Area
Item No. Change | [6 empty] | P.32 | 1 | No. | Floor drain with stainless steel gratings. 1000 x 300 | PKI / Techsteel | Custom | U. A. E. | 861 | 861 | MIR # 002 | 1 | 90% | 775 | 775 | 0
Item No. Change | [6 empty] | P.47 | 1 | No. | Floor drain with stainless steel gratings. 500+1900+500 x 300 | PKI / Techsteel | Custom | U. A. E. | 1726 | 1726 | MIR # 002 | 1 | 90% | 1553 | 1553 | 0
Item No. Change | [6 empty] | P.48 | 1 | No. | 2 Compartment Modular Coldroom Suite | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | P.48a | 1 | No. | Dual Compartment Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | P.48b | 1 | No. | Evaporator (Coldroom 1) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | P.48c | 1 | No. | Evaporator (Coldroom 2) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | P.48d | 1 | No. | Air Cooled Compressor (Coldroom 1) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | P.48e | 1 | No. | Air Cooled Compressor (Coldroom 2) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Description Change | [9 empty] | BP.00 BAKERY & PASTRY
Item No. Change | [6 empty] | BP.11 | 1 | No. | 2 Compartment Modular Coldroom Suite | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BP.11a | 1 | No. | Dual Compartment Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BP.11b | 1 | No. | Evaporator (Coldroom) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BP.11c | 1 | No. | Evaporator (Freezer Room) | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BP.11d | 1 | No. | Air Cooled Compressor (Coldroom) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BP.11e | 1 | No. | Air Cooled Compressor (Freezer Room) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BP.20 | 1 | No. | Floor drain with stainless steel gratings. 2030 x 300 | PKI / Techsteel | Custom | U. A. E. | 1199 | 1199 | MIR # 002 | 1 | 90% | 1079 | 1079 | 0
Item No. Change | [6 empty] | BP.24 | 6 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 2922 | MIR # 002 | 6 | 90% | 2630 | 2630 | 0
Item No. Change | [6 empty] | BP.35 | 1 | No. | Hood type: Baffle - Wall mount - Wall type - Double skin Hood dimension: 3100 (L) x 2450 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 4644 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 26941 | 26941 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BP.35.1 | 1 | No. | Incl. 3 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 15197 | 15197 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BP.35a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 0 | INCLUDED IN BP.37a |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BP.36 | 1 | No. | service distribution unit with grid shelf. 2850 x 200 | PKI / Techsteel | Custom - SDU | U. A. E. | 6041 | 6041 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BP.37 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 2300 (L) x 1500 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 1530 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 1 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 50439 | 50439 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BP.37.1 | 1 | No. | Incl. 2 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 10137 | 10137 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BP.37a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 11603 | 11603 |  | 1 | 0% | 0 | 0 | 0
Description Change | [9 empty] | GM.00 GARDE MANGER
Item No. Change | [6 empty] | GM.11 | 1 | No. | Modular Coldroom comprising | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 008 | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | GM.11a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | GM.11b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | GM.11c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Description Change | [9 empty] | HK.00 HOT KITCHEN
Item No. Change | [6 empty] | HK.09 | 1 | No. | Floor drain with stainless steel gratings. 3150+350+350 x 400/350 | PKI / Techsteel | Custom | U. A. E. | 3155 | 3155 | MIR # 002 | 1 | 90% | 2840 | 2840 | 0
Item No. Change | [6 empty] | HK.10 | 1 | No. | Floor drain with stainless steel gratings. 850+300 x 400/350 | PKI / Techsteel | Custom | U. A. E. | 1316 | 1316 | MIR # 002 | 1 | 90% | 1184 | 1184 | 0
Item No. Change | [6 empty] | HK.11 | 1 | No. | service distribution unit with grid shelf. 5460 x 250 | PKI / Techsteel | Custom - SDU | U. A. E. | 10696 | 10696 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | HK.12 | 1 | No. | Hood type: UV - Island mount - Island type - Double skin Hood dimension: 6055 (L) x 2975 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 16,085 m3/h Make-up air by Ginox: 13,672 m3/h - Hood front Lights: Flurorescent panel, 8 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 183742 | 183742 | MIR # 007 | 1 | 90% | 165368 | 0 | 165368
Item No. Change | [6 empty] | HK.12.1 | 1 | No. | Incl. 6 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 30381 | 30381 | MIR # 007 | 1 | 90% | 27343 | 0 | 27343
Item No. Change | [6 empty] | HK.12a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 19957 | 19957 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | HK.15 | 1 | No. | Modular Coldroom comprising | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 008 | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.15a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.15b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.15c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.20 | 1 | No. | Modular Coldroom/Freezer comprising: | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 008 | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.20a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.20b | 1 | No. | Evaporator | LU-VE | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.20c | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | HK.24 | 1 | No. | Hood type: Water Wash - Wall mount - Wall type - Double skin Hood dimension: 4480 (L) x 1500 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 4,585 m3/h Make-up air by Ginox: 3,897 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Gravity | GINOX Hoods | CUSTOM HOOD | U. A. E. | 59489 | 59489 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | HK.24.1 | 1 | No. | Incl. 4 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 20259 | 20259 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | HK.24a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 7890 | 7890 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | HK.30 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1500 (L) x 1250 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 2,425 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 5136 | 5136 | MIR # 005 | 1 | 90% | 4622 | 4622 | 0
Item No. Change | [6 empty] | HK.34 | 1 | No. | Floor drain with stainless steel gratings. 1400 x 300 | PKI / Techsteel | Custom | U. A. E. | 941 | 941 | MIR # 002 | 1 | 90% | 847 | 847 | 0
Description Change | [9 empty] | SDP.00 STAFF DINING SUPPORT PANTRY
Item No. Change | [6 empty] | SDP.07 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439 | 439 | 0
Item No. Change | [6 empty] | SD.09 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439 | 439 | 0
Description Change | [9 empty] | WW.00 STAFF DINING ROOM WAREWASH
Item No. Change | [6 empty] | WW.07 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1140 (L) x 1050 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 825 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 4383 | 4383 | MIR # 005 | 1 | 90% | 3945 | 3945 | 0
Item No. Change | [6 empty] | WW.08 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 001 | 2 | 90% | 878 | 878 | 0
Item No. Change | [6 empty] | WW.10 | 1 | No. | Floor drain with stainless steel gratings. 1200 x 300 | PKI / Techsteel | Custom | U. A. E. | 861 | 861 | MIR # 001 | 1 | 90% | 775 | 775 | 0
Description Change | [9 empty] | R.00 CENTRAL REFUSE AREA
Item No. Change | [6 empty] | R.05 | 4 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1948 | MIR # 002 | 4 | 90% | 1753 | 1753 | 0
Item No. Change | [6 empty] | R.12 | 1 | No. | Modular Coldroom comprising: | TSSC. | Custom | U. A. E. | 0 | INCLUDED IN FL.01 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | R.12a | 1 | No. | Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | R.12b | 1 | No. | Air Cooled Compressor | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | R.12c | 2 | No. | Evaporators | LU-VE | - | GERMANY | 0 | 0 |  | 2 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | R.13 | 1 | No. | Floor drain with stainless steel gratings. 2770 x 2500 | PKI / Techsteel | Custom | U. A. E. | 9056 | 9056 | MIR # 002 | 1 | 90% | 8150 | 8150 | 0
Description Change | [9 empty] | R.00 CENTRAL REFUSE AREA
Item No. Change | [6 empty] | R1.03 | 1 | No. | Floor drain with stainless steel gratings. 2000 x 300 | PKI / Techsteel | Custom | U. A. E. | 1185 | 1185 | MIR # 002 | 1 | 90% | 1067 | 1067 | 0
Description Change | [9 empty] | R1.00 REFUSE STORE 1
Item No. Change | [6 empty] | R2.03 | 3 | No. | Floor drain with stainless steel gratings. 2000 x 300 | PKI / Techsteel | Custom | U. A. E. | 1181 | 3543 | MIR # 002 | 3 | 90% | 3189 | 3189 | 0
[5 empty] | Sub-Total for BASEMENT 1 : |  | Sub-Total for Basement 1 : | [6 empty] | UAE Dirhams | 1476101 |  |  |  | 385544 | 97856 | 287688
Description Change | [9 empty] | Laundry Room |  |  |  | 0 | 0
Description Change | [9 empty] | LAUNDRY BASEMENT 1
UD.00 UNIFORM DISTRIBUTION AREA | [9 empty] | UD.00 UNIFORM DISTRIBUTION AREA
UD.00 UNIFORM DISTRIBUTION AREA | [6 empty] | UD.06 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 001 | 1 | 90% | 439 | 439 | 0
Description Change | [9 empty] | UD.00 UNIFORM DISTRIBUTION AREA
Item No. Change | [6 empty] | GV.07 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 001 | 3 | 90% | 1315 | 1315 | 0
Description Change | [9 empty] | LAUNDRY BASEMENT 2
Description Change | [9 empty] | LL.00 LOBBY LOUNGE SUPPORT AREAS
Item No. Change | [6 empty] | DL.08 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 002 | 1 | 90% | 439 | 439 | 0
Item No. Change |  |  |  |  | Sub-Total for BASEMENT 1 : |  | Sub-Total for Laundry Room : | [6 empty] | UAE Dirhams | 2437 |  |  |  | 2193 | 2193 | 0
Description Change | [9 empty] | GROUND FLOOR
Description Change | [9 empty] | BQ.00 BANQUET KITCHEN AND SUPPORT
Item No. Change | [6 empty] | BQ.06 | 6 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 2922 | MIR # 002 | 6 | 90% | 2630 | 2630 | 0
Item No. Change | [6 empty] | BQ.08 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 3850 (L) x 1550 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 3269 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 65610 | 65610 | MIR # 003 | 1 | 90% | 59049 | 59049 | 0
Item No. Change | [6 empty] | BQ.08.1 | 1 | No. | Incl. 3 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 15217 | 15217 | MIR # 003 | 1 | 90% | 13695 | 13695 | 0
Item No. Change | [6 empty] | BQ.08A | 1 | No. | service distribution unit. 3460 x 200 | PKI / Techsteel | Custom - SDU | U. A. E. | 5826 | 5826 | MIR # 004 | 1 | 90% | 5243 | 5243 | 0
Item No. Change | [6 empty] | BQ.08B | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 11603 | 11603 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BQ.13 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 2050 (L) x 1300 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 1339 m3/h Make-up air by Ginox: 0 m3/h - Hood front Lights: Flurorescent panel, 1 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 48151 | 48151 | MIR # 003 | 1 | 90% | 43336 | 43336 | 0
Item No. Change | [6 empty] | BQ.13.1 | 1 | No. | Incl. 2 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 10137 | 10137 | MIR # 003 | 1 | 90% | 9123 | 9123 | 0
Item No. Change | [6 empty] | BQ.13A | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 0 | INCLUDED IN BQ.08B |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BQ.14 | 1 | No. | Coldroom Comprising: | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 006 | 1 | 90% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BQ.14A | 1 | No. | Panel Sytem with 2 Single Door | TSSC. | Custom | U. A. E. | 0 | 0 | MIR # 006 | 1 | 90% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BQ.14B | 1 | No. | Dual Compartment Control Panel | TSSC. | Custom | U. A. E. | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BQ.14C | 1 | No. | Evaporator (Coldroom 01) | RIVACOLD | MONOBLOCK | ITALY | 6559 | 6559 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BQ.14D | 1 | No. | Evaporator(Coldroom 02) | RIVACOLD | MONOBLOCK | ITALY | 6559 | 6559 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | BQ.14E | 1 | No. | Air-Cooled Compressor (Coldroom 01) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BQ.14F | 1 | No. | Air- Cooled Compressor(Coldroom 02) | COPELAND - HERMETIC COMPRESSOR / RIVACOLD | - | GERMANY | 0 | 0 |  | 1 | 0% | 0 | 0 | 0 | INCLUDED IN FL.01
Item No. Change | [6 empty] | BQ.23 | 2 | No. | Floor drain with stainless steel gratings. 1000 x 300 1200+525 x 300 | PKI / Techsteel | Custom | U. A. E. | 1111 | 2222 | MIR # 002 | 2 | 90% | 2000 | 2000 | 0
Item No. Change | [6 empty] | BQ.48 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 2000 (L) x 1200 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: - m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 6188 | 6188 | MIR # 005 | 1 | 90% | 5569 | 5569 | 0
Description Change | [9 empty] | ADDITIONAL UNIT
Item No. Change | [6 empty] | 1 | 1 | Lot | FLOOR PANEL Floor panels constructed from 100 mm thick Rigid injected CFC free polyurethane foam finished with 1.4 mm thick AISI 304 stainless steel chequered plate on top, and 0.7 mm thick pre-painted GI sheet on unexposed side below. Overall sizes as per individual cold rooms listed above. | TSSC.. | Custom | U. A. E. | 135840 | 135840 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | 2 | 1 | Lot | FIRE SUPPRESSION SYSTEM PRE PIPING | AVENGER | CUSTOM | U. S. A. | 25251 | 25251 |  | 1 | 0% | 0 | 0 | 0
Item No. Change |  |  |  |  | Sub-Total for GROUND FLOOR : |  | Sub-Total for Ground Floor : | [6 empty] | UAE Dirhams | 342085 |  |  |  | 140645 | 140645 | 0
LEVEL 2
LP.00 LOBBY PATISSERIE
[7 empty] | LP.01 | 1 | No. | Refrigerated Display Counter | GINOX | Custom | U. A. E. | 0 | INCLUDED IN LP.01A |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.01A | 1 | No. | Refrigerated venitlated display for cakes 1060 x 800 x 1200 Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 46685 | 46685 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.01B | 1 | No. | Refrigerated venitlated display for cakes 1060 x 800 x 1200 Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 0 | INCLUDED IN LP.01A |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.01C | 1 | No. | Work counter with: * Closed storage cabinet with shelf, * Void under. Excludes: Front fascia and any decorative/joinery works. 2200 x 800 x 900 | GINOX | Custom | U. A. E. | 11163 | 11163 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.01D | 1 | No. | Undercounter refrigerator with two sets of two drawers 1350 x 660 x 780 | GINOX Refri. | Custom | U. A. E. | 0 | INCLUDED IN LP.01A |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.01E | 1 | No. | Closed storage cabinet with shelf | GINOX | Custom | U. A. E. | 0 | INCLUDED IN LP.01C |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.02 | 1 | No. | Work counter with: * 3 x Utensil drawer with closed storage cabinet, * Service riser. Excludes: Front fascia and any decorative/joinery works. 1810 x 445 x 900 | GINOX | Custom | U. A. E. | 15396 | 15396 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.03 | 1 | No. | Pastry Working Counter with: * 1 x Utensil drawer with closed storage cabinet, * Void under. Excludes: Front fascia and any decorative/joinery works. 1715 x 750 x 900 | GINOX | Custom | U. A. E. | 7021 | 7021 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.03A | 1 | No. | Two doors biscuit top chiller 1/1GN with remote condensing unit, digital temperature display and controller Temperature ‐2ᵒC to +8ᵒC Interior and exterior in stainless steel Silicone gaskets Technical compartment on the right side and two sets of two drawers Remote compressor to be located at 30 lineal meters Dim: 1150 x 660 x 780 Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | CB721‐HD‐HD | U. A. E. | 12272 | 12272 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.03B | 1 | No. | Utensil drawer with closed storage cabinet | GINOX | Custom | U. A. E. | 0 | INCLUDED IN LP.03 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.06 | 1 | No. | Work counter with: * 1 x WHB, * 1 x Waste bin cabinet, * Open storage cabinet. 1640 x 490 x 900 | GINOX | Custom | U. A. E. | 10136 | 10136 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.08 | 1 | No. | Work counter with: * 1 x Utility sink, * 1 x Waste bin cabinet, * 1 x Knock out drawer with closed cabinet * Closed storage cabinet, * Void under. 2990+735 x 640 x 900 | GINOX | Custom | U. A. E. | 17360 | 17360 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | LP.14 | 1 | No. | Run of Heated, Chilled and Ambient Cupboards | GINOX | Custom | U. A. E. | 57732 | 57732 |  | 1 | 0% | 0 | 0 | 0
Description Change | [9 empty] | TB.00 TERRACE BAR
Item No. Change | [6 empty] | TB.05 | 2 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 976 | MIR # 002 | 2 | 90% | 878 | 878 | 0
Description Change | [9 empty] | SBP.00 SECRET BAR PANTRY
Item No. Change | [6 empty] | SBP.08 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 002 | 1 | 90% | 439 | 439 | 0
Description Change | [9 empty] | LL.00 LOBBY LOUNGE SUPPORT PANTRY
Item No. Change | [6 empty] | LL.04 | 1 | No. | Floor drain with stainless steel gratings. 1200+525 x 300 | PKI / Techsteel | Custom | U. A. E. | 1446 | 1446 | MIR # 002 | 1 | 90% | 1301 | 1301 | 0
Item No. Change | [6 empty] | LL.16 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 002 | 3 | 90% | 1315 | 1315 | 0
Item No. Change | [6 empty] | LL.22 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1000 (L) x 1000 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 1350 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 4089 | 4089 | MIR # 005 | 1 | 90% | 3680 | 3680 | 0
Item No. Change | [6 empty] | LL.46 | 1 | No. | Services Distribution Unit with Potshelf and panels | PKI / Techsteel | Custom - SDU | U. A. E. | 8781 | 8781 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | LL.49 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 3800 (L) x 1265 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 3700 m3/h Make-up air by Ginox: 3145 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 64400 | 64400 | MIR # 007 | 1 | 90% | 57960 | 0 | 57960
Item No. Change | [6 empty] | LL.49.1 | 1 | No. | Incl. 3 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 15197 | 15197 | MIR # 007 | 1 | 90% | 13677 | 0 | 13677
Item No. Change | [6 empty] | LL.49A | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 7890 | 7890 |  | 1 | 0% | 0 | 0 | 0
[5 empty] | Sub-Total for LEVEL 2 : |  | Sub-Total for LEVEL 2 : | [6 empty] | UAE Dirhams | 282493 |  |  |  | 79250 | 7613 | 71637
Description Change | [9 empty] | LEVEL 4
Description Change | [9 empty] | RS.00 ROOM SERVICE BOH
Item No. Change | [6 empty] | RS.24 | 4 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1948 | MIR # 002 | 4 | 90% | 1753 | 1753 | 0
Item No. Change | [6 empty] | RS.27 | 1 | No. | Hood type: UV - Wall mount - Wall type - Double skin Hood dimension: 4500 (L) x 1050 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 4310 m3/h Make-up air by Ginox: 3664 m3/h - Hood front Lights: Flurorescent panel, 2 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 70146 | 70146 | MIR # 007 | 1 | 90% | 63131 | 0 | 63131
Item No. Change | [6 empty] | RS.27.1 | 1 | No. | Incl. 4 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 20259 | 20259 | MIR # 007 | 1 | 90% | 18233 | 0 | 18233
Item No. Change | [6 empty] | RS.27A | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 11603 | 11603 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | RS.27B | 1 | No. | Service distribution unit. 3950 x 200 | PKI / Techsteel | Custom - SDU | U. A. E. | 6650 | 6650 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | RS.27C | 1 | No. | Demand control: Incl. 0 automated damper(s), 1 pair(s) optical sensors, 2 temp. sensor(s). |  |  |  | 0 | DELETED |  |  | 0 | 0 | 0 | 0
Description Change | [9 empty] | ADK.00 ALL DAY DNING KITCHEN
Item No. Change | [6 empty] | ADK.07 | 3 | No. | Floor drain with stainless steel gratings. 900 x 300 1200 X 250 | PKI / Techsteel | Custom | U. A. E. | 821 | 2463 | MIR # 002 | 3 | 90% | 2217 | 2217 | 0
Item No. Change | [6 empty] | ADK.09 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 1025 (L) x 990 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 600 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 4142 | 4142 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | ADK.14 | 3 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 487 | 1461 | MIR # 002 | 3 | 90% | 1315 | 1315 | 0
[7 empty] | ADK.48 | 1 | No. | Stone Hearth Oven | Clay Oven | Bespoke | U. K. | 140235 | 140235 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | ADK.49 | 1 | No. | Hood type: Water Mist Wash - Island mount - Island type - Double skin Hood dimension: 3950 (L) x 2350 (W) x 600 (H) , in 2 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 10670 m3/h Make-up air by Ginox: 9072 m3/h - Hood front Lights: LED spot, 12 unit(s) Drain type: Gravity Note: Special finishes as per consultant specifications | GINOX Hoods | CUSTOM HOOD | U. A. E. | 136483 | 136483 | MIR # 007 | 1 | 90% | 122835 | 0 | 122835
Item No. Change | [6 empty] | ADK.49.1 | 1 | No. | Incl. 4 x Automated Dampers, 1 x Touchpad (On/Off Control) | GINOX Hoods | CUSTOM | U. A. E. | 20259 | 20259 | MIR # 007 | 1 | 90% | 18233 | 0 | 18233
Item No. Change | [6 empty] | ADK.49a | 1 | No. | Fire Suppression System | AVENGER | WET CHEMICAL | U. S. A. | 15316 | 15316 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | ADK.49b | 1 | No. | Demand control: Incl. 0 automated damper(s), 2 pair(s) optical sensors, 4 temp. sensor(s). |  |  |  | 0 | DELETED |  |  | 0 | 0 | 0 | 0
Item No. Change | [6 empty] | ADK.55 | 1 | No. | Hood type: Steam - Wall mount - Wall type - Single skin Hood dimension: 2165 (L) x 900 (W) x 600 (H) , in 1 section(s) Material: AISI 304, 1.2 mm - Brush Finish Exhaust air: 918 m3/h Make-up air by Ginox: 0 m3/h - none Lights: No, 0 unit(s) Drain type: Not applicable | GINOX Hoods | CUSTOM HOOD | U. A. E. | 6541 | 6541 | MIR # 005 | 1 | 90% | 5887 | 5887 | 0
[7 empty] | ADK.56a | 2 | No. | Refrigerated ventilated vertical display for wine Composed of : Nr. 2 units with two doors, Nr. 1 unit with one door Special shelves for wine bottles, Remote compressor to be located within 20 lineal meters (excluded), No cladding, Internal mirror finish, Dimmable lighting 2700 x 550 x 2000 (As per drawings) | GINOX Refri. | DISPLAY | U. A. E. | 160170 | 320340 |  | 2 | 0% | 0 | 0 | 0
Description Change | [6 empty] | ADK.56b | 1 | No. | Vertical Ambient display for wine Composed of : Nr. 2 units with two doors, Nr. 1 unit with one door Special shelves for wine bottles, No cladding Internal mirror finish, Dimmable lighting 2700 x 550 x 2000, (As per drawings) Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 101303 | 101303 |  | 1 | 0% | 0 | 0 | 0
Description Change | [6 empty] | ADK.57 | 1 | No. | Display Ambient for wine Composed of : Nr. 1 units with 3 doors, Special shelves for wine bottle Special handles, No cladding, Internal mirror finish Dimmable lighting, 1600 x 550 x 2000 (As per drawings) Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 56029 | 56029 |  | 1 | 0% | 0 | 0 | 0
Description Change | [9 empty] | CB.00 CAFÉ BAR
[7 empty] | CB.01 | 1 | No. | Kombucha Dispenser | KEGCO | KOM20S-1 | U. S. A. | 7205 | 7205 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.05 | 1 | No. | Nitro Cold Brew Dispenser With Filter | KEGCO | K163S-2 | U. S. A. | 9181 | 9181 |  | 1 | 0% | 0 | 0 | 0
Item No. Change | [6 empty] | CB.11 | 1 | No. | Floor drain with stainless steel gratings. 200 x 200 | PKI / Techsteel | Custom | U. A. E. | 488 | 488 | MIR # 002 | 1 | 90% | 439 | 439 | 0
[7 empty] | CB.15 | 1 | No. | 4 WELL ICE CREAM CHURNER | Carpigiani | CC400 | ITALY | 70779 | 70779 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.16 | 1 | No. | Double door bottle cooler (two sets of two drawers) with digital temperature display and controller Dim: 900 x 505 x 840 | GINOX Refri. | CF | U. A. E. | 10868 | 10868 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.17 | 1 | No. | Refrigerated ventilated display 700 x 500 x 1200 Finishes on the front fascia, sides and stone not to be included within this package Remote compressor to be located within 20 lineal meters (excluded) | GINOX Refri. | DISPLAY | U. A. E. | 18117 | 18117 |  | 1 | 0% | 0 | 0 | 0 | Item deleted
[7 empty] | CB.18 | 1 | No. | Hot display 700 x 500 x 1200 Finishes on the front fascia, sides and stone not to be included within this package | GINOX Refri. | DISPLAY | U. A. E. | 12078 | 12078 |  | 1 | 0% | 0 | 0 | 0 | Item deleted
[7 empty] | CB.19 | 1 | No. | "U" shaped bar counter with: * 1 x WHB, * 2 x Utility sink with closed storage cabinet, * 1 x Cutting board, * 1 x Cashier station, * Cocktail station with insulated ice well with sliding lids, partation and perforated false bottom. Unit to have condiment well to rear and speed rail to front, * Recessed blender station, * Closed storage cabinet with shelf, * Void under. Excludes: Front fascia and any decorative/joinery works. 5000+1100+5000 x 600 x 900 | GINOX | Custom | U. A. E. | 118616 | 118616 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19a | 1 | No. | Preparation Counter with inset cutting boards | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19b | 1 | No. | Wash Hand Station | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19c | 1 | No. | Panelled Recess for Undercounter Refrigerator | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19d | 1 | No. | Panelled Recess for Ice Cream Unit | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19e | 1 | No. | Recessed Worktop for Equipment | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19f | 1 | No. | Ice Well with Double Speed Rail | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19g | 1 | No. | Recessed Worktop for Equipment | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19h | 1 | No. | Panelled Recess for Waste Bin | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19i | 1 | No. | Sink Bowl with Shelf Under | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[7 empty] | CB.19j | 1 | No. | Panelled Recess for Ice Machine | GINOX | Custom | U. A. E. | 0 | included in CB.19 |  | 1 | 0% | 0 | 0 | 0
[5 empty] | Sub-Total for BASEMENT 1 : |  | Sub-Total for Level 4 : | [6 empty] | UAE Dirhams | 1162510 |  |  |  | 234043 | 11611 | 222432
Description Change | [9 empty] | Remote Condensing Unit of Display Refrigeration as per the quotation ref: Ref: DCD/KLE/13A20/HP/MTS/BOQ013Pkg.1 a
Item No. Change | [6 empty] | RCU-01 | 1 | Lot | Supply and Installation of the Remote Condensing Unit for the following item, where the limit of piping would be of 20 Meter. Level 4 ADK.56a Refrigerated ventilated vertical display for wine ADK.56b Vertical display for wine ADK.57 Display for wine CB.17 Refrigerated ventilated display Level 2 LP.01A Refrigerated venitlated display for cakes LP.01B Refrigerated venitlated display for cakes | GINOX Refri.. | Custom | U. A. E. | 101877 | 101877 |  | 1 | 0% | 0 | 0 | 0
Description Change | [9 empty] | Design Charges - Engineering Work, Quotation Ref: VQTE-0002-HP-DCD-EW/KL/P1-27D21-JA-02
Item No. Change | [6 empty] | DC-01 | 1 | Lot | Scope of Engineering Work: (As per work completed under RPJV before change in scope) 1. Material Submittal for Approval 2. Shop Drawings including Equipment Layout & MEP Requirements in 2D 3. Coordination of drawings with Main Contractor | TSSC Dubai | Service | U. A. E. | 35000 | 35000 |  | 1 | 0% | 0 | 0 | 0
[5 empty] | Total For Food Service Equipment In All Areas As Listed (Installed & Commissioned) : |  | Grand Total For Kitchen Equipment In All Areas As Listed (Installed & Commissioned) : | [6 empty] | UAE Dirhams | 3402503 |  |  |  | 841675 | 259918 | 581757
[7 empty] | Special Discount | [6 empty] | UAE Dirhams | -18821 |  |  | 25% | -4705 | -1506 | -3199
[7 empty] | Total Amount After Discount | [6 empty] | UAE Dirhams | 3383682 |  |  |  | 836970 | 258412 | 578558
[7 empty] | VAT 5% | [6 empty] | UAE Dirhams | 169184 |  |  |  | 41849 | 12921 | 28928
[7 empty] | Grand Total | [6 empty] | UAE Dirhams | 3552866 |  |  |  | 878819 | 271333 | 607486
(Three Million, Five Hundred and Fifty Two Thousand, Eight Hundred and Sixty Six UAE Dirhams)

## CERTIFIED TO DATE
PREVIOUS PAYMENTS -ANNEXURE 2
Project Name : |  | Plot 18, Business Bay Dubai, UAE |  |  |  | TSSC-04
Company : |  | Sky Palaces Real Estate Development LLC
Contractor : |  | M/s TSSC Kitchen & Laundry Equipment Trading LLC
Payment Cert. No. |  | TSSC-04 | Budget |  | 3383682 | D171 | 2023-03-06
Contract Title: |  | Supply, Installation, Testing and Commissioning of Kitchen Equipment
SN | PC No. | INVOICE NO. |  | PHASE |  | PREVIOUSLY CERTIFIED | CERTIFIED TO DATE
1 | 1 | 10/SIP/21186-R1 |  | Advance Payment |  | 307108.5 | 307108.5 | 292484.29 | 3383682 | 8.64% | 9.08%
2 | 2 | 22082 |  | Advance Payment |  | 707996.1 | 707996.1 | 674282
3 | 03 (Rename of IPC No. TSSC-01) | 23007/R1 |  | Delivery of Kitchen Equipment to the site |  | 155047.2 | 155047.2 | 708000 |  | 0.20924
4 | 4 | TSSC/IPA002 |  | Delivery of Kitchen Equipment to the site |  |  | 347134.8
TOTAL | [5 empty] | 1170151.8 | 1517286.6
PC No (Please don’t delete this) |  |  |  | 4
Invoice No (Please don’t delete this) |  |  |  | TSSC/IPA002
Work Done (Please don’t delete this) |  |  |  | Delivery of Kitchen Equipment to the site
Type |  |  |  | Contractor :
Name |  |  |  | M/s TSSC Kitchen & Laundry Equipment Trading LLC
Address 01 |  |  |  | P.O. Box 69
Address 02 |  |  |  | Dubai, UAE
Cost Code |  |  |  | D171
Contract Start Date |  |  |  | 2021-12-19
Date of Application |  |  |  | 2023-02-24
Period for Works Certified |  |  |  | Refer the attachment
Payment Due Date |  |  |  | 2023-03-26
Certificate Currency |  |  |  | AED
Payment Terms |  |  |  | The Payment shall be released within 30 days of the Payment Application

## PS (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Client Provisional Sums
SUMMARY - Bill 2
|  | Accepted Contract Amount | PROGRESS VALUATION
Item | Package |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
2 | Provisional Sum Packages
2.1 | Structure - Steel | 10600000
2.2 | Roof Coverings | 1100000
2.3 | External Walls - Gartners | 154500000
2.4 | External Walls - Remaining Provisional Sum | 11700000
2.5 | BMU | 7000000
2.6 | External Doors | 300000
2.7 | Internal Walls & Partitions | 2600000
2.8 | Contractor Floor Finishes | 1000000
2.9 | Contractor Wall Finishes | 1300000
2.1 | Contractor Ceiling Finishes | 900000
2.11 | Sanitary Appliances | 1900000
2.12 | Electrical Installations | 57800000
2.13 | Mechanical Installations | 63200000
2.14 | Vertical Transportation - KONE | 30000000
2.15 | BWIC | 2800000
2.16 | Drainage | 9600000
2.17 | External Works | 12750000
2.18 | External Lighting | 8000000
2.19 | Client Finishes, Incl Doors, Ironmongery, Fixtures & Fittings & Oyster Fit Out | 28700000
15000000
2.2 | IT Building Automation
| Totals | 420750000 | 0% | 0 | 0% | 0 | 0% | 0

## Contractor's Application (hidden)
NASA MULTIPLEX L.L.C.
THE OPUS, BUSINESS BAY
CONTRACTOR'S APPLICATION FOR INTERIM CERTIFICATE
Contract Title: |  | The Opus, Business Bay |  | Application No: | 11
Date of Contract: |  | 9th March 2008 (Letter of Acceptance) |  | Date of Application: | 2009-03-01
Contractor: |  | Nasa Multiplex L.L.C.
Contract Sum: |  | UAE Dirhams 794,057,000
Contractor's Application for Interim Certificate No: |  |  | 11
We hereby apply for an Interim Certificate in accordance with Clause 14.2 (Advance Payment) and 14.3 (Application for Interim Payment
Certificates ) the amount of such Interim Certificate being as set out below.
| Advance Payment (In Accordance with Item 41 of the LOA dated 9th March 08) |  |  |  | 54196050
| Estimate of the Contract Value of the Works carried out on Site |  |  |  | #N/A
up to Date of Application
| 90% of the Invoice Value delivered to Site of all Plant on Site |  |  |  | 0
| Any other amounts to which we consider ourselves to be |  |  |  | 0
entitled
| GROSS AMOUNT OF INTERIM CERTIFICATE APPLICATION |  |  |  | #N/A
| Deduct Recovery of Advance Payment |  |  |  | 0
(Subject to Receipt of Advanced Payment)
| Amount owed by Omniyat for NMX portion of Certificate No 1 |  |  |  | -2654754.4
| Amount owed by Omniyat for NMX against Certificate No 5 |  |  |  | -999607
| Amount owed by Omniyat for NMX against Certificate No 6 |  |  |  | -806223.4
| Advance Abatement uopto and Including Certificate No 6 |  |  |  | -1143169
| Amount owed by Omniyat for NMX against Certificate No7 |  |  |  | -1880835
| Amount owed by Omniyat for NMX against Certificate No 8 |  |  |  | -1427250
| Amount Owed by Omniyat for NMx against Certificate No 9 |  |  |  | -800000
| Amount Owed by Omniyat for NMx against Certificate No 10 |  |  |  | -800000
| Amount Owed by Omniyat for NMx against Certificate No 11 |  |  |  | -800000
| NET AMOUNT TO DATE |  |  |  | #N/A
| Deduct: Retention |  |  |  | #N/A
| Add: Retention Bond |  |  |  | #N/A
| Deduct: Previous Employer's Representatives Certificate |  |  |  | -61288954
| NETT AMOUNT OF INTERIM CERTIFICATE APPLICATION |  |  |  | #N/A
For and on behalf of
NASA MULTIPLEX L.L.C.
Mr. Andrew Phillips
Contractor's Representative
Distribution (By the Engineer): |  | Original: Employer's Representative
Copies: (1) Employer (2) Quantity Surveyor
Note on H7: lizae:
Note on H8: lizae:
Note on H53: ashleyw: Gross Certified Less Advance Payment Payback

## Payment Application (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
[5 empty] | Accepted Contract Amount | Application Value |  | Total Application Value
1 | Structural Concrete : |  |  |  | 204300000 | 0
(Refer to the Breakdown Appended)
2 | Provisional Sum Packages : |  |  |  | 420750000 | 0
(Refer to the Breakdown Appended)
3 | Design Fees :
| 3.1 | Structural Engineer : |  |  | 10439000 | 6119850
(Refer to the Breakdown Appended)
| 3.2 | MEP : |  |  | 1561000 | 528000
(Refer to the Breakdown Appended)
4 | Preliminaries : |  |  |  | 80000000 | 0
(Refer to the Breakdown Appended)
5 | Attendances for Enabling Works : |  |  |  | 2820000 | 1794548
(Refer to the Breakdown Appended)
6 | Professional Indemnity Insurance : |  |  |  | 2000000 | 437500
(Refer to the Breakdown Appended)
7 | Variation Works : |  |  |  | 0 | #N/A
(Refer to the Breakdown Appended)
8 | Remeasurements : |  |  |  | 0 | 0
(Refer to the Breakdown Appended)
|  |  |  | Sub Total | 721870000 |  |  | #N/A
9 | Margin |  |  | 10% | 72187000 |  |  | #N/A
[5 empty] | 794057000 |  |  | #N/A
10 | Materials On Site:
| 11.1 | NMX Works : | [5 empty] | 0
11 | Additional Expenditure for Preliminaries, EOT : | [6 empty] | 3200000
(Refer to the Breakdown Appended)
(Subject to Receipt of Advanced Payment)
|  |  |  | GROSS AMOUNT DUE |  |  |  | #N/A
|  |  | LESS RETENTION |  |  |  | 5% | #N/A
|  |  |  | GROSS AMOUNT DUE |  |  |  | #N/A
Note on I11: lizae: Linked Structural Concrete Temporary Sheet
Note on I19: lizae: linked to LEC
Note on I22: lizae: linked to LEC
Note on I25: lizae: Linked Prelim Temporary Sheet
Note on I28: lizae: linked to LEC
Note on I31: lizae: linked to LEC
Note on I34: lizae: linked to LEC
Note on I53: lizae: Linked EOT Temporary Sheet

## Advance Payment (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Advance Payment
|  |  | Advance Payment Claim |  |  | Advance Payment Abatement
Item |  | Description | Accepted Contract Amount | % | Value | Works Complete | % | Value
1 | Bill No. 1 | Structural Concrete Frame | 204300000 | 15% | 30645000 | 0 | 15% | 0
2 | Bill No. 2 | Provisional Sum Packages :
|  | Structure - Steel | 10600000
|  | Roof Coverings | 1100000
|  | External Walls - Gartners | 154500000 | 15% |  | 0
|  | External Walls - Remaining PS Allowance | 11700000
|  | BMU | 7000000
|  | External Doors | 300000
|  | Internal Walls & Partitions | 2600000
|  | Contractor Floor Finishes | 1000000
|  | Contractor Wall Finishes | 1300000
|  | Contractor Ceiling Finishes | 900000
|  | Sanitary Appliances | 1900000
|  | Electrical Installations | 57800000
|  | Mechanical Installations | 63200000
|  | Vertical Transportation - KONE | 30000000 | 15% | 0 | 0
|  | BWIC | 2800000
|  | Drainage | 9600000
|  | External Works | 12750000
|  | External Lighting | 8000000
|  | Client Finishes, Incl Doors, Ironmongery, Fixtures & Fittings & Oyster Fit Out | 28700000
|  | IT Building Automation | 15000000
3 | Bill No. 3 | Provisional Sum for Completion of Mechanical, Electrical and Plumbing (MEP) Design and Structural Design Supervision and Inspections :
|  | Structural - BG&E | 10439000 | 15% | 0 | 6119850 | 0% | 0
|  | MEP - Whitby & Bird LOI | 960000 | 15% | 0 | 528000 | 0% | 0
|  | Remaining Design Provisional Sum | 601000
4 |  | Preliminaries (Fixed) | 80000000 | 15% | 12000000 | 0 | 15% | 0
5 | Bill No. 4(a) | Attendances for Piling, Shoring and Enabling Works (Fixed) | 2820000 | 15% | 423000 | 1794548 | 0% | 0
6 | Bill No. 4(b) | Professional Indemnity Insurance (Fixed) | 2000000 | 15% | 300000 | 437500 | 0% | 0
|  | Sub Totals | 721870000 |  | 43368000 | 8879898 |  | 0
7 |  | Add Contractor's Profit Margin at 10% | 72187000 | 15% | 10828050 | 887990 | 0% | 0
|  | TOTAL | 794057000 |  | 54196050 | 9767888 |  | 0
Note on H15: lizae: Linked Structural Concrete Temporary Sheet
Note on H49: lizae: Linked Prelim Temporary Sheet

## Structure-Temp (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: |  |  |  |  | 2009-03-01
Application No: |  |  |  |  | 11
Structural Concrete
|  | Accepted Contract Amount | Percentage Complete | Application Amount | Remarks
Item | Package
1 | Structural Concrete
1.1 | System Formwork |  |  | 0 | Included within Advance Payment
1.2 | Jumpform |  |  | 0 | Included within Advance Payment
1.3 | Substructure Waterproofing |  |  | 0 | Included within Advance Payment
| Totals | 204300000 | 0% | 0

## Structural Sum (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Structural Concrete
SUMMARY - Bill 1
|  | Accepted Contract Amount | PROGRESS VALUATION
Item | Package |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
1 | Structural Concrete
1.1 | Dewatering | Excluded
1.2 | Earthworks | 110228.24 |  |  | 0% | 0
1.3 | Termite Treatment | 64071.44 |  |  | 0% | 0
1.4 | Pile Head Cut Off | 509200 |  |  | 0% | 0
1.5 | Road Markings | Excluded
1.6 | Road Markings | Excluded
1.7 | Formwork | 51071506.79 | 26% | 13354958 | 0% | 0 | 26% | 13354958 | 22191310 | 80% | 17753048
-4398090
1.8 | Expansion / Construction Joints | 32144.5 |  |  | 0% | 0
1.9 | Reinforcement | 81596753.79 |  |  | 0% | 0
1.1 | Concrete | 57422108.31 |  |  | 0% | 0
1.11 | Post Tensioning Works | 10311307.2 |  |  | 0% | 0
1.12 | Waterproofing Works | 3182679.73 |  |  | 0% | 0
| Totals | 204300000 | 7% | 13354958 | 0% | 0 | 7% | 13354958

## ◄Formwork (hidden)
Omniyat Properties
The Opus, Business Bay | [13 empty] | 2009-03-01
Application No: |  | 11
Contract : | The Opus At Business Bay, Dubai, U.A.E.
Item : | Formwork
Ref: | Description | Qty | Unit | Rate | Amount | PROGRESS VALUATION | [8 empty] | Remeasured Surplus/ Deficit
[6 empty] | Last Month |  |  | This Month |  |  | To Date |  |  | Estimated Qty Tower | Diff from Orig Qty | Rate | Value At Risk
[6 empty] | % | Qty | Value | % | Qty | Value | % | Qty | Value
Formwork
A | To Pile Caps | 560.68 | m2 | 280.73 | 157399.7 | 25% |  | 39349.93 | 0% |  | 0 | 25% |  | 39349.93 | 560.68 | 0 | 280.73 | 0
B | To Raft slab | 2488.93 | m2 | 380.7 | 947535.65 | 25% |  | 236883.91 | 0% |  | 0 | 25% |  | 236883.91 | 2488.93 | 0 | 380.7 | 0
C | To Retaining Walls | 19343.32 | m2 | 155.6 | 3009820.59 | 25% |  | 752455.15 | 0% |  | 0 | 25% |  | 752455.15 | 19343.32 | 0 | 155.6 | 0
D | To Staircases | 3600.64 | m2 | 144.6 | 520652.54 | 25% |  | 130163.14 | 0% |  | 0 | 25% |  | 130163.14 | 3600.64 | 0 | 144.6 | 0
E | To Walls | 90092.55 | m2 | 206.1 | 18568074.56 | 25% |  | 4642018.64 | 0% |  | 0 | 25% |  | 4642018.64 | 90092.55 | 0 | 206.1 | 0
F | To Columns | 17844.87 | m2 | 114.3 | 2039668.64 | 25% |  | 509917.16 | 0% |  | 0 | 25% |  | 509917.16 | 17844.87 | 0 | 114.3 | 0
G | To Columns (inclined) | 3702.86 | m2 | 247 | 914606.42 | 25% |  | 228651.61 | 0% |  | 0 | 25% |  | 228651.61 | 3702.86 | 0 | 247 | 0
H | To Post Tensioned Beams & Slabs | 46418.66 | m2 | 138.4 | 6424342.54 | 25% |  | 1606085.64 | 0% |  | 0 | 25% |  | 1606085.64 | 46418.66 | 0 | 138.4 | 0
I | To Suspended Slabs | 125250.76 | m2 | 153.5 | 19225991.66 | 25% |  | 4806497.92 | 0% |  | 0 | 25% |  | 4806497.92 | 125250.76 | 0 | 153.5 | 0
J | To Suspended Beams | 3964.92 | m2 | 128.4 | 509095.73 | 25% |  | 127273.93 | 0% |  | 0 | 25% |  | 127273.93 | 3964.92 | 0 | 128.4 | 0
K | To Civil Works concrete | 2000 | m2 | 171.2 | 342400 | 25% |  | 85600 | 0% |  | 0 | 25% |  | 85600 | 2000 | 0 | 171.2 | 0
L | To Miscellaneous Concrete | 800 | m2 | 171.2 | 136960 | 25% |  | 34240 | 0% |  | 0 | 25% |  | 34240 | 800 | 0 | 171.2 | 0
|  | 316068.19 | m2 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 316068.19 | 0
M | To edges of slab: 600mm thick | 960 | m | 43.4 | 41664 | 25% |  | 10416 | 0% |  | 0 | 25% |  | 10416 | 960 | 0 | 43.4 | 0
N | To edges of slab: 500mm thick |  | m | [5 empty] | 0% |  | 0 |  |  |  |  | 0 | 0 | 0
O | To edges of slab: 350mm thick | 1321.74 | m | 27.4 | 36215.68 | 25% |  | 9053.92 | 0% |  | 0 | 25% |  | 9053.92 | 1321.74 | 0 | 27.4 | 0
P | To edges of slab: 350mm thick (curved) | 445 | m | 27.4 | 12193 | 25% |  | 3048.25 | 0% |  | 0 | 25% |  | 3048.25 | 445 | 0 | 27.4 | 0
Q | To edges of slab: 300mm thick | 248.88 | m | 24.2 | 6022.9 | 25% |  | 1505.73 | 0% |  | 0 | 25% |  | 1505.73 | 248.88 | 0 | 24.2 | 0
R | To edges of slab: 400mm thick | 467.23 | m | 30.6 | 14297.24 | 25% |  | 3574.31 | 0% |  | 0 | 25% |  | 3574.31 | 467.23 | 0 | 30.6 | 0
S | To edges of slab: 300mm thick (curved) |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
T | To edges of slab: 275mm thick | 8708.3 | m | 22.6 | 196807.58 | 25% |  | 49201.9 | 0% |  | 0 | 25% |  | 49201.9 | 8708.3 | 0 | 22.6 | 0
U | To edges of slab: 275mm thick (curved) | 4609.78 | m | 22.6 | 104181.03 | 25% |  | 26045.26 | 0% |  | 0 | 25% |  | 26045.26 | 4609.78 | 0 | 22.6 | 0
Formwork Continued
A | To edges of slab: 250mm thick |  | m | 20.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 20.2 | 0
B | To edges of slab: 300mm thick |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
C | To edges of slab: 280mm thick |  | m | 22.9 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 22.9 | 0
D | To edges of slab: 280mm thick (curved) |  | m | 22.9 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 22.9 | 0
E | To edges of slab: 250mm thick |  | m | 20.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 20.2 | 0
F | To edges of slab: 250mm thick (curved) | 355.58 | m | 20.2 | 7182.72 | 25% |  | 1795.68 | 0% |  | 0 | 25% |  | 1795.68 | 355.58 | 0 | 20.2 | 0
G | To edges of slab: 300mm thick |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
H | To edges of slab: 300mm thick (curved) |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
I | To edges of slab: 225mm thick |  | m | 18.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 18.2 | 0
J | To edges of slab: 150mm thick | 605.48 | m | 12.2 | 7386.86 | 25% |  | 1846.72 | 0% |  | 0 | 25% |  | 1846.72 | 605.48 | 0 | 12.2 | 0
K | To edges of slab: 150mm thick (curved) | 52.86 | m | 12.2 | 644.89 | 25% |  | 161.22 | 0% |  | 0 | 25% |  | 161.22 | 52.86 | 0 | 12.2 | 0
L | To edges of slab: 225mm thick (curved) |  | m | 18.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 18.2 | 0
M | Formwork to edges to form Construction Joints | 12528 | m | 15 | 187920 | 25% |  | 46980 | 0% |  | 0 | 25% |  | 46980 | 12528 | 0 | 15 | 0
N | Formwork to edges to form Expansion Joints | 292.3 | m | 30 | 8769 | 25% |  | 2192.25 | 0% |  | 0 | 25% |  | 2192.25 | 292.3 | 0 | 30 | 0
|  | 30595.15 | m |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 30595.15 | 0
| TOTAL |  |  |  | 53419832.93 | 25% |  | 13354958.27 | 0% |  | 0 | 25% |  | 13354958.27 |  |  |  | 0
Note on M15: lizae:

## Design (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Provisional Sums - Design
|  | Accepted Contract Amount | PROGRESS VALUATION
Item | Description |  | Total Claim |  | Previous Claims |  | This Claim
|  |  | % | Value | % | Value | % | Value
3 | Provisional Sums - Design
Provisional Sum for Completion of Mechanical, Electrical and Plumbing (MEP) Design and Structural Design Supervision and Inspections :
| Structure | 10439000 | 59% | 6119850 | 59% | 6119850 | 0% | 0
3.1 | Structure - BG&E Engineers | 6900000 | 89% | 6119850 | -89% | 6119850 | 0% | 0
| Supervision | 3539000 |  | 0 |  | 0 |  | 0
| MEP | 1561000 | 34% | 528000 | 34% | 528000 | 0% | 0
3.2 | MEP - Whitby & Bird | 960000 | 55% | 528000 | 55% | 528000 | 0% | 0
| MEP Design - Outstanding Provisional Sum Value | 601000 |  | 0 |  | 0 |  | 0
| Totals | 12000000 | 55% | 6647850 | 55% | 6647850 | 0% | 0

## Prelim-Temp (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: |  |  |  |  | 2009-03-01
Application No: |  |  |  |  | 11
Preliminaries
|  | Accepted Contract Amount | Percentage Complete | Application Amount | Remarks
Item | Package
1 | Preliminaries | 80000000
1.1 | Site Administration and Supervision(Pre & Post Construction,Staff - Management & Supervision) |  |  | 0 | Included within Advance Payment
1.2 | Miscellaneous Labour (Labour for site) |  |  | 0 | Included within Advance Payment
1.3 | Crane Operator, Alimak, Drivers and Banksman |  |  | 0 | Included within Advance Payment
1.4 | Transport of People |  |  | 0 | Included within Advance Payment
1.5 | Health and Safety Programme(Safety Training, First Aid, Safety Signage, Extinguishers) |  |  | 0 | Included within Advance Payment
1.6 | Site Accomodation (Temporary Buildings, Office Furniture , IT & Software Set Up, Consumables, Plotter, Photocopy machines) |  |  | 0 | Included within Advance Payment
1.7 | Site Signage |  |  | 0 | Included within Advance Payment
1.8 | Temporary Utilities ( Site Power, Water, Drainage, Genset, Fuel) |  |  | 0 | Included within Advance Payment
1.9 | Telecommunications (Telephone, & Telephone Set up, Fax & Mobile Phones) |  |  | 0 | Included within Advance Payment
1.1 | Plant and Cranage ( Crane, Hoist, Other Plant & Equipment, FOL) |  |  | 0 | Included within Advance Payment
1.11 | Scaffolding-Access / Edge Protection |  |  | 0 | Included within Advance Payment
1.12 | Site Clean Up( Rubbish Removal ) |  |  | 0 | Included within Advance Payment
1.13 | Final Cleaning |  |  | 0 | Included within Advance Payment
1.14 | Site Security (Security Guards, Protection of Permanent Works) |  |  | 0 | Included within Advance Payment
1.15 | Surveys ( Survey and Surveying Equipment ) |  |  | 0 | Included within Advance Payment
1.16 | Photographs and Records |  |  | 0 | Included within Advance Payment
1.17 | Facilities for Employer |  |  | 0 | Included within Advance Payment
1.18 | Insurance and Bonds |  |  | 0 | Included within Advance Payment
| Totals | 80000000 | 0% | 0

## ◄Cranes (hidden)
MPXPE / HOA / OPUS - 001
OPUS - Business Bay
Appendix A
Multiplex Plant & Equipment LLC
| TC1 | TC2 | TC3 | TC4
Tower Crane Specification
Make | HKTC | HKTC | HKTC | HKTC
Model | 290-HC 12 | 290-HC 12 | 290-HC 12 | 290-HC 12
Y.O.M | 2008 | 2008 | 2008 | 2008
Jib Length | 60m | 55m | 55m | 55m
Maximum Capacity Freestand | 12T | 12T | 12T | 12T
Tip Load | 4.1T@60m | 4.8T@55m | 4.8T@55m | 4.8T@55m
Freestand Height | 69.9m | 57.3m | 69.9m | 57.3m
Final Height | 119.58m | 131.82m | 119.58m | 131.82m
Additional Tower Sections Required | 12 | 18 | 12 | 18
No Collars Required | 2 | 3 | 2 | 3
Mast Dimension | 2.3 x 2.3 x 4.14 | 2.3 x 2.3 x 4.14 | 2.3 x 2.3 x 4.14 | 2.3 x 2.3 x 4.14
Rental (Incl. Maintenance)
Minimum Hire Duration (Months) | 20 | 18 | 19 | 17
Rental / Month | 95000 | 95000 | 95000 | 95000
Total Rent Payable | 1900000 | 1710000 | 1805000 | 1615000
Extras
Fixing Angles | 40000 | 35000 | 40000 | 35000
Transport to Site | 40000 | 40000 | 40000 | 40000
First Erection | 20000 | 20000 | 20000 | 20000
Tie Installation (Dhs 4000 / Set) | 8000 | 12000 | 8000 | 12000
Jacking Up or Down (Dhs 1400 / Section) | 16800 | 25200 | 16800 | 25200
Third party Inspections (Dhs 1,500 / Test) | 4500 | 6000 | 4500 | 6000
Dismantling | 45000 | 45000 | 45000 | 45000
Transport from Site | 40000 | 40000 | 40000 | 40000
Total Extras | 214300 | 223200 | 214300 | 223200
Minimum Payable to Multiplex Plant & Equipment LLC | 2114300 | 1933200 | 2019300 | 1838200
Totals | 7905000

## Enabling Works Attendances (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Enabling Work Attendances
SUMMARY - Bill 4(b)
Month No |  | Accepted Contract Amount | PROGRESS VALUATION
| Month |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
Enabling Works Attendances
-6 | May 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-5 | June 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-4 | July 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-3 | Áugust 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-2 | September 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-1 | Óctober 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
1 | November 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
2 | December 2008 | 256364
3 | Januray 2009 | 256364
4 | February 2009 | 256364
5 | March 2009 | 256360
| Totals | 2820000 | 64% | 1794549 | 0% | 0 | 64% | 1794548

## PI Insurance (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Professional Indemnity Insurance
Month No |  | Accepted Contract Amount | PROGRESS VALUATION
| Month |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
Professional Indemnity Insurance
2008
-7 | Ápril 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-6 | May 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-5 | June 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-4 | July 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-3 | Áugust 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-2 | September 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-1 | Óctober 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
1 | November 2009 | 62500 |  |  |  |  | 0% | 0
2 | December 2008 | 62500 |  |  | 0% | 0 |  | 0
2009
3 | January 2009 | 62500 |  |  | 0% | 0 |  | 0
4 | February 2009 | 62500 |  |  | 0% | 0 |  | 0
5 | March 2009 | 62500 |  |  | 0% | 0 |  | 0
6 | Ápril 2009 | 62500 |  |  | 0% | 0 |  | 0
7 | May 2009 | 62500 |  |  | 0% | 0 |  | 0
8 | June 2009 | 62500 |  |  | 0% | 0 |  | 0
9 | July 2009 | 62500 |  |  | 0% | 0 |  | 0
10 | Áugust 2009 | 62500 |  |  | 0% | 0 |  | 0
11 | September 2009 | 62500 |  |  | 0% | 0 |  | 0
12 | Óctober 2009 | 62500 |  |  | 0% | 0 |  | 0
13 | November 2009 | 62500 |  |  | 0% | 0 |  | 0
14 | December 2009 | 62500 |  |  | 0% | 0 |  | 0
2010
15 | January 2010 | 62500 |  |  | 0% | 0 |  | 0
16 | February 2010 | 62500 |  |  | 0% | 0 |  | 0
17 | March 2010 | 62500 |  |  | 0% | 0 |  | 0
18 | Ápril 2010 | 62500 |  |  | 0% | 0 |  | 0
19 | May 2010 | 62500 |  |  | 0% | 0 |  | 0
20 | June 2010 | 62500 |  |  | 0% | 0 |  | 0
21 | July 2010 | 62500 |  |  | 0% | 0 |  | 0
22 | Áugust 2010 | 62500 |  |  | 0% | 0 |  | 0
23 | September 2010 | 62500 |  |  | 0% | 0 |  | 0
24 | Óctober 2010 | 62500 |  |  | 0% | 0 |  | 0
25 | November 2010 | 62500 |  |  | 0% | 0 |  | 0
| Totals | 2000000 | 22% | 437500 | 0% | 0 | 22% | 437500

## EOT-Temp (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: |  |  |  |  | 2009-03-01
Application No: |  |  |  |  | 11
Additional Expenditure for Preliminaries Extension of Time
|  | Accepted Contract Amount | Percentage Complete | Application Amount | Remarks
Item | Package
1 | Additional Expenditure for Preliminaries Extension of Time
1.1 | Month 1 - Nov 08 | 800000 | 100% | 800000
1.2 | Month 2 - Dec 08 | 800000 | 100% | 800000
1.3 | Month 3 - Jan 09 | 800000 | 100% | 800000
1.4 | Month 4 - Feb 09 | 800000 | 100% | 800000
1.5 | Month 5 - Mar 09 | 800000 |  | 0
1.5 | Month 6 - Apr 09 | 800000 |  | 0
1.5 | Month 7 - May 09 | 361290.32 |  | 0
Note : Month 7 May 09 based on proposed
start date on site 15/05/09
| Totals | 5161290 | 62% | 3200000

## Anwa (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | ANWA, DUBAI MARITIME CITY |  | Certificate No: | 014
|  |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Asset Management LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Manamgement LLC |  | Contract Start Date :
Date of Application:
Employer : | ANWA Real Estate Developments LLC |  | Payment Due Date :
| PO Box 709298 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMNIYAT ASSET MANAGEMENT LLC
Oliver Keegan |  | Tore Zeidler |  | Dean Lander
Project Manager |  | Development Manager |  | Development Director
ANWA REAL ESTATE DEVELOPMENT LLC approval to proceed the net amount certified for approval
Mohammad Ali Al Rahma |  |  |  | Date
Manager
ALMASA MARITIME ONE LIMITED approval to proceed the net amount certified for approval
Ishan Garga |  | Mark Phoenix |  | Date
Authorized Signatory |  | Authorized Signatory
Note: MA is POA of M. Ali Al Rahma

## The Sterling East (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Sterling East House |  | Certificate No: | 014
| Business Bay Dubai UAE |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Middle East Real Estate Developments LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Management LLC |  | Contract Start Date :
Date of Application:
Employer : | OP 17 Limited |  | Payment Due Date :
| PO Box 48926 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMINIYAT MIDDLE EAST REAL ESTATE DEVELOPMENTS LLC
Oliver Keegan |  | Tore Zeidler |  | Dean Lander
Project Manager |  | Development Manager |  | Development Director
Ishan Garga |  | Mark Phoenix |  | Date
Director - Corporate Finance |  | Managing Director
OP 17 LIMITED approval to proceed the net amount certified for approval
Anthony Manning
Authorized Signatory

## The Sterling West (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Sterling West House |  | Certificate No: | 014
| Business Bay Dubai UAE |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Middle East Real Estate Developments LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Management LLC |  | Contract Start Date :
Date of Application:
Employer : | Omniyat Properties Seventeen Ltd. |  | Payment Due Date :
| PO Box 48926 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMINIYAT MIDDLE EAST REAL ESTATE DEVELOPMENTS LLC
Oliver Keegan |  | Tore Zeidler |  | Dean Lander
Project Manager |  | Development Manager |  | Development Director
Ishan Garga |  | Mark Phoenix |  | Date
Director - Corporate Finance |  | Managing Director
OMNIYAT PROPERTIES SEVENTEEN LTD. approval to proceed the net amount certified for approval
Zainab T A M Ali
Authorized Signatory

## The Gemini (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Gemini, Business Bay Dubai UAE |  | Certificate No: | 014
|  |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Middle East Real Estate Developments LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Middle East Real Estate Developments LLC |  | Contract Start Date :
Date of Application:
Employer : | Omniyat Properties Ten Limited |  | Payment Due Date :
| PO Box 48926 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMNIYAT MIDDLE EAST REAL ESTATE DEVELOPMENTS LLC
Colin James |  | Joel Shearer |  | John Airey
Project Manager |  | Senior Development Manager |  | Development Director
Ishan Garga
Director - Corporate Finance
OMNIYAT PROPERTIES TEN LIMITED approval to proceed the net amount certified
Anthony Manning |  | Mark Phoenix |  | Date
Authorized Signatory |  | Authorized Signatory

## Opus Hotel (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Opus Boutique Hotel |  | Certificate No: | 014
| Business Bay Dubai UAE |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Asset Management LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Management LLC |  | Contract Start Date :
Date of Application:
Employer : | Opus HM Limited |  | Payment Due Date :
| PO Box 506503 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMNIYAT ASSET MANAGEMENT LLC
Joel Shearer
Senior Development Manager |  |  |  | Date
John Airey
Development Director |  |  |  | Date
OPUS HM LIMITED approval to proceed the net amount certified
Ishan Garga |  | Mark Phoenix
Authorized Signatory |  | Authorized Signatory |  | Date