## DAR Summary
Dar Al Rokham
2022-12-01
SN | Description | Amount | Previous Work Done - WFA | New Subcontract Amount - WFA | Previous | This Month | Cumulative
1 | Total for Guest Room Works | 14192642.75 | 11495377 | 2697265.75 | 2173860.8706 | 64027.8783 | 2237888.7489 | 459377.0011
| Subtotal 1 | 14192642.75 | 11495377 | 2697265.75 | 2173860.8706 | 64027.8783 | 2237888.7489 | 82.61%
WFA VARIATIONS
2 | Omit PS Package | -698968 | -698968 | 0 | 0 | 0 | 0
3 | Omit Tilling to balconies | -461231 | -461231 | 0 | 0 | 0 | 0
4 | Metal Frames in Guest Rooms | 1084943 | 1084943 | 0 | 0 | 0 | 0
5 | Stonework to Room Type 7A & 15A | 746070 | 0 | 746070 | 470738.56 | 67362.9 | 538101.46
6 | Corridor Works stone works | 1644447.65 | 835600 | 808847.65 | 726280.957 | 10249.3115 | 736530.2685
7 | Discount | -7905 | 0 | -7905 | -6085.4922 | -394.5704 | -6480.0627
| Subtotal 2 | 2307356.65 | 760344 | 1547012.65 | 1190934.0248 | 77217.6411 | 1268151.6658
VARIATIONS UNDER KCE
8 | AHK Balance Works - Resi Amenities |  |  | 617777 | 384864.0086 | 78510.6897 | 463374.6984
9 | Marble Floor at Corridor - GF |  |  | 5502.33 | 5502.33 | 0 | 5502.33
10 | Marble Architrave at Lift Lobby Lvl 7 - Lvl 27 Hotel |  |  | 58140 |  | 23256 | 23256
11 | Pink Onyx Cladding at Lvl 2 |  |  | 757050 |  | 0
12 | SS Strip |  |  | 21000 |  | 0 | 0
| Subtotal 2 |  |  | 623279.33 | 390366.3386 | 101766.6897 | 492133.0284
10 | MOS @ 75% |  | 132458 | -132458 | -105010.5484 | -4408.0754 | -109418.6237
| Subtotal 3 | 0 | 132458 | -132458 | -105010.5484 | -4408.0754 | -109418.6237
| TOTAL | 16499999.4 | 12388179 | 4111820.4 | 3650150.6857 | 238604.1337 | 3888754.8194
|  |  |  | KCE Claim | 4520429.78 | 91096.64 | 4611526.42
|  |  |  | Difference | -870279.0943 | 147507.4937 | -722771.6006

## Guest Room Summary
Dar Al Rakhom Guest Room Work Done Assessment
[12 empty] | Payment Upto End Of | 2022-12-01
Bill No. | Item No. | Description | Quantity | Unit | Unit Rate | Amount | Work Progress (%) |  |  | Total Amount |  |  | Note
[7 empty] | Previous | Current | Cummulative | Previous | Current | Cummulative
| 1 | PACKAGE 7 - STONE WORKS
Bill Of Quantities No. 01
01 |  | Unit Type 1A | 6 | Nos. | 42584.7 | 255508.2 | 99.09% | 0% | 99.09% | 253177.2839 | 0 | 253177.2839
Bill Of Quantities No. 02
02 |  | Unit Type 1B / 1C | 8 | Nos. | 42666.9 | 341335.2 | 99.58% | 0% | 99.58% | 339890.4865 | 0 | 339890.4865
Bill Of Quantities No. 03
03 |  | Unit Type 2A/2B/2C/2D (Mock-Up) | 44 | Nos. | 50610.4 | 2226857.6 | 99.32% | 0.162% | 99.48% | 2211700.5312 | 3607.562 | 2215308.0932
Bill Of Quantities No. 04
04 |  | Unit Type 2E/2F/2G/2H | 27 | Nos. | 52529.2 | 1418288.4 | 99.67% | 0% | 99.67% | 1413661.9855 | 0 | 1413661.9855
Bill Of Quantities No. 05
05 |  | Unit Type 3A/3B/3D/3E/3G (Mock-Up) | 39 | Nos. | 55461.9 | 2163014.1 | 98.9% | 0.169% | 99.07% | 2139313.4122 | 3656.5024 | 2142969.9146
Bill Of Quantities No. 06
06 |  | Unit Type 3C/3F | 18 | Nos. | 54801.72 | 986430.96 | 98.58% | 0.04363% | 98.62% | 972381.1731 | 430.4079 | 972811.581
Bill Of Quantities No. 07
07 |  | Unit Type 4A/4B | 5 | Nos. | 57500.75 | 287503.75 | 98.52% | 0% | 98.52% | 283240.4702 | 0 | 283240.4702
Bill Of Quantities No. 08
08 |  | Unit Type 5A | 9 | Nos. | 60409.1 | 543681.9 | 99.01% | 0% | 99.01% | 538310.2419 | 0 | 538310.2419
Bill Of Quantities No. 09
09 |  | Unit Type 6A | 5 | Nos. | 56443.1 | 282215.5 | 97.85% | 0% | 97.85% | 276149.9655 | 0 | 276149.9655
Bill Of Quantities No. 10
10 |  | Unit Type 8A | 5 | Nos. | 89984.3 | 449921.5 | 99.84% | 0% | 99.84% | 449184.3494 | 0 | 449184.3494
Bill Of Quantities No. 11
11 |  | Unit Type 9A | 2 | Nos. | 73372.75 | 146745.5 | 100% | 0% | 100% | 146745.5 | 0 | 146745.5
Bill Of Quantities No. 12
12 |  | Unit Type 9B | 2 | Nos. | 72328.85 | 144657.7 | 100% | 0% | 100% | 144657.7 | 0 | 144657.7
Bill Of Quantities No. 13
13 |  | Unit Type 10A | 5 | Nos. | 78477.69 | 392388.45 | 100% | 0% | 100% | 392388.45 | 0 | 392388.45
Bill Of Quantities No. 14
14 |  | Unit Type 10B | 3 | Nos. | 80238.59 | 240715.77 | 99.24% | 0% | 99.24% | 238886.6552 | 0 | 238884.4952
Bill Of Quantities No. 15
15 |  | Unit Type 11A/11B/11C/11D | 19 | Nos. | 82662.6 | 1570589.4 | 82.31% | 0.9348% | 83.24% | 1292718.7592 | 14681.7294 | 1307400.4887
Bill Of Quantities No. 16
16 |  | Unit Type 12A | 5 | Nos. | 96149 | 480745 | 98.7% | 0.8453% | 99.54% | 474480.3488 | 4063.9445 | 478544.2933
Bill Of Quantities No. 17
17 |  | Unit Type 13A | 1 | Nos. | 77622.56 | 77622.56 | 98.96% | 0% | 98.96% | 76815.5967 | 0 | 76815.5967
Bill Of Quantities No. 18
18 |  | Unit Type 14A | 4 | Nos. | 87188.85 | 348755.4 | 98.63% | 0.7999% | 99.43% | 343973.1611 | 2789.6394 | 346762.8005
Bill Of Quantities No. 19
19 |  | Unit Type 16A | 3 | Nos. | 54490.71 | 163472.13 | 95.44% | 0.4199% | 95.86% | 156011.0718 | 686.4267 | 156697.4984
Bill Of Quantities No. 20
20 |  | Unit Type 19A | 6 | Nos. | 60833.9 | 365003.4 | 90.87% | 9.13% | 100% | 324073.0307 | 33326.3762 | 365003.4
Bill Of Quantities No. 21
21 |  | Balconies | 1 | Nos. |  | Included
Bill Of Quantities No. 22
22 |  | Stone Works With Provisional Sum
| A | Add Provisional Sum for remaining 9no. guestrooms |  |  |  | 698968 | 100% | 0% | 100% | 698968 | 0 | 698968
Preliminaries
|  | Including financial cost, shop drawings, site administration, stone sample test, health and safety. | 1 |  | L.S.
|  | Preliminaries (Mobilization -10%) |  |  |  | 85000 | 100% | 0% | 100% | 85000 | 0 | 85000
|  | Preliminaries (Time related - 30%) |  |  |  | 255000 | 100% | 0% | 100% | 255000 | 0 | 255000
|  | Preliminaries (Progress Related - 60%) |  |  |  | 510000 | 96.82% | 0.4908% | 97.31% | 493768.8189 | 2503.1112 | 496271.9301
|  | 2% Attick Stock / Spares | 1 |  | L.S. | 108222.33 | 0% | 0% | 0% | 0 | 0 | 0
|  | Special Discount |  |  |  | -350000 | 96.82% | 0.4908% | 97.31% | -338860.9542 | -1717.8214 | -340578.7756
|  | Total Amount Works (A) |  |  |  | 14192642.75 |  |  |  | 13661636.0376 | 71629.7114 | 13733265.7489
|  | Metal Frame Variation as per the ASI Rates |  |  |  | 1084943 | 100% |  | 100% | 1084943 | 0 | 1084943
|  | Total Amount Variation (B) | [7 empty] | 1084943 | 0 | 1084943
|  | TOTAL AMOUNT FOR GUEST ROOM WORKS | [7 empty] | 14746579.0376 | 71629.7114 | 14818208.7489
-2.16

## KCE VO Schedule (hidden)
PROJECT: DORCHESTER HOTEL AND RESIDENCES
VARIATION SHEDULE - M/S DAR AL ROKHAM | [10 empty] | 2023-03-22
Item No. | WA Ref. | Description of Variation | SUBMITTED (AED) |  | KCE INITIAL ASSESSEMENT | STATUS | KCE ASSESSED |  | Difference | Action By | Remarks | Previous |  | This Month |  | Cumulative
|  |  |  | TOTAL AMOUNT (AED) |  |  | ASSESSED (AED) | AGREED (AED) |  |  |  | % | Amount | % | Amount | % | Amount
Main Contract VO's
1 | PS045 | Supply & Install Marble to Lift Lobbies at Hotel L7-L27 | 58140 | 58140 | 58140 |  | 58140 |  | PS046 | Supply & Install Marble to Lift Lobbies at Hotel L7-L28
2 | PS045 R1 | Supply & Fixing of Pink Onyx at Hotel L2 Entrance | 757050 | 757050 | 757050 |  | 757050 |  | PS045 R2 | Supply & Fixing of Pink Onyx at Hotel L2 Entrance | Competitive price in comparison with Reem.
3 | PS042 | Stone Works - AHK Balance Work | 617777.4 | 617777.4 |  |  | 617777.4 | 617777.4 | PS043 | Stone Works - AHK Balance Work | Lump sum and based on Original Scope with AHK | 42.45% | 262256.0049 | 32.56% | 201118.6935 | 75.01% | 463374.6984
|  | Total Variation Amount ( AED ) | 1432967.4 | 1432967.4 | 815190 | 0 | 1432967.4 | 617777.4

## Corridor
BILL OF QUANTITIES - Guestroom Corridor & Lift Lobby - Dar Al Rokham
Bill No. | Item No. | Description | Unit | Quantity | Material | Thick | Supply Rate | Fixing Rate | Unit Rate | Amount | Progress | Previous | This Month | Progress Amount
| A | HOTEL GUESTROOM CORRIDOR & LIFT LOBBY
Wall Finishes
Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche etc and the like all in accordance with drawings and specifications.
| 1 | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] at door frame at guest corridor, Lvl 7 to Lvl 27 | m2 | 766 |  |  | - | - | - | Deleted-as discussed in meeting
| 2 | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] at lift lobby, guest corridor, Lvl 7 to Lvl 27 | m2 | 302.35 | Volakas | 20 | 422 | 327 | 749 | 226460.15 | 95% | 212872.541 | 2264.6015 | 215137.1425 | 0.94
| 2A | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] show case overall size 3.4 x 2.5 m at guest corridor, Lvl 7 to Lvl 27 [ Inc. metal framing] | M2 | 153 | Volakas | 20 | 422 | 731 | 1153 | 176409 | 95% | 165824.46 | 1764.09 | 167588.55 | 0.94
| 2.A. 1 | Extra Over for Supply and Fix of Steel Frame for projected 2 Sides cladding. Q'ty = 18 levels x 2 sides = 36 No ( lvl 19 excluded) | Set | 36 | Steel frame | [7 empty] | 0
| 3 | Supply and installation of 20mm thk, projected stone cladding ST-06 [ Volakas Marble ] at guest corridor, Lvl 7 to Lvl 27 [ Inc. metal framing] | m2 | 612 | Volakas | 20 | 422 | 731 | 1153 | 705636 | 99.1% | 699285.276 | 0 | 699285.276 | 0.991
| 3.a | Extra Over for Supply and Fix of Steel Frame | Set | 417 | Steel frame | [7 empty] | 0
| 4 | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] at fire door at lift lobby, guest corridor, Lvl 7 to Lvl 27 | m2 | 153 | Volakas | 20 | - | - | - | Omitted From DAR Scope |  |  | 0
| 5 | Supply and installation of ST-06 [ Volakas Marble ] marble cladding to the fire door, Size .998+.998 x 2.4m at lift lobby, guest corridor.Lvl 7 to Lvl 27 | No | 19 | Volakas | 20 | - | - | - | Cancelled |  |  | 0
| 6 | 85mm wide x 5mm thick Brass strip insert in brushed finish with top layer brass coat (HTL-ME-01) | mr | 2210.1 | Brass | 5 | - | - | - | NIC-By Others |  |  | 0
| 7 | Supply and installation of architrave ST-03 [ Arbsecato Marble ], size 185+40+110 x 20mm at lift cabin, guest corridor | mr | 38 | Arabescato | 20 | - | - | - | Under Main Lobby Tender |  |  | 0
| 8 | Supply and installation of soffit ST-06 [ Volakas Marble ], size 150 x 20mm at guest corridor, Lvl 7 to Lvl 27 | mr | 240.6 | Volakas | 20 | 121 | 40 | 161 | Metal Soffit By Other |  |  | 0
| 9 | Supply and installation of soffit ST-06 [ Volakas Marble ], size 190 x 20mm at lift lobby, guest corridor, Lvl 7 to Lvl 27 | mr | 126 | Volakas | 20 | 126 | 51 | 177 | 22302 | 95% | 20963.88 | 223.02 | 21186.9 | 0.94
| 10 | Supply and installation of architrave ST-06 [ Volakas Marble ], size 236+30+236 x 20mm at fire door at lift lobby, guest corridor, Lvl 7 to Lvl 27 | mr | - | Volakas | 20 | - | - | - | Omitted From DAR Scope
Floor Finishes
Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications.
| 11 | Supply and installation of 20mm thk, stone flooring, ST-06 [ Volakas Marble ] at lift lobby, guest corridor, Lvl 7 to Lvl 27 | m2 | 105.65 | Volakas | 20 | 415 | 215 | 630 | 66559.5 | 100% | 66559.5 | 0 | 66559.5 | 1
| 12 | 7mm wide x 5mm thick Brass strip insert in brushed finish with top layer brass coat (HTL-ME-04) | mr | 357 | Brass | 5 | 0 | 60 | 60 | 21420 | 90% | 13280.4 | 5997.6 | 19278 | 0.62
| 13 | Supply and installation of 20mm thk, stone flooring, ST-04 [ Griggio Carnico Marble ] and Border, ST-03 [ Arbsecato Marble ], Size 1.80x1.60m at lift cabin, guest corridor | No | 6 | Grigio Carnico, Arabescato | 20 | - | - | - | Under Main Lobby Tender
Skirting
Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing,
polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications.
| 14 | Supply and installation of skirting ST-06 [ Volakas Marble ], size 150+55 x 20mm at guest corridor, Lvl 7 to Lvl 27 [ Back support considered ] | mr | 1681.9 | Volakas | 20 | 130 | 100 | 230 | 386837 | 90% | 348153.3 | 0 | 348153.3 | 0.9
| 15 | Supply and installation of skirting ST-06 [ Volakas Marble ], size 150+55 x 20mm at lift lobby, guest corridor, Lvl 7 to Lvl 27 [ Back support considered ] | mr | 168.8 | Volakas | 20 | 130 | 100 | 230 | 38824 | 90% | 34941.6 | 0 | 34941.6 | 0.9
| 16 | Supply and installation of skirting ST-03 [ Arbsecato Marble ], size 150+105 x 20mm at lift cabin, guest corridor [ Back support considered ] | mr | 29 | Arabescato | 20 | - | - | - | Under Main Lobby Tender
Threshold
Supply and fixing of Stone Threshold, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications.
| 17 | Supply and installation of threshold ST-06 [ Volakas Marble ], size 75 x 20mm at guest corridor, Lvl 7 to Lvl 27 | mr | 349.5 | Volakas | 20 | 63 | 28 | 91 | Unit rate Only
|  | Total Amount in AED | [7 empty] | 1644447.65 | 95.6% | 1561880.957 | 10249.3115 | 1572130.2685
1644447.65

## Guest Rooms
[18 empty] | Payment Upto End Of |  | 44896
BILL OF QUANTITIES
Bill No. | Item No. | Description | Qty / Room | Unit | No Of Rooms | Material | Thick | Supply Rate | Fixing Rate | Unit Rate | Amount | Amount | This month Qty | Previous | Current | Cummulative | Total Amount |  |  | Note
[17 empty] | Previous | Current | Cummulative
| 1 | PACKAGE 7 - STONE WORKS
Floor Finishes
Stone flooring fixed with approved tile adhesive and
bedding in cement mortar cutting and cleaning, etc.,
complete as per drawings and specification (Screed
measured separately)
DELUXE ROOM
01 |  | TYPE -01A (8 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
01 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.4 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1760 | 10560 | 0 | 100% | 0% | 100% | 10560 | 0 | 10560
01 | B | 20mm thick polished Crystal White, maximum 145mm width border. | 1.9 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 927.2 | 5563.2 | 0 | 100% | 0% | 100% | 5563.2 | 0 | 5563.2
01 | C | 7 x 5mm Brass strip insert in brushed finish . | 10.25 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 584.25 | 3505.5 |  | 100% | 0% | 100% | 3505.5 | 0 | 3505.5
01 | D | 215mm wide x 900mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 97 | 35 | 132 | 132 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
Bedroom
01 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.9 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1960 | 11760 | 0 | 100% | 0% | 100% | 11760 | 0 | 11760
01 | F | 20mm thick polished Crystal White, cut to size. | 1.8 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 878.4 | 5270.4 | 0 | 100% | 0% | 100% | 5270.4 | 0 | 5270.4
01 | G | 20mm thick polished Crystal White, average of 125mm width border. | 2.8 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1366.4 | 8198.4 | 0 | 100% | 0% | 100% | 8198.4 | 0 | 8198.4
01 | H | 7 x 5mm Brass strip insert in brushed finish . | 17 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 969 | 5814 |  | 100% | 0% | 100% | 5814 | 0 | 5814
01 | J | 7 x 5mm Brass strip insert in brushed finish . | 14.35 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 817.95 | 4907.7 |  | 100% | 0% | 100% | 4907.7 | 0 | 4907.7
01 | K | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 6 | Crystal White | 20 | 155 | 62 | 217 | 217 | 1302 | 0 | 100% | 0% | 100% | 1302 | 0 | 1302
Bathroom
01 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.1 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1240 | 7440 | 0 | 100% | 0% | 100% | 7440 | 0 | 7440
01 | M | 20mm thick polished Crystal White, average 143mm width border. | 1.3 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 634.4 | 3806.4 | 0 | 100% | 0% | 100% | 3806.4 | 0 | 3806.4
01 | N | 7 x 5mm Brass strip insert in brushed finish . | 7.8 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 444.6 | 2667.6 |  | 100% | 0% | 100% | 2667.6 | 0 | 2667.6
01 | P | Threshold (20mm thick); 220mm wide x 945mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 105 | 39 | 144 | 144 | 864 | 0 | 100% | 0% | 100% | 864 | 0 | 864
Shower
01 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.5 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1000 | 6000 | 0 | 100% | 0% | 100% | 6000 | 0 | 6000
01 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
Toilet
01 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.9 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 360 | 2160 | 0 | 100% | 0% | 100% | 2160 | 0 | 2160
01 | E | 20mm thick polished Crystal White, average of 101mm width border. | 0.55 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1610.4 | 0 | 100% | 0% | 100% | 1610.4 | 0 | 1610.4
01 | F | 7 x 5mm Brass strip insert in brushed finish . | 4 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 228 | 1368 |  | 100% | 0% | 100% | 1368 | 0 | 1368
01 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
Balcony Floor Finishes
01 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 7 | M2 | 6 | PC Rate | 20 | 50 | 100 | 150 | 1050 | 6300 | 0 | 100% | 0% | 100% | 6300 | 0 | 6300
Wall Finishes
Bathroom
01 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.2 | Lm | 6 | Crystal White | 20 | 86 | 48 | 134 | 428.8 | 2572.8 | 0 | 100% | 0% | 100% | 2572.8 | 0 | 2572.8
01 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 6.5 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 4082 | 24492 | 0 | 100% | 0% | 100% | 24492 | 0 | 24492
Shower
01 | K | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.75 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 9263 | 55578 | 0 | 100% | 0% | 100% | 55578 | 0 | 55578
01 | L | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.5 | Lm | 6 | Crystal White | 20 | 79 | 43 | 122 | 793 | 4758 | 0 | 100% | 0% | 100% | 4758 | 0 | 4758
Toilet
01 | M | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 4.5 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 2826 | 16956 | 0 | 100% | 0% | 100% | 16956 | 0 | 16956
01 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.15 | Lm | 6 | Crystal White | 20 | 79 | 43 | 122 | 506.3 | 3037.8 | 0 | 100% | 0% | 100% | 3037.8 | 0 | 3037.8
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
01 | B | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 7332 | 0 | 87.5% | 0% | 87.5% | 6415.5 | 0 | 6415.5
01 | C | Bathroom : 220mm wide; total size of 945 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 644 | 291 | 935 | 935 | 5610 | 0 | 87.5% | 0% | 87.5% | 4908.75 | 0 | 4908.75
01 | D | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 6 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 11568 | 0 | 100% | 0% | 100% | 11568 | 0 | 11568
Joinery Items
Foyer
01 | E | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 700 x 1430mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 457 | 255 | 712 | 712 | 4272 | 0 | 87.5% | 0% | 87.5% | 3738 | 0 | 3738
Bathroom
01 | F | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 12474 | 0 | 100% | 0% | 100% | 12474 | 0 | 12474
Shower
01 | G | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 570 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 574 | 281 | 855 | 855 | 5130 | 0 | 100% | 0% | 100% | 5130 | 0 | 5130
01 | H | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 985mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 240 | 100 | 340 | 340 | 2040 | 0 | 100% | 0% | 100% | 2040 | 0 | 2040
01 | J | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 6 | Volakas | 20 | 44 | 12 | 56 | 112 | 672 | 0 | 100% | 0% | 100% | 672 | 0 | 672
Toilet
01 | A | Cistern Top : Supply and installation of 20mm thick polished Volakas, 260mm W x 900mm length, pencil edge finish. | 1 | No | 6 | Volakas | 20 | 109 | 55 | 164 | 164 | 984 | 0 | 100% | 0% | 100% | 984 | 0 | 984
01 | B | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 2 | No | 6 | Volakas | 20 | 25 | 5 | 30 | 60 | 360 | 0 | 100% | 0% | 100% | 360 | 0 | 360
01 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 118 | 59 | 177 | 177 | 1062 | 0 | 87.5% | 0% | 87.5% | 929.25 | 0 | 929.25
Miscellaneous Items
01 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 74 | M2 | 6 |  |  | 0 | 8 | 8 | 592 | 3552 |  | 99.09% | 0% | 99.09% | 3519.5963 | 0 | 3519.5963
01 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 32 | M2 | 6 |  |  | 0 | 8 | 8 | 256 | 1536 |  | 99.09% | 0% | 99.09% | 1521.9876 | 0 | 1521.9876
01 |  | Total Amount for TYPE -01A | [14 empty] | 253177.2839 | 0 | 253177.2839
02 |  | TYPE -01B & 01C (6 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
02 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.4 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1760 | 14080 | 0 | 100% | 0% | 100% | 14080 | 0 | 14080
02 | B | 20mm thick polished Crystal White, maximum 130mm width border. | 1.9 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 927.2 | 7417.6 | 0 | 100% | 0% | 100% | 7417.6 | 0 | 7417.6
02 | C | 7 x 5mm Brass strip insert in brushed finish . | 10.25 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 584.25 | 4674 |  | 100% | 0% | 100% | 4674 | 0 | 4674
02 | Add | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 8 | Crystal White | 20 | 123 | 48 | 171 | 171 | 1368 | 0 | 100% | 0% | 100% | 1368 | 0 | 1368
Bedroom
02 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.9 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1960 | 15680 | 0 | 100% | 0% | 100% | 15680 | 0 | 15680
02 | E | 20mm thick polished Crystal White, average of 157mm width border. | 2.8 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 1366.4 | 10931.2 | 0 | 100% | 0% | 100% | 10931.2 | 0 | 10931.2
02 | F | 7 x 5mm Brass strip insert in brushed finish . | 17 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 969 | 7752 |  | 100% | 0% | 100% | 7752 | 0 | 7752
02 | G | 7 x 5mm Brass strip insert in brushed finish . | 14.35 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 817.95 | 6543.6 |  | 100% | 0% | 100% | 6543.6 | 0 | 6543.6
02 | H | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 8 | Crystal White | 20 | 155 | 62 | 217 | 217 | 1736 | 0 | 100% | 0% | 100% | 1736 | 0 | 1736
02 | Add | 20mm thick polished CrystalWhite, cut to size (HTL-ST-01) | 1.8 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 878.4 | 7027.2 | 0 | 100% | 0% | 100% | 7027.2 | 0 | 7027.2
Bathroom
02 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.1 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1240 | 9920 | 0 | 100% | 0% | 100% | 9920 | 0 | 9920
02 | K | 20mm thick polished Crystal White, average 149mm width border. | 1.45 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 707.6 | 5660.8 | 0 | 100% | 0% | 100% | 5660.8 | 0 | 5660.8
02 | L | 7 x 5mm Brass strip insert in brushed finish . | 7.8 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 444.6 | 3556.8 |  | 100% | 0% | 100% | 3556.8 | 0 | 3556.8
02 | M | Threshold (20mm thick); 220mm wide x 945mm length polished Crystal White. | 1 | No | 8 | Crystal White | 20 | 105 | 39 | 144 | 144 | 1152 | 0 | 100% | 0% | 100% | 1152 | 0 | 1152
Shower
02 | N | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.5 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1000 | 8000 | 0 | 100% | 0% | 100% | 8000 | 0 | 8000
02 | Q | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 8 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1088 | 0 | 100% | 0% | 100% | 1088 | 0 | 1088
Toilet
02 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.9 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 360 | 2880 | 0 | 100% | 0% | 100% | 2880 | 0 | 2880
02 | B | 20mm thick polished Crystal White, average of 109mm width border. | 0.55 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 2147.2 | 0 | 100% | 0% | 100% | 2147.2 | 0 | 2147.2
02 | C | 7 x 5mm Brass strip insert in brushed finish . | 4 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 228 | 1824 |  | 100% | 0% | 100% | 1824 | 0 | 1824
02 | D | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 8 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1088 | 0 | 100% | 0% | 100% | 1088 | 0 | 1088
Balcony Floor Finishes
02 |  | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 7 | M2 | 8 | PC Rate | 20 | 50 | 100 | 150 | 1050 | 8400 | 0 | 100% | 0% | 100% | 8400 | 0 | 8400
Wall Finishes
Bathroom
02 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.2 | Lm | 8 | Crystal White | 20 | 86 | 48 | 134 | 428.8 | 3430.4 | 0 | 100% | 0% | 100% | 3430.4 | 0 | 3430.4
02 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 6.5 | M2 | 8 | Volakas | 20 | 406 | 222 | 628 | 4082 | 32656 | 0 | 100% | 0% | 100% | 32656 | 0 | 32656
Shower
02 | F | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.75 | M2 | 8 | Volakas | 20 | 406 | 222 | 628 | 9263 | 74104 | 0 | 100% | 0% | 100% | 74104 | 0 | 74104
02 | G | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.5 | Lm | 8 | Crystal White | 20 | 79 | 43 | 122 | 793 | 6344 | 0 | 100% | 0% | 100% | 6344 | 0 | 6344
Toilet
02 | H | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 4.5 | M2 | 8 | Volakas | 20 | 406 | 222 | 628 | 2826 | 22608 | 0 | 100% | 0% | 100% | 22608 | 0 | 22608
02 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.15 | Lm | 8 | Crystal White | 20 | 79 | 43 | 122 | 506.3 | 4050.4 | 0 | 100% | 0% | 100% | 4050.4 | 0 | 4050.4
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
02 | A | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 8 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 9776 | 0 | 100% | 0% | 100% | 9776 | 0 | 9776
02 | B | Bathroom : 220mm wide; total size of 945 x 2430mm high. | 1 | No | 8 | Crystal White | 20 | 644 | 291 | 935 | 935 | 7480 | 0 | 100% | 0% | 100% | 7480 | 0 | 7480
02 | C | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 8 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 15424 | 0 | 100% | 0% | 100% | 15424 | 0 | 15424
Joinery Items
Foyer
02 | D | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 700 x 1430mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 8 | Crystal White | 20 | 457 | 255 | 712 | 712 | 5696 | 0 | 100% | 0% | 100% | 5696 | 0 | 5696
Bathroom
02 | E | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 8 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 16632 | 0 | 100% | 0% | 100% | 16632 | 0 | 16632
Shower
02 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 570 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 8 | Volakas | 20 | 574 | 281 | 855 | 855 | 6840 | 0 | 100% | 0% | 100% | 6840 | 0 | 6840
02 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 985mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 8 | Volakas | 20 | 240 | 100 | 340 | 340 | 2720 | 0 | 100% | 0% | 100% | 2720 | 0 | 2720
02 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 8 | Volakas | 20 | 44 | 12 | 56 | 112 | 896 | 0 | 100% | 0% | 100% | 896 | 0 | 896
Toilet
02 | J | Cistern Top : Supply and installation of 20mm thick polished Volakas, 260mm W x 900mm length, pencil edge finish. | 1 | No | 8 | Volakas | 20 | 109 | 55 | 164 | 164 | 1312 | 0 | 100% | 0% | 100% | 1312 | 0 | 1312
02 | K | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 8 | Volakas | 20 | 25 | 5 | 30 | 30 | 240 | 0 | 100% | 0% | 100% | 240 | 0 | 240
02 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 8 | Crystal White | 20 | 118 | 59 | 177 | 177 | 1416 |  |  |  |  | 0 | 0 | 0
Miscellaneous Items
02 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 74 | M2 | 8 |  |  | 0 | 8 | 8 | 592 | 4736 |  | 99.58% | 0% | 99.58% | 4715.9547 | 0 | 4715.9547
02 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 32 | M2 | 8 |  |  | 0 | 8 | 8 | 256 | 2048 |  | 99.58% | 0% | 99.58% | 2039.3318 | 0 | 2039.3318
02 |  | Total Amount for TYPE -01C | [14 empty] | 339890.4865 | 0 | 339890.4865
03 |  | TYPE -2A/2B/2C/2D (44 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
03 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 7.2 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 2880 | 126720 | 0 | 100% | 0% | 100% | 126720 | 0 | 126720
03 | B | 20mm thick polished Crystal White, maximum 160mm width border. | 2.05 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 1000.4 | 44017.6 | 0 | 100% | 0% | 100% | 44017.6 | 0 | 44017.6
03 | C | Extra-over to 7 x 5mm brass strips. | 11.6 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 661.2 | 29092.8 |  | 97.73% | 2.273% | 100% | 28431.6 | 661.2 | 29092.8
03 | D | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 44 | Crystal White | 20 | 123 | 48 | 171 | 171 | 7524 | 0 | 100% | 0% | 100% | 7524 | 0 | 7524
Bedroom
03 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.45 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 2180 | 95920 | 0 | 100% | 0% | 100% | 95920 | 0 | 95920
03 | F | 20mm thick polished Crystal White, cut to size. | 2.2 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 1073.6 | 47238.4 | 0 | 100% | 0% | 100% | 47238.4 | 0 | 47238.4
03 | G | 20mm thick polished Crystal White, average of 155mm width border. | 3.3 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 1610.4 | 70857.6 | 0 | 100% | 0% | 100% | 70857.6 | 0 | 70857.6
03 | H | Extra-over to 7 x 5mm brass strips. | 20.1 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 1145.7 | 50410.8 |  | 97.73% | 2.273% | 100% | 49265.1 | 1145.7 | 50410.8
03 | J | Extra-over to 7 x 5mm brass strips. | 17.6 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 1003.2 | 44140.8 |  | 97.73% | 2.273% | 100% | 43137.6 | 1003.2 | 44140.8
03 | K | Threshold (20mm thick polished Crystal White); 310mm wide x 1115mm length. | 1.1 | Lm | 44 | Crystal White | 20 | 158 | 64 | 222 | 244.2 | 10744.8 | 0 | 100% | 0% | 100% | 10744.8 | 0 | 10744.8
Bathroom
03 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.7 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 1880 | 82720 | 0 | 100% | 0% | 100% | 82720 | 0 | 82720
03 | M | 20mm thick polished Crystal White, average 140mm width border. | 1.55 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 756.4 | 33281.6 | 0 | 100% | 0% | 100% | 33281.6 | 0 | 33281.6
03 | N | Extra-over to 7 x 5mm brass strips. | 9.7 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 552.9 | 24327.6 |  | 97.73% | 2.273% | 100% | 23774.7 | 552.9 | 24327.6
03 |  | Threshold (20mm thick); 300mm wide x 945mm length polished Crystal White | 1 | Lm | 44 | Crystal White | 20 | 132 | 53 | 185 | 185 | 8140 | 0 | 100% | 0% | 100% | 8140 | 0 | 8140
Shower
03 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.2 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 38720 | 0 | 100% | 0% | 100% | 38720 | 0 | 38720
03 | C | Threshold (20mm thick); 235mm wide x 830mm length and 40mm high fascia, polished Crystal White | 1 | No | 44 | Crystal White | 20 | 107 | 43 | 150 | 150 | 6600 | 0 | 100% | 0% | 100% | 6600 | 0 | 6600
Toilet
03 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.6 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 240 | 10560 | 0 | 100% | 0% | 100% | 10560 | 0 | 10560
03 | E | 20mm thick polished Crystal White, average of 110mm width border. | 0.45 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 9662.4 | 0 | 100% | 0% | 100% | 9662.4 | 0 | 9662.4
03 | F | Extra-over to 7 x 5mm brass strips. | 3 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 171 | 7524 |  | 97.73% | 2.273% | 100% | 7353 | 171 | 7524
03 |  | Threshold (20mm thick); 235mm wide x 830mm length, polished Crystal White | 1 | No | 44 | Crystal White | 20 | 98 | 37 | 135 | 135 | 5940 | 0 | 100% | 0% | 100% | 5940 | 0 | 5940
Balcony Floor Finishes
03 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10.35 | M2 | 44 | PC Rate | 20 | 50 | 100 | 150 | 1552.5 | 68310 | 0 | 100% | 0% | 100% | 68310 | 0 | 68310
Wall Finishes
Bathroom
03 | J | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.9 | M2 | 44 | Volakas | 20 | 406 | 222 | 628 | 9357.2 | 411716.8 | 0 | 100% | 0% | 100% | 411716.8 | 0 | 411716.8
03 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.7 | Lm | 44 | Crystal White | 20 | 86 | 48 | 134 | 629.8 | 27711.2 | 0 | 100% | 0% | 100% | 27711.2 | 0 | 27711.2
Shower
03 | L | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 12.65 | M2 | 44 | Volakas | 20 | 406 | 222 | 628 | 7944.2 | 349544.8 | 0 | 100% | 0% | 100% | 349544.8 | 0 | 349544.8
03 | M | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.55 | Lm | 44 | Crystal White | 20 | 79 | 43 | 122 | 677.1 | 29792.4 | 0 | 100% | 0% | 100% | 29792.4 | 0 | 29792.4
Toilet
03 | A | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 3.35 | M2 | 44 | Volakas | 20 | 406 | 222 | 628 | 2103.8 | 92567.2 | 0 | 100% | 0% | 100% | 92567.2 | 0 | 92567.2
03 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.1 | Lm | 44 | Crystal White | 20 | 79 | 43 | 122 | 378.2 | 16640.8 | 0 | 100% | 0% | 100% | 16640.8 | 0 | 16640.8
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
03 | C | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 44 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 53768 | 0 | 93.18% | 0% | 93.18% | 50102 | 0 | 50102
03 | D | Bathroom : 250mm wide; total size of 945 x 2430mm high. | 1 | No | 44 | Crystal White | 20 | 699 | 329 | 1028 | 1028 | 45232 | 0 | 93.18% | 0% | 93.18% | 42148 | 0 | 42148
03 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 44 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 84832 | 0 | 95.45% | 0% | 95.45% | 80976 | 0 | 80976
Joinery Items
Foyer
03 | F | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 44 | Crystal White | 20 | 118 | 59 | 177 | 177 | 7788 | 0 | 90.91% | 0% | 90.91% | 7080 | 0 | 7080
03 | G | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 680 x 615mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 44 | Crystal White | 20 | 217 | 108 | 325 | 325 | 14300 | 0 | 100% | 0% | 100% | 14300 | 0 | 14300
Toilet
03 | H | Cistern Top : Supply and installation of 20mm thick polished Volakas, 245mm W x 950mm length, pencil edge finish. | 1 | No | 44 | Volakas | 20 | 110 | 55 | 165 | 165 | 7260 | 0 | 100% | 0% | 100% | 7260 | 0 | 7260
03 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 44 | Volakas | 20 | 25 | 5 | 30 | 30 | 1320 | 0 | 100% | 0% | 100% | 1320 | 0 | 1320
Shower
03 | K | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 740 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 44 | Volakas | 20 | 726 | 355 | 1081 | 1081 | 47564 | 0 | 100% | 0% | 100% | 47564 | 0 | 47564
03 | A | Bench : Supply and installation of 20mm thick polished Volakas, 410mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 44 | Volakas | 20 | 278 | 119 | 397 | 397 | 17468 | 0 | 100% | 0% | 100% | 17468 | 0 | 17468
03 | B | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 44 | Volakas | 20 | 44 | 12 | 56 | 112 | 4928 | 0 | 100% | 0% | 100% | 4928 | 0 | 4928
Bathroom
03 | C | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 44 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 91476 | 0 | 100% | 0% | 100% | 91476 | 0 | 91476
Sanitaryware - Stoneworks
03 | D | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 44 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 55088 | 0 | 100% | 0% | 100% | 55088 | 0 | 55088
Miscellaneous Items
03 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 89 | M2 | 44 |  |  | 0 | 8 | 8 | 712 | 31328 |  | 99.32% | 0.162% | 99.48% | 31114.7665 | 50.7521 | 31165.5186
03 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 40 | M2 | 44 |  |  | 0 | 8 | 8 | 320 | 14080 |  | 99.32% | 0.162% | 99.48% | 13984.1647 | 22.8099 | 14006.9747
03 |  | Total Amount for TYPE -2A/2B/2C/2D | [14 empty] | 2211700.5312 | 3607.562 | 2215308.0932
04 |  | TYPE -2E/2F/2G/2H (27 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
04 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 7 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 2800 | 75600 | 0 | 100% | 0% | 100% | 75600 | 0 | 75600
04 | B | 20mm thick polished Crystal White, maximum 135mm width border. | 2.05 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 1000.4 | 27010.8 | 0 | 100% | 0% | 100% | 27010.8 | 0 | 27010.8
04 | C | 7 x 5mm Brass strip insert in brushed finish . | 11.6 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 661.2 | 17852.4 |  | 100% | 0% | 100% | 17852.4 | 0 | 17852.4
04 | D | 215mm wide x 900mm length polished Crystal White. | 1 | No | 27 | Crystal White | 20 | 97 | 35 | 132 | 132 | 3564 | 0 | 100% | 0% | 100% | 3564 | 0 | 3564
Bedroom
04 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.1 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 2040 | 55080 | 0 | 100% | 0% | 100% | 55080 | 0 | 55080
04 | F | 20mm thick polished Crystal White, cut to size. | 2.5 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 1220 | 32940 | 0 | 100% | 0% | 100% | 32940 | 0 | 32940
04 | G | 20mm thick polished Crystal White, average of 130mm width border. | 3.15 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 1537.2 | 41504.4 | 0 | 100% | 0% | 100% | 41504.4 | 0 | 41504.4
04 | H | 7 x 5mm Brass strip insert in brushed finish . | 19.3 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 1100.1 | 29702.7 |  | 100% | 0% | 100% | 29702.7 | 0 | 29702.7
04 | J | 7 x 5mm Brass strip insert in brushed finish . | 16.8 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 957.6 | 25855.2 |  | 100% | 0% | 100% | 25855.2 | 0 | 25855.2
04 | K | Threshold (20mm thick polished Crystal White); 215mm wide x 1115mm length. | 1 | Lm | 27 | Crystal White | 20 | 122 | 44 | 166 | 166 | 4482 | 0 | 100% | 0% | 100% | 4482 | 0 | 4482
Bathroom
04 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.6 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 1840 | 49680 | 0 | 100% | 0% | 100% | 49680 | 0 | 49680
04 | M | 20mm thick polished Crystal White, average 130mm width border. | 1.5 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 732 | 19764 | 0 | 100% | 0% | 100% | 19764 | 0 | 19764
04 | N | 7 x 5mm Brass strip insert in brushed finish . | 9.6 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 547.2 | 14774.4 |  | 100% | 0% | 100% | 14774.4 | 0 | 14774.4
04 | P | Threshold (20mm thick); 250mm wide x 945mm length polished Crystal White. | 1 | Lm | 27 | Crystal White | 20 | 116 | 44 | 160 | 160 | 4320 | 0 | 100% | 0% | 100% | 4320 | 0 | 4320
Shower
04 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.2 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 23760 | 0 | 100% | 0% | 100% | 23760 | 0 | 23760
04 | C | Threshold (20mm thick); 235mm wide x 860mm length and 40mm high fascia, polished Crystal White | 1 | No | 27 | Crystal White | 20 | 112 | 44 | 156 | 156 | 4212 | 0 | 100% | 0% | 100% | 4212 | 0 | 4212
Toilet
04 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.2 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 480 | 12960 | 0 | 100% | 0% | 100% | 12960 | 0 | 12960
04 | E | 20mm thick polished Crystal White, average of 127mm width border. | 0.6 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 292.8 | 7905.6 | 0 | 100% | 0% | 100% | 7905.6 | 0 | 7905.6
04 | F | 7 x 5mm Brass strip insert in brushed finish . | 4.4 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 250.8 | 6771.6 |  | 100% | 0% | 100% | 6771.6 | 0 | 6771.6
04 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 27 | Crystal White | 20 | 99 | 37 | 136 | 136 | 3672 | 0 | 100% | 0% | 100% | 3672 | 0 | 3672
Balcony Floor Finishes
04 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10.35 | M2 | 27 | PC Rate | 20 | 50 | 100 | 150 | 1552.5 | 41917.5 | 0 | 100% | 0% | 100% | 41917.5 | 0 | 41917.5
Wall Finishes
Bathroom
04 | J | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.9 | M2 | 27 | Volakas | 20 | 406 | 222 | 628 | 9357.2 | 252644.4 | 0 | 100% | 0% | 100% | 252644.4 | 0 | 252644.4
04 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.8 | Lm | 27 | Crystal White | 20 | 86 | 48 | 134 | 643.2 | 17366.4 | 0 | 100% | 0% | 100% | 17366.4 | 0 | 17366.4
Shower
04 | L | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.95 | M2 | 27 | Volakas | 20 | 406 | 222 | 628 | 8760.6 | 236536.2 | 0 | 100% | 0% | 100% | 236536.2 | 0 | 236536.2
04 | M | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.1 | Lm | 27 | Crystal White | 20 | 79 | 43 | 122 | 744.2 | 20093.4 | 0 | 100% | 0% | 100% | 20093.4 | 0 | 20093.4
Toilet
04 | A | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 4.9 | M2 | 27 | Volakas | 20 | 406 | 222 | 628 | 3077.2 | 83084.4 | 0 | 100% | 0% | 100% | 83084.4 | 0 | 83084.4
04 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 27 | Crystal White | 20 | 79 | 43 | 122 | 549 | 14823 | 0 | 100% | 0% | 100% | 14823 | 0 | 14823
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
04 | C | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 27 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 32994 | 0 | 96.3% | 0% | 96.3% | 31772 | 0 | 31772
04 | D | Bathroom : 250mm wide; total size of 945 x 2430mm high. | 1 | No | 27 | Crystal White | 20 | 699 | 329 | 1028 | 1028 | 27756 | 0 | 96.3% | 0% | 96.3% | 26728 | 0 | 26728
04 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 27 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 52056 | 0 | 96.3% | 0% | 96.3% | 50128 | 0 | 50128
Joinery Items
Foyer
04 | F | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 27 | Crystal White | 20 | 118 | 59 | 177 | 177 | 4779 | 0 | 92.59% | 0% | 92.59% | 4425 | 0 | 4425
04 | G | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 680 x 615mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 27 | Crystal White | 20 | 217 | 108 | 325 | 325 | 8775 | 0 | 100% | 0% | 100% | 8775 | 0 | 8775
Bathroom
04 | H | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 27 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 56133 | 0 | 100% | 0% | 100% | 56133 | 0 | 56133
04 | J | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 27 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 33804 | 0 | 100% | 0% | 100% | 33804 | 0 | 33804
Shower
04 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 27 | Volakas | 20 | 639 | 312 | 951 | 951 | 25677 | 0 | 100% | 0% | 100% | 25677 | 0 | 25677
04 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 27 | Volakas | 20 | 256 | 107 | 363 | 363 | 9801 | 0 | 100% | 0% | 100% | 9801 | 0 | 9801
04 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 27 | Volakas | 20 | 44 | 12 | 56 | 112 | 3024 | 0 | 100% | 0% | 100% | 3024 | 0 | 3024
Toilet
04 | D | Cistern : Supply and installation of 20mm thick polished Volakas, 225mm W x 1315mm length, pencil edge finish. | 1 | No | 27 | Volakas | 20 | 145 | 72 | 217 | 217 | 5859 | 0 | 100% | 0% | 100% | 5859 | 0 | 5859
04 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 27 | Volakas | 20 | 25 | 5 | 30 | 30 | 810 | 0 | 100% | 0% | 100% | 810 | 0 | 810
Miscellaneous Items
04 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 93 | M2 | 27 |  |  | 0 | 8 | 8 | 744 | 20088 |  | 99.67% | 0% | 99.67% | 20022.4735 | 0 | 20022.4735
04 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 41 | M2 | 27 |  |  | 0 | 8 | 8 | 328 | 8856 |  | 99.67% | 0% | 99.67% | 8827.112 | 0 | 8827.112
04 |  | Total Amount for TYPE -2E/2F/2G/2H | [14 empty] | 1413661.9855 | 0 | 1413661.9855
05 |  | TYPE -3A/3B/3D/3E/3G (39 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
05 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.4 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 1360 | 53040 | 0 | 100% | 0% | 100% | 53040 | 0 | 53040
05 | B | 20mm thick polished Crystal White, maximum 155mm width border. | 1.3 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 634.4 | 24741.6 | 0 | 100% | 0% | 100% | 24741.6 | 0 | 24741.6
05 | C | Extra-over to 7 x 5mm brass strips. | 7.4 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 421.8 | 16450.2 |  | 97.44% | 2.564% | 100% | 16028.4 | 421.8 | 16450.2
05 | D | Extra-over to 7 x 5mm brass strips; 950mm length (only the length between threshold and carpet, other locations are excluded) | 1 | No | 39 | Brass | 5 | 0 | 48 | 48 | 48 | 1872 |  | 100% | 0% | 100% | 1872 | 0 | 1872
05 | E | Threshold (20mm thick); 340mm wide x 925mm length polished Crystal White | 1 | No | 39 | Crystal White | 20 | 140 | 59 | 199 | 199 | 7761 | 0 | 100% | 0% | 100% | 7761 | 0 | 7761
Bedroom
05 | F | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 6.5 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 2600 | 101400 | 0 | 100% | 0% | 100% | 101400 | 0 | 101400
05 | G | 20mm thick polished Crystal White, cut to size. | 1.4 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 683.2 | 26644.8 | 0 | 100% | 0% | 100% | 26644.8 | 0 | 26644.8
05 | H | 20mm thick polished Crystal White, average of 135mm width border. | 2.75 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 52338 | 0 | 100% | 0% | 100% | 52338 | 0 | 52338
05 | J | Extra-over to 7 x 5mm brass strips. | 19.3 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 1100.1 | 42903.9 |  | 97.44% | 2.564% | 100% | 41803.8 | 1100.1 | 42903.9
05 | K | Extra-over to 7 x 5mm brass strips. | 16.8 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 957.6 | 37346.4 |  | 97.44% | 2.564% | 100% | 36388.8 | 957.6 | 37346.4
05 | L | Threshold (20mm thick polished Crystal White); 300mm wide x 1510mm length. | 1 | Lm | 39 | Crystal White | 20 | 206 | 82 | 288 | 288 | 11232 | 0 | 100% | 0% | 100% | 11232 | 0 | 11232
Bathroom
05 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 10.3 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 4120 | 160680 | 0 | 100% | 0% | 100% | 160680 | 0 | 160680
05 | N | 20mm thick polished Crystal White, average 170mm width border. | 2.85 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 1390.8 | 54241.2 | 0 | 100% | 0% | 100% | 54241.2 | 0 | 54241.2
05 | P | Extra-over to 7 x 5mm brass strips. | 15.8 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 900.6 | 35123.4 |  | 97.44% | 2.564% | 100% | 34222.8 | 900.6 | 35123.4
05 | Q | Threshold (20mm thick); 375mm wide x 861mm length polished Crystal White. | 1 | Lm | 39 | Crystal White | 20 | 138 | 59 | 197 | 197 | 7683 | 0 | 100% | 0% | 100% | 7683 | 0 | 7683
Shower
05 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.5 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 23400 | 0 | 100% | 0% | 100% | 23400 | 0 | 23400
05 | C | Threshold (20mm thick); 235mm wide x 860mm length and 40mm high fascia, polished Crystal White | 1 | No | 39 | Crystal White | 20 | 112 | 44 | 156 | 156 | 6084 | 0 | 100% | 0% | 100% | 6084 | 0 | 6084
Toilet
05 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 12480 | 0 | 100% | 0% | 100% | 12480 | 0 | 12480
05 | E | 20mm thick polished Crystal White, average of 110mm width border. | 0.5 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 244 | 9516 | 0 | 100% | 0% | 100% | 9516 | 0 | 9516
05 | F | Extra-over to 7 x 5mm brass strips. | 3.6 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 205.2 | 8002.8 |  | 97.44% | 2.564% | 100% | 7797.6 | 205.2 | 8002.8
05 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 39 | Crystal White | 20 | 99 | 37 | 136 | 136 | 5304 | 0 | 100% | 0% | 100% | 5304 | 0 | 5304
Balcony Floor Finishes
05 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10 | M2 | 39 | PC Rate | 20 | 50 | 100 | 150 | 1500 | 58500 | 0 | 100% | 0% | 100% | 58500 | 0 | 58500
Wall Finishes
Bathroom
05 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9 | Lm | 39 | Crystal White | 20 | 86 | 48 | 134 | 1206 | 47034 | 0 | 100% | 0% | 100% | 47034 | 0 | 47034
05 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-12) | 12.5 | M2 | 39 | Volakas | 20 | 406 | 222 | 628 | 7850 | 306150 | 0 | 100% | 0% | 100% | 306150 | 0 | 306150
Shower
05 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.5 | M2 | 39 | Volakas | 20 | 406 | 222 | 628 | 6594 | 257166 | 0 | 100% | 0% | 100% | 257166 | 0 | 257166
05 | L | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.3 | Lm | 39 | Crystal White | 20 | 79 | 43 | 122 | 524.6 | 20459.4 | 0 | 100% | 0% | 100% | 20459.4 | 0 | 20459.4
Toilet
05 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.2 | M2 | 39 | Volakas | 20 | 406 | 222 | 628 | 2637.6 | 102866.4 | 0 | 100% | 0% | 100% | 102866.4 | 0 | 102866.4
05 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4 | Lm | 39 | Crystal White | 20 | 79 | 43 | 122 | 488 | 19032 | 0 | 100% | 0% | 100% | 19032 | 0 | 19032
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
05 | B | Bedroom : 300mm wide; total size of 1510 x 2430mm high. | 1 | No | 39 | Crystal White | 20 | 869 | 433 | 1302 | 1302 | 50778 | 0 | 97.44% | 0% | 97.44% | 49476 | 0 | 49476
05 | C | Foyer : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 39 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 42393 | 0 | 100% | 0% | 100% | 42393 | 0 | 42393
05 | D | Bathroom : (145 + 160)mm wide; total size of 995 x 2430mm high. | 1 | No | 39 | Crystal White | 20 | 811 | 407 | 1218 | 1218 | 47502 | 0 | 100% | 0% | 100% | 47501.1316 | 0 | 47501.1316
05 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 39 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 75192 | 0 | 100% | 0% | 100% | 75192 | 0 | 75192
Joinery Items
Entrance
05 | F | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 233 | 118 | 351 | 351 | 13689 |  |  |  |  | 0 | 0 | 0
Walk-In Closet
05 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1100mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 310 | 164 | 474 | 474 | 18486 | 0 | 100% | 0% | 100% | 18486 | 0 | 18486
Bedroom
05 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 660mm length, mitered with 40mm high fascia, (full high cladding to 2 sides, elsewhere). Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 200 | 99 | 299 | 299 | 11661 | 0 | 97.44% | 0% | 97.44% | 11362 | 0 | 11362
05 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (a) 595mm wide x 1535mm high cladding to 2 sides having (b) 30mm width complete front frame and (c) soffit/ceiling. Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 1172 | 654 | 1826 | 1826 | 71214 | 0 | 97.44% | 0% | 97.44% | 69388 | 0 | 69388
Bathroom
05 | K | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 118 | 59 | 177 | 177 | 6903 | 0 | 97.44% | 0% | 97.44% | 6726 | 0 | 6726
05 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround, shelf, and back support elsewhere). | 1 | No | 39 | Volakas | 20 | 1935 | 872 | 2807 | 2807 | 109473 | 0 | 100% | 0% | 100% | 109473 | 0 | 109473
05 | B | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 170mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 2 | No | 39 | Volakas | 20 | 519 | 254 | 773 | 1546 | 60294 | 0 | 100% | 0% | 100% | 60294 | 0 | 60294
05 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 68 | 31 | 99 | 99 | 3861 | 0 | 100% | 0% | 100% | 3861 | 0 | 3861
05 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 39 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 36816 | 0 | 93.59% | 0% | 93.59% | 34456 | 0 | 34456
Shower
05 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 639 | 312 | 951 | 951 | 37089 | 0 | 100% | 0% | 100% | 37089 | 0 | 37089
05 | F | Bench : Supply and installation of 20mm thick polished Volakas, 410mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 278 | 119 | 397 | 397 | 15483 | 0 | 100% | 0% | 100% | 15483 | 0 | 15483
05 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 39 | Volakas | 20 | 44 | 12 | 56 | 112 | 4368 | 0 | 100% | 0% | 100% | 4368 | 0 | 4368
Toilet
05 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1020mm length, pencil edge finish. | 1 | No | 39 | Volakas | 20 | 107 | 53 | 160 | 160 | 6240 | 0 | 100% | 0% | 100% | 6240 | 0 | 6240
Miscellaneous Items
05 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 94 | M2 | 39 |  |  | 0 | 8 | 8 | 752 | 29328 |  | 98.9% | 0.169% | 99.07% | 29006.6458 | 49.578 | 29056.2237
05 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 41 | M2 | 39 |  |  | 0 | 8 | 8 | 328 | 12792 |  | 98.9% | 0.169% | 99.07% | 12651.8348 | 21.6244 | 12673.4593
05 |  | Total Amount for TYPE -3A/3B/3D/3E/3G | [14 empty] | 2139313.4122 | 3656.5024 | 2142969.9146
06 |  | TYPE -03C/03F (18 No's)
Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
06 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.8 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 1120 | 20160 | 0 | 100% | 0% | 100% | 20160 | 0 | 20160
06 | B | 20mm thick polished Crystal White, maximum 140mm width border. | 1.35 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 658.8 | 11858.4 | 0 | 100% | 0% | 100% | 11858.4 | 0 | 11858.4
06 | C | 7 x 5mm Brass strip insert in brushed finish . | 7.4 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 421.8 | 7592.4 |  | 94.44% | 5.556% | 100% | 7170.6 | 421.8 | 7592.4
06 | D | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat; 925mm length (only the length between threshold and carpet, other locations are excluded) | 0.93 | Lm | 18 | Brass | 5 | 0 | 54 | 54 | 50.22 | 903.96 |  | 100% | 0% | 100% | 903.96 | 0 | 903.96
06 | E | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White | 1 | No | 18 | Crystal White | 20 | 134 | 55 | 189 | 189 | 3402 | 0 | 100% | 0% | 100% | 3402 | 0 | 3402
Bedroom
06 | F | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.6 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 2240 | 40320 | 0 | 100% | 0% | 100% | 40320 | 0 | 40320
06 | G | 20mm thick polished Crystal White, cut to size. | 1.6 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 780.8 | 14054.4 | 0 | 100% | 0% | 100% | 14054.4 | 0 | 14054.4
06 | H | 20mm thick polished Crystal White, average of 137mm width border. | 2.75 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 24156 | 0 | 100% | 0% | 100% | 24156 | 0 | 24156
06 | J | 7 x 5mm Brass strip insert in brushed finish . | 19.3 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 1100.1 | 19801.8 |  | 100% | 0% | 100% | 19801.8 | 0 | 19801.8
06 | K | 7 x 5mm Brass strip insert in brushed finish . | 16.8 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 957.6 | 17236.8 |  | 100% | 0% | 100% | 17236.8 | 0 | 17236.8
06 | L | Threshold (20mm thick polished Crystal White); 300mm wide x 1510mm length. | 1 | No | 18 | Crystal White | 20 | 206 | 82 | 288 | 288 | 5184 | 0 | 100% | 0% | 100% | 5184 | 0 | 5184
Bathroom
06 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 10 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 4000 | 72000 | 0 | 100% | 0% | 100% | 72000 | 0 | 72000
06 | N | 20mm thick polished Crystal White, average 153mm width border. | 2.7 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 1317.6 | 23716.8 | 0 | 100% | 0% | 100% | 23716.8 | 0 | 23716.8
06 | P | 7 x 5mm Brass strip insert in brushed finish . | 15.8 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 900.6 | 16210.8 |  | 100% | 0% | 100% | 16210.8 | 0 | 16210.8
06 | A | Threshold (20mm thick); 375mm wide x 995mm length polished Crystal White. | 1 | No | 18 | Crystal White | 20 | 163 | 70 | 233 | 233 | 4194 | 0 | 100% | 0% | 100% | 4194 | 0 | 4194
Shower
06 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.7 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 680 | 12240 | 0 | 100% | 0% | 100% | 12240 | 0 | 12240
06 | D | Threshold (20mm thick); 235mm wide x 860mm length and 40mm high fascia, polished Crystal White | 1 | No | 18 | Crystal White | 20 | 112 | 44 | 156 | 156 | 2808 | 0 | 100% | 0% | 100% | 2808 | 0 | 2808
Toilet
06 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 5760 | 0 | 100% | 0% | 100% | 5760 | 0 | 5760
06 | F | 20mm thick polished Crystal White, average of 107mm width border. | 0.5 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 244 | 4392 | 0 | 100% | 0% | 100% | 4392 | 0 | 4392
06 | G | 7 x 5mm Brass strip insert in brushed finish . | 3.6 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 205.2 | 3693.6 |  | 100% | 0% | 100% | 3693.6 | 0 | 3693.6
06 | H | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 18 | Crystal White | 20 | 99 | 37 | 136 | 136 | 2448 | 0 | 100% | 0% | 100% | 2448 | 0 | 2448
Balcony Floor Finishes
06 | J | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10 | M2 | 18 | PC Rate | 20 | 50 | 100 | 150 | 1500 | 27000 | 0 | 100% | 0% | 100% | 27000 | 0 | 27000
Wall Finishes
Bathroom
06 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9 | Lm | 18 | Crystal White | 20 | 86 | 48 | 134 | 1206 | 21708 | 0 | 100% | 0% | 100% | 21708 | 0 | 21708
06 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-12) | 12.5 | M2 | 18 | Volakas | 20 | 406 | 222 | 628 | 7850 | 141300 | 0 | 100% | 0% | 100% | 141300 | 0 | 141300
Shower
06 | L | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 11.5 | M2 | 18 | Volakas | 20 | 406 | 222 | 628 | 7222 | 129996 | 0 | 100% | 0% | 100% | 129996 | 0 | 129996
06 | M | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.7 | Lm | 18 | Crystal White | 20 | 94 | 56 | 150 | 705 | 12690 | 0 | 100% | 0% | 100% | 12690 | 0 | 12690
Toilet
06 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.2 | M2 | 18 | Volakas | 20 | 406 | 222 | 628 | 2637.6 | 47476.8 | 0 | 100% | 0% | 100% | 47476.8 | 0 | 47476.8
06 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.2 | Lm | 18 | Crystal White | 20 | 79 | 43 | 122 | 512.4 | 9223.2 | 0 | 100% | 0% | 100% | 9223.2 | 0 | 9223.2
Stone to Doors
Door Architraves: Supply and installation of (20 x 10mm) thick polished Crystal White
06 |  | Bedroom : 300mm wide; total size of 1510 x 2430mm high. | 1 | No | 18 | Crystal White | 20 | 869 | 433 | 1302 | 1302 | 23436 | 0 | 94.44% | 0% | 94.44% | 22134 | 0 | 22134
06 | C | Foyer : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 18 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 19566 | 0 | 100% | 0% | 100% | 19566 | 0 | 19566
06 | D | Bathroom : (145 + 160)mm wide; total size of 995 x 2430mm high. | 1 | No | 18 | Crystal White | 20 | 811 | 407 | 1218 | 1218 | 21924 | 0 | 94.44% | 0% | 94.44% | 20706 | 0 | 20706
06 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 18 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 34704 | 0 | 94.44% | 0% | 94.44% | 32776 | 0 | 32776
Joinery Items
Entrance
06 | F | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 233 | 118 | 351 | 351 | 6318 |  |  |  |  | 0 | 0 | 0
Walk-In Closet
06 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 286 | 149 | 435 | 435 | 7830 | 0 | 94.44% | 0% | 94.44% | 7395 | 0 | 7395
Bedroom
06 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 655mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 200 | 99 | 299 | 299 | 5382 | 0 | 94.44% | 0% | 94.44% | 5083 | 0 | 5083
06 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 655 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 946 | 528 | 1474 | 1474 | 26532 | 0 | 94.44% | 0% | 94.44% | 25058 | 0 | 25058
Bathroom
06 | A | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 118 | 59 | 177 | 177 | 3186 | 0 | 94.44% | 0% | 94.44% | 3009 | 0 | 3009
06 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 18 | Volakas | 20 | 1935 | 872 | 2807 | 2807 | 50526 | 0 | 100% | 0% | 100% | 50526 | 0 | 50526
06 | C | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 18 | Volakas | 20 | 372 | 182 | 554 | 1108 | 19944 | 0 | 100% | 0% | 100% | 19944 | 0 | 19944
06 | D | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 68 | 31 | 99 | 99 | 1782 | 0 | 100% | 0% | 100% | 1782 | 0 | 1782
06 | E | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 18 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 16992 | 0 | 100% | 0% | 100% | 16992 | 0 | 16992
Shower
06 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 639 | 312 | 951 | 951 | 17118 | 0 | 100% | 0% | 100% | 17118 | 0 | 17118
06 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 805mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 199 | 81 | 280 | 280 | 5040 | 0 | 97.22% | 0% | 97.22% | 4900 | 0 | 4900
06 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 18 | Volakas | 20 | 44 | 12 | 56 | 112 | 2016 | 0 | 97.22% | 0% | 97.22% | 1960 | 0 | 1960
Toilet
06 | A | Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) | 1 | No | 18 | Volakas | 20 | 107 | 53 | 160 | 160 | 2880 | 0 | 100% | 0% | 100% | 2880 | 0 | 2880
Miscellaneous Items
06 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 96 | M2 | 18 |  |  | 0 | 8 | 8 | 768 | 13824 |  | 98.58% | 0.04363% | 98.62% | 13627.1041 | 6.0318 | 13633.1359
06 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 41 | M2 | 18 |  |  | 0 | 8 | 8 | 328 | 5904 |  | 98.58% | 0.04363% | 98.62% | 5819.909 | 2.5761 | 5822.4851
06 |  | Total Amount for TYPE -3C/3F | [14 empty] | 972381.1731 | 430.4079 | 972811.581
07 |  | TYPE -04A/4B (5 No's)
Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
07 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.65 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1460 | 7300 | 0 | 100% | 0% | 100% | 7300 | 0 | 7300
07 | B | 20mm thick polished Crystal White, maximum 135mm width border. | 1.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 756.4 | 3782 | 0 | 100% | 0% | 100% | 3782 | 0 | 3782
07 | C | 7 x 5mm Brass strip insert in brushed finish . | 8.9 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 507.3 | 2536.5 |  | 100% | 0% | 100% | 2536.5 | 0 | 2536.5
07 | D | Threshold (20mm thick); 210mm wide x 1100mm length polished Crystal White | 1 | No | 5 | Crystal White | 20 | 119 | 43 | 162 | 162 | 810 | 0 | 100% | 0% | 100% | 810 | 0 | 810
07 | Add | 8 x 8mm Brass strip insert in brushed finish with top layer brass coat; 800mm length (only the legth between threshold and carpet, other locations are excluded) (HTL-ME-04) | 1 | No | 5 | Brass | 5 | 0 | 48 | 48 | 48 | 240 |  | 100% | 0% | 100% | 240 | 0 | 240
Bedroom
07 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 10.4 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 4160 | 20800 | 0 | 100% | 0% | 100% | 20800 | 0 | 20800
07 | F | 20mm thick polished Crystal White, cut to size. | 3 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1464 | 7320 | 0 | 100% | 0% | 100% | 7320 | 0 | 7320
07 | G | 20mm thick polished Crystal White, average of 167mm width border; 20850mm length. | 3.05 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1488.4 | 7442 | 0 | 100% | 0% | 100% | 7442 | 0 | 7442
07 | H | 7 x 5mm Brass strip insert in brushed finish . | 21.4 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1219.8 | 6099 |  | 100% | 0% | 100% | 6099 | 0 | 6099
07 | J | 7 x 5mm Brass strip insert in brushed finish . | 17 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 969 | 4845 |  | 100% | 0% | 100% | 4845 | 0 | 4845
07 | K | Threshold (20mm thick polished Crystal White); 320mm wide x 945mm length. | 1 | Lm | 5 | Crystal White | 20 | 135 | 55 | 190 | 190 | 950 | 0 | 100% | 0% | 100% | 950 | 0 | 950
07 | L | Threshold (20mm thick polished Crystal White); 215mm wide x 890mm length. | 1 | Lm | 5 | Crystal White | 20 | 97 | 35 | 132 | 132 | 660 | 0 | 100% | 0% | 100% | 660 | 0 | 660
Bathroom
07 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 7.5 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3000 | 15000 | 0 | 100% | 0% | 100% | 15000 | 0 | 15000
07 | N | 20mm thick polished Crystal White, average 139mm width border; 12275mm length. | 2.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1024.8 | 5124 | 0 | 100% | 0% | 100% | 5124 | 0 | 5124
07 | A | 7 x 5mm Brass strip insert in brushed finish . | 11 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 627 | 3135 |  | 100% | 0% | 100% | 3135 | 0 | 3135
07 | B | Threshold (20mm thick); 375mm wide x 995mm length polished Crystal White. | 1 | Lm | 5 | Crystal White | 20 | 163 | 70 | 233 | 233 | 1165 | 0 | 100% | 0% | 100% | 1165 | 0 | 1165
Shower
07 | C | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1200 | 6000 | 0 | 100% | 0% | 100% | 6000 | 0 | 6000
07 | E | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Toilet
07 | F | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.9 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 360 | 1800 | 0 | 100% | 0% | 100% | 1800 | 0 | 1800
07 | G | 20mm thick polished Crystal White, average of 107mm width border; 4570mm length. | 0.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1342 | 0 | 100% | 0% | 100% | 1342 | 0 | 1342
07 | H | 7 x 5mm Brass strip insert in brushed finish . | 3.85 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 219.45 | 1097.25 |  | 100% | 0% | 100% | 1097.25 | 0 | 1097.25
07 | J | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Balcony Floor Finishes
07 | K | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 24 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 3600 | 18000 | 0 | 100% | 0% | 100% | 18000 | 0 | 18000
Wall Finishes
Bathroom
07 | L | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.9 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 924.6 | 4623 | 0 | 100% | 0% | 100% | 4623 | 0 | 4623
07 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-12) | 9.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 29987 | 0 | 100% | 0% | 100% | 29987 | 0 | 29987
Shower
07 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 11.85 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 7441.8 | 37209 | 0 | 100% | 0% | 100% | 37209 | 0 | 37209
07 | N | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.2 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 780 | 3900 | 0 | 100% | 0% | 100% | 3900 | 0 | 3900
Toilet
07 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.1 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2574.8 | 12874 | 0 | 100% | 0% | 100% | 12874 | 0 | 12874
07 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.8 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 463.6 | 2318 | 0 | 100% | 0% | 100% | 2318 | 0 | 2318
Stone to Doors
Door Architraves: Supply and installation of (20 x 10mm) thick polished Crystal White
07 | C | Bedroom : 320mm wide; total size of 945 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 831 | 421 | 1252 | 1252 | 6260 | 0 | 100% | 0% | 100% | 6260 | 0 | 6260
07 | D | Bathroom : (160 + 145)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 789 | 395 | 1184 | 1184 | 5920 | 0 | 100% | 0% | 100% | 5920 | 0 | 5920
07 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
07 | Add | 135+131mm wide; total size of 860 x 2430mm high (HTL-ST-01) | 1 | No | 5 | Crystal White | 20 | 718 | 344 | 1062 | 1062 | 5310 | 0 | 100% | 0% | 100% | 5310 | 0 | 5310
Joinery Items
Entrance
07 | F | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 233 | 118 | 351 | 351 | 1755 |  |  |  |  | 0 | 0 | 0
Walk-In Closet
07 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2175 | 0 | 100% | 0% | 100% | 2175 | 0 | 2175
Bedroom
07 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 655mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 200 | 99 | 299 | 299 | 1495 | 0 | 100% | 0% | 100% | 1495 | 0 | 1495
07 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 655 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 946 | 528 | 1474 | 1474 | 7370 | 0 | 100% | 0% | 100% | 7370 | 0 | 7370
07 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 118 | 59 | 177 | 177 | 885 | 0 | 100% | 0% | 100% | 885 | 0 | 885
Bathroom
07 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 5 | Volakas | 20 | 1935 | 872 | 2807 | 2807 | 14035 | 0 | 100% | 0% | 100% | 14035 | 0 | 14035
07 | B | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 372 | 182 | 554 | 1108 | 5540 | 0 | 100% | 0% | 100% | 5540 | 0 | 5540
07 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 43 | 19 | 62 | 124 | 620 | 0 | 100% | 0% | 100% | 620 | 0 | 620
Bath Tub Base
07 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 5 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 4720 | 0 | 100% | 0% | 100% | 4720 | 0 | 4720
Shower
07 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 492 | 240 | 732 | 732 | 3660 | 0 | 100% | 0% | 100% | 3660 | 0 | 3660
07 | F | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1145mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 272 | 114 | 386 | 386 | 1930 | 0 | 100% | 0% | 100% | 1930 | 0 | 1930
07 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
Toilet
07 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 102 | 50 | 152 | 152 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
07 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Miscellaneous Items
07 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 113 | M2 | 5 |  |  | 0 | 8 | 8 | 904 | 4520 |  | 99.37% | 0% | 99.37% | 4491.7202 | 0 | 4491.7202
07 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 62 | M2 | 5 |  |  | 0 | 8 | 8 | 496 | 2480 |  |  |  |  | 0 | 0 | 0
07 |  | Total Amount for TYPE -4A/4B | [14 empty] | 283240.4702 | 0 | 283240.4702
08 |  | TYPE -05A (9 No's)
Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
08 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.4 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 960 | 8640 | 0 | 100% | 0% | 100% | 8640 | 0 | 8640
08 | B | 20mm thick polished Crystal White, maximum 171mm width border. | 1.2 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 585.6 | 5270.4 | 0 | 100% | 0% | 100% | 5270.4 | 0 | 5270.4
08 | C | 7 x 5mm Brass strip insert in brushed finish . | 6.3 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 359.1 | 3231.9 |  | 100% | 0% | 100% | 3231.9 | 0 | 3231.9
08 | D | Threshold (20mm thick); 210mm wide x 1100mm length polished Crystal White | 1 | No | 9 | Crystal White | 20 | 119 | 43 | 162 | 162 | 1458 | 0 | 100% | 0% | 100% | 1458 | 0 | 1458
Bedroom
08 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 22.6 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 9040 | 81360 | 0 | 100% | 0% | 100% | 81360 | 0 | 81360
08 | F | 20mm thick polished Crystal White, cut to size. | 3.3 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 1610.4 | 14493.6 | 0 | 100% | 0% | 100% | 14493.6 | 0 | 14493.6
08 | G | 20mm thick polished Crystal White, average of 132mm width border. | 4.15 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 2025.2 | 18226.8 | 0 | 100% | 0% | 100% | 18226.8 | 0 | 18226.8
08 | H | 7 x 5mm Brass strip insert in brushed finish . | 25.4 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 1447.8 | 13030.2 |  | 88.89% | 0% | 88.89% | 11582.4 | 0 | 11582.4
08 | J | 7 x 5mm Brass strip insert in brushed finish . | 11.3 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 644.1 | 5796.9 |  | 88.89% | 0% | 88.89% | 5152.8 | 0 | 5152.8
08 | K | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | Lm | 9 | Crystal White | 20 | 231 | 97 | 328 | 328 | 2952 | 0 | 100% | 0% | 100% | 2952 | 0 | 2952
Bathroom
08 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 11.5 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 4600 | 41400 | 0 | 100% | 0% | 100% | 41400 | 0 | 41400
08 | M | 20mm thick polished Crystal White, average 139mm width border. | 2.5 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 1220 | 10980 | 0 | 100% | 0% | 100% | 10980 | 0 | 10980
08 | N | 7 x 5mm Brass strip insert in brushed finish . | 16.6 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 946.2 | 8515.8 |  | 100% | 0% | 100% | 8515.8 | 0 | 8515.8
08 | P | Threshold (20mm thick); 375mm wide x 860mm length polished Crystal White. | 1 | Lm | 9 | Crystal White | 20 | 138 | 59 | 197 | 197 | 1773 | 0 | 100% | 0% | 100% | 1773 | 0 | 1773
Shower
08 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.7 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 680 | 6120 | 0 | 100% | 0% | 100% | 6120 | 0 | 6120
08 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 9 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1224 | 0 | 100% | 0% | 100% | 1224 | 0 | 1224
Toilet
08 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 2880 | 0 | 100% | 0% | 100% | 2880 | 0 | 2880
08 | E | 20mm thick polished Crystal White, average of 101mm width border. | 0.45 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 1976.4 | 0 | 100% | 0% | 100% | 1976.4 | 0 | 1976.4
08 | F | 7 x 5mm Brass strip insert in brushed finish . | 3.5 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 199.5 | 1795.5 |  | 100% | 0% | 100% | 1795.5 | 0 | 1795.5
08 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 9 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1224 | 0 | 100% | 0% | 100% | 1224 | 0 | 1224
Balcony Floor Finishes
08 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 13.5 | M2 | 9 | PC Rate | 20 | 50 | 100 | 150 | 2025 | 18225 | 0 | 100% | 0% | 100% | 18225 | 0 | 18225
Wall Finishes
Bathroom
08 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 13.9 | Lm | 9 | Crystal White | 20 | 86 | 48 | 134 | 1862.6 | 16763.4 | 0 | 100% | 0% | 100% | 16763.4 | 0 | 16763.4
08 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 9.55 | M2 | 9 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 53976.6 | 0 | 100% | 0% | 100% | 53976.6 | 0 | 53976.6
Shower
08 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.8 | M2 | 9 | Volakas | 20 | 406 | 222 | 628 | 6782.4 | 61041.6 | 0 | 100% | 0% | 100% | 61041.6 | 0 | 61041.6
08 | L | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 9 | Crystal White | 20 | 94 | 56 | 150 | 675 | 6075 | 0 | 100% | 0% | 100% | 6075 | 0 | 6075
Toilet
08 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4 | M2 | 9 | Volakas | 20 | 406 | 222 | 628 | 2512 | 22608 | 0 | 100% | 0% | 100% | 22608 | 0 | 22608
08 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.6 | Lm | 9 | Crystal White | 20 | 79 | 43 | 122 | 439.2 | 3952.8 | 0 | 100% | 0% | 100% | 3952.8 | 0 | 3952.8
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
08 | B | Bedroom : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 9 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 13302 | 0 | 88.89% | 0% | 88.89% | 11824 | 0 | 11824
08 | C | Bathroom : (160 + 145)mm wide); total size of 860 x 2430mm high. | 1 | No | 9 | Crystal White | 20 | 789 | 395 | 1184 | 1184 | 10656 | 0 | 100% | 0% | 100% | 10656 | 0 | 10656
08 | D | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 9 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 17352 | 0 | 100% | 0% | 100% | 17352 | 0 | 17352
Joinery Items
Entrance
08 | E | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 233 | 118 | 351 | 351 | 3159 | 0 | 100% | 0% | 100% | 3159 | 0 | 3159
08 | F | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 262 | 134 | 396 | 396 | 3564 | 0 | 100% | 0% | 100% | 3564 | 0 | 3564
08 | G | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 15057 | 0 | 88.89% | 0% | 88.89% | 13384 | 0 | 13384
Walk-In Closet
08 | H | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 286 | 149 | 435 | 435 | 3915 | 0 | 100% | 0% | 100% | 3915 | 0 | 3915
Bathroom
08 | J | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 118 | 59 | 177 | 177 | 1593 | 0 | 100% | 0% | 100% | 1593 | 0 | 1593
08 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 9 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 18711 | 0 | 100% | 0% | 100% | 18711 | 0 | 18711
08 | B | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 372 | 182 | 554 | 554 | 4986 | 0 | 100% | 0% | 100% | 4986 | 0 | 4986
08 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 9 | Volakas | 20 | 43 | 19 | 62 | 124 | 1116 | 0 | 100% | 0% | 100% | 1116 | 0 | 1116
Bath Tub Base
08 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 9 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 8496 | 0 | 100% | 0% | 100% | 8496 | 0 | 8496
Shower
08 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 492 | 240 | 732 | 732 | 6588 | 0 | 100% | 0% | 100% | 6588 | 0 | 6588
08 | F | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1385mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 324 | 138 | 462 | 462 | 4158 | 0 | 100% | 0% | 100% | 4158 | 0 | 4158
08 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 9 | Volakas | 20 | 44 | 12 | 56 | 112 | 1008 | 0 | 100% | 0% | 100% | 1008 | 0 | 1008
Additional Items
08 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 260mm W x 1050mm length, pencil edge finish. | 1 | No | 9 | Volakas | 20 | 127 | 65 | 192 | 192 | 1728 | 0 | 100% | 0% | 100% | 1728 | 0 | 1728
08 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 9 | Volakas | 20 | 25 | 5 | 30 | 30 | 270 | 0 | 100% | 0% | 100% | 270 | 0 | 270
Miscellaneous Items
08 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 115 | M2 | 9 |  |  | 0 | 8 | 8 | 920 | 8280 |  | 99.01% | 0% | 99.01% | 8198.1924 | 0 | 8198.1924
08 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 66 | M2 | 9 |  |  | 0 | 8 | 8 | 528 | 4752 |  | 99.01% | 0% | 99.01% | 4705.0495 | 0 | 4705.0495
08 |  | Total Amount for TYPE -5A | [14 empty] | 538310.2419 | 0 | 538310.2419
09 |  | TYPE -06A (5 No's)
Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
09 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 920 | 4600 | 0 | 100% | 0% | 100% | 4600 | 0 | 4600
09 | B | 20mm thick polished Crystal White, maximum 159mm width border. | 1.15 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 561.2 | 2806 | 0 | 100% | 0% | 100% | 2806 | 0 | 2806
09 | C | 7 x 5mm Brass strip insert in brushed finish. | 5.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 330.6 | 1653 |  | 100% | 0% | 100% | 1653 | 0 | 1653
09 | D | 7 x 5mm Brass strip insert in brushed finish. 900mm length (only the length between threshold and carpet, other locations are excluded) | 0.9 | Lm | 5 | Brass | 5 | 0 | 53 | 53 | 47.7 | 238.5 |  | 100% | 0% | 100% | 238.5 | 0 | 238.5
09 | E | Threshold (20mm thick); 220mm wide x 1100mm length polished Crystal White | 1 | No | 5 | Crystal White | 20 | 121 | 44 | 165 | 165 | 825 | 0 | 100% | 0% | 100% | 825 | 0 | 825
09 | F | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
Bedroom
09 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 18.2 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 7280 | 36400 | 0 | 100% | 0% | 100% | 36400 | 0 | 36400
09 | H | 20mm thick polished Crystal White, cut to size. | 3.5 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1708 | 8540 | 0 | 100% | 0% | 100% | 8540 | 0 | 8540
09 | J | 20mm thick polished Crystal White, average of 165mm width border. | 4.5 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 2196 | 10980 | 0 | 100% | 0% | 100% | 10980 | 0 | 10980
09 | K | 7 x 5mm Brass strip insert in brushed finish. | 27 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1539 | 7695 |  | 100% | 0% | 100% | 7695 | 0 | 7695
09 | L | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 627 | 3135 |  | 100% | 0% | 100% | 3135 | 0 | 3135
09 | M | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | Lm | 5 | Crystal White | 20 | 155 | 62 | 217 | 217 | 1085 | 0 | 100% | 0% | 100% | 1085 | 0 | 1085
Bathroom
09 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3720 | 18600 | 0 | 100% | 0% | 100% | 18600 | 0 | 18600
09 | P | 20mm thick polished Crystal White, average 167mm width border. | 2.5 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1220 | 6100 | 0 | 100% | 0% | 100% | 6100 | 0 | 6100
09 | Q | 7 x 5mm Brass strip insert in brushed finish. | 15.6 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 889.2 | 4446 |  | 100% | 0% | 100% | 4446 | 0 | 4446
09 | A | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | Lm | 5 | Crystal White | 20 | 134 | 55 | 189 | 189 | 945 | 0 | 100% | 0% | 100% | 945 | 0 | 945
Shower
09 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.5 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 3000 | 0 | 100% | 0% | 100% | 3000 | 0 | 3000
09 | D | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 0.8 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 108.8 | 544 | 0 | 100% | 0% | 100% | 544 | 0 | 544
Toilet
09 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.6 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 240 | 1200 | 0 | 100% | 0% | 100% | 1200 | 0 | 1200
09 | F | 20mm thick polished Crystal White, average of 109mm width border. | 0.45 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 1098 | 0 | 100% | 0% | 100% | 1098 | 0 | 1098
09 | G | 7 x 5mm Brass strip insert in brushed finish. | 3.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 182.4 | 912 |  | 100% | 0% | 100% | 912 | 0 | 912
09 | H | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Balcony Floor Finishes
09 | J | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 6.5 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 975 | 4875 | 0 | 100% | 0% | 100% | 4875 | 0 | 4875
Wall Finishes
Bathroom
09 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 10.3 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 1380.2 | 6901 | 0 | 100% | 0% | 100% | 6901 | 0 | 6901
09 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 9.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 29987 | 0 | 100% | 0% | 100% | 29987 | 0 | 29987
Shower
09 | L | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 6280 | 31400 | 0 | 100% | 0% | 100% | 31400 | 0 | 31400
09 | M | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 600 | 3000 | 0 | 100% | 0% | 100% | 3000 | 0 | 3000
Toilet
09 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2229.4 | 11147 | 0 | 100% | 0% | 100% | 11147 | 0 | 11147
09 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.3 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 402.6 | 2013 | 0 | 100% | 0% | 100% | 2013 | 0 | 2013
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
09 | C | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 6110 | 0 | 100% | 0% | 100% | 6110 | 0 | 6110
09 | D | Foyer : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 5370 | 0 | 60% | 0% | 60% | 3222 | 0 | 3222
09 | E | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 5435 | 0 | 80% | 0% | 80% | 4348 | 0 | 4348
09 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
Joinery Items
Entrance
09 | G | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 233 | 118 | 351 | 351 | 1755 |  |  |  |  | 0 | 0 | 0
Foyer
09 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 262 | 134 | 396 | 396 | 1980 | 0 | 100% | 0% | 100% | 1980 | 0 | 1980
09 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 8365 | 0 | 100% | 0% | 100% | 8365 | 0 | 8365
09 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 118 | 59 | 177 | 177 | 885 | 0 | 100% | 0% | 100% | 885 | 0 | 885
Walk-In Closet
09 | A | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2175 | 0 | 100% | 0% | 100% | 2175 | 0 | 2175
Bathroom
09 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 5 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 10395 | 0 | 100% | 0% | 100% | 10395 | 0 | 10395
09 | C | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 372 | 182 | 554 | 1108 | 5540 | 0 | 100% | 0% | 100% | 5540 | 0 | 5540
09 | D | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 43 | 19 | 62 | 124 | 620 | 0 | 100% | 0% | 100% | 620 | 0 | 620
Bath Tub Base
09 | E | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 5 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 4720 | 0 | 80% | 0% | 80% | 3776 | 0 | 3776
Shower
09 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 492 | 240 | 732 | 732 | 3660 | 0 | 100% | 0% | 100% | 3660 | 0 | 3660
09 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1275mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 303 | 129 | 432 | 432 | 2160 | 0 | 100% | 0% | 100% | 2160 | 0 | 2160
09 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
Toilet
09 | A | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 260mm W x 970mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 118 | 60 | 178 | 178 | 890 | 0 | 100% | 0% | 100% | 890 | 0 | 890
09 | B | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Miscellaneous Items
09 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 101 | M2 | 5 |  |  | 0 | 8 | 8 | 808 | 4040 |  | 97.85% | 0% | 97.85% | 3953.17 | 0 | 3953.17
09 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 52 | M2 | 5 |  |  | 0 | 8 | 8 | 416 | 2080 |  | 97.85% | 0% | 97.85% | 2035.2955 | 0 | 2035.2955
09 |  | Total Amount for TYPE -6A | [14 empty] | 276149.9655 | 0 | 276149.9655
10 |  | TYPE -8A (5 No's)
Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
10 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1500 | 7500 | 0 | 100% | 0% | 100% | 7500 | 0 | 7500
10 | B | 20mm thick polished Crystal White, maximum 147mm width border. | 1.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 756.4 | 3782 | 0 | 100% | 0% | 100% | 3782 | 0 | 3782
10 | C | 7 x 5mm Brass strip insert in brushed finish. | 9.25 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 527.25 | 2636.25 |  | 100% | 0% | 100% | 2636.25 | 0 | 2636.25
Living Room
10 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 10.8 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 4320 | 21600 | 0 | 100% | 0% | 100% | 21600 | 0 | 21600
10 | E | 20mm thick polished Crystal White, cut to size. | 2.25 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1098 | 5490 | 0 | 100% | 0% | 100% | 5490 | 0 | 5490
10 | F | 20mm thick polished Crystal White, average of 157mm width border. | 3.75 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1830 | 9150 | 0 | 100% | 0% | 100% | 9150 | 0 | 9150
10 | G | 7 x 5mm Brass strip insert in brushed finish. | 22.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1299.6 | 6498 |  | 100% | 0% | 100% | 6498 | 0 | 6498
10 | H | 7 x 5mm Brass strip insert in brushed finish. | 17.9 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1020.3 | 5101.5 |  | 100% | 0% | 100% | 5101.5 | 0 | 5101.5
10 | J | Threshold (20mm thick polished Crystal White); 320mm wide x 1575mm length. | 1 | No | 5 | Crystal White | 20 | 227 | 94 | 321 | 321 | 1605 | 0 | 100% | 0% | 100% | 1605 | 0 | 1605
Toilet @ Foyer
10 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 3500 | 0 | 100% | 0% | 100% | 3500 | 0 | 3500
10 | L | 20mm thick polished Crystal White, average 117mm width border. | 0.7 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1708 | 0 | 100% | 0% | 100% | 1708 | 0 | 1708
10 | M | 7 x 5mm Brass strip insert in brushed finish. | 5.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 296.4 | 1482 |  | 100% | 0% | 100% | 1482 | 0 | 1482
10 | N | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
Bedroom
10 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 14.1 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 5640 | 28200 | 0 | 100% | 0% | 100% | 28200 | 0 | 28200
10 | A | 20mm thick polished Crystal White, cut to size. | 2.75 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 6710 | 0 | 100% | 0% | 100% | 6710 | 0 | 6710
10 | B | 20mm thick polished Crystal White, average of 137mm width border. | 3.35 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1634.8 | 8174 | 0 | 100% | 0% | 100% | 8174 | 0 | 8174
10 | C | 7 x 5mm Brass strip insert in brushed finish. | 25.6 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1459.2 | 7296 |  | 100% | 0% | 100% | 7296 | 0 | 7296
10 | D | 7 x 5mm Brass strip insert in brushed finish. | 6.5 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 370.5 | 1852.5 |  | 100% | 0% | 100% | 1852.5 | 0 | 1852.5
10 | E | Threshold (20mm thick polished Crystal White); 270mm wide x 945mm length. | 2 | No | 5 | Crystal White | 20 | 122 | 48 | 170 | 340 | 1700 | 0 | 100% | 0% | 100% | 1700 | 0 | 1700
10 | F | 7 x 5mm Brass strip insert in brushed finish. 950mm length (only the length between threshold and carpet, other locations are excluded) | 0.95 | Lm | 5 | Brass | 5 | 0 | 55 | 55 | 52.25 | 261.25 |  | 100% | 0% | 100% | 261.25 | 0 | 261.25
Bathroom
10 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.25 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3700 | 18500 | 0 | 100% | 0% | 100% | 18500 | 0 | 18500
10 | H | 20mm thick polished Crystal White, average 163mm width border. | 2.6 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1268.8 | 6344 | 0 | 100% | 0% | 100% | 6344 | 0 | 6344
10 | J | 7 x 5mm Brass strip insert in brushed finish. | 14.55 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 829.35 | 4146.75 |  | 100% | 0% | 100% | 4146.75 | 0 | 4146.75
10 | K | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
Shower
10 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.45 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 980 | 4900 | 0 | 100% | 0% | 100% | 4900 | 0 | 4900
10 | N | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Toilet
10 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.25 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3700 | 18500 | 0 | 100% | 0% | 100% | 18500 | 0 | 18500
10 | Q | 20mm thick polished Crystal White, average of 131mm width border. | 2.6 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1268.8 | 6344 | 0 | 100% | 0% | 100% | 6344 | 0 | 6344
10 | R | 7 x 5mm Brass strip insert in brushed finish. | 14.55 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 829.35 | 4146.75 |  | 100% | 0% | 100% | 4146.75 | 0 | 4146.75
10 | A | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Balcony Floor Finishes
10 | B | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 48 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 7200 | 36000 | 0 | 100% | 0% | 100% | 36000 | 0 | 36000
Wall Finishes
Bathroom
Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick.
10 | C | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.35 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 716.9 | 3584.5 | 0 | 80% | 0% | 80% | 2867.6 | 0 | 2867.6
10 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 9.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 29987 | 0 | 100% | 0% | 100% | 29987 | 0 | 29987
Shower
10 | D | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 15 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 9420 | 47100 | 0 | 100% | 0% | 100% | 47100 | 0 | 47100
10 | E | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.85 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 877.5 | 4387.5 | 0 | 100% | 0% | 100% | 4387.5 | 0 | 4387.5
Toilet
10 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.15 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2606.2 | 13031 | 0 | 100% | 0% | 100% | 13031 | 0 | 13031
10 | G | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.8 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 463.6 | 2318 | 0 | 100% | 0% | 100% | 2318 | 0 | 2318
Toilet @ Foyer
10 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 10.05 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 6311.4 | 31557 | 0 | 100% | 0% | 100% | 31557 | 0 | 31557
10 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.35 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 652.7 | 3263.5 | 0 | 100% | 0% | 100% | 3263.5 | 0 | 3263.5
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
10 | A | Living : 320mm wide; total size of 1575 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 921 | 467 | 1388 | 1388 | 6940 | 0 | 100% | 0% | 100% | 6940 | 0 | 6940
10 | B | Bedroom : 270mm wide; total size of 945 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 738 | 356 | 1094 | 2188 | 10940 | 0 | 100% | 0% | 100% | 10940 | 0 | 10940
10 | C | Toilet @ Foyer : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 5395 | 0 | 100% | 0% | 100% | 5395 | 0 | 5395
10 | D | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 5370 | 0 | 100% | 0% | 100% | 5370 | 0 | 5370
10 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
Joinery Items
Walk-In Closet
10 | F | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2175 | 0 | 100% | 0% | 100% | 2175 | 0 | 2175
Bathroom
10 | G | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 5 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 10395 | 0 | 100% | 0% | 100% | 10395 | 0 | 10395
10 | H | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 372 | 182 | 554 | 1108 | 5540 | 0 | 100% | 0% | 100% | 5540 | 0 | 5540
10 | J | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 43 | 19 | 62 | 124 | 620 | 0 | 100% | 0% | 100% | 620 | 0 | 620
Bath Tub Base
10 | A | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 5 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 4720 | 0 | 100% | 0% | 100% | 4720 | 0 | 4720
Shower
10 | B | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 215mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 588 | 287 | 875 | 875 | 4375 | 0 | 100% | 0% | 100% | 4375 | 0 | 4375
10 | C | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 256 | 107 | 363 | 363 | 1815 | 0 | 100% | 0% | 100% | 1815 | 0 | 1815
10 | D | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
Toilet
10 | E | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 112 | 55 | 167 | 167 | 835 | 0 | 100% | 0% | 100% | 835 | 0 | 835
10 | F | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Toilet @ Foyer
10 | G | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1395mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 150 | 74 | 224 | 224 | 1120 | 0 | 100% | 0% | 100% | 1120 | 0 | 1120
10 | H | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (955 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 5 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 5345 | 0 | 100% | 0% | 100% | 5345 | 0 | 5345
10 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Miscellaneous Items
10 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 188 | M2 | 5 |  |  | 0 | 8 | 8 | 1504 | 7520 |  | 99.84% | 0% | 99.84% | 7507.6792 | 0 | 7507.6792
10 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 121 | M2 | 5 |  |  | 0 | 8 | 8 | 968 | 4840 |  | 99.84% | 0% | 99.84% | 4832.0702 | 0 | 4832.0702
10 |  | Total Amount for TYPE -8A | [14 empty] | 449184.3494 | 0 | 449184.3494
11 |  | TYPE -09A (2 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
11 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.8 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 720 | 1440 | 0 | 100% | 0% | 100% | 1440 | 0 | 1440
11 | B | 20mm thick polished Crystal White, cut to size. | 1.8 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 878.4 | 1756.8 | 0 | 100% | 0% | 100% | 1756.8 | 0 | 1756.8
11 | C | 20mm thick polished Crystal White, maximum 145mm width border | 1.4 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 683.2 | 1366.4 | 0 | 100% | 0% | 100% | 1366.4 | 0 | 1366.4
11 | D | 7 x 5mm Brass strip insert in brushed finish. | 6.05 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 344.85 | 689.7 |  | 100% | 0% | 100% | 689.7 | 0 | 689.7
11 | Add | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 2 | Crystal White | 20 | 123 | 48 | 171 | 171 | 342 | 0 | 100% | 0% | 100% | 342 | 0 | 342
Living Room
11 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 7.35 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 2940 | 5880 | 0 | 100% | 0% | 100% | 5880 | 0 | 5880
11 | F | 20mm thick polished Crystal White, cut to size. | 2.85 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1390.8 | 2781.6 | 0 | 100% | 0% | 100% | 2781.6 | 0 | 2781.6
11 | G | 20mm thick polished Crystal White, average of 160mm width border. | 3.05 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1488.4 | 2976.8 | 0 | 100% | 0% | 100% | 2976.8 | 0 | 2976.8
11 | H | 7 x 5mm Brass strip insert in brushed finish. | 17.7 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 1008.9 | 2017.8 |  | 100% | 0% | 100% | 2017.8 | 0 | 2017.8
11 | J | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 627 | 1254 |  | 100% | 0% | 100% | 1254 | 0 | 1254
11 | K | Threshold (20mm thick polished Crystal White); 270mm wide x 940mm length. | 1 | No | 2 | Crystal White | 20 | 119 | 46 | 165 | 165 | 330 | 0 | 100% | 0% | 100% | 330 | 0 | 330
Toilet
11 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.95 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 380 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
11 | M | 20mm thick polished Crystal White, average 119mm width border. | 0.5 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 244 | 488 | 0 | 100% | 0% | 100% | 488 | 0 | 488
11 | N | 7 x 5mm Brass strip insert in brushed finish. | 4.1 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 233.7 | 467.4 |  | 100% | 0% | 100% | 467.4 | 0 | 467.4
11 | P | Threshold (20mm thick); 270mm wide x 860mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 109 | 43 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
Bedroom
11 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.25 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 1700 | 3400 | 0 | 100% | 0% | 100% | 3400 | 0 | 3400
11 | A | 20mm thick polished Crystal White, cut to size. | 1.2 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 585.6 | 1171.2 | 0 | 100% | 0% | 100% | 1171.2 | 0 | 1171.2
11 | B | 20mm thick polished Crystal White, average of 141mm width border. | 2.1 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1024.8 | 2049.6 | 0 | 100% | 0% | 100% | 2049.6 | 0 | 2049.6
11 | C | 7 x 5mm Brass strip insert in brushed finish. | 14 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 798 | 1596 |  | 100% | 0% | 100% | 1596 | 0 | 1596
11 | D | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 627 | 1254 |  | 100% | 0% | 100% | 1254 | 0 | 1254
11 | E | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 2 | Crystal White | 20 | 155 | 62 | 217 | 217 | 434 | 0 | 100% | 0% | 100% | 434 | 0 | 434
11 | F | Threshold (20mm thick polished Crystal White); 320mm wide x 750mm length. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
11 | G | 7 x 5mm Brass strip insert in brushed finish. 750mm length (only the length between threshold and carpet, other locations are excluded) | 1.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 85.5 | 171 |  | 100% | 0% | 100% | 171 | 0 | 171
Bathroom
11 | H | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.35 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 1740 | 3480 | 0 | 100% | 0% | 100% | 3480 | 0 | 3480
11 | J | 20mm thick polished Crystal White, average 153mm width border. | 1.5 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 732 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
11 | K | 7 x 5mm Brass strip insert in brushed finish. | 10.2 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 581.4 | 1162.8 |  | 100% | 0% | 100% | 1162.8 | 0 | 1162.8
11 | L | Threshold (20mm thick); 320mm wide x 750mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
Shower
11 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.6 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 1280 | 0 | 100% | 0% | 100% | 1280 | 0 | 1280
11 | P | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
Toilet
11 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.95 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 380 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
11 | R | 20mm thick polished Crystal White, average of 111mm width border. | 0.6 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 292.8 | 585.6 | 0 | 100% | 0% | 100% | 585.6 | 0 | 585.6
11 | A | 7 x 5mm Brass strip insert in brushed finish. | 4.1 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 233.7 | 467.4 |  | 100% | 0% | 100% | 467.4 | 0 | 467.4
11 | B | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
Balcony Floor Finishes
11 | C | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 38 | M2 | 2 | PC Rate | 20 | 50 | 100 | 150 | 5700 | 11400 | 0 | 100% | 0% | 100% | 11400 | 0 | 11400
Wall Finishes
Bathroom
11 | D | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 16 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 10048 | 20096 | 0 | 100% | 0% | 100% | 20096 | 0 | 20096
11 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9.4 | Lm | 2 | Crystal White | 20 | 86 | 48 | 134 | 1259.6 | 2519.2 | 0 | 100% | 0% | 100% | 2519.2 | 0 | 2519.2
Shower
11 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.8 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 6782.4 | 13564.8 | 0 | 100% | 0% | 100% | 13564.8 | 0 | 13564.8
11 | G | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 2 | Crystal White | 20 | 94 | 56 | 150 | 675 | 1350 | 0 | 100% | 0% | 100% | 1350 | 0 | 1350
Toilet
11 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.6 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 2888.8 | 5777.6 | 0 | 100% | 0% | 100% | 5777.6 | 0 | 5777.6
11 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.2 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 512.4 | 1024.8 | 0 | 100% | 0% | 100% | 1024.8 | 0 | 1024.8
Toilet @ Foyer
11 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.15 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 3862.2 | 7724.4 | 0 | 100% | 0% | 100% | 7724.4 | 0 | 7724.4
11 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.65 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 689.3 | 1378.6 | 0 | 100% | 0% | 100% | 1378.6 | 0 | 1378.6
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
11 | B | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 2444 | 0 | 100% | 0% | 100% | 2444 | 0 | 2444
11 | C | Living : 270mm wide; total size of 945 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 737 | 356 | 1093 | 1093 | 2186 | 0 | 100% | 0% | 100% | 2186 | 0 | 2186
11 | D | Toilet @ Foyer : (110 + 110)mm wide); total size of 860 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 634 | 286 | 920 | 920 | 1840 | 0 | 100% | 0% | 100% | 1840 | 0 | 1840
11 | E | Bathroom : (135 + 135)mm wide); total size of 750 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 710 | 343 | 1053 | 2106 | 4212 | 0 | 100% | 0% | 100% | 4212 | 0 | 4212
11 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 3856 | 0 | 100% | 0% | 100% | 3856 | 0 | 3856
Joinery Items
Foyer
11 | G | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 262 | 134 | 396 | 396 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
11 | H | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 3346 | 0 | 100% | 0% | 100% | 3346 | 0 | 3346
Walk-In Closet
11 | J | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1305mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 364 | 195 | 559 | 559 | 1118 | 0 | 100% | 0% | 100% | 1118 | 0 | 1118
Bathroom
11 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2315mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 2315mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1740 | 808 | 2548 | 2548 | 5096 | 0 | 100% | 0% | 100% | 5096 | 0 | 5096
11 | Add | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 372 | 182 | 554 | 1108 | 2216 | 0 | 100% | 0% | 100% | 2216 | 0 | 2216
11 | Add | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 43 | 19 | 62 | 124 | 248 | 0 | 100% | 0% | 100% | 248 | 0 | 248
Bath Tub Base
11 | B | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 2 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 2504 | 0 | 100% | 0% | 100% | 2504 | 0 | 2504
Shower
11 | C | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 492 | 240 | 732 | 732 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
11 | D | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 950mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 230 | 95 | 325 | 325 | 650 | 0 | 100% | 0% | 100% | 650 | 0 | 650
11 | E | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 44 | 12 | 56 | 112 | 224 | 0 | 100% | 0% | 100% | 224 | 0 | 224
Toilet
11 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 112 | 55 | 167 | 167 | 334 | 0 | 100% | 0% | 100% | 334 | 0 | 334
11 | G | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
Toilet @ Foyer
11 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 102 | 50 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
11 | A | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (150 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 2 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 2138 | 0 | 100% | 0% | 100% | 2138 | 0 | 2138
11 | B | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
Miscellaneous Items
11 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 145 | M2 | 2 |  |  | 0 | 8 | 8 | 1160 | 2320 |  | 100% | 0% | 100% | 2320 | 0 | 2320
11 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 76 | M2 | 2 |  |  | 0 | 8 | 8 | 608 | 1216 |  | 100% | 0% | 100% | 1216 | 0 | 1216
11 |  | Total Amount for TYPE -9A | [14 empty] | 146745.5 | 0 | 146745.5
12 |  | TYPE -09B (2 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
12 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.75 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 1400 | 0 | 100% | 0% | 100% | 1400 | 0 | 1400
12 | B | 20mm thick polished Crystal White, cut to size. | 0.55 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 536.8 | 0 | 100% | 0% | 100% | 536.8 | 0 | 536.8
12 | C | 20mm thick polished Crystal White, maximum 141mm width border. | 1 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 488 | 976 | 0 | 100% | 0% | 100% | 976 | 0 | 976
12 | D | 7 x 5mm Brass strip insert in brushed finish. | 5.9 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 336.3 | 672.6 |  | 100% | 0% | 100% | 672.6 | 0 | 672.6
12 | Add | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 2 | Crystal White | 20 | 123 | 48 | 171 | 171 | 342 | 0 | 100% | 0% | 100% | 342 | 0 | 342
Living Room
12 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 6.7 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 2680 | 5360 | 0 | 100% | 0% | 100% | 5360 | 0 | 5360
12 | F | 20mm thick polished Crystal White, cut to size. | 3.05 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1488.4 | 2976.8 | 0 | 100% | 0% | 100% | 2976.8 | 0 | 2976.8
12 | G | 20mm thick polished Crystal White, average of 150mm width border. | 2.75 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 2684 | 0 | 100% | 0% | 100% | 2684 | 0 | 2684
12 | H | 7 x 5mm Brass strip insert in brushed finish. | 16.8 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 957.6 | 1915.2 |  | 100% | 0% | 100% | 1915.2 | 0 | 1915.2
12 | J | 7 x 5mm Brass strip insert in brushed finish. | 10.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 598.5 | 1197 |  | 100% | 0% | 100% | 1197 | 0 | 1197
12 | K | Threshold (20mm thick polished Crystal White); 270mm wide x 860mm length. | 1 | No | 2 | Crystal White | 20 | 109 | 43 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
Toilet
12 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.85 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 340 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
12 | M | 20mm thick polished Crystal White, average 116mm width border. | 0.7 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 683.2 | 0 | 100% | 0% | 100% | 683.2 | 0 | 683.2
12 | N | 7 x 5mm Brass strip insert in brushed finish. | 3.65 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 208.05 | 416.1 |  | 100% | 0% | 100% | 416.1 | 0 | 416.1
12 | P | Threshold (20mm thick); 270mm wide x 750mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 95 | 37 | 132 | 132 | 264 | 0 | 100% | 0% | 100% | 264 | 0 | 264
Bedroom
12 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 3.95 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 1580 | 3160 | 0 | 100% | 0% | 100% | 3160 | 0 | 3160
12 | B | 20mm thick polished Crystal White, cut to size. | 1.15 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 561.2 | 1122.4 | 0 | 100% | 0% | 100% | 1122.4 | 0 | 1122.4
12 | C | 20mm thick polished Crystal White, average of 141mm width border. | 1.95 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 951.6 | 1903.2 | 0 | 100% | 0% | 100% | 1903.2 | 0 | 1903.2
12 | D | 7 x 5mm Brass strip insert in brushed finish. | 13.05 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 743.85 | 1487.7 |  | 100% | 0% | 100% | 1487.7 | 0 | 1487.7
12 | E | 7 x 5mm Brass strip insert in brushed finish. | 10.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 598.5 | 1197 |  | 100% | 0% | 100% | 1197 | 0 | 1197
12 | F | Threshold (20mm thick polished Crystal White); 300mm wide x 925mm length. | 1 | No | 2 | Crystal White | 20 | 128 | 51 | 179 | 179 | 358 | 0 | 100% | 0% | 100% | 358 | 0 | 358
12 | G | Threshold (20mm thick polished Crystal White); 320mm wide x 750mm length. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
12 | H | 7 x 5mm Brass strip insert in brushed finish. 750mm length (only the length between threshold and carpet, other locations are excluded) | 1.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 85.5 | 171 |  | 100% | 0% | 100% | 171 | 0 | 171
Bathroom
12 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 5.4 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 2160 | 4320 | 0 | 100% | 0% | 100% | 4320 | 0 | 4320
12 | K | 20mm thick polished Crystal White, average 153mm width border. | 1.85 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 902.8 | 1805.6 | 0 | 100% | 0% | 100% | 1805.6 | 0 | 1805.6
12 | L | 7 x 5mm Brass strip insert in brushed finish. | 11.2 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 638.4 | 1276.8 |  | 100% | 0% | 100% | 1276.8 | 0 | 1276.8
12 | M | Threshold (20mm thick); 320mm wide x 750mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
Shower
12 | P | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.6 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 1280 | 0 | 100% | 0% | 100% | 1280 | 0 | 1280
12 | Q | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
Toilet
12 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 640 | 0 | 100% | 0% | 100% | 640 | 0 | 640
12 | B | 20mm thick polished Crystal White, average of 110mm width border; 4545mm length. | 0.5 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 244 | 488 | 0 | 100% | 0% | 100% | 488 | 0 | 488
12 | C | 7 x 5mm Brass strip insert in brushed finish. | 3.65 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 208.05 | 416.1 |  | 100% | 0% | 100% | 416.1 | 0 | 416.1
12 | D | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
Balcony Floor Finishes
12 | E | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 49 | M2 | 2 | PC Rate | 20 | 50 | 100 | 150 | 7350 | 14700 | 0 | 100% | 0% | 100% | 14700 | 0 | 14700
Wall Finishes
Bathroom
12 | F | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.9 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 9357.2 | 18714.4 | 0 | 100% | 0% | 100% | 18714.4 | 0 | 18714.4
12 | G | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 10.3 | Lm | 2 | Crystal White | 20 | 86 | 48 | 134 | 1380.2 | 2760.4 | 0 | 100% | 0% | 100% | 2760.4 | 0 | 2760.4
Shower
12 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.55 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 6625.4 | 13250.8 | 0 | 100% | 0% | 100% | 13250.8 | 0 | 13250.8
12 | J | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.4 | Lm | 2 | Crystal White | 20 | 94 | 56 | 150 | 660 | 1320 | 0 | 100% | 0% | 100% | 1320 | 0 | 1320
Toilet
12 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.1 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 2574.8 | 5149.6 | 0 | 100% | 0% | 100% | 5149.6 | 0 | 5149.6
12 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.75 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 457.5 | 915 | 0 | 100% | 0% | 100% | 915 | 0 | 915
Toilet @ Foyer
12 | B | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 5.8 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 3642.4 | 7284.8 | 0 | 100% | 0% | 100% | 7284.8 | 0 | 7284.8
12 | C | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.3 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 646.6 | 1293.2 | 0 | 100% | 0% | 100% | 1293.2 | 0 | 1293.2
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
12 | D | Living : 270mm wide; total size of 860 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 2148 | 0 | 100% | 0% | 100% | 2148 | 0 | 2148
12 | E | Bedroom : 270mm wide; total size of 925 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 2174 | 0 | 100% | 0% | 100% | 2174 | 0 | 2174
12 | F | Toilet @ Foyer : (110 + 110)mm wide); total size of 860 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 634 | 286 | 920 | 920 | 1840 | 0 | 100% | 0% | 100% | 1840 | 0 | 1840
12 | G | Bathroom : (135 + 135)mm wide); total size of 750 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 710 | 343 | 1053 | 2106 | 4212 | 0 | 100% | 0% | 100% | 4212 | 0 | 4212
12 | Add | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 3856 | 0 | 100% | 0% | 100% | 3856 | 0 | 3856
Joinery Items
Living
12 | J | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 262 | 134 | 396 | 396 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
12 | K | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 3346 | 0 | 100% | 0% | 100% | 3346 | 0 | 3346
Walk-In Closet
12 | A | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1305mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 364 | 195 | 559 | 559 | 1118 | 0 | 100% | 0% | 100% | 1118 | 0 | 1118
Bathroom
12 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2055mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 2055mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1576 | 718 | 2294 | 2294 | 4588 | 0 | 100% | 0% | 100% | 4588 | 0 | 4588
12 | Add | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 372 | 182 | 554 | 1108 | 2216 | 0 | 100% | 0% | 100% | 2216 | 0 | 2216
12 | Add | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 43 | 19 | 62 | 124 | 248 | 0 | 100% | 0% | 100% | 248 | 0 | 248
Sanitaryware - Stone Works
12 | C | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 2 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 2504 | 0 | 100% | 0% | 100% | 2504 | 0 | 2504
Shower
12 | D | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 492 | 240 | 732 | 732 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
12 | E | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1035mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 251 | 105 | 356 | 356 | 712 | 0 | 100% | 0% | 100% | 712 | 0 | 712
12 | F | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 44 | 12 | 56 | 112 | 224 | 0 | 100% | 0% | 100% | 224 | 0 | 224
Toilet
12 | G | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 102 | 50 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
12 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
Toilet @ Foyer
12 | A | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 102 | 50 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
12 | B | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (150 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 2 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 2138 | 0 | 100% | 0% | 100% | 2138 | 0 | 2138
12 | C | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
Miscellaneous Items
12 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 151 | M2 | 2 |  |  | 0 | 8 | 8 | 1208 | 2416 |  | 100% | 0% | 100% | 2416 | 0 | 2416
12 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 85 | M2 | 2 |  |  | 0 | 8 | 8 | 680 | 1360 |  | 100% | 0% | 100% | 1360 | 0 | 1360
12 |  | Total Amount for TYPE -9B | [14 empty] | 144657.7 | 0 | 144657.7
13 |  | TYPE -10A (5 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
13 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.15 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 860 | 4300 | 0 | 100% | 0% | 100% | 4300 | 0 | 4300
13 | B | 20mm thick polished Crystal White, maximum 135mm width border. | 0.65 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 317.2 | 1586 | 0 | 100% | 0% | 100% | 1586 | 0 | 1586
13 | C | 7 x 5mm Brass strip insert in brushed finish. | 5.9 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 336.3 | 1681.5 |  | 100% | 0% | 100% | 1681.5 | 0 | 1681.5
13 | Add | Threshold (20mm thick polished Crystal White); 270mm wide x 980mm length | 1 | No | 5 | Crystal White | 20 | 123 | 48 | 171 | 171 | 855 | 0 | 100% | 0% | 100% | 855 | 0 | 855
Living Room
13 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 20.15 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 8060 | 40300 | 0 | 100% | 0% | 100% | 40300 | 0 | 40300
13 | E | 20mm thick polished Crystal White, cut to size. | 20.15 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 9833.2 | 49166 | 0 | 100% | 0% | 100% | 49166 | 0 | 49166
13 | F | 20mm thick polished Crystal White, average of 148mm width border. | 3.35 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1634.8 | 8174 | 0 | 100% | 0% | 100% | 8174 | 0 | 8174
13 | G | 7 x 5mm Brass strip insert in brushed finish. | 21.35 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1216.95 | 6084.75 |  | 100% | 0% | 100% | 6084.75 | 0 | 6084.75
13 | H | Threshold (20mm thick polished Crystal White); 300mm wide x 1490mm length. | 1 | No | 5 | Crystal White | 20 | 204 | 82 | 286 | 286 | 1430 | 0 | 100% | 0% | 100% | 1430 | 0 | 1430
Toilet
13 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.85 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 340 | 1700 | 0 | 100% | 0% | 100% | 1700 | 0 | 1700
13 | K | 20mm thick polished Crystal White, average 110mm width border. | 0.45 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 1098 | 0 | 100% | 0% | 100% | 1098 | 0 | 1098
13 | L | 7 x 5mm Brass strip insert in brushed finish. | 3.75 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 213.75 | 1068.75 |  | 100% | 0% | 100% | 1068.75 | 0 | 1068.75
13 | M | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Bedroom
13 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.6 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1840 | 9200 | 0 | 100% | 0% | 100% | 9200 | 0 | 9200
13 | P | 20mm thick polished Crystal White, cut to size. | 2.85 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1390.8 | 6954 | 0 | 100% | 0% | 100% | 6954 | 0 | 6954
13 | A | 20mm thick polished Crystal White, average of 139mm width border. | 3.3 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1610.4 | 8052 | 0 | 100% | 0% | 100% | 8052 | 0 | 8052
13 | B | 7 x 5mm Brass strip insert in brushed finish. | 14.25 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 812.25 | 4061.25 |  | 100% | 0% | 100% | 4061.25 | 0 | 4061.25
13 | C | 7 x 5mm Brass strip insert in brushed finish. | 11.15 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 635.55 | 3177.75 |  | 100% | 0% | 100% | 3177.75 | 0 | 3177.75
13 | D | Threshold (20mm thick polished Crystal White); 320mm wide x 945mm length. | 0.9 | Lm | 5 | Crystal White | 20 | 135 | 55 | 190 | 171 | 855 | 0 | 100% | 0% | 100% | 855 | 0 | 855
13 | E | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 0.9 | Lm | 5 | Crystal White | 20 | 125 | 51 | 176 | 158.4 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
13 | F | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 1.72 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 98.04 | 490.2 |  | 100% | 0% | 100% | 490.2 | 0 | 490.2
Bathroom
13 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.8 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1520 | 7600 | 0 | 100% | 0% | 100% | 7600 | 0 | 7600
13 | H | 20mm thick polished Crystal White, average 153mm width border. | 1.45 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 707.6 | 3538 | 0 | 100% | 0% | 100% | 3538 | 0 | 3538
13 | J | 7 x 5mm Brass strip insert in brushed finish. | 10.05 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 572.85 | 2864.25 |  | 100% | 0% | 100% | 2864.25 | 0 | 2864.25
13 | K | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1.6 | Lm | 5 | Crystal White | 20 | 125 | 51 | 176 | 281.6 | 1408 | 0 | 100% | 0% | 100% | 1408 | 0 | 1408
Shower
13 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.45 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 580 | 2900 | 0 | 100% | 0% | 100% | 2900 | 0 | 2900
13 | N | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Powder Room
13 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 3500 | 0 | 100% | 0% | 100% | 3500 | 0 | 3500
13 | Q | 20mm thick polished Crystal White, average of 116mm width border. | 0.65 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 317.2 | 1586 | 0 | 100% | 0% | 100% | 1586 | 0 | 1586
13 | R | 7 x 5mm Brass strip insert in brushed finish. | 5.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 330.6 | 1653 |  | 100% | 0% | 100% | 1653 | 0 | 1653
13 | S | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Balcony Floor Finishes
13 | A | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 6.1 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 915 | 4575 | 0 | 100% | 0% | 100% | 4575 | 0 | 4575
Wall Finishes
Bathroom
13 | B | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 16.4 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 10299.2 | 51496 | 0 | 100% | 0% | 100% | 51496 | 0 | 51496
13 | C | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 8.9 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 1192.6 | 5963 | 0 | 100% | 0% | 100% | 5963 | 0 | 5963
Shower
13 | D | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 9.05 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5683.4 | 28417 | 0 | 100% | 0% | 100% | 28417 | 0 | 28417
13 | E | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.95 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 592.5 | 2962.5 | 0 | 100% | 0% | 100% | 2962.5 | 0 | 2962.5
Toilet
13 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.05 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2543.4 | 12717 | 0 | 100% | 0% | 100% | 12717 | 0 | 12717
13 | G | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.75 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 457.5 | 2287.5 | 0 | 100% | 0% | 100% | 2287.5 | 0 | 2287.5
Powder Room
13 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.3 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 3956.4 | 19782 | 0 | 100% | 0% | 100% | 19782 | 0 | 19782
13 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.8 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 707.6 | 3538 | 0 | 100% | 0% | 100% | 3538 | 0 | 3538
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
13 | A | Living : 300mm wide; total size of 1490 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 868 | 433 | 1301 | 1301 | 6505 | 0 | 100% | 0% | 100% | 6505 | 0 | 6505
13 | B | Bedroom : 320mm wide; total size of 945 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 831 | 421 | 1252 | 1252 | 6260 | 0 | 100% | 0% | 100% | 6260 | 0 | 6260
13 | C | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 964 | 4820 | 0 | 100% | 0% | 100% | 4820 | 0 | 4820
13 | D | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 724 | 350 | 1074 | 2148 | 10740 | 0 | 100% | 0% | 100% | 10740 | 0 | 10740
13 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
Joinery Items
Walk-In Closet
13 | F | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1400mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 388 | 209 | 597 | 597 | 2985 | 0 | 100% | 0% | 100% | 2985 | 0 | 2985
Bathroom
13 | G | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2055mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 2055mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 1576 | 718 | 2294 | 2294 | 11470 | 0 | 100% | 0% | 100% | 11470 | 0 | 11470
Sanitaryware - Stoneworks
13 | H | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 5 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 6260 | 0 | 100% | 0% | 100% | 6260 | 0 | 6260
Shower
13 | J | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 305mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 717 | 350 | 1067 | 1067 | 5335 | 0 | 100% | 0% | 100% | 5335 | 0 | 5335
13 | K | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1205mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 287 | 122 | 409 | 409 | 2045 | 0 | 100% | 0% | 100% | 2045 | 0 | 2045
13 | A | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
Toilet
13 | B | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 910mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 97 | 48 | 145 | 145 | 725 | 0 | 100% | 0% | 100% | 725 | 0 | 725
13 | C | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Toilet @ Foyer
13 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1065mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 116 | 57 | 173 | 173 | 865 | 0 | 100% | 0% | 100% | 865 | 0 | 865
13 | E | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (900 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 5 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 5345 | 0 | 100% | 0% | 100% | 5345 | 0 | 5345
13 | F | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Miscellaneous Items
13 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 140 | M2 | 5 |  |  | 0 | 8 | 8 | 1120 | 5600 |  | 100% | 0% | 100% | 5600 | 0 | 5600
13 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 77 | M2 | 5 |  |  | 0 | 8 | 8 | 616 | 3080 |  | 100% | 0% | 100% | 3080 | 0 | 3080
13 |  | Total Amount for TYPE -10A | [14 empty] | 392388.45 | 0 | 392388.45
14 |  | TYPE -10B (3 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
14 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.25 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1300 | 3900 | 0 | 100% | 0% | 100% | 3900 | 0 | 3900
14 | B | 20mm thick polished Crystal White, maximum 130mm width border. | 1.25 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 610 | 1830 | 0 | 100% | 0% | 100% | 1830 | 0 | 1830
14 | C | 7 x 5mm Brass strip insert in brushed finish. | 8.55 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 487.35 | 1462.05 |  | 100% | 0% | 100% | 1462.05 | 0 | 1462.05
14 | D | Threshold (20mm thick); 175mm wide x 1100mm length polished Crystal White | 1 | No | 3 | Crystal White | 20 | 106 | 35 | 141 | 141 | 423 | 0 | 100% | 0% | 100% | 423 | 0 | 423
Living Room
14 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 27.2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 10880 | 32640 | 0 | 100% | 0% | 100% | 32640 | 0 | 32640
14 | F | 20mm thick polished Crystal White, cut to size. | 4.5 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 2196 | 6588 | 0 | 100% | 0% | 100% | 6588 | 0 | 6588
14 | G | 20mm thick polished Crystal White, average of 202mm width border. | 8.3 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 4050.4 | 12151.2 | 0 | 100% | 0% | 100% | 12151.2 | 0 | 12151.2
14 | H | 7 x 5mm Brass strip insert in brushed finish. | 27.25 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 1553.25 | 4659.75 |  | 100% | 0% | 100% | 4659.75 | 0 | 4659.75
14 | J | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 3 | Crystal White | 20 | 231 | 97 | 328 | 328 | 984 | 0 | 100% | 0% | 100% | 984 | 0 | 984
Toilet
14 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.85 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 340 | 1020 | 0 | 100% | 0% | 100% | 1020 | 0 | 1020
14 | L | 20mm thick polished Crystal White, average 110mm width border. | 0.5 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 244 | 732 | 0 | 100% | 0% | 100% | 732 | 0 | 732
14 | M | 7 x 5mm Brass strip insert in brushed finish. | 3.85 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 219.45 | 658.35 |  | 100% | 0% | 100% | 658.35 | 0 | 658.35
14 | N | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
Bedroom
14 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 2000 | 6000 | 0 | 100% | 0% | 100% | 6000 | 0 | 6000
14 | A | 20mm thick polished Crystal White, cut to size. | 1.85 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 902.8 | 2708.4 | 0 | 100% | 0% | 100% | 2708.4 | 0 | 2708.4
14 | B | 20mm thick polished Crystal White, average of 163mm width border. | 3.1 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 4538.4 | 0 | 100% | 0% | 100% | 4538.4 | 0 | 4538.4
14 | C | 7 x 5mm Brass strip insert in brushed finish. | 17.7 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 1008.9 | 3026.7 |  | 100% | 0% | 100% | 3026.7 | 0 | 3026.7
14 | D | 7 x 5mm Brass strip insert in brushed finish. | 15.1 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 860.7 | 2582.1 |  | 100% | 0% | 100% | 2582.1 | 0 | 2582.1
14 | E | Threshold (20mm thick polished Crystal White); 320mm wide x 945mm length. | 1 | Lm | 3 | Crystal White | 20 | 135 | 55 | 190 | 190 | 570 | 0 | 100% | 0% | 100% | 570 | 0 | 570
14 | F | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 1 | Lm | 3 | Crystal White | 20 | 125 | 51 | 176 | 176 | 528 | 0 | 100% | 0% | 100% | 528 | 0 | 528
14 | G | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 1.72 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 98.04 | 294.12 |  | 100% | 0% | 100% | 294.12 | 0 | 294.12
Bathroom
14 | H | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 5.25 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 2100 | 6300 | 0 | 100% | 0% | 100% | 6300 | 0 | 6300
14 | J | 20mm thick polished Crystal White, average 165mm width border. | 0.35 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 170.8 | 512.4 | 0 | 100% | 0% | 100% | 512.4 | 0 | 512.4
14 | K | 7 x 5mm Brass strip insert in brushed finish. | 12.3 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 701.1 | 2103.3 |  | 100% | 0% | 100% | 2103.3 | 0 | 2103.3
14 | L | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1 | Lm | 3 | Crystal White | 20 | 125 | 51 | 176 | 176 | 528 | 0 | 100% | 0% | 100% | 528 | 0 | 528
Shower
14 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 3.3 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1320 | 3960 | 0 | 100% | 0% | 100% | 3960 | 0 | 3960
14 | P | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
Toilet @ Foyer
14 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 2640 | 0 | 100% | 0% | 100% | 2640 | 0 | 2640
14 | R | 20mm thick polished Crystal White, average of 116mm width border. | 0.8 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 390.4 | 1171.2 | 0 | 100% | 0% | 100% | 1171.2 | 0 | 1171.2
14 | A | 7 x 5mm Brass strip insert in brushed finish. | 6.4 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 364.8 | 1094.4 |  | 100% | 0% | 100% | 1094.4 | 0 | 1094.4
14 | B | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
Balcony Floor Finishes
14 | C | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 4 | M2 | 3 | PC Rate | 20 | 50 | 100 | 150 | 600 | 1800 | 0 | 100% | 0% | 100% | 1800 | 0 | 1800
Wall Finishes
Bathroom
14 | D | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.5 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 9106 | 27318 | 0 | 100% | 0% | 100% | 27318 | 0 | 27318
14 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 11.4 | Lm | 3 | Crystal White | 20 | 86 | 48 | 134 | 1527.6 | 4582.8 | 0 | 100% | 0% | 100% | 4582.8 | 0 | 4582.8
Shower
14 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 15.95 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 10016.6 | 30049.8 | 0 | 100% | 0% | 100% | 30049.8 | 0 | 30049.8
14 | G | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.65 | Lm | 3 | Crystal White | 20 | 94 | 56 | 150 | 997.5 | 2992.5 | 0 | 100% | 0% | 100% | 2992.5 | 0 | 2992.5
Toilet
14 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.3 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 2072.4 | 6217.2 | 0 | 100% | 0% | 100% | 6217.2 | 0 | 6217.2
14 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.95 | Lm | 3 | Crystal White | 20 | 79 | 43 | 122 | 481.9 | 1445.7 | 0 | 100% | 0% | 100% | 1445.7 | 0 | 1445.7
Toilet @ Foyer
14 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.1 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 3830.8 | 11492.4 | 0 | 100% | 0% | 100% | 11492.4 | 0 | 11492.4
14 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.5 | Lm | 3 | Crystal White | 20 | 79 | 43 | 122 | 793 | 2379 | 0 | 100% | 0% | 100% | 2379 | 0 | 2379
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
14 | B | Living : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 4434 | 0 | 100% | 0% | 100% | 4434 | 0 | 4434
14 | C | Bedroom : 320mm wide; total size of 945 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 831 | 421 | 1252 | 1252 | 3756 | 0 | 100% | 0% | 100% | 3756 | 0 | 3756
14 | D | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 660 | 304 | 964 | 964 | 2892 | 0 | 100% | 0% | 100% | 2892 | 0 | 2892
14 | E | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 2 | No | 3 | Crystal White | 20 | 724 | 350 | 1074 | 2148 | 6444 | 0 | 100% | 0% | 100% | 6444 | 0 | 6444
14 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 660 | 304 | 964 | 964 | 2892 | 0 | 100% | 0% | 100% | 2892 | 0 | 2892
Joinery Items
Walk-In Closet
14 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1400mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 3 | Crystal White | 20 | 388 | 209 | 597 | 597 | 1791 | 0 | 0% | 0% | 0% | 0 | 0 | 0
Bathroom
14 | H | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 6237 | 0 | 100% | 0% | 100% | 6237 | 0 | 6237
Sanitaryware - Stoneworks
14 | J | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 3 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 3756 | 0 | 100% | 0% | 100% | 3756 | 0 | 3756
Shower
14 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 492 | 240 | 732 | 732 | 2196 | 0 | 100% | 0% | 100% | 2196 | 0 | 2196
14 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1430mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 334 | 143 | 477 | 477 | 1431 | 0 | 100% | 0% | 100% | 1431 | 0 | 1431
14 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 3 | Volakas | 20 | 44 | 12 | 56 | 112 | 336 | 0 | 100% | 0% | 100% | 336 | 0 | 336
Toilet
14 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 910mm length, pencil edge finish. | 1 | No | 3 | Volakas | 20 | 97 | 48 | 145 | 145 | 435 | 0 | 100% | 0% | 100% | 435 | 0 | 435
14 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 3 | Volakas | 20 | 25 | 5 | 30 | 30 | 90 | 0 | 100% | 0% | 100% | 90 | 0 | 90
Toilet @ Foyer
14 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1245mm length, pencil edge finish. | 1 | No | 3 | Volakas | 20 | 135 | 67 | 202 | 202 | 606 | 0 | 100% | 0% | 100% | 606 | 0 | 606
14 | G | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (900 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 3 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 3207 | 0 | 100% | 0% | 100% | 3207 | 0 | 3207
14 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 3 | Volakas | 20 | 25 | 5 | 30 | 30 | 90 | 0 | 100% | 0% | 100% | 90 | 0 | 90
Miscellaneous Items
14 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 138 | M2 | 3 |  |  | 0 | 8 | 8 | 1104 | 3312 | 0 | 99.24% | 0% | 99.24% | 3286.8333 | 0 | 3286.8333
14 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 71 | M2 | 3 |  |  | 0 | 8 | 8 | 568 | 1704 | 0 | 99.24% | 0% | 99.24% | 1691.0519 | 0 | 1691.0519
14 |  | Total Amount for TYPE -10B | [14 empty] | 238886.6552 | 0 | 238886.6552
15 |  | TYPE -11A/11B/11C/11D (19 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Entrance
15 | A | Supply and installation of 20mm thick brushed Beige Travertine, 335 x 335mm. | 1.6 | M2 | 19 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 12160 | 0 | 98.95% | 0% | 98.95% | 12032 | 0 | 12032
15 | B | Supply and installation of 20mm thick brushed Beige Stone, 335 x 335mm. | 1.6 | M2 | 19 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 12160 | 0 | 98.95% | 0% | 98.95% | 12032 | 0 | 12032
15 | C | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 7.2 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 410.4 | 7797.6 | 0 | 84.21% | 0% | 84.21% | 6566.4 | 0 | 6566.4
15 | Add | Threshold To Main Entrance : Supply and installation of 20mm thick honed Volakas, 160mm W x 1100mm L | 1 | No | 19 | Volakas | 20 | 115 | 33 | 148 | 148 | 2812 | 0 | 98.95% | 0% | 98.95% | 2782.4 | 0 | 2782.4
Living Room
15 | D | Threshold To Connecting Room : Supply and installation of 20mm thick brushed Beige Travertine, 395mm W x 980mm L. | 1 | No | 19 | Beige Travertine | 20 | 139 | 71 | 210 | 210 | 3990 | 0 | 88.42% | 0% | 88.42% | 3528 | 0 | 3528
15 | E | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone threshold | 1.8 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 102.6 | 1949.4 |  | 73.68% | 14.74% | 88.42% | 1436.4 | 287.28 | 1723.68
Vestibule
15 | F | Supply and installation of 20mm thick honed Volakas floor border, cut to size. | 2.5 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 1595 | 30305 | 0 | 88.42% | 0% | 88.42% | 26796 | 0 | 26796
15 | G | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border/threshold to bedroom. | 7.3 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 416.1 | 7905.9 | 20.44 | 73.68% | 14.74% | 88.42% | 5825.4 | 1165.08 | 6990.48
15 | H | Threshold To Bed Room : Supply and installation of 20mm thick honed Volakas, 270mm W x 1145mm L | 1 | No | 19 | Volakas | 20 | 168 | 56 | 224 | 224 | 4256 | 0 | 88.42% | 0% | 88.42% | 3763.2 | 0 | 3763.2
15 | J | Threshold To Walk-in Closet : Supply and installation of 20mm thick honed Volakas, 220mm W x 865mm L | 1 | No | 19 | Volakas | 20 | 110 | 35 | 145 | 145 | 2755 | 0 | 88.42% | 0% | 88.42% | 2436 | 0 | 2436
Walk-In Closet
15 | K | Supply and installation of 20mm thick honed Volakas floor border, cut to size. | 1.35 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 861.3 | 16364.7 | 1.89 | 88.42% | 7.368% | 95.79% | 14469.84 | 1205.82 | 15675.66
15 | L | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 4.25 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 242.25 | 4602.75 |  | 73.68% | 15.79% | 89.47% | 3391.5 | 726.75 | 4118.25
15 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 710.2 | 13493.8 | 0 | 100% | 0% | 100% | 13493.8 | 0 | 13493.8
Bathroom
15 | M | 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 3.45 | M2 | 19 | Pink Desert | 20 | 503 | 125 | 628 | 2166.6 | 41165.4 | 0 | 96.84% | 0% | 96.84% | 39865.44 | 0 | 39865.44
15 | N | 20mm thick honed Volakas in herringbone pattern at 100mm wide stone strips, as per drawing. | 4.15 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 2647.7 | 50306.3 | 0 | 96.84% | 0% | 96.84% | 48717.68 | 0 | 48717.68
15 | P | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 11 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 627 | 11913 |  | 84.21% | 5.263% | 89.47% | 10032 | 627 | 10659
15 | A | Threshold To Bathroom : Supply and installation of 20mm thick honed Volakas, 420mm W x 1130mm L | 1 | No | 19 | Volakas | 20 | 230 | 85 | 315 | 315 | 5985 | 0 | 96.84% | 0% | 96.84% | 5796 | 0 | 5796
Toilet
15 | B | 20mm thick honed Volakas in herringbone pattern at 100mm wide stone strips, as per drawing. | 0.8 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 510.4 | 9697.6 | 0 | 97.89% | 0% | 97.89% | 9493.44 | 0 | 9493.44
15 | C | 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 1 | M2 | 19 | Pink Desert | 20 | 503 | 125 | 628 | 628 | 11932 | 0 | 97.89% | 0% | 97.89% | 11680.8 | 0 | 11680.8
15 | D | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 3.9 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 222.3 | 4223.7 |  | 78.95% | 5.263% | 84.21% | 3334.5 | 222.3 | 3556.8
Shower
15 | E | 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 1.9 | M2 | 19 | Pink Desert | 20 | 503 | 125 | 628 | 1193.2 | 22670.8 | 0 | 89.47% | 0% | 89.47% | 20284.4 | 0 | 20284.4
Balcony Floor Finishes
15 | F | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10.35 | M2 | 19 | PC Rate | 20 | 50 | 100 | 150 | 1552.5 | 29497.5 | 0 | 100% | 0% | 100% | 29497.5 | 0 | 29497.5
Wall Finishes
Pantry
15 | G | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 3.05 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 1915.4 | 36392.6 |  |  |  |  | 0 | 0 | 0
15 | H | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 2.2 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 294.8 | 5601.2 |  |  |  |  | 0 | 0 | 0
15 |  | Skirting : 20mm thick honed Volakas 150mm high skirting, chamfered edge. | 3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 402 | 7638 |  |  |  |  | 0 | 0 | 0
15 | J | Skirting : 20mm thick honed Volakas 150mm high skirting with ventilation slots as applicable, chamfered edge. | 1.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 174.2 | 3309.8 |  |  |  |  | 0 | 0 | 0
Walk-In Closet
15 | K | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 1.75 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 234.5 | 4455.5 |  |  |  |  | 0 | 0 | 0
Powder Room
15 | L | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 576.2 | 10947.8 | 0 | 100% | 0% | 100% | 10947.8 | 0 | 10947.8
15 | A | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 4.75 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 2983 | 56677 | 0 | 100% | 0% | 100% | 56677 | 0 | 56677
15 | B | Cistern Top : 20mm thick honed Volakas, 230mm W x 1455mm L, pencil edge finish. | 1 | No | 19 | Volakas | 20 | 163 | 81 | 244 | 244 | 4636 | 0 | 100% | 0% | 100% | 4636 | 0 | 4636
Bathroom
15 | C | Wall : 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 21.45 | M2 | 19 | Pink Desert | 20 | 503 | 188 | 691 | 14821.95 | 281617.05 | 0 | 100% | 0% | 100% | 281617.05 | 0 | 281617.05
15 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 3 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 1884 | 35796 | 0 | 100% | 0% | 100% | 35796 | 0 | 35796
15 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 576.2 | 10947.8 | 0 | 100% | 0% | 100% | 10947.8 | 0 | 10947.8
Shower
15 | D | Wall : 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 15.25 | M2 | 19 | Pink Desert | 20 | 503 | 188 | 691 | 10537.75 | 200217.25 | 0 | 100% | 0% | 100% | 200217.25 | 0 | 200217.25
15 | E | Skirting : 20mm thick honed Volakas (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 19 | Volakas | 20 | 111 | 55 | 166 | 747 | 14193 | 0 | 100% | 0% | 100% | 14193 | 0 | 14193
Toilet
15 | F | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 5.15 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 3234.2 | 61449.8 | 0 | 100% | 0% | 100% | 61449.8 | 0 | 61449.8
15 | G | To Wall : 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 6.7 | M2 | 19 | Pink Desert | 20 | 503 | 188 | 691 | 4629.7 | 87964.3 | 0 | 100% | 0% | 100% | 87964.3 | 0 | 87964.3
15 | H | Cistern Top : 20mm thick honed Volakas, 230mm W x 1055mm L, pencil edge finish. | 1 | No | 19 | Volakas | 20 | 116 | 57 | 173 | 173 | 3287 | 0 | 100% | 0% | 100% | 3287 | 0 | 3287
15 | J | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.75 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 636.5 | 12093.5 | 0 | 100% | 0% | 100% | 12093.5 | 0 | 12093.5
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick honed Volakas as per below details and drawing.
15 | K | Bedroom To Vestibule : 270mm wide; total size of 1160 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 766 | 369 | 1135 | 1135 | 21565 | 4.8843 | 73.68% | 15.79% | 89.47% | 15890 | 3405 | 19295
15 | L | Vestibule To Bathroom : 420mm wide; total size of 1160 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 1055 | 574 | 1629 | 1629 | 30951 | 5.0652 | 78.95% | 10.53% | 89.47% | 24435 | 3258 | 27693
15 | M | Bathroom To Toilet : 175mm wide; total size of 860 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 550 | 227 | 777 | 777 | 14763 | 0 | 94.74% | 0% | 94.74% | 13986 | 0 | 13986
15 | N | Bathroom To Shower : 175mm wide; total size of 860 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 550 | 227 | 777 | 777 | 14763 | 0 | 94.74% | 0% | 94.74% | 13986 | 0 | 13986
Joinery Items
Powder Room
15 | A | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (665 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 19 | Volakas | 20 | 668 | 297 | 965 | 965 | 18335 | 0 | 97.37% | 0% | 97.37% | 17852.5 | 0 | 17852.5
Pantry
15 | B | Counter : supply and installation of 20mm thick polished White Quartz (equivalent, as per our sample) top size of 655mm W x (1875 + 2225)mm L, mitered with 40mm high fascia. | 1 | No | 19 | Crystal White | 20 | 1027 | 684 | 1711 | 1711 | 32509 |  |  |  |  | 0 | 0 | 0
15 | C | Underside Stone Shelf To Overhead Cabinet : supply and installation of 20mm thick honed Volakas, size of (80 + 40 + 65)mm x (1885 + 1535)mm L. | 1 | No | 19 | Volakas | 20 | 429 | 150 | 579 | 579 | 11001 |  |  |  |  | 0 | 0 | 0
Living Room To Entrance
15 | D | Cupboard Top : supply & installation of 20mm thick honed Volakas top size of 400mm W x 450mm L, mitered with 40mm high fascia. | 2 | No | 19 | Volakas | 20 | 126 | 48 | 174 | 348 | 6612 |  |  |  |  | 0 | 0 | 0
Mini Bar @ Living Room
15 | E | Counter Top : supply & installation of 20mm thick honed Volakas top size of 595mm W x 2045mm L, mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 565 | 309 | 874 | 874 | 16606 | 3.2464 | 81.58% | 13.16% | 94.74% | 13547 | 2185 | 15732
Mini Bar Upper Shelf @ Living Room
15 | F | Shelf Top : supply & installation of 20mm thick honed Volakas top size of 245mm W x (2045 + 600)mm L, having 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 369 | 181 | 550 | 550 | 10450 | 1.8846 | 81.58% | 13.16% | 94.74% | 8525 | 1375 | 9900
Podium Battles To Upper Shelf Mini Bar @ Living Room
15 | G | Step-Like Podium : supply & installation of 20mm thick polished standard White Onyx top size of (100 + 100)mm W x (380 + 380)mm L, mitered with (65 + 100)mm high fascia. | 1 | No | 19 | White Onyx | 20 | 1330 | 67 | 1397 | 1397 | 26543 |  |  |  |  | 0 | 0 | 0
Living Room To Connecting Room
15 | H | Cabinet Top/Shelf : supply & installation of 20mm thick honed Volakas top size of 400/250mm W x 700mm L, both mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 141 | 74 | 215 | 215 | 4085 |  |  |  |  | 0 | 0 | 0
Vestibule
15 | J | Vanity Counter : supply and installation of 20mm thick honed Volakas top size of 600mm W x 1300mm L, mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 539 | 183 | 722 | 722 | 13718 | 0 | 97.37% | 0% | 97.37% | 13357 | 0 | 13357
Walk-In Closet
15 | K | Wardrobe Base : supply and installation of 20mm thick honed Volakas size of 650mm W x 1215mm L. | 1 | No | 19 | Volakas | 20 | 343 | 188 | 531 | 531 | 10089 |  |  |  |  | 0 | 0 | 0
15 | A | Luggage Counter : supply and installation of 20mm thick honed Volakas size of 650mm W x (965 + 615)mm L mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 470 | 259 | 729 | 729 | 13851 |  |  |  |  | 0 | 0 | 0
15 | B | Niche : supply and installation of 20mm thick honed Volakas size of 450 x 735 x 400mm depth, complete with surround and back cladding. | 1 | No | 19 | Volakas | 20 | 588 | 287 | 875 | 875 | 16625 | 0 | 100% | 0% | 100% | 16625 | 0 | 16625
15 | C | Skirting @ Cabinet : 20mm thick honed Volakas (150 + 115)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.15 | Lm | 19 | Volakas | 20 | 126 | 65 | 191 | 601.65 | 11431.35 |  |  |  |  | 0 | 0 | 0
Bathroom
15 | D | To Column : supply and installation of 20mm thick honed Volakas cladding to column, total size of (295 + 270 + 170 + 160)mm x 2650mm H. Shelf, elsewhere. | 2 | No | 19 | Volakas | 20 | 1018 | 530 | 1548 | 3096 | 58824 |  |  |  |  | 0 | 0 | 0
15 | E | Shelf : supply and installation of 20mm thick honed Volakas, 140mm W x 225mmL, mitered with 40mm high fascia. | 2 | No | 19 | Volakas | 20 | 22 | 10 | 32 | 64 | 1216 | 0 | 100% | 0% | 100% | 1216 | 0 | 1216
15 | F | Vanity Counter : supply and installation of 20mm thick honed Volakas, 560mm W x 985mmL, mitered with 250mm high fascia. Including integrated basin total size of 450 * 350 * 225mm depth (not block stone). | 2 | No | 19 | Volakas | 20 | 704 | 314 | 1018 | 2036 | 38684 | 0 | 97.37% | 0% | 97.37% | 37666 | 0 | 37666
15 | G | Bath Tub Top @ Bathroom : supply and installation of 20mm thick honed Volakas top size of maximum 100/480mm wide, total size of 930mm wide x 2040mm length. Complete with 590mm high cladding to 3-sides. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 19 | Volakas | 20 | 796 | 309 | 1105 | 1105 | 20995 | 0 | 100% | 0% | 100% | 20995 | 0 | 20995
Shower
15 | H | Shelf : supply and installation of 20mm thick honed Volakas, 180mm W x 600mmL, mitered with 40mm high fascia to 2-sides. | 1 | No | 19 | Volakas | 20 | 67 | 31 | 98 | 98 | 1862 | 0 | 100% | 0% | 100% | 1862 | 0 | 1862
15 | J | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1040mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 19 | Volakas | 20 | 208 | 104 | 312 | 312 | 5928 | 0 | 100% | 0% | 100% | 5928 | 0 | 5928
Miscellaneous Items
15 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 126 | M2 | 19 |  |  | 0 | 8 | 8 | 1008 | 19152 |  | 82.31% | 0.9348% | 83.24% | 15763.6042 | 179.0312 | 15942.6354
15 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 32 | M2 | 19 |  |  | 0 | 8 | 8 | 256 | 4864 |  | 82.31% | 0.9348% | 83.24% | 4003.455 | 45.4682 | 4048.9233
15 |  | Total Amount for TYPE -11A/11B/11C/11D | [14 empty] | 1292718.7592 | 14681.7294 | 1307400.4887
16 |  | TYPE -12A (5 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Entrance
16 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 6.9 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 2760 | 13800 | 0 | 100% | 0% | 100% | 13800 | 0 | 13800
16 | B | 20mm thick polished Crystal White, cut to size. | 0.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1342 | 0 | 100% | 0% | 100% | 1342 | 0 | 1342
16 | C | 20mm thick polished Crystal White, maximum 130mm width border. | 2.2 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1073.6 | 5368 | 0 | 100% | 0% | 100% | 5368 | 0 | 5368
16 | D | 7 x 5mm Brass strip insert in brushed finish. | 10.95 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 624.15 | 3120.75 |  | 100% | 0% | 100% | 3120.75 | 0 | 3120.75
16 | Add | Threshold To Main Entrance : Supply and installation of 20mm thick honed Volakas, 160mm W x 1100mm L | 1 | No | 5 | Volakas | 20 | 115 | 33 | 148 | 148 | 740 | 0 | 100% | 0% | 100% | 740 | 0 | 740
Living Room
16 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 27.35 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 10940 | 54700 | 0 | 100% | 0% | 100% | 54700 | 0 | 54700
16 | F | 20mm thick polished Crystal White, cut to size. | 3.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 7564 | 0 | 100% | 0% | 100% | 7564 | 0 | 7564
16 | G | 20mm thick polished Crystal White, average of 167mm width border. | 4.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 2000.8 | 10004 | 0 | 100% | 0% | 100% | 10004 | 0 | 10004
16 | H | 7 x 5mm Brass strip insert in brushed finish. | 23.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1322.4 | 6612 |  | 100% | 0% | 100% | 6612 | 0 | 6612
16 | J | 7 x 5mm Brass strip insert in brushed finish. | 12.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 729.6 | 3648 |  | 100% | 0% | 100% | 3648 | 0 | 3648
16 | K | Threshold (20mm thick polished Crystal White); 300mm wide x 1490mm length. | 1 | No | 5 | Crystal White | 20 | 204 | 82 | 286 | 286 | 1430 | 0 | 100% | 0% | 100% | 1430 | 0 | 1430
Toilet @ Foyer
16 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.6 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 3200 | 0 | 100% | 0% | 100% | 3200 | 0 | 3200
16 | M | 20mm thick polished Crystal White, average 110mm width border. | 0.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1342 | 0 | 100% | 0% | 100% | 1342 | 0 | 1342
16 | N | 7 x 5mm Brass strip insert in brushed finish. | 5.1 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 290.7 | 1453.5 |  | 100% | 0% | 100% | 1453.5 | 0 | 1453.5
16 |  | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
Bathroom
16 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 7.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 2920 | 14600 | 0 | 100% | 0% | 100% | 14600 | 0 | 14600
16 | B | 20mm thick polished Crystal White, cut to size. | 1.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 536.8 | 2684 | 0 | 100% | 0% | 100% | 2684 | 0 | 2684
16 | C | 20mm thick polished Crystal White, average of 121mm width border. | 1.95 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 951.6 | 4758 | 0 | 100% | 0% | 100% | 4758 | 0 | 4758
16 | D | 7 x 5mm Brass strip insert in brushed finish. | 15.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 866.4 | 4332 |  | 100% | 0% | 100% | 4332 | 0 | 4332
16 | E | 7 x 5mm Brass strip insert in brushed finish. | 12.5 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 712.5 | 3562.5 |  | 100% | 0% | 100% | 3562.5 | 0 | 3562.5
16 | F | Threshold (20mm thick polished Crystal White); 375mm wide x 860mm length. | 1 | No | 5 | Crystal White | 20 | 138 | 59 | 197 | 197 | 985 | 0 | 100% | 0% | 100% | 985 | 0 | 985
16 | G | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
16 | H | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 1.72 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 98.04 | 490.2 |  | 100% | 0% | 100% | 490.2 | 0 | 490.2
Vestibule
16 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 920 | 4600 | 0 | 100% | 0% | 100% | 4600 | 0 | 4600
16 | K | 20mm thick polished Crystal White, cut to size. | 0.7 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1708 | 0 | 100% | 0% | 100% | 1708 | 0 | 1708
16 | L | 20mm thick polished Crystal White, average of 160mm width border. | 1.2 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 585.6 | 2928 | 0 | 100% | 0% | 100% | 2928 | 0 | 2928
16 | M | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border/threshold to bedroom. | 6.15 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 350.55 | 1752.75 |  | 100% | 0% | 100% | 1752.75 | 0 | 1752.75
16 | N | Threshold To Walk-in Closet : Supply and installation of 20mm thick polished Crystal White, 270mm W x 860mm L | 1 | No | 5 | Crystal White | 20 | 109 | 43 | 152 | 152 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
16 | P | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 0.86 | Lm | 5 | Brass | 5 | 0 | 51 | 51 | 43.86 | 219.3 |  | 100% | 0% | 100% | 219.3 | 0 | 219.3
Bathroom
16 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.05 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3620 | 18100 | 0 | 100% | 0% | 100% | 18100 | 0 | 18100
16 | A | 20mm thick polished Crystal White, average 165mm width border. | 2.05 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1000.4 | 5002 | 0 | 100% | 0% | 100% | 5002 | 0 | 5002
16 | B | 7 x 5mm Brass strip insert in brushed finish. | 11.4 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 649.8 | 3249 |  | 100% | 0% | 100% | 3249 | 0 | 3249
16 | C | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 134 | 55 | 189 | 189 | 945 | 0 | 100% | 0% | 100% | 945 | 0 | 945
16 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.55 | Lm | 5 | Volakas | 20 | 91 | 43 | 134 | 877.7 | 4388.5 | 0 | 100% | 0% | 100% | 4388.5 | 0 | 4388.5
Shower
16 | D | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 3500 | 0 | 100% | 0% | 100% | 3500 | 0 | 3500
16 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Toilet
16 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.95 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 780 | 3900 | 0 | 100% | 0% | 100% | 3900 | 0 | 3900
16 | H | 20mm thick polished Crystal White, average of 116mm width border. | 0.7 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1708 | 0 | 100% | 0% | 100% | 1708 | 0 | 1708
16 | J | 7 x 5mm Brass strip insert in brushed finish. | 5.6 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 319.2 | 1596 |  | 100% | 0% | 100% | 1596 | 0 | 1596
16 | K | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
Balcony Floor Finishes
16 | L | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 13.2 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 1980 | 9900 | 0 | 100% | 0% | 100% | 9900 | 0 | 9900
Wall Finishes
Bathroom
16 | M | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 24.3 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 15260.4 | 76302 | 0 | 100% | 0% | 100% | 76302 | 0 | 76302
16 | N | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.1 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 549.4 | 2747 | 0 | 100% | 0% | 100% | 2747 | 0 | 2747
Shower
16 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 11.85 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 7441.8 | 37209 | 0 | 100% | 0% | 100% | 37209 | 0 | 37209
16 | B | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 675 | 3375 | 0 | 100% | 0% | 100% | 3375 | 0 | 3375
Toilet
16 | C | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 5.1 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 3202.8 | 16014 | 0 | 100% | 0% | 100% | 16014 | 0 | 16014
16 | D | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.7 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 573.4 | 2867 | 0 | 100% | 0% | 100% | 2867 | 0 | 2867
Toilet @ Foyer
16 | E | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.3 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 3956.4 | 19782 | 0 | 100% | 0% | 100% | 19782 | 0 | 19782
16 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.95 | Lm | 5 | Volakas | 20 | 91 | 43 | 134 | 797.3 | 3986.5 | 0 | 100% | 0% | 100% | 3986.5 | 0 | 3986.5
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick honed Volakas as per below details and drawing.
16 | G | Living : 300mm wide; total size of 1490 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 868 | 433 | 1301 | 1301 | 6505 | 0 | 100% | 0% | 100% | 6505 | 0 | 6505
16 | H | Bedroom : (145 + 160)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 792 | 397 | 1189 | 1189 | 5945 | 0 | 100% | 0% | 100% | 5945 | 0 | 5945
16 | J | Bedroom To Vestibule : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 5395 | 0 | 100% | 0% | 100% | 5395 | 0 | 5395
16 | K | Toilet @ Foyer : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 5395 | 0 | 100% | 0% | 100% | 5395 | 0 | 5395
16 | A | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 5435 | 0 | 100% | 0% | 100% | 5435 | 0 | 5435
16 | B | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 964 | 4820 | 0 | 100% | 0% | 100% | 4820 | 0 | 4820
Joinery Items
Mini Bar @ Living Room
16 | C | Counter Top : supply & installation of 20mm thick polished Volakas top size of 690mm W x 1550mm L, including shelf top size of 290mm W, both mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 686 | 390 | 1076 | 1076 | 5380 | 0 | 60% | 0% | 60% | 3228 | 0 | 3228
Vestibule
16 | D | Vanity Counter : supply and installation of 20mm thick polished Volakas top size of 550mm W x 1215mm L, mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 539 | 183 | 722 | 722 | 3610 | 1 | 80% | 20% | 100% | 2888 | 722 | 3610
Walk-In Closet
16 | E | Wardrobe Counter (smaller) : supply and installation of 20mm thick honed Volakas size of 650mm W x 700mm L, mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 208 | 114 | 322 | 322 | 1610 | 0 | 100% | 0% | 100% | 1610 | 0 | 1610
16 | F | Wardrobe Counter : supply and installation of 20mm thick polished Volakas size of 650mm W x 1590mm L mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 475 | 262 | 737 | 737 | 3685 | 0 | 100% | 0% | 100% | 3685 | 0 | 3685
Bathroom
16 | G | To Column : supply and installation of 20mm thick polished Volakas cladding to column, total size of (295 + 270 + 170 + 160)mm x 2650mm H. Shelf, elsewhere. | 2 | No | 5 | Volakas | 20 | 1018 | 530 | 1548 | 3096 | 15480 | 0 | 100% | 0% | 100% | 15480 | 0 | 15480
16 | H | Shelf : supply and installation of 20mm thick honed Volakas, 140mm W x 225mmL, mitered with 40mm high fascia. | 2 | No | 5 | Volakas | 20 | 22 | 10 | 32 | 64 | 320 | 0 | 100% | 0% | 100% | 320 | 0 | 320
16 | J | Vanity Counter : supply and installation of 20mm thick polished Volakas, 560mm W x 985mmL, mitered with 250mm high fascia. Including integrated basin total size of 450 * 350 * 225mm depth (not block stone). -- back cladding, elsewhere. | 2 | No | 5 | Volakas | 20 | 704 | 314 | 1018 | 2036 | 10180 | 2 | 80% | 20% | 100% | 8144 | 2036 | 10180
16 | K | Bath Tub Top @ Bathroom : supply and installation of 20mm thick honed Volakas top size of maximum 100/480mm wide, total size of 930mm wide x 2040mm length. Complete with 590mm high cladding to 3-sides. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 5 | Volakas | 20 | 796 | 309 | 1105 | 1105 | 5525 | 0 | 100% | 0% | 100% | 5525 | 0 | 5525
Shower
16 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 602 | 294 | 896 | 896 | 4480 | 0 | 100% | 0% | 100% | 4480 | 0 | 4480
16 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1290mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 303 | 129 | 432 | 432 | 2160 | 0 | 100% | 0% | 100% | 2160 | 0 | 2160
16 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
Toilet
16 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 102 | 50 | 152 | 152 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
16 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Toilet @ Foyer
16 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1350mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 145 | 72 | 217 | 217 | 1085 | 0 | 100% | 0% | 100% | 1085 | 0 | 1085
16 | G | Vanity Counter : supply and installation of 20mm thick polished Volakas, top size of 225mm W x (1370 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 5 | Volakas | 20 | 838 | 378 | 1216 | 1216 | 6080 | 1 | 80% | 20% | 100% | 4864 | 1216 | 6080
16 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
Miscellaneous Items
16 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 173 | M2 | 5 |  |  | 0 | 8 | 8 | 1384 | 6920 |  | 98.7% | 0.8453% | 99.54% | 6829.8246 | 58.4977 | 6888.3223
16 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 93 | M2 | 5 |  |  | 0 | 8 | 8 | 744 | 3720 |  | 98.7% | 0.8453% | 99.54% | 3671.5242 | 31.4468 | 3702.971
16 |  | Total Amount for TYPE -12A | [14 empty] | 474480.3488 | 4063.9445 | 478544.2933
17 |  | TYPE -13A (1 No)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
17 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.1 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 840 | 840 | 0 | 100% | 0% | 100% | 840 | 0 | 840
17 | B | 20mm thick polished Crystal White, maximum 126mm width border. | 1 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 488 | 488 | 0 | 100% | 0% | 100% | 488 | 0 | 488
17 | C | 7 x 5mm Brass strip insert in brushed finish. | 6.5 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 370.5 | 370.5 |  |  |  |  | 0 | 0 | 0
17 | Add | Threshold To Main Entrance : Supply and installation of 20mm thick honed Volakas, 160mm W x 1100mm L | 1 | No | 1 | Volakas | 20 | 115 | 33 | 148 | 148 | 148 | 0 | 100% | 0% | 100% | 148 | 0 | 148
Living Room
17 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 25.5 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 10200 | 10200 | 0 | 100% | 0% | 100% | 10200 | 0 | 10200
17 | E | 20mm thick polished Crystal White, cut to size. | 3.1 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 1512.8 | 0 | 100% | 0% | 100% | 1512.8 | 0 | 1512.8
17 | F | 20mm thick polished Crystal White, average of 153mm width border. | 3.65 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 1781.2 | 1781.2 | 0 | 100% | 0% | 100% | 1781.2 | 0 | 1781.2
17 | G | 7 x 5mm Brass strip insert in brushed finish. | 22.6 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 1288.2 | 1288.2 |  | 100% | 0% | 100% | 1288.2 | 0 | 1288.2
17 | H | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 1 | Crystal White | 20 | 231 | 97 | 328 | 328 | 328 | 0 | 100% | 0% | 100% | 328 | 0 | 328
Toilet @ Foyer
17 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.5 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 600 | 0 | 100% | 0% | 100% | 600 | 0 | 600
17 | K | 20mm thick polished Crystal White, average 110mm width border. | 0.65 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 317.2 | 317.2 | 0 | 100% | 0% | 100% | 317.2 | 0 | 317.2
17 | L | 7 x 5mm Brass strip insert in brushed finish. | 4.9 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 279.3 | 279.3 |  | 100% | 0% | 100% | 279.3 | 0 | 279.3
17 | M | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 1 | Crystal White | 20 | 99 | 37 | 136 | 136 | 136 | 0 | 100% | 0% | 100% | 136 | 0 | 136
BED ROOM
17 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 16.9 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 6760 | 6760 | 0 | 100% | 0% | 100% | 6760 | 0 | 6760
17 | A | 20mm thick polished Crystal White, cut to size. | 1.35 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 658.8 | 658.8 | 0 | 100% | 0% | 100% | 658.8 | 0 | 658.8
17 | B | 20mm thick polished Crystal White, average of 146mm width border. | 2.6 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 1268.8 | 1268.8 | 0 | 100% | 0% | 100% | 1268.8 | 0 | 1268.8
17 | C | 7 x 5mm Brass strip insert in brushed finish. | 16.6 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 946.2 | 946.2 |  | 100% | 0% | 100% | 946.2 | 0 | 946.2
17 | D | 7 x 5mm Brass strip insert in brushed finish. | 13.9 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 792.3 | 792.3 |  | 100% | 0% | 100% | 792.3 | 0 | 792.3
17 | E | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 3 | No | 1 | Crystal White | 20 | 125 | 51 | 176 | 528 | 528 | 0 | 100% | 0% | 100% | 528 | 0 | 528
17 | F | 7 x 5mm Brass strip insert in brushed finish. 860mm length (only the length between threshold and carpet, other locations are excluded) | 0.86 | Lm | 1 | Brass | 5 | 0 | 51 | 51 | 43.86 | 43.86 |  | 100% | 0% | 100% | 43.86 | 0 | 43.86
Bathroom
17 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.5 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 1400 | 1400 | 0 | 100% | 0% | 100% | 1400 | 0 | 1400
17 | H | 20mm thick polished Crystal White, average 165mm width border. | 4.5 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 2196 | 2196 | 0 | 100% | 0% | 100% | 2196 | 0 | 2196
17 | J | 7 x 5mm Brass strip insert in brushed finish. | 10.9 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 621.3 | 621.3 |  | 100% | 0% | 100% | 621.3 | 0 | 621.3
17 | Add | Threshold (20mm thick polished Crystal White); 420mm wide x 1130mm length. | 1 | No | 1 | Crystal White | 20 | 197 | 86 | 283 | 283 | 283 | 0 | 100% | 0% | 100% | 283 | 0 | 283
17 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 10.9 | Lm | 1 | Volakas | 20 | 91 | 43 | 134 | 1460.6 | 1460.6 | 0 | 100% | 0% | 100% | 1460.6 | 0 | 1460.6
Shower
17 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.2 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
17 | M | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 1 | Crystal White | 20 | 99 | 37 | 136 | 136 | 136 | 0 | 100% | 0% | 100% | 136 | 0 | 136
Toilet
17 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.75 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 300 | 300 | 0 | 100% | 0% | 100% | 300 | 0 | 300
17 | P | 20mm thick polished Crystal White, average of 116mm width border. | 0.45 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 219.6 | 0 | 100% | 0% | 100% | 219.6 | 0 | 219.6
17 | Q | 7 x 5mm Brass strip insert in brushed finish. | 3.4 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 193.8 | 193.8 |  | 100% | 0% | 100% | 193.8 | 0 | 193.8
17 | R | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 1 | Crystal White | 20 | 99 | 37 | 136 | 136 | 136 | 0 | 100% | 0% | 100% | 136 | 0 | 136
Balcony Floor Finishes
17 | A | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10 | M2 | 1 | PC Rate | 20 | 50 | 100 | 150 | 1500 | 1500 | 0 | 100% | 0% | 100% | 1500 | 0 | 1500
Wall Finishes
Bathroom
17 | B | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.55 | Lm | 1 | Crystal White | 20 | 79 | 43 | 122 | 555.1 | 555.1 | 0 | 100% | 0% | 100% | 555.1 | 0 | 555.1
17 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 6.35 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 3987.8 | 3987.8 | 0 | 100% | 0% | 100% | 3987.8 | 0 | 3987.8
Shower
17 | C | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.6 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 8540.8 | 8540.8 | 0 | 100% | 0% | 100% | 8540.8 | 0 | 8540.8
17 | D | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.3 | Lm | 1 | Crystal White | 20 | 94 | 56 | 150 | 795 | 795 | 0 | 100% | 0% | 100% | 795 | 0 | 795
Toilet
17 | E | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.9 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 2449.2 | 2449.2 | 0 | 100% | 0% | 100% | 2449.2 | 0 | 2449.2
17 | F | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.55 | Lm | 1 | Crystal White | 20 | 79 | 43 | 122 | 433.1 | 433.1 | 0 | 100% | 0% | 100% | 433.1 | 0 | 433.1
Toilet @ Foyer
17 | G | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 5.5 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 3454 | 3454 | 0 | 100% | 0% | 100% | 3454 | 0 | 3454
17 | H | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.05 | Lm | 1 | Crystal White | 20 | 79 | 43 | 122 | 616.1 | 616.1 | 0 | 100% | 0% | 100% | 616.1 | 0 | 616.1
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
17 | A | Living : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 1478 | 0 | 100% | 0% | 100% | 1478 | 0 | 1478
17 | B | Bedroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 1079 | 0 | 100% | 0% | 100% | 1079 | 0 | 1079
17 | C | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 1 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 1928 | 0 | 100% | 0% | 100% | 1928 | 0 | 1928
17 | D | Bedroom To WIW : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 1079 | 0 | 100% | 0% | 100% | 1079 | 0 | 1079
17 | E | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 1074 | 0 | 100% | 0% | 100% | 1074 | 0 | 1074
17 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 1 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 1928 | 0 | 100% | 0% | 100% | 1928 | 0 | 1928
Joinery Items
Walk-In Closet
17 | G | Counter Top @ Walk-In Closet (smaller) : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 270 | 148 | 418 | 418 | 418 | 0 | 0% | 0% | 0% | 0 | 0 | 0
Bathroom
17 | H | To Column : supply and installation of 20mm thick honed Volakas cladding to column, total size of (295 + 270 + 170 + 160)mm x 2650mm H. Shelf, elsewhere. | 1 | No | 1 | Volakas | 20 | 1018 | 530 | 1548 | 1548 | 1548 | 0 | 100% | 0% | 100% | 1548 | 0 | 1548
17 | J | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 2079 | 0 | 100% | 0% | 100% | 2079 | 0 | 2079
Bath Tub Base
17 | K | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 1 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 944 | 0 | 100% | 0% | 100% | 944 | 0 | 944
Shower
17 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 492 | 240 | 732 | 732 | 732 | 0 | 100% | 0% | 100% | 732 | 0 | 732
17 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1300mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 308 | 131 | 439 | 439 | 439 | 0 | 100% | 0% | 100% | 439 | 0 | 439
17 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 1 | Volakas | 20 | 44 | 12 | 56 | 112 | 112 | 0 | 100% | 0% | 100% | 112 | 0 | 112
Toilet
17 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 1 | Volakas | 20 | 112 | 55 | 167 | 167 | 167 | 0 | 100% | 0% | 100% | 167 | 0 | 167
17 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 1 | Volakas | 20 | 25 | 5 | 30 | 30 | 30 | 0 | 100% | 0% | 100% | 30 | 0 | 30
Toilet @ Foyer
17 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1395mm length, pencil edge finish. | 1 | No | 1 | Volakas | 20 | 150 | 74 | 224 | 224 | 224 | 0 | 100% | 0% | 100% | 224 | 0 | 224
17 | G | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (1090 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 1 | Volakas | 20 | 768 | 345 | 1113 | 1113 | 1113 | 0 | 100% | 0% | 100% | 1113 | 0 | 1113
17 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 1 | Volakas | 20 | 25 | 5 | 30 | 30 | 30 | 0 | 100% | 0% | 100% | 30 | 0 | 30
Miscellaneous Items
17 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 140 | M2 | 1 |  |  | 0 | 8 | 8 | 1120 | 1120 | 0 | 98.96% | 0% | 98.96% | 1108.3565 | 0 | 1108.3565
17 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 82 | M2 | 1 |  |  | 0 | 8 | 8 | 656 | 656 | 0 | 98.96% | 0% | 98.96% | 649.1802 | 0 | 649.1802
17 |  | Total Amount for TYPE -13A | [14 empty] | 76815.5967 | 0 | 76815.5967
18 |  | TYPE -14A (4 No)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
18 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 840 | 3360 | 0 | 100% | 0% | 100% | 3360 | 0 | 3360
18 | B | 20mm thick polished Crystal White, maximum 126mm width border. | 1 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 488 | 1952 | 0 | 100% | 0% | 100% | 1952 | 0 | 1952
18 | C | 7 x 5mm Brass strip insert in brushed finish. | 7.2 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 410.4 | 1641.6 |  | 100% | 0% | 100% | 1641.6 | 0 | 1641.6
18 | Add | Threshold (20mm thick); 160mm wide x 1100mm length, polished Crystal White | 1 | No | 4 | Crystal White | 20 | 102 | 33 | 135 | 135 | 540 | 0 | 100% | 0% | 100% | 540 | 0 | 540
Living Room
18 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 20 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 8000 | 32000 | 0 | 100% | 0% | 100% | 32000 | 0 | 32000
18 | E | 20mm thick polished Crystal White, cut to size. | 1.6 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 780.8 | 3123.2 | 0 | 100% | 0% | 100% | 3123.2 | 0 | 3123.2
18 | F | 20mm thick polished Crystal White, average of 147mm width border. | 3.5 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 1708 | 6832 | 0 | 100% | 0% | 100% | 6832 | 0 | 6832
18 | G | 7 x 5mm Brass strip insert in brushed finish. | 22.6 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 1288.2 | 5152.8 |  | 100% | 0% | 100% | 5152.8 | 0 | 5152.8
18 | H | 7 x 5mm Brass strip insert in brushed finish. | 12.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 712.5 | 2850 |  | 100% | 0% | 100% | 2850 | 0 | 2850
18 | J | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 4 | Crystal White | 20 | 231 | 97 | 328 | 328 | 1312 | 0 | 100% | 0% | 100% | 1312 | 0 | 1312
POWDER ROOM
18 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.5 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 2400 | 0 | 100% | 0% | 100% | 2400 | 0 | 2400
18 | L | 20mm thick polished Crystal White, cut to size. | 0.4 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 195.2 | 780.8 | 0 | 100% | 0% | 100% | 780.8 | 0 | 780.8
18 | M | 20mm thick polished Crystal White, average 120mm width border. | 0.85 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 414.8 | 1659.2 | 0 | 100% | 0% | 100% | 1659.2 | 0 | 1659.2
18 | N | 7 x 5mm Brass strip insert in brushed finish. | 5.25 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 299.25 | 1197 |  | 100% | 0% | 100% | 1197 | 0 | 1197
18 | P | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 4 | Crystal White | 20 | 94 | 35 | 129 | 129 | 516 | 0 | 100% | 0% | 100% | 516 | 0 | 516
BED ROOM
18 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 2040 | 8160 | 0 | 100% | 0% | 100% | 8160 | 0 | 8160
18 | B | 20mm thick polished Crystal White, cut to size. | 1.5 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 732 | 2928 | 0 | 100% | 0% | 100% | 2928 | 0 | 2928
18 | C | 20mm thick polished Crystal White, average of 140mm width border. | 2.3 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 1122.4 | 4489.6 | 0 | 100% | 0% | 100% | 4489.6 | 0 | 4489.6
18 | D | 7 x 5mm Brass strip insert in brushed finish. | 14.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 826.5 | 3306 |  | 100% | 0% | 100% | 3306 | 0 | 3306
18 | E | 7 x 5mm Brass strip insert in brushed finish. | 12.05 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 686.85 | 2747.4 |  | 100% | 0% | 100% | 2747.4 | 0 | 2747.4
18 | F | Threshold (20mm thick polished Crystal White); 320mm wide x 1140mm length. | 3 | No | 4 | Crystal White | 20 | 162 | 66 | 228 | 684 | 2736 | 0 | 100% | 0% | 100% | 2736 | 0 | 2736
Walk-In Closet
18 | G | 20mm thick polished Crystal White, average 135mm width border. | 2 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 976 | 3904 | 0 | 100% | 0% | 100% | 3904 | 0 | 3904
18 | H | 7 x 5mm Brass strip insert in brushed finish. | 8.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 484.5 | 1938 |  | 100% | 0% | 100% | 1938 | 0 | 1938
Bathroom
18 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 15.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 6040 | 24160 | 0 | 100% | 0% | 100% | 24160 | 0 | 24160
18 | K | 20mm thick polished Crystal White, average 145mm width border. | 2 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 976 | 3904 | 0 | 100% | 0% | 100% | 3904 | 0 | 3904
18 | L | 7 x 5mm Brass strip insert in brushed finish. | 16.45 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 937.65 | 3750.6 |  | 100% | 0% | 100% | 3750.6 | 0 | 3750.6
18 | Add | Threshold (20mm thick polished Crystal White); 420mm wide x 1130mm length. | 1 | No | 4 | Crystal White | 20 | 197 | 86 | 283 | 283 | 1132 | 0 | 100% | 0% | 100% | 1132 | 0 | 1132
Shower
18 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 840 | 3360 | 0 | 100% | 0% | 100% | 3360 | 0 | 3360
18 | P | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 4 | Crystal White | 20 | 99 | 37 | 136 | 136 | 544 | 0 | 100% | 0% | 100% | 544 | 0 | 544
Toilet
18 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.9 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 760 | 3040 | 0 | 100% | 0% | 100% | 3040 | 0 | 3040
18 | A | 20mm thick polished Crystal White, average of 105mm width border. | 0.7 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1366.4 | 0 | 100% | 0% | 100% | 1366.4 | 0 | 1366.4
18 | B | 7 x 5mm Brass strip insert in brushed finish. | 4.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 256.5 | 1026 |  | 100% | 0% | 100% | 1026 | 0 | 1026
18 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 4 | Crystal White | 20 | 99 | 37 | 136 | 136 | 544 | 0 | 100% | 0% | 100% | 544 | 0 | 544
Balcony Floor Finishes
18 | D | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 17 | M2 | 4 | PC Rate | 20 | 50 | 100 | 150 | 2550 | 10200 | 0 | 100% | 0% | 100% | 10200 | 0 | 10200
Wall Finishes
Bathroom
18 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9.65 | Lm | 4 | Crystal White | 20 | 86 | 48 | 134 | 1293.1 | 5172.4 | 0 | 100% | 0% | 100% | 5172.4 | 0 | 5172.4
18 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 11.6 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 7284.8 | 29139.2 | 0 | 100% | 0% | 100% | 29139.2 | 0 | 29139.2
Shower
18 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.5 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 8478 | 33912 | 0 | 100% | 0% | 100% | 33912 | 0 | 33912
18 | G | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.5 | Lm | 4 | Crystal White | 20 | 94 | 56 | 150 | 825 | 3300 | 0 | 100% | 0% | 100% | 3300 | 0 | 3300
Toilet
18 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 12.7 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 7975.6 | 31902.4 | 0 | 100% | 0% | 100% | 31902.4 | 0 | 31902.4
18 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5 | Lm | 4 | Crystal White | 20 | 79 | 43 | 122 | 610 | 2440 | 0 | 100% | 0% | 100% | 2440 | 0 | 2440
Powder Room
18 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.05 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 3799.4 | 15197.6 | 0 | 100% | 0% | 100% | 15197.6 | 0 | 15197.6
18 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.9 | Lm | 4 | Crystal White | 20 | 79 | 43 | 122 | 719.8 | 2879.2 | 0 | 100% | 0% | 100% | 2879.2 | 0 | 2879.2
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
18 | B | Living : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 5912 | 0 | 75% | 0% | 75% | 4434 | 0 | 4434
18 | C | Bedroom : (120 + 120)mm wide); total size of 1140 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 704 | 327 | 1031 | 1031 | 4124 | 0 | 100% | 0% | 100% | 4124 | 0 | 4124
18 | D | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 4 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 7712 | 0 | 100% | 0% | 100% | 7712 | 0 | 7712
18 | E | Bedroom To WIW : (120 + 120)mm wide); total size of 1140 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 704 | 327 | 1031 | 1031 | 4124 | 0 | 100% | 0% | 100% | 4124 | 0 | 4124
18 | F | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 4348 | 0 | 100% | 0% | 100% | 4348 | 0 | 4348
18 | G | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 4 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 7712 | 0 | 100% | 0% | 100% | 7712 | 0 | 7712
Joinery Items
Walk-In Closet
18 | J | Counter Top @ Walk-In Closet (smaller) : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 270 | 148 | 418 | 418 | 1672 | 3 | 25% | 75% | 100% | 418 | 1254 | 1672
Walk-In Closet
18 | K | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1170mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 318 | 174 | 492 | 492 | 1968 | 3 | 25% | 75% | 100% | 492 | 1476 | 1968
Bathroom
18 | A | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 4 | Crystal White | 20 | 118 | 59 | 177 | 177 | 708 | 0 | 100% | 0% | 100% | 708 | 0 | 708
18 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround, shelf, and back support elsewhere). | 1 | No | 4 | Volakas | 20 | 2088 | 999 | 3087 | 3087 | 12348 | 0 | 100% | 0% | 100% | 12348 | 0 | 12348
18 | C | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 170mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 519 | 254 | 773 | 773 | 3092 | 0 | 100% | 0% | 100% | 3092 | 0 | 3092
18 | D | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 68 | 31 | 99 | 99 | 396 | 0 | 100% | 0% | 100% | 396 | 0 | 396
Bath Tub Base
18 | E | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 4 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 3776 | 0 | 87.5% | 0% | 87.5% | 3304 | 0 | 3304
Shower
18 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 492 | 240 | 732 | 732 | 2928 | 0 | 100% | 0% | 100% | 2928 | 0 | 2928
18 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1065mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 256 | 107 | 363 | 363 | 1452 | 0 | 100% | 0% | 100% | 1452 | 0 | 1452
18 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 4 | Volakas | 20 | 44 | 12 | 56 | 112 | 448 | 0 | 100% | 0% | 100% | 448 | 0 | 448
Toilet
18 | J | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 4 | Volakas | 20 | 112 | 55 | 167 | 167 | 668 | 0 | 100% | 0% | 100% | 668 | 0 | 668
18 | A | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 4 | Volakas | 20 | 25 | 5 | 30 | 30 | 120 | 0 | 100% | 0% | 100% | 120 | 0 | 120
Toilet @ Foyer
18 | B | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1120mm length, pencil edge finish. | 1 | No | 4 | Volakas | 20 | 121 | 60 | 181 | 181 | 724 | 0 | 100% | 0% | 100% | 724 | 0 | 724
18 | C | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (450 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 4 | Volakas | 20 | 768 | 345 | 1113 | 1113 | 4452 | 0 | 100% | 0% | 100% | 4452 | 0 | 4452
18 | D | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 4 | Volakas | 20 | 25 | 5 | 30 | 30 | 120 | 0 | 100% | 0% | 100% | 120 | 0 | 120
Miscellaneous Items
18 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 152 | M2 | 4 |  |  | 0 | 8 | 8 | 1216 | 4864 |  | 98.63% | 0.7999% | 99.43% | 4797.3034 | 38.9064 | 4836.2097
18 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 81 | M2 | 4 |  |  | 0 | 8 | 8 | 648 | 2592 |  | 98.63% | 0.7999% | 99.43% | 2556.4577 | 20.733 | 2577.1907
18 |  | Total Amount for TYPE -14A | [14 empty] | 343973.1611 | 2789.6394 | 346762.8005
19 |  | TYPE -16A (3 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
19 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.8 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1920 | 5760 | 0 | 100% | 0% | 100% | 5760 | 0 | 5760
19 | B | 20mm thick polished Crystal White, maximum 138mm width border. | 1.7 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 829.6 | 2488.8 | 0 | 100% | 0% | 100% | 2488.8 | 0 | 2488.8
19 | C | 7 x 5mm Brass strip insert in brushed finish. | 9.5 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 541.5 | 1624.5 |  | 66.67% | 0% | 66.67% | 1083 | 0 | 1083
19 | D | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 3 | Crystal White | 20 | 123 | 48 | 171 | 171 | 513 | 0 | 100% | 0% | 100% | 513 | 0 | 513
Living Room/Bedroom
19 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 10 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 4000 | 12000 | 0 | 100% | 0% | 100% | 12000 | 0 | 12000
19 | E | 20mm thick polished Crystal White, cut to size. | 4.2 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 2049.6 | 6148.8 | 0 | 100% | 0% | 100% | 6148.8 | 0 | 6148.8
19 | F | 20mm thick polished Crystal White, average of 130mm width border. | 3.6 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 1756.8 | 5270.4 | 0 | 100% | 0% | 100% | 5270.4 | 0 | 5270.4
19 | G | 7 x 5mm Brass strip insert in brushed finish. | 24 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 1368 | 4104 |  | 66.67% | 0% | 66.67% | 2736 | 0 | 2736
19 | H | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 627 | 1881 |  | 66.67% | 0% | 66.67% | 1254 | 0 | 1254
19 | J | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 627 | 1881 |  | 66.67% | 0% | 66.67% | 1254 | 0 | 1254
19 | K | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 3 | Crystal White | 20 | 155 | 62 | 217 | 217 | 651 | 0 | 100% | 0% | 100% | 651 | 0 | 651
19 | L | Threshold (20mm thick polished Crystal White); 320mm wide x 925mm length. | 1 | No | 3 | Crystal White | 20 | 128 | 51 | 179 | 179 | 537 | 0 | 100% | 0% | 100% | 537 | 0 | 537
19 | M | 7 x 5mm Brass strip insert in brushed finish. 925mm length (only the length between threshold and carpet, other locations are excluded) | 0.93 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 53.01 | 159.03 |  | 66.67% | 0% | 66.67% | 106.02 | 0 | 106.02
Bathroom
19 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1280 | 3840 | 0 | 100% | 0% | 100% | 3840 | 0 | 3840
19 | P | 20mm thick polished Crystal White, average 165mm width border. | 1.15 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 561.2 | 1683.6 | 0 | 100% | 0% | 100% | 1683.6 | 0 | 1683.6
19 | Q | 7 x 5mm Brass strip insert in brushed finish. | 7.1 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 404.7 | 1214.1 |  | 100% | 0% | 100% | 1214.1 | 0 | 1214.1
19 | P | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | No | 3 | Crystal White | 20 | 134 | 55 | 189 | 189 | 567 | 0 | 100% | 0% | 100% | 567 | 0 | 567
Shower
19 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 800 | 2400 | 0 | 100% | 0% | 100% | 2400 | 0 | 2400
19 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
Toilet
19 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.7 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 280 | 840 | 0 | 100% | 0% | 100% | 840 | 0 | 840
19 | F | 20mm thick polished Crystal White, average of 110mm width border. | 0.5 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 244 | 732 | 0 | 100% | 0% | 100% | 732 | 0 | 732
19 | G | 7 x 5mm Brass strip insert in brushed finish. | 3.1 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 176.7 | 530.1 |  | 100% | 0% | 100% | 530.1 | 0 | 530.1
19 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
Balcony Floor Finishes
19 | J | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 23.5 | M2 | 3 | PC Rate | 20 | 50 | 100 | 150 | 3525 | 10575 | 0 | 100% | 0% | 100% | 10575 | 0 | 10575
Wall Finishes
Bathroom
19 | K | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.6 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 8540.8 | 25622.4 | 0 | 100% | 0% | 100% | 25622.4 | 0 | 25622.4
19 | L | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.6 | Lm | 3 | Crystal White | 20 | 86 | 48 | 134 | 884.4 | 2653.2 | 0 | 100% | 0% | 100% | 2653.2 | 0 | 2653.2
Shower
19 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 12 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 7536 | 22608 | 0 | 100% | 0% | 100% | 22608 | 0 | 22608
19 | A | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5 | Lm | 3 | Crystal White | 20 | 94 | 56 | 150 | 750 | 2250 | 0 | 100% | 0% | 100% | 2250 | 0 | 2250
Toilet
19 | B | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.6 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 2260.8 | 6782.4 | 0 | 100% | 0% | 100% | 6782.4 | 0 | 6782.4
19 | C | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.3 | Lm | 3 | Crystal White | 20 | 79 | 43 | 122 | 402.6 | 1207.8 | 0 | 100% | 0% | 100% | 1207.8 | 0 | 1207.8
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
19 | D | Living/Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 3666 | 0 | 66.67% | 0% | 66.67% | 2444 | 0 | 2444
19 | E | Bedroom To WIW : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 3261 | 0 | 66.67% | 0% | 66.67% | 2174 | 0 | 2174
19 | F | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 3261 | 0 | 66.67% | 0% | 66.67% | 2174 | 0 | 2174
19 | G | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 3 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 5784 | 0 | 100% | 0% | 100% | 5784 | 0 | 5784
Joinery Items
Walk-In Closet
19 | H | Wardrobe Counter (smaller) : supply and installation of 20mm thick honed Volakas size of 650mm W x 665mm L, mitered with 40mm high fascia. | 1 | No | 3 | Crystal White | 20 | 221 | 111 | 332 | 332 | 996 | 1 | 66.67% | 33.33% | 100% | 664 | 332 | 996
19 | J | Wardrobe Counter : supply and installation of 20mm thick polished Volakas size of 650mm W x 675mm L mitered with 40mm high fascia. | 1 | No | 3 | Crystal White | 20 | 225 | 113 | 338 | 338 | 1014 | 1 | 66.67% | 33.33% | 100% | 676 | 338 | 1014
Bathroom
19 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1900mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1900mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 6237 | 0 | 100% | 0% | 100% | 6237 | 0 | 6237
Sanitaryware - Stoneworks
19 | B | Bath Tub Top @ Bathroom : supply and installation of 20mm thick honed Volakas top size of maximum 100/480mm wide, total size of 930mm wide x 2040mm length. Complete with 590mm high cladding to 3-sides. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 3 | Volakas | 20 | 796 | 309 | 1105 | 1105 | 3315 | 0 | 100% | 0% | 100% | 3315 | 0 | 3315
Shower
19 | C | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 602 | 294 | 896 | 896 | 2688 | 0 | 100% | 0% | 100% | 2688 | 0 | 2688
19 | D | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1100mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 262 | 110 | 372 | 372 | 1116 | 0 | 100% | 0% | 100% | 1116 | 0 | 1116
19 | E | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 3 | Volakas | 20 | 44 | 12 | 56 | 112 | 336 | 0 | 100% | 0% | 100% | 336 | 0 | 336
Toilet
19 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 3 | Volakas | 20 | 102 | 50 | 152 | 152 | 456 | 0 | 100% | 0% | 100% | 456 | 0 | 456
19 | G | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 3 | Volakas | 20 | 25 | 5 | 30 | 30 | 90 | 0 | 100% | 0% | 100% | 90 | 0 | 90
Miscellaneous Items
19 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 106 | M2 | 3 |  |  | 0 | 8 | 8 | 848 | 2544 |  | 95.44% | 0.4199% | 95.86% | 2427.8889 | 10.6824 | 2438.5712
19 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 57 | M2 | 3 |  |  | 0 | 8 | 8 | 456 | 1368 |  | 95.44% | 0.4199% | 95.86% | 1305.5629 | 5.7443 | 1311.3072
19 |  | Total Amount for TYPE -16A | [14 empty] | 156011.0718 | 686.4267 | 156697.4984
20 |  | TYPE -19A (6 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
20 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.1 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1240 | 7440 | 0 | 100% | 0% | 100% | 7440 | 0 | 7440
20 | B | 20mm thick polished Crystal White, maximum 126mm width border. | 1.35 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 658.8 | 3952.8 | 0 | 100% | 0% | 100% | 3952.8 | 0 | 3952.8
20 | C | 7 x 5mm Brass strip insert in brushed finish. | 7.2 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 410.4 | 2462.4 |  | 100% | 0% | 100% | 2462.4 | 0 | 2462.4
20 | D | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 6 | Crystal White | 20 | 123 | 48 | 171 | 171 | 1026 | 0 | 100% | 0% | 100% | 1026 | 0 | 1026
Bedroom
20 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.5 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 2200 | 13200 | 29.3333 | 11.11% | 88.89% | 100% | 1466.6667 | 11733.3333 | 13200
20 | E | 20mm thick polished Crystal White, cut to size. | 3.8 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1854.4 | 11126.4 | 20.2667 | 11.11% | 88.89% | 100% | 1236.2667 | 9890.1333 | 11126.4
20 | F | 20mm thick polished Crystal White, average of 150mm width border. | 3.1 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 9076.8 | 16.5333 | 11.11% | 88.89% | 100% | 1008.5333 | 8068.2667 | 9076.8
20 | G | 7 x 5mm Brass strip insert in brushed finish. | 18.9 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 1077.3 | 6463.8 |  | 100% | 0% | 100% | 6463.8 | 0 | 6463.8
20 | H | 7 x 5mm Brass strip insert in brushed finish. | 16.7 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 951.9 | 5711.4 |  | 100% | 0% | 100% | 5711.4 | 0 | 5711.4
20 | J | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 6 | Crystal White | 20 | 231 | 97 | 328 | 328 | 1968 | 2.8187 | 11.11% | 88.89% | 100% | 218.6667 | 1749.3333 | 1968
Walk-In Closet
20 | K | 320mm wide x 860mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 125 | 51 | 176 | 176 | 1056 | 1.4677 | 11.11% | 88.89% | 100% | 117.3333 | 938.6667 | 1056
20 | L | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 9 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 513 | 3078 |  | 100% | 0% | 100% | 3078 | 0 | 3078
Bathroom
20 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 11 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 4400 | 26400 | 0 | 100% | 0% | 100% | 26400 | 0 | 26400
20 | N | 20mm thick polished Crystal White, average 130mm width border. | 2.15 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1049.2 | 6295.2 | 0 | 100% | 0% | 100% | 6295.2 | 0 | 6295.2
20 | P | 7 x 5mm Brass strip insert in brushed finish. | 14.5 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 826.5 | 4959 |  | 100% | 0% | 100% | 4959 | 0 | 4959
20 | Add | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 134 | 55 | 189 | 189 | 1134 | 0 | 100% | 0% | 100% | 1134 | 0 | 1134
Shower
20 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.6 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 3840 | 0 | 100% | 0% | 100% | 3840 | 0 | 3840
20 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
Toilet
20 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 1920 | 0 | 100% | 0% | 100% | 1920 | 0 | 1920
20 | E | 20mm thick polished Crystal White, average of 105mm width border. | 0.5 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 244 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
20 | F | 7 x 5mm Brass strip insert in brushed finish. | 3.6 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 205.2 | 1231.2 |  | 100% | 0% | 100% | 1231.2 | 0 | 1231.2
20 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
Balcony Floor Finishes
20 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 39 | M2 | 6 | PC Rate | 20 | 50 | 100 | 150 | 5850 | 35100 | 0 | 100% | 0% | 100% | 35100 | 0 | 35100
Wall Finishes
Bathroom
20 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 7.7 | Lm | 6 | Crystal White | 20 | 86 | 48 | 134 | 1031.8 | 6190.8 | 0 | 100% | 0% | 100% | 6190.8 | 0 | 6190.8
20 | Add | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 12.2 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 7661.6 | 45969.6 | 0 | 100% | 0% | 100% | 45969.6 | 0 | 45969.6
Shower
20 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.6 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 6656.8 | 39940.8 | 0 | 100% | 0% | 100% | 39940.8 | 0 | 39940.8
20 | L | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.4 | Lm | 6 | Crystal White | 20 | 94 | 56 | 150 | 660 | 3960 | 0 | 100% | 0% | 100% | 3960 | 0 | 3960
Toilet
20 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.1 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 2574.8 | 15448.8 | 0 | 100% | 0% | 100% | 15448.8 | 0 | 15448.8
20 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.7 | Lm | 6 | Crystal White | 20 | 79 | 43 | 122 | 451.4 | 2708.4 | 0 | 100% | 0% | 100% | 2708.4 | 0 | 2708.4
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
20 | B | Bedroom : 300mm wide; total size of 1510 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 869 | 433 | 1302 | 1302 | 7812 | 0 | 100% | 0% | 100% | 7812 | 0 | 7812
20 | C | Foyer To WIW : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 6444 | 0 | 100% | 0% | 100% | 6444 | 0 | 6444
20 | D | Bathroom : (145 + 160)mm wide); total size of 860 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 789 | 395 | 1184 | 1184 | 7104 | 0 | 100% | 0% | 100% | 7104 | 0 | 7104
20 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 6 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 11568 | 0 | 100% | 0% | 100% | 11568 | 0 | 11568
Joinery Items
Bedroom
20 | F | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 660mm length, mitered with 40mm high fascia, (full high cladding to 2 sides, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 200 | 99 | 299 | 299 | 1794 | 0 | 100% | 0% | 100% | 1794 | 0 | 1794
20 | G | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (a) 595mm wide x 1535mm high cladding to 2 sides having (b) 30mm width complete front frame and (c) soffit/ceiling. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 1172 | 654 | 1826 | 1826 | 10956 | 0 | 100% | 0% | 100% | 10956 | 0 | 10956
Walk-In Closet
20 | H | Counter Top @ Walk-In Closet (smaller) : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2610 | 0 | 100% | 0% | 100% | 2610 | 0 | 2610
Walk-In Closet
20 | J | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1670mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 457 | 250 | 707 | 707 | 4242 | 0 | 100% | 0% | 100% | 4242 | 0 | 4242
Bathroom
20 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround, shelf, and back support elsewhere). | 1 | No | 6 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 12474 | 0 | 100% | 0% | 100% | 12474 | 0 | 12474
20 | B | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 170mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 2 | No | 6 | Volakas | 20 | 519 | 254 | 773 | 1546 | 9276 | 0 | 100% | 0% | 100% | 9276 | 0 | 9276
20 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 68 | 31 | 99 | 99 | 594 | 0 | 100% | 0% | 100% | 594 | 0 | 594
Sanitaryware - Stoneworks
20 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 6 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 5664 | 0 | 100% | 0% | 100% | 5664 | 0 | 5664
Shower
20 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 565 | 276 | 841 | 841 | 5046 | 0 | 100% | 0% | 100% | 5046 | 0 | 5046
20 | F | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1180mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 282 | 119 | 401 | 401 | 2406 | 0 | 100% | 0% | 100% | 2406 | 0 | 2406
20 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 6 | Volakas | 20 | 44 | 12 | 56 | 112 | 672 | 0 | 100% | 0% | 100% | 672 | 0 | 672
Toilet
20 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1085mm length, pencil edge finish. | 1 | No | 6 | Volakas | 20 | 116 | 57 | 173 | 173 | 1038 | 0 | 100% | 0% | 100% | 1038 | 0 | 1038
20 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 6 | Volakas | 20 | 25 | 5 | 30 | 30 | 180 | 0 | 100% | 0% | 100% | 180 | 0 | 180
Miscellaneous Items
20 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 143 | M2 | 6 |  |  | 0 | 8 | 8 | 1144 | 6864 |  | 90.87% | 9.13% | 100% | 6237.2874 | 626.7126 | 6864
20 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 73 | M2 | 6 |  |  | 0 | 8 | 8 | 584 | 3504 |  | 90.87% | 9.13% | 100% | 3184.0698 | 319.9302 | 3504
20 |  | Total Amount for TYPE -19A | [14 empty] | 324073.0307 | 33326.3762 | 365003.4
119.8302

## Work progress Summary
Work Progress Summary
Room Type | No of Units | FLORING INC. BORDER | [6 empty] | BRASS STRIP |  |  |  |  | WALL |  |  | SKIRTING |  |  | ARCHITRAVE |  |  |  |  | JOINARY ITEMS
|  | FOYER | LIVING | BED RM | BATH RM | SHOWER | TOILET | BALCONY | FOYER | LIVING | BED RM | BATH RM | TOILET | BATH RM | SHOWER | TOILET | BATH RM | SHOWER | TOILET | FOYER | BED RM | BATH RM | SHOWER | TOILET | COUNTER TOP | MINI BAR | VANITY | NICHE | SHELF | BATHTUB | BENCH | CISTERN TOP
1A | 8 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 87.5% | 87.5% | 100% | 100% | 87.5% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
1B/1C | 6 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
2A/2B/2C/2D | 44 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 93.18% | 93.18% | 95.45% | 95.45% | 95.45% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
2E/2F/2G/2H | 27 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 96.3% | 96.3% | 96.3% | 96.3% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
3A/3B/3D/3E/3G | 39 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 87.18% | 97.44% | 100% | 100% | 100% | 100% | 97.44% | 100% | 100% | 100% | N/A | 100% | 100%
3C/3F | 18 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 94.44% | 94.44% | 94.44% | 100% | 94.44% | 94.44% | 100% | 100% | 100% | N/A | 97.22% | 100%
4A/4B | 5 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
5A | 9 | 100% | N/A | 95.56% | 100% | 100% | 100% | 100% | 100% | N/A | 88.89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 88.89% | 100% | 100% | 100% | 100% | 88.89% | 100% | 100% | 100% | N/A | 100% | 100%
6A | 5 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 40% | 100% | 80% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
8A | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
9A | 2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9B | 2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10A | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
10B | 3 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 66.67% | 66.67% | 66.67% | 66.67% | 66.67% | 0% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
11A/11B/11C/11D | 19 | 94.74% | N/A | N/A | 95.79% | 84.21% | 95.79% | 100% | 15.79% | N/A | N/A | 89.47% | 84.21% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 89.47% | 89.47% | 89.47% | 89.47% | 94.74% | 47.37% | 97.37% | 100% | 100% | 100% | 100% | 100%
12A | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 80% | 100% | 100% | 100% | 100% | 40% | 100% | 100% | 100% | 100% | 100% | 100%
13A | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
14A | 4 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 75% | 25% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
16A | 3 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 66.67% | N/A | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 66.67% | 66.67% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
19A | 6 | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
PROV.SUM | 9 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
225

## Work progress Summary BreakDown
[6 empty] | FLORING INC. BORDER | [6 empty] | BRASS STRIP |  |  |  |  | WALL |  |  | SKIRTING |  |  | ARCHITRAVE |  |  |  |  | JOINARY ITEMS
SR NO | LEVEL | ROOM NAME | ROOM TYPE | ROOM NO | ROOM CATEGORY | FOYER | LIVING | BED RM | BATH RM | SHOWER | TOILET | BALCONY | FOYER2 | LIVING3 | BED RM4 | BATH RM5 | TOILET 6 | BATH RM7 | SHOWER8 | TOILET 9 | BATH RM10 | SHOWER11 | TOILET 12 | FOYER13 | BED RM14 | BATH RM15 | SHOWER16 | TOILET 17 | COUNTER TOP | MINI BAR | VANITY | NICHE | SHELF | BATHTUB | BENCH | CISTERN TOP
1 | 7 | 1 BEDROOM | 8A | 701 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
2 | 7 | STD. GUEST | 2B | 702 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
3 | 7 | STD. GUEST | 2C | 703 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
4 | 7 | STD. GUEST | 3A | 704 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
5 | 7 | STD. GUEST | 3D | 705 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
6 | 7 | STD. GUEST | 2A | 706 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
7 | 7 | CORNER. GUEST | 19A | 708 | 19A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
8 | 7 | STD. GUEST | 1C | 709 | 1B/1C | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
9 | 7 | JUNIOR SUITE | 4B | 710 | 4A/4B | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100%
10 | 7 | DELUX SUITE | 7A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
11 | 8 | 1 BEDROOM | 8A | 801 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
12 | 8 | STD. GUEST | 2B | 802 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
13 | 8 | STD. GUEST | 2C | 803 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
14 | 8 | STD. GUEST | 3A | 804 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
15 | 8 | STD. GUEST | 3D | 805 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
16 | 8 | STD. GUEST | 2A | 806 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
17 | 8 | STD. GUEST | 1B | 807 | 1B/1C | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
18 | 8 | JUNIOR SUITE | 4A | 808 | 4A/4B | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100%
19 | 9 | 1 BEDROOM | 8A | 901 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
20 | 9 | STD. GUEST | 2B | 902 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
21 | 9 | STD. GUEST | 2C | 903 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
22 | 9 | STD. GUEST | 3A | 904 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
23 | 9 | STD. GUEST | 3D | 905 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
24 | 9 | STD. GUEST | 2A | 906 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
25 | 9 | 1 BEDROOM | 9A | 907 | 9A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | 9 | 1 BEDROOM | 9B | 908 | 9B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | 9 | STD. GUEST | 1B | 909 | 1B/1C | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
28 | 9 | JUNIOR SUITE | 4A | 910 | 4A/4B | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100%
29 | 10 | 1 BEDROOM | 8A | 1001 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
30 | 10 | STD. GUEST | 2B | 1002 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
31 | 10 | STD. GUEST | 2C | 1003 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
32 | 10 | STD. GUEST | 3A | 1004 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
33 | 10 | STD. GUEST | 3D | 1005 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
34 | 10 | STD. GUEST | 2A | 1006 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
35 | 10 | STD. GUEST | 1B | 1008 | 1B/1C | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
36 | 10 | JUNIOR SUITE | 4A | 1009 | 4A/4B | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100%
37 | 10 | DOUBLE HT | 15A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
38 | 11 | 1 BEDROOM | 8A | 1101 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
39 | 11 | STD. GUEST | 2B | 1102 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
40 | 11 | STD. GUEST | 2C | 1103 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
41 | 11 | STD. GUEST | 3A | 1104 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
42 | 11 | STD. GUEST | 3D | 1105 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
43 | 11 | STD. GUEST | 2A | 1106 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
44 | 11 | CORNER. GUEST | 16A | 1107 | 16A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
45 | 11 | STD. GUEST | 1B | 1108 | 1B/1C | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100% | 100%
46 | 11 | JUNIOR SUITE | 4A | 1109 | 4A/4B | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
47 | 12 | 1 BEDROOM | 10A | 1201 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
48 | 12 | STD. GUEST | 3G | 1202 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
49 | 12 | STD. GUEST | 2B | 1203 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
50 | 12 | DELUX SUITE | 11C | 1204 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
51 | 12 | STD. GUEST | 3D | 1205 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
52 | 12 | STD. GUEST | 2B | 1206 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
53 | 12 | DELUX SUITE | 11C | 1207 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
54 | 12 | STD. GUEST | 3D | 1208 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
55 | 12 | STD. GUEST | 2A | 1209 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
56 | 12 | 1 BEDROOM | 9A | 1210 | 9A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
57 | 12 | 1 BEDROOM | 9B | 1211 | 9B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
58 | 12 | STD. GUEST | 1A | 1212 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
59 | 12 | STD. GUEST | 2F | 1213 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
60 | 12 | STD. GUEST | 3C | 1214 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
61 | 12 | STD. GUEST | 3F | 1215 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
62 | 12 | STD. GUEST | 2G | 1216 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
63 | 12 | STD. GUEST | 2E | 1217 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
64 | 12 | JUNIOR SUITE | 5A | 1218 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 99.58%
65 | 13 | 1 BEDROOM | 10A | 1301 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
66 | 13 | STD. GUEST | 3G | 1302 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
67 | 13 | STD. GUEST | 2B | 1303 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
68 | 13 | DELUX SUITE | 11C | 1304 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
69 | 13 | STD. GUEST | 3D | 1305 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
70 | 13 | STD. GUEST | 2B | 1306 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
71 | 13 | DELUX SUITE | 11C | 1307 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
72 | 13 | STD. GUEST | 3D | 1308 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
73 | 13 | STD. GUEST | 2A | 1309 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
74 | 13 | CORNER. GUEST | 19A | 1311 | 19A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
75 | 13 | STD. GUEST | 1A | 1312 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
76 | 13 | STD. GUEST | 2F | 1313 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
77 | 13 | STD. GUEST | 3C | 1314 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
78 | 13 | STD. GUEST | 3F | 1315 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
79 | 13 | STD. GUEST | 2G | 1316 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
80 | 13 | STD. GUEST | 2E | 1317 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
81 | 13 | JUNIOR SUITE | 5A | 1318 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 99.11%
82 | 13 | DELUX SUITE | 7A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
83 | 14 | 1 BEDROOM | 10A | 1401 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
84 | 14 | STD. GUEST | 3G | 1402 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
85 | 14 | STD. GUEST | 2B | 1403 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
86 | 14 | DELUX SUITE | 11C | 1404 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
87 | 14 | STD. GUEST | 3D | 1405 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
88 | 14 | STD. GUEST | 2B | 1406 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
89 | 14 | DELUX SUITE | 11C | 1407 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
90 | 14 | STD. GUEST | 3D | 1408 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
91 | 14 | STD. GUEST | 2A | 1409 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
92 | 14 | STD. GUEST | 1A | 1410 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
93 | 14 | STD. GUEST | 2F | 1411 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
94 | 14 | STD. GUEST | 3C | 1412 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
95 | 14 | STD. GUEST | 3F | 1413 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
96 | 14 | STD. GUEST | 2G | 1414 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
97 | 14 | STD. GUEST | 2E | 1415 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
98 | 14 | JUNIOR SUITE | 5A | 1416 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 99.52% | 100% | FALSE
99 | 15 | 1 BEDROOM | 10A | 1501 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
100 | 15 | STD. GUEST | 3G | 1502 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
101 | 15 | STD. GUEST | 2B | 1503 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
102 | 15 | DELUX SUITE | 11C | 1504 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
103 | 15 | STD. GUEST | 3D | 1505 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
104 | 15 | STD. GUEST | 2B | 1506 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
105 | 15 | DELUX SUITE | 11C | 1507 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
106 | 15 | STD. GUEST | 3D | 1508 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
107 | 15 | STD. GUEST | 2A | 1509 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
108 | 15 | CORNER. GUEST | 19A | 1511 | 19A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
109 | 15 | STD. GUEST | 1A | 1512 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
110 | 15 | STD. GUEST | 2F | 1513 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
111 | 15 | STD. GUEST | 3C | 1514 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
112 | 15 | STD. GUEST | 3F | 1515 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
113 | 15 | STD. GUEST | 2G | 1516 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
114 | 15 | STD. GUEST | 2E | 1517 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
115 | 15 | JUNIOR SUITE | 5A | 1518 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 99.55% | 100% | FALSE
116 | 15 | DELUX SUITE | 7A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
117 | 16 | 1 BEDROOM | 10A | 1601 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
118 | 16 | DELUX SUITE | 11D | 1602 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100%
119 | 16 | STD. GUEST | 2C | 1603 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
120 | 16 | STD. GUEST | 3A | 1604 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
121 | 16 | STD. GUEST | 3D | 1605 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
122 | 16 | STD. GUEST | 2B | 1606 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
123 | 16 | DELUX SUITE | 11C | 1607 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
124 | 16 | STD. GUEST | 3D | 1608 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
125 | 16 | STD. GUEST | 2A | 1609 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
126 | 16 | STD. GUEST | 1C | 1610 | 1B/1C | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
127 | 16 | STD. GUEST | 2H | 1611 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
128 | 16 | STD. GUEST | 3C | 1612 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
129 | 16 | STD. GUEST | 3F | 1613 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
130 | 16 | STD. GUEST | 2G | 1614 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
131 | 16 | STD. GUEST | 2E | 1615 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
132 | 16 | JUNIOR SUITE | 5A | 1616 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 99.41% | 100% | FALSE
135 | 19 | 1 BEDROOM | 12A | 1901 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
136 | 19 | CORNER. GUEST | 19A | 1903 | 19A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
137 | 19 | JUNIOR SUITE | 6A | 1904 | 6A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
138 | 19 | PRESIDENTIAL | 17A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
139 | 20 | 1 BEDROOM | 12A | 2001 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
140 | 20 | STD. GUEST | 2D | 2002 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
141 | 20 | STD. GUEST | 3A | 2003 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
142 | 20 | DELUX SUITE | 11B | 2004 | 11A/11B/11C/11D | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
143 | 20 | CORNER. GUEST | 19A | 2006 | 19A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
144 | 20 | JUNIOR SUITE | 6A | 2007 | 6A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
145 | 20 | DELUX SUITE | 7A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
146 | 21 | 1 BEDROOM | 12A | 2101 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
147 | 21 | STD. GUEST | 2D | 2102 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
148 | 21 | STD. GUEST | 3A | 2103 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
149 | 21 | DELUX SUITE | 11B | 2104 | 11A/11B/11C/11D | 100% | N/A | N/A | 80% | 100% | 80% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
150 | 21 | JUNIOR SUITE | 6A | 2105 | 6A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
151 | 22 | 1 BEDROOM | 12A | 2201 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
152 | 22 | DELUX SUITE | 11A | 2202 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 0% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
153 | 22 | STD. GUEST | 3D | 2203 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
154 | 22 | STD. GUEST | 2A | 2204 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
155 | 22 | JUNIOR SUITE | 6A | 2206 | 6A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
156 | 22 | DOUBLE HT | 15A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
157 | 23 | 1 BEDROOM | 12A | 2301 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
158 | 23 | STD. GUEST | 2D | 2302 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
159 | 23 | STD. GUEST | 3A | 2303 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
160 | 23 | DELUX SUITE | 11B | 2304 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
161 | 23 | CORNER. GUEST | 16A | 2305 | 16A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
162 | 23 | JUNIOR SUITE | 6A | 2306 | 6A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
163 | 24 | 1 BEDROOM | 13A | 2401 | 13A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
164 | 24 | 1 BEDROOM | 14A | 2402 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
165 | 24 | STD. GUEST | 2D | 2403 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
166 | 24 | STD. GUEST | 3A | 2404 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
167 | 24 | STD. GUEST | 3D | 2405 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
168 | 24 | STD. GUEST | 2B | 2406 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
169 | 24 | DELUX SUITE | 11C | 2407 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
170 | 24 | STD. GUEST | 3D | 2408 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
171 | 24 | STD. GUEST | 2B | 2409 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
172 | 24 | CORNER. GUEST | 19A | 2411 | 19A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
173 | 24 | STD. GUEST | 1A | 2412 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
174 | 24 | STD. GUEST | 2F | 2413 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
175 | 24 | STD. GUEST | 3C | 2414 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
176 | 24 | STD. GUEST | 3F | 2415 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
177 | 24 | STD. GUEST | 2G | 2416 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 0% | 0% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
178 | 24 | STD. GUEST | 2E | 2417 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
179 | 24 | JUNIOR SUITE | 5A | 2418 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
180 | 24 | DELUX SUITE | 7A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
181 | 25 | 1 BEDROOM | 10B | 2501 | 10B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
182 | 25 | 1 BEDROOM | 14A | 2502 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
183 | 25 | STD. GUEST | 2D | 2503 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 4000000
184 | 25 | STD. GUEST | 3A | 2504 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
185 | 25 | STD. GUEST | 3D | 2505 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% |  |  | 300000
186 | 25 | STD. GUEST | 2B | 2506 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 400000
187 | 25 | DELUX SUITE | 11C | 2507 | 11A/11B/11C/11D | 100% | N/A | N/A | 100% | 100% | 100% | 100% | 0% | N/A | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 0% | 0% | 50% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
188 | 25 | STD. GUEST | 3D | 2508 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
189 | 25 | STD. GUEST | 2B | 2509 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
190 | 25 | STD. GUEST | 1A | 2510 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
191 | 25 | STD. GUEST | 2F | 2511 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
192 | 25 | STD. GUEST | 3C | 2512 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 50% | 100%
193 | 25 | STD. GUEST | 3F | 2513 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
194 | 25 | STD. GUEST | 2G | 2514 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
195 | 25 | STD. GUEST | 2E | 2515 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
196 | 25 | JUNIOR SUITE | 5A | 2516 | 5A | 100% | N/A | 80% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | N/A | 100% | 100%
197 | 26 | 1 BEDROOM | 10B | 2601 | 10B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
198 | 26 | 1 BEDROOM | 14A | 2602 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
199 | 26 | STD. GUEST | 2D | 2603 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 0% | 0% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
200 | 26 | STD. GUEST | 3A | 2604 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
201 | 26 | DELUX SUITE | 11D | 2605 | 11A/11B/11C/11D | 100% | N/A | N/A | 80% | 0% | 80% | 100% | 0% | N/A | N/A | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 50% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
202 | 26 | STD. GUEST | 2C | 2606 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
203 | 26 | STD. GUEST | 3A | 2607 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99.93% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
204 | 26 | STD. GUEST | 1A | 2609 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
205 | 26 | STD. GUEST | 2F | 2610 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
206 | 26 | STD. GUEST | 3C | 2611 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
207 | 26 | STD. GUEST | 3F | 2612 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
208 | 26 | STD. GUEST | 2G | 2613 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
209 | 26 | STD. GUEST | 2E | 2614 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
210 | 26 | JUNIOR SUITE | 5A | 2615 | 5A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
211 | 26 | ROYAL | 18A |  | PROV.SUM | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
212 | 27 | 1 BEDROOM | 10B | 2701 | 10B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
213 | 27 | 1 BEDROOM | 14A | 2702 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
214 | 27 | STD. GUEST | 2D | 2703 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 0% | 0% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
215 | 27 | STD. GUEST | 3A | 2704 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
216 | 27 | DELUX SUITE | 11B | 2705 | 11A/11B/11C/11D | 100% | N/A | N/A | 80% | 0% | 80% | 100% | 0% | N/A | N/A | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
217 | 27 | STD. GUEST | 2C | 2706 | 2A/2B/2C/2D | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
218 | 27 | STD. GUEST | 3A | 2707 | 3A/3B/3D/3E/3G | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | N/A | 100% | 100%
219 | 27 | DELUX SUITE | 11D | 2708 | 11A/11B/11C/11D | 100% | N/A | N/A | 80% | 0% | 80% | 100% | 0% | N/A | N/A | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
220 | 27 | CORNER. GUEST | 16A | 2709 | 16A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 0% | N/A | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
221 | 27 | STD. GUEST | 1A | 2710 | 1A | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | N/A | 100% | 100%
222 | 27 | STD. GUEST | 2F | 2711 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 0% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
223 | 27 | STD. GUEST | 3C | 2712 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
224 | 27 | STD. GUEST | 3F | 2713 | 3C/3F | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | N/A | 100% | 100%
225 | 27 | STD. GUEST | 2G | 2714 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
226 | 27 | STD. GUEST | 2E | 2715 | 2E/2F/2G/2H | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100% | 100% | 100% | 100% | 100%
227 | 27 | JUNIOR SUITE | 5A | 2716 | 5A | 100% | N/A | 80% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | N/A | 100% | 100%
[6 empty] | 215 | 27 | 195 | 212 | 213 | 212 | 216 | 199 | 27 | 195 | 214 | 213 | 216 | 216 | 216 | 216 | 216 | 216 | 82 | 202 | 201 | 209 | 210 | 206 | 93 | 215 | 216 | 216 | 110 | 215 | 216
[5 empty] | N/A | 9 | 198 | 28 | 9 | 9 | 9 | 9 | 9 | 198 | 28 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 9 | 128 | 9 | 9 | 9 | 9 | 9 | 116 | 9 | 9 | 9 | 115 | 9 | 9

## MOS Summary (hidden)
MOS Summary - Dar (Guest Rooms)
| Description | QTY | Unit
1 | Material Qty considered for December,2021 Payment | 0 | m2
2 | New Deliveries from February to June | 0
3 | Deduct this month progress | -119.8302
4 | Material Stock Qty for this month (January,2022) | -119.8302
5 | Agreed rate for Materials | 300 | AED
6 | Material to be certifed under this payment | -35949.07 | AED
7 | MOS @ 75% | -26961.8025

## MOS Deliveries (hidden)
S.I | Jc No | Level | Room No | R. Type | Scope | Material | Deliver Qty( M Sq.) | Certified Qty | Remarks | Date
From 05th January to 13th January
1 | MM-3140-195 | 25 | 2515 | 2E | wall(CL) | Volkas | 33.45 | 33.45 |  | 2022-01-05
2 | MM-3140-217 | 25 | 2501 | 10B | wall(CL) | Volkas Polished | 44.16 | 44.16 |  | 2022-01-05
3 | MM-3140-222 | 25 | 2507 | 11C | Dado, Wall, Border Skirting | Volkas Polished | 34.12 | 34.12 |  | 2022-01-05
4 | MM-3140-001-Dr | Different rooms |  |  | Bathroom Drain | Travertine | 1.53 | 1.53 |  | 2022-01-10
5 | MM-3140-002-Dr | Different rooms |  |  | Bathroom Drain | Travertine | 1.55 | 1.55 |  | 2022-01-10
6 | MM-3140-002-Dr | Different rooms |  |  | Bathroom Drain | Crystal white polished | 3.27 | 3.27 |  | 2022-01-10
7 | MM-3140-287 Revised | 8 | 807 (Uper & Lower level) | 07A | wall(CL) | crystal white | 1.61 | 1.61 |  | 2022-01-10
8 | MM-3140-334 | 25 | 2510 (Uper & Lower level) | 7A | wall(CL) | crystal white | 1.61 | 1.61 |  | 2022-01-10
9 | MM-3140-215 | 25 | 2503 | 02D | wall(CL) | Volkas Polished | 36.26 | 36.26 |  | 2022-01-12
10 | MM-3140-151 | 25 | 2502 | 14A | wall(CL) | Volkas Polished | 29.59 | 29.59 |  | 2022-01-12
11 | MM-3140-151 | 25 | 2502 | 14A | VT Self & Bench | Volkas Polished | 1.94 | 1.94 |  | 2022-01-13
12 | MM-3140-195 | 25 | 2515 | 2E | VT Self & Bench | Volkas Polished | 1.69 | 1.69 |  | 2022-01-13
13 | MM-3140-215 | 25 | 2503 | 02D | VT Self & Bench | Volkas Polished | 1.55 | 1.55 |  | 2022-01-13
From 14th January to 22nd January
1 | MM-3140-193A | 27 | 2714 | 2G | floor(FL) | Travertine | 18.31 | 18.31 |  | 2022-01-14
2 | MM-3140-287 Revised | 8 | 807 | 07A | wall(CL) | Perlato Queen Beige | 28.4 | 28.4 |  | 2022-01-15
3 | MM-3140-288 revised | 14 | 1410 | 07A | wall(CL) | Perlato Queen Beige | 27.98 | 27.98 |  | 2022-01-15
4 | MM-3140-196 | 26 | 2614 | 2E | wall(CL) | Volkas | 31.44 | 31.44 |  | 2022-01-17
5 | MM-3140-128G | 15 | 1511 | 19A | MINI BAR(MB) | volkas polished | 3.04 | 3.04 |  | 2022-01-17
6 | MM-3140-128G | 15 | 1511 | 19A | MINI BAR(MB) | crystal white | 0.4 | 0.4 |  | 2022-01-17
7 | M-3140-129G | 13 | 1311 | 19A | Minibar | Volkas | 3.04 | 3.04 |  | 2022-01-17
8 | M-3140-129G | 13 | 1311 | 19A | Minibar | crystal white | 0.4 | 0.4 |  | 2022-01-17
9 | MM-3140-199G | 20 | 2006 | 19A | MINI BAR(MB) | volkas polished | 3.04 | 3.04 |  | 2022-01-17
10 | MM-3140-199G | 20 | 2006 | 19A | MINI BAR(MB) | crystal white | 0.4 | 0.4 |  | 2022-01-17
11 | MM-3140-233G | 19 | 1903 | 19A | MINI BAR(MB) | volkas polished | 3.04 | 3.04 |  | 2022-01-17
12 | MM-3140-233G | 19 | 1903 | 19A | MINI BAR(MB) | crystal white | 0.4 | 0.4 |  | 2022-01-17
13 | MM-3140-234G | 24 | 2411 | 19A | Minibar | Volkas | 3.04 | 3.04 |  | 2022-01-17
14 | MM-3140-234G | 24 | 2411 | 19A | Minibar | Crytsal white | 0.4 | 0.4 |  | 2022-01-17
15 | MM-3140-167 | 26 | 2607 | 03A | wall(CL) | Volkas polished | 28.72 | 28.72 |  | 2022-01-17
16 | MM-3140-183 | 25 | 2512 | 3C | wall(CL) | Volkas polished | 30.66 | 30.66 |  | 2022-01-18
17 | MM-3140-213CC | 16 | 1617 | 05A | Curve floor(FL) | travertine | 5.92 | 5.92 |  | 2022-01-18
18 | MM-3140-335MK | 7 | 707 | 07A | Stair | Dark Emperador | 1.57 | 1.57 |  | 2022-01-19
19 | MM-3140-169A rev 01 | 27 | 2707 | 3A | floor(FL) | Travertine | 21.72 | 21.72 |  | 2022-01-20
20 | MM-3140-289 revised | 16 | 1610 | 07A | wall(CL) | Perlato Queen Beige | 26.25 | 26.25 |  | 2022-01-20
21 | MM-3140-214 | 26 | 2606 | 2C | wall(CL) | Volkas polished | 35.39 | 35.39 |  | 2022-01-20
22 | MM-3140-222 | 25 | 2507 | 11C | Dado, Wall, Border Skirting | Volkas Polished | 3.28 | 3.28 |  | 2022-01-21
23 | MM-3140-176A | 26 | 2609 | 1A | Shower floor(FL) | Travertine | 2.97 | 2.97 |  | 2022-01-21
24 | MM-3140-235A | 19 | 1904 | 06A | Shower floor(FL) | travertine | 1.82 | 1.82 |  | 2022-01-21
25 | MM-3140-286A | 27 | 2706 | 2C | Shower floor(FL) | Travertine | 2.52 | 2.52 |  | 2022-01-21
26 | MM-3140-283A | 23 | 2305 | 16A | Shower floor(FL) | Travertine | 2.3 | 2.3 |  | 2022-01-21
27 | MM-3140-175A | 25 | 2510 | 1A | Shower floor(FL) | Travertine | 2.86 | 2.86 |  | 2022-01-21
28 | MM-3140-173A | 22 | 2204 | 02A | Shower floor(FL) | Travertine | 2.82 | 2.82 |  | 2022-01-21
29 | MM-3140-231A | 27 | 2702 | 14A | Shower floor(FL) | Travertine | 2.51 | 2.51 |  | 2022-01-21
30 | MM-3140-151 | 25 | 2502 | 14A | wall(CL) | Volkas Polished | 8.2 | 8.2 |  | 2022-01-21
31 | MM-3140-150CC | 20 | 2007 | 06A | Bathroom skirting(SK) | Crystal White | 0.95 | 0.95 |  | 2022-01-21
32 | MM-3140-206CC | 21 | 2105 but as per site 2107 | 06A | Bathroom skirting(SK) | Crystal White | 0.95 | 0.95 |  | 2022-01-21
33 | MM-3140-287C | 8 | 807 | 07A | border(BR)& threshold | crystal white | 1.36 | 1.36 |  | 2022-01-21
34 | MM-3140-334C | 25 | 2510 | 7A | border(BR)& threshold | Crystal white | 1.36 | 1.36 |  | 2022-01-21
35 | MM-3140-215 | 25 | 2503 | 02D | wall(CL) | Volkas Polished | 2.34 | 2.34 |  | 2022-01-22
36 | MM-3140-187 | 25 | 2513 | 3F | wall(CL) | Volkas polished | 30.31 | 30.31 |  | 2022-01-22
37 | MM-3140-230 | 26 | 2602 | 14A | wall(CL) | Volkas polished | 37.13 | 37.13 |  | 2022-01-22
38 | MM-3140-184A | 27 | 2712 | 3C | floor(FL) | Travertine | 20.52 | 20.52 |  | 2022-01-22
From 24th January to 31st January
1 | MM-3140-281CX | 8 | Different Room |  | Corridor | Volkas | 0.75 | 0.75
2 | MM-3140-222 | 25 | 2507 | 11C | Vanity Top | Volkas Polished | 1.16 | 1.16
3 | MM-3140-155L | 2003, 2103, 2203, 2303, 2404, 2414, 2405, 2408, 2415, 2504, 2512, 2505, 2508, 2513, 2604, 2607, 2611, 2612, 2704, 2707, 2712, 2713 |  | 03-Series | Wardrobe | Crystal | 2.68 | 2.68
4 | MM-3140-235L | 1904, 2006, 2106, 2206 & 2306 |  | 06A-Type | Wardrobe | Crystal | 3.08 | 3.08
5 | MM-3140-328S | 22 | Lift Lobby |  | Sofit | Volkas Polished | 2.16 | 2.16
6 | MM-3140-196 | 26 | 2614 | 2E | wall(CL) | Volkas | 2.54 | 2.54
7 | MM-3140-191 | 25 | 2514 | 2G | wall(CL) | Volkas | 34.27 | 34.27
8 | MM-3140-328C | 22 | Lift Lobby |  | Border | Volkas Polished | 8.79 | 8.79
9 | MM-3140-328C | 22 | Lift Lobby |  | Skirting | Volkas Polished | 1.59 | 1.59
10 | MM-3140-328A | 22 | Coridoor |  | skirting(SK) | Volkas Polished | 6.78 | 6.78
11 | MM-3140-328 | 22 | Lift Lobby |  | Cladding | Volkas Polished | 22.08 | 22.08
12 | MM-3140-100MKP | Mockup |  |  |  | Black absolute | 0.86 | 0.86
13 | MM-3140-177A | 27 | 2710 | 1A | floor(FL) | Travertine | 13.34 | 13.34
14 | MM-3140-289 revised | 16 | 1610 | 07A | wall(CL) | Perlato Queen Beige | 1.76 | 1.76
15 | MM-3140-192 | 26 | 2613 | 2G | wall(CL) | Volkas polished | 34.4 | 34.4
16 | MM-3140-218 | 26 | 2601 | 10B | wall(CL) | Volkas polished | 46.79 | 46.79
17 | MM-3140-168A | 27 | 2704 | 3A | floor(FL) | Travertine | 21.67 | 21.67
18 | MM-3140-247 | 26 | 2603 | 2D | wall(CL) | Volkas | 39.8 | 39.8
19 | MM-3140-292 | 26 | 2605 | 11D | wall(CL) | Volkas | 39.95 | 39.95
20 | MM-3140-180 | 26 | 2610 | 02F | wall(CL) | Volkas | 22.99 | 22.99
21 | MM-3140-289C | 16 | 1610 | 07A | border(BR)& threshold | crystal white | 1.36 | 1.36
22 | MM-3140-288C | 14 | 1410 | 07A | border(BR)& threshold | crystal white | 1.36 | 1.36
From 01st February to 08th February
1 | MM-3140-166 | 26 | 2604 | 3A | wall(CL) | Volkas polished | 27.53 | 27.53 |  | 2022-02-01
2 | MM-3140-154L | 2002, 2102, 2204, 2302, 2406, 2409, 2403, 2412, 2417, 2416, 2506, 2509, 2510, 2503, 2515, 2514, 2606, 2603, 2609, 2614, 2613, 2706, 2703, 2710, 2715, 2714 |  | 02A,02B,02C,02D,02E,02G and 01A | Wardrobe | Crystal | 14.23 | 14.23 |  | 2022-02-03
3 | MM-3140-155L | 2404, 2414, 2405, 2408 & 2415 |  | 03-Series | Wardrobe | Crystal | 3.35 | 3.35 |  | 2022-02-03
4 | MM-3140-130CX | 1417 & 1617 |  | 5A | Border | Crystal White | 2.42 | 2.42 |  | 2022-02-03
5 | MM-3140-178L | 2413, 2511, 2610 & 2711 |  | 02F | Wardrobe | Crystal | 2.13 | 2.13 |  | 2022-02-03
6 | MM-3140-288 revised | 14 | 1410 | 07A | wall(CL) | crystal white | 1.61 | 1.61 |  | 2022-02-03
7 | MM-3140-292 | 26 | 2605 | 11D | wall(CL) | Volkas | 2.1 | 2.1 |  | 2022-02-03
8 | MM-3140-154AEX | L-13 & 15 |  |  | architrave(AR) | Crystal White | 4.45 | 4.45 |  | 2022-02-03
9 | MM-3140-188 | 26 | 2612 | 3F | wall(CL) | Volkas polished | 30.31 | 30.31 |  | 2022-02-05
10 | MM-3140-155L | 2504, 2512, 2505, 2508, 2513, 2604 & 2607 |  | 03-Series | Wardrobe | Crystal | 4.69 | 4.69 |  | 2022-02-05
11 | MM-3140-233L | 1903 & 2006 |  | 19A | Wardrobe | Crystal | 2.56 | 2.56 |  | 2022-02-05
12 | MM-3140-156 | 10 | 1007 | 15A | wall(CL) | Perlato Queen Beige | 16.81 | 16.81 |  | 2022-02-05
13 | MM-3140-156X | 10 | 1007 | 15A | wall(CL) | Perlato Queen Beige | 10.87 | 10.87 |  | 2022-02-05
14 | MM-3140-336 revised | 22 | 2205 | 15A | wall(CL) | Parlato Queen Beige Polished | 27.66 | 27.66 |  | 2022-02-05
15 | MM-3140-212 | 26 | 2615 | 05A | wall(CL) | Volkas polished | 27.97 | 27.97 |  | 2022-02-07
16 | MM-3140-334A | 25 | 10 (Uper & Lower level) | 7A | floor(FL) | Volkas | 18.28 | 18.28 |  | 2022-02-07
17 | MM-3140-233L | 24 | 2411 | 19A | Wardrobe | Crystal | 1.28 | 1.28 |  | 2022-02-08
18 | MM-3140-155L | 2611, 2612, 2704, 2707, 2712 & 2713 |  | 03-Series | Wardrobe | Crystal | 4.06 | 4.06 |  | 2022-02-08
19 | MM-3140-169A rev 01 | 27 | 2707 | 3A | Shower floor(FL) | Travertine | 1.6 | 1.6 |  | 2022-02-08
20 | MM-3140-177A | 27 | 2710 | 1A | Shower floor(FL) | Travertine | 2.95 | 2.95 |  | 2022-02-08
21 | MM-3140-284A | 23 | 2306 | 06A | Shower floor(FL) | Travertine | 1.63 | 1.63 |  | 2022-02-08
22 | MM-3140-218A | 26 | 2601 | 10B | Shower floor(FL) | Travertine | 1.79 | 1.79 |  | 2022-02-08
23 | MM-3140-168A | 27 | 2704 | 3A | Shower floor(FL) | Travertine | 1.64 | 1.64 |  | 2022-02-08
24 | MM-3140-193A | 27 | 2714 | 2G | Shower floor(FL) | Travertine | 2.71 | 2.71 |  | 2022-02-08
25 | MM-3140-184A | 27 | 2712 | 3C | Shower floor(FL) | Travertine | 1.95 | 1.95 |  | 2022-02-08
26 | MM-3140-132AEX | L-13 & 14 |  |  | Extra floor(FL) Pieces | Travertine | 12.1 | 12.1 |  | 2022-02-08
| Total material delivered to the site from 29th November to 02nd January | [6 empty] | 1128.93

## Metal Frame Assesment (hidden)
Metal frame Progress Assesment
Level 08 to Level 16)
S.No | Type | Item Description |  | Level 8 | Level 9 | Level 10 | Level 11 | Level 12 | Level 13 | Level 14 | Level 15 | Level 16 | Level 19 | Level 20 | Level 21 | Level 22 | Level 23 | Level 24 | Level 25 | Level 26 | Level 27 | Total | Unit
Total Qty
Level 8 to Level 10
1 | 01A/1B | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
2 | 2A/2B/2C/2D | Vanity Top | 9 | 3 | 3 | 3 | [15 empty] | 9 | Nr
3 | 2A/2B/2C/2D | Bath Tub Top | 9 | 3 | 3 | 3 | [15 empty] | 9 | Nr
4 | 3A/3B/3D/3E/3G | Vanity Top | 6 | 2 | 2 | 2 | [15 empty] | 6 | Nr
5 | 4A/4B | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
6 | 8A | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
7 | 8A | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
8 | 9A | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
9 | 9A | Bath Tub Top | 1 |  | 1 | [16 empty] | 1 | Nr
10 | 9A | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
11 | 9B | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
12 | 9B | Bath Tub Top | 1 |  | 1 | [16 empty] | 1 | Nr
13 | 9B | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
Level 11 to Level 16
1 | 01A | Vanity Top | 2 | [6 empty] | 1 | 1 | [10 empty] | 2 | Nr
2 | 01C | Vanity Top | 4 |  |  |  | 1 | 1 | 1 |  |  | 1 | [9 empty] | 4 | Nr
3 | 2A/2B/2C/2D | Vanity Top | 18 |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | [9 empty] | 18 | Nr
4 | 2A/2B/2C/2D | Bath Tub Top | 18 |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | [9 empty] | 18 | Nr
5 | 2E/2F/2G/2H | Vanity Top | 15 |  |  |  |  | 3 | 3 | 3 | 3 | 3 | [9 empty] | 15 | Nr
6 | 2E/2F/2G/2H | Bath Tub Top | 15 |  |  |  |  | 3 | 3 | 3 | 3 | 3 | [9 empty] | 15 | Nr
7 | 3A/3B/3D/3E/3G | Vanity Top | 17 |  |  |  | 2 | 3 | 3 | 3 | 3 | 3 | [9 empty] | 17 | Nr
8 | 3C/3F | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
9 | 4A/4B | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
10 | 5A | Vanity Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
11 | 8A | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
12 | 8A | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
13 | 9A | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
14 | 9A | Bath Tub Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
15 | 9A | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
16 | 9B | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
17 | 9B | Bath Tub Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
18 | 9B | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
19 | 10A | Vanity Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
20 | 10A | Bath Tub Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
21 | 10A | Vanity Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
22 | 11A/11B/11C/11D | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
23 | 11A/11B/11C/11D | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
24 | 11A/11B/11C/11D | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
25 | 11A/11B/11C/11D | Bath Tub Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
26 | 16A | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
27 | 16A | Bath Tub Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
28 | 19A | Vanity Top | 2 | [5 empty] | 1 |  | 1 | [10 empty] | 2 | Nr
Level 19 to Level 27
| 01A | Vanity Top and side walls | 4 | [14 empty] | 1 | 1 | 1 | 1 | 4 | Nr
| 2A/2B/2C/2D | Vanity Top and side walls | 14 | [10 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 14 | Nr
| 2A/2B/2C/2D | Bath Tub Top, side walls | 14 | [10 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 14 | Nr
| 2E/2F/2G/2H | Vanity Top and side walls | 12 | [14 empty] | 3 | 3 |  |  | 6 | Nr
| 2E/2F/2G/2H | Bath Tub Top and side walls | 12 | [14 empty] | 3 | 3 |  |  | 6 | Nr
| 3A/3B/3D/3E/3G | Vanity top and walls type 2 | 14 | [10 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 12 | Nr
| 3C/3F | Vanity top and walls type 2 | 8 | [14 empty] | 2 | 2 |  |  | 4 | Nr
| 5A | Vanity top and walls type 3 | 4 | [14 empty] | 1 | 1 |  |  | 2 | Nr
| 6A | Vanity top and walls type 4 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 10B | Vanity Top and side walls type 1 | 3 | [15 empty] | 1 |  |  | 1 | Nr
| 10B | Bath Tub Top and side walls | 3 | [15 empty] | 1 |  |  | 1 | Nr
| 10B | Vanity Top type 3 | 3 | [15 empty] | 1 |  |  | 1 | Nr
| 11A/11B/11C/11D | Vanity Top type 3 | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 11A/11B/11C/11D | Vanity Top type 3 | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 11A/11B/11C/11D | Vanity Top type 3 | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 11A/11B/11C/11D | Bath Tub Top and side walls | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 12A | Vanity Top type 3 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 12A | Bath Tub Top and side walls | 10 | [9 empty] | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 10 | Nr
| 12A | Vanity Top type 3 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 12A | Vanity Top type 3 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 13A | Vanity top and side walls | 1 | [15 empty] | 1 |  |  | 1 | Nr
| 13A | Vanity top type 3 | 1 | [15 empty] | 1 |  |  | 1 | Nr
| 14A | Vanity top and walls type 2 | 4 | [14 empty] | 1 | 1 |  |  | 2 | Nr
| 14A | Vanity top type 3 | 4 | [14 empty] | 1 | 1 |  |  | 2 | Nr
| 16A | Vanity top and side walls | 2 | [13 empty] | 1 |  |  |  |  | 1 | Nr
| 16A | Bath Tub Top | 2 | [13 empty] | 1 |  |  |  |  | 1 | Nr
| 19A | Vanity top snd walls | 3 | [10 empty] | 1 |  |  |  | 1 |  |  |  | 2
| Total Metal Frame Qty |  | 384 | [18 empty] | 343
| Total Progress Metal Frame Qty |  | 343
| Progress % |  | 89.32%
| Total allocated amount as per ASI rates |  | 766683
| Total approved amount for Metal frame variation |  | 684823.6172

## Metal Frame Variation (hidden)
Metal Frame Total value descoped from ASI
ASI
Sr. No: | Type | Item Description | Total Q'ty | Unit | Category | Rate | Amount (AED)
1 | TYPE -01A (6 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 6 | No | Vanity Top / Side Walls | 1769 | 10614
4 | TYPE -01C (8 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 8 | No | Vanity Top / Side Walls | 1955 | 15268
9 | TYPE -2A/2B/2C/2D (44 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 44 | No | Vanity Top / Side Walls | 1769 | 77836
11 | TYPE -2E/2F/2G/2H (27 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 27 | No | Vanity Top / Side Walls | 1769 | 46458
15 | TYPE -3A/3B/3D/3E/3G (39 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 39 | No | Vanity Top / walls | 4780 | 148180
19 | TYPE -03C/03F (18 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 18 | No | Vanity Top / walls | 4780 | 86040
23 | TYPE -04A/4B (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 5 | No | Vanity Top / walls | 3946 | 19730
27 | TYPE -05A (9 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 9 | No | Vanity Top / walls | 3946 | 35514
31 | TYPE -06A (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 5 | No | Vanity Top / walls | 3946 | 19730
35 | TYPE -08A (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 5 | No | Vanity Top / walls | 3946 | 19730
40 | TYPE -08A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 1397 | 6985
41 | TYPE -09A (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 2 | No | Vanity Top / Side Walls | 2028 | 4056
46 | TYPE -09A (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 2 | No | Vanity Top | 679 | 1358
47 | TYPE -09B (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 2 | No | Vanity Top / Side Walls | 1932 | 3864
48 | TYPE -09B (2 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 | 2 | No | Bath Tub Top / Side Walls | 418 | 836
52 | TYPE -09B (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 2 | No | Vanity Top | 679 | 1358
53 | TYPE -10A (5 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 5 | No | Vanity Top / Side Walls | 1769 | 8845
58 | TYPE -10A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 1379 | 6895
59 | TYPE -10B (3 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 3 | No | Vanity Top / Side Walls | 1769 | 5307
64 | TYPE -10B (3 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 3 | No | Vanity Top | 1397 | 4191
67 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 19 | No | Vanity Top | 4510 | 85690
68 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 19 | No | Vanity Top | 1265 | 24035
72 | TYPE -12A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 4510 | 22550
78 | TYPE -12A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 1619 | 8095
79 | TYPE -13A (1 No) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 1 | No | Vanity Top / Side Walls | 1769 | 1769
84 | TYPE -13A (1 No) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 1 | No | Vanity Top | 1593 | 1593
85 | TYPE -14A (4 No) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 4 | No | Vanity Top / walls | 4780 | 19120
90 | TYPE -14A (4 No) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 4 | No | Vanity Top | 1120 | 4480
91 | TYPE -16A (3 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 3 | No | Vanity Top / Side Walls | 1932 | 5796
95 | TYPE -19A (6 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 6 | No | Vanity Top / walls | 4780 | 28680
| TYPE - 07A ( 5 Nos) | Master Bath Vanity | 5 | No | Vanity Top | 7772 | 38860
|  | Powder Room Vanity | 5 | No | Vanity Top | 644 | 3220
|  | TOTAL AMOUNT |  |  |  |  | 766683
724603
713989
Verify Basic Data

## 7A & 15A
STONE WORKS TO ROOM TYPE 7A & 15A | [21 empty] | Payment Upto End of: | 2022-12-01
Bill No. | Item No. | Description | Quantity | Unit | Material | Thick | Supply Rate | Fixing Rate | Unit Rate | Amount | Work Progress (%) |  |  | Total Amount |  |  | Total | 7A | 7A | 7A | 7A | 7A | 15A | 15A
[11 empty] | Previous | Current | Cummulative | Previous | Current | Cummulative |  | Lvl 7 | Lvl 13 | Lvl 15 | Lvl 20 | Lvl 24 | Lvl 10 | Lvl 22
| 1 | PACKAGE 7 - STONE WORKS
1 Bed Duplex Suite
| A | TYPE -07A (5 No's)
FLOOR FINISHES
Master Bathroom
| A.1 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 70.5 | m2 | Volakas | 20 | 433 | 205 | 638 | 44979 | 100% | 0% | 100% | 44979 | 0 | 44979 | 100% | 100% | 100% | 100% | 100% | 100%
| A.2 | 7 x 5mm Brass strip insert in brushed finish . | 30 | mr | Brass | 5 | 0 | 60 | 60 | 1800 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Toilet
| A.3 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 11 | m2 | Volakas | 20 | 433 | 205 | 638 | 7018 | 100% | 0% | 100% | 7018 | 0 | 7018 | 100% | 100% | 100% | 100% | 100% | 100%
| A.4 | Supply & fixing of 20m thk threshold 800mm x 240mm, polished Calacatta Vagli | 5 | No | Volakas | 20 | 124 | 41 | 165 | 825 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Guest WC
| A.5 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 5.5 | m2 | Volakas | 20 | 433 | 205 | 638 | 3509 | 100% | 0% | 100% | 3509 | 0 | 3509 | 100% | 100% | 100% | 100% | 100% | 100%
| A.6 | 20mm thick polished Crystal White, average 130mm width border. | 5.5 | m2 | Crystal White | 20 | 282 | 206 | 488 | 2684 | 100% | 0% | 100% | 2684 | 0 | 2684 | 100% | 100% | 100% | 100% | 100% | 100%
| A.7 | 7 x 5mm Brass strip insert in brushed finish . | 22.5 | mr | Brass | 5 | 0 | 60 | 60 | 1350 | 100% | 0% | 100% | 1350 | 0 | 1350 | 100% | 100% | 100% | 100% | 100% | 100%
Wall Finishes
Master Bathroom
| A.8 | Supply and installation of skirting Crystal White 300 x 20 mm thk | 25 | mr | Crystal White | 20 | 111 | 75 | 186 | 4650 | 80% | 0% | 80% | 3720 | 0 | 3720 | 80% | 100% | 100% | 100% | 0% | 100%
| A.9 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 30 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 39360 | 80% | 0% | 80% | 31488 | 0 | 31488 | 80% | 100% | 100% | 100% | 0% | 100%
Toilet
| A.10 | Supply and installation of skirting Victoria falls quartzite, 150+35 x 20 mm thk | 25 | mr | Victoria Falls | 20 | 233 | 53 | 286 | 7150 | 100% | 0% | 100% | 7150 | 0 | 7150 | 100% | 100% | 100% | 100% | 100% | 100%
| A.11 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick - upto dado level | 27.5 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 36080 | 100% | 0% | 100% | 36080 | 0 | 36080 | 100% | 100% | 100% | 100% | 100% | 100%
Guest WC
| A.12 | Supply and installation of skirting Victoria falls quartzite, 150+35 x 20 mm thk | 30 | mr | Victoria Falls | 20 | 233 | 53 | 286 | 8580 | 100% | 0% | 100% | 8580 | 0 | 8580 | 100% | 100% | 100% | 100% | 100% | 100%
| A.13 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick - upto dado level | 32.25 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 42312 | 100% | 0% | 100% | 42312 | 0 | 42312 | 100% | 100% | 100% | 100% | 100% | 100%
Lobby
| A.14 | Supply and installation of cladding, 20mm thick polished Saint Laurent Marble, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 79 | m2 | New Saint Laurent | 20 | 369 | 222 | 591 | 46689 | 0% | 20% | 20% | 0 | 9337.8 | 9337.8 | 20% | 100% | 0% | 0% | 0% | 0%
| A.15 | Supply and installation of cladding on the door, 20mm thick polished Saint Laurent Marble, to be fixed with honey comb with standard cementitious adhesive maximum up to 5mm thick | 22.5 | m2 | New Saint Laurent | 20 | 940 | 283 | 1223 | 27517.5 | 0% | 20% | 20% | 0 | 5503.5 | 5503.5 | 20% | 100% | 0% | 0% | 0% | 0%
Joinery Items
Bathroom
| A.16 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 4566 x 605, with 280mm high fascia and 400x20 mm splashback with 2 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 5 | No | Victoria Falls | 20 | 8307 | 20462 | 28769 | 143845 | 100% | 0% | 100% | 143845 | 0 | 143845 | 100% | 100% | 100% | 100% | 100% | 100%
Toilet
| A.17 | Cistern Top : Supply and installation of 20mm thick polished Victoria falls, 260mm W x 1250mm length, pencil edge finish. | 5 | No | Victoria Falls | 20 | 375 | 87 | 462 | 2310 | 100% | 0% | 100% | 2310 | 0 | 2310 | 100% | 100% | 100% | 100% | 100% | 100%
| A.18 | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Victoria falls shelf size of 120mm W x 200mm L, edges chamfered. | 5 | No | Victoria Falls | 20 | 41 | 6 | 47 | 235 | 100% | 0% | 100% | 235 | 0 | 235 | 100% | 100% | 100% | 100% | 100% | 100%
Guest WC
| A.19 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 595 x 400, with 400mm high fascia with 1 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 5 | No | Victoria Falls | 20 | 1230 | 2761 | 3991 | 19955 | 100% | 0% | 100% | 19955 | 0 | 19955 | 100% | 100% | 100% | 100% | 100% | 100%
| A.20 | Cistern Top : Supply and installation of 20mm thick polished Victoria falls, 260mm W x 1250mm length, pencil edge finish. | 5 | No | Victoria Falls | 20 | 375 | 87 | 462 | 2310 | 100% | 0% | 100% | 2310 | 0 | 2310 | 100% | 100% | 100% | 100% | 100% | 100%
| A.21 | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Victoria falls shelf size of 120mm W x 200mm L, edges chamfered. | 5 | No | Victoria Falls | 20 | 41 | 6 | 47 | 235 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Vestibule
| A.22 | Supply and installation of 20mm thick, Counter top polished Saint Laurent Marble, top size 1482 x 555, with 40mm fascia and 2 nos of drawer cladding, size 400 x 100mm. [Inc. ss framing] | 5 | No | New Saint Laurent | 20 | 409 | 1572 | 1981 | 9905 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Walk-In Closet
| A.23 | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 1280 x 690mm, with 40mm fascia. [ Frameworks and back support by others ] | 5 | No | Crystal White | 20 | 397 | 235 | 632 | 3160 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
| A.24 | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 770 x 690mm, with 40mm fascia. [ Frameworks and back support by others ] | 5 | No | Crystal White | 20 | 256 | 141 | 397 | 1985 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Mini Bar
| A.25 | Supply and installation of Mini Bar 20mm thick Saint Laurent Marble, Counter top size 1560 x 620, with 40mm fascia and 2 nos shelf size 1560 x 250 with 40mm fascia with cladding to front and side of the mini bar including soffit, skirting & drawer cladding. [ Frameworks and back support by others ] | 5 | No | New Saint Laurent | 20 | 4300 | 2534 | 6834 | 34170 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Side Table
| A.26 | Supply and installation of side table 20mm thick Vlota Marble, table top size 1826 x 650. [ Frameworks and back support by others ] | 10 | No | Viola | 20 | 2852 | 313 | 3165 | 31650 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Stair Case
| A.27 | Supply & instllation of staircase 20mm thk. Polished Saint Laurent Marble, tread 300 x 200mm thk & Riser 150x20mm | 102 | mr | New Saint Laurent | 20 | 217 | 113 | 330 | 33660 | 100% | 0% | 100% | 33660 | 0 | 33660 | 100% | 100% | 100% | 100% | 100% | 100%
| A.28 | Supply & instllation of stringer 20mm thk. Polished Saint Laurent Marble, size 350 x 20mm | 36.5 | mr | New Saint Laurent | 20 | 146 | 88 | 234 | 8541 | 96% | 0% | 96% | 8199.36 | 0 | 8199.36 | 96% | 100% | 100% | 100% | 80% | 100%
| A.29 | Supply & instllation of mid landing at staircase 20mm thk. Polished Saint Laurent Marble, with 3 nos of tread & Riser. | 16 | m2 | New Saint Laurent | 20 | 354 | 153 | 507 | 8112 | 20% | 80% | 100% | 1622.4 | 6489.6 | 8112 | 100% | 100% | 100% | 100% | 100% | 100%
Miscellaneous Items
| A.30 | Extra over charges for standard sealer coating to top surface of stone if required. | 495 | m2 |  |  | 0 | 8 | 8 | 3960 | 100% | 0% | 100% | 3960 | 0 | 3960 | 100% | 100% | 100% | 100% | 100% | 100%
| A.31 | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 93.5 | m2 |  |  | 0 | 8 | 8 | 748 | 100% | 0% | 100% | 748 | 0 | 748 | 100% | 100% | 100% | 100% | 100% | 100%
1 Bed Double Height Suite
| B | TYPE -15A (2 No's)
FLOOR FINISHES
Master Bathroom
| B.1 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 10 | m2 | Volakas | 20 | 433 | 205 | 638 | 6380 | 100% | 0% | 100% | 6380 | 0 | 6380 | 100% | [5 empty] | 100% | 100%
| B.2 | 7 x 5mm Brass strip insert in brushed finish . | 6 | mr | Brass | 5 | 0 | 60 | 60 | 360 | 0% | 100% | 100% | 0 | 360 | 360 | 100% | [5 empty] | 100% | 100%
Guest WC
| B.3 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 1.7 | m2 | Volakas | 20 | 433 | 205 | 638 | 1084.6 | 100% | 0% | 100% | 1084.6 | 0 | 1084.6 | 100% | [5 empty] | 100% | 100%
| B.4 | 20mm thick polished Crystal White, average 130mm width border. | 2 | m2 | Crystal White | 20 | 282 | 206 | 488 | 976 | 100% | 0% | 100% | 976 | 0 | 976 | 100% | [5 empty] | 100% | 100%
| B.5 | 7 x 5mm Brass strip insert in brushed finish . | 7.6 | mr | Brass | 5 | 0 | 60 | 60 | 456 | 100% | 0% | 100% | 456 | 0 | 456 | 100% | [5 empty] | 100% | 100%
Wall Finishes
Master Bathroom
| B.6 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 30 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 39360 | 100% | 0% | 100% | 39360 | 0 | 39360 | 100% | [5 empty] | 100% | 100%
Guest WC
| B.7 | Supply and installation of skirting Victoria falls quartzite, 150+35 x 20 mm thk | 10 | mr | Victoria Falls | 20 | 233 | 53 | 286 | 2860 | 100% | 0% | 100% | 2860 | 0 | 2860 | 100% | [5 empty] | 100% | 100%
| B.8 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick - upto dado level | 10.6 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 13907.2 | 100% | 0% | 100% | 13907.2 | 0 | 13907.2 | 100% | [5 empty] | 100% | 100%
Lobby
| B.9 | Supply and installation of cladding, 20mm thick polished Saint Laurent Marble, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 11.6 | m2 | New Saint Laurent | 20 | 369 | 222 | 591 | 6855.6 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.10 | Supply and installation of cladding on the door, 20mm thick polished Saint Laurent Marble, to be fixed with honey comb with standard cementitious adhesive maximum up to 5mm thick | 14.6 | m2 | New Saint Laurent | 20 | 940 | 283 | 1223 | 17855.8 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Joinery Items
Bathroom
| B.11 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 3250 x 605, with 280mm high fascia and 400x20 mm splashback with 2 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 2 | No | Victoria Falls | 20 | 6638 | 16198 | 22836 | 45672 | 0% | 100% | 100% | 0 | 45672 | 45672 | 100% | [5 empty] | 100% | 100%
| B.12 | Supply and installation of shelf top 20mm thick Victoria falls quartzite, size of 120 x 200mm, chamfered edges . | 2 | No | Victoria Falls | 20 | 41 | 6 | 47 | 94 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Guest WC
| B.13 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 595 x 400, with 400mm high fascia with 1 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 2 | No | Victoria Falls | 20 | 1230 | 2761 | 3991 | 7982 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.14 | Cistern Top : Supply and installation of 20mm thick polished Victoria falls, 260mm W x 1250mm length, pencil edge finish. | 2 | No | Victoria Falls | 20 | 375 | 87 | 462 | 924 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.15 | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Victoria falls shelf size of 120mm W x 200mm L, edges chamfered. | 2 | No | Victoria Falls | 20 | 41 | 6 | 47 | 94 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Vestibule
| B.16 | Supply and installation of 20mm thick, Counter top polished Saint Laurent Marble, top size 1482 x 555, with 40mm fascia and 2 nos of drawer cladding, size 400 x 100mm. [Inc. ss framing] | 2 | No | New Saint Laurent | 20 | 409 | 1572 | 1981 | 3962 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
| B.17 | Vestibule : 325mm wide; total size of 1500 x 2400mm high. | 2 | No | Crystal White | 30 | 1126 | 477 | 1603 | 3206 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Mini Bar
| B.18 | Supply and installation of Mini Bar 20mm thick Saint Laurent Marble, Counter top size 1560 x 620, with 40mm fascia and 2 nos shelf size 1560 x 250 with 40mm fascia with cladding to front and side of the mini bar including soffit, skirting & drawer cladding. [ Frameworks and back support by others ] | 2 | No | New Saint Laurent | 20 | 4300 | 2534 | 6834 | 13668 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Miscellaneous Items
| B.13 | Extra over charges for standard sealer coating to top surface of stone if required. | 122 | m2 |  |  |  | 8 | 8 | 976 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.14 | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 14 | m2 |  |  |  | 8 | 8 | 112 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
|  | Total Amount AED | [7 empty] | 746069.7 | 53.75% | 9.029% | 72.12% | 470738.56 | 67362.9 | 538101.46

## VO Summary
SUMMARY - POST WFA VARIATIONS
Vo.No: | Description | Amount Submitted | % Work Done | Amount Submitted | Remark
2 | Variation Orders - Post Sub Contract Agreement - KCE
A.1 | Proceed with supply & installation of balance stone works at lift lobbies basement 1 & 2, Ground lvl, 2nd, 4th, & 23ed floor. DAR/3333/as/mb/0971 Dated 11 Oct 2022 | 617777 | 75.01% | 463374.6984 | Approved E11/K109/KD/SR/304
1 - Rev 1 | Supply & installation of marble floor at corridor ground floor. DAR/3333/as/rj/0772 Dated 5 Aug 2022 | 5502.33 | 100% | 5502.33 | Instrction via e mail Dated 4 Aug 2022 (Mr. Anil Kariyappa)
2 | Supply & installation of marble architrave at lift lobby, Lvl 7 - Lvl . Hotel Area. DAR/3333/as/rj/0975 Dated 12 Oct 2022 | 58140 | 40% | 23256 | Instruction Ref: E11/K109/SN/dm/230 Dated 23 Sept 22
3 | Supply and installation of pink onyx cladding at level 2. DAR/3214/as/rj/0982 Dated 13 Oct 2022 | 757050 | 0% | 0 | Instruction Ref: E11/K109/SN/dm/232 Dated 23 Sept 22
4 | Supply and Fixing of SS Strip. DAR/3333/as/rj/1109 Dated 15 Nov 2022 | 21000 | 0% | 0 | Instrction via e mail Dated 10-Nov-22 (Mr. Saman)
| Sub Total | 1459469.33 | 33.72% | 492133.0284
TOTAL AMOUNT |  | 1459469.33 | Dhs. | #REF!

## AHK Balance Work
SUBJECT | Supply & Installation Of Balance Stone Works At Lift Lobbies Basement 1 & 2, Ground Lvl, 2nd, 4th, & 23ed Floor.
BILL OF QUANTITIES
[9 empty] | Payment Upto End Of | : Nov 2022
Bill No. | Item No. | Description | Unit | Quantity | Unit Rate | Amount | Balance Works | Amount Balance Work | % Of Work Completed | Amount
STONE WORKS
RESIDENTIAL AMENITIES, LOBBIES AND LIFT LOBBIES (B1, B2, GF, L2, L4 and L23)
FLOOR FINISHES
Stone floor finish laid on cement and sand screed including all necessary grouting, movement joints, pointing, polishing, dry set mortar or adhesive and the like; all in accordance with the drawings and specification
Residential - Basement 1 Lift Lobby
| A | Type RES-ST-16; Stone border to lift lobby | m2 | 13 | 479 | 6227 | 23.7% | 1476.03 | 95% | 1402.2285
Residential - Basement 2 Lift Lobby
| B | Type RES-ST-16; Stone border to lift lobby | m2 | 13 | 479 | 6227 | 23.7% | 1476.03 | 95% | 1402.2285
Residential - Ground Floor Lobby
| C | Type RES-ST-16; Stone border to concierge and corridor | m2 | 59 | 479 | 28261 | 23.7% | 6698.89 | 95% | 6363.9455
| D | Type RES-ST-16; Stone border to lift lobby | m2 | 13 | 479 | 6227 | 23.7% | 1476.03 | 95% | 1402.2285
| D1 | Type RES-ST-26; Stone border to Main Entrance | m2 | 6 | 557 | 3342 | 100% | 3342 | 95% | 3174.9
| D2 | Type RES-ST-27; Stone border to Main Entrance | m2 | 6 | 557 | 3342 | 100% | 3342 | 95% | 3174.9
Residential - Level 2 Lobby and Corridor
| E | Type RES-ST-16; Stone border to lobby | m2 | 39 | 479 | 18681 | 23.7% | 4428.09 | 95% | 4206.6855
| F | Type RES-ST-16; Stone border to lift lobby | m2 | 9 | 479 | 4311 | 23.7% | 1021.8669 | 95% | 970.7736
Residential - Level 4 Amenities, Corridor and Lift Lobby
| A | Type RES-ST-16; Stone flooring to reception | m2 | 65 | 479 | 31135 | 23.7% | 7380.15 | 95% | 7011.1425
| B | Type RES-ST-16; Stone flooring to lift lobby | m2 | 10 | 479 | 4790 | 23.7% | 1135.4077 | 95% | 1078.6373
| C | Type RES-ST-24; Stone flooring to men's changing room | m2 | 23 | 625 | 14375 | 23.7% | 3407.4083 | 95% | 3237.0378
| D | Type RES-ST-24; Stone flooring to women's changing room | m2 | 31 | 625 | 19375 | 23.7% | 4592.5937 | 95% | 4362.9641
| E | Type RES-ST-25; Stone flooring to shower room at men's changing room | m2 | 6 | 625 | 3750 | 23.7% | 888.8891 | 95% | 844.4447
| F | Type RES-ST-25; Stone flooring to shower room at women's changing room | m2 | 6 | 625 | 3750 | 23.7% | 888.8891 | 95% | 844.4447
Residential - Level 23 Amenities, Corridor and Lift Lobby
| G | Type RES-ST-02; Stone border to lift lobby | m2 | 9 | 805 | 7245 | 23.7% | 1717.3338 | 95% | 1631.4671
| H | Type RES-ST-02; Stone border to corridor | m2 | 31 | 805 | 24955 | 23.7% | 5915.2607 | 95% | 5619.4977
| J | Type RES-ST-02; Stone border to meeting room | m2 | 14 | 805 | 11270 | 23.7% | 2671.4081 | 95% | 2537.8377
| K | Type RES-ST-02; Stone border to multifunction room | m2 | 12 | 805 | 9660 | 23.7% | 2289.7784 | 95% | 2175.2894
| L | Type RES-ST-21; Stone flooring to men's restroom | m2 | 21 | 512 | 10752 | 23.7% | 2548.6229 | 95% | 2421.1917
| M | Type RES-ST-21; Stone flooring to women's restroom | m2 | 21 | 512 | 10752 | 23.7% | 2548.6229 | 95% | 2421.1917
WALL FINISHES
Stone wall finish including all necessary supports, framing, backing, fixings, fittings, accessories, etc. and the like; all in accordance with the drawings and specification (linear lighting by others)
Residential - Basement 1 Lift Lobby
| N | Type RES-ST-26; Stone cladding in open book to lift lobby | m2 | 30 | 744 | 22320 | 100% | 22320 | 90% | 20088
| A | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 90% | 8436.6
Residential - Basement 2 Lift Lobby
| B | Type RES-ST-26; Stone cladding in open book to lift lobby | m2 | 30 | 744 | 22320 | 23.7% | 5290.668 | 95% | 5026.1346
| C | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 95% | 8905.3
Residential - Ground Floor Lobby
| D | Type RES-ST-16; Stone cladding to cloakroom | m2 | 14 | 598 | 8372 | 23.7% | 1984.4746 | 95% | 1885.2508
| E | Type RES-ST-16; Stone cladding to concierge area | m2 | 53 | 598 | 31694 | 23.7% | 7512.6537 | 95% | 7137.0211
| F | Type RES-ST-16; Stone pillars with lit surface to corridor including metal structure | m2 | 175 | 626 | 109550 | 23.7% | 25967.4139 | 95% | 24669.0432
| G | Type RES-ST-16; Backlit stone cladding to corridor | m2 | 2 | 598 | 1196 | 23.7% | 283.4964 | 95% | 269.3215
| H | Type RES-ST-16; Stone fascia 250mm wide to corridor (refer Drawing 120) | mr | 4 | 214 | 856 | 23.7% | 202.9038 | 95% | 192.7586
| J | Type RES-ST-16; Stone fascia 250mm wide to cloakroom (refer Drawing 120) | mr | 2 | 214 | 428 | 23.7% | 101.4519 | 95% | 96.3793
| K | Type RES-ST-26; Stone cladding in open book to lift lobby | m2 | 61 | 676 | 41236 | 23.7% | 9774.4617 | 95% | 9285.7386
| L | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4497 | 8994 | 100% | 8994 |  | 0
Residential - Level 2 Lobby and Corridor
| M | Type RES-ST-16; Stone pillars with lit surface to lobby including metal structure | m2 | 49 | 626 | 30674 | 23.7% | 7270.8759 | 95% | 6907.3321
| N | Type RES-ST-26; Stone cladding to lift lobby | m2 | 24 | 744 | 17856 | 23.7% | 4232.5344 | 95% | 4020.9077
| S | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 95% | 8905.3
Residential - Level 4 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-16; Stone cladding to corridor (wooden stiles and rails measured separately) | m2 | 83 | 598 | 49634 | 23.7% | 11765.0992 | 95% | 11176.8443
| C | Type RES-ST-23; Stone screen (2 layers of stone) 2100mm high to men's changing room (refer Drawings 315 to 318) | m2 | 21 | 842 | 17682 | 23.7% | 4191.2899 | 95% | 3981.7254
| D | Type RES-ST-23; Stone screen (2 layers of stone) 2100mm high to women's changing room (refer Drawings 310 to 313) | m2 | 23 | 842 | 19366 | 23.7% | 4590.4604 | 95% | 4360.9374
| E | Type RES-ST-23; Stone fluted walls to men's changing room | m2 | 19 | 954 | 18126 | 23.7% | 4296.5344 | 95% | 4081.7077
| F | Type RES-ST-23; Stone fluted walls to women's changing room | m2 | 31 | 954 | 29574 | 23.7% | 7010.1351 | 95% | 6659.6283
| G | Type RES-ST-23; Stone cladding to men's changing room | m2 | 7 | 744 | 5208 | 23.7% | 1234.4892 | 95% | 1172.7647
| H | Type RES-ST-23; Stone cladding to shower room at men's changing room | m2 | 35 | 744 | 26040 | 23.7% | 6172.446 | 95% | 5863.8237
| J | Type RES-ST-23; Stone cladding to shower room at women's changing room | m2 | 36 | 744 | 26784 | 23.7% | 6348.8016 | 95% | 6031.3615
| K | Type RES-ST-23; Stone wall to cistern enclosure overall size 1020mm (L) x 1080mm (H) at men's changing room (refer Drawing 322) | No | 2 | 1021 | 2042 | 23.7% | 484.0298 | 95% | 459.8283
| L | Type RES-ST-23; Stone wall to cistern enclosure overall size 1020mm (L) x 1080mm (H) at women's changing room (refer Drawing 322) | No | 2 | 1021 | 2042 | 23.7% | 484.0298 | 95% | 459.8283
| M | Type RES-ST-26; Stone cladding to lift lobby | m2 | 46 | 954 | 43884 | 100% | 43884 | 90% | 39495.6
| A | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 90% | 8436.6
Residential - Level 23 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-26; Stone cladding to lift lobby | m2 | 38 | 954 | 36252 | 100% | 36252 | 90% | 32626.8
| C | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 90% | 8436.6
| D | Type RES-ST-22; Stone wall to men's restroom (refer Detail 12 & 13 of Drawing 33) (metal strips measured separately) | m2 | 36 | 1466 | 52776 | 100% | 52776 | 80% | 42220.8
| E | Type RES-ST-22; Stone wall to women's restroom (refer Detail 12 & 13 of Drawing 33) (metal strips measured separately) | m2 | 40 | 1466 | 58640 | 100% | 58640 | 80% | 46912
| F | Type RES-ST-21; Stone wall to cistern enclosure overall size 1270mm (L) x 1080mm (H) at men's changing room (refer Drawing 354) | No | 2 | 860 | 1720 | 100% | 1720 | 80% | 1376
| G | Type RES-ST-21; Stone wall to cistern enclosure overall size 1270mm (L) x 1080mm (H) at women's changing room (refer Drawing 354) | No | 2 | 860 | 1720 | 100% | 1720 | 80% | 1376
SKIRTING
Stone skirting finish including all necessary supports, framing, backing, fixings, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| H | Type RES-ST-16; Stone skirting 250mm high to cloakroom (refer Detail 03 of Drawing 301) | mr | 6 | 360 | 2160 | 23.7% | 512.0001 | 95% | 486.4001
| J | Type RES-ST-16; Stone skirting 250mm high to concierge (refer Detail 05 of Drawing 300) | mr | 10 | 360 | 3600 | 23.7% | 853.3335 | 95% | 810.6669
Residential - Level 2 Lobby and Corridor
| A | Type RES-ST-02; Stone skirting 250mm high to lobby (refer Detail 08 of Drawing 300) | mr | 19 | 458 | 8702 | 23.7% | 2062.6968 | 95% | 1959.562
Residential - Level 4 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-23; Stone skirting 150mm high to men's changing room | mr | 7 | 288 | 2016 | 23.7% | 477.8668 | 95% | 453.9734
| C | Type RES-ST-23; Stone skirting 200mm high to men's changing room inside cubicles (refer Detail 02 of Drawing 301) | mr | 5 | 346 | 1730 | 23.7% | 410.0742 | 95% | 389.5705
| D | Type RES-ST-23; Stone skirting 150mm high to women's changing room | mr | 5 | 288 | 1440 | 23.7% | 341.3334 | 95% | 324.2667
| E | Type RES-ST-23; Stone skirting 200mm high to women's changing room inside cubicles (refer Detail 02 of Drawing 301) | mr | 15 | 346 | 5190 | 23.7% | 1230.2225 | 95% | 1168.7114
Residential - Level 23 Amenities, Corridor and Lift Lobby
| F | Type RES-ST-11; Stone skirting 300mm high to meeting room (refer Detail 02 of Drawing 336) | mr | 3 | 449 | 1347 | 100% | 1347 | 90% | 1212.3
| G | Type RES-ST-11; Stone skirting 300mm high to mulfunction room (refer Detail 02 of Drawing 336) | mr | 2 | 449 | 898 | 100% | 898 | 90% | 808.2
| H | Type RES-ST-21; Stone skirting 300mm high to men's restroom (refer Detail 02 of Drawing 336) | mr | 2 | 433 | 866 | 100% | 866 | 90% | 779.4
| J | Type RES-ST-21; Stone skirting 300mm high to women's restroom (refer Detail 02 of Drawing 336) | mr | 2 | 433 | 866 | 100% | 866 | 90% | 779.4
THRESHOLD
Supply and fixing of stone threshold, including all necessary grouting, polishing, adhesives, etc. and the like; all in accordance with the drawings and specification
Residential - Basement 1 Lift Lobby
| A | Type RES-ST-16; Stone threshold 225mm wide to lift lobby | mr | 2 | 164 | 328 | 23.7% | 77.7482 | 95% | 73.8608
| B | Type RES-ST-16; Stone threshold 305mm wide to lift lobby | mr | 5 | 207 | 1035 | 23.7% | 245.3334 | 95% | 233.0667
Residential - Basement 2 Lift Lobby
| C | Type RES-ST-16; Stone threshold 225mm wide to lift lobby | mr | 2 | 164 | 328 | 23.7% | 77.7482 | 95% | 73.8608
| D | Type RES-ST-16; Stone threshold 305mm wide to lift lobby | mr | 5 | 207 | 1035 | 23.7% | 245.3334 | 95% | 233.0667
Residential - Ground Floor Lobby
| E | Type RES-ST-16; Stone threshold 225mm wide to lift lobby | mr | 3 | 164 | 492 | 23.7% | 116.6223 | 95% | 110.7911
| F | Type RES-ST-16; Stone threshold 305mm wide to lift lobby | mr | 5 | 207 | 1035 | 23.7% | 245.3334 | 95% | 233.0667
| G | Type RES-ST-16; Stone threshold 500mm wide to BOH door | mr | 2 | 307 | 614 | 23.7% | 145.5408 | 95% | 138.2637
| H | Type RES-ST-26; Stone threshold 250mm wide to airlock | mr | 21 | 211 | 4431 | 23.7% | 1050.3114 | 95% | 997.7958
| J | Type RES-ST-27; Stone threshold 250mm wide to airlock | mr | 20 | 211 | 4220 | 23.7% | 1000.2965 | 95% | 950.2817
| K | Type RES-ST-27; Stone threshold 315mm wide to concierge | mr | 2 | 258 | 516 | 23.7% | 122.3111 | 95% | 116.1956
Residential - Level 2 Lobby and Corridor
| A | Type RES-ST-16; Stone threshold 375mm wide to lift lobby | mr | 3 | 244 | 732 | 23.7% | 173.5112 | 95% | 164.8356
| B | Type RES-ST-16; Stone threshold 415mm wide to lift lobby | mr | 5 | 264 | 1320 | 23.7% | 312.889 | 95% | 297.2445
| C | Type RES-ST-16; Stone threshold 1450mm wide to lift lobby | mr | 3 | 809 | 2427 | 23.7% | 575.289 | 95% | 546.5246
Residential - Level 4 Amenities, Corridor and Lift Lobby
| D | Type RES-ST-16; Stone threshold 375mm wide to lift lobby | mr | 2 | 244 | 488 | 23.7% | 115.6741 | 95% | 109.8904
| E | Type RES-ST-16; Stone threshold 415mm wide to lift lobby | mr | 5 | 264 | 1320 | 23.7% | 312.889 | 95% | 297.2445
| F | Type RES-ST-16; Stone threshold 1180mm wide to lift lobby | mr | 3 | 666 | 1998 | 23.7% | 473.6001 | 95% | 449.9201
| G | Type RES-ST-24; Stone threshold 100mm wide to men's and women's changing room | mr | 4 | 110 | 440 | 23.7% | 104.2963 | 95% | 99.0815
| H | Type RES-ST-25; Stone threshold 100mm wide to men's and women's changing room | mr | 4 | 110 | 440 | 23.7% | 104.2963 | 95% | 99.0815
Residential - Level 23 Amenities, Corridor and Lift Lobby
| J | Type RES-ST-02; Stone threshold 200mm wide to corridor | mr | 2 | 213 | 426 | 100% | 426 | 90% | 383.4
| K | Type RES-ST-02; Stone threshold 285mm wide to lift lobby | mr | 5 | 291 | 1455 | 100% | 1455 | 95% | 1382.25
| L | Type RES-ST-02; Stone threshold 340mm wide to meeting and multifunction room | mr | 7 | 334 | 2338 | 100% | 2338 | 90% | 2104.2
| M | Type RES-ST-02; Stone threshold 500mm wide to BOH doors | mr | 4 | 470 | 1880 | 100% | 1880 | 90% | 1692
| N | Type RES-ST-21; Stone threshold 250mm wide to men's and women's restrooms | mr | 2 | 183 | 366 | 100% | 366 | 90% | 329.4
ARCHITRAVE FINISHES
Stone architrave finishes including all necessary supports, framing, backing, fixings, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Basement 1 Lift Lobby
| A | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 100% | 7175 | 90% | 6457.5
| B | Type RES-ST-02; Stone architrave size 1450mm wide (refer Drawing 202) | mr | 15 | 1295 | 19425 | 100% | 19425 | 90% | 17482.5
Residential - Basement 2 Lift Lobby
| C | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 23.7% | 1700.7412 | 95% | 1615.7041
| D | Type RES-ST-02; Stone architrave size 1450mm wide (refer Drawing 202) | mr | 15 | 1295 | 19425 | 23.7% | 4604.4456 | 95% | 4374.2233
Residential - Ground Floor Lobby
| E | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby (refer Drawing 310) | mr | 25 | 287 | 7175 | 23.7% | 1700.7412 | 95% | 1615.7041
| F | Type RES-ST-16; Stone architrave size 400mm wide (refer Drawing 305) (linear lighting by others) | mr | 39 | 268 | 10452 | 23.7% | 2477.5117 | 95% | 2353.6361
| G | Type RES-ST-16; Stone architrave size 400mm wide (refer Drawing 306) (linear lighting by others) | mr | 29 | 268 | 7772 | 23.7% | 1842.2523 | 95% | 1750.1397
| H | Type RES-ST-16; Stone architrave size 400mm wide (refer Drawing 307) (linear lighting by others) | mr | 10 | 268 | 2680 | 23.7% | 635.2594 | 95% | 603.4964
Residential - Level 2 Lobby and Corridor
| J | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby (refer Drawing 310) | mr | 25 | 287 | 7175 | 23.7% | 1700.7412 | 95% | 1615.7041
| K | Type RES-ST-02; Stone architrave size 1450mm wide (refer Drawing 202) | mr | 8 | 1295 | 10360 | 23.7% | 2455.7043 | 95% | 2332.9191
| A | Type RES-ST-16; Stone architrave size 1800mm wide (refer Drawing 201) | mr | 16 | 1008 | 16128 | 23.7% | 3822.9343 | 95% | 3631.7876
Residential - Level 4 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 100% | 7175 | 95% | 6816.25
Residential - Level 23 Amenities, Corridor and Lift Lobby
| C | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 100% | 7175 | 95% | 6816.25
STONE VANITY
Supply and installation of stone vanity counter top with fascia and splash back, including all necessary supports, framing, backing, fittings, accessories, cut-out hole for basin, etc. and the like; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| D | Vanity counter with finish Type RES-ST-23; overall size 4300mm (L) x 600mm (W) x 290mm (H) to women's changing room (refer Drawings 310, 311 and 313) | No | 1 | 3697 | 3697 | 100% | 3697 | 95% | 3512.15
| E | Towel hamper with finish Type RES-ST-23; overall size 605mm (L) x 560mm (W) x 565mm (H) to women's changing room (refer Drawings 310, 311 and 313) | No | 1 | 908 | 908 | 100% | 908 | 95% | 862.6
| F | Vanity counter with finish Type RES-ST-23; overall size 3320mm (L) x 600mm (W) x 280mm (H) to men's changing room (refer Drawings 315, 316 and 318) | No | 1 | 2982 | 2982 | 100% | 2982 | 95% | 2832.9
| G | Vanity counter with finish Type RES-ST-23; overall size 640mm (L) x 360mm (W) x 850mm (H) to men's changing room (refer Drawing 319) | No | 1 | 2988 | 2988 | 100% | 2988 | 95% | 2838.6
Residential - Level 23 Amenities, Corridor and Lift Lobby
| A | Vanity with finish Type RES-ST-21; overall size 2700mm (L) x 460 / 480 mm (W) x 800 / 850 mm (H) to men's restroom (refer Drawing 355 to 357) | No | 1 | 2767 | 2767 | 100% | 2767 |  | 0
| A1 | Vanity basin with finish Type RES-ST-21; overall size 420mm (L) x 420mm (W) x 160 mm (H) to men's restroom | No | 2 | 2017 | 4034 | 100% | 4034 |  | 0
| A2 | Vanity cladding with finish Type RES-ST-21; overall size 1510mm (L) x 850 mm (H) to men's restroom | No | 2 | 966 | 1932 | 100% | 1932 |  | 0
| B | Vanity with finish Type RES-ST-21; overall size 2700mm (L) x 460 / 480 mm (W) x 800 / 850 mm (H) to women's restroom (refer Drawing 355 to 357) | No | 1 | 4733 | 4733 | 100% | 4733 |  | 0
| B1 | Vanity basin with finish Type RES-ST-21; overall size 420mm (L) x 420mm (W) x 160 mm (H) to women's restroom | No | 2 | 2017 | 4034 | 100% | 4034 |  | 0
| B2 | Vanity cladding with finish Type RES-ST-21; overall size 1510mm (L) x 850 mm (H) to women's restroom | No | 2 | 966 | 1932 | 100% | 1932 |  | 0
STONE LEDGE TOP
Supply and installation of stone ledge top at wc cistern including all necessary supports, framing, backing, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| C | Ledge top with finish Type RES-ST-23; overall size 1020mm (L) x 230mm (W) to men's changing room (refer Drawing 322) | No | 2 | 267 | 534 | 23.7% | 126.5778 | 95% | 120.2489
| D | Ledge top with finish Type RES-ST-23; overall size 1020mm (L) x 230mm (W) to women's changing room (refer Drawing 322) | No | 2 | 267 | 534 | 23.7% | 126.5778 | 95% | 120.2489
Residential - Level 23 Amenities, Corridor and Lift Lobby
| E | Ledge top with finish Type RES-ST-21; overall size 1270mm (L) x 230mm (W) to men's changing room (refer Drawing 354) | No | 2 | 299 | 598 | 100% | 598 | 90% | 538.2
| F | Ledge top with finish Type RES-ST-21; overall size 1270mm (L) x 230mm (W) to women's changing room (refer Drawing 354) | No | 2 | 299 | 598 | 100% | 598 | 90% | 538.2
STONE TOP
Supply and installation of stone top including all necessary supports, framing, backing, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| A | Stone top and cladding finish RES-ST-10 to concierge desk; overall size 3000mm (L) x 600mm (W) x 1100mm (H) (Drawing 302) | No | 1 | 5291 | 5291 | 100% | 5291 |  | 0
| B | Stone top to concierge station; overall size 1370mm (L) x 720mm (W) x 2215mm (H) (Drawing 303) | No | 1 | 884 | 884 | 100% | 884 |  | 0
Residential - Level 4 Amenities, Corridor and Lift Lobby
| C | Stone top with finish Type RES-ST-02; overall size 2205mm (L) x 505mm (W) to refreshment cabinet at fitness room (refer Drawing 326 and 327) (timber cabinet measured separately) | No | 1 | 1334 | 1334 | 100% | 1334 |  | 0
Residential - Level 23 Amenities, Corridor and Lift Lobby
| D | Stone top with finish Type RES-ST-07b to Meeting room cupboard; overall size 2670mm (L) x 580mm (W) (refer Drawing 349 to 351) | No | 2 | 4279 | 8558 | 100% | 8558 |  | 0
| D1 | Stone top with finish Type RES-ST-07b to Meeting room TV cupboard; overall size 1900mm (L) x 580mm (W) | No | 1 | 3125 | 3125 | 100% | 3125 |  | 0
| E | Stone top with finish Type RES-ST-07b to Multifunction room cupboard; overall size 2590mm (L) x 580mm (W) (refer Drawing 350 to 352) | No | 2 | 4151 | 8302 | 100% | 8302 |  | 0
| E1 | Stone top with finish Type RES-ST-07b to Multifunction room TV cupboard; overall size 1900mm (L) x 580mm (W) | No | 1 | 3125 | 3125 | 100% | 3125 |  | 0
STONE SHELF
Supply and installation of stone shelf including all necessary supports, framing, backing, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| A | Shelf with finish Type RES-ST-23; overall size 640mm (L) x 340mm (W) fixed to the wall at men's changing room (refer Drawing 319) | No | 1 | 5140 | 5140 | 100% | 5140 | 95% | 4883
| B | Shelf with finish Type RES-ST-23; overall size 600mm (L) x 530mm (W) fixed to the wall to women's changing room (refer Drawings 310, 311 and 313) | No | 1 | 479 | 479 | 100% | 479 | 95% | 455.05
STONE BENCH
Supply and installation of stone bench including all necessary supports, framing, backing, fixings, fittings, accessories, finishes, etc. and the like complete; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| C | Entrance bench with finish Type RES-ST-16; overall size 1965mm (L) x 340mm (W) x 450mm (H) fixed to the wall (refer Drawing 301) | No | 2 | 946 | 1892 | 100% | 1892 |  | 0
STONE WATER FEATURE
Supply and installation of stone water feature including all necessary supports, framing, backing, fixings, fittings, accessories, finishes, etc. and the like complete; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| D | Water feature with finish Type RES-ST-16; overall size 1550mm (D) x 500mm (H) to corridor (refer Drawing 308) | No | 1 | 4767 | 4767 | 100% | 4767 |  | 0
STONE WELCOME DESK
Supply and installation of stone welcome desk including all necessary supports, framing, backing, fixings, fittings, accessories, finishes, etc. and the like complete; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| A | Welcome desk with finish Type RES-ST-16; overall size 1300mm (L) x 500mm (W) x 1100mm (H) to corridor (refer Drawing 303 to 305) | No | 1 | 3918 | 3918 | 100% | 3918 |  | 0
| Add | LIFT CAR
LIFT CAR (4 NOS.)
| 1 | Type RES-ST-03; Stone border to lift car | m2 | 6 | 805 | 4830 | 100% | 4830 |  | 0
| 2 | Type RES-ST-03; Stone threshold 120mm wide | mr | 1 | 154 | 154 | 100% | 154 |  | 0
| 3 | Type RES-ST-03; Stone skirting 250mm high | mr | 7 | 458 | 3206 | 100% | 3206 |  | 0
| 4 | Type RES-ST-16; Stone wall | m2 | 41 | 542 | 22222 | 100% | 22222 |  | 0
| 5 | Type RES-ST-03; Stone lit cornice | m2 | 9 | 994 | 8946 | 100% | 8946 |  | 0
LIFT CAR (1 NO.)
| 1 | Type RES-ST-03; Stone border to lift car | m2 | 2 | 805 | 1610 | 23.7% | 381.6297 | 95% | 362.5482
| 2 | Type RES-ST-03; Stone threshold 120mm wide | mr | 1 | 154 | 154 | 23.7% | 36.5037 | 95% | 34.6785
| 3 | Type RES-ST-03; Stone skirting 250mm high | mr | 3 | 458 | 1374 | 23.7% | 325.689 | 95% | 309.4045
| 4 | Type RES-ST-16; Stone wall | m2 | 13 | 542 | 7046 | 23.7% | 1670.1634 | 95% | 1586.6552
| 5 | Type RES-ST-03; Stone lit cornice | m2 | 2 | 994 | 1988 | 23.7% | 471.2297 | 95% | 447.6683
|  | Total Amount in AED |  |  |  | 1280670 |  | 645852.8045 |  | 484432.7143
|  | Less Special Discount | -0.043469 |  |  | -55670 |  | -28074.8558 |  | -21058.0159 | -4.347%
|  | Total Amount in AED |  |  |  | 1225000 |  | 617777.9486 |  | 463374.6984
50.43%
317606
[8 empty] | 245000 |  | -145768.6984

## 7A and 15A (hidden)
| 7A and 15A | Dar Al Rokham
Level | Room | Floor | Wall | Architrave | Joinery | Total Progress | Remark
|  | 19.61% | 53.31% | 5.224% | 21.86% | 100%
7-8 | 7A | 100% | 100% |  |  | 72.91% | Wet area floor done
10-11 | 15A | 100% | 100% |  |  | 72.91%
13-14 | 7A | 100% | 100% |  |  | 72.91%
15-16 | 7A | 100% | 100% |  |  | 72.91%
20-21 | 7A |  |  |  |  | 0%
22-23 | 15A |  |  |  |  | 0%
24-25 | 7A | 100% | 100% |  |  | 72.91%
|  | Overall progress for 7A and 15A |  |  |  | 52.08%

## Weightage caluclation (hidden)
11A Guest Room
| Amount | Weightage
Floor | 307943.45 | 19.61%
Wall | 837223.6 | 53.31%
Architraves | 82042 | 5.224%
Joinery Works | 343380.35 | 21.86%
Total | 1570589.4 | 100%

## Vo Sum (hidden)
PROJECT | : Plot 18, Plot BB.B03.018, Business Bay, Dubai, UAE.
CLIENT | : Roberts - Pizzarotti JV
SITE NO | : 3140
PAYMENT APPLICATION NO. 5 |  |  |  | Payment Upto End Of | : April 2020
LIST OF VARATION ORDER APPLICATIONS
Vo.No: | Description | Amount Submitted | % Work Done | Amount Submitted | Remark
1 Rev 3 - Part A | Supply & installation of steel frame - lvl 8,9 & 10 DAR/3140/m/rj/0299 Dated 30 Jan 2020. | 124139.48 | 100% | 124139.48 | Approved
1 Rev 3 - Part B | Supply & installation of steel frame - lvl 11 to 16 DAR/3140/m/rj/0962 Dated 24 March 2020. | 462929.09 | 100% | 462929.0875 | Work Progress As Per The Attached List
2 | Supply & installation of stone works at guest room corridor. DAR/3140/m/rj/0516 Dated 17 Feb 2020. | 1876688 | 0% | 0
.
TOTAL AMOUNT |  |  | Dhs. | 587068.5675

## VO # 01 rev 3 part B (hidden)
PROJECT | : Dorchester Hotel at Business Bay - Dubai
Client | : Sky Palaces Real Estate Development LLC / Omniyat Properties Fifteen Limited
MAIN CONT. | : Roberts - Pizzarotti JV
SITE NO | : 3140
SUBJECT | : Supply & Installation Of Steel Frame Support - Lvl 11 To 16
VARIATION ORDER APPLICATION # 1 Rev 3 - Part B [ WORK PROGRESS ]
Sr. No: | Type | Item Description | Lvl 11 | Lvl 12 | Lvl 13 | Lvl 14 | Lvl 15 | Lvl 16 | Total No Of Room Work Completed | Unit | Rate | Amount (AED) | Notes
1 | TYPE -01A (6 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  |  |  | 1 | 1 |  | 2 | No | 2716.4 | 5432.8 |  | V - Type 1
2 | TYPE -01C (8 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 1 | 1 | 1 |  |  | 1 | 4 | No | 2716.4 | 10865.6 |  | V - Type 1
3 | TYPE -2A/2B/2C/2D (44 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | No | 2716.4 | 48895.2 |  | V - Type 1
4 | TYPE -2A/2B/2C/2D (44 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | No | 2700 | 48600
5 | TYPE -2E/2F/2G/2H (27 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 3 | 3 | 3 | 3 | 3 | 15 | No | 2716.4 | 40746 |  | V - Type 1
6 | TYPE -2E/2F/2G/2H (27 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 3 | 3 | 3 | 3 | 3 | 15 | No | 2700 | 40500
7 | TYPE -3A/3B/3D/3E/3G (39 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 2 | 3 | 3 | 3 | 3 | 3 | 17 | No | 4705.2 | 79988.4 |  | V - Type 2
8 | TYPE -03C/03F (18 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 4705.2 | 47052 |  | V - Type 2
9 | TYPE -04A/4B (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 1 | [5 empty] | 1 | No | 3716.4 | 3716.4 |  | V - Type 2
10 | TYPE -05A (9 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 3716.4 | 18582 |  | V - Type 2
11 | TYPE -08A (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 1 | [5 empty] | 1 | No | 3716.4 | 3716.4 |  | V - Type 2
12 | TYPE -08A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 1 | [5 empty] | 1 | No | 1041.6562 | 1041.6562 |  | V - Type 3
13 | TYPE -09A (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 1 |  |  |  |  | 1 | No | 3177.2 | 3177.2 |  | V - Type 1
14 | TYPE -09A (2 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 1 |  |  |  |  | 1 | No | 2700 | 2700
15 | TYPE -09A (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 1 |  |  |  |  | 1 | No | 1041.6562 | 1041.6562 |  | V - Type 3
16 | TYPE -09B (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 1 |  |  |  |  | 1 | No | 2927.6 | 2927.6 |  | V - Type 1
17 | TYPE -09B (2 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 1 |  |  |  |  | 1 | No | 2700 | 2700
18 | TYPE -09B (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 1 |  |  |  |  | 1 | No | 1041.6562 | 1041.6562 |  | V - Type 3
19 | TYPE -10A (5 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 2927.6 | 14638 |  | V - Type 1
20 | TYPE -10A (5 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 2700 | 13500
21 | TYPE -10A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 1041.6562 | 5208.2812 |  | V - Type 3
22 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 938.3438 | 9383.4375 |  | V - Type 3
23 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 575.25 | 5752.5 |  | V - Type 3
24 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 989.55 | 9895.5 |  | V - Type 3
25 | TYPE -11A/11B/11C/11D (19 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 2700 | 27000
26 | TYPE -16A (3 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 1 | [5 empty] | 1 | No | 2716.4 | 2716.4 |  | V - Type 1
27 | TYPE -16A (3 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 | 1 | [5 empty] | 1 | No | 2700 | 2700
28 | TYPE -19A (6 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A |  |  | 1 |  | 1 |  | 2 | No | 4705.2 | 9410.4 |  | V - Type 2
|  | TOTAL AMOUNT | [8 empty] | Aed. | 462929.0875
Notes : | * This Submittal is for Steel Frames Support Only - Cement board / Gypsum board are not under DAR scope of work.
* Limit of Scope is as indicated in "Notes" Column
* Back Wall for Bath Tub and V - Type 1 are assumed to be safely carry the load of of stone as advised by Wall Partion's Sub Contractor thru the Contractor.
* Walls to V - Type 3 are assumed to be safely carry the load of stone as advised by Wall Partion's Sub Contractor thru the Contractor.
* Rates / Amounts excludes VAT
* This variation is the extracted portion ( Lvl 11,12,13,14,15 & 16 ) of DAR variation 1 rev 3 ( Ref. DAR/3140/m/mh/0022, Dated 5th Jan 2020 )
Verify Basic Data