## DAR Summary
Dar Al Rokham
2022-12-01
SN | Description | Amount | Previous Work Done - WFA | New Subcontract Amount - WFA | Previous | This Month | Cumulative
1 | Total for Guest Room Works | 14192642.75 | 11495377 | 2697265.75 | 2018527.7337 | 155333.1369 | 2173860.8706 | 523404.8794
| Subtotal 1 | 14192642.75 | 11495377 | 2697265.75 | 2018527.7337 | 155333.1369 | 2173860.8706 | 79.28%
WFA VARIATIONS
2 | Omit PS Package | -698968 | -698968 | 0 | 0 | 0 | 0
3 | Omit Tilling to balconies | -461231 | -461231 | 0 | 0 | 0 | 0
4 | Metal Frames in Guest Rooms | 1084943 | 1084943 | 0 | 0 | 0 | 0
5 | Stonework to Room Type 7A & 15A | 746070 | 0 | 746070 | 401042.36 | 69696.2 | 470738.56
6 | Corridor Works stone works | 1644447.65 | 835600 | 808847.65 | 695104.682 | 31176.275 | 726280.957
7 | Discount | -7905 | 0 | -7905 | -5572.6696 | -512.8226 | -6085.4922
| Subtotal 2 | 2307356.65 | 760344 | 1547012.65 | 1090574.3724 | 100359.6524 | 1190934.0248
VARIATIONS UNDER KCE
8 | AHK Balance Works - Resi Amenities |  |  | 617777 | 322803.6838 | 62060.3249 | 384864.0086
9 | Marble Floor at Corridor - GF |  |  | 5502.33 | 5502.33 | 0 | 5502.33
| Subtotal 2 |  |  | 623279.33 | 328306.0138 | 62060.3249 | 390366.3386
10 | MOS @ 75% |  | 132458 | -132458 | -97030.7336 | -7979.8148 | -105010.5484
| Subtotal 3 | 0 | 132458 | -132458 | -97030.7336 | -7979.8148 | -105010.5484
| TOTAL | 16499999.4 | 12388179 | 4111820.4 | 3340377.3863 | 309773.2994 | 3650150.6857

## Guest Room Summary
Dar Al Rakhom Guest Room Work Done Assessment
[12 empty] | Payment Upto End Of | 2022-12-01
Bill No. | Item No. | Description | Quantity | Unit | Unit Rate | Amount | Work Progress (%) |  |  | Total Amount |  |  | Note
[7 empty] | Previous | Current | Cummulative | Previous | Current | Cummulative
| 1 | PACKAGE 7 - STONE WORKS
Bill Of Quantities No. 01
01 |  | Unit Type 1A | 6 | Nos. | 42584.7 | 255508.2 | 97% | 2.089% | 99.09% | 247838.5217 | 5338.7621 | 253177.2839
Bill Of Quantities No. 02
02 |  | Unit Type 1B / 1C | 8 | Nos. | 42666.9 | 341335.2 | 99.58% | 0% | 99.58% | 339890.4865 | 0 | 339890.4865
Bill Of Quantities No. 03
03 |  | Unit Type 2A/2B/2C/2D (Mock-Up) | 44 | Nos. | 50610.4 | 2226857.6 | 98.44% | 0.8839% | 99.32% | 2192018.3914 | 19682.1398 | 2211700.5312
Bill Of Quantities No. 04
04 |  | Unit Type 2E/2F/2G/2H | 27 | Nos. | 52529.2 | 1418288.4 | 97.31% | 2.359% | 99.67% | 1380202.7598 | 33459.2257 | 1413661.9855
Bill Of Quantities No. 05
05 |  | Unit Type 3A/3B/3D/3E/3G (Mock-Up) | 39 | Nos. | 55461.9 | 2163014.1 | 96.06% | 2.843% | 98.9% | 2077822.7144 | 61490.6977 | 2139313.4122
Bill Of Quantities No. 06
06 |  | Unit Type 3C/3F | 18 | Nos. | 54801.72 | 986430.96 | 94.07% | 4.51% | 98.58% | 927896.0995 | 44485.0735 | 972381.1731
Bill Of Quantities No. 07
07 |  | Unit Type 4A/4B | 5 | Nos. | 57500.75 | 287503.75 | 98.52% | 0% | 98.52% | 283240.4702 | 0 | 283240.4702
Bill Of Quantities No. 08
08 |  | Unit Type 5A | 9 | Nos. | 60409.1 | 543681.9 | 90.39% | 8.625% | 99.01% | 491419.352 | 46890.8899 | 538310.2419
Bill Of Quantities No. 09
09 |  | Unit Type 6A | 5 | Nos. | 56443.1 | 282215.5 | 94.51% | 3.338% | 97.85% | 266730.8058 | 9419.1597 | 276149.9655
Bill Of Quantities No. 10
10 |  | Unit Type 8A | 5 | Nos. | 89984.3 | 449921.5 | 99.84% | 0% | 99.84% | 449184.3494 | 0 | 449184.3494
Bill Of Quantities No. 11
11 |  | Unit Type 9A | 2 | Nos. | 73372.75 | 146745.5 | 100% | 0% | 100% | 146745.5 | 0 | 146745.5
Bill Of Quantities No. 12
12 |  | Unit Type 9B | 2 | Nos. | 72328.85 | 144657.7 | 100% | 0% | 100% | 144657.7 | 0 | 144657.7
Bill Of Quantities No. 13
13 |  | Unit Type 10A | 5 | Nos. | 78477.69 | 392388.45 | 100% | 0% | 100% | 392388.45 | 0 | 392388.45
Bill Of Quantities No. 14
14 |  | Unit Type 10B | 3 | Nos. | 80238.59 | 240715.77 | 90.02% | 9.222% | 99.24% | 216688.0846 | 22198.5706 | 238884.4952
Bill Of Quantities No. 15
15 |  | Unit Type 11A/11B/11C/11D | 19 | Nos. | 82662.6 | 1570589.4 | 80.59% | 1.713% | 82.31% | 1265813.7274 | 26905.0319 | 1292718.7592
Bill Of Quantities No. 16
16 |  | Unit Type 12A | 5 | Nos. | 96149 | 480745 | 98.47% | 0.2289% | 98.7% | 473379.9954 | 1100.3534 | 474480.3488
Bill Of Quantities No. 17
17 |  | Unit Type 13A | 1 | Nos. | 77622.56 | 77622.56 | 97.72% | 1.245% | 98.96% | 75849.4923 | 966.1044 | 76815.5967
Bill Of Quantities No. 18
18 |  | Unit Type 14A | 4 | Nos. | 87188.85 | 348755.4 | 95.79% | 2.834% | 98.63% | 334087.8236 | 9885.3374 | 343973.1611
Bill Of Quantities No. 19
19 |  | Unit Type 16A | 3 | Nos. | 54490.71 | 163472.13 | 89.1% | 6.332% | 95.44% | 145660.0446 | 10351.0272 | 156011.0718
Bill Of Quantities No. 20
20 |  | Unit Type 19A | 6 | Nos. | 60833.9 | 365003.4 | 88.79% | 2.083% | 90.87% | 324073.0307 | 7603.9931 | 331677.0238
Bill Of Quantities No. 21
21 |  | Balconies | 1 | Nos. |  | Included
Bill Of Quantities No. 22
22 |  | Stone Works With Provisional Sum
| A | Add Provisional Sum for remaining 9no. guestrooms |  |  |  | 698968 | 100% | 0% | 100% | 698968 | 0 | 698968
Preliminaries
|  | Including financial cost, shop drawings, site administration, stone sample test, health and safety. | 1 |  | L.S.
|  | Preliminaries (Mobilization -10%) |  |  |  | 85000 | 100% | 0% | 100% | 85000 | 0 | 85000
|  | Preliminaries (Time related - 30%) |  |  |  | 255000 | 100% | 0% | 100% | 255000 | 0 | 255000
|  | Preliminaries (Progress Related - 60%) |  |  |  | 510000 | 94.49% | 2.326% | 96.82% | 481903.8148 | 11865.0042 | 493768.8189
|  | 2% Attick Stock / Spares | 1 |  | L.S. | 108222.33 | 0% | 0% | 0% | 0 | 0 | 0
|  | Special Discount |  |  |  | -350000 | 94.49% | 2.326% | 96.82% | -330718.3042 | -8142.6499 | -338860.9542
|  | Total Amount Works (A) |  |  |  | 14192642.75 |  |  |  | 13365739.1499 | 303498.7207 | 13669237.8706
|  | Metal Frame Variation as per the ASI Rates |  |  |  | 1084943 | 100% |  | 100% | 1084943 | 0 | 1084943
|  | Total Amount Variation (B) | [7 empty] | 1084943 | 0 | 1084943
|  | TOTAL AMOUNT FOR GUEST ROOM WORKS | [7 empty] | 14450682.1499 | 303498.7207 | 14754180.8706
-2.16

## KCE VO Schedule
PROJECT: DORCHESTER HOTEL AND RESIDENCES
VARIATION SHEDULE - M/S DAR AL ROKHAM | [10 empty] | 2023-02-10
Item No. | WA Ref. | Description of Variation | SUBMITTED (AED) |  | KCE INITIAL ASSESSEMENT | STATUS | KCE ASSESSED |  | Difference | Action By | Remarks | Previous |  | This Month |  | Cumulative
|  |  |  | TOTAL AMOUNT (AED) |  |  | ASSESSED (AED) | AGREED (AED) |  |  |  | % | Amount | % | Amount | % | Amount
Main Contract VO's
1 | PS045 | Supply & Install Marble to Lift Lobbies at Hotel L7-L27 | 58140 | 58140 | 58140 |  | 58140 |  | PS046 | Supply & Install Marble to Lift Lobbies at Hotel L7-L28
2 | PS045 R1 | Supply & Fixing of Pink Onyx at Hotel L2 Entrance | 757050 | 757050 | 757050 |  | 757050 |  | PS045 R2 | Supply & Fixing of Pink Onyx at Hotel L2 Entrance | Competitive price in comparison with Reem.
3 | PS042 | Stone Works - AHK Balance Work | 617777.4 | 617777.4 |  |  | 617777.4 | 617777.4 | PS043 | Stone Works - AHK Balance Work | Lump sum and based on Original Scope with AHK | 42.45% | 262256.0049 | 19.85% | 122608.0038 | 62.3% | 384864.0086
|  | Total Variation Amount ( AED ) | 1432967.4 | 1432967.4 | 815190 | 0 | 1432967.4 | 617777.4

## Corridor
BILL OF QUANTITIES - Guestroom Corridor & Lift Lobby - Dar Al Rokham
Bill No. | Item No. | Description | Unit | Quantity | Material | Thick | Supply Rate | Fixing Rate | Unit Rate | Amount | Progress | Previous | This Month | Progress Amount
| A | HOTEL GUESTROOM CORRIDOR & LIFT LOBBY
Wall Finishes
Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche etc and the like all in accordance with drawings and specifications.
| 1 | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] at door frame at guest corridor, Lvl 7 to Lvl 27 | m2 | 766 |  |  | - | - | - | Deleted-as discussed in meeting
| 2 | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] at lift lobby, guest corridor, Lvl 7 to Lvl 27 | m2 | 302.35 | Volakas | 20 | 422 | 327 | 749 | 226460.15 | 94% | 212395.7828 | 476.7582 | 212872.541 | 0.93789
| 2A | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] show case overall size 3.4 x 2.5 m at guest corridor, Lvl 7 to Lvl 27 [ Inc. metal framing] | M2 | 153 | Volakas | 20 | 422 | 731 | 1153 | 176409 | 94% | 165453.0726 | 371.3874 | 165824.46 | 0.93789
| 2.A. 1 | Extra Over for Supply and Fix of Steel Frame for projected 2 Sides cladding. Q'ty = 18 levels x 2 sides = 36 No ( lvl 19 excluded) | Set | 36 | Steel frame | [7 empty] | 0
| 3 | Supply and installation of 20mm thk, projected stone cladding ST-06 [ Volakas Marble ] at guest corridor, Lvl 7 to Lvl 27 [ Inc. metal framing] | m2 | 612 | Volakas | 20 | 422 | 731 | 1153 | 705636 | 99.1% | 698951.0274 | 334.2486 | 699285.276 | 0.99053
| 3.a | Extra Over for Supply and Fix of Steel Frame | Set | 417 | Steel frame | [7 empty] | 0
| 4 | Supply and installation of 20mm thk, stone cladding ST-06 [ Volakas Marble ] at fire door at lift lobby, guest corridor, Lvl 7 to Lvl 27 | m2 | 153 | Volakas | 20 | - | - | - | Omitted From DAR Scope |  |  | 0
| 5 | Supply and installation of ST-06 [ Volakas Marble ] marble cladding to the fire door, Size .998+.998 x 2.4m at lift lobby, guest corridor.Lvl 7 to Lvl 27 | No | 19 | Volakas | 20 | - | - | - | Cancelled |  |  | 0
| 6 | 85mm wide x 5mm thick Brass strip insert in brushed finish with top layer brass coat (HTL-ME-01) | mr | 2210.1 | Brass | 5 | - | - | - | NIC-By Others |  |  | 0
| 7 | Supply and installation of architrave ST-03 [ Arbsecato Marble ], size 185+40+110 x 20mm at lift cabin, guest corridor | mr | 38 | Arabescato | 20 | - | - | - | Under Main Lobby Tender |  |  | 0
| 8 | Supply and installation of soffit ST-06 [ Volakas Marble ], size 150 x 20mm at guest corridor, Lvl 7 to Lvl 27 | mr | 240.6 | Volakas | 20 | 121 | 40 | 161 | Metal Soffit By Other |  |  | 0
| 9 | Supply and installation of soffit ST-06 [ Volakas Marble ], size 190 x 20mm at lift lobby, guest corridor, Lvl 7 to Lvl 27 | mr | 126 | Volakas | 20 | 126 | 51 | 177 | 22302 | 94% | 20943.3387 | 20.5413 | 20963.88 | 0.93908
| 10 | Supply and installation of architrave ST-06 [ Volakas Marble ], size 236+30+236 x 20mm at fire door at lift lobby, guest corridor, Lvl 7 to Lvl 27 | mr | - | Volakas | 20 | - | - | - | Omitted From DAR Scope
Floor Finishes
Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications.
| 11 | Supply and installation of 20mm thk, stone flooring, ST-06 [ Volakas Marble ] at lift lobby, guest corridor, Lvl 7 to Lvl 27 | m2 | 105.65 | Volakas | 20 | 415 | 215 | 630 | 66559.5 | 100% | 66559.5 | 0 | 66559.5 | 1
| 12 | 7mm wide x 5mm thick Brass strip insert in brushed finish with top layer brass coat (HTL-ME-04) | mr | 357 | Brass | 5 | 0 | 60 | 60 | 21420 | 62% | 13077.4737 | 202.9263 | 13280.4 | 0.61053
| 13 | Supply and installation of 20mm thk, stone flooring, ST-04 [ Griggio Carnico Marble ] and Border, ST-03 [ Arbsecato Marble ], Size 1.80x1.60m at lift cabin, guest corridor | No | 6 | Grigio Carnico, Arabescato | 20 | - | - | - | Under Main Lobby Tender
Skirting
Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing,
polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications.
| 14 | Supply and installation of skirting ST-06 [ Volakas Marble ], size 150+55 x 20mm at guest corridor, Lvl 7 to Lvl 27 [ Back support considered ] | mr | 1681.9 | Volakas | 20 | 130 | 100 | 230 | 386837 | 90% | 330847.4342 | 17305.8658 | 348153.3 | 0.85526
| 15 | Supply and installation of skirting ST-06 [ Volakas Marble ], size 150+55 x 20mm at lift lobby, guest corridor, Lvl 7 to Lvl 27 [ Back support considered ] | mr | 168.8 | Volakas | 20 | 130 | 100 | 230 | 38824 | 90% | 22477.0526 | 12464.5474 | 34941.6 | 0.57895
| 16 | Supply and installation of skirting ST-03 [ Arbsecato Marble ], size 150+105 x 20mm at lift cabin, guest corridor [ Back support considered ] | mr | 29 | Arabescato | 20 | - | - | - | Under Main Lobby Tender
Threshold
Supply and fixing of Stone Threshold, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications.
| 17 | Supply and installation of threshold ST-06 [ Volakas Marble ], size 75 x 20mm at guest corridor, Lvl 7 to Lvl 27 | mr | 349.5 | Volakas | 20 | 63 | 28 | 91 | Unit rate Only
|  | Total Amount in AED | [7 empty] | 1644447.65 | 94.98% | 1530704.682 | 31176.275 | 1561880.957
1644447.65

## Guest Rooms
[18 empty] | Payment Upto End Of |  | 44896
BILL OF QUANTITIES
Bill No. | Item No. | Description | Qty / Room | Unit | No Of Rooms | Material | Thick | Supply Rate | Fixing Rate | Unit Rate | Amount | Amount | This month Qty | Previous | Current | Cummulative | Total Amount |  |  | Note
[17 empty] | Previous | Current | Cummulative
| 1 | PACKAGE 7 - STONE WORKS
Floor Finishes
Stone flooring fixed with approved tile adhesive and
bedding in cement mortar cutting and cleaning, etc.,
complete as per drawings and specification (Screed
measured separately)
DELUXE ROOM
01 |  | TYPE -01A (8 No's)
Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works
FLOOR FINISHES
Foyer
01 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.4 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1760 | 10560 | 0 | 100% | 0% | 100% | 10560 | 0 | 10560
[13 empty] | 0 |  | 0%
01 | B | 20mm thick polished Crystal White, maximum 145mm width border. | 1.9 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 927.2 | 5563.2 | 0 | 100% | 0% | 100% | 5563.2 | 0 | 5563.2
[13 empty] | 0 |  | 0%
01 | C | 7 x 5mm Brass strip insert in brushed finish . | 10.25 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 584.25 | 3505.5 |  | 75% | 25% | 100% | 2629.125 | 876.375 | 3505.5
[13 empty] | 0 |  | 0%
01 | D | 215mm wide x 900mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 97 | 35 | 132 | 132 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.9 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1960 | 11760 | 0 | 100% | 0% | 100% | 11760 | 0 | 11760
[13 empty] | 0 |  | 0%
01 | F | 20mm thick polished Crystal White, cut to size. | 1.8 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 878.4 | 5270.4 | 0 | 100% | 0% | 100% | 5270.4 | 0 | 5270.4
[13 empty] | 0 |  | 0%
01 | G | 20mm thick polished Crystal White, average of 125mm width border. | 2.8 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1366.4 | 8198.4 | 0 | 100% | 0% | 100% | 8198.4 | 0 | 8198.4
[13 empty] | 0 |  | 0%
01 | H | 7 x 5mm Brass strip insert in brushed finish . | 17 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 969 | 5814 |  | 75% | 25% | 100% | 4360.5 | 1453.5 | 5814
[13 empty] | 0 |  | 0%
01 | J | 7 x 5mm Brass strip insert in brushed finish . | 14.35 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 817.95 | 4907.7 |  | 75% | 25% | 100% | 3680.775 | 1226.925 | 4907.7
[13 empty] | 0 |  | 0%
01 | K | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 6 | Crystal White | 20 | 155 | 62 | 217 | 217 | 1302 | 0 | 100% | 0% | 100% | 1302 | 0 | 1302
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.1 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1240 | 7440 | 0 | 100% | 0% | 100% | 7440 | 0 | 7440
[13 empty] | 0 |  | 0%
01 | M | 20mm thick polished Crystal White, average 143mm width border. | 1.3 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 634.4 | 3806.4 | 0 | 100% | 0% | 100% | 3806.4 | 0 | 3806.4
[13 empty] | 0 |  | 0%
01 | N | 7 x 5mm Brass strip insert in brushed finish . | 7.8 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 444.6 | 2667.6 |  | 75% | 25% | 100% | 2000.7 | 666.9 | 2667.6
[13 empty] | 0 |  | 0%
01 | P | Threshold (20mm thick); 220mm wide x 945mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 105 | 39 | 144 | 144 | 864 | 0 | 100% | 0% | 100% | 864 | 0 | 864
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.5 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1000 | 6000 | 0 | 100% | 0% | 100% | 6000 | 0 | 6000
[13 empty] | 0 |  | 0%
01 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.9 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 360 | 2160 | 0 | 100% | 0% | 100% | 2160 | 0 | 2160
[13 empty] | 0 |  | 0%
01 | E | 20mm thick polished Crystal White, average of 101mm width border. | 0.55 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1610.4 | 0 | 100% | 0% | 100% | 1610.4 | 0 | 1610.4
[13 empty] | 0 |  | 0%
01 | F | 7 x 5mm Brass strip insert in brushed finish . | 4 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 228 | 1368 |  | 75% | 25% | 100% | 1026 | 342 | 1368
[13 empty] | 0 |  | 0%
01 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 7 | M2 | 6 | PC Rate | 20 | 50 | 100 | 150 | 1050 | 6300 | 0 | 100% | 0% | 100% | 6300 | 0 | 6300
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.2 | Lm | 6 | Crystal White | 20 | 86 | 48 | 134 | 428.8 | 2572.8 | 0 | 100% | 0% | 100% | 2572.8 | 0 | 2572.8
[13 empty] | 0 |  | 0%
01 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 6.5 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 4082 | 24492 | 0 | 100% | 0% | 100% | 24492 | 0 | 24492
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | K | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.75 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 9263 | 55578 | 0 | 100% | 0% | 100% | 55578 | 0 | 55578
[13 empty] | 0 |  | 0%
01 | L | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.5 | Lm | 6 | Crystal White | 20 | 79 | 43 | 122 | 793 | 4758 | 0 | 100% | 0% | 100% | 4758 | 0 | 4758
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | M | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 4.5 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 2826 | 16956 | 0 | 100% | 0% | 100% | 16956 | 0 | 16956
[13 empty] | 0 |  | 0%
01 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.15 | Lm | 6 | Crystal White | 20 | 79 | 43 | 122 | 506.3 | 3037.8 | 0 | 100% | 0% | 100% | 3037.8 | 0 | 3037.8
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | B | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 7332 | 0 | 87.5% | 0% | 87.5% | 6415.5 | 0 | 6415.5
[13 empty] | 0 |  | 0%
01 | C | Bathroom : 220mm wide; total size of 945 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 644 | 291 | 935 | 935 | 5610 | 0 | 87.5% | 0% | 87.5% | 4908.75 | 0 | 4908.75
[13 empty] | 0 |  | 0%
01 | D | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 6 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 11568 | 0 | 100% | 0% | 100% | 11568 | 0 | 11568
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | E | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 700 x 1430mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 457 | 255 | 712 | 712 | 4272 | 0.79365 | 75% | 12.5% | 87.5% | 3204 | 534 | 3738
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | F | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 12474 | 0 | 100% | 0% | 100% | 12474 | 0 | 12474
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | G | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 570 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 574 | 281 | 855 | 855 | 5130 | 0 | 100% | 0% | 100% | 5130 | 0 | 5130
[13 empty] | 0 |  | 0%
01 | H | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 985mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 240 | 100 | 340 | 340 | 2040 | 0 | 100% | 0% | 100% | 2040 | 0 | 2040
[13 empty] | 0 |  | 0%
01 | J | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 6 | Volakas | 20 | 44 | 12 | 56 | 112 | 672 | 0 | 100% | 0% | 100% | 672 | 0 | 672
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 | A | Cistern Top : Supply and installation of 20mm thick polished Volakas, 260mm W x 900mm length, pencil edge finish. | 1 | No | 6 | Volakas | 20 | 109 | 55 | 164 | 164 | 984 | 0 | 100% | 0% | 100% | 984 | 0 | 984
[13 empty] | 0 |  | 0%
01 | B | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 2 | No | 6 | Volakas | 20 | 25 | 5 | 30 | 60 | 360 | 0 | 100% | 0% | 100% | 360 | 0 | 360
[13 empty] | 0 |  | 0%
01 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 118 | 59 | 177 | 177 | 1062 | 0.75 | 75% | 12.5% | 87.5% | 796.5 | 132.75 | 929.25
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
01 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 74 | M2 | 6 |  |  | 0 | 8 | 8 | 592 | 3552 |  | 97% | 2.089% | 99.09% | 3445.3784 | 74.2179 | 3519.5963
[13 empty] | 0 |  | 0%
01 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 32 | M2 | 6 |  |  | 0 | 8 | 8 | 256 | 1536 |  | 97% | 2.089% | 99.09% | 1489.8934 | 32.0942 | 1521.9876
[13 empty] | 0 |  | 0%
01 |  | Total Amount for TYPE -01A | [10 empty] | 0 |  | 0% |  | 247838.5217 | 5338.7621 | 253177.2839
[13 empty] | 0 |  | 0%
02 |  | TYPE -01B & 01C (6 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.4 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1760 | 14080 | 0 | 100% | 0% | 100% | 14080 | 0 | 14080
[13 empty] | 0 |  | 0%
02 | B | 20mm thick polished Crystal White, maximum 130mm width border. | 1.9 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 927.2 | 7417.6 | 0 | 100% | 0% | 100% | 7417.6 | 0 | 7417.6
[13 empty] | 0 |  | 0%
02 | C | 7 x 5mm Brass strip insert in brushed finish . | 10.25 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 584.25 | 4674 |  | 100% | 0% | 100% | 4674 | 0 | 4674
[13 empty] | 0 |  | 0%
02 | Add | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 8 | Crystal White | 20 | 123 | 48 | 171 | 171 | 1368 | 0 | 100% | 0% | 100% | 1368 | 0 | 1368
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.9 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1960 | 15680 | 0 | 100% | 0% | 100% | 15680 | 0 | 15680
[13 empty] | 0 |  | 0%
02 | E | 20mm thick polished Crystal White, average of 157mm width border. | 2.8 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 1366.4 | 10931.2 | 0 | 100% | 0% | 100% | 10931.2 | 0 | 10931.2
[13 empty] | 0 |  | 0%
02 | F | 7 x 5mm Brass strip insert in brushed finish . | 17 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 969 | 7752 |  | 100% | 0% | 100% | 7752 | 0 | 7752
[13 empty] | 0 |  | 0%
02 | G | 7 x 5mm Brass strip insert in brushed finish . | 14.35 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 817.95 | 6543.6 |  | 100% | 0% | 100% | 6543.6 | 0 | 6543.6
[13 empty] | 0 |  | 0%
02 | H | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 8 | Crystal White | 20 | 155 | 62 | 217 | 217 | 1736 | 0 | 100% | 0% | 100% | 1736 | 0 | 1736
[13 empty] | 0 |  | 0%
02 | Add | 20mm thick polished CrystalWhite, cut to size (HTL-ST-01) | 1.8 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 878.4 | 7027.2 | 0 | 100% | 0% | 100% | 7027.2 | 0 | 7027.2
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.1 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1240 | 9920 | 0 | 100% | 0% | 100% | 9920 | 0 | 9920
[13 empty] | 0 |  | 0%
02 | K | 20mm thick polished Crystal White, average 149mm width border. | 1.45 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 707.6 | 5660.8 | 0 | 100% | 0% | 100% | 5660.8 | 0 | 5660.8
[13 empty] | 0 |  | 0%
02 | L | 7 x 5mm Brass strip insert in brushed finish . | 7.8 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 444.6 | 3556.8 |  | 100% | 0% | 100% | 3556.8 | 0 | 3556.8
[13 empty] | 0 |  | 0%
02 | M | Threshold (20mm thick); 220mm wide x 945mm length polished Crystal White. | 1 | No | 8 | Crystal White | 20 | 105 | 39 | 144 | 144 | 1152 | 0 | 100% | 0% | 100% | 1152 | 0 | 1152
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | N | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.5 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 1000 | 8000 | 0 | 100% | 0% | 100% | 8000 | 0 | 8000
[13 empty] | 0 |  | 0%
02 | Q | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 8 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1088 | 0 | 100% | 0% | 100% | 1088 | 0 | 1088
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.9 | M2 | 8 | Beige Travertine | 20 | 255 | 145 | 400 | 360 | 2880 | 0 | 100% | 0% | 100% | 2880 | 0 | 2880
[13 empty] | 0 |  | 0%
02 | B | 20mm thick polished Crystal White, average of 109mm width border. | 0.55 | M2 | 8 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 2147.2 | 0 | 100% | 0% | 100% | 2147.2 | 0 | 2147.2
[13 empty] | 0 |  | 0%
02 | C | 7 x 5mm Brass strip insert in brushed finish . | 4 | Lm | 8 | Brass | 5 | 0 | 57 | 57 | 228 | 1824 |  | 100% | 0% | 100% | 1824 | 0 | 1824
[13 empty] | 0 |  | 0%
02 | D | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 8 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1088 | 0 | 100% | 0% | 100% | 1088 | 0 | 1088
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 |  | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 7 | M2 | 8 | PC Rate | 20 | 50 | 100 | 150 | 1050 | 8400 | 0 | 100% | 0% | 100% | 8400 | 0 | 8400
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.2 | Lm | 8 | Crystal White | 20 | 86 | 48 | 134 | 428.8 | 3430.4 | 0 | 100% | 0% | 100% | 3430.4 | 0 | 3430.4
[13 empty] | 0 |  | 0%
02 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 6.5 | M2 | 8 | Volakas | 20 | 406 | 222 | 628 | 4082 | 32656 | 0 | 100% | 0% | 100% | 32656 | 0 | 32656
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | F | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.75 | M2 | 8 | Volakas | 20 | 406 | 222 | 628 | 9263 | 74104 | 0 | 100% | 0% | 100% | 74104 | 0 | 74104
[13 empty] | 0 |  | 0%
02 | G | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.5 | Lm | 8 | Crystal White | 20 | 79 | 43 | 122 | 793 | 6344 | 0 | 100% | 0% | 100% | 6344 | 0 | 6344
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | H | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 4.5 | M2 | 8 | Volakas | 20 | 406 | 222 | 628 | 2826 | 22608 | 0 | 100% | 0% | 100% | 22608 | 0 | 22608
[13 empty] | 0 |  | 0%
02 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.15 | Lm | 8 | Crystal White | 20 | 79 | 43 | 122 | 506.3 | 4050.4 | 0 | 100% | 0% | 100% | 4050.4 | 0 | 4050.4
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | A | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 8 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 9776 | 0 | 100% | 0% | 100% | 9776 | 0 | 9776
[13 empty] | 0 |  | 0%
02 | B | Bathroom : 220mm wide; total size of 945 x 2430mm high. | 1 | No | 8 | Crystal White | 20 | 644 | 291 | 935 | 935 | 7480 | 0 | 100% | 0% | 100% | 7480 | 0 | 7480
[13 empty] | 0 |  | 0%
02 | C | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 8 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 15424 | 0 | 100% | 0% | 100% | 15424 | 0 | 15424
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | D | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 700 x 1430mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 8 | Crystal White | 20 | 457 | 255 | 712 | 712 | 5696 | 0 | 100% | 0% | 100% | 5696 | 0 | 5696
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | E | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 8 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 16632 | 0 | 100% | 0% | 100% | 16632 | 0 | 16632
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 570 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 8 | Volakas | 20 | 574 | 281 | 855 | 855 | 6840 | 0 | 100% | 0% | 100% | 6840 | 0 | 6840
[13 empty] | 0 |  | 0%
02 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 985mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 8 | Volakas | 20 | 240 | 100 | 340 | 340 | 2720 | 0 | 100% | 0% | 100% | 2720 | 0 | 2720
[13 empty] | 0 |  | 0%
02 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 8 | Volakas | 20 | 44 | 12 | 56 | 112 | 896 | 0 | 100% | 0% | 100% | 896 | 0 | 896
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 | J | Cistern Top : Supply and installation of 20mm thick polished Volakas, 260mm W x 900mm length, pencil edge finish. | 1 | No | 8 | Volakas | 20 | 109 | 55 | 164 | 164 | 1312 | 0 | 100% | 0% | 100% | 1312 | 0 | 1312
[13 empty] | 0 |  | 0%
02 | K | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 8 | Volakas | 20 | 25 | 5 | 30 | 30 | 240 | 0 | 100% | 0% | 100% | 240 | 0 | 240
[13 empty] | 0 |  | 0%
02 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 8 | Crystal White | 20 | 118 | 59 | 177 | 177 | 1416 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
02 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 74 | M2 | 8 |  |  | 0 | 8 | 8 | 592 | 4736 |  | 99.58% | 0% | 99.58% | 4715.9547 | 0 | 4715.9547
[13 empty] | 0 |  | 0%
02 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 32 | M2 | 8 |  |  | 0 | 8 | 8 | 256 | 2048 |  | 99.58% | 0% | 99.58% | 2039.3318 | 0 | 2039.3318
[13 empty] | 0 |  | 0%
02 |  | Total Amount for TYPE -01C | [10 empty] | 0 |  | 0% |  | 339890.4865 | 0 | 339890.4865
[13 empty] | 0 |  | 0%
03 |  | TYPE -2A/2B/2C/2D (44 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 7.2 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 2880 | 126720 | 0 | 100% | 0% | 100% | 126720 | 0 | 126720
[13 empty] | 0 |  | 0%
03 | B | 20mm thick polished Crystal White, maximum 160mm width border. | 2.05 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 1000.4 | 44017.6 | 0 | 100% | 0% | 100% | 44017.6 | 0 | 44017.6
[13 empty] | 0 |  | 0%
03 | C | Extra-over to 7 x 5mm brass strips. | 11.6 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 661.2 | 29092.8 |  | 97.73% | 0% | 97.73% | 27770.4 | 661.2 | 28431.6
[13 empty] | 0 |  | 0%
03 | D | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 44 | Crystal White | 20 | 123 | 48 | 171 | 171 | 7524 | 0 | 100% | 0% | 100% | 7524 | 0 | 7524
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.45 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 2180 | 95920 | 0 | 100% | 0% | 100% | 95920 | 0 | 95920
[13 empty] | 0 |  | 0%
03 | F | 20mm thick polished Crystal White, cut to size. | 2.2 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 1073.6 | 47238.4 | 0 | 100% | 0% | 100% | 47238.4 | 0 | 47238.4
[13 empty] | 0 |  | 0%
03 | G | 20mm thick polished Crystal White, average of 155mm width border. | 3.3 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 1610.4 | 70857.6 | 0 | 100% | 0% | 100% | 70857.6 | 0 | 70857.6
[13 empty] | 0 |  | 0%
03 | H | Extra-over to 7 x 5mm brass strips. | 20.1 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 1145.7 | 50410.8 |  | 97.73% | 0% | 97.73% | 46973.7 | 2291.4 | 49265.1
[13 empty] | 0 |  | 0%
03 | J | Extra-over to 7 x 5mm brass strips. | 17.6 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 1003.2 | 44140.8 |  | 97.73% | 0% | 97.73% | 41131.2 | 2006.4 | 43137.6
[13 empty] | 0 |  | 0%
03 | K | Threshold (20mm thick polished Crystal White); 310mm wide x 1115mm length. | 1.1 | Lm | 44 | Crystal White | 20 | 158 | 64 | 222 | 244.2 | 10744.8 | 0 | 100% | 0% | 100% | 10744.8 | 0 | 10744.8
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.7 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 1880 | 82720 | 0 | 100% | 0% | 100% | 82720 | 0 | 82720
[13 empty] | 0 |  | 0%
03 | M | 20mm thick polished Crystal White, average 140mm width border. | 1.55 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 756.4 | 33281.6 | 0 | 100% | 0% | 100% | 33281.6 | 0 | 33281.6
[13 empty] | 0 |  | 0%
03 | N | Extra-over to 7 x 5mm brass strips. | 9.7 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 552.9 | 24327.6 |  | 97.73% | 0% | 97.73% | 22668.9 | 1105.8 | 23774.7
[13 empty] | 0 |  | 0%
03 |  | Threshold (20mm thick); 300mm wide x 945mm length polished Crystal White | 1 | Lm | 44 | Crystal White | 20 | 132 | 53 | 185 | 185 | 8140 | 0 | 100% | 0% | 100% | 8140 | 0 | 8140
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.2 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 38720 | 0 | 100% | 0% | 100% | 38720 | 0 | 38720
[13 empty] | 0 |  | 0%
03 | C | Threshold (20mm thick); 235mm wide x 830mm length and 40mm high fascia, polished Crystal White | 1 | No | 44 | Crystal White | 20 | 107 | 43 | 150 | 150 | 6600 | 0 | 100% | 0% | 100% | 6600 | 0 | 6600
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.6 | M2 | 44 | Beige Travertine | 20 | 255 | 145 | 400 | 240 | 10560 | 0 | 100% | 0% | 100% | 10560 | 0 | 10560
[13 empty] | 0 |  | 0%
03 | E | 20mm thick polished Crystal White, average of 110mm width border. | 0.45 | M2 | 44 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 9662.4 | 0 | 100% | 0% | 100% | 9662.4 | 0 | 9662.4
[13 empty] | 0 |  | 0%
03 | F | Extra-over to 7 x 5mm brass strips. | 3 | Lm | 44 | Brass | 5 | 0 | 57 | 57 | 171 | 7524 |  | 97.73% | 0% | 97.73% | 7011 | 342 | 7353
[13 empty] | 0 |  | 0%
03 |  | Threshold (20mm thick); 235mm wide x 830mm length, polished Crystal White | 1 | No | 44 | Crystal White | 20 | 98 | 37 | 135 | 135 | 5940 | 0 | 100% | 0% | 100% | 5940 | 0 | 5940
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10.35 | M2 | 44 | PC Rate | 20 | 50 | 100 | 150 | 1552.5 | 68310 | 0 | 100% | 0% | 100% | 68310 | 0 | 68310
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | J | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.9 | M2 | 44 | Volakas | 20 | 406 | 222 | 628 | 9357.2 | 411716.8 | 0 | 100% | 0% | 100% | 411716.8 | 0 | 411716.8
[13 empty] | 0 |  | 0%
03 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.7 | Lm | 44 | Crystal White | 20 | 86 | 48 | 134 | 629.8 | 27711.2 | 0 | 100% | 0% | 100% | 27711.2 | 0 | 27711.2
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | L | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 12.65 | M2 | 44 | Volakas | 20 | 406 | 222 | 628 | 7944.2 | 349544.8 | 0 | 100% | 0% | 100% | 349544.8 | 0 | 349544.8
[13 empty] | 0 |  | 0%
03 | M | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.55 | Lm | 44 | Crystal White | 20 | 79 | 43 | 122 | 677.1 | 29792.4 | 0 | 100% | 0% | 100% | 29792.4 | 0 | 29792.4
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | A | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 3.35 | M2 | 44 | Volakas | 20 | 406 | 222 | 628 | 2103.8 | 92567.2 | 0 | 100% | 0% | 100% | 92567.2 | 0 | 92567.2
[13 empty] | 0 |  | 0%
03 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.1 | Lm | 44 | Crystal White | 20 | 79 | 43 | 122 | 378.2 | 16640.8 | 0 | 100% | 0% | 100% | 16640.8 | 0 | 16640.8
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | C | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 44 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 53768 | 0 | 93.18% | 0% | 93.18% | 48880 | 1222 | 50102
[13 empty] | 0 |  | 0%
03 | D | Bathroom : 250mm wide; total size of 945 x 2430mm high. | 1 | No | 44 | Crystal White | 20 | 699 | 329 | 1028 | 1028 | 45232 | 1 | 90.91% | 2.273% | 93.18% | 41120 | 1028 | 42148
[13 empty] | 0 |  | 0%
03 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 44 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 84832 | 0 | 95.45% | 0% | 95.45% | 77120 | 3856 | 80976
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | F | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 44 | Crystal White | 20 | 118 | 59 | 177 | 177 | 7788 | 6 | 77.27% | 13.64% | 90.91% | 6195 | 885 | 7080
[13 empty] | 0 |  | 0%
03 | G | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 680 x 615mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 44 | Crystal White | 20 | 217 | 108 | 325 | 325 | 14300 | 0.8908 | 95.45% | 4.545% | 100% | 13000 | 1300 | 14300
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | H | Cistern Top : Supply and installation of 20mm thick polished Volakas, 245mm W x 950mm length, pencil edge finish. | 1 | No | 44 | Volakas | 20 | 110 | 55 | 165 | 165 | 7260 | 0 | 100% | 0% | 100% | 7260 | 0 | 7260
[13 empty] | 0 |  | 0%
03 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 44 | Volakas | 20 | 25 | 5 | 30 | 30 | 1320 | 0 | 100% | 0% | 100% | 1320 | 0 | 1320
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | K | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 740 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 44 | Volakas | 20 | 726 | 355 | 1081 | 1081 | 47564 | 0 | 100% | 0% | 100% | 47564 | 0 | 47564
[13 empty] | 0 |  | 0%
03 | A | Bench : Supply and installation of 20mm thick polished Volakas, 410mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 44 | Volakas | 20 | 278 | 119 | 397 | 397 | 17468 | 0 | 100% | 0% | 100% | 17468 | 0 | 17468
[13 empty] | 0 |  | 0%
03 | B | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 44 | Volakas | 20 | 44 | 12 | 56 | 112 | 4928 | 0 | 100% | 0% | 100% | 4928 | 0 | 4928
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | C | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 44 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 91476 | 0 | 100% | 0% | 100% | 89397 | 2079 | 91476
[13 empty] | 0 |  | 0%
|  | Sanitaryware - Stoneworks | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 | D | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 44 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 55088 | 0 | 100% | 0% | 100% | 52584 | 2504 | 55088
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
03 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 89 | M2 | 44 |  |  | 0 | 8 | 8 | 712 | 31328 |  | 99.19% | 0.1256% | 99.32% | 30837.8731 | 276.8934 | 31114.7665
[13 empty] | 0 |  | 0%
03 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 40 | M2 | 44 |  |  | 0 | 8 | 8 | 320 | 14080 |  | 99.19% | 0.1256% | 99.32% | 13859.7183 | 124.4465 | 13984.1647
[13 empty] | 0 |  | 0%
03 |  | Total Amount for TYPE -2A/2B/2C/2D | [10 empty] | 0 |  | 0% |  | 2192018.3914 | 19682.1398 | 2211700.5312
[13 empty] | 0 |  | 0%
04 |  | TYPE -2E/2F/2G/2H (27 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 7 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 2800 | 75600 | 0 | 100% | 0% | 100% | 75600 | 0 | 75600
[13 empty] | 0 |  | 0%
04 | B | 20mm thick polished Crystal White, maximum 135mm width border. | 2.05 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 1000.4 | 27010.8 | 0 | 100% | 0% | 100% | 27010.8 | 0 | 27010.8
[13 empty] | 0 |  | 0%
04 | C | 7 x 5mm Brass strip insert in brushed finish . | 11.6 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 661.2 | 17852.4 |  | 88.89% | 11.11% | 100% | 13885.2 | 3967.2 | 17852.4
[13 empty] | 0 |  | 0%
04 | D | 215mm wide x 900mm length polished Crystal White. | 1 | No | 27 | Crystal White | 20 | 97 | 35 | 132 | 132 | 3564 | 0 | 100% | 0% | 100% | 3564 | 0 | 3564
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.1 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 2040 | 55080 | 0 | 100% | 0% | 100% | 55080 | 0 | 55080
[13 empty] | 0 |  | 0%
04 | F | 20mm thick polished Crystal White, cut to size. | 2.5 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 1220 | 32940 | 0 | 100% | 0% | 100% | 32940 | 0 | 32940
[13 empty] | 0 |  | 0%
04 | G | 20mm thick polished Crystal White, average of 130mm width border. | 3.15 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 1537.2 | 41504.4 | 0 | 100% | 0% | 100% | 41504.4 | 0 | 41504.4
[13 empty] | 0 |  | 0%
04 | H | 7 x 5mm Brass strip insert in brushed finish . | 19.3 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 1100.1 | 29702.7 |  | 88.89% | 11.11% | 100% | 23102.1 | 6600.6 | 29702.7
[13 empty] | 0 |  | 0%
04 | J | 7 x 5mm Brass strip insert in brushed finish . | 16.8 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 957.6 | 25855.2 |  | 88.89% | 11.11% | 100% | 20109.6 | 5745.6 | 25855.2
[13 empty] | 0 |  | 0%
04 | K | Threshold (20mm thick polished Crystal White); 215mm wide x 1115mm length. | 1 | Lm | 27 | Crystal White | 20 | 122 | 44 | 166 | 166 | 4482 | 0 | 100% | 0% | 100% | 4482 | 0 | 4482
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.6 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 1840 | 49680 | 0 | 100% | 0% | 100% | 49680 | 0 | 49680
[13 empty] | 0 |  | 0%
04 | M | 20mm thick polished Crystal White, average 130mm width border. | 1.5 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 732 | 19764 | 0 | 100% | 0% | 100% | 19764 | 0 | 19764
[13 empty] | 0 |  | 0%
04 | N | 7 x 5mm Brass strip insert in brushed finish . | 9.6 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 547.2 | 14774.4 |  | 88.89% | 11.11% | 100% | 11491.2 | 3283.2 | 14774.4
[13 empty] | 0 |  | 0%
04 | P | Threshold (20mm thick); 250mm wide x 945mm length polished Crystal White. | 1 | Lm | 27 | Crystal White | 20 | 116 | 44 | 160 | 160 | 4320 | 0 | 100% | 0% | 100% | 4320 | 0 | 4320
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.2 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 23760 | 0 | 100% | 0% | 100% | 23760 | 0 | 23760
[13 empty] | 0 |  | 0%
04 | C | Threshold (20mm thick); 235mm wide x 860mm length and 40mm high fascia, polished Crystal White | 1 | No | 27 | Crystal White | 20 | 112 | 44 | 156 | 156 | 4212 | 0 | 100% | 0% | 100% | 4212 | 0 | 4212
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.2 | M2 | 27 | Beige Travertine | 20 | 255 | 145 | 400 | 480 | 12960 | 0 | 100% | 0% | 100% | 12960 | 0 | 12960
[13 empty] | 0 |  | 0%
04 | E | 20mm thick polished Crystal White, average of 127mm width border. | 0.6 | M2 | 27 | Crystal White | 20 | 282 | 206 | 488 | 292.8 | 7905.6 | 0 | 100% | 0% | 100% | 7905.6 | 0 | 7905.6
[13 empty] | 0 |  | 0%
04 | F | 7 x 5mm Brass strip insert in brushed finish . | 4.4 | Lm | 27 | Brass | 5 | 0 | 57 | 57 | 250.8 | 6771.6 |  | 88.89% | 11.11% | 100% | 5266.8 | 1504.8 | 6771.6
[13 empty] | 0 |  | 0%
04 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 27 | Crystal White | 20 | 99 | 37 | 136 | 136 | 3672 | 0 | 100% | 0% | 100% | 3672 | 0 | 3672
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10.35 | M2 | 27 | PC Rate | 20 | 50 | 100 | 150 | 1552.5 | 41917.5 | 0 | 100% | 0% | 100% | 41917.5 | 0 | 41917.5
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | J | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.9 | M2 | 27 | Volakas | 20 | 406 | 222 | 628 | 9357.2 | 252644.4 | 0 | 100% | 0% | 100% | 252644.4 | 0 | 252644.4
[13 empty] | 0 |  | 0%
04 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.8 | Lm | 27 | Crystal White | 20 | 86 | 48 | 134 | 643.2 | 17366.4 | 0 | 100% | 0% | 100% | 17366.4 | 0 | 17366.4
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | L | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.95 | M2 | 27 | Volakas | 20 | 406 | 222 | 628 | 8760.6 | 236536.2 | 0 | 100% | 0% | 100% | 236536.2 | 0 | 236536.2
[13 empty] | 0 |  | 0%
04 | M | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.1 | Lm | 27 | Crystal White | 20 | 79 | 43 | 122 | 744.2 | 20093.4 | 0 | 100% | 0% | 100% | 20093.4 | 0 | 20093.4
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | A | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 4.9 | M2 | 27 | Volakas | 20 | 406 | 222 | 628 | 3077.2 | 83084.4 | 0 | 100% | 0% | 100% | 83084.4 | 0 | 83084.4
[13 empty] | 0 |  | 0%
04 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 27 | Crystal White | 20 | 79 | 43 | 122 | 549 | 14823 | 0 | 100% | 0% | 100% | 14823 | 0 | 14823
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | C | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 27 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 32994 | 0 | 96.3% | 0% | 96.3% | 31772 | 0 | 31772
[13 empty] | 0 |  | 0%
04 | D | Bathroom : 250mm wide; total size of 945 x 2430mm high. | 1 | No | 27 | Crystal White | 20 | 699 | 329 | 1028 | 1028 | 27756 | 0 | 96.3% | 0% | 96.3% | 26728 | 0 | 26728
[13 empty] | 0 |  | 0%
04 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 27 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 52056 | -2.6884 | 100% | -3.704% | 96.3% | 52056 | -1928 | 50128
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | F | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 27 | Crystal White | 20 | 118 | 59 | 177 | 177 | 4779 | 0.9 | 74.07% | 18.52% | 92.59% | 3540 | 885 | 4425
[13 empty] | 0 |  | 0%
04 | G | Counter Top @ Closet : Supply and installation of 20mm thick polished Crystal White size of 680 x 615mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 27 | Crystal White | 20 | 217 | 108 | 325 | 325 | 8775 | 0.4454 | 96.3% | 3.704% | 100% | 7800 | 975 | 8775
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | H | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 27 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 56133 | 0 | 100% | 0% | 100% | 56133 | 0 | 56133
[13 empty] | 0 |  | 0%
04 | J | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 27 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 33804 | 3.0876 | 94.44% | 5.556% | 100% | 22536 | 11268 | 33804
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 27 | Volakas | 20 | 639 | 312 | 951 | 951 | 25677 | 0 | 100% | 0% | 100% | 25677 | 0 | 25677
[13 empty] | 0 |  | 0%
04 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 27 | Volakas | 20 | 256 | 107 | 363 | 363 | 9801 | 1 | 96.3% | 3.704% | 100% | 9438 | 363 | 9801
[13 empty] | 0 |  | 0%
04 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 27 | Volakas | 20 | 44 | 12 | 56 | 112 | 3024 | 2 | 96.3% | 3.704% | 100% | 2912 | 112 | 3024
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 | D | Cistern : Supply and installation of 20mm thick polished Volakas, 225mm W x 1315mm length, pencil edge finish. | 1 | No | 27 | Volakas | 20 | 145 | 72 | 217 | 217 | 5859 | 0 | 100% | 0% | 100% | 5859 | 0 | 5859
[13 empty] | 0 |  | 0%
04 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 27 | Volakas | 20 | 25 | 5 | 30 | 30 | 810 | 0 | 100% | 0% | 100% | 810 | 0 | 810
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
04 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 93 | M2 | 27 |  |  | 0 | 8 | 8 | 744 | 20088 |  | 98.8% | 0.8771% | 99.67% | 19548.5721 | 473.9014 | 20022.4735
[13 empty] | 0 |  | 0%
04 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 41 | M2 | 27 |  |  | 0 | 8 | 8 | 328 | 8856 |  | 98.8% | 0.8771% | 99.67% | 8618.1877 | 208.9243 | 8827.112
[13 empty] | 0 |  | 0%
04 |  | Total Amount for TYPE -2E/2F/2G/2H | [10 empty] | 0 |  | 0% |  | 1380202.7598 | 33459.2257 | 1413661.9855
[13 empty] | 0 |  | 0%
05 |  | TYPE -3A/3B/3D/3E/3G (39 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.4 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 1360 | 53040 | 0 | 100% | 0% | 100% | 53040 | 0 | 53040
[13 empty] | 0 |  | 0%
05 | B | 20mm thick polished Crystal White, maximum 155mm width border. | 1.3 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 634.4 | 24741.6 | 0 | 100% | 0% | 100% | 24741.6 | 0 | 24741.6
[13 empty] | 0 |  | 0%
05 | C | Extra-over to 7 x 5mm brass strips. | 7.4 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 421.8 | 16450.2 |  | 94.87% | 2.564% | 97.44% | 15606.6 | 421.8 | 16028.4
[13 empty] | 0 |  | 0%
05 | D | Extra-over to 7 x 5mm brass strips; 950mm length (only the length between threshold and carpet, other locations are excluded) | 1 | No | 39 | Brass | 5 | 0 | 48 | 48 | 48 | 1872 |  | 100% | 0% | 100% | 1872 | 0 | 1872
[13 empty] | 0 |  | 0%
05 | E | Threshold (20mm thick); 340mm wide x 925mm length polished Crystal White | 1 | No | 39 | Crystal White | 20 | 140 | 59 | 199 | 199 | 7761 | 0 | 100% | 0% | 100% | 7761 | 0 | 7761
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | F | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 6.5 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 2600 | 101400 | 0 | 100% | 0% | 100% | 101400 | 0 | 101400
[13 empty] | 0 |  | 0%
05 | G | 20mm thick polished Crystal White, cut to size. | 1.4 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 683.2 | 26644.8 | 0 | 100% | 0% | 100% | 26644.8 | 0 | 26644.8
[13 empty] | 0 |  | 0%
05 | H | 20mm thick polished Crystal White, average of 135mm width border. | 2.75 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 52338 | 0 | 100% | 0% | 100% | 52338 | 0 | 52338
[13 empty] | 0 |  | 0%
05 | J | Extra-over to 7 x 5mm brass strips. | 19.3 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 1100.1 | 42903.9 |  | 94.87% | 2.564% | 97.44% | 40703.7 | 1100.1 | 41803.8
[13 empty] | 0 |  | 0%
05 | K | Extra-over to 7 x 5mm brass strips. | 16.8 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 957.6 | 37346.4 |  | 94.87% | 2.564% | 97.44% | 35431.2 | 957.6 | 36388.8
[13 empty] | 0 |  | 0%
05 | L | Threshold (20mm thick polished Crystal White); 300mm wide x 1510mm length. | 1 | Lm | 39 | Crystal White | 20 | 206 | 82 | 288 | 288 | 11232 | 0 | 100% | 0% | 100% | 11232 | 0 | 11232
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 10.3 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 4120 | 160680 | 0 | 100% | 0% | 100% | 160680 | 0 | 160680
[13 empty] | 0 |  | 0%
05 | N | 20mm thick polished Crystal White, average 170mm width border. | 2.85 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 1390.8 | 54241.2 | 0 | 100% | 0% | 100% | 54241.2 | 0 | 54241.2
[13 empty] | 0 |  | 0%
05 | P | Extra-over to 7 x 5mm brass strips. | 15.8 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 900.6 | 35123.4 |  | 94.87% | 2.564% | 97.44% | 33322.2 | 900.6 | 34222.8
[13 empty] | 0 |  | 0%
05 | Q | Threshold (20mm thick); 375mm wide x 861mm length polished Crystal White. | 1 | Lm | 39 | Crystal White | 20 | 138 | 59 | 197 | 197 | 7683 | 0 | 100% | 0% | 100% | 7683 | 0 | 7683
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.5 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 23400 | 0 | 100% | 0% | 100% | 23400 | 0 | 23400
[13 empty] | 0 |  | 0%
05 | C | Threshold (20mm thick); 235mm wide x 860mm length and 40mm high fascia, polished Crystal White | 1 | No | 39 | Crystal White | 20 | 112 | 44 | 156 | 156 | 6084 | 0 | 100% | 0% | 100% | 6084 | 0 | 6084
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 39 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 12480 | 0 | 100% | 0% | 100% | 12480 | 0 | 12480
[13 empty] | 0 |  | 0%
05 | E | 20mm thick polished Crystal White, average of 110mm width border. | 0.5 | M2 | 39 | Crystal White | 20 | 282 | 206 | 488 | 244 | 9516 | 0 | 100% | 0% | 100% | 9516 | 0 | 9516
[13 empty] | 0 |  | 0%
05 | F | Extra-over to 7 x 5mm brass strips. | 3.6 | Lm | 39 | Brass | 5 | 0 | 57 | 57 | 205.2 | 8002.8 |  | 94.87% | 2.564% | 97.44% | 7592.4 | 205.2 | 7797.6
[13 empty] | 0 |  | 0%
05 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 39 | Crystal White | 20 | 99 | 37 | 136 | 136 | 5304 | 0 | 100% | 0% | 100% | 5304 | 0 | 5304
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10 | M2 | 39 | PC Rate | 20 | 50 | 100 | 150 | 1500 | 58500 | 0 | 100% | 0% | 100% | 58500 | 0 | 58500
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9 | Lm | 39 | Crystal White | 20 | 86 | 48 | 134 | 1206 | 47034 | 0 | 100% | 0% | 100% | 47034 | 0 | 47034
[13 empty] | 0 |  | 0%
05 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-12) | 12.5 | M2 | 39 | Volakas | 20 | 406 | 222 | 628 | 7850 | 306150 | 0 | 100% | 0% | 100% | 306150 | 0 | 306150
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.5 | M2 | 39 | Volakas | 20 | 406 | 222 | 628 | 6594 | 257166 | 0 | 100% | 0% | 100% | 257166 | 0 | 257166
[13 empty] | 0 |  | 0%
05 | L | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.3 | Lm | 39 | Crystal White | 20 | 79 | 43 | 122 | 524.6 | 20459.4 | 0 | 100% | 0% | 100% | 20459.4 | 0 | 20459.4
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.2 | M2 | 39 | Volakas | 20 | 406 | 222 | 628 | 2637.6 | 102866.4 | 0 | 100% | 0% | 100% | 102866.4 | 0 | 102866.4
[13 empty] | 0 |  | 0%
05 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4 | Lm | 39 | Crystal White | 20 | 79 | 43 | 122 | 488 | 19032 | 0 | 100% | 0% | 100% | 19032 | 0 | 19032
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | B | Bedroom : 300mm wide; total size of 1510 x 2430mm high. | 1 | No | 39 | Crystal White | 20 | 869 | 433 | 1302 | 1302 | 50778 | 1.911 | 94.87% | 2.564% | 97.44% | 48174 | 1302 | 49476
[13 empty] | 0 |  | 0%
05 | C | Foyer : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 39 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 42393 | 56.2302 | 7.692% | 92.31% | 100% | 2174 | 40219 | 42393
[13 empty] | 0 |  | 0%
05 | D | Bathroom : (145 + 160)mm wide; total size of 995 x 2430mm high. | 1 | No | 39 | Crystal White | 20 | 811 | 407 | 1218 | 1218 | 47502 | 0 | 100% | 0% | 100% | 47501.1316 | 0 | 47501.1316
[13 empty] | 0 |  | 0%
05 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 39 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 75192 | 0 | 100% | 0% | 100% | 75192 | 0 | 75192
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | F | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 233 | 118 | 351 | 351 | 13689 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1100mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 310 | 164 | 474 | 474 | 18486 | 0.96344 | 96.3% | 3.704% | 100% | 16432 | 2054 | 18486
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 660mm length, mitered with 40mm high fascia, (full high cladding to 2 sides, elsewhere). Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 200 | 99 | 299 | 299 | 11661 | 0 | 97.44% | 0% | 97.44% | 11063 | 299 | 11362
[13 empty] | 0 |  | 0%
05 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (a) 595mm wide x 1535mm high cladding to 2 sides having (b) 30mm width complete front frame and (c) soffit/ceiling. Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 1172 | 654 | 1826 | 1826 | 71214 | 0 | 97.44% | 0% | 97.44% | 67562 | 1826 | 69388
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | K | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 39 | Crystal White | 20 | 118 | 59 | 177 | 177 | 6903 | 0 | 97.44% | 0% | 97.44% | 6549 | 177 | 6726
[13 empty] | 0 |  | 0%
05 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround, shelf, and back support elsewhere). | 1 | No | 39 | Volakas | 20 | 1935 | 872 | 2807 | 2807 | 109473 | 0 | 100% | 0% | 100% | 106666 | 2807 | 109473
[13 empty] | 0 |  | 0%
05 | B | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 170mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 2 | No | 39 | Volakas | 20 | 519 | 254 | 773 | 1546 | 60294 | 0 | 100% | 0% | 100% | 60294 | 0 | 60294
[13 empty] | 0 |  | 0%
05 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 68 | 31 | 99 | 99 | 3861 | 0 | 100% | 0% | 100% | 3861 | 0 | 3861
[13 empty] | 0 |  | 0%
05 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 39 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 36816 | 7.0265 | 87.18% | 6.41% | 93.59% | 26432 | 8024 | 34456
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 639 | 312 | 951 | 951 | 37089 | 0 | 100% | 0% | 100% | 37089 | 0 | 37089
[13 empty] | 0 |  | 0%
05 | F | Bench : Supply and installation of 20mm thick polished Volakas, 410mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 39 | Volakas | 20 | 278 | 119 | 397 | 397 | 15483 | 0 | 100% | 0% | 100% | 15483 | 0 | 15483
[13 empty] | 0 |  | 0%
05 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 39 | Volakas | 20 | 44 | 12 | 56 | 112 | 4368 | 0 | 100% | 0% | 100% | 4368 | 0 | 4368
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1020mm length, pencil edge finish. | 1 | No | 39 | Volakas | 20 | 107 | 53 | 160 | 160 | 6240 | 0 | 100% | 0% | 100% | 6240 | 0 | 6240
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
05 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 94 | M2 | 39 |  |  | 0 | 8 | 8 | 752 | 29328 |  | 96.69% | 2.219% | 98.9% | 28172.9021 | 833.7436 | 29006.6458
[13 empty] | 0 |  | 0%
05 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 41 | M2 | 39 |  |  | 0 | 8 | 8 | 328 | 12792 |  | 96.69% | 2.219% | 98.9% | 12288.1807 | 363.6541 | 12651.8348
[13 empty] | 0 |  | 0%
05 |  | Total Amount for TYPE -3A/3B/3D/3E/3G | [10 empty] | 0 |  | 0% |  | 2077822.7144 | 61490.6977 | 2139313.4122
[13 empty] | 0 |  | 0%
06 |  | TYPE -03C/03F (18 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.8 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 1120 | 20160 | 0 | 100% | 0% | 100% | 20160 | 0 | 20160
[13 empty] | 0 |  | 0%
06 | B | 20mm thick polished Crystal White, maximum 140mm width border. | 1.35 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 658.8 | 11858.4 | 0 | 100% | 0% | 100% | 11858.4 | 0 | 11858.4
[13 empty] | 0 |  | 0%
06 | C | 7 x 5mm Brass strip insert in brushed finish . | 7.4 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 421.8 | 7592.4 |  | 88.89% | 5.556% | 94.44% | 5905.2 | 1265.4 | 7170.6
[13 empty] | 0 |  | 0%
06 | D | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat; 925mm length (only the length between threshold and carpet, other locations are excluded) | 0.93 | Lm | 18 | Brass | 5 | 0 | 54 | 54 | 50.22 | 903.96 |  | 100% | 0% | 100% | 903.96 | 0 | 903.96
[13 empty] | 0 |  | 0%
06 | E | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White | 1 | No | 18 | Crystal White | 20 | 134 | 55 | 189 | 189 | 3402 | 0 | 100% | 0% | 100% | 3402 | 0 | 3402
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | F | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.6 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 2240 | 40320 | 0 | 100% | 0% | 100% | 40320 | 0 | 40320
[13 empty] | 0 |  | 0%
06 | G | 20mm thick polished Crystal White, cut to size. | 1.6 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 780.8 | 14054.4 | 0 | 100% | 0% | 100% | 14054.4 | 0 | 14054.4
[13 empty] | 0 |  | 0%
06 | H | 20mm thick polished Crystal White, average of 137mm width border. | 2.75 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 24156 | 0 | 100% | 0% | 100% | 24156 | 0 | 24156
[13 empty] | 0 |  | 0%
06 | J | 7 x 5mm Brass strip insert in brushed finish . | 19.3 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 1100.1 | 19801.8 |  | 88.89% | 11.11% | 100% | 15401.4 | 4400.4 | 19801.8
[13 empty] | 0 |  | 0%
06 | K | 7 x 5mm Brass strip insert in brushed finish . | 16.8 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 957.6 | 17236.8 |  | 88.89% | 11.11% | 100% | 13406.4 | 3830.4 | 17236.8
[13 empty] | 0 |  | 0%
06 | L | Threshold (20mm thick polished Crystal White); 300mm wide x 1510mm length. | 1 | No | 18 | Crystal White | 20 | 206 | 82 | 288 | 288 | 5184 | 0 | 100% | 0% | 100% | 5184 | 0 | 5184
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 10 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 4000 | 72000 | 0 | 100% | 0% | 100% | 72000 | 0 | 72000
[13 empty] | 0 |  | 0%
06 | N | 20mm thick polished Crystal White, average 153mm width border. | 2.7 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 1317.6 | 23716.8 | 0 | 100% | 0% | 100% | 23716.8 | 0 | 23716.8
[13 empty] | 0 |  | 0%
06 | P | 7 x 5mm Brass strip insert in brushed finish . | 15.8 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 900.6 | 16210.8 |  | 88.89% | 11.11% | 100% | 12608.4 | 3602.4 | 16210.8
[13 empty] | 0 |  | 0%
06 | A | Threshold (20mm thick); 375mm wide x 995mm length polished Crystal White. | 1 | No | 18 | Crystal White | 20 | 163 | 70 | 233 | 233 | 4194 | 0 | 100% | 0% | 100% | 4194 | 0 | 4194
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.7 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 680 | 12240 | 0 | 100% | 0% | 100% | 12240 | 0 | 12240
[13 empty] | 0 |  | 0%
06 | D | Threshold (20mm thick); 235mm wide x 860mm length and 40mm high fascia, polished Crystal White | 1 | No | 18 | Crystal White | 20 | 112 | 44 | 156 | 156 | 2808 | 0 | 100% | 0% | 100% | 2808 | 0 | 2808
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 18 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 5760 | 0 | 100% | 0% | 100% | 5760 | 0 | 5760
[13 empty] | 0 |  | 0%
06 | F | 20mm thick polished Crystal White, average of 107mm width border. | 0.5 | M2 | 18 | Crystal White | 20 | 282 | 206 | 488 | 244 | 4392 | 0 | 100% | 0% | 100% | 4392 | 0 | 4392
[13 empty] | 0 |  | 0%
06 | G | 7 x 5mm Brass strip insert in brushed finish . | 3.6 | Lm | 18 | Brass | 5 | 0 | 57 | 57 | 205.2 | 3693.6 |  | 88.89% | 11.11% | 100% | 2872.8 | 820.8 | 3693.6
[13 empty] | 0 |  | 0%
06 | H | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 18 | Crystal White | 20 | 99 | 37 | 136 | 136 | 2448 | 0 | 100% | 0% | 100% | 2448 | 0 | 2448
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | J | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10 | M2 | 18 | PC Rate | 20 | 50 | 100 | 150 | 1500 | 27000 | 0 | 100% | 0% | 100% | 27000 | 0 | 27000
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9 | Lm | 18 | Crystal White | 20 | 86 | 48 | 134 | 1206 | 21708 | 0 | 100% | 0% | 100% | 21708 | 0 | 21708
[13 empty] | 0 |  | 0%
06 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-12) | 12.5 | M2 | 18 | Volakas | 20 | 406 | 222 | 628 | 7850 | 141300 | 0 | 100% | 0% | 100% | 141300 | 0 | 141300
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | L | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 11.5 | M2 | 18 | Volakas | 20 | 406 | 222 | 628 | 7222 | 129996 | 0 | 100% | 0% | 100% | 129996 | 0 | 129996
[13 empty] | 0 |  | 0%
06 | M | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.7 | Lm | 18 | Crystal White | 20 | 94 | 56 | 150 | 705 | 12690 | 0 | 100% | 0% | 100% | 12690 | 0 | 12690
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.2 | M2 | 18 | Volakas | 20 | 406 | 222 | 628 | 2637.6 | 47476.8 | 0 | 100% | 0% | 100% | 47476.8 | 0 | 47476.8
[13 empty] | 0 |  | 0%
06 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.2 | Lm | 18 | Crystal White | 20 | 79 | 43 | 122 | 512.4 | 9223.2 | 0 | 100% | 0% | 100% | 9223.2 | 0 | 9223.2
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves: Supply and installation of (20 x 10mm) thick polished Crystal White | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 |  | Bedroom : 300mm wide; total size of 1510 x 2430mm high. | 1 | No | 18 | Crystal White | 20 | 869 | 433 | 1302 | 1302 | 23436 | 0 | 94.44% | 0% | 94.44% | 22134 | 0 | 22134
[13 empty] | 0 |  | 0%
06 | C | Foyer : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 18 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 19566 | 18 | 0% | 100% | 100% | 0 | 19566 | 19566
[13 empty] | 0 |  | 0%
06 | D | Bathroom : (145 + 160)mm wide; total size of 995 x 2430mm high. | 1 | No | 18 | Crystal White | 20 | 811 | 407 | 1218 | 1218 | 21924 | 1 | 88.89% | 5.556% | 94.44% | 19488 | 1218 | 20706
[13 empty] | 0 |  | 0%
06 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 18 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 34704 | -2 | 100% | -5.556% | 94.44% | 34704 | -1928 | 32776
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | F | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 233 | 118 | 351 | 351 | 6318 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 286 | 149 | 435 | 435 | 7830 | 0.6169 | 88.89% | 5.556% | 94.44% | 6960 | 435 | 7395
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 655mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 200 | 99 | 299 | 299 | 5382 | 1 | 88.89% | 5.556% | 94.44% | 4784 | 299 | 5083
[13 empty] | 0 |  | 0%
06 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 655 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 946 | 528 | 1474 | 1474 | 26532 | 1 | 88.89% | 5.556% | 94.44% | 23584 | 1474 | 25058
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | A | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 18 | Crystal White | 20 | 118 | 59 | 177 | 177 | 3186 | 1 | 88.89% | 5.556% | 94.44% | 2832 | 177 | 3009
[13 empty] | 0 |  | 0%
06 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 18 | Volakas | 20 | 1935 | 872 | 2807 | 2807 | 50526 | 0 | 100% | 0% | 100% | 47719 | 2807 | 50526
[13 empty] | 0 |  | 0%
06 | C | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 18 | Volakas | 20 | 372 | 182 | 554 | 1108 | 19944 | 0 | 100% | 0% | 100% | 19944 | 0 | 19944
[13 empty] | 0 |  | 0%
06 | D | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 68 | 31 | 99 | 99 | 1782 | 0 | 100% | 0% | 100% | 1782 | 0 | 1782
[13 empty] | 0 |  | 0%
06 | E | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 18 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 16992 | 8.4318 | 83.33% | 16.67% | 100% | 11328 | 5664 | 16992
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 250mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 639 | 312 | 951 | 951 | 17118 | 0 | 100% | 0% | 100% | 17118 | 0 | 17118
[13 empty] | 0 |  | 0%
06 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 805mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 18 | Volakas | 20 | 199 | 81 | 280 | 280 | 5040 | 0 | 97.22% | 0% | 97.22% | 5040 | -140 | 4900
[13 empty] | 0 |  | 0%
06 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 18 | Volakas | 20 | 44 | 12 | 56 | 112 | 2016 | 0 | 97.22% | 0% | 97.22% | 2016 | -56 | 1960
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 | A | Cictern Top at Toilet. Supply and installation of 20mm thick polished Volakas, 220mm width x 1020mm length, pencil edge finish (HTL-ST-12) | 1 | No | 18 | Volakas | 20 | 107 | 53 | 160 | 160 | 2880 | 0 | 100% | 0% | 100% | 2720 | 160 | 2880
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
06 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 96 | M2 | 18 |  |  | 0 | 8 | 8 | 768 | 13824 |  | 95.39% | 3.188% | 98.58% | 13003.6832 | 623.4209 | 13627.1041
[13 empty] | 0 |  | 0%
06 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 41 | M2 | 18 |  |  | 0 | 8 | 8 | 328 | 5904 |  | 95.39% | 3.188% | 98.58% | 5553.6564 | 266.2527 | 5819.909
[13 empty] | 0 |  | 0%
06 |  | Total Amount for TYPE -3C/3F | [10 empty] | 0 |  | 0% |  | 927896.0995 | 44485.0735 | 972381.1731
[13 empty] | 0 |  | 0%
07 |  | TYPE -04A/4B (5 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.65 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1460 | 7300 | 0 | 100% | 0% | 100% | 7300 | 0 | 7300
[13 empty] | 0 |  | 0%
07 | B | 20mm thick polished Crystal White, maximum 135mm width border. | 1.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 756.4 | 3782 | 0 | 100% | 0% | 100% | 3782 | 0 | 3782
[13 empty] | 0 |  | 0%
07 | C | 7 x 5mm Brass strip insert in brushed finish . | 8.9 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 507.3 | 2536.5 |  | 100% | 0% | 100% | 2536.5 | 0 | 2536.5
[13 empty] | 0 |  | 0%
07 | D | Threshold (20mm thick); 210mm wide x 1100mm length polished Crystal White | 1 | No | 5 | Crystal White | 20 | 119 | 43 | 162 | 162 | 810 | 0 | 100% | 0% | 100% | 810 | 0 | 810
[13 empty] | 0 |  | 0%
07 | Add | 8 x 8mm Brass strip insert in brushed finish with top layer brass coat; 800mm length (only the legth between threshold and carpet, other locations are excluded) (HTL-ME-04) | 1 | No | 5 | Brass | 5 | 0 | 48 | 48 | 48 | 240 |  | 100% | 0% | 100% | 240 | 0 | 240
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 10.4 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 4160 | 20800 | 0 | 100% | 0% | 100% | 20800 | 0 | 20800
[13 empty] | 0 |  | 0%
07 | F | 20mm thick polished Crystal White, cut to size. | 3 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1464 | 7320 | 0 | 100% | 0% | 100% | 7320 | 0 | 7320
[13 empty] | 0 |  | 0%
07 | G | 20mm thick polished Crystal White, average of 167mm width border; 20850mm length. | 3.05 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1488.4 | 7442 | 0 | 100% | 0% | 100% | 7442 | 0 | 7442
[13 empty] | 0 |  | 0%
07 | H | 7 x 5mm Brass strip insert in brushed finish . | 21.4 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1219.8 | 6099 |  | 100% | 0% | 100% | 6099 | 0 | 6099
[13 empty] | 0 |  | 0%
07 | J | 7 x 5mm Brass strip insert in brushed finish . | 17 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 969 | 4845 |  | 100% | 0% | 100% | 4845 | 0 | 4845
[13 empty] | 0 |  | 0%
07 | K | Threshold (20mm thick polished Crystal White); 320mm wide x 945mm length. | 1 | Lm | 5 | Crystal White | 20 | 135 | 55 | 190 | 190 | 950 | 0 | 100% | 0% | 100% | 950 | 0 | 950
[13 empty] | 0 |  | 0%
07 | L | Threshold (20mm thick polished Crystal White); 215mm wide x 890mm length. | 1 | Lm | 5 | Crystal White | 20 | 97 | 35 | 132 | 132 | 660 | 0 | 100% | 0% | 100% | 660 | 0 | 660
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 7.5 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3000 | 15000 | 0 | 100% | 0% | 100% | 15000 | 0 | 15000
[13 empty] | 0 |  | 0%
07 | N | 20mm thick polished Crystal White, average 139mm width border; 12275mm length. | 2.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1024.8 | 5124 | 0 | 100% | 0% | 100% | 5124 | 0 | 5124
[13 empty] | 0 |  | 0%
07 | A | 7 x 5mm Brass strip insert in brushed finish . | 11 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 627 | 3135 |  | 100% | 0% | 100% | 3135 | 0 | 3135
[13 empty] | 0 |  | 0%
07 | B | Threshold (20mm thick); 375mm wide x 995mm length polished Crystal White. | 1 | Lm | 5 | Crystal White | 20 | 163 | 70 | 233 | 233 | 1165 | 0 | 100% | 0% | 100% | 1165 | 0 | 1165
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | C | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1200 | 6000 | 0 | 100% | 0% | 100% | 6000 | 0 | 6000
[13 empty] | 0 |  | 0%
07 | E | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | F | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.9 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 360 | 1800 | 0 | 100% | 0% | 100% | 1800 | 0 | 1800
[13 empty] | 0 |  | 0%
07 | G | 20mm thick polished Crystal White, average of 107mm width border; 4570mm length. | 0.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1342 | 0 | 100% | 0% | 100% | 1342 | 0 | 1342
[13 empty] | 0 |  | 0%
07 | H | 7 x 5mm Brass strip insert in brushed finish . | 3.85 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 219.45 | 1097.25 |  | 100% | 0% | 100% | 1097.25 | 0 | 1097.25
[13 empty] | 0 |  | 0%
07 | J | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | K | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 24 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 3600 | 18000 | 0 | 100% | 0% | 100% | 18000 | 0 | 18000
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | L | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.9 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 924.6 | 4623 | 0 | 100% | 0% | 100% | 4623 | 0 | 4623
[13 empty] | 0 |  | 0%
07 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-12) | 9.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 29987 | 0 | 100% | 0% | 100% | 29987 | 0 | 29987
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 11.85 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 7441.8 | 37209 | 0 | 100% | 0% | 100% | 37209 | 0 | 37209
[13 empty] | 0 |  | 0%
07 | N | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.2 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 780 | 3900 | 0 | 100% | 0% | 100% | 3900 | 0 | 3900
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.1 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2574.8 | 12874 | 0 | 100% | 0% | 100% | 12874 | 0 | 12874
[13 empty] | 0 |  | 0%
07 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.8 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 463.6 | 2318 | 0 | 100% | 0% | 100% | 2318 | 0 | 2318
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves: Supply and installation of (20 x 10mm) thick polished Crystal White | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | C | Bedroom : 320mm wide; total size of 945 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 831 | 421 | 1252 | 1252 | 6260 | 0 | 100% | 0% | 100% | 6260 | 0 | 6260
[13 empty] | 0 |  | 0%
07 | D | Bathroom : (160 + 145)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 789 | 395 | 1184 | 1184 | 5920 | 0 | 100% | 0% | 100% | 5920 | 0 | 5920
[13 empty] | 0 |  | 0%
07 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
[13 empty] | 0 |  | 0%
07 | Add | 135+131mm wide; total size of 860 x 2430mm high (HTL-ST-01) | 1 | No | 5 | Crystal White | 20 | 718 | 344 | 1062 | 1062 | 5310 | 0 | 100% | 0% | 100% | 5310 | 0 | 5310
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | F | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 233 | 118 | 351 | 351 | 1755 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2175 | 0 | 100% | 0% | 100% | 2175 | 0 | 2175
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 655mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 200 | 99 | 299 | 299 | 1495 | 0 | 100% | 0% | 100% | 1495 | 0 | 1495
[13 empty] | 0 |  | 0%
07 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 655 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 946 | 528 | 1474 | 1474 | 7370 | 0 | 100% | 0% | 100% | 7370 | 0 | 7370
[13 empty] | 0 |  | 0%
07 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 118 | 59 | 177 | 177 | 885 | 0 | 100% | 0% | 100% | 885 | 0 | 885
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 5 | Volakas | 20 | 1935 | 872 | 2807 | 2807 | 14035 | 0 | 100% | 0% | 100% | 14035 | 0 | 14035
[13 empty] | 0 |  | 0%
07 | B | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 372 | 182 | 554 | 1108 | 5540 | 0 | 100% | 0% | 100% | 5540 | 0 | 5540
[13 empty] | 0 |  | 0%
07 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 43 | 19 | 62 | 124 | 620 | 0 | 100% | 0% | 100% | 620 | 0 | 620
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 5 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 4720 | 0 | 100% | 0% | 100% | 4720 | 0 | 4720
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 492 | 240 | 732 | 732 | 3660 | 0 | 100% | 0% | 100% | 3660 | 0 | 3660
[13 empty] | 0 |  | 0%
07 | F | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1145mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 272 | 114 | 386 | 386 | 1930 | 0 | 100% | 0% | 100% | 1930 | 0 | 1930
[13 empty] | 0 |  | 0%
07 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 102 | 50 | 152 | 152 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
[13 empty] | 0 |  | 0%
07 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
07 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 113 | M2 | 5 |  |  | 0 | 8 | 8 | 904 | 4520 |  | 99.37% | 0% | 99.37% | 4491.7202 | 0 | 4491.7202
[13 empty] | 0 |  | 0%
07 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 62 | M2 | 5 |  |  | 0 | 8 | 8 | 496 | 2480 |  |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
07 |  | Total Amount for TYPE -4A/4B | [10 empty] | 0 |  | 0% |  | 283240.4702 | 0 | 283240.4702
[13 empty] | 0 |  | 0%
08 |  | TYPE -05A (9 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.4 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 960 | 8640 | 0 | 100% | 0% | 100% | 8640 | 0 | 8640
[13 empty] | 0 |  | 0%
08 | B | 20mm thick polished Crystal White, maximum 171mm width border. | 1.2 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 585.6 | 5270.4 | 0 | 100% | 0% | 100% | 5270.4 | 0 | 5270.4
[13 empty] | 0 |  | 0%
08 | C | 7 x 5mm Brass strip insert in brushed finish . | 6.3 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 359.1 | 3231.9 |  | 66.67% | 33.33% | 100% | 2154.6 | 1077.3 | 3231.9
[13 empty] | 0 |  | 0%
08 | D | Threshold (20mm thick); 210mm wide x 1100mm length polished Crystal White | 1 | No | 9 | Crystal White | 20 | 119 | 43 | 162 | 162 | 1458 | 0 | 100% | 0% | 100% | 1458 | 0 | 1458
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 22.6 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 9040 | 81360 | 4.52 | 97.78% | 2.222% | 100% | 79552 | 1808 | 81360
[13 empty] | 0 |  | 0%
08 | F | 20mm thick polished Crystal White, cut to size. | 3.3 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 1610.4 | 14493.6 | 0.66 | 97.78% | 2.222% | 100% | 14171.52 | 322.08 | 14493.6
[13 empty] | 0 |  | 0%
08 | G | 20mm thick polished Crystal White, average of 132mm width border. | 4.15 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 2025.2 | 18226.8 | 0.83 | 97.78% | 2.222% | 100% | 17821.76 | 405.04 | 18226.8
[13 empty] | 0 |  | 0%
08 | H | 7 x 5mm Brass strip insert in brushed finish . | 25.4 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 1447.8 | 13030.2 |  | 66.67% | 22.22% | 88.89% | 8686.8 | 2895.6 | 11582.4
[13 empty] | 0 |  | 0%
08 | J | 7 x 5mm Brass strip insert in brushed finish . | 11.3 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 644.1 | 5796.9 |  | 66.67% | 22.22% | 88.89% | 3864.6 | 1288.2 | 5152.8
[13 empty] | 0 |  | 0%
08 | K | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | Lm | 9 | Crystal White | 20 | 231 | 97 | 328 | 328 | 2952 | 0.1057 | 97.78% | 2.222% | 100% | 2886.4 | 65.6 | 2952
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 11.5 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 4600 | 41400 | 2.3 | 97.78% | 2.222% | 100% | 40480 | 920 | 41400
[13 empty] | 0 |  | 0%
08 | M | 20mm thick polished Crystal White, average 139mm width border. | 2.5 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 1220 | 10980 | 0.5 | 97.78% | 2.222% | 100% | 10736 | 244 | 10980
[13 empty] | 0 |  | 0%
08 | N | 7 x 5mm Brass strip insert in brushed finish . | 16.6 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 946.2 | 8515.8 |  | 66.67% | 33.33% | 100% | 5677.2 | 2838.6 | 8515.8
[13 empty] | 0 |  | 0%
08 | P | Threshold (20mm thick); 375mm wide x 860mm length polished Crystal White. | 1 | Lm | 9 | Crystal White | 20 | 138 | 59 | 197 | 197 | 1773 | 0.129 | 97.78% | 2.222% | 100% | 1733.6 | 39.4 | 1773
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.7 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 680 | 6120 | 0 | 100% | 0% | 100% | 6120 | 0 | 6120
[13 empty] | 0 |  | 0%
08 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 9 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1224 | 0 | 100% | 0% | 100% | 1224 | 0 | 1224
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 9 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 2880 | 0 | 100% | 0% | 100% | 2880 | 0 | 2880
[13 empty] | 0 |  | 0%
08 | E | 20mm thick polished Crystal White, average of 101mm width border. | 0.45 | M2 | 9 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 1976.4 | 0 | 100% | 0% | 100% | 1976.4 | 0 | 1976.4
[13 empty] | 0 |  | 0%
08 | F | 7 x 5mm Brass strip insert in brushed finish . | 3.5 | Lm | 9 | Brass | 5 | 0 | 57 | 57 | 199.5 | 1795.5 |  | 66.67% | 33.33% | 100% | 1197 | 598.5 | 1795.5
[13 empty] | 0 |  | 0%
08 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 9 | Crystal White | 20 | 99 | 37 | 136 | 136 | 1224 | 0 | 100% | 0% | 100% | 1224 | 0 | 1224
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 13.5 | M2 | 9 | PC Rate | 20 | 50 | 100 | 150 | 2025 | 18225 | 0 | 100% | 0% | 100% | 18225 | 0 | 18225
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 13.9 | Lm | 9 | Crystal White | 20 | 86 | 48 | 134 | 1862.6 | 16763.4 | 0 | 100% | 0% | 100% | 16763.4 | 0 | 16763.4
[13 empty] | 0 |  | 0%
08 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 9.55 | M2 | 9 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 53976.6 | 9.55 | 88.89% | 11.11% | 100% | 47979.2 | 5997.4 | 53976.6
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.8 | M2 | 9 | Volakas | 20 | 406 | 222 | 628 | 6782.4 | 61041.6 | 0 | 100% | 0% | 100% | 61041.6 | 0 | 61041.6
[13 empty] | 0 |  | 0%
08 | L | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 9 | Crystal White | 20 | 94 | 56 | 150 | 675 | 6075 | 1.035 | 88.89% | 11.11% | 100% | 5400 | 675 | 6075
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4 | M2 | 9 | Volakas | 20 | 406 | 222 | 628 | 2512 | 22608 | 0 | 100% | 0% | 100% | 22608 | 0 | 22608
[13 empty] | 0 |  | 0%
08 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.6 | Lm | 9 | Crystal White | 20 | 79 | 43 | 122 | 439.2 | 3952.8 | 0.648 | 88.89% | 11.11% | 100% | 3513.6 | 439.2 | 3952.8
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | B | Bedroom : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 9 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 13302 | 4.459 | 66.67% | 22.22% | 88.89% | 7390 | 4434 | 11824
[13 empty] | 0 |  | 0%
08 | C | Bathroom : (160 + 145)mm wide); total size of 860 x 2430mm high. | 1 | No | 9 | Crystal White | 20 | 789 | 395 | 1184 | 1184 | 10656 | 5.2338 | 66.67% | 33.33% | 100% | 5920 | 4736 | 10656
[13 empty] | 0 |  | 0%
08 | D | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 9 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 17352 | 2.6884 | 88.89% | 11.11% | 100% | 11568 | 5784 | 17352
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | E | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 233 | 118 | 351 | 351 | 3159 | 1.4783 | 66.67% | 33.33% | 100% | 2106 | 1053 | 3159
[13 empty] | 0 |  | 0%
08 | F | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 262 | 134 | 396 | 396 | 3564 | 1.679 | 66.67% | 33.33% | 100% | 2376 | 1188 | 3564
[13 empty] | 0 |  | 0%
08 | G | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 15057 | 0.73713 | 66.67% | 22.22% | 88.89% | 10038 | 3346 | 13384
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | H | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 286 | 149 | 435 | 435 | 3915 | 1.8507 | 66.67% | 33.33% | 100% | 2610 | 1305 | 3915
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | J | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 9 | Crystal White | 20 | 118 | 59 | 177 | 177 | 1593 | 0.27 | 66.67% | 33.33% | 100% | 1062 | 531 | 1593
[13 empty] | 0 |  | 0%
08 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 9 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 18711 | 0 | 100% | 0% | 100% | 18711 | 0 | 18711
[13 empty] | 0 |  | 0%
08 | B | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 372 | 182 | 554 | 554 | 4986 | 0 | 100% | 0% | 100% | 4986 | 0 | 4986
[13 empty] | 0 |  | 0%
08 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 9 | Volakas | 20 | 43 | 19 | 62 | 124 | 1116 | 0 | 100% | 0% | 100% | 1116 | 0 | 1116
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 9 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 8496 | 2 | 77.78% | 22.22% | 100% | 4720 | 3776 | 8496
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 492 | 240 | 732 | 732 | 6588 | 0 | 100% | 0% | 100% | 6588 | 0 | 6588
[13 empty] | 0 |  | 0%
08 | F | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1385mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 9 | Volakas | 20 | 324 | 138 | 462 | 462 | 4158 | 0 | 100% | 0% | 100% | 4158 | 0 | 4158
[13 empty] | 0 |  | 0%
08 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 9 | Volakas | 20 | 44 | 12 | 56 | 112 | 1008 | 0 | 100% | 0% | 100% | 1008 | 0 | 1008
[13 empty] | 0 |  | 0%
|  | Additional Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 260mm W x 1050mm length, pencil edge finish. | 1 | No | 9 | Volakas | 20 | 127 | 65 | 192 | 192 | 1728 | 0 | 100% | 0% | 100% | 1728 | 0 | 1728
[13 empty] | 0 |  | 0%
08 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 9 | Volakas | 20 | 25 | 5 | 30 | 30 | 270 | 0 | 100% | 0% | 100% | 270 | 0 | 270
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
08 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 115 | M2 | 9 |  |  | 0 | 8 | 8 | 920 | 8280 |  | 91.97% | 7.041% | 99.01% | 7484.0679 | 714.1245 | 8198.1924
[13 empty] | 0 |  | 0%
08 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 66 | M2 | 9 |  |  | 0 | 8 | 8 | 528 | 4752 |  | 91.97% | 7.041% | 99.01% | 4295.2042 | 409.8454 | 4705.0495
[13 empty] | 0 |  | 0%
08 |  | Total Amount for TYPE -5A | [10 empty] | 0 |  | 0% |  | 491419.352 | 46890.8899 | 538310.2419
[13 empty] | 0 |  | 0%
09 |  | TYPE -06A (5 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 920 | 4600 | 0 | 100% | 0% | 100% | 4600 | 0 | 4600
[13 empty] | 0 |  | 0%
09 | B | 20mm thick polished Crystal White, maximum 159mm width border. | 1.15 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 561.2 | 2806 | 0 | 100% | 0% | 100% | 2806 | 0 | 2806
[13 empty] | 0 |  | 0%
09 | C | 7 x 5mm Brass strip insert in brushed finish. | 5.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 330.6 | 1653 |  | 80% | 20% | 100% | 1322.4 | 330.6 | 1653
[13 empty] | 0 |  | 0%
09 | D | 7 x 5mm Brass strip insert in brushed finish. 900mm length (only the length between threshold and carpet, other locations are excluded) | 0.9 | Lm | 5 | Brass | 5 | 0 | 53 | 53 | 47.7 | 238.5 |  | 80% | 20% | 100% | 190.8 | 47.7 | 238.5
[13 empty] | 0 |  | 0%
09 | E | Threshold (20mm thick); 220mm wide x 1100mm length polished Crystal White | 1 | No | 5 | Crystal White | 20 | 121 | 44 | 165 | 165 | 825 | 0.242 | 80% | 20% | 100% | 660 | 165 | 825
[13 empty] | 0 |  | 0%
09 | F | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0.2752 | 80% | 20% | 100% | 704 | 176 | 880
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 18.2 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 7280 | 36400 | 0 | 100% | 0% | 100% | 36400 | 0 | 36400
[13 empty] | 0 |  | 0%
09 | H | 20mm thick polished Crystal White, cut to size. | 3.5 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1708 | 8540 | 0 | 100% | 0% | 100% | 8540 | 0 | 8540
[13 empty] | 0 |  | 0%
09 | J | 20mm thick polished Crystal White, average of 165mm width border. | 4.5 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 2196 | 10980 | 0 | 100% | 0% | 100% | 10980 | 0 | 10980
[13 empty] | 0 |  | 0%
09 | K | 7 x 5mm Brass strip insert in brushed finish. | 27 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1539 | 7695 |  | 80% | 20% | 100% | 6156 | 1539 | 7695
[13 empty] | 0 |  | 0%
09 | L | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 627 | 3135 |  | 80% | 20% | 100% | 2508 | 627 | 3135
[13 empty] | 0 |  | 0%
09 | M | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | Lm | 5 | Crystal White | 20 | 155 | 62 | 217 | 217 | 1085 | 0 | 100% | 0% | 100% | 1085 | 0 | 1085
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3720 | 18600 | 0 | 100% | 0% | 100% | 18600 | 0 | 18600
[13 empty] | 0 |  | 0%
09 | P | 20mm thick polished Crystal White, average 167mm width border. | 2.5 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1220 | 6100 | 0 | 100% | 0% | 100% | 6100 | 0 | 6100
[13 empty] | 0 |  | 0%
09 | Q | 7 x 5mm Brass strip insert in brushed finish. | 15.6 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 889.2 | 4446 |  | 80% | 20% | 100% | 3556.8 | 889.2 | 4446
[13 empty] | 0 |  | 0%
09 | A | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | Lm | 5 | Crystal White | 20 | 134 | 55 | 189 | 189 | 945 | 0 | 100% | 0% | 100% | 945 | 0 | 945
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | B | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.5 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 3000 | 0 | 100% | 0% | 100% | 3000 | 0 | 3000
[13 empty] | 0 |  | 0%
09 | D | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 0.8 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 108.8 | 544 | 0 | 100% | 0% | 100% | 544 | 0 | 544
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.6 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 240 | 1200 | 0 | 100% | 0% | 100% | 1200 | 0 | 1200
[13 empty] | 0 |  | 0%
09 | F | 20mm thick polished Crystal White, average of 109mm width border. | 0.45 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 1098 | 0 | 100% | 0% | 100% | 1098 | 0 | 1098
[13 empty] | 0 |  | 0%
09 | G | 7 x 5mm Brass strip insert in brushed finish. | 3.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 182.4 | 912 |  | 80% | 20% | 100% | 729.6 | 182.4 | 912
[13 empty] | 0 |  | 0%
09 | H | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | J | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 6.5 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 975 | 4875 | 0 | 100% | 0% | 100% | 4875 | 0 | 4875
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | K | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 10.3 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 1380.2 | 6901 | 0 | 100% | 0% | 100% | 6901 | 0 | 6901
[13 empty] | 0 |  | 0%
09 | Add | Supply and installation of 20mm thick polished Volakas, to be fixed with standard cementitious adhesive maximum up to 5mm thick (HTL-ST-03) | 9.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 29987 | 0 | 100% | 0% | 100% | 29987 | 0 | 29987
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | L | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 6280 | 31400 | 0 | 100% | 0% | 100% | 31400 | 0 | 31400
[13 empty] | 0 |  | 0%
09 | M | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 600 | 3000 | 0 | 100% | 0% | 100% | 3000 | 0 | 3000
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2229.4 | 11147 | 0 | 100% | 0% | 100% | 11147 | 0 | 11147
[13 empty] | 0 |  | 0%
09 | B | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.3 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 402.6 | 2013 | 0 | 100% | 0% | 100% | 2013 | 0 | 2013
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | C | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 6110 | 0 | 100% | 0% | 100% | 4888 | 1222 | 6110
[13 empty] | 0 |  | 0%
09 | D | Foyer : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 5370 | 0 | 60% | 0% | 60% | 1074 | 2148 | 3222
[13 empty] | 0 |  | 0%
09 | E | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 5435 | 0 | 80% | 0% | 80% | 4348 | 0 | 4348
[13 empty] | 0 |  | 0%
09 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | G | Base Floor @ Entrance Closet : Supply and installation of 20mm thick polished Crystal White size of 675 x 730mm length. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 233 | 118 | 351 | 351 | 1755 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | H | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 262 | 134 | 396 | 396 | 1980 | 0 | 100% | 0% | 100% | 1980 | 0 | 1980
[13 empty] | 0 |  | 0%
09 | J | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 8365 | 0 | 100% | 0% | 100% | 8365 | 0 | 8365
[13 empty] | 0 |  | 0%
09 | Add | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 118 | 59 | 177 | 177 | 885 | 0 | 100% | 0% | 100% | 885 | 0 | 885
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | A | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2175 | 0 | 100% | 0% | 100% | 2175 | 0 | 2175
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 5 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 10395 | 0 | 100% | 0% | 100% | 10395 | 0 | 10395
[13 empty] | 0 |  | 0%
09 | C | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 372 | 182 | 554 | 1108 | 5540 | 0 | 100% | 0% | 100% | 5540 | 0 | 5540
[13 empty] | 0 |  | 0%
09 | D | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 43 | 19 | 62 | 124 | 620 | 0 | 100% | 0% | 100% | 620 | 0 | 620
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | E | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 5 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 4720 | 0.5 | 70% | 10% | 80% | 1888 | 1888 | 3776
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 492 | 240 | 732 | 732 | 3660 | 0 | 100% | 0% | 100% | 3660 | 0 | 3660
[13 empty] | 0 |  | 0%
09 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1275mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 303 | 129 | 432 | 432 | 2160 | 0 | 100% | 0% | 100% | 2160 | 0 | 2160
[13 empty] | 0 |  | 0%
09 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 | A | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 260mm W x 970mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 118 | 60 | 178 | 178 | 890 | 0 | 100% | 0% | 100% | 890 | 0 | 890
[13 empty] | 0 |  | 0%
09 | B | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
09 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 101 | M2 | 5 |  |  | 0 | 8 | 8 | 808 | 4040 |  | 96.25% | 1.604% | 97.85% | 3818.3319 | 134.8381 | 3953.17
[13 empty] | 0 |  | 0%
09 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 52 | M2 | 5 |  |  | 0 | 8 | 8 | 416 | 2080 |  | 96.25% | 1.604% | 97.85% | 1965.8739 | 69.4216 | 2035.2955
[13 empty] | 0 |  | 0%
09 |  | Total Amount for TYPE -6A | [10 empty] | 0 |  | 0% |  | 266730.8058 | 9419.1597 | 276149.9655
[13 empty] | 0 |  | 0%
10 |  | TYPE -8A (5 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thick stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1500 | 7500 | 0 | 100% | 0% | 100% | 7500 | 0 | 7500
[13 empty] | 0 |  | 0%
10 | B | 20mm thick polished Crystal White, maximum 147mm width border. | 1.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 756.4 | 3782 | 0 | 100% | 0% | 100% | 3782 | 0 | 3782
[13 empty] | 0 |  | 0%
10 | C | 7 x 5mm Brass strip insert in brushed finish. | 9.25 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 527.25 | 2636.25 |  | 100% | 0% | 100% | 2636.25 | 0 | 2636.25
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 10.8 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 4320 | 21600 | 0 | 100% | 0% | 100% | 21600 | 0 | 21600
[13 empty] | 0 |  | 0%
10 | E | 20mm thick polished Crystal White, cut to size. | 2.25 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1098 | 5490 | 0 | 100% | 0% | 100% | 5490 | 0 | 5490
[13 empty] | 0 |  | 0%
10 | F | 20mm thick polished Crystal White, average of 157mm width border. | 3.75 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1830 | 9150 | 0 | 100% | 0% | 100% | 9150 | 0 | 9150
[13 empty] | 0 |  | 0%
10 | G | 7 x 5mm Brass strip insert in brushed finish. | 22.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1299.6 | 6498 |  | 100% | 0% | 100% | 6498 | 0 | 6498
[13 empty] | 0 |  | 0%
10 | H | 7 x 5mm Brass strip insert in brushed finish. | 17.9 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1020.3 | 5101.5 |  | 100% | 0% | 100% | 5101.5 | 0 | 5101.5
[13 empty] | 0 |  | 0%
10 | J | Threshold (20mm thick polished Crystal White); 320mm wide x 1575mm length. | 1 | No | 5 | Crystal White | 20 | 227 | 94 | 321 | 321 | 1605 | 0 | 100% | 0% | 100% | 1605 | 0 | 1605
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 3500 | 0 | 100% | 0% | 100% | 3500 | 0 | 3500
[13 empty] | 0 |  | 0%
10 | L | 20mm thick polished Crystal White, average 117mm width border. | 0.7 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1708 | 0 | 100% | 0% | 100% | 1708 | 0 | 1708
[13 empty] | 0 |  | 0%
10 | M | 7 x 5mm Brass strip insert in brushed finish. | 5.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 296.4 | 1482 |  | 100% | 0% | 100% | 1482 | 0 | 1482
[13 empty] | 0 |  | 0%
10 | N | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 14.1 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 5640 | 28200 | 0 | 100% | 0% | 100% | 28200 | 0 | 28200
[13 empty] | 0 |  | 0%
10 | A | 20mm thick polished Crystal White, cut to size. | 2.75 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 6710 | 0 | 100% | 0% | 100% | 6710 | 0 | 6710
[13 empty] | 0 |  | 0%
10 | B | 20mm thick polished Crystal White, average of 137mm width border. | 3.35 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1634.8 | 8174 | 0 | 100% | 0% | 100% | 8174 | 0 | 8174
[13 empty] | 0 |  | 0%
10 | C | 7 x 5mm Brass strip insert in brushed finish. | 25.6 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1459.2 | 7296 |  | 100% | 0% | 100% | 7296 | 0 | 7296
[13 empty] | 0 |  | 0%
10 | D | 7 x 5mm Brass strip insert in brushed finish. | 6.5 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 370.5 | 1852.5 |  | 100% | 0% | 100% | 1852.5 | 0 | 1852.5
[13 empty] | 0 |  | 0%
10 | E | Threshold (20mm thick polished Crystal White); 270mm wide x 945mm length. | 2 | No | 5 | Crystal White | 20 | 122 | 48 | 170 | 340 | 1700 | 0 | 100% | 0% | 100% | 1700 | 0 | 1700
[13 empty] | 0 |  | 0%
10 | F | 7 x 5mm Brass strip insert in brushed finish. 950mm length (only the length between threshold and carpet, other locations are excluded) | 0.95 | Lm | 5 | Brass | 5 | 0 | 55 | 55 | 52.25 | 261.25 |  | 100% | 0% | 100% | 261.25 | 0 | 261.25
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.25 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3700 | 18500 | 0 | 100% | 0% | 100% | 18500 | 0 | 18500
[13 empty] | 0 |  | 0%
10 | H | 20mm thick polished Crystal White, average 163mm width border. | 2.6 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1268.8 | 6344 | 0 | 100% | 0% | 100% | 6344 | 0 | 6344
[13 empty] | 0 |  | 0%
10 | J | 7 x 5mm Brass strip insert in brushed finish. | 14.55 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 829.35 | 4146.75 |  | 100% | 0% | 100% | 4146.75 | 0 | 4146.75
[13 empty] | 0 |  | 0%
10 | K | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.45 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 980 | 4900 | 0 | 100% | 0% | 100% | 4900 | 0 | 4900
[13 empty] | 0 |  | 0%
10 | N | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.25 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3700 | 18500 | 0 | 100% | 0% | 100% | 18500 | 0 | 18500
[13 empty] | 0 |  | 0%
10 | Q | 20mm thick polished Crystal White, average of 131mm width border. | 2.6 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1268.8 | 6344 | 0 | 100% | 0% | 100% | 6344 | 0 | 6344
[13 empty] | 0 |  | 0%
10 | R | 7 x 5mm Brass strip insert in brushed finish. | 14.55 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 829.35 | 4146.75 |  | 100% | 0% | 100% | 4146.75 | 0 | 4146.75
[13 empty] | 0 |  | 0%
10 | A | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | B | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 48 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 7200 | 36000 | 0 | 100% | 0% | 100% | 36000 | 0 | 36000
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | C | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.35 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 716.9 | 3584.5 | 0 | 80% | 0% | 80% | 2867.6 | 0 | 2867.6
[13 empty] | 0 |  | 0%
10 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 9.55 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5997.4 | 29987 | 0 | 100% | 0% | 100% | 29987 | 0 | 29987
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | D | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 15 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 9420 | 47100 | 0 | 100% | 0% | 100% | 47100 | 0 | 47100
[13 empty] | 0 |  | 0%
10 | E | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.85 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 877.5 | 4387.5 | 0 | 100% | 0% | 100% | 4387.5 | 0 | 4387.5
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.15 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2606.2 | 13031 | 0 | 100% | 0% | 100% | 13031 | 0 | 13031
[13 empty] | 0 |  | 0%
10 | G | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.8 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 463.6 | 2318 | 0 | 100% | 0% | 100% | 2318 | 0 | 2318
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 10.05 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 6311.4 | 31557 | 0 | 100% | 0% | 100% | 31557 | 0 | 31557
[13 empty] | 0 |  | 0%
10 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.35 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 652.7 | 3263.5 | 0 | 100% | 0% | 100% | 3263.5 | 0 | 3263.5
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | A | Living : 320mm wide; total size of 1575 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 921 | 467 | 1388 | 1388 | 6940 | 0 | 100% | 0% | 100% | 6940 | 0 | 6940
[13 empty] | 0 |  | 0%
10 | B | Bedroom : 270mm wide; total size of 945 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 738 | 356 | 1094 | 2188 | 10940 | 0 | 100% | 0% | 100% | 10940 | 0 | 10940
[13 empty] | 0 |  | 0%
10 | C | Toilet @ Foyer : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 5395 | 0 | 100% | 0% | 100% | 5395 | 0 | 5395
[13 empty] | 0 |  | 0%
10 | D | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 5370 | 0 | 100% | 0% | 100% | 5370 | 0 | 5370
[13 empty] | 0 |  | 0%
10 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | F | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2175 | 0 | 100% | 0% | 100% | 2175 | 0 | 2175
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | G | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1880mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 1880mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround and shelf, elsewhere). | 1 | No | 5 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 10395 | 0 | 100% | 0% | 100% | 10395 | 0 | 10395
[13 empty] | 0 |  | 0%
10 | H | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 372 | 182 | 554 | 1108 | 5540 | 0 | 100% | 0% | 100% | 5540 | 0 | 5540
[13 empty] | 0 |  | 0%
10 | J | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 43 | 19 | 62 | 124 | 620 | 0 | 100% | 0% | 100% | 620 | 0 | 620
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | A | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 5 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 4720 | 0 | 100% | 0% | 100% | 4720 | 0 | 4720
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | B | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 215mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 588 | 287 | 875 | 875 | 4375 | 0 | 100% | 0% | 100% | 4375 | 0 | 4375
[13 empty] | 0 |  | 0%
10 | C | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1055mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 256 | 107 | 363 | 363 | 1815 | 0 | 100% | 0% | 100% | 1815 | 0 | 1815
[13 empty] | 0 |  | 0%
10 | D | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | E | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 112 | 55 | 167 | 167 | 835 | 0 | 100% | 0% | 100% | 835 | 0 | 835
[13 empty] | 0 |  | 0%
10 | F | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 | G | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1395mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 150 | 74 | 224 | 224 | 1120 | 0 | 100% | 0% | 100% | 1120 | 0 | 1120
[13 empty] | 0 |  | 0%
10 | H | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (955 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 5 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 5345 | 0 | 100% | 0% | 100% | 5345 | 0 | 5345
[13 empty] | 0 |  | 0%
10 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
10 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 188 | M2 | 5 |  |  | 0 | 8 | 8 | 1504 | 7520 |  | 99.84% | 0% | 99.84% | 7507.6792 | 0 | 7507.6792
[13 empty] | 0 |  | 0%
10 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 121 | M2 | 5 |  |  | 0 | 8 | 8 | 968 | 4840 |  | 99.84% | 0% | 99.84% | 4832.0702 | 0 | 4832.0702
[13 empty] | 0 |  | 0%
10 |  | Total Amount for TYPE -8A | [10 empty] | 0 |  | 0% |  | 449184.3494 | 0 | 449184.3494
[13 empty] | 0 |  | 0%
11 |  | TYPE -09A (2 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.8 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 720 | 1440 | 0 | 100% | 0% | 100% | 1440 | 0 | 1440
[13 empty] | 0 |  | 0%
11 | B | 20mm thick polished Crystal White, cut to size. | 1.8 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 878.4 | 1756.8 | 0 | 100% | 0% | 100% | 1756.8 | 0 | 1756.8
[13 empty] | 0 |  | 0%
11 | C | 20mm thick polished Crystal White, maximum 145mm width border | 1.4 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 683.2 | 1366.4 | 0 | 100% | 0% | 100% | 1366.4 | 0 | 1366.4
[13 empty] | 0 |  | 0%
11 | D | 7 x 5mm Brass strip insert in brushed finish. | 6.05 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 344.85 | 689.7 |  | 100% | 0% | 100% | 689.7 | 0 | 689.7
[13 empty] | 0 |  | 0%
11 | Add | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 2 | Crystal White | 20 | 123 | 48 | 171 | 171 | 342 | 0 | 100% | 0% | 100% | 342 | 0 | 342
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 7.35 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 2940 | 5880 | 0 | 100% | 0% | 100% | 5880 | 0 | 5880
[13 empty] | 0 |  | 0%
11 | F | 20mm thick polished Crystal White, cut to size. | 2.85 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1390.8 | 2781.6 | 0 | 100% | 0% | 100% | 2781.6 | 0 | 2781.6
[13 empty] | 0 |  | 0%
11 | G | 20mm thick polished Crystal White, average of 160mm width border. | 3.05 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1488.4 | 2976.8 | 0 | 100% | 0% | 100% | 2976.8 | 0 | 2976.8
[13 empty] | 0 |  | 0%
11 | H | 7 x 5mm Brass strip insert in brushed finish. | 17.7 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 1008.9 | 2017.8 |  | 100% | 0% | 100% | 2017.8 | 0 | 2017.8
[13 empty] | 0 |  | 0%
11 | J | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 627 | 1254 |  | 100% | 0% | 100% | 1254 | 0 | 1254
[13 empty] | 0 |  | 0%
11 | K | Threshold (20mm thick polished Crystal White); 270mm wide x 940mm length. | 1 | No | 2 | Crystal White | 20 | 119 | 46 | 165 | 165 | 330 | 0 | 100% | 0% | 100% | 330 | 0 | 330
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.95 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 380 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
[13 empty] | 0 |  | 0%
11 | M | 20mm thick polished Crystal White, average 119mm width border. | 0.5 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 244 | 488 | 0 | 100% | 0% | 100% | 488 | 0 | 488
[13 empty] | 0 |  | 0%
11 | N | 7 x 5mm Brass strip insert in brushed finish. | 4.1 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 233.7 | 467.4 |  | 100% | 0% | 100% | 467.4 | 0 | 467.4
[13 empty] | 0 |  | 0%
11 | P | Threshold (20mm thick); 270mm wide x 860mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 109 | 43 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.25 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 1700 | 3400 | 0 | 100% | 0% | 100% | 3400 | 0 | 3400
[13 empty] | 0 |  | 0%
11 | A | 20mm thick polished Crystal White, cut to size. | 1.2 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 585.6 | 1171.2 | 0 | 100% | 0% | 100% | 1171.2 | 0 | 1171.2
[13 empty] | 0 |  | 0%
11 | B | 20mm thick polished Crystal White, average of 141mm width border. | 2.1 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1024.8 | 2049.6 | 0 | 100% | 0% | 100% | 2049.6 | 0 | 2049.6
[13 empty] | 0 |  | 0%
11 | C | 7 x 5mm Brass strip insert in brushed finish. | 14 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 798 | 1596 |  | 100% | 0% | 100% | 1596 | 0 | 1596
[13 empty] | 0 |  | 0%
11 | D | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 627 | 1254 |  | 100% | 0% | 100% | 1254 | 0 | 1254
[13 empty] | 0 |  | 0%
11 | E | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 2 | Crystal White | 20 | 155 | 62 | 217 | 217 | 434 | 0 | 100% | 0% | 100% | 434 | 0 | 434
[13 empty] | 0 |  | 0%
11 | F | Threshold (20mm thick polished Crystal White); 320mm wide x 750mm length. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
11 | G | 7 x 5mm Brass strip insert in brushed finish. 750mm length (only the length between threshold and carpet, other locations are excluded) | 1.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 85.5 | 171 |  | 100% | 0% | 100% | 171 | 0 | 171
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | H | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.35 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 1740 | 3480 | 0 | 100% | 0% | 100% | 3480 | 0 | 3480
[13 empty] | 0 |  | 0%
11 | J | 20mm thick polished Crystal White, average 153mm width border. | 1.5 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 732 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
[13 empty] | 0 |  | 0%
11 | K | 7 x 5mm Brass strip insert in brushed finish. | 10.2 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 581.4 | 1162.8 |  | 100% | 0% | 100% | 1162.8 | 0 | 1162.8
[13 empty] | 0 |  | 0%
11 | L | Threshold (20mm thick); 320mm wide x 750mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.6 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 1280 | 0 | 100% | 0% | 100% | 1280 | 0 | 1280
[13 empty] | 0 |  | 0%
11 | P | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.95 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 380 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
[13 empty] | 0 |  | 0%
11 | R | 20mm thick polished Crystal White, average of 111mm width border. | 0.6 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 292.8 | 585.6 | 0 | 100% | 0% | 100% | 585.6 | 0 | 585.6
[13 empty] | 0 |  | 0%
11 | A | 7 x 5mm Brass strip insert in brushed finish. | 4.1 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 233.7 | 467.4 |  | 100% | 0% | 100% | 467.4 | 0 | 467.4
[13 empty] | 0 |  | 0%
11 | B | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | C | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 38 | M2 | 2 | PC Rate | 20 | 50 | 100 | 150 | 5700 | 11400 | 0 | 100% | 0% | 100% | 11400 | 0 | 11400
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | D | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 16 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 10048 | 20096 | 0 | 100% | 0% | 100% | 20096 | 0 | 20096
[13 empty] | 0 |  | 0%
11 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9.4 | Lm | 2 | Crystal White | 20 | 86 | 48 | 134 | 1259.6 | 2519.2 | 0 | 100% | 0% | 100% | 2519.2 | 0 | 2519.2
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.8 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 6782.4 | 13564.8 | 0 | 100% | 0% | 100% | 13564.8 | 0 | 13564.8
[13 empty] | 0 |  | 0%
11 | G | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 2 | Crystal White | 20 | 94 | 56 | 150 | 675 | 1350 | 0 | 100% | 0% | 100% | 1350 | 0 | 1350
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.6 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 2888.8 | 5777.6 | 0 | 100% | 0% | 100% | 5777.6 | 0 | 5777.6
[13 empty] | 0 |  | 0%
11 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.2 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 512.4 | 1024.8 | 0 | 100% | 0% | 100% | 1024.8 | 0 | 1024.8
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.15 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 3862.2 | 7724.4 | 0 | 100% | 0% | 100% | 7724.4 | 0 | 7724.4
[13 empty] | 0 |  | 0%
11 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.65 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 689.3 | 1378.6 | 0 | 100% | 0% | 100% | 1378.6 | 0 | 1378.6
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | B | Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 2444 | 0 | 100% | 0% | 100% | 2444 | 0 | 2444
[13 empty] | 0 |  | 0%
11 | C | Living : 270mm wide; total size of 945 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 737 | 356 | 1093 | 1093 | 2186 | 0 | 100% | 0% | 100% | 2186 | 0 | 2186
[13 empty] | 0 |  | 0%
11 | D | Toilet @ Foyer : (110 + 110)mm wide); total size of 860 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 634 | 286 | 920 | 920 | 1840 | 0 | 100% | 0% | 100% | 1840 | 0 | 1840
[13 empty] | 0 |  | 0%
11 | E | Bathroom : (135 + 135)mm wide); total size of 750 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 710 | 343 | 1053 | 2106 | 4212 | 0 | 100% | 0% | 100% | 4212 | 0 | 4212
[13 empty] | 0 |  | 0%
11 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 3856 | 0 | 100% | 0% | 100% | 3856 | 0 | 3856
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | G | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 262 | 134 | 396 | 396 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
[13 empty] | 0 |  | 0%
11 | H | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 3346 | 0 | 100% | 0% | 100% | 3346 | 0 | 3346
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | J | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1305mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 364 | 195 | 559 | 559 | 1118 | 0 | 100% | 0% | 100% | 1118 | 0 | 1118
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2315mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 2315mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1740 | 808 | 2548 | 2548 | 5096 | 0 | 100% | 0% | 100% | 5096 | 0 | 5096
[13 empty] | 0 |  | 0%
11 | Add | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 372 | 182 | 554 | 1108 | 2216 | 0 | 100% | 0% | 100% | 2216 | 0 | 2216
[13 empty] | 0 |  | 0%
11 | Add | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 43 | 19 | 62 | 124 | 248 | 0 | 100% | 0% | 100% | 248 | 0 | 248
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | B | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 2 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 2504 | 0 | 100% | 0% | 100% | 2504 | 0 | 2504
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | C | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 492 | 240 | 732 | 732 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
[13 empty] | 0 |  | 0%
11 | D | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 950mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 230 | 95 | 325 | 325 | 650 | 0 | 100% | 0% | 100% | 650 | 0 | 650
[13 empty] | 0 |  | 0%
11 | E | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 44 | 12 | 56 | 112 | 224 | 0 | 100% | 0% | 100% | 224 | 0 | 224
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 112 | 55 | 167 | 167 | 334 | 0 | 100% | 0% | 100% | 334 | 0 | 334
[13 empty] | 0 |  | 0%
11 | G | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 102 | 50 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
11 | A | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (150 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 2 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 2138 | 0 | 100% | 0% | 100% | 2138 | 0 | 2138
[13 empty] | 0 |  | 0%
11 | B | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
11 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 145 | M2 | 2 |  |  | 0 | 8 | 8 | 1160 | 2320 |  | 100% | 0% | 100% | 2320 | 0 | 2320
[13 empty] | 0 |  | 0%
11 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 76 | M2 | 2 |  |  | 0 | 8 | 8 | 608 | 1216 |  | 100% | 0% | 100% | 1216 | 0 | 1216
[13 empty] | 0 |  | 0%
11 |  | Total Amount for TYPE -9A | [10 empty] | 0 |  | 0% |  | 146745.5 | 0 | 146745.5
[13 empty] | 0 |  | 0%
12 |  | TYPE -09B (2 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.75 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 1400 | 0 | 100% | 0% | 100% | 1400 | 0 | 1400
[13 empty] | 0 |  | 0%
12 | B | 20mm thick polished Crystal White, cut to size. | 0.55 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 536.8 | 0 | 100% | 0% | 100% | 536.8 | 0 | 536.8
[13 empty] | 0 |  | 0%
12 | C | 20mm thick polished Crystal White, maximum 141mm width border. | 1 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 488 | 976 | 0 | 100% | 0% | 100% | 976 | 0 | 976
[13 empty] | 0 |  | 0%
12 | D | 7 x 5mm Brass strip insert in brushed finish. | 5.9 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 336.3 | 672.6 |  | 100% | 0% | 100% | 672.6 | 0 | 672.6
[13 empty] | 0 |  | 0%
12 | Add | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 2 | Crystal White | 20 | 123 | 48 | 171 | 171 | 342 | 0 | 100% | 0% | 100% | 342 | 0 | 342
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 6.7 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 2680 | 5360 | 0 | 100% | 0% | 100% | 5360 | 0 | 5360
[13 empty] | 0 |  | 0%
12 | F | 20mm thick polished Crystal White, cut to size. | 3.05 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1488.4 | 2976.8 | 0 | 100% | 0% | 100% | 2976.8 | 0 | 2976.8
[13 empty] | 0 |  | 0%
12 | G | 20mm thick polished Crystal White, average of 150mm width border. | 2.75 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 1342 | 2684 | 0 | 100% | 0% | 100% | 2684 | 0 | 2684
[13 empty] | 0 |  | 0%
12 | H | 7 x 5mm Brass strip insert in brushed finish. | 16.8 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 957.6 | 1915.2 |  | 100% | 0% | 100% | 1915.2 | 0 | 1915.2
[13 empty] | 0 |  | 0%
12 | J | 7 x 5mm Brass strip insert in brushed finish. | 10.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 598.5 | 1197 |  | 100% | 0% | 100% | 1197 | 0 | 1197
[13 empty] | 0 |  | 0%
12 | K | Threshold (20mm thick polished Crystal White); 270mm wide x 860mm length. | 1 | No | 2 | Crystal White | 20 | 109 | 43 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.85 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 340 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
12 | M | 20mm thick polished Crystal White, average 116mm width border. | 0.7 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 683.2 | 0 | 100% | 0% | 100% | 683.2 | 0 | 683.2
[13 empty] | 0 |  | 0%
12 | N | 7 x 5mm Brass strip insert in brushed finish. | 3.65 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 208.05 | 416.1 |  | 100% | 0% | 100% | 416.1 | 0 | 416.1
[13 empty] | 0 |  | 0%
12 | P | Threshold (20mm thick); 270mm wide x 750mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 95 | 37 | 132 | 132 | 264 | 0 | 100% | 0% | 100% | 264 | 0 | 264
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 3.95 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 1580 | 3160 | 0 | 100% | 0% | 100% | 3160 | 0 | 3160
[13 empty] | 0 |  | 0%
12 | B | 20mm thick polished Crystal White, cut to size. | 1.15 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 561.2 | 1122.4 | 0 | 100% | 0% | 100% | 1122.4 | 0 | 1122.4
[13 empty] | 0 |  | 0%
12 | C | 20mm thick polished Crystal White, average of 141mm width border. | 1.95 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 951.6 | 1903.2 | 0 | 100% | 0% | 100% | 1903.2 | 0 | 1903.2
[13 empty] | 0 |  | 0%
12 | D | 7 x 5mm Brass strip insert in brushed finish. | 13.05 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 743.85 | 1487.7 |  | 100% | 0% | 100% | 1487.7 | 0 | 1487.7
[13 empty] | 0 |  | 0%
12 | E | 7 x 5mm Brass strip insert in brushed finish. | 10.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 598.5 | 1197 |  | 100% | 0% | 100% | 1197 | 0 | 1197
[13 empty] | 0 |  | 0%
12 | F | Threshold (20mm thick polished Crystal White); 300mm wide x 925mm length. | 1 | No | 2 | Crystal White | 20 | 128 | 51 | 179 | 179 | 358 | 0 | 100% | 0% | 100% | 358 | 0 | 358
[13 empty] | 0 |  | 0%
12 | G | Threshold (20mm thick polished Crystal White); 320mm wide x 750mm length. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
12 | H | 7 x 5mm Brass strip insert in brushed finish. 750mm length (only the length between threshold and carpet, other locations are excluded) | 1.5 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 85.5 | 171 |  | 100% | 0% | 100% | 171 | 0 | 171
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 5.4 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 2160 | 4320 | 0 | 100% | 0% | 100% | 4320 | 0 | 4320
[13 empty] | 0 |  | 0%
12 | K | 20mm thick polished Crystal White, average 153mm width border. | 1.85 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 902.8 | 1805.6 | 0 | 100% | 0% | 100% | 1805.6 | 0 | 1805.6
[13 empty] | 0 |  | 0%
12 | L | 7 x 5mm Brass strip insert in brushed finish. | 11.2 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 638.4 | 1276.8 |  | 100% | 0% | 100% | 1276.8 | 0 | 1276.8
[13 empty] | 0 |  | 0%
12 | M | Threshold (20mm thick); 320mm wide x 750mm length polished Crystal White. | 1 | No | 2 | Crystal White | 20 | 108 | 44 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | P | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.6 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 1280 | 0 | 100% | 0% | 100% | 1280 | 0 | 1280
[13 empty] | 0 |  | 0%
12 | Q | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 2 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 640 | 0 | 100% | 0% | 100% | 640 | 0 | 640
[13 empty] | 0 |  | 0%
12 | B | 20mm thick polished Crystal White, average of 110mm width border; 4545mm length. | 0.5 | M2 | 2 | Crystal White | 20 | 282 | 206 | 488 | 244 | 488 | 0 | 100% | 0% | 100% | 488 | 0 | 488
[13 empty] | 0 |  | 0%
12 | C | 7 x 5mm Brass strip insert in brushed finish. | 3.65 | Lm | 2 | Brass | 5 | 0 | 57 | 57 | 208.05 | 416.1 |  | 100% | 0% | 100% | 416.1 | 0 | 416.1
[13 empty] | 0 |  | 0%
12 | D | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 2 | Crystal White | 20 | 99 | 37 | 136 | 136 | 272 | 0 | 100% | 0% | 100% | 272 | 0 | 272
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | E | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 49 | M2 | 2 | PC Rate | 20 | 50 | 100 | 150 | 7350 | 14700 | 0 | 100% | 0% | 100% | 14700 | 0 | 14700
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | F | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.9 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 9357.2 | 18714.4 | 0 | 100% | 0% | 100% | 18714.4 | 0 | 18714.4
[13 empty] | 0 |  | 0%
12 | G | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 10.3 | Lm | 2 | Crystal White | 20 | 86 | 48 | 134 | 1380.2 | 2760.4 | 0 | 100% | 0% | 100% | 2760.4 | 0 | 2760.4
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.55 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 6625.4 | 13250.8 | 0 | 100% | 0% | 100% | 13250.8 | 0 | 13250.8
[13 empty] | 0 |  | 0%
12 | J | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.4 | Lm | 2 | Crystal White | 20 | 94 | 56 | 150 | 660 | 1320 | 0 | 100% | 0% | 100% | 1320 | 0 | 1320
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.1 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 2574.8 | 5149.6 | 0 | 100% | 0% | 100% | 5149.6 | 0 | 5149.6
[13 empty] | 0 |  | 0%
12 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.75 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 457.5 | 915 | 0 | 100% | 0% | 100% | 915 | 0 | 915
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | B | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 5.8 | M2 | 2 | Volakas | 20 | 406 | 222 | 628 | 3642.4 | 7284.8 | 0 | 100% | 0% | 100% | 7284.8 | 0 | 7284.8
[13 empty] | 0 |  | 0%
12 | C | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.3 | Lm | 2 | Crystal White | 20 | 79 | 43 | 122 | 646.6 | 1293.2 | 0 | 100% | 0% | 100% | 1293.2 | 0 | 1293.2
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | D | Living : 270mm wide; total size of 860 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 2148 | 0 | 100% | 0% | 100% | 2148 | 0 | 2148
[13 empty] | 0 |  | 0%
12 | E | Bedroom : 270mm wide; total size of 925 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 2174 | 0 | 100% | 0% | 100% | 2174 | 0 | 2174
[13 empty] | 0 |  | 0%
12 | F | Toilet @ Foyer : (110 + 110)mm wide); total size of 860 x 2430mm high. | 1 | No | 2 | Crystal White | 20 | 634 | 286 | 920 | 920 | 1840 | 0 | 100% | 0% | 100% | 1840 | 0 | 1840
[13 empty] | 0 |  | 0%
12 | G | Bathroom : (135 + 135)mm wide); total size of 750 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 710 | 343 | 1053 | 2106 | 4212 | 0 | 100% | 0% | 100% | 4212 | 0 | 4212
[13 empty] | 0 |  | 0%
12 | Add | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 2 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 3856 | 0 | 100% | 0% | 100% | 3856 | 0 | 3856
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Living | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | J | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 910mm length, mitered with 40mm high fascia, (1225mm high cladding to 3 sides, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 262 | 134 | 396 | 396 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
[13 empty] | 0 |  | 0%
12 | K | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (575 + 910 + 575)mm length at 1225mm high cladding to 3 sides. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1074 | 599 | 1673 | 1673 | 3346 | 0 | 100% | 0% | 100% | 3346 | 0 | 3346
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | A | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1305mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Crystal White | 20 | 364 | 195 | 559 | 559 | 1118 | 0 | 100% | 0% | 100% | 1118 | 0 | 1118
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2055mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 2055mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 1576 | 718 | 2294 | 2294 | 4588 | 0 | 100% | 0% | 100% | 4588 | 0 | 4588
[13 empty] | 0 |  | 0%
12 | Add | Niche Surround @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 480 wide x 700mm high. (vanity counter, shelf and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 372 | 182 | 554 | 1108 | 2216 | 0 | 100% | 0% | 100% | 2216 | 0 | 2216
[13 empty] | 0 |  | 0%
12 | Add | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 380mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 43 | 19 | 62 | 124 | 248 | 0 | 100% | 0% | 100% | 248 | 0 | 248
[13 empty] | 0 |  | 0%
|  | Sanitaryware - Stone Works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | C | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 2 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 2504 | 0 | 100% | 0% | 100% | 2504 | 0 | 2504
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | D | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 492 | 240 | 732 | 732 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
[13 empty] | 0 |  | 0%
12 | E | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1035mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 2 | Volakas | 20 | 251 | 105 | 356 | 356 | 712 | 0 | 100% | 0% | 100% | 712 | 0 | 712
[13 empty] | 0 |  | 0%
12 | F | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 2 | Volakas | 20 | 44 | 12 | 56 | 112 | 224 | 0 | 100% | 0% | 100% | 224 | 0 | 224
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | G | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 102 | 50 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
12 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 | A | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 2 | Volakas | 20 | 102 | 50 | 152 | 152 | 304 | 0 | 100% | 0% | 100% | 304 | 0 | 304
[13 empty] | 0 |  | 0%
12 | B | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (150 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 2 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 2138 | 0 | 100% | 0% | 100% | 2138 | 0 | 2138
[13 empty] | 0 |  | 0%
12 | C | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 2 | Volakas | 20 | 25 | 5 | 30 | 30 | 60 | 0 | 100% | 0% | 100% | 60 | 0 | 60
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
12 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 151 | M2 | 2 |  |  | 0 | 8 | 8 | 1208 | 2416 |  | 100% | 0% | 100% | 2416 | 0 | 2416
[13 empty] | 0 |  | 0%
12 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 85 | M2 | 2 |  |  | 0 | 8 | 8 | 680 | 1360 |  | 100% | 0% | 100% | 1360 | 0 | 1360
[13 empty] | 0 |  | 0%
12 |  | Total Amount for TYPE -9B | [10 empty] | 0 |  | 0% |  | 144657.7 | 0 | 144657.7
[13 empty] | 0 |  | 0%
13 |  | TYPE -10A (5 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.15 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 860 | 4300 | 0 | 100% | 0% | 100% | 4300 | 0 | 4300
[13 empty] | 0 |  | 0%
13 | B | 20mm thick polished Crystal White, maximum 135mm width border. | 0.65 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 317.2 | 1586 | 0 | 100% | 0% | 100% | 1586 | 0 | 1586
[13 empty] | 0 |  | 0%
13 | C | 7 x 5mm Brass strip insert in brushed finish. | 5.9 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 336.3 | 1681.5 |  | 100% | 0% | 100% | 1681.5 | 0 | 1681.5
[13 empty] | 0 |  | 0%
13 | Add | Threshold (20mm thick polished Crystal White); 270mm wide x 980mm length | 1 | No | 5 | Crystal White | 20 | 123 | 48 | 171 | 171 | 855 | 0 | 100% | 0% | 100% | 855 | 0 | 855
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 20.15 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 8060 | 40300 | 0 | 100% | 0% | 100% | 40300 | 0 | 40300
[13 empty] | 0 |  | 0%
13 | E | 20mm thick polished Crystal White, cut to size. | 20.15 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 9833.2 | 49166 | 0 | 100% | 0% | 100% | 49166 | 0 | 49166
[13 empty] | 0 |  | 0%
13 | F | 20mm thick polished Crystal White, average of 148mm width border. | 3.35 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1634.8 | 8174 | 0 | 100% | 0% | 100% | 8174 | 0 | 8174
[13 empty] | 0 |  | 0%
13 | G | 7 x 5mm Brass strip insert in brushed finish. | 21.35 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1216.95 | 6084.75 |  | 100% | 0% | 100% | 6084.75 | 0 | 6084.75
[13 empty] | 0 |  | 0%
13 | H | Threshold (20mm thick polished Crystal White); 300mm wide x 1490mm length. | 1 | No | 5 | Crystal White | 20 | 204 | 82 | 286 | 286 | 1430 | 0 | 100% | 0% | 100% | 1430 | 0 | 1430
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.85 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 340 | 1700 | 0 | 100% | 0% | 100% | 1700 | 0 | 1700
[13 empty] | 0 |  | 0%
13 | K | 20mm thick polished Crystal White, average 110mm width border. | 0.45 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 1098 | 0 | 100% | 0% | 100% | 1098 | 0 | 1098
[13 empty] | 0 |  | 0%
13 | L | 7 x 5mm Brass strip insert in brushed finish. | 3.75 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 213.75 | 1068.75 |  | 100% | 0% | 100% | 1068.75 | 0 | 1068.75
[13 empty] | 0 |  | 0%
13 | M | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 4.6 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1840 | 9200 | 0 | 100% | 0% | 100% | 9200 | 0 | 9200
[13 empty] | 0 |  | 0%
13 | P | 20mm thick polished Crystal White, cut to size. | 2.85 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1390.8 | 6954 | 0 | 100% | 0% | 100% | 6954 | 0 | 6954
[13 empty] | 0 |  | 0%
13 | A | 20mm thick polished Crystal White, average of 139mm width border. | 3.3 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1610.4 | 8052 | 0 | 100% | 0% | 100% | 8052 | 0 | 8052
[13 empty] | 0 |  | 0%
13 | B | 7 x 5mm Brass strip insert in brushed finish. | 14.25 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 812.25 | 4061.25 |  | 100% | 0% | 100% | 4061.25 | 0 | 4061.25
[13 empty] | 0 |  | 0%
13 | C | 7 x 5mm Brass strip insert in brushed finish. | 11.15 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 635.55 | 3177.75 |  | 100% | 0% | 100% | 3177.75 | 0 | 3177.75
[13 empty] | 0 |  | 0%
13 | D | Threshold (20mm thick polished Crystal White); 320mm wide x 945mm length. | 0.9 | Lm | 5 | Crystal White | 20 | 135 | 55 | 190 | 171 | 855 | 0 | 100% | 0% | 100% | 855 | 0 | 855
[13 empty] | 0 |  | 0%
13 | E | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 0.9 | Lm | 5 | Crystal White | 20 | 125 | 51 | 176 | 158.4 | 792 | 0 | 100% | 0% | 100% | 792 | 0 | 792
[13 empty] | 0 |  | 0%
13 | F | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 1.72 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 98.04 | 490.2 |  | 100% | 0% | 100% | 490.2 | 0 | 490.2
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.8 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 1520 | 7600 | 0 | 100% | 0% | 100% | 7600 | 0 | 7600
[13 empty] | 0 |  | 0%
13 | H | 20mm thick polished Crystal White, average 153mm width border. | 1.45 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 707.6 | 3538 | 0 | 100% | 0% | 100% | 3538 | 0 | 3538
[13 empty] | 0 |  | 0%
13 | J | 7 x 5mm Brass strip insert in brushed finish. | 10.05 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 572.85 | 2864.25 |  | 100% | 0% | 100% | 2864.25 | 0 | 2864.25
[13 empty] | 0 |  | 0%
13 | K | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1.6 | Lm | 5 | Crystal White | 20 | 125 | 51 | 176 | 281.6 | 1408 | 0 | 100% | 0% | 100% | 1408 | 0 | 1408
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.45 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 580 | 2900 | 0 | 100% | 0% | 100% | 2900 | 0 | 2900
[13 empty] | 0 |  | 0%
13 | N | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Powder Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 3500 | 0 | 100% | 0% | 100% | 3500 | 0 | 3500
[13 empty] | 0 |  | 0%
13 | Q | 20mm thick polished Crystal White, average of 116mm width border. | 0.65 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 317.2 | 1586 | 0 | 100% | 0% | 100% | 1586 | 0 | 1586
[13 empty] | 0 |  | 0%
13 | R | 7 x 5mm Brass strip insert in brushed finish. | 5.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 330.6 | 1653 |  | 100% | 0% | 100% | 1653 | 0 | 1653
[13 empty] | 0 |  | 0%
13 | S | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | A | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 6.1 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 915 | 4575 | 0 | 100% | 0% | 100% | 4575 | 0 | 4575
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | B | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 16.4 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 10299.2 | 51496 | 0 | 100% | 0% | 100% | 51496 | 0 | 51496
[13 empty] | 0 |  | 0%
13 | C | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 8.9 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 1192.6 | 5963 | 0 | 100% | 0% | 100% | 5963 | 0 | 5963
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | D | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 9.05 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 5683.4 | 28417 | 0 | 100% | 0% | 100% | 28417 | 0 | 28417
[13 empty] | 0 |  | 0%
13 | E | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.95 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 592.5 | 2962.5 | 0 | 100% | 0% | 100% | 2962.5 | 0 | 2962.5
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.05 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 2543.4 | 12717 | 0 | 100% | 0% | 100% | 12717 | 0 | 12717
[13 empty] | 0 |  | 0%
13 | G | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.75 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 457.5 | 2287.5 | 0 | 100% | 0% | 100% | 2287.5 | 0 | 2287.5
[13 empty] | 0 |  | 0%
|  | Powder Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.3 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 3956.4 | 19782 | 0 | 100% | 0% | 100% | 19782 | 0 | 19782
[13 empty] | 0 |  | 0%
13 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.8 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 707.6 | 3538 | 0 | 100% | 0% | 100% | 3538 | 0 | 3538
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | A | Living : 300mm wide; total size of 1490 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 868 | 433 | 1301 | 1301 | 6505 | 0 | 100% | 0% | 100% | 6505 | 0 | 6505
[13 empty] | 0 |  | 0%
13 | B | Bedroom : 320mm wide; total size of 945 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 831 | 421 | 1252 | 1252 | 6260 | 0 | 100% | 0% | 100% | 6260 | 0 | 6260
[13 empty] | 0 |  | 0%
13 | C | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 964 | 4820 | 0 | 100% | 0% | 100% | 4820 | 0 | 4820
[13 empty] | 0 |  | 0%
13 | D | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 724 | 350 | 1074 | 2148 | 10740 | 0 | 100% | 0% | 100% | 10740 | 0 | 10740
[13 empty] | 0 |  | 0%
13 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 9640 | 0 | 100% | 0% | 100% | 9640 | 0 | 9640
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | F | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1400mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Crystal White | 20 | 388 | 209 | 597 | 597 | 2985 | 0 | 100% | 0% | 100% | 2985 | 0 | 2985
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | G | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2055mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 2055mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 1576 | 718 | 2294 | 2294 | 11470 | 0 | 100% | 0% | 100% | 11470 | 0 | 11470
[13 empty] | 0 |  | 0%
|  | Sanitaryware - Stoneworks | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | H | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 5 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 6260 | 0 | 100% | 0% | 100% | 6260 | 0 | 6260
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | J | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 305mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 717 | 350 | 1067 | 1067 | 5335 | 0 | 100% | 0% | 100% | 5335 | 0 | 5335
[13 empty] | 0 |  | 0%
13 | K | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1205mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 287 | 122 | 409 | 409 | 2045 | 0 | 100% | 0% | 100% | 2045 | 0 | 2045
[13 empty] | 0 |  | 0%
13 | A | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | B | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 910mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 97 | 48 | 145 | 145 | 725 | 0 | 100% | 0% | 100% | 725 | 0 | 725
[13 empty] | 0 |  | 0%
13 | C | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1065mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 116 | 57 | 173 | 173 | 865 | 0 | 100% | 0% | 100% | 865 | 0 | 865
[13 empty] | 0 |  | 0%
13 | E | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (900 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 5 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 5345 | 0 | 100% | 0% | 100% | 5345 | 0 | 5345
[13 empty] | 0 |  | 0%
13 | F | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
13 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 140 | M2 | 5 |  |  | 0 | 8 | 8 | 1120 | 5600 |  | 100% | 0% | 100% | 5600 | 0 | 5600
[13 empty] | 0 |  | 0%
13 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 77 | M2 | 5 |  |  | 0 | 8 | 8 | 616 | 3080 |  | 100% | 0% | 100% | 3080 | 0 | 3080
[13 empty] | 0 |  | 0%
13 |  | Total Amount for TYPE -10A | [10 empty] | 0 |  | 0% |  | 392388.45 | 0 | 392388.45
[13 empty] | 0 |  | 0%
14 |  | TYPE -10B (3 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.25 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1300 | 3900 | 0 | 100% | 0% | 100% | 3900 | 0 | 3900
[13 empty] | 0 |  | 0%
14 | B | 20mm thick polished Crystal White, maximum 130mm width border. | 1.25 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 610 | 1830 | 0 | 100% | 0% | 100% | 1830 | 0 | 1830
[13 empty] | 0 |  | 0%
14 | C | 7 x 5mm Brass strip insert in brushed finish. | 8.55 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 487.35 | 1462.05 |  | 100% | 0% | 100% | 1462.05 | 0 | 1462.05
[13 empty] | 0 |  | 0%
14 | D | Threshold (20mm thick); 175mm wide x 1100mm length polished Crystal White | 1 | No | 3 | Crystal White | 20 | 106 | 35 | 141 | 141 | 423 | 0 | 100% | 0% | 100% | 423 | 0 | 423
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 27.2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 10880 | 32640 | 0 | 100% | 0% | 100% | 32640 | 0 | 32640
[13 empty] | 0 |  | 0%
14 | F | 20mm thick polished Crystal White, cut to size. | 4.5 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 2196 | 6588 | 0 | 100% | 0% | 100% | 6588 | 0 | 6588
[13 empty] | 0 |  | 0%
14 | G | 20mm thick polished Crystal White, average of 202mm width border. | 8.3 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 4050.4 | 12151.2 | 0 | 100% | 0% | 100% | 12151.2 | 0 | 12151.2
[13 empty] | 0 |  | 0%
14 | H | 7 x 5mm Brass strip insert in brushed finish. | 27.25 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 1553.25 | 4659.75 |  | 100% | 0% | 100% | 4659.75 | 0 | 4659.75
[13 empty] | 0 |  | 0%
14 | J | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 3 | Crystal White | 20 | 231 | 97 | 328 | 328 | 984 | 0 | 100% | 0% | 100% | 984 | 0 | 984
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.85 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 340 | 1020 | 0 | 100% | 0% | 100% | 1020 | 0 | 1020
[13 empty] | 0 |  | 0%
14 | L | 20mm thick polished Crystal White, average 110mm width border. | 0.5 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 244 | 732 | 0 | 100% | 0% | 100% | 732 | 0 | 732
[13 empty] | 0 |  | 0%
14 | M | 7 x 5mm Brass strip insert in brushed finish. | 3.85 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 219.45 | 658.35 |  | 100% | 0% | 100% | 658.35 | 0 | 658.35
[13 empty] | 0 |  | 0%
14 | N | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | P | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 2000 | 6000 | 0 | 100% | 0% | 100% | 6000 | 0 | 6000
[13 empty] | 0 |  | 0%
14 | A | 20mm thick polished Crystal White, cut to size. | 1.85 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 902.8 | 2708.4 | 0 | 100% | 0% | 100% | 2708.4 | 0 | 2708.4
[13 empty] | 0 |  | 0%
14 | B | 20mm thick polished Crystal White, average of 163mm width border. | 3.1 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 4538.4 | 0 | 100% | 0% | 100% | 4538.4 | 0 | 4538.4
[13 empty] | 0 |  | 0%
14 | C | 7 x 5mm Brass strip insert in brushed finish. | 17.7 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 1008.9 | 3026.7 |  | 100% | 0% | 100% | 3026.7 | 0 | 3026.7
[13 empty] | 0 |  | 0%
14 | D | 7 x 5mm Brass strip insert in brushed finish. | 15.1 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 860.7 | 2582.1 |  | 100% | 0% | 100% | 2582.1 | 0 | 2582.1
[13 empty] | 0 |  | 0%
14 | E | Threshold (20mm thick polished Crystal White); 320mm wide x 945mm length. | 1 | Lm | 3 | Crystal White | 20 | 135 | 55 | 190 | 190 | 570 | 0 | 100% | 0% | 100% | 570 | 0 | 570
[13 empty] | 0 |  | 0%
14 | F | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 1 | Lm | 3 | Crystal White | 20 | 125 | 51 | 176 | 176 | 528 | 0 | 100% | 0% | 100% | 528 | 0 | 528
[13 empty] | 0 |  | 0%
14 | G | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 1.72 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 98.04 | 294.12 |  | 100% | 0% | 100% | 294.12 | 0 | 294.12
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | H | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 5.25 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 2100 | 6300 | 0 | 100% | 0% | 100% | 6300 | 0 | 6300
[13 empty] | 0 |  | 0%
14 | J | 20mm thick polished Crystal White, average 165mm width border. | 0.35 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 170.8 | 512.4 | 0 | 100% | 0% | 100% | 512.4 | 0 | 512.4
[13 empty] | 0 |  | 0%
14 | K | 7 x 5mm Brass strip insert in brushed finish. | 12.3 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 701.1 | 2103.3 |  | 100% | 0% | 100% | 2103.3 | 0 | 2103.3
[13 empty] | 0 |  | 0%
14 | L | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1 | Lm | 3 | Crystal White | 20 | 125 | 51 | 176 | 176 | 528 | 0 | 100% | 0% | 100% | 528 | 0 | 528
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 3.3 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1320 | 3960 | 0 | 100% | 0% | 100% | 3960 | 0 | 3960
[13 empty] | 0 |  | 0%
14 | P | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 2640 | 0 | 100% | 0% | 100% | 2640 | 0 | 2640
[13 empty] | 0 |  | 0%
14 | R | 20mm thick polished Crystal White, average of 116mm width border. | 0.8 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 390.4 | 1171.2 | 0 | 100% | 0% | 100% | 1171.2 | 0 | 1171.2
[13 empty] | 0 |  | 0%
14 | A | 7 x 5mm Brass strip insert in brushed finish. | 6.4 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 364.8 | 1094.4 |  | 100% | 0% | 100% | 1094.4 | 0 | 1094.4
[13 empty] | 0 |  | 0%
14 | B | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | C | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 4 | M2 | 3 | PC Rate | 20 | 50 | 100 | 150 | 600 | 1800 | 0 | 100% | 0% | 100% | 1800 | 0 | 1800
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | D | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 14.5 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 9106 | 27318 | 0 | 100% | 0% | 100% | 27318 | 0 | 27318
[13 empty] | 0 |  | 0%
14 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 11.4 | Lm | 3 | Crystal White | 20 | 86 | 48 | 134 | 1527.6 | 4582.8 | 0 | 100% | 0% | 100% | 4582.8 | 0 | 4582.8
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 15.95 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 10016.6 | 30049.8 | 0 | 100% | 0% | 100% | 30049.8 | 0 | 30049.8
[13 empty] | 0 |  | 0%
14 | G | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.65 | Lm | 3 | Crystal White | 20 | 94 | 56 | 150 | 997.5 | 2992.5 | 0 | 100% | 0% | 100% | 2992.5 | 0 | 2992.5
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.3 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 2072.4 | 6217.2 | 0 | 100% | 0% | 100% | 6217.2 | 0 | 6217.2
[13 empty] | 0 |  | 0%
14 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.95 | Lm | 3 | Crystal White | 20 | 79 | 43 | 122 | 481.9 | 1445.7 | 0 | 100% | 0% | 100% | 1445.7 | 0 | 1445.7
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.1 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 3830.8 | 11492.4 | 0 | 100% | 0% | 100% | 11492.4 | 0 | 11492.4
[13 empty] | 0 |  | 0%
14 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.5 | Lm | 3 | Crystal White | 20 | 79 | 43 | 122 | 793 | 2379 | 0 | 100% | 0% | 100% | 2379 | 0 | 2379
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | B | Living : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 4434 | 0 | 100% | 0% | 100% | 1478 | 2956 | 4434
[13 empty] | 0 |  | 0%
14 | C | Bedroom : 320mm wide; total size of 945 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 831 | 421 | 1252 | 1252 | 3756 | 0 | 100% | 0% | 100% | 1252 | 2504 | 3756
[13 empty] | 0 |  | 0%
14 | D | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 660 | 304 | 964 | 964 | 2892 | 0 | 100% | 0% | 100% | 1928 | 964 | 2892
[13 empty] | 0 |  | 0%
14 | E | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 2 | No | 3 | Crystal White | 20 | 724 | 350 | 1074 | 2148 | 6444 | 2 | 66.67% | 33.33% | 100% | 2148 | 4296 | 6444
[13 empty] | 0 |  | 0%
14 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 660 | 304 | 964 | 964 | 2892 | 0 | 100% | 0% | 100% | 1928 | 964 | 2892
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | G | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1400mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 3 | Crystal White | 20 | 388 | 209 | 597 | 597 | 1791 | 0 | 0% | 0% | 0% | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | H | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 6237 | 0 | 100% | 0% | 100% | 2079 | 4158 | 6237
[13 empty] | 0 |  | 0%
|  | Sanitaryware - Stoneworks | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | J | Bath Tub Top @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of maximum 150/450mm wide, total size of 1050mm wide x 1895mm length. Complete with 1 no. of 620mm high cladding. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 3 | Volakas | 20 | 893 | 359 | 1252 | 1252 | 3756 | 0 | 100% | 0% | 100% | 0 | 3756 | 3756
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 492 | 240 | 732 | 732 | 2196 | 0 | 100% | 0% | 100% | 2196 | 0 | 2196
[13 empty] | 0 |  | 0%
14 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1430mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 334 | 143 | 477 | 477 | 1431 | 0 | 100% | 0% | 100% | 1431 | 0 | 1431
[13 empty] | 0 |  | 0%
14 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 3 | Volakas | 20 | 44 | 12 | 56 | 112 | 336 | 0 | 100% | 0% | 100% | 336 | 0 | 336
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 910mm length, pencil edge finish. | 1 | No | 3 | Volakas | 20 | 97 | 48 | 145 | 145 | 435 | 0 | 100% | 0% | 100% | 435 | 0 | 435
[13 empty] | 0 |  | 0%
14 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 3 | Volakas | 20 | 25 | 5 | 30 | 30 | 90 | 0 | 100% | 0% | 100% | 90 | 0 | 90
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1245mm length, pencil edge finish. | 1 | No | 3 | Volakas | 20 | 135 | 67 | 202 | 202 | 606 | 0 | 100% | 0% | 100% | 606 | 0 | 606
[13 empty] | 0 |  | 0%
14 | G | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (900 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 3 | Volakas | 20 | 738 | 331 | 1069 | 1069 | 3207 | 0 | 100% | 0% | 100% | 1069 | 2138 | 3207
[13 empty] | 0 |  | 0%
14 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 3 | Volakas | 20 | 25 | 5 | 30 | 30 | 90 | 0 | 100% | 0% | 100% | 90 | 0 | 90
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
14 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 138 | M2 | 3 |  |  | 0 | 8 | 8 | 1104 | 3312 | 3.7729 | 98.33% | 0.9113% | 99.24% | 2981.4039 | 305.4294 | 3286.8333
[13 empty] | 0 |  | 0%
14 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 71 | M2 | 3 |  |  | 0 | 8 | 8 | 568 | 1704 | 1.9411 | 98.33% | 0.9113% | 99.24% | 1533.9107 | 157.1412 | 1691.0519
[13 empty] | 0 |  | 0%
14 |  | Total Amount for TYPE -10B | [10 empty] | 0 |  | 0% |  | 216688.0846 | 22198.5706 | 238886.6552
[13 empty] | 0 |  | 0%
15 |  | TYPE -11A/11B/11C/11D (19 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | A | Supply and installation of 20mm thick brushed Beige Travertine, 335 x 335mm. | 1.6 | M2 | 19 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 12160 | 0.08 | 98.68% | 0.2632% | 98.95% | 12000 | 32 | 12032
[13 empty] | 0 |  | 0%
15 | B | Supply and installation of 20mm thick brushed Beige Stone, 335 x 335mm. | 1.6 | M2 | 19 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 12160 | 0.08 | 98.68% | 0.2632% | 98.95% | 12000 | 32 | 12032
[13 empty] | 0 |  | 0%
15 | C | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 7.2 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 410.4 | 7797.6 |  | 84.21% | 0% | 84.21% | 6566.4 | 0 | 6566.4
[13 empty] | 0 |  | 0%
15 | Add | Threshold To Main Entrance : Supply and installation of 20mm thick honed Volakas, 160mm W x 1100mm L | 1 | No | 19 | Volakas | 20 | 115 | 33 | 148 | 148 | 2812 | 0.0088 | 98.68% | 0.2632% | 98.95% | 2775 | 7.4 | 2782.4
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | D | Threshold To Connecting Room : Supply and installation of 20mm thick brushed Beige Travertine, 395mm W x 980mm L. | 1 | No | 19 | Beige Travertine | 20 | 139 | 71 | 210 | 210 | 3990 | 0.40646 | 82.89% | 5.526% | 88.42% | 3202.5 | 325.5 | 3528
[13 empty] | 0 |  | 0%
15 | E | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone threshold | 1.8 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 102.6 | 1949.4 |  | 73.68% | 0% | 73.68% | 1333.8 | 102.6 | 1436.4
[13 empty] | 0 |  | 0%
|  | Vestibule | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | F | Supply and installation of 20mm thick honed Volakas floor border, cut to size. | 2.5 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 1595 | 30305 | 2.625 | 82.89% | 5.526% | 88.42% | 24323.75 | 2472.25 | 26796
[13 empty] | 0 |  | 0%
15 | G | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border/threshold to bedroom. | 7.3 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 416.1 | 7905.9 |  | 73.68% | 0% | 73.68% | 5409.3 | 416.1 | 5825.4
[13 empty] | 0 |  | 0%
15 | H | Threshold To Bed Room : Supply and installation of 20mm thick honed Volakas, 270mm W x 1145mm L | 1 | No | 19 | Volakas | 20 | 168 | 56 | 224 | 224 | 4256 | 0.32461 | 82.89% | 5.526% | 88.42% | 3416 | 347.2 | 3763.2
[13 empty] | 0 |  | 0%
15 | J | Threshold To Walk-in Closet : Supply and installation of 20mm thick honed Volakas, 220mm W x 865mm L | 1 | No | 19 | Volakas | 20 | 110 | 35 | 145 | 145 | 2755 | 0.19982 | 82.89% | 5.526% | 88.42% | 2211.25 | 224.75 | 2436
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | K | Supply and installation of 20mm thick honed Volakas floor border, cut to size. | 1.35 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 861.3 | 16364.7 | 1.4175 | 82.89% | 5.526% | 88.42% | 13134.825 | 1335.015 | 14469.84
[13 empty] | 0 |  | 0%
15 | L | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 4.25 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 242.25 | 4602.75 |  | 73.68% | 0% | 73.68% | 3149.25 | 242.25 | 3391.5
[13 empty] | 0 |  | 0%
15 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 710.2 | 13493.8 | 0 | 100% | 0% | 100% | 12783.6 | 710.2 | 13493.8
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | M | 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 3.45 | M2 | 19 | Pink Desert | 20 | 503 | 125 | 628 | 2166.6 | 41165.4 | 4.83 | 89.47% | 7.368% | 96.84% | 36832.2 | 3033.24 | 39865.44
[13 empty] | 0 |  | 0%
15 | N | 20mm thick honed Volakas in herringbone pattern at 100mm wide stone strips, as per drawing. | 4.15 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 2647.7 | 50306.3 | 5.81 | 89.47% | 7.368% | 96.84% | 45010.9 | 3706.78 | 48717.68
[13 empty] | 0 |  | 0%
15 | P | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 11 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 627 | 11913 |  | 78.95% | 5.263% | 84.21% | 9405 | 627 | 10032
[13 empty] | 0 |  | 0%
15 | A | Threshold To Bathroom : Supply and installation of 20mm thick honed Volakas, 420mm W x 1130mm L | 1 | No | 19 | Volakas | 20 | 230 | 85 | 315 | 315 | 5985 | 0.66444 | 89.47% | 7.368% | 96.84% | 5355 | 441 | 5796
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | B | 20mm thick honed Volakas in herringbone pattern at 100mm wide stone strips, as per drawing. | 0.8 | M2 | 19 | Volakas | 20 | 433 | 205 | 638 | 510.4 | 9697.6 | -0.32 | 100% | -2.105% | 97.89% | 8676.8 | 816.64 | 9493.44
[13 empty] | 0 |  | 0%
15 | C | 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 1 | M2 | 19 | Pink Desert | 20 | 503 | 125 | 628 | 628 | 11932 | -0.4 | 100% | -2.105% | 97.89% | 10676 | 1004.8 | 11680.8
[13 empty] | 0 |  | 0%
15 | D | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border. | 3.9 | Lm | 19 | Brass | 5 | 0 | 57 | 57 | 222.3 | 4223.7 |  | 78.95% | 0% | 78.95% | 3334.5 | 0 | 3334.5
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | E | 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 1.9 | M2 | 19 | Pink Desert | 20 | 503 | 125 | 628 | 1193.2 | 22670.8 | -1.9 | 94.74% | -5.263% | 89.47% | 20284.4 | 0 | 20284.4
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | F | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10.35 | M2 | 19 | PC Rate | 20 | 50 | 100 | 150 | 1552.5 | 29497.5 | 0 | 100% | 0% | 100% | 29497.5 | 0 | 29497.5
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Pantry | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | G | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 3.05 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 1915.4 | 36392.6 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 | H | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 2.2 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 294.8 | 5601.2 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 |  | Skirting : 20mm thick honed Volakas 150mm high skirting, chamfered edge. | 3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 402 | 7638 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 | J | Skirting : 20mm thick honed Volakas 150mm high skirting with ventilation slots as applicable, chamfered edge. | 1.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 174.2 | 3309.8 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | K | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 1.75 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 234.5 | 4455.5 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Powder Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | L | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 576.2 | 10947.8 | 0 | 100% | 0% | 100% | 10371.6 | 576.2 | 10947.8
[13 empty] | 0 |  | 0%
15 | A | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 4.75 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 2983 | 56677 | 0 | 100% | 0% | 100% | 56677 | 0 | 56677
[13 empty] | 0 |  | 0%
15 | B | Cistern Top : 20mm thick honed Volakas, 230mm W x 1455mm L, pencil edge finish. | 1 | No | 19 | Volakas | 20 | 163 | 81 | 244 | 244 | 4636 | 0 | 100% | 0% | 100% | 4636 | 0 | 4636
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | C | Wall : 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 21.45 | M2 | 19 | Pink Desert | 20 | 503 | 188 | 691 | 14821.95 | 281617.05 | 0 | 100% | 0% | 100% | 281617.05 | 0 | 281617.05
[13 empty] | 0 |  | 0%
15 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 3 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 1884 | 35796 | 0 | 100% | 0% | 100% | 35796 | 0 | 35796
[13 empty] | 0 |  | 0%
15 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.3 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 576.2 | 10947.8 | 0 | 100% | 0% | 100% | 10371.6 | 576.2 | 10947.8
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | D | Wall : 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 15.25 | M2 | 19 | Pink Desert | 20 | 503 | 188 | 691 | 10537.75 | 200217.25 | 0 | 100% | 0% | 100% | 200217.25 | 0 | 200217.25
[13 empty] | 0 |  | 0%
15 | E | Skirting : 20mm thick honed Volakas (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 19 | Volakas | 20 | 111 | 55 | 166 | 747 | 14193 | 0 | 100% | 0% | 100% | 13446 | 747 | 14193
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | F | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 5.15 | M2 | 19 | Volakas | 20 | 406 | 222 | 628 | 3234.2 | 61449.8 | 0 | 100% | 0% | 100% | 61449.8 | 0 | 61449.8
[13 empty] | 0 |  | 0%
15 | G | To Wall : 20mm thick honed Amber Pink stone at 20mm x 20mm (as per our sample). | 6.7 | M2 | 19 | Pink Desert | 20 | 503 | 188 | 691 | 4629.7 | 87964.3 | 0 | 100% | 0% | 100% | 87964.3 | 0 | 87964.3
[13 empty] | 0 |  | 0%
15 | H | Cistern Top : 20mm thick honed Volakas, 230mm W x 1055mm L, pencil edge finish. | 1 | No | 19 | Volakas | 20 | 116 | 57 | 173 | 173 | 3287 | 0 | 100% | 0% | 100% | 3287 | 0 | 3287
[13 empty] | 0 |  | 0%
15 | J | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.75 | Lm | 19 | Volakas | 20 | 91 | 43 | 134 | 636.5 | 12093.5 | 0 | 100% | 0% | 100% | 11457 | 636.5 | 12093.5
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick honed Volakas as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | K | Bedroom To Vestibule : 270mm wide; total size of 1160 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 766 | 369 | 1135 | 1135 | 21565 | 0 | 73.68% | 0% | 73.68% | 17025 | -1135 | 15890
[13 empty] | 0 |  | 0%
15 | L | Vestibule To Bathroom : 420mm wide; total size of 1160 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 1055 | 574 | 1629 | 1629 | 30951 | 0 | 78.95% | 0% | 78.95% | 26064 | -1629 | 24435
[13 empty] | 0 |  | 0%
15 | M | Bathroom To Toilet : 175mm wide; total size of 860 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 550 | 227 | 777 | 777 | 14763 | 0 | 94.74% | 0% | 94.74% | 13986 | 0 | 13986
[13 empty] | 0 |  | 0%
15 | N | Bathroom To Shower : 175mm wide; total size of 860 x 2435mm high. | 1 | No | 19 | Crystal White | 20 | 550 | 227 | 777 | 777 | 14763 | 0 | 94.74% | 0% | 94.74% | 13986 | 0 | 13986
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Powder Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | A | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (665 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 19 | Volakas | 20 | 668 | 297 | 965 | 965 | 18335 | 0 | 97.37% | 0% | 97.37% | 17852.5 | 0 | 17852.5
[13 empty] | 0 |  | 0%
|  | Pantry | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | B | Counter : supply and installation of 20mm thick polished White Quartz (equivalent, as per our sample) top size of 655mm W x (1875 + 2225)mm L, mitered with 40mm high fascia. | 1 | No | 19 | Crystal White | 20 | 1027 | 684 | 1711 | 1711 | 32509 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 | C | Underside Stone Shelf To Overhead Cabinet : supply and installation of 20mm thick honed Volakas, size of (80 + 40 + 65)mm x (1885 + 1535)mm L. | 1 | No | 19 | Volakas | 20 | 429 | 150 | 579 | 579 | 11001 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Living Room To Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | D | Cupboard Top : supply & installation of 20mm thick honed Volakas top size of 400mm W x 450mm L, mitered with 40mm high fascia. | 2 | No | 19 | Volakas | 20 | 126 | 48 | 174 | 348 | 6612 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Mini Bar @ Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | E | Counter Top : supply & installation of 20mm thick honed Volakas top size of 595mm W x 2045mm L, mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 565 | 309 | 874 | 874 | 16606 | 2.5972 | 71.05% | 10.53% | 81.58% | 11799 | 1748 | 13547
[13 empty] | 0 |  | 0%
|  | Mini Bar Upper Shelf @ Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | F | Shelf Top : supply & installation of 20mm thick honed Volakas top size of 245mm W x (2045 + 600)mm L, having 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 369 | 181 | 550 | 550 | 10450 | 1.5076 | 71.05% | 10.53% | 81.58% | 7425 | 1100 | 8525
[13 empty] | 0 |  | 0%
|  | Podium Battles To Upper Shelf Mini Bar @ Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | G | Step-Like Podium : supply & installation of 20mm thick polished standard White Onyx top size of (100 + 100)mm W x (380 + 380)mm L, mitered with (65 + 100)mm high fascia. | 1 | No | 19 | White Onyx | 20 | 1330 | 67 | 1397 | 1397 | 26543 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Living Room To Connecting Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | H | Cabinet Top/Shelf : supply & installation of 20mm thick honed Volakas top size of 400/250mm W x 700mm L, both mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 141 | 74 | 215 | 215 | 4085 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Vestibule | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | J | Vanity Counter : supply and installation of 20mm thick honed Volakas top size of 600mm W x 1300mm L, mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 539 | 183 | 722 | 722 | 13718 | 0 | 97.37% | 0% | 97.37% | 13357 | 0 | 13357
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | K | Wardrobe Base : supply and installation of 20mm thick honed Volakas size of 650mm W x 1215mm L. | 1 | No | 19 | Volakas | 20 | 343 | 188 | 531 | 531 | 10089 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 | A | Luggage Counter : supply and installation of 20mm thick honed Volakas size of 650mm W x (965 + 615)mm L mitered with 40mm high fascia. | 1 | No | 19 | Volakas | 20 | 470 | 259 | 729 | 729 | 13851 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 | B | Niche : supply and installation of 20mm thick honed Volakas size of 450 x 735 x 400mm depth, complete with surround and back cladding. | 1 | No | 19 | Volakas | 20 | 588 | 287 | 875 | 875 | 16625 | 0 | 100% | 0% | 100% | 15575 | 1050 | 16625
[13 empty] | 0 |  | 0%
15 | C | Skirting @ Cabinet : 20mm thick honed Volakas (150 + 115)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.15 | Lm | 19 | Volakas | 20 | 126 | 65 | 191 | 601.65 | 11431.35 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | D | To Column : supply and installation of 20mm thick honed Volakas cladding to column, total size of (295 + 270 + 170 + 160)mm x 2650mm H. Shelf, elsewhere. | 2 | No | 19 | Volakas | 20 | 1018 | 530 | 1548 | 3096 | 58824 | 0 |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
15 | E | Shelf : supply and installation of 20mm thick honed Volakas, 140mm W x 225mmL, mitered with 40mm high fascia. | 2 | No | 19 | Volakas | 20 | 22 | 10 | 32 | 64 | 1216 | 0.162 | 89.47% | 10.53% | 100% | 1024 | 192 | 1216
[13 empty] | 0 |  | 0%
15 | F | Vanity Counter : supply and installation of 20mm thick honed Volakas, 560mm W x 985mmL, mitered with 250mm high fascia. Including integrated basin total size of 450 * 350 * 225mm depth (not block stone). | 2 | No | 19 | Volakas | 20 | 704 | 314 | 1018 | 2036 | 38684 | 0 | 97.37% | 0% | 97.37% | 37666 | 0 | 37666
[13 empty] | 0 |  | 0%
15 | G | Bath Tub Top @ Bathroom : supply and installation of 20mm thick honed Volakas top size of maximum 100/480mm wide, total size of 930mm wide x 2040mm length. Complete with 590mm high cladding to 3-sides. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 19 | Volakas | 20 | 796 | 309 | 1105 | 1105 | 20995 | 0 | 100% | 0% | 100% | 15470 | 5525 | 20995
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 | H | Shelf : supply and installation of 20mm thick honed Volakas, 180mm W x 600mmL, mitered with 40mm high fascia to 2-sides. | 1 | No | 19 | Volakas | 20 | 67 | 31 | 98 | 98 | 1862 | 0.264 | 89.47% | 10.53% | 100% | 1568 | 294 | 1862
[13 empty] | 0 |  | 0%
15 | J | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1040mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 19 | Volakas | 20 | 208 | 104 | 312 | 312 | 5928 | 0.4368 | 94.74% | 5.263% | 100% | 4992 | 936 | 5928
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
15 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 126 | M2 | 19 |  |  | 0 | 8 | 8 | 1008 | 19152 |  | 81.47% | 0.8342% | 82.31% | 15435.5203 | 328.0839 | 15763.6042
0%
15 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 32 | M2 | 19 |  |  | 0 | 8 | 8 | 256 | 4864 |  | 81.47% | 0.8342% | 82.31% | 3920.1321 | 83.3229 | 4003.455
[13 empty] | 0 |  | 0%
15 |  | Total Amount for TYPE -11A/11B/11C/11D | [10 empty] | 0 |  | 0% |  | 1265813.7274 | 26905.0319 | 1292718.7592
[13 empty] | 0 |  | 0%
16 |  | TYPE -12A (5 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Entrance | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 6.9 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 2760 | 13800 | 0 | 100% | 0% | 100% | 13800 | 0 | 13800
[13 empty] | 0 |  | 0%
16 | B | 20mm thick polished Crystal White, cut to size. | 0.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1342 | 0 | 100% | 0% | 100% | 1342 | 0 | 1342
[13 empty] | 0 |  | 0%
16 | C | 20mm thick polished Crystal White, maximum 130mm width border. | 2.2 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1073.6 | 5368 | 0 | 100% | 0% | 100% | 5368 | 0 | 5368
[13 empty] | 0 |  | 0%
16 | D | 7 x 5mm Brass strip insert in brushed finish. | 10.95 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 624.15 | 3120.75 |  | 100% | 0% | 100% | 3120.75 | 0 | 3120.75
[13 empty] | 0 |  | 0%
16 | Add | Threshold To Main Entrance : Supply and installation of 20mm thick honed Volakas, 160mm W x 1100mm L | 1 | No | 5 | Volakas | 20 | 115 | 33 | 148 | 148 | 740 | 0 | 100% | 0% | 100% | 740 | 0 | 740
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 27.35 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 10940 | 54700 | 0 | 100% | 0% | 100% | 54700 | 0 | 54700
[13 empty] | 0 |  | 0%
16 | F | 20mm thick polished Crystal White, cut to size. | 3.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 7564 | 0 | 100% | 0% | 100% | 7564 | 0 | 7564
[13 empty] | 0 |  | 0%
16 | G | 20mm thick polished Crystal White, average of 167mm width border. | 4.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 2000.8 | 10004 | 0 | 100% | 0% | 100% | 10004 | 0 | 10004
[13 empty] | 0 |  | 0%
16 | H | 7 x 5mm Brass strip insert in brushed finish. | 23.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 1322.4 | 6612 |  | 100% | 0% | 100% | 6612 | 0 | 6612
[13 empty] | 0 |  | 0%
16 | J | 7 x 5mm Brass strip insert in brushed finish. | 12.8 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 729.6 | 3648 |  | 100% | 0% | 100% | 3648 | 0 | 3648
[13 empty] | 0 |  | 0%
16 | K | Threshold (20mm thick polished Crystal White); 300mm wide x 1490mm length. | 1 | No | 5 | Crystal White | 20 | 204 | 82 | 286 | 286 | 1430 | 0 | 100% | 0% | 100% | 1430 | 0 | 1430
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | L | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.6 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 3200 | 0 | 100% | 0% | 100% | 3200 | 0 | 3200
[13 empty] | 0 |  | 0%
16 | M | 20mm thick polished Crystal White, average 110mm width border. | 0.55 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 268.4 | 1342 | 0 | 100% | 0% | 100% | 1342 | 0 | 1342
[13 empty] | 0 |  | 0%
16 | N | 7 x 5mm Brass strip insert in brushed finish. | 5.1 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 290.7 | 1453.5 |  | 100% | 0% | 100% | 1453.5 | 0 | 1453.5
[13 empty] | 0 |  | 0%
16 |  | Threshold (20mm thick); 320mm wide x 860mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 7.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 2920 | 14600 | 0 | 100% | 0% | 100% | 14600 | 0 | 14600
[13 empty] | 0 |  | 0%
16 | B | 20mm thick polished Crystal White, cut to size. | 1.1 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 536.8 | 2684 | 0 | 100% | 0% | 100% | 2684 | 0 | 2684
[13 empty] | 0 |  | 0%
16 | C | 20mm thick polished Crystal White, average of 121mm width border. | 1.95 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 951.6 | 4758 | 0 | 100% | 0% | 100% | 4758 | 0 | 4758
[13 empty] | 0 |  | 0%
16 | D | 7 x 5mm Brass strip insert in brushed finish. | 15.2 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 866.4 | 4332 |  | 100% | 0% | 100% | 4332 | 0 | 4332
[13 empty] | 0 |  | 0%
16 | E | 7 x 5mm Brass strip insert in brushed finish. | 12.5 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 712.5 | 3562.5 |  | 100% | 0% | 100% | 3562.5 | 0 | 3562.5
[13 empty] | 0 |  | 0%
16 | F | Threshold (20mm thick polished Crystal White); 375mm wide x 860mm length. | 1 | No | 5 | Crystal White | 20 | 138 | 59 | 197 | 197 | 985 | 0 | 100% | 0% | 100% | 985 | 0 | 985
[13 empty] | 0 |  | 0%
16 | G | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 1 | No | 5 | Crystal White | 20 | 125 | 51 | 176 | 176 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
[13 empty] | 0 |  | 0%
16 | H | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 1.72 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 98.04 | 490.2 |  | 100% | 0% | 100% | 490.2 | 0 | 490.2
[13 empty] | 0 |  | 0%
|  | Vestibule | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.3 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 920 | 4600 | 0 | 100% | 0% | 100% | 4600 | 0 | 4600
[13 empty] | 0 |  | 0%
16 | K | 20mm thick polished Crystal White, cut to size. | 0.7 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1708 | 0 | 100% | 0% | 100% | 1708 | 0 | 1708
[13 empty] | 0 |  | 0%
16 | L | 20mm thick polished Crystal White, average of 160mm width border. | 1.2 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 585.6 | 2928 | 0 | 100% | 0% | 100% | 2928 | 0 | 2928
[13 empty] | 0 |  | 0%
16 | M | 7 x 5mm Brass strip insert in brushed finish with top layer brass coat. - to stone floor border/threshold to bedroom. | 6.15 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 350.55 | 1752.75 |  | 100% | 0% | 100% | 1752.75 | 0 | 1752.75
[13 empty] | 0 |  | 0%
16 | N | Threshold To Walk-in Closet : Supply and installation of 20mm thick polished Crystal White, 270mm W x 860mm L | 1 | No | 5 | Crystal White | 20 | 109 | 43 | 152 | 152 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
[13 empty] | 0 |  | 0%
16 | P | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 0.86 | Lm | 5 | Brass | 5 | 0 | 51 | 51 | 43.86 | 219.3 |  | 100% | 0% | 100% | 219.3 | 0 | 219.3
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 9.05 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 3620 | 18100 | 0 | 100% | 0% | 100% | 18100 | 0 | 18100
[13 empty] | 0 |  | 0%
16 | A | 20mm thick polished Crystal White, average 165mm width border. | 2.05 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 1000.4 | 5002 | 0 | 100% | 0% | 100% | 5002 | 0 | 5002
[13 empty] | 0 |  | 0%
16 | B | 7 x 5mm Brass strip insert in brushed finish. | 11.4 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 649.8 | 3249 |  | 100% | 0% | 100% | 3249 | 0 | 3249
[13 empty] | 0 |  | 0%
16 | C | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | No | 5 | Crystal White | 20 | 134 | 55 | 189 | 189 | 945 | 0 | 100% | 0% | 100% | 945 | 0 | 945
[13 empty] | 0 |  | 0%
16 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.55 | Lm | 5 | Volakas | 20 | 91 | 43 | 134 | 877.7 | 4388.5 | 0 | 100% | 0% | 100% | 4388.5 | 0 | 4388.5
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | D | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.75 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 700 | 3500 | 0 | 100% | 0% | 100% | 3500 | 0 | 3500
[13 empty] | 0 |  | 0%
16 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.95 | M2 | 5 | Beige Travertine | 20 | 255 | 145 | 400 | 780 | 3900 | 0 | 100% | 0% | 100% | 3900 | 0 | 3900
[13 empty] | 0 |  | 0%
16 | H | 20mm thick polished Crystal White, average of 116mm width border. | 0.7 | M2 | 5 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1708 | 0 | 100% | 0% | 100% | 1708 | 0 | 1708
[13 empty] | 0 |  | 0%
16 | J | 7 x 5mm Brass strip insert in brushed finish. | 5.6 | Lm | 5 | Brass | 5 | 0 | 57 | 57 | 319.2 | 1596 |  | 100% | 0% | 100% | 1596 | 0 | 1596
[13 empty] | 0 |  | 0%
16 | K | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 5 | Crystal White | 20 | 99 | 37 | 136 | 136 | 680 | 0 | 100% | 0% | 100% | 680 | 0 | 680
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | L | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 13.2 | M2 | 5 | PC Rate | 20 | 50 | 100 | 150 | 1980 | 9900 | 0 | 100% | 0% | 100% | 9900 | 0 | 9900
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | M | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 24.3 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 15260.4 | 76302 | 0 | 100% | 0% | 100% | 76302 | 0 | 76302
[13 empty] | 0 |  | 0%
16 | N | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.1 | Lm | 5 | Crystal White | 20 | 86 | 48 | 134 | 549.4 | 2747 | 0 | 100% | 0% | 100% | 2747 | 0 | 2747
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | A | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 11.85 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 7441.8 | 37209 | 0 | 100% | 0% | 100% | 37209 | 0 | 37209
[13 empty] | 0 |  | 0%
16 | B | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.5 | Lm | 5 | Crystal White | 20 | 94 | 56 | 150 | 675 | 3375 | 0 | 100% | 0% | 100% | 3375 | 0 | 3375
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | C | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 5.1 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 3202.8 | 16014 | 0 | 100% | 0% | 100% | 16014 | 0 | 16014
[13 empty] | 0 |  | 0%
16 | D | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.7 | Lm | 5 | Crystal White | 20 | 79 | 43 | 122 | 573.4 | 2867 | 0 | 100% | 0% | 100% | 2867 | 0 | 2867
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | E | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.3 | M2 | 5 | Volakas | 20 | 406 | 222 | 628 | 3956.4 | 19782 | 0 | 100% | 0% | 100% | 19782 | 0 | 19782
[13 empty] | 0 |  | 0%
16 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.95 | Lm | 5 | Volakas | 20 | 91 | 43 | 134 | 797.3 | 3986.5 | 0 | 100% | 0% | 100% | 3986.5 | 0 | 3986.5
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick honed Volakas as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | G | Living : 300mm wide; total size of 1490 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 868 | 433 | 1301 | 1301 | 6505 | 0 | 100% | 0% | 100% | 6505 | 0 | 6505
[13 empty] | 0 |  | 0%
16 | H | Bedroom : (145 + 160)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 792 | 397 | 1189 | 1189 | 5945 | 0 | 100% | 0% | 100% | 5945 | 0 | 5945
[13 empty] | 0 |  | 0%
16 | J | Bedroom To Vestibule : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 5395 | 0 | 100% | 0% | 100% | 5395 | 0 | 5395
[13 empty] | 0 |  | 0%
16 | K | Toilet @ Foyer : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 5395 | 0 | 100% | 0% | 100% | 5395 | 0 | 5395
[13 empty] | 0 |  | 0%
16 | A | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 5435 | 0 | 100% | 0% | 100% | 5435 | 0 | 5435
[13 empty] | 0 |  | 0%
16 | B | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 1 | No | 5 | Crystal White | 20 | 660 | 304 | 964 | 964 | 4820 | 0 | 100% | 0% | 100% | 4820 | 0 | 4820
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Mini Bar @ Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | C | Counter Top : supply & installation of 20mm thick polished Volakas top size of 690mm W x 1550mm L, including shelf top size of 290mm W, both mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 686 | 390 | 1076 | 1076 | 5380 | 1 | 40% | 20% | 60% | 2152 | 1076 | 3228
[13 empty] | 0 |  | 0%
|  | Vestibule | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | D | Vanity Counter : supply and installation of 20mm thick polished Volakas top size of 550mm W x 1215mm L, mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 539 | 183 | 722 | 722 | 3610 | 0 | 80% | 0% | 80% | 2888 | 0 | 2888
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | E | Wardrobe Counter (smaller) : supply and installation of 20mm thick honed Volakas size of 650mm W x 700mm L, mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 208 | 114 | 322 | 322 | 1610 | 0 | 100% | 0% | 100% | 1610 | 0 | 1610
[13 empty] | 0 |  | 0%
16 | F | Wardrobe Counter : supply and installation of 20mm thick polished Volakas size of 650mm W x 1590mm L mitered with 40mm high fascia. | 1 | No | 5 | Volakas | 20 | 475 | 262 | 737 | 737 | 3685 | 0 | 100% | 0% | 100% | 3685 | 0 | 3685
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | G | To Column : supply and installation of 20mm thick polished Volakas cladding to column, total size of (295 + 270 + 170 + 160)mm x 2650mm H. Shelf, elsewhere. | 2 | No | 5 | Volakas | 20 | 1018 | 530 | 1548 | 3096 | 15480 | 0 | 100% | 0% | 100% | 15480 | 0 | 15480
[13 empty] | 0 |  | 0%
16 | H | Shelf : supply and installation of 20mm thick honed Volakas, 140mm W x 225mmL, mitered with 40mm high fascia. | 2 | No | 5 | Volakas | 20 | 22 | 10 | 32 | 64 | 320 | 0 | 100% | 0% | 100% | 320 | 0 | 320
[13 empty] | 0 |  | 0%
16 | J | Vanity Counter : supply and installation of 20mm thick polished Volakas, 560mm W x 985mmL, mitered with 250mm high fascia. Including integrated basin total size of 450 * 350 * 225mm depth (not block stone). -- back cladding, elsewhere. | 2 | No | 5 | Volakas | 20 | 704 | 314 | 1018 | 2036 | 10180 | 0 | 80% | 0% | 80% | 8144 | 0 | 8144
[13 empty] | 0 |  | 0%
16 | K | Bath Tub Top @ Bathroom : supply and installation of 20mm thick honed Volakas top size of maximum 100/480mm wide, total size of 930mm wide x 2040mm length. Complete with 590mm high cladding to 3-sides. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 5 | Volakas | 20 | 796 | 309 | 1105 | 1105 | 5525 | 0 | 100% | 0% | 100% | 5525 | 0 | 5525
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 602 | 294 | 896 | 896 | 4480 | 0 | 100% | 0% | 100% | 4480 | 0 | 4480
[13 empty] | 0 |  | 0%
16 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1290mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 5 | Volakas | 20 | 303 | 129 | 432 | 432 | 2160 | 0 | 100% | 0% | 100% | 2160 | 0 | 2160
[13 empty] | 0 |  | 0%
16 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 5 | Volakas | 20 | 44 | 12 | 56 | 112 | 560 | 0 | 100% | 0% | 100% | 560 | 0 | 560
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 102 | 50 | 152 | 152 | 760 | 0 | 100% | 0% | 100% | 760 | 0 | 760
[13 empty] | 0 |  | 0%
16 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1350mm length, pencil edge finish. | 1 | No | 5 | Volakas | 20 | 145 | 72 | 217 | 217 | 1085 | 0 | 100% | 0% | 100% | 1085 | 0 | 1085
[13 empty] | 0 |  | 0%
16 | G | Vanity Counter : supply and installation of 20mm thick polished Volakas, top size of 225mm W x (1370 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 5 | Volakas | 20 | 838 | 378 | 1216 | 1216 | 6080 | 0 | 80% | 0% | 80% | 4864 | 0 | 4864
[13 empty] | 0 |  | 0%
16 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 5 | Volakas | 20 | 25 | 5 | 30 | 30 | 150 | 0 | 100% | 0% | 100% | 150 | 0 | 150
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
16 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 173 | M2 | 5 |  |  | 0 | 8 | 8 | 1384 | 6920 |  | 98.47% | 0.2289% | 98.7% | 6813.9857 | 15.8388 | 6829.8246
0%
16 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 93 | M2 | 5 |  |  | 0 | 8 | 8 | 744 | 3720 |  | 98.47% | 0.2289% | 98.7% | 3663.0097 | 8.5145 | 3671.5242
[13 empty] | 0 |  | 0%
16 |  | Total Amount for TYPE -12A | [10 empty] | 0 |  | 0% |  | 473379.9954 | 1100.3534 | 474480.3488
[13 empty] | 0 |  | 0%
17 |  | TYPE -13A (1 No) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.1 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 840 | 840 | 0 | 100% | 0% | 100% | 840 | 0 | 840
[13 empty] | 0 |  | 0%
17 | B | 20mm thick polished Crystal White, maximum 126mm width border. | 1 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 488 | 488 | 0 | 100% | 0% | 100% | 488 | 0 | 488
[13 empty] | 0 |  | 0%
17 | C | 7 x 5mm Brass strip insert in brushed finish. | 6.5 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 370.5 | 370.5 |  |  | 0% |  | 0 | 0 | 0
[13 empty] | 0 |  | 0%
17 | Add | Threshold To Main Entrance : Supply and installation of 20mm thick honed Volakas, 160mm W x 1100mm L | 1 | No | 1 | Volakas | 20 | 115 | 33 | 148 | 148 | 148 | 0 | 100% | 0% | 100% | 148 | 0 | 148
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 25.5 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 10200 | 10200 | 0 | 100% | 0% | 100% | 10200 | 0 | 10200
[13 empty] | 0 |  | 0%
17 | E | 20mm thick polished Crystal White, cut to size. | 3.1 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 1512.8 | 0 | 100% | 0% | 100% | 1512.8 | 0 | 1512.8
[13 empty] | 0 |  | 0%
17 | F | 20mm thick polished Crystal White, average of 153mm width border. | 3.65 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 1781.2 | 1781.2 | 0 | 100% | 0% | 100% | 1781.2 | 0 | 1781.2
[13 empty] | 0 |  | 0%
17 | G | 7 x 5mm Brass strip insert in brushed finish. | 22.6 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 1288.2 | 1288.2 |  | 100% | 0% | 100% | 1288.2 | 0 | 1288.2
[13 empty] | 0 |  | 0%
17 | H | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 1 | Crystal White | 20 | 231 | 97 | 328 | 328 | 328 | 0 | 100% | 0% | 100% | 328 | 0 | 328
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.5 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 600 | 0 | 100% | 0% | 100% | 600 | 0 | 600
[13 empty] | 0 |  | 0%
17 | K | 20mm thick polished Crystal White, average 110mm width border. | 0.65 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 317.2 | 317.2 | 0 | 100% | 0% | 100% | 317.2 | 0 | 317.2
[13 empty] | 0 |  | 0%
17 | L | 7 x 5mm Brass strip insert in brushed finish. | 4.9 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 279.3 | 279.3 |  | 100% | 0% | 100% | 279.3 | 0 | 279.3
[13 empty] | 0 |  | 0%
17 | M | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 1 | Crystal White | 20 | 99 | 37 | 136 | 136 | 136 | 0 | 100% | 0% | 100% | 136 | 0 | 136
[13 empty] | 0 |  | 0%
|  | BED ROOM | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 16.9 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 6760 | 6760 | 0 | 100% | 0% | 100% | 6760 | 0 | 6760
[13 empty] | 0 |  | 0%
17 | A | 20mm thick polished Crystal White, cut to size. | 1.35 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 658.8 | 658.8 | 0 | 100% | 0% | 100% | 658.8 | 0 | 658.8
[13 empty] | 0 |  | 0%
17 | B | 20mm thick polished Crystal White, average of 146mm width border. | 2.6 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 1268.8 | 1268.8 | 0 | 100% | 0% | 100% | 1268.8 | 0 | 1268.8
[13 empty] | 0 |  | 0%
17 | C | 7 x 5mm Brass strip insert in brushed finish. | 16.6 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 946.2 | 946.2 |  | 100% | 0% | 100% | 946.2 | 0 | 946.2
[13 empty] | 0 |  | 0%
17 | D | 7 x 5mm Brass strip insert in brushed finish. | 13.9 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 792.3 | 792.3 |  | 100% | 0% | 100% | 792.3 | 0 | 792.3
[13 empty] | 0 |  | 0%
17 | E | Threshold (20mm thick polished Crystal White); 320mm wide x 860mm length. | 3 | No | 1 | Crystal White | 20 | 125 | 51 | 176 | 528 | 528 | 0 | 100% | 0% | 100% | 528 | 0 | 528
[13 empty] | 0 |  | 0%
17 | F | 7 x 5mm Brass strip insert in brushed finish. 860mm length (only the length between threshold and carpet, other locations are excluded) | 0.86 | Lm | 1 | Brass | 5 | 0 | 51 | 51 | 43.86 | 43.86 |  | 100% | 0% | 100% | 43.86 | 0 | 43.86
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | G | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.5 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 1400 | 1400 | 0 | 100% | 0% | 100% | 1400 | 0 | 1400
[13 empty] | 0 |  | 0%
17 | H | 20mm thick polished Crystal White, average 165mm width border. | 4.5 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 2196 | 2196 | 0 | 100% | 0% | 100% | 2196 | 0 | 2196
[13 empty] | 0 |  | 0%
17 | J | 7 x 5mm Brass strip insert in brushed finish. | 10.9 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 621.3 | 621.3 |  | 100% | 0% | 100% | 621.3 | 0 | 621.3
[13 empty] | 0 |  | 0%
17 | Add | Threshold (20mm thick polished Crystal White); 420mm wide x 1130mm length. | 1 | No | 1 | Crystal White | 20 | 197 | 86 | 283 | 283 | 283 | 0 | 100% | 0% | 100% | 283 | 0 | 283
[13 empty] | 0 |  | 0%
17 | Add | Skirting : 20mm thick honed Volakas (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 10.9 | Lm | 1 | Volakas | 20 | 91 | 43 | 134 | 1460.6 | 1460.6 | 0 | 100% | 0% | 100% | 1460.6 | 0 | 1460.6
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.2 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 880 | 880 | 0 | 100% | 0% | 100% | 880 | 0 | 880
[13 empty] | 0 |  | 0%
17 | M | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 1 | Crystal White | 20 | 99 | 37 | 136 | 136 | 136 | 0 | 100% | 0% | 100% | 136 | 0 | 136
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.75 | M2 | 1 | Beige Travertine | 20 | 255 | 145 | 400 | 300 | 300 | 0 | 100% | 0% | 100% | 300 | 0 | 300
[13 empty] | 0 |  | 0%
17 | P | 20mm thick polished Crystal White, average of 116mm width border. | 0.45 | M2 | 1 | Crystal White | 20 | 282 | 206 | 488 | 219.6 | 219.6 | 0 | 100% | 0% | 100% | 219.6 | 0 | 219.6
[13 empty] | 0 |  | 0%
17 | Q | 7 x 5mm Brass strip insert in brushed finish. | 3.4 | Lm | 1 | Brass | 5 | 0 | 57 | 57 | 193.8 | 193.8 |  | 100% | 0% | 100% | 193.8 | 0 | 193.8
[13 empty] | 0 |  | 0%
17 | R | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 1 | Crystal White | 20 | 99 | 37 | 136 | 136 | 136 | 0 | 100% | 0% | 100% | 136 | 0 | 136
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | A | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 10 | M2 | 1 | PC Rate | 20 | 50 | 100 | 150 | 1500 | 1500 | 0 | 100% | 0% | 100% | 1500 | 0 | 1500
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | B | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.55 | Lm | 1 | Crystal White | 20 | 79 | 43 | 122 | 555.1 | 555.1 | 0 | 100% | 0% | 100% | 555.1 | 0 | 555.1
[13 empty] | 0 |  | 0%
17 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 6.35 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 3987.8 | 3987.8 | 0 | 100% | 0% | 100% | 3987.8 | 0 | 3987.8
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | C | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.6 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 8540.8 | 8540.8 | 0 | 100% | 0% | 100% | 8540.8 | 0 | 8540.8
[13 empty] | 0 |  | 0%
17 | D | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.3 | Lm | 1 | Crystal White | 20 | 94 | 56 | 150 | 795 | 795 | 0 | 100% | 0% | 100% | 795 | 0 | 795
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | E | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.9 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 2449.2 | 2449.2 | 0 | 100% | 0% | 100% | 2449.2 | 0 | 2449.2
[13 empty] | 0 |  | 0%
17 | F | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.55 | Lm | 1 | Crystal White | 20 | 79 | 43 | 122 | 433.1 | 433.1 | 0 | 100% | 0% | 100% | 433.1 | 0 | 433.1
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | G | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 5.5 | M2 | 1 | Volakas | 20 | 406 | 222 | 628 | 3454 | 3454 | 0 | 100% | 0% | 100% | 3454 | 0 | 3454
[13 empty] | 0 |  | 0%
17 | H | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.05 | Lm | 1 | Crystal White | 20 | 79 | 43 | 122 | 616.1 | 616.1 | 0 | 100% | 0% | 100% | 616.1 | 0 | 616.1
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | A | Living : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 1478 | 0 | 100% | 0% | 100% | 1478 | 0 | 1478
[13 empty] | 0 |  | 0%
17 | B | Bedroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 1079 | 0 | 100% | 0% | 100% | 1079 | 0 | 1079
[13 empty] | 0 |  | 0%
17 | C | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 1 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 1928 | 0 | 100% | 0% | 100% | 1928 | 0 | 1928
[13 empty] | 0 |  | 0%
17 | D | Bedroom To WIW : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 728 | 351 | 1079 | 1079 | 1079 | 0 | 100% | 0% | 100% | 1079 | 0 | 1079
[13 empty] | 0 |  | 0%
17 | E | Bathroom : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 1 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 1074 | 0 | 100% | 0% | 100% | 1074 | 0 | 1074
[13 empty] | 0 |  | 0%
17 | F | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 1 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 1928 | 0 | 100% | 0% | 100% | 1928 | 0 | 1928
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | G | Counter Top @ Walk-In Closet (smaller) : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 270 | 148 | 418 | 418 | 418 | 0 | 0% | 0% | 0% | 0 | 0 | 0
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | H | To Column : supply and installation of 20mm thick honed Volakas cladding to column, total size of (295 + 270 + 170 + 160)mm x 2650mm H. Shelf, elsewhere. | 1 | No | 1 | Volakas | 20 | 1018 | 530 | 1548 | 1548 | 1548 | 0 | 100% | 0% | 100% | 1548 | 0 | 1548
[13 empty] | 0 |  | 0%
17 | J | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1835mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1835mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 2079 | 0 | 100% | 0% | 100% | 2079 | 0 | 2079
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | K | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 1 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 944 | 0 | 100% | 0% | 100% | 0 | 944 | 944
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | A | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 492 | 240 | 732 | 732 | 732 | 0 | 100% | 0% | 100% | 732 | 0 | 732
[13 empty] | 0 |  | 0%
17 | B | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1300mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 1 | Volakas | 20 | 308 | 131 | 439 | 439 | 439 | 0 | 100% | 0% | 100% | 439 | 0 | 439
[13 empty] | 0 |  | 0%
17 | C | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 1 | Volakas | 20 | 44 | 12 | 56 | 112 | 112 | 0 | 100% | 0% | 100% | 112 | 0 | 112
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | D | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 1 | Volakas | 20 | 112 | 55 | 167 | 167 | 167 | 0 | 100% | 0% | 100% | 167 | 0 | 167
[13 empty] | 0 |  | 0%
17 | E | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 1 | Volakas | 20 | 25 | 5 | 30 | 30 | 30 | 0 | 100% | 0% | 100% | 30 | 0 | 30
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1395mm length, pencil edge finish. | 1 | No | 1 | Volakas | 20 | 150 | 74 | 224 | 224 | 224 | 0 | 100% | 0% | 100% | 224 | 0 | 224
[13 empty] | 0 |  | 0%
17 | G | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (1090 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 1 | Volakas | 20 | 768 | 345 | 1113 | 1113 | 1113 | 0 | 100% | 0% | 100% | 1113 | 0 | 1113
[13 empty] | 0 |  | 0%
17 | H | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 1 | Volakas | 20 | 25 | 5 | 30 | 30 | 30 | 0 | 100% | 0% | 100% | 30 | 0 | 30
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
17 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 140 | M2 | 1 |  |  | 0 | 8 | 8 | 1120 | 1120 | 0 | 98.96% | 0% | 98.96% | 1094.4168 | 13.9397 | 1108.3565
[13 empty] | 0 |  | 0%
17 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 82 | M2 | 1 |  |  | 0 | 8 | 8 | 656 | 656 | 0 | 98.96% | 0% | 98.96% | 641.0155 | 8.1647 | 649.1802
[13 empty] | 0 |  | 0%
17 |  | Total Amount for TYPE -13A | [10 empty] | 0 |  | 0% |  | 75849.4923 | 966.1044 | 76815.5967
[13 empty] | 0 |  | 0%
18 |  | TYPE -14A (4 No) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 2.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 840 | 3360 | 0 | 100% | 0% | 100% | 3360 | 0 | 3360
[13 empty] | 0 |  | 0%
18 | B | 20mm thick polished Crystal White, maximum 126mm width border. | 1 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 488 | 1952 | 0 | 100% | 0% | 100% | 1952 | 0 | 1952
[13 empty] | 0 |  | 0%
18 | C | 7 x 5mm Brass strip insert in brushed finish. | 7.2 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 410.4 | 1641.6 |  | 100% | 0% | 100% | 1231.2 | 410.4 | 1641.6
[13 empty] | 0 |  | 0%
18 | Add | Threshold (20mm thick); 160mm wide x 1100mm length, polished Crystal White | 1 | No | 4 | Crystal White | 20 | 102 | 33 | 135 | 135 | 540 | 0 | 100% | 0% | 100% | 540 | 0 | 540
[13 empty] | 0 |  | 0%
|  | Living Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 20 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 8000 | 32000 | 0 | 100% | 0% | 100% | 32000 | 0 | 32000
[13 empty] | 0 |  | 0%
18 | E | 20mm thick polished Crystal White, cut to size. | 1.6 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 780.8 | 3123.2 | 0 | 100% | 0% | 100% | 3123.2 | 0 | 3123.2
[13 empty] | 0 |  | 0%
18 | F | 20mm thick polished Crystal White, average of 147mm width border. | 3.5 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 1708 | 6832 | 0 | 100% | 0% | 100% | 6832 | 0 | 6832
[13 empty] | 0 |  | 0%
18 | G | 7 x 5mm Brass strip insert in brushed finish. | 22.6 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 1288.2 | 5152.8 |  | 100% | 0% | 100% | 3864.6 | 1288.2 | 5152.8
[13 empty] | 0 |  | 0%
18 | H | 7 x 5mm Brass strip insert in brushed finish. | 12.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 712.5 | 2850 |  | 100% | 0% | 100% | 2137.5 | 712.5 | 2850
[13 empty] | 0 |  | 0%
18 | J | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 4 | Crystal White | 20 | 231 | 97 | 328 | 328 | 1312 | 0 | 100% | 0% | 100% | 1312 | 0 | 1312
[13 empty] | 0 |  | 0%
|  | POWDER ROOM | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | K | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.5 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 600 | 2400 | 0 | 100% | 0% | 100% | 2400 | 0 | 2400
[13 empty] | 0 |  | 0%
18 | L | 20mm thick polished Crystal White, cut to size. | 0.4 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 195.2 | 780.8 | 0 | 100% | 0% | 100% | 780.8 | 0 | 780.8
[13 empty] | 0 |  | 0%
18 | M | 20mm thick polished Crystal White, average 120mm width border. | 0.85 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 414.8 | 1659.2 | 0 | 100% | 0% | 100% | 1659.2 | 0 | 1659.2
[13 empty] | 0 |  | 0%
18 | N | 7 x 5mm Brass strip insert in brushed finish. | 5.25 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 299.25 | 1197 |  | 100% | 0% | 100% | 897.75 | 299.25 | 1197
[13 empty] | 0 |  | 0%
18 | P | Threshold (20mm thick); 235mm wide x 860mm length polished Crystal White. | 1 | No | 4 | Crystal White | 20 | 94 | 35 | 129 | 129 | 516 | 0 | 100% | 0% | 100% | 516 | 0 | 516
[13 empty] | 0 |  | 0%
|  | BED ROOM | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 2040 | 8160 | 0 | 100% | 0% | 100% | 8160 | 0 | 8160
[13 empty] | 0 |  | 0%
18 | B | 20mm thick polished Crystal White, cut to size. | 1.5 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 732 | 2928 | 0 | 100% | 0% | 100% | 2928 | 0 | 2928
[13 empty] | 0 |  | 0%
18 | C | 20mm thick polished Crystal White, average of 140mm width border. | 2.3 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 1122.4 | 4489.6 | 0 | 100% | 0% | 100% | 4489.6 | 0 | 4489.6
[13 empty] | 0 |  | 0%
18 | D | 7 x 5mm Brass strip insert in brushed finish. | 14.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 826.5 | 3306 |  | 100% | 0% | 100% | 3306 | 0 | 3306
[13 empty] | 0 |  | 0%
18 | E | 7 x 5mm Brass strip insert in brushed finish. | 12.05 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 686.85 | 2747.4 |  | 100% | 0% | 100% | 2747.4 | 0 | 2747.4
[13 empty] | 0 |  | 0%
18 | F | Threshold (20mm thick polished Crystal White); 320mm wide x 1140mm length. | 3 | No | 4 | Crystal White | 20 | 162 | 66 | 228 | 684 | 2736 | 0 | 100% | 0% | 100% | 2736 | 0 | 2736
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | G | 20mm thick polished Crystal White, average 135mm width border. | 2 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 976 | 3904 | 0 | 100% | 0% | 100% | 3904 | 0 | 3904
[13 empty] | 0 |  | 0%
18 | H | 7 x 5mm Brass strip insert in brushed finish. | 8.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 484.5 | 1938 |  | 100% | 0% | 100% | 1938 | 0 | 1938
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | J | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 15.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 6040 | 24160 | 0 | 100% | 0% | 100% | 24160 | 0 | 24160
[13 empty] | 0 |  | 0%
18 | K | 20mm thick polished Crystal White, average 145mm width border. | 2 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 976 | 3904 | 0 | 100% | 0% | 100% | 3904 | 0 | 3904
[13 empty] | 0 |  | 0%
18 | L | 7 x 5mm Brass strip insert in brushed finish. | 16.45 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 937.65 | 3750.6 |  | 100% | 0% | 100% | 2812.95 | 937.65 | 3750.6
[13 empty] | 0 |  | 0%
18 | Add | Threshold (20mm thick polished Crystal White); 420mm wide x 1130mm length. | 1 | No | 4 | Crystal White | 20 | 197 | 86 | 283 | 283 | 1132 | 0 | 100% | 0% | 100% | 1132 | 0 | 1132
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | M | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2.1 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 840 | 3360 | 0 | 100% | 0% | 100% | 3360 | 0 | 3360
[13 empty] | 0 |  | 0%
18 | P | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 4 | Crystal White | 20 | 99 | 37 | 136 | 136 | 544 | 0 | 100% | 0% | 100% | 544 | 0 | 544
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | Q | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 1.9 | M2 | 4 | Beige Travertine | 20 | 255 | 145 | 400 | 760 | 3040 | 0 | 100% | 0% | 100% | 3040 | 0 | 3040
[13 empty] | 0 |  | 0%
18 | A | 20mm thick polished Crystal White, average of 105mm width border. | 0.7 | M2 | 4 | Crystal White | 20 | 282 | 206 | 488 | 341.6 | 1366.4 | 0 | 100% | 0% | 100% | 1366.4 | 0 | 1366.4
[13 empty] | 0 |  | 0%
18 | B | 7 x 5mm Brass strip insert in brushed finish. | 4.5 | Lm | 4 | Brass | 5 | 0 | 57 | 57 | 256.5 | 1026 |  | 100% | 0% | 100% | 1026 | 0 | 1026
[13 empty] | 0 |  | 0%
18 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 4 | Crystal White | 20 | 99 | 37 | 136 | 136 | 544 | 0 | 100% | 0% | 100% | 544 | 0 | 544
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | D | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 17 | M2 | 4 | PC Rate | 20 | 50 | 100 | 150 | 2550 | 10200 | 0 | 100% | 0% | 100% | 10200 | 0 | 10200
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | E | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 9.65 | Lm | 4 | Crystal White | 20 | 86 | 48 | 134 | 1293.1 | 5172.4 | 0 | 100% | 0% | 100% | 5172.4 | 0 | 5172.4
[13 empty] | 0 |  | 0%
18 | Add | Wall : 20mm thick honed Volakas, cut to size and to be fixed with standard cementitious adhesive maximum up to 5mm thick. | 11.6 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 7284.8 | 29139.2 | 0 | 100% | 0% | 100% | 29139.2 | 0 | 29139.2
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | F | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.5 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 8478 | 33912 | 0 | 100% | 0% | 100% | 33912 | 0 | 33912
[13 empty] | 0 |  | 0%
18 | G | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.5 | Lm | 4 | Crystal White | 20 | 94 | 56 | 150 | 825 | 3300 | 0 | 100% | 0% | 100% | 3300 | 0 | 3300
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | H | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 12.7 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 7975.6 | 31902.4 | 0 | 100% | 0% | 100% | 31902.4 | 0 | 31902.4
[13 empty] | 0 |  | 0%
18 | J | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5 | Lm | 4 | Crystal White | 20 | 79 | 43 | 122 | 610 | 2440 | 0 | 100% | 0% | 100% | 2440 | 0 | 2440
[13 empty] | 0 |  | 0%
|  | Powder Room | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 6.05 | M2 | 4 | Volakas | 20 | 406 | 222 | 628 | 3799.4 | 15197.6 | 0 | 100% | 0% | 100% | 15197.6 | 0 | 15197.6
[13 empty] | 0 |  | 0%
18 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5.9 | Lm | 4 | Crystal White | 20 | 79 | 43 | 122 | 719.8 | 2879.2 | 0 | 100% | 0% | 100% | 2879.2 | 0 | 2879.2
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | B | Living : 350mm wide; total size of 1510 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 972 | 506 | 1478 | 1478 | 5912 | -1 | 100% | -25% | 75% | 5912 | -1478 | 4434
[13 empty] | 0 |  | 0%
18 | C | Bedroom : (120 + 120)mm wide); total size of 1140 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 704 | 327 | 1031 | 1031 | 4124 | 0 | 100% | 0% | 100% | 4124 | 0 | 4124
[13 empty] | 0 |  | 0%
18 | D | Toilet @ Foyer : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 4 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 7712 | 0 | 100% | 0% | 100% | 7712 | 0 | 7712
[13 empty] | 0 |  | 0%
18 | E | Bedroom To WIW : (120 + 120)mm wide); total size of 1140 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 704 | 327 | 1031 | 1031 | 4124 | 0 | 100% | 0% | 100% | 4124 | 0 | 4124
[13 empty] | 0 |  | 0%
18 | F | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 4 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 4348 | 0 | 100% | 0% | 100% | 4348 | 0 | 4348
[13 empty] | 0 |  | 0%
18 | G | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 4 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 7712 | 0 | 100% | 0% | 100% | 7712 | 0 | 7712
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | J | Counter Top @ Walk-In Closet (smaller) : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 270 | 148 | 418 | 418 | 1672 | 0 | 25% | 0% | 25% | 418 | 0 | 418
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | K | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1170mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 318 | 174 | 492 | 492 | 1968 | 0 | 25% | 0% | 25% | 492 | 0 | 492
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | A | Back Stone Strip @ Minibar Wall Screen Junction : Supply and installation of 2 nos, 20 x 40mm polished Crystal White size of 2250mm high. Frameworks and back support by others. | 1 | No | 4 | Crystal White | 20 | 118 | 59 | 177 | 177 | 708 | 0 | 100% | 0% | 100% | 708 | 0 | 708
[13 empty] | 0 |  | 0%
18 | B | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround, shelf, and back support elsewhere). | 1 | No | 4 | Volakas | 20 | 2088 | 999 | 3087 | 3087 | 12348 | 0 | 100% | 0% | 100% | 9261 | 3087 | 12348
[13 empty] | 0 |  | 0%
18 | C | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 170mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 519 | 254 | 773 | 773 | 3092 | 0 | 100% | 0% | 100% | 3092 | 0 | 3092
[13 empty] | 0 |  | 0%
18 | D | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 68 | 31 | 99 | 99 | 396 | 0 | 100% | 0% | 100% | 396 | 0 | 396
[13 empty] | 0 |  | 0%
|  | Bath Tub Base | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | E | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 4 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 3776 | 0.5 | 75% | 12.5% | 87.5% | 0 | 3304 | 3304
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | F | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 150mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 492 | 240 | 732 | 732 | 2928 | 0 | 100% | 0% | 100% | 2928 | 0 | 2928
[13 empty] | 0 |  | 0%
18 | G | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1065mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 4 | Volakas | 20 | 256 | 107 | 363 | 363 | 1452 | 0 | 100% | 0% | 100% | 1452 | 0 | 1452
[13 empty] | 0 |  | 0%
18 | H | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 4 | Volakas | 20 | 44 | 12 | 56 | 112 | 448 | 0 | 100% | 0% | 100% | 448 | 0 | 448
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | J | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1055mm length, pencil edge finish. | 1 | No | 4 | Volakas | 20 | 112 | 55 | 167 | 167 | 668 | 0 | 100% | 0% | 100% | 668 | 0 | 668
[13 empty] | 0 |  | 0%
18 | A | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 4 | Volakas | 20 | 25 | 5 | 30 | 30 | 120 | 0 | 100% | 0% | 100% | 120 | 0 | 120
[13 empty] | 0 |  | 0%
|  | Toilet @ Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 | B | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1120mm length, pencil edge finish. | 1 | No | 4 | Volakas | 20 | 121 | 60 | 181 | 181 | 724 | 0 | 100% | 0% | 100% | 724 | 0 | 724
[13 empty] | 0 |  | 0%
18 | C | Vanity Counter : supply and installation of 20mm thick honed Volakas, top size of 225mm W x (450 + 150)mm L mitered with 250mm high fascia, including built-in basin total size of 400 x 400 x 440mm. | 1 | No | 4 | Volakas | 20 | 768 | 345 | 1113 | 1113 | 4452 | 0 | 100% | 0% | 100% | 3339 | 1113 | 4452
[13 empty] | 0 |  | 0%
18 | D | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 4 | Volakas | 20 | 25 | 5 | 30 | 30 | 120 | 0 | 100% | 0% | 100% | 120 | 0 | 120
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
18 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 152 | M2 | 4 |  |  | 0 | 8 | 8 | 1216 | 4864 |  | 98.92% | -0.2948% | 98.63% | 4659.4352 | 137.8682 | 4797.3034
[13 empty] | 0 |  | 0%
18 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 81 | M2 | 4 |  |  | 0 | 8 | 8 | 648 | 2592 |  | 98.92% | -0.2948% | 98.63% | 2482.9885 | 73.4692 | 2556.4577
[13 empty] | 0 |  | 0%
18 |  | Total Amount for TYPE -14A | [10 empty] | 0 |  | 0% |  | 334087.8236 | 9885.3374 | 343973.1611
[13 empty] | 0 |  | 0%
19 |  | TYPE -16A (3 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 4.8 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1920 | 5760 | 0 | 100% | 0% | 100% | 5376 | 384 | 5760
[13 empty] | 0 |  | 0%
19 | B | 20mm thick polished Crystal White, maximum 138mm width border. | 1.7 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 829.6 | 2488.8 | 0 | 100% | 0% | 100% | 2322.88 | 165.92 | 2488.8
[13 empty] | 0 |  | 0%
19 | C | 7 x 5mm Brass strip insert in brushed finish. | 9.5 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 541.5 | 1624.5 |  | 66.67% | 0% | 66.67% | 1083 | 0 | 1083
[13 empty] | 0 |  | 0%
19 | D | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 3 | Crystal White | 20 | 123 | 48 | 171 | 171 | 513 | 0 | 100% | 0% | 100% | 478.8 | 34.2 | 513
[13 empty] | 0 |  | 0%
|  | Living Room/Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 10 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 4000 | 12000 | 0 | 100% | 0% | 100% | 12000 | 0 | 12000
[13 empty] | 0 |  | 0%
19 | E | 20mm thick polished Crystal White, cut to size. | 4.2 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 2049.6 | 6148.8 | 0 | 100% | 0% | 100% | 6148.8 | 0 | 6148.8
[13 empty] | 0 |  | 0%
19 | F | 20mm thick polished Crystal White, average of 130mm width border. | 3.6 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 1756.8 | 5270.4 | 0 | 100% | 0% | 100% | 5270.4 | 0 | 5270.4
[13 empty] | 0 |  | 0%
19 | G | 7 x 5mm Brass strip insert in brushed finish. | 24 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 1368 | 4104 |  | 66.67% | 0% | 66.67% | 2736 | 0 | 2736
[13 empty] | 0 |  | 0%
19 | H | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 627 | 1881 |  | 66.67% | 0% | 66.67% | 1254 | 0 | 1254
[13 empty] | 0 |  | 0%
19 | J | 7 x 5mm Brass strip insert in brushed finish. | 11 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 627 | 1881 |  | 66.67% | 0% | 66.67% | 1254 | 0 | 1254
[13 empty] | 0 |  | 0%
19 | K | Threshold (20mm thick polished Crystal White); 300mm wide x 1115mm length. | 1 | No | 3 | Crystal White | 20 | 155 | 62 | 217 | 217 | 651 | 0 | 100% | 0% | 100% | 651 | 0 | 651
[13 empty] | 0 |  | 0%
19 | L | Threshold (20mm thick polished Crystal White); 320mm wide x 925mm length. | 1 | No | 3 | Crystal White | 20 | 128 | 51 | 179 | 179 | 537 | 0 | 100% | 0% | 100% | 537 | 0 | 537
[13 empty] | 0 |  | 0%
19 | M | 7 x 5mm Brass strip insert in brushed finish. 925mm length (only the length between threshold and carpet, other locations are excluded) | 0.93 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 53.01 | 159.03 |  | 66.67% | 0% | 66.67% | 106.02 | 0 | 106.02
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | N | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 1280 | 3840 | 0 | 100% | 0% | 100% | 3840 | 0 | 3840
[13 empty] | 0 |  | 0%
19 | P | 20mm thick polished Crystal White, average 165mm width border. | 1.15 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 561.2 | 1683.6 | 0 | 100% | 0% | 100% | 1683.6 | 0 | 1683.6
[13 empty] | 0 |  | 0%
19 | Q | 7 x 5mm Brass strip insert in brushed finish. | 7.1 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 404.7 | 1214.1 |  | 66.67% | 33.33% | 100% | 809.4 | 404.7 | 1214.1
[13 empty] | 0 |  | 0%
19 | P | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | No | 3 | Crystal White | 20 | 134 | 55 | 189 | 189 | 567 | 0 | 100% | 0% | 100% | 567 | 0 | 567
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 2 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 800 | 2400 | 0 | 100% | 0% | 100% | 2400 | 0 | 2400
[13 empty] | 0 |  | 0%
19 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | E | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.7 | M2 | 3 | Beige Travertine | 20 | 255 | 145 | 400 | 280 | 840 | 0 | 100% | 0% | 100% | 840 | 0 | 840
[13 empty] | 0 |  | 0%
19 | F | 20mm thick polished Crystal White, average of 110mm width border. | 0.5 | M2 | 3 | Crystal White | 20 | 282 | 206 | 488 | 244 | 732 | 0 | 100% | 0% | 100% | 732 | 0 | 732
[13 empty] | 0 |  | 0%
19 | G | 7 x 5mm Brass strip insert in brushed finish. | 3.1 | Lm | 3 | Brass | 5 | 0 | 57 | 57 | 176.7 | 530.1 |  | 66.67% | 33.33% | 100% | 353.4 | 176.7 | 530.1
[13 empty] | 0 |  | 0%
19 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 3 | Crystal White | 20 | 99 | 37 | 136 | 136 | 408 | 0 | 100% | 0% | 100% | 408 | 0 | 408
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | J | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 23.5 | M2 | 3 | PC Rate | 20 | 50 | 100 | 150 | 3525 | 10575 | 0 | 100% | 0% | 100% | 10575 | 0 | 10575
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | K | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 13.6 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 8540.8 | 25622.4 | 0 | 100% | 0% | 100% | 25622.4 | 0 | 25622.4
[13 empty] | 0 |  | 0%
19 | L | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 6.6 | Lm | 3 | Crystal White | 20 | 86 | 48 | 134 | 884.4 | 2653.2 | 0 | 100% | 0% | 100% | 2653.2 | 0 | 2653.2
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 12 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 7536 | 22608 | 0 | 100% | 0% | 100% | 22608 | 0 | 22608
[13 empty] | 0 |  | 0%
19 | A | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 5 | Lm | 3 | Crystal White | 20 | 94 | 56 | 150 | 750 | 2250 | 0 | 100% | 0% | 100% | 2250 | 0 | 2250
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | B | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 3.6 | M2 | 3 | Volakas | 20 | 406 | 222 | 628 | 2260.8 | 6782.4 | 0 | 100% | 0% | 100% | 4521.6 | 2260.8 | 6782.4
[13 empty] | 0 |  | 0%
19 | C | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.3 | Lm | 3 | Crystal White | 20 | 79 | 43 | 122 | 402.6 | 1207.8 | 0 | 100% | 0% | 100% | 1207.8 | 0 | 1207.8
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | D | Living/Bedroom : 300mm wide; total size of 1115 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 815 | 407 | 1222 | 1222 | 3666 | 0 | 66.67% | 0% | 66.67% | 1222 | 1222 | 2444
[13 empty] | 0 |  | 0%
19 | E | Bedroom To WIW : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 3261 | 0 | 66.67% | 0% | 66.67% | 1087 | 1087 | 2174
[13 empty] | 0 |  | 0%
19 | F | Bathroom : (135 + 135)mm wide); total size of 925 x 2430mm high. | 1 | No | 3 | Crystal White | 20 | 733 | 354 | 1087 | 1087 | 3261 | 0 | 66.67% | 0% | 66.67% | 2174 | 0 | 2174
[13 empty] | 0 |  | 0%
19 | G | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 3 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 5784 | 0 | 100% | 0% | 100% | 5784 | 0 | 5784
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | H | Wardrobe Counter (smaller) : supply and installation of 20mm thick honed Volakas size of 650mm W x 665mm L, mitered with 40mm high fascia. | 1 | No | 3 | Crystal White | 20 | 221 | 111 | 332 | 332 | 996 | 1 | 33.33% | 33.33% | 66.67% | 332 | 332 | 664
[13 empty] | 0 |  | 0%
19 | J | Wardrobe Counter : supply and installation of 20mm thick polished Volakas size of 650mm W x 675mm L mitered with 40mm high fascia. | 1 | No | 3 | Crystal White | 20 | 225 | 113 | 338 | 338 | 1014 | 1 | 33.33% | 33.33% | 66.67% | 338 | 338 | 676
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 1900mm length, with 250mm high fascia. Including (b) lower shelf top size of 428mm x 1900mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 6237 | 0 | 100% | 0% | 100% | 4158 | 2079 | 6237
[13 empty] | 0 |  | 0%
|  | Sanitaryware - Stoneworks | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | B | Bath Tub Top @ Bathroom : supply and installation of 20mm thick honed Volakas top size of maximum 100/480mm wide, total size of 930mm wide x 2040mm length. Complete with 590mm high cladding to 3-sides. Frameworks and back support by others. (Basin/Sink, excluded) | 1 | No | 3 | Volakas | 20 | 796 | 309 | 1105 | 1105 | 3315 | 0 | 100% | 0% | 100% | 2210 | 1105 | 3315
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | C | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 225mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 602 | 294 | 896 | 896 | 2688 | 0 | 100% | 0% | 100% | 2688 | 0 | 2688
[13 empty] | 0 |  | 0%
19 | D | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1100mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 3 | Volakas | 20 | 262 | 110 | 372 | 372 | 1116 | 1 | 66.67% | 33.33% | 100% | 744 | 372 | 1116
[13 empty] | 0 |  | 0%
19 | E | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 3 | Volakas | 20 | 44 | 12 | 56 | 112 | 336 | 2 | 66.67% | 33.33% | 100% | 224 | 112 | 336
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 | F | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 950mm length, pencil edge finish. | 1 | No | 3 | Volakas | 20 | 102 | 50 | 152 | 152 | 456 | 0 | 100% | 0% | 100% | 456 | 0 | 456
[13 empty] | 0 |  | 0%
19 | G | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 3 | Volakas | 20 | 25 | 5 | 30 | 30 | 90 | 0 | 100% | 0% | 100% | 60 | 30 | 90
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
19 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 106 | M2 | 3 |  |  | 0 | 8 | 8 | 848 | 2544 |  | 94.35% | 1.088% | 95.44% | 2266.8032 | 161.0856 | 2427.8889
0%
19 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 57 | M2 | 3 |  |  | 0 | 8 | 8 | 456 | 1368 |  | 94.35% | 1.088% | 95.44% | 1218.9414 | 86.6215 | 1305.5629
[13 empty] | 0 |  | 0%
19 |  | Total Amount for TYPE -16A | [10 empty] | 0 |  | 0% |  | 145660.0446 | 10351.0272 | 156011.0718
[13 empty] | 0 |  | 0%
20 |  | TYPE -19A (6 No's) | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Supply and installation of 20mm thisck stone. Frameworks, back support, sanitary wares/ accessories and surface preparation works | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | FLOOR FINISHES | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Foyer | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | A | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 3.1 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 1240 | 7440 | 0 | 100% | 0% | 100% | 7440 | 0 | 7440
[13 empty] | 0 |  | 0%
20 | B | 20mm thick polished Crystal White, maximum 126mm width border. | 1.35 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 658.8 | 3952.8 | 0 | 100% | 0% | 100% | 3952.8 | 0 | 3952.8
[13 empty] | 0 |  | 0%
20 | C | 7 x 5mm Brass strip insert in brushed finish. | 7.2 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 410.4 | 2462.4 |  | 100% | 0% | 100% | 2462.4 | 0 | 2462.4
[13 empty] | 0 |  | 0%
20 | D | 270mm wide x 980mm length polished Crystal White (HTL-ST-01) | 1 | No | 6 | Crystal White | 20 | 123 | 48 | 171 | 171 | 1026 | 0 | 100% | 0% | 100% | 1026 | 0 | 1026
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. (Stone not running under the carpet) | 5.5 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 2200 | 13200 | 0 | 11.11% | 0% | 11.11% | 1466.6667 | 0 | 1466.6667
[13 empty] | 0 |  | 0%
20 | E | 20mm thick polished Crystal White, cut to size. | 3.8 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1854.4 | 11126.4 | 0 | 11.11% | 0% | 11.11% | 1236.2667 | 0 | 1236.2667
[13 empty] | 0 |  | 0%
20 | F | 20mm thick polished Crystal White, average of 150mm width border. | 3.1 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1512.8 | 9076.8 | 0 | 11.11% | 0% | 11.11% | 1008.5333 | 0 | 1008.5333
[13 empty] | 0 |  | 0%
20 | G | 7 x 5mm Brass strip insert in brushed finish. | 18.9 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 1077.3 | 6463.8 |  | 100% | 0% | 100% | 6463.8 | 0 | 6463.8
[13 empty] | 0 |  | 0%
20 | H | 7 x 5mm Brass strip insert in brushed finish. | 16.7 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 951.9 | 5711.4 |  | 100% | 0% | 100% | 5711.4 | 0 | 5711.4
[13 empty] | 0 |  | 0%
20 | J | Threshold (20mm thick polished Crystal White); 350mm wide x 1510mm length. | 1 | No | 6 | Crystal White | 20 | 231 | 97 | 328 | 328 | 1968 | 0 | 11.11% | 0% | 11.11% | 218.6667 | 0 | 218.6667
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | K | 320mm wide x 860mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 125 | 51 | 176 | 176 | 1056 | 0 | 11.11% | 0% | 11.11% | 117.3333 | 0 | 117.3333
[13 empty] | 0 |  | 0%
20 | L | 7 x 5mm Brass strip insert in brushed finish . 860mm length (only the length between threshold and carpet, other locations are excluded) | 9 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 513 | 3078 |  | 100% | 0% | 100% | 3078 | 0 | 3078
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | M | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 11 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 4400 | 26400 | 0 | 100% | 0% | 100% | 26400 | 0 | 26400
[13 empty] | 0 |  | 0%
20 | N | 20mm thick polished Crystal White, average 130mm width border. | 2.15 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 1049.2 | 6295.2 | 0 | 100% | 0% | 100% | 6295.2 | 0 | 6295.2
[13 empty] | 0 |  | 0%
20 | P | 7 x 5mm Brass strip insert in brushed finish. | 14.5 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 826.5 | 4959 |  | 100% | 0% | 100% | 4959 | 0 | 4959
[13 empty] | 0 |  | 0%
20 | Add | Threshold (20mm thick); 320mm wide x 925mm length polished Crystal White. | 1 | No | 6 | Crystal White | 20 | 134 | 55 | 189 | 189 | 1134 | 0 | 100% | 0% | 100% | 1134 | 0 | 1134
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | A | 20mm thick Beige Travertine (anti-gliss treatment, elsewhere). | 1.6 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 640 | 3840 | 0 | 100% | 0% | 100% | 3840 | 0 | 3840
[13 empty] | 0 |  | 0%
20 | C | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | D | 20mm thick brushed (no anti-gliss treatment) Beige Travertine in herringbone pattern as per drawing. | 0.8 | M2 | 6 | Beige Travertine | 20 | 255 | 145 | 400 | 320 | 1920 | 0 | 100% | 0% | 100% | 1920 | 0 | 1920
[13 empty] | 0 |  | 0%
20 | E | 20mm thick polished Crystal White, average of 105mm width border. | 0.5 | M2 | 6 | Crystal White | 20 | 282 | 206 | 488 | 244 | 1464 | 0 | 100% | 0% | 100% | 1464 | 0 | 1464
[13 empty] | 0 |  | 0%
20 | F | 7 x 5mm Brass strip insert in brushed finish. | 3.6 | Lm | 6 | Brass | 5 | 0 | 57 | 57 | 205.2 | 1231.2 |  | 100% | 0% | 100% | 1231.2 | 0 | 1231.2
[13 empty] | 0 |  | 0%
20 | G | Threshold (20mm thick); 235mm wide x 860mm length, polished Crystal White | 1 | No | 6 | Crystal White | 20 | 99 | 37 | 136 | 136 | 816 | 0 | 100% | 0% | 100% | 816 | 0 | 816
[13 empty] | 0 |  | 0%
|  | Balcony Floor Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | H | Add Travertine balcony flooring at supply PC rate of AED50/sqm and install PC rate of AED100/sqm | 39 | M2 | 6 | PC Rate | 20 | 50 | 100 | 150 | 5850 | 35100 | 0 | 100% | 0% | 100% | 35100 | 0 | 35100
[13 empty] | 0 |  | 0%
|  | Wall Finishes | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | J | Supply and installation of 20mm thick polished Crystal White (150 + 50)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 7.7 | Lm | 6 | Crystal White | 20 | 86 | 48 | 134 | 1031.8 | 6190.8 | 0 | 100% | 0% | 100% | 6190.8 | 0 | 6190.8
[13 empty] | 0 |  | 0%
20 | Add | Supply and installation of 20mm thick polished Volakas as per drawing and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 12.2 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 7661.6 | 45969.6 | 0 | 100% | 0% | 100% | 45969.6 | 0 | 45969.6
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | K | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick. Frameworks and back support by others. | 10.6 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 6656.8 | 39940.8 | 0 | 100% | 0% | 100% | 39940.8 | 0 | 39940.8
[13 empty] | 0 |  | 0%
20 | L | Supply and installation of 20mm thick polished Crystal White (200 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 4.4 | Lm | 6 | Crystal White | 20 | 94 | 56 | 150 | 660 | 3960 | 0 | 100% | 0% | 100% | 3960 | 0 | 3960
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | M | Supply and installation of 20mm thick polished Volakas and to be fixed with standard cementitious adhesive maximum up to 5mm thick, including 20 x 35mm W daddo, pencil edge finish. Frameworks and back support by others. | 4.1 | M2 | 6 | Volakas | 20 | 406 | 222 | 628 | 2574.8 | 15448.8 | 0 | 100% | 0% | 100% | 15448.8 | 0 | 15448.8
[13 empty] | 0 |  | 0%
20 | A | Supply and installation of 20mm thick polished Crystal White (150 + 30)mm high skirting L-shape (2 pcs. Stone), chamfered edge. | 3.7 | Lm | 6 | Crystal White | 20 | 79 | 43 | 122 | 451.4 | 2708.4 | 0 | 100% | 0% | 100% | 2708.4 | 0 | 2708.4
[13 empty] | 0 |  | 0%
|  | Stone to Doors | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing. | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | B | Bedroom : 300mm wide; total size of 1510 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 869 | 433 | 1302 | 1302 | 7812 | 0 | 100% | 0% | 100% | 7812 | 0 | 7812
[13 empty] | 0 |  | 0%
20 | C | Foyer To WIW : (135 + 135)mm wide); total size of 860 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 724 | 350 | 1074 | 1074 | 6444 | 6 | 0% | 100% | 100% | 0 | 6444 | 6444
[13 empty] | 0 |  | 0%
20 | D | Bathroom : (145 + 160)mm wide); total size of 860 x 2430mm high. | 1 | No | 6 | Crystal White | 20 | 789 | 395 | 1184 | 1184 | 7104 | 0 | 100% | 0% | 100% | 7104 | 0 | 7104
[13 empty] | 0 |  | 0%
20 | E | Shower/Toilet : 235mm wide; total size of 860 x 2430mm high. | 2 | No | 6 | Crystal White | 20 | 660 | 304 | 964 | 1928 | 11568 | 0 | 100% | 0% | 100% | 11568 | 0 | 11568
[13 empty] | 0 |  | 0%
|  | Joinery Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
|  | Bedroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | F | Counter @ Mini Bar : Supply and installation of 20mm thick polished Crystal White size of 575 x 660mm length, mitered with 40mm high fascia, (full high cladding to 2 sides, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 200 | 99 | 299 | 299 | 1794 | 0 | 100% | 0% | 100% | 1794 | 0 | 1794
[13 empty] | 0 |  | 0%
20 | G | Cladding @ Mini Bar : Supply and installation of 20mm thick polished Volakas size of (a) 595mm wide x 1535mm high cladding to 2 sides having (b) 30mm width complete front frame and (c) soffit/ceiling. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 1172 | 654 | 1826 | 1826 | 10956 | 0 | 100% | 0% | 100% | 10956 | 0 | 10956
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | H | Counter Top @ Walk-In Closet (smaller) : Supply and installation of 20mm thick polished Crystal White size of 580 x 995mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 286 | 149 | 435 | 435 | 2610 | 0 | 100% | 0% | 100% | 2610 | 0 | 2610
[13 empty] | 0 |  | 0%
|  | Walk-In Closet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | J | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 580 x 1670mm length, mitered with 40mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Crystal White | 20 | 457 | 250 | 707 | 707 | 4242 | 0 | 100% | 0% | 100% | 4242 | 0 | 4242
[13 empty] | 0 |  | 0%
|  | Bathroom | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | A | Vanity Counter @ Bathroom : Supply and installation of 20mm thick polished Volakas top size of (a) 561mm wide x 2867mm length, with 250mm high fascia. Including lower shelf top size of 428mm x 2867mm length, mitered with 40mm high fascia. Complete with cut outs, back and 2 nos of side (full height) cladding. (niche surround, shelf, and back support elsewhere). | 1 | No | 6 | Volakas | 20 | 1437 | 642 | 2079 | 2079 | 12474 | 0 | 100% | 0% | 100% | 12474 | 0 | 12474
[13 empty] | 0 |  | 0%
20 | B | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 170mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 2 | No | 6 | Volakas | 20 | 519 | 254 | 773 | 1546 | 9276 | 0 | 100% | 0% | 100% | 9276 | 0 | 9276
[13 empty] | 0 |  | 0%
20 | C | Shelf @ Bathroom Vanity : Supply and installation of 20mm thick polished Volakas shelf top size of 150mm W x 630mm length mitered with 50mm high fascia with soffit (vanity counter, niche and cladding, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 68 | 31 | 99 | 99 | 594 | 0 | 100% | 0% | 100% | 594 | 0 | 594
[13 empty] | 0 |  | 0%
|  | Sanitaryware - Stoneworks | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | D | Bath Tub Base : Supply and installation of (20+20)mm thick (no anti-gliss treatment) Beige Travertine stone to bath tub base having overall size of 1495mm L x 470mm W (4 pieces), including waterjet cutting. | 1 | No | 6 | Beige Travertine | 20 | 730 | 214 | 944 | 944 | 5664 | 0 | 100% | 0% | 100% | 4720 | 944 | 5664
[13 empty] | 0 |  | 0%
|  | Shower | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | E | Niche Surround @ Shower : Supply and installation of 20mm thick polished Volakas niche surround at 200mm depth, total size of 610 wide x 975mm high. (cladding, elsewhere). Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 565 | 276 | 841 | 841 | 5046 | 0 | 100% | 0% | 100% | 5046 | 0 | 5046
[13 empty] | 0 |  | 0%
20 | F | Bench : Supply and installation of 20mm thick polished Volakas, 360mm W x 1180mm L, mitered with 60mm high fascia. Frameworks and back support by others. | 1 | No | 6 | Volakas | 20 | 282 | 119 | 401 | 401 | 2406 | 0 | 100% | 0% | 100% | 2406 | 0 | 2406
[13 empty] | 0 |  | 0%
20 | G | Foot Upstand @ Shower Bench (Provisionary Rate) : Supply and installation of 20mm thick polished Volakas foot upstand at bench having total size of 150mm H x 150mm W x 150mm L, edges chamfered. Frameworks and back support by others. | 2 | No | 6 | Volakas | 20 | 44 | 12 | 56 | 112 | 672 | 0 | 100% | 0% | 100% | 672 | 0 | 672
[13 empty] | 0 |  | 0%
|  | Toilet | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 | H | Cistern Top @ Toilet; Supply and installation of 20mm thick polished Volakas, 220mm W x 1085mm length, pencil edge finish. | 1 | No | 6 | Volakas | 20 | 116 | 57 | 173 | 173 | 1038 | 0 | 100% | 0% | 100% | 1038 | 0 | 1038
[13 empty] | 0 |  | 0%
20 | J | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Volakas shelf size of 120mm W x 200mm L, edges chamfered. | 1 | No | 6 | Volakas | 20 | 25 | 5 | 30 | 30 | 180 | 0 | 100% | 0% | 100% | 180 | 0 | 180
[13 empty] | 0 |  | 0%
|  | Miscellaneous Items | [10 empty] | 0 |  | 0%
[13 empty] | 0 |  | 0%
20 |  | Extra over charges for standard sealer coating to top surface of stone if required. | 143 | M2 | 6 |  |  | 0 | 8 | 8 | 1144 | 6864 |  | 89.05% | 1.817% | 90.87% | 6094.292 | 142.9954 | 6237.2874
0%
20 |  | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 73 | M2 | 6 |  |  | 0 | 8 | 8 | 584 | 3504 |  | 89.05% | 1.817% | 90.87% | 3111.0721 | 72.9977 | 3184.0698
20 |  | Total Amount for TYPE -19A | [14 empty] | 324073.0307 | 7603.9931 | 331677.0238
189.0583

## Work progress Summary
Work Progress Summary
Room Type | No of Units | FLORING INC. BORDER | [6 empty] | BRASS STRIP |  |  |  |  | WALL |  |  | SKIRTING |  |  | ARCHITRAVE |  |  |  |  | JOINARY ITEMS
|  | FOYER | LIVING | BED RM | BATH RM | SHOWER | TOILET | BALCONY | FOYER | LIVING | BED RM | BATH RM | TOILET | BATH RM | SHOWER | TOILET | BATH RM | SHOWER | TOILET | FOYER | BED RM | BATH RM | SHOWER | TOILET | COUNTER TOP | MINI BAR | VANITY | NICHE | SHELF | BATHTUB | BENCH | CISTERN TOP
1A | 8 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 87.5% | 87.5% | 100% | 100% | 87.5% | 87.5% | 100% | 100% | 100% | 50% | 100% | 100%
1B/1C | 6 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2A/2B/2C/2D | 44 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97.73% | 100% | 97.73% | 97.73% | 97.73% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 93.18% | 93.18% | 95.45% | 95.45% | 100% | 90.91% | 100% | 100% | 100% | 100% | 100% | 100%
2E/2F/2G/2H | 27 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 96.3% | 96.3% | 96.3% | 96.3% | 100% | 92.59% | 100% | 100% | 100% | 100% | 100% | 100%
3A/3B/3D/3E/3G | 39 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97.44% | 100% | 97.44% | 97.44% | 97.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 97.44% | 100% | 100% | 100% | 97.44% | 97.44% | 100% | 100% | 100% | 93.59% | 100% | 100%
3C/3F | 18 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 94.44% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 94.44% | 100% | 100% | 100% | 100% | 97.22% | 100%
4A/4B | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5A | 9 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 88.89% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 88.89% | 100% | 100% | 100% | 100% | 88.89% | 100% | 100% | 100% | 100% | 100% | 100%
6A | 5 | 100% | 20% | 100% | 100% | 100% | 100% | 100% | 100% | 20% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 100% | 80% | 100% | 100% | 100% | 60% | 100% | 100% | 100% | 80% | 100% | 100%
8A | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9A | 2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9B | 2 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10A | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10B | 3 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
11A/11B/11C/11D | 19 | 98.95% | 88.42% | 96.32% | 96.84% | 89.47% | 97.89% | 100% | 84.21% | 73.68% | 78.95% | 84.21% | 78.95% | 100% | 100% | 100% | 100% | 100% | 100% | 57.89% | 73.68% | 78.95% | 94.74% | 94.74% | 81.58% | 76.32% | 97.37% | 100% | 100% | 100% | 100% | 100%
12A | 5 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 60% | 80% | 100% | 100% | 100% | 100% | 100%
13A | 1 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
14A | 4 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 75% | 100% | 25% | 100% | 100% | 25% | 0% | 100% | 100% | 100% | 87.5% | 100% | 100%
16A | 3 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 66.67% | 66.67% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 66.67% | 66.67% | 66.67% | 100% | 100% | 66.67% | 66.67% | 100% | 100% | 100% | 100% | 100% | 100%
19A | 6 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
PROV.SUM | 9 | 11.11% | 100% | 11.11% | 55.56% | 55.56% | 55.56% | 100% | 0% | 100% | 0% | 0% | 22.22% | 66.67% | 66.67% | 66.67% | 22.22% | 33.33% | 66.67% | 100% | 0% | 0% | 0% | 0% | 0% | 0% | 11.11% | 0% | 0% | 5.556% | 0% | 22.22%
225

## Work progress Summary BreakDown
SR NO | LEVEL | ROOM NAME | ROOM TYPE | ROOM NO | ROOM CATEGORY | FLORING INC. BORDER | [6 empty] | BRASS STRIP |  |  |  |  | WALL |  |  | SKIRTING |  |  | ARCHITRAVE |  |  |  |  | JOINARY ITEMS
[6 empty] | FOYER | LIVING | BED RM | BATH RM | SHOWER | TOILET | BALCONY | FOYER | LIVING | BED RM | BATH RM | TOILET | BATH RM | SHOWER | TOILET | BATH RM | SHOWER | TOILET | FOYER | BED RM | BATH RM | SHOWER | TOILET | COUNTER TOP | MINI BAR | VANITY | NICHE | SHELF | BATHTUB | BENCH | CISTERN TOP
1 | 7 | 1 BEDROOM | 8A | 701 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
2 | 7 | STD. GUEST | 2B | 702 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
3 | 7 | STD. GUEST | 2C | 703 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
4 | 7 | STD. GUEST | 3A | 704 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
5 | 7 | STD. GUEST | 3D | 705 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
6 | 7 | STD. GUEST | 2A | 706 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
7 | 7 | CORNER. GUEST | 19A | 708 | 19A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
8 | 7 | STD. GUEST | 1C | 709 | 1B/1C | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
9 | 7 | JUNIOR SUITE | 4B | 710 | 4A/4B | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
10 | 7 | DELUX SUITE | 7A |  | PROV.SUM | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% |  | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% |  | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 100%
11 | 8 | 1 BEDROOM | 8A | 801 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
12 | 8 | STD. GUEST | 2B | 802 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
13 | 8 | STD. GUEST | 2C | 803 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
14 | 8 | STD. GUEST | 3A | 804 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
15 | 8 | STD. GUEST | 3D | 805 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
16 | 8 | STD. GUEST | 2A | 806 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
17 | 8 | STD. GUEST | 1B | 807 | 1B/1C | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
18 | 8 | JUNIOR SUITE | 4A | 808 | 4A/4B | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
19 | 9 | 1 BEDROOM | 8A | 901 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
20 | 9 | STD. GUEST | 2B | 902 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
21 | 9 | STD. GUEST | 2C | 903 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
22 | 9 | STD. GUEST | 3A | 904 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
23 | 9 | STD. GUEST | 3D | 905 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
24 | 9 | STD. GUEST | 2A | 906 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
25 | 9 | 1 BEDROOM | 9A | 907 | 9A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
26 | 9 | 1 BEDROOM | 9B | 908 | 9B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
27 | 9 | STD. GUEST | 1B | 909 | 1B/1C | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
28 | 9 | JUNIOR SUITE | 4A | 910 | 4A/4B | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
29 | 10 | 1 BEDROOM | 8A | 1001 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
30 | 10 | STD. GUEST | 2B | 1002 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
31 | 10 | STD. GUEST | 2C | 1003 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
32 | 10 | STD. GUEST | 3A | 1004 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
33 | 10 | STD. GUEST | 3D | 1005 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
34 | 10 | STD. GUEST | 2A | 1006 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
35 | 10 | STD. GUEST | 1B | 1008 | 1B/1C | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
36 | 10 | JUNIOR SUITE | 4A | 1009 | 4A/4B | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
37 | 10 | DOUBLE HT | 15A |  | PROV.SUM | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 100% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
38 | 11 | 1 BEDROOM | 8A | 1101 | 8A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
39 | 11 | STD. GUEST | 2B | 1102 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
40 | 11 | STD. GUEST | 2C | 1103 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
41 | 11 | STD. GUEST | 3A | 1104 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
42 | 11 | STD. GUEST | 3D | 1105 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
43 | 11 | STD. GUEST | 2A | 1106 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
44 | 11 | CORNER. GUEST | 16A | 1107 | 16A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
45 | 11 | STD. GUEST | 1B | 1108 | 1B/1C | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
46 | 11 | JUNIOR SUITE | 4A | 1109 | 4A/4B | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
47 | 12 | 1 BEDROOM | 10A | 1201 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
48 | 12 | STD. GUEST | 3G | 1202 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
49 | 12 | STD. GUEST | 2B | 1203 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
50 | 12 | DELUX SUITE | 11C | 1204 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
51 | 12 | STD. GUEST | 3D | 1205 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
52 | 12 | STD. GUEST | 2B | 1206 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
53 | 12 | DELUX SUITE | 11C | 1207 | 11A/11B/11C/11D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
54 | 12 | STD. GUEST | 3D | 1208 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
55 | 12 | STD. GUEST | 2A | 1209 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
56 | 12 | 1 BEDROOM | 9A | 1210 | 9A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
57 | 12 | 1 BEDROOM | 9B | 1211 | 9B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
58 | 12 | STD. GUEST | 1A | 1212 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
59 | 12 | STD. GUEST | 2F | 1213 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
60 | 12 | STD. GUEST | 3C | 1214 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
61 | 12 | STD. GUEST | 3F | 1215 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
62 | 12 | STD. GUEST | 2G | 1216 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
63 | 12 | STD. GUEST | 2E | 1217 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
64 | 12 | JUNIOR SUITE | 5A | 1218 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
65 | 13 | 1 BEDROOM | 10A | 1301 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
66 | 13 | STD. GUEST | 3G | 1302 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
67 | 13 | STD. GUEST | 2B | 1303 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
68 | 13 | DELUX SUITE | 11C | 1304 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
69 | 13 | STD. GUEST | 3D | 1305 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
70 | 13 | STD. GUEST | 2B | 1306 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
71 | 13 | DELUX SUITE | 11C | 1307 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
72 | 13 | STD. GUEST | 3D | 1308 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
73 | 13 | STD. GUEST | 2A | 1309 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
74 | 13 | CORNER. GUEST | 19A | 1311 | 19A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
75 | 13 | STD. GUEST | 1A | 1312 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
76 | 13 | STD. GUEST | 2F | 1313 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
77 | 13 | STD. GUEST | 3C | 1314 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
78 | 13 | STD. GUEST | 3F | 1315 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
79 | 13 | STD. GUEST | 2G | 1316 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
80 | 13 | STD. GUEST | 2E | 1317 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
81 | 13 | JUNIOR SUITE | 5A | 1318 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
82 | 13 | DELUX SUITE | 7A |  | PROV.SUM | 0% |  | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 0% | 0% | 100% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
83 | 14 | 1 BEDROOM | 10A | 1401 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
84 | 14 | STD. GUEST | 3G | 1402 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
85 | 14 | STD. GUEST | 2B | 1403 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
86 | 14 | DELUX SUITE | 11C | 1404 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
87 | 14 | STD. GUEST | 3D | 1405 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
88 | 14 | STD. GUEST | 2B | 1406 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
89 | 14 | DELUX SUITE | 11C | 1407 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
90 | 14 | STD. GUEST | 3D | 1408 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
91 | 14 | STD. GUEST | 2A | 1409 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
92 | 14 | STD. GUEST | 1A | 1410 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
93 | 14 | STD. GUEST | 2F | 1411 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
94 | 14 | STD. GUEST | 3C | 1412 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
95 | 14 | STD. GUEST | 3F | 1413 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
96 | 14 | STD. GUEST | 2G | 1414 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
97 | 14 | STD. GUEST | 2E | 1415 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
98 | 14 | JUNIOR SUITE | 5A | 1416 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | TRUE
99 | 15 | 1 BEDROOM | 10A | 1501 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
100 | 15 | STD. GUEST | 3G | 1502 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
101 | 15 | STD. GUEST | 2B | 1503 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
102 | 15 | DELUX SUITE | 11C | 1504 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
103 | 15 | STD. GUEST | 3D | 1505 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
104 | 15 | STD. GUEST | 2B | 1506 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
105 | 15 | DELUX SUITE | 11C | 1507 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
106 | 15 | STD. GUEST | 3D | 1508 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
107 | 15 | STD. GUEST | 2A | 1509 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
108 | 15 | CORNER. GUEST | 19A | 1511 | 19A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
109 | 15 | STD. GUEST | 1A | 1512 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
110 | 15 | STD. GUEST | 2F | 1513 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
111 | 15 | STD. GUEST | 3C | 1514 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
112 | 15 | STD. GUEST | 3F | 1515 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
113 | 15 | STD. GUEST | 2G | 1516 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
114 | 15 | STD. GUEST | 2E | 1517 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
115 | 15 | JUNIOR SUITE | 5A | 1518 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | TRUE
116 | 15 | DELUX SUITE | 7A |  | PROV.SUM | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 0% | 0% | 100% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
117 | 16 | 1 BEDROOM | 10A | 1601 | 10A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
118 | 16 | DELUX SUITE | 11D | 1602 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100%
119 | 16 | STD. GUEST | 2C | 1603 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
120 | 16 | STD. GUEST | 3A | 1604 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
121 | 16 | STD. GUEST | 3D | 1605 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
122 | 16 | STD. GUEST | 2B | 1606 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
123 | 16 | DELUX SUITE | 11C | 1607 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
124 | 16 | STD. GUEST | 3D | 1608 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
125 | 16 | STD. GUEST | 2A | 1609 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
126 | 16 | STD. GUEST | 1C | 1610 | 1B/1C | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
127 | 16 | STD. GUEST | 2H | 1611 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
128 | 16 | STD. GUEST | 3C | 1612 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
129 | 16 | STD. GUEST | 3F | 1613 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
130 | 16 | STD. GUEST | 2G | 1614 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
131 | 16 | STD. GUEST | 2E | 1615 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
132 | 16 | JUNIOR SUITE | 5A | 1616 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 99.89% | 100% | FALSE
135 | 19 | 1 BEDROOM | 12A | 1901 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
136 | 19 | CORNER. GUEST | 19A | 1903 | 19A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
137 | 19 | JUNIOR SUITE | 6A | 1904 | 6A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
138 | 19 | PRESIDENTIAL | 17A |  | PROV.SUM | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
139 | 20 | 1 BEDROOM | 12A | 2001 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
140 | 20 | STD. GUEST | 2D | 2002 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
141 | 20 | STD. GUEST | 3A | 2003 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
142 | 20 | DELUX SUITE | 11B | 2004 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
143 | 20 | CORNER. GUEST | 19A | 2006 | 19A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
144 | 20 | JUNIOR SUITE | 6A | 2007 | 6A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
145 | 20 | DELUX SUITE | 7A |  | PROV.SUM | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
146 | 21 | 1 BEDROOM | 12A | 2101 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
147 | 21 | STD. GUEST | 2D | 2102 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
148 | 21 | STD. GUEST | 3A | 2103 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
149 | 21 | DELUX SUITE | 11B | 2104 | 11A/11B/11C/11D | 80% | 80% | 80% | 80% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
150 | 21 | JUNIOR SUITE | 6A | 2105 | 6A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 100% | 100%
151 | 22 | 1 BEDROOM | 12A | 2201 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100%
152 | 22 | DELUX SUITE | 11A | 2202 | 11A/11B/11C/11D | 100% | 100% | 50% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 50% | 50% | 100% | 100% | 100% | 100% | 100% | 100%
153 | 22 | STD. GUEST | 3D | 2203 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
154 | 22 | STD. GUEST | 2A | 2204 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
155 | 22 | JUNIOR SUITE | 6A | 2206 | 6A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 0% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
156 | 22 | DOUBLE HT | 15A |  | PROV.SUM | 0% | 0% | 0% | 0% | 0% | 0% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 50% | 0% | 0%
157 | 23 | 1 BEDROOM | 12A | 2301 | 12A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
158 | 23 | STD. GUEST | 2D | 2302 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
159 | 23 | STD. GUEST | 3A | 2303 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
160 | 23 | DELUX SUITE | 11B | 2304 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
161 | 23 | CORNER. GUEST | 16A | 2305 | 16A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
162 | 23 | JUNIOR SUITE | 6A | 2306 | 6A | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
163 | 24 | 1 BEDROOM | 13A | 2401 | 13A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
164 | 24 | 1 BEDROOM | 14A | 2402 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 50% | 100% | 100%
165 | 24 | STD. GUEST | 2D | 2403 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
166 | 24 | STD. GUEST | 3A | 2404 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
167 | 24 | STD. GUEST | 3D | 2405 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
168 | 24 | STD. GUEST | 2B | 2406 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
169 | 24 | DELUX SUITE | 11C | 2407 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
170 | 24 | STD. GUEST | 3D | 2408 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100% | 100%
171 | 24 | STD. GUEST | 2B | 2409 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
172 | 24 | CORNER. GUEST | 19A | 2411 | 19A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
173 | 24 | STD. GUEST | 1A | 2412 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100%
174 | 24 | STD. GUEST | 2F | 2413 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
175 | 24 | STD. GUEST | 3C | 2414 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
176 | 24 | STD. GUEST | 3F | 2415 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
177 | 24 | STD. GUEST | 2G | 2416 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
178 | 24 | STD. GUEST | 2E | 2417 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
179 | 24 | JUNIOR SUITE | 5A | 2418 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
180 | 24 | DELUX SUITE | 7A |  | PROV.SUM | 0% |  | 0% | 100% | 100% | 100% | 100% | 0% |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 100%
181 | 25 | 1 BEDROOM | 10B | 2501 | 10B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
182 | 25 | 1 BEDROOM | 14A | 2502 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
183 | 25 | STD. GUEST | 2D | 2503 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 4000000
184 | 25 | STD. GUEST | 3A | 2504 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
185 | 25 | STD. GUEST | 3D | 2505 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 300000
186 | 25 | STD. GUEST | 2B | 2506 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  |  | 400000
187 | 25 | DELUX SUITE | 11C | 2507 | 11A/11B/11C/11D | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
188 | 25 | STD. GUEST | 3D | 2508 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
189 | 25 | STD. GUEST | 2B | 2509 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
190 | 25 | STD. GUEST | 1A | 2510 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100%
191 | 25 | STD. GUEST | 2F | 2511 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
192 | 25 | STD. GUEST | 3C | 2512 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 50% | 100%
193 | 25 | STD. GUEST | 3F | 2513 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
194 | 25 | STD. GUEST | 2G | 2514 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
195 | 25 | STD. GUEST | 2E | 2515 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
196 | 25 | JUNIOR SUITE | 5A | 2516 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
197 | 26 | 1 BEDROOM | 10B | 2601 | 10B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
198 | 26 | 1 BEDROOM | 14A | 2602 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
199 | 26 | STD. GUEST | 2D | 2603 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
200 | 26 | STD. GUEST | 3A | 2604 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
201 | 26 | DELUX SUITE | 11D | 2605 | 11A/11B/11C/11D | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% |  | 0% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
202 | 26 | STD. GUEST | 2C | 2606 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
203 | 26 | STD. GUEST | 3A | 2607 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 99.93% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
204 | 26 | STD. GUEST | 1A | 2609 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 0% | 100% | 100%
205 | 26 | STD. GUEST | 2F | 2610 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
206 | 26 | STD. GUEST | 3C | 2611 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
207 | 26 | STD. GUEST | 3F | 2612 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
208 | 26 | STD. GUEST | 2G | 2613 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
209 | 26 | STD. GUEST | 2E | 2614 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
210 | 26 | JUNIOR SUITE | 5A | 2615 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
211 | 26 | ROYAL | 18A |  | PROV.SUM | 0% |  | 0% | 0% | 0% | 0% | 100% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% |  | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0%
212 | 27 | 1 BEDROOM | 10B | 2701 | 10B | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
213 | 27 | 1 BEDROOM | 14A | 2702 | 14A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
214 | 27 | STD. GUEST | 2D | 2703 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
215 | 27 | STD. GUEST | 3A | 2704 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100%
216 | 27 | DELUX SUITE | 11B | 2705 | 11A/11B/11C/11D | 100% | 100% | 100% | 80% | 0% | 80% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
217 | 27 | STD. GUEST | 2C | 2706 | 2A/2B/2C/2D | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
218 | 27 | STD. GUEST | 3A | 2707 | 3A/3B/3D/3E/3G | 100% |  | 100% | 100% | 100% | 100% | 100% | 0% |  | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 100% | 100% | 100% | 100% | 0% | 100% | 100% | 100% | 0% | 100% | 100%
219 | 27 | DELUX SUITE | 11D | 2708 | 11A/11B/11C/11D | 100% | 100% | 100% | 80% | 0% | 80% | 100% | 0% | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
220 | 27 | CORNER. GUEST | 16A | 2709 | 16A | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 0% | 0% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
221 | 27 | STD. GUEST | 1A | 2710 | 1A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 0% | 100% | 100%
222 | 27 | STD. GUEST | 2F | 2711 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
223 | 27 | STD. GUEST | 3C | 2712 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 0% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
224 | 27 | STD. GUEST | 3F | 2713 | 3C/3F | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 0% | 0% | 100% | 100% | 100% | 100% | 100% | 100%
225 | 27 | STD. GUEST | 2G | 2714 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
226 | 27 | STD. GUEST | 2E | 2715 | 2E/2F/2G/2H | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%
227 | 27 | JUNIOR SUITE | 5A | 2716 | 5A | 100% |  | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% |  | 0% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100%

## MOS Summary (hidden)
MOS Summary - Dar (Guest Rooms)
| Description | QTY | Unit
1 | Material Qty considered for December,2021 Payment | 0 | m2
2 | New Deliveries from February to June | 0
3 | Deduct this month progress | -189.0583
4 | Material Stock Qty for this month (January,2022) | -189.0583
5 | Agreed rate for Materials | 300 | AED
6 | Material to be certifed under this payment | -56717.4817 | AED
7 | MOS @ 75% | -42538.1113

## MOS Deliveries (hidden)
S.I | Jc No | Level | Room No | R. Type | Scope | Material | Deliver Qty( M Sq.) | Certified Qty | Remarks | Date
From 05th January to 13th January
1 | MM-3140-195 | 25 | 2515 | 2E | wall(CL) | Volkas | 33.45 | 33.45 |  | 2022-01-05
2 | MM-3140-217 | 25 | 2501 | 10B | wall(CL) | Volkas Polished | 44.16 | 44.16 |  | 2022-01-05
3 | MM-3140-222 | 25 | 2507 | 11C | Dado, Wall, Border Skirting | Volkas Polished | 34.12 | 34.12 |  | 2022-01-05
4 | MM-3140-001-Dr | Different rooms |  |  | Bathroom Drain | Travertine | 1.53 | 1.53 |  | 2022-01-10
5 | MM-3140-002-Dr | Different rooms |  |  | Bathroom Drain | Travertine | 1.55 | 1.55 |  | 2022-01-10
6 | MM-3140-002-Dr | Different rooms |  |  | Bathroom Drain | Crystal white polished | 3.27 | 3.27 |  | 2022-01-10
7 | MM-3140-287 Revised | 8 | 807 (Uper & Lower level) | 07A | wall(CL) | crystal white | 1.61 | 1.61 |  | 2022-01-10
8 | MM-3140-334 | 25 | 2510 (Uper & Lower level) | 7A | wall(CL) | crystal white | 1.61 | 1.61 |  | 2022-01-10
9 | MM-3140-215 | 25 | 2503 | 02D | wall(CL) | Volkas Polished | 36.26 | 36.26 |  | 2022-01-12
10 | MM-3140-151 | 25 | 2502 | 14A | wall(CL) | Volkas Polished | 29.59 | 29.59 |  | 2022-01-12
11 | MM-3140-151 | 25 | 2502 | 14A | VT Self & Bench | Volkas Polished | 1.94 | 1.94 |  | 2022-01-13
12 | MM-3140-195 | 25 | 2515 | 2E | VT Self & Bench | Volkas Polished | 1.69 | 1.69 |  | 2022-01-13
13 | MM-3140-215 | 25 | 2503 | 02D | VT Self & Bench | Volkas Polished | 1.55 | 1.55 |  | 2022-01-13
From 14th January to 22nd January
1 | MM-3140-193A | 27 | 2714 | 2G | floor(FL) | Travertine | 18.31 | 18.31 |  | 2022-01-14
2 | MM-3140-287 Revised | 8 | 807 | 07A | wall(CL) | Perlato Queen Beige | 28.4 | 28.4 |  | 2022-01-15
3 | MM-3140-288 revised | 14 | 1410 | 07A | wall(CL) | Perlato Queen Beige | 27.98 | 27.98 |  | 2022-01-15
4 | MM-3140-196 | 26 | 2614 | 2E | wall(CL) | Volkas | 31.44 | 31.44 |  | 2022-01-17
5 | MM-3140-128G | 15 | 1511 | 19A | MINI BAR(MB) | volkas polished | 3.04 | 3.04 |  | 2022-01-17
6 | MM-3140-128G | 15 | 1511 | 19A | MINI BAR(MB) | crystal white | 0.4 | 0.4 |  | 2022-01-17
7 | M-3140-129G | 13 | 1311 | 19A | Minibar | Volkas | 3.04 | 3.04 |  | 2022-01-17
8 | M-3140-129G | 13 | 1311 | 19A | Minibar | crystal white | 0.4 | 0.4 |  | 2022-01-17
9 | MM-3140-199G | 20 | 2006 | 19A | MINI BAR(MB) | volkas polished | 3.04 | 3.04 |  | 2022-01-17
10 | MM-3140-199G | 20 | 2006 | 19A | MINI BAR(MB) | crystal white | 0.4 | 0.4 |  | 2022-01-17
11 | MM-3140-233G | 19 | 1903 | 19A | MINI BAR(MB) | volkas polished | 3.04 | 3.04 |  | 2022-01-17
12 | MM-3140-233G | 19 | 1903 | 19A | MINI BAR(MB) | crystal white | 0.4 | 0.4 |  | 2022-01-17
13 | MM-3140-234G | 24 | 2411 | 19A | Minibar | Volkas | 3.04 | 3.04 |  | 2022-01-17
14 | MM-3140-234G | 24 | 2411 | 19A | Minibar | Crytsal white | 0.4 | 0.4 |  | 2022-01-17
15 | MM-3140-167 | 26 | 2607 | 03A | wall(CL) | Volkas polished | 28.72 | 28.72 |  | 2022-01-17
16 | MM-3140-183 | 25 | 2512 | 3C | wall(CL) | Volkas polished | 30.66 | 30.66 |  | 2022-01-18
17 | MM-3140-213CC | 16 | 1617 | 05A | Curve floor(FL) | travertine | 5.92 | 5.92 |  | 2022-01-18
18 | MM-3140-335MK | 7 | 707 | 07A | Stair | Dark Emperador | 1.57 | 1.57 |  | 2022-01-19
19 | MM-3140-169A rev 01 | 27 | 2707 | 3A | floor(FL) | Travertine | 21.72 | 21.72 |  | 2022-01-20
20 | MM-3140-289 revised | 16 | 1610 | 07A | wall(CL) | Perlato Queen Beige | 26.25 | 26.25 |  | 2022-01-20
21 | MM-3140-214 | 26 | 2606 | 2C | wall(CL) | Volkas polished | 35.39 | 35.39 |  | 2022-01-20
22 | MM-3140-222 | 25 | 2507 | 11C | Dado, Wall, Border Skirting | Volkas Polished | 3.28 | 3.28 |  | 2022-01-21
23 | MM-3140-176A | 26 | 2609 | 1A | Shower floor(FL) | Travertine | 2.97 | 2.97 |  | 2022-01-21
24 | MM-3140-235A | 19 | 1904 | 06A | Shower floor(FL) | travertine | 1.82 | 1.82 |  | 2022-01-21
25 | MM-3140-286A | 27 | 2706 | 2C | Shower floor(FL) | Travertine | 2.52 | 2.52 |  | 2022-01-21
26 | MM-3140-283A | 23 | 2305 | 16A | Shower floor(FL) | Travertine | 2.3 | 2.3 |  | 2022-01-21
27 | MM-3140-175A | 25 | 2510 | 1A | Shower floor(FL) | Travertine | 2.86 | 2.86 |  | 2022-01-21
28 | MM-3140-173A | 22 | 2204 | 02A | Shower floor(FL) | Travertine | 2.82 | 2.82 |  | 2022-01-21
29 | MM-3140-231A | 27 | 2702 | 14A | Shower floor(FL) | Travertine | 2.51 | 2.51 |  | 2022-01-21
30 | MM-3140-151 | 25 | 2502 | 14A | wall(CL) | Volkas Polished | 8.2 | 8.2 |  | 2022-01-21
31 | MM-3140-150CC | 20 | 2007 | 06A | Bathroom skirting(SK) | Crystal White | 0.95 | 0.95 |  | 2022-01-21
32 | MM-3140-206CC | 21 | 2105 but as per site 2107 | 06A | Bathroom skirting(SK) | Crystal White | 0.95 | 0.95 |  | 2022-01-21
33 | MM-3140-287C | 8 | 807 | 07A | border(BR)& threshold | crystal white | 1.36 | 1.36 |  | 2022-01-21
34 | MM-3140-334C | 25 | 2510 | 7A | border(BR)& threshold | Crystal white | 1.36 | 1.36 |  | 2022-01-21
35 | MM-3140-215 | 25 | 2503 | 02D | wall(CL) | Volkas Polished | 2.34 | 2.34 |  | 2022-01-22
36 | MM-3140-187 | 25 | 2513 | 3F | wall(CL) | Volkas polished | 30.31 | 30.31 |  | 2022-01-22
37 | MM-3140-230 | 26 | 2602 | 14A | wall(CL) | Volkas polished | 37.13 | 37.13 |  | 2022-01-22
38 | MM-3140-184A | 27 | 2712 | 3C | floor(FL) | Travertine | 20.52 | 20.52 |  | 2022-01-22
From 24th January to 31st January
1 | MM-3140-281CX | 8 | Different Room |  | Corridor | Volkas | 0.75 | 0.75
2 | MM-3140-222 | 25 | 2507 | 11C | Vanity Top | Volkas Polished | 1.16 | 1.16
3 | MM-3140-155L | 2003, 2103, 2203, 2303, 2404, 2414, 2405, 2408, 2415, 2504, 2512, 2505, 2508, 2513, 2604, 2607, 2611, 2612, 2704, 2707, 2712, 2713 |  | 03-Series | Wardrobe | Crystal | 2.68 | 2.68
4 | MM-3140-235L | 1904, 2006, 2106, 2206 & 2306 |  | 06A-Type | Wardrobe | Crystal | 3.08 | 3.08
5 | MM-3140-328S | 22 | Lift Lobby |  | Sofit | Volkas Polished | 2.16 | 2.16
6 | MM-3140-196 | 26 | 2614 | 2E | wall(CL) | Volkas | 2.54 | 2.54
7 | MM-3140-191 | 25 | 2514 | 2G | wall(CL) | Volkas | 34.27 | 34.27
8 | MM-3140-328C | 22 | Lift Lobby |  | Border | Volkas Polished | 8.79 | 8.79
9 | MM-3140-328C | 22 | Lift Lobby |  | Skirting | Volkas Polished | 1.59 | 1.59
10 | MM-3140-328A | 22 | Coridoor |  | skirting(SK) | Volkas Polished | 6.78 | 6.78
11 | MM-3140-328 | 22 | Lift Lobby |  | Cladding | Volkas Polished | 22.08 | 22.08
12 | MM-3140-100MKP | Mockup |  |  |  | Black absolute | 0.86 | 0.86
13 | MM-3140-177A | 27 | 2710 | 1A | floor(FL) | Travertine | 13.34 | 13.34
14 | MM-3140-289 revised | 16 | 1610 | 07A | wall(CL) | Perlato Queen Beige | 1.76 | 1.76
15 | MM-3140-192 | 26 | 2613 | 2G | wall(CL) | Volkas polished | 34.4 | 34.4
16 | MM-3140-218 | 26 | 2601 | 10B | wall(CL) | Volkas polished | 46.79 | 46.79
17 | MM-3140-168A | 27 | 2704 | 3A | floor(FL) | Travertine | 21.67 | 21.67
18 | MM-3140-247 | 26 | 2603 | 2D | wall(CL) | Volkas | 39.8 | 39.8
19 | MM-3140-292 | 26 | 2605 | 11D | wall(CL) | Volkas | 39.95 | 39.95
20 | MM-3140-180 | 26 | 2610 | 02F | wall(CL) | Volkas | 22.99 | 22.99
21 | MM-3140-289C | 16 | 1610 | 07A | border(BR)& threshold | crystal white | 1.36 | 1.36
22 | MM-3140-288C | 14 | 1410 | 07A | border(BR)& threshold | crystal white | 1.36 | 1.36
From 01st February to 08th February
1 | MM-3140-166 | 26 | 2604 | 3A | wall(CL) | Volkas polished | 27.53 | 27.53 |  | 2022-02-01
2 | MM-3140-154L | 2002, 2102, 2204, 2302, 2406, 2409, 2403, 2412, 2417, 2416, 2506, 2509, 2510, 2503, 2515, 2514, 2606, 2603, 2609, 2614, 2613, 2706, 2703, 2710, 2715, 2714 |  | 02A,02B,02C,02D,02E,02G and 01A | Wardrobe | Crystal | 14.23 | 14.23 |  | 2022-02-03
3 | MM-3140-155L | 2404, 2414, 2405, 2408 & 2415 |  | 03-Series | Wardrobe | Crystal | 3.35 | 3.35 |  | 2022-02-03
4 | MM-3140-130CX | 1417 & 1617 |  | 5A | Border | Crystal White | 2.42 | 2.42 |  | 2022-02-03
5 | MM-3140-178L | 2413, 2511, 2610 & 2711 |  | 02F | Wardrobe | Crystal | 2.13 | 2.13 |  | 2022-02-03
6 | MM-3140-288 revised | 14 | 1410 | 07A | wall(CL) | crystal white | 1.61 | 1.61 |  | 2022-02-03
7 | MM-3140-292 | 26 | 2605 | 11D | wall(CL) | Volkas | 2.1 | 2.1 |  | 2022-02-03
8 | MM-3140-154AEX | L-13 & 15 |  |  | architrave(AR) | Crystal White | 4.45 | 4.45 |  | 2022-02-03
9 | MM-3140-188 | 26 | 2612 | 3F | wall(CL) | Volkas polished | 30.31 | 30.31 |  | 2022-02-05
10 | MM-3140-155L | 2504, 2512, 2505, 2508, 2513, 2604 & 2607 |  | 03-Series | Wardrobe | Crystal | 4.69 | 4.69 |  | 2022-02-05
11 | MM-3140-233L | 1903 & 2006 |  | 19A | Wardrobe | Crystal | 2.56 | 2.56 |  | 2022-02-05
12 | MM-3140-156 | 10 | 1007 | 15A | wall(CL) | Perlato Queen Beige | 16.81 | 16.81 |  | 2022-02-05
13 | MM-3140-156X | 10 | 1007 | 15A | wall(CL) | Perlato Queen Beige | 10.87 | 10.87 |  | 2022-02-05
14 | MM-3140-336 revised | 22 | 2205 | 15A | wall(CL) | Parlato Queen Beige Polished | 27.66 | 27.66 |  | 2022-02-05
15 | MM-3140-212 | 26 | 2615 | 05A | wall(CL) | Volkas polished | 27.97 | 27.97 |  | 2022-02-07
16 | MM-3140-334A | 25 | 10 (Uper & Lower level) | 7A | floor(FL) | Volkas | 18.28 | 18.28 |  | 2022-02-07
17 | MM-3140-233L | 24 | 2411 | 19A | Wardrobe | Crystal | 1.28 | 1.28 |  | 2022-02-08
18 | MM-3140-155L | 2611, 2612, 2704, 2707, 2712 & 2713 |  | 03-Series | Wardrobe | Crystal | 4.06 | 4.06 |  | 2022-02-08
19 | MM-3140-169A rev 01 | 27 | 2707 | 3A | Shower floor(FL) | Travertine | 1.6 | 1.6 |  | 2022-02-08
20 | MM-3140-177A | 27 | 2710 | 1A | Shower floor(FL) | Travertine | 2.95 | 2.95 |  | 2022-02-08
21 | MM-3140-284A | 23 | 2306 | 06A | Shower floor(FL) | Travertine | 1.63 | 1.63 |  | 2022-02-08
22 | MM-3140-218A | 26 | 2601 | 10B | Shower floor(FL) | Travertine | 1.79 | 1.79 |  | 2022-02-08
23 | MM-3140-168A | 27 | 2704 | 3A | Shower floor(FL) | Travertine | 1.64 | 1.64 |  | 2022-02-08
24 | MM-3140-193A | 27 | 2714 | 2G | Shower floor(FL) | Travertine | 2.71 | 2.71 |  | 2022-02-08
25 | MM-3140-184A | 27 | 2712 | 3C | Shower floor(FL) | Travertine | 1.95 | 1.95 |  | 2022-02-08
26 | MM-3140-132AEX | L-13 & 14 |  |  | Extra floor(FL) Pieces | Travertine | 12.1 | 12.1 |  | 2022-02-08
| Total material delivered to the site from 29th November to 02nd January | [6 empty] | 1128.93

## Metal Frame Assesment
Metal frame Progress Assesment
Level 08 to Level 16)
S.No | Type | Item Description |  | Level 8 | Level 9 | Level 10 | Level 11 | Level 12 | Level 13 | Level 14 | Level 15 | Level 16 | Level 19 | Level 20 | Level 21 | Level 22 | Level 23 | Level 24 | Level 25 | Level 26 | Level 27 | Total | Unit
Total Qty
Level 8 to Level 10
1 | 01A/1B | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
2 | 2A/2B/2C/2D | Vanity Top | 9 | 3 | 3 | 3 | [15 empty] | 9 | Nr
3 | 2A/2B/2C/2D | Bath Tub Top | 9 | 3 | 3 | 3 | [15 empty] | 9 | Nr
4 | 3A/3B/3D/3E/3G | Vanity Top | 6 | 2 | 2 | 2 | [15 empty] | 6 | Nr
5 | 4A/4B | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
6 | 8A | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
7 | 8A | Vanity Top | 3 | 1 | 1 | 1 | [15 empty] | 3 | Nr
8 | 9A | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
9 | 9A | Bath Tub Top | 1 |  | 1 | [16 empty] | 1 | Nr
10 | 9A | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
11 | 9B | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
12 | 9B | Bath Tub Top | 1 |  | 1 | [16 empty] | 1 | Nr
13 | 9B | Vanity Top | 1 |  | 1 | [16 empty] | 1 | Nr
Level 11 to Level 16
1 | 01A | Vanity Top | 2 | [6 empty] | 1 | 1 | [10 empty] | 2 | Nr
2 | 01C | Vanity Top | 4 |  |  |  | 1 | 1 | 1 |  |  | 1 | [9 empty] | 4 | Nr
3 | 2A/2B/2C/2D | Vanity Top | 18 |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | [9 empty] | 18 | Nr
4 | 2A/2B/2C/2D | Bath Tub Top | 18 |  |  |  | 3 | 3 | 3 | 3 | 3 | 3 | [9 empty] | 18 | Nr
5 | 2E/2F/2G/2H | Vanity Top | 15 |  |  |  |  | 3 | 3 | 3 | 3 | 3 | [9 empty] | 15 | Nr
6 | 2E/2F/2G/2H | Bath Tub Top | 15 |  |  |  |  | 3 | 3 | 3 | 3 | 3 | [9 empty] | 15 | Nr
7 | 3A/3B/3D/3E/3G | Vanity Top | 17 |  |  |  | 2 | 3 | 3 | 3 | 3 | 3 | [9 empty] | 17 | Nr
8 | 3C/3F | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
9 | 4A/4B | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
10 | 5A | Vanity Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
11 | 8A | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
12 | 8A | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
13 | 9A | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
14 | 9A | Bath Tub Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
15 | 9A | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
16 | 9B | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
17 | 9B | Bath Tub Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
18 | 9B | Vanity Top | 1 |  |  |  |  | 1 | [13 empty] | 1 | Nr
19 | 10A | Vanity Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
20 | 10A | Bath Tub Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
21 | 10A | Vanity Top | 5 |  |  |  |  | 1 | 1 | 1 | 1 | 1 | [9 empty] | 5 | Nr
22 | 11A/11B/11C/11D | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
23 | 11A/11B/11C/11D | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
24 | 11A/11B/11C/11D | Vanity Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
25 | 11A/11B/11C/11D | Bath Tub Top | 10 |  |  |  |  | 2 | 2 | 2 | 2 | 2 | [9 empty] | 10 | Nr
26 | 16A | Vanity Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
27 | 16A | Bath Tub Top | 1 |  |  |  | 1 | [14 empty] | 1 | Nr
28 | 19A | Vanity Top | 2 | [5 empty] | 1 |  | 1 | [10 empty] | 2 | Nr
Level 19 to Level 27
| 01A | Vanity Top and side walls | 4 | [14 empty] | 1 | 1 | 1 | 1 | 4 | Nr
| 2A/2B/2C/2D | Vanity Top and side walls | 14 | [10 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 14 | Nr
| 2A/2B/2C/2D | Bath Tub Top, side walls | 14 | [10 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 2 | 2 | 14 | Nr
| 2E/2F/2G/2H | Vanity Top and side walls | 12 | [14 empty] | 3 | 3 |  |  | 6 | Nr
| 2E/2F/2G/2H | Bath Tub Top and side walls | 12 | [14 empty] | 3 | 3 |  |  | 6 | Nr
| 3A/3B/3D/3E/3G | Vanity top and walls type 2 | 14 | [10 empty] | 1 | 1 | 1 | 1 | 3 | 3 | 1 | 1 | 12 | Nr
| 3C/3F | Vanity top and walls type 2 | 8 | [14 empty] | 2 | 2 |  |  | 4 | Nr
| 5A | Vanity top and walls type 3 | 4 | [14 empty] | 1 | 1 |  |  | 2 | Nr
| 6A | Vanity top and walls type 4 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 10B | Vanity Top and side walls type 1 | 3 | [15 empty] | 1 |  |  | 1 | Nr
| 10B | Bath Tub Top and side walls | 3 | [15 empty] | 1 |  |  | 1 | Nr
| 10B | Vanity Top type 3 | 3 | [15 empty] | 1 |  |  | 1 | Nr
| 11A/11B/11C/11D | Vanity Top type 3 | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 11A/11B/11C/11D | Vanity Top type 3 | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 11A/11B/11C/11D | Vanity Top type 3 | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 11A/11B/11C/11D | Bath Tub Top and side walls | 8 | [10 empty] | 1 | 1 | 1 | 1 | 1 | 1 |  |  | 6 | Nr
| 12A | Vanity Top type 3 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 12A | Bath Tub Top and side walls | 10 | [9 empty] | 2 | 2 | 2 | 2 | 2 |  |  |  |  | 10 | Nr
| 12A | Vanity Top type 3 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 12A | Vanity Top type 3 | 5 | [9 empty] | 1 | 1 | 1 | 1 | 1 |  |  |  |  | 5 | Nr
| 13A | Vanity top and side walls | 1 | [15 empty] | 1 |  |  | 1 | Nr
| 13A | Vanity top type 3 | 1 | [15 empty] | 1 |  |  | 1 | Nr
| 14A | Vanity top and walls type 2 | 4 | [14 empty] | 1 | 1 |  |  | 2 | Nr
| 14A | Vanity top type 3 | 4 | [14 empty] | 1 | 1 |  |  | 2 | Nr
| 16A | Vanity top and side walls | 2 | [13 empty] | 1 |  |  |  |  | 1 | Nr
| 16A | Bath Tub Top | 2 | [13 empty] | 1 |  |  |  |  | 1 | Nr
| 19A | Vanity top snd walls | 3 | [10 empty] | 1 |  |  |  | 1 |  |  |  | 2
| Total Metal Frame Qty |  | 384 | [18 empty] | 343
| Total Progress Metal Frame Qty |  | 343
| Progress % |  | 89.32%
| Total allocated amount as per ASI rates |  | 766683
| Total approved amount for Metal frame variation |  | 684823.6172

## Metal Frame Variation
Metal Frame Total value descoped from ASI
ASI
Sr. No: | Type | Item Description | Total Q'ty | Unit | Category | Rate | Amount (AED)
1 | TYPE -01A (6 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 6 | No | Vanity Top / Side Walls | 1769 | 10614
4 | TYPE -01C (8 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 8 | No | Vanity Top / Side Walls | 1955 | 15268
9 | TYPE -2A/2B/2C/2D (44 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 44 | No | Vanity Top / Side Walls | 1769 | 77836
11 | TYPE -2E/2F/2G/2H (27 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 27 | No | Vanity Top / Side Walls | 1769 | 46458
15 | TYPE -3A/3B/3D/3E/3G (39 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 39 | No | Vanity Top / walls | 4780 | 148180
19 | TYPE -03C/03F (18 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 18 | No | Vanity Top / walls | 4780 | 86040
23 | TYPE -04A/4B (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 5 | No | Vanity Top / walls | 3946 | 19730
27 | TYPE -05A (9 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 9 | No | Vanity Top / walls | 3946 | 35514
31 | TYPE -06A (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 5 | No | Vanity Top / walls | 3946 | 19730
35 | TYPE -08A (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 5 | No | Vanity Top / walls | 3946 | 19730
40 | TYPE -08A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 1397 | 6985
41 | TYPE -09A (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 2 | No | Vanity Top / Side Walls | 2028 | 4056
46 | TYPE -09A (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 2 | No | Vanity Top | 679 | 1358
47 | TYPE -09B (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 2 | No | Vanity Top / Side Walls | 1932 | 3864
48 | TYPE -09B (2 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 | 2 | No | Bath Tub Top / Side Walls | 418 | 836
52 | TYPE -09B (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 2 | No | Vanity Top | 679 | 1358
53 | TYPE -10A (5 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 5 | No | Vanity Top / Side Walls | 1769 | 8845
58 | TYPE -10A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 1379 | 6895
59 | TYPE -10B (3 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 3 | No | Vanity Top / Side Walls | 1769 | 5307
64 | TYPE -10B (3 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 3 | No | Vanity Top | 1397 | 4191
67 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 19 | No | Vanity Top | 4510 | 85690
68 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 19 | No | Vanity Top | 1265 | 24035
72 | TYPE -12A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 4510 | 22550
78 | TYPE -12A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 5 | No | Vanity Top | 1619 | 8095
79 | TYPE -13A (1 No) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 1 | No | Vanity Top / Side Walls | 1769 | 1769
84 | TYPE -13A (1 No) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 1 | No | Vanity Top | 1593 | 1593
85 | TYPE -14A (4 No) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 4 | No | Vanity Top / walls | 4780 | 19120
90 | TYPE -14A (4 No) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 4 | No | Vanity Top | 1120 | 4480
91 | TYPE -16A (3 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 3 | No | Vanity Top / Side Walls | 1932 | 5796
95 | TYPE -19A (6 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 6 | No | Vanity Top / walls | 4780 | 28680
| TYPE - 07A ( 5 Nos) | Master Bath Vanity | 5 | No | Vanity Top | 7772 | 38860
|  | Powder Room Vanity | 5 | No | Vanity Top | 644 | 3220
|  | TOTAL AMOUNT |  |  |  |  | 766683
724603
713989
Verify Basic Data

## 7A & 15A
STONE WORKS TO ROOM TYPE 7A & 15A | [21 empty] | Payment Upto End of: | 2022-12-01
Bill No. | Item No. | Description | Quantity | Unit | Material | Thick | Supply Rate | Fixing Rate | Unit Rate | Amount | Work Progress (%) |  |  | Total Amount |  |  | Total | 7A | 7A | 7A | 7A | 7A | 15A | 15A
[11 empty] | Previous | Current | Cummulative | Previous | Current | Cummulative |  | Lvl 7 | Lvl 13 | Lvl 15 | Lvl 20 | Lvl 24 | Lvl 10 | Lvl 22
| 1 | PACKAGE 7 - STONE WORKS
1 Bed Duplex Suite
| A | TYPE -07A (5 No's)
FLOOR FINISHES
Master Bathroom
| A.1 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 70.5 | m2 | Volakas | 20 | 433 | 205 | 638 | 44979 | 80% | 20% | 100% | 35983.2 | 8995.8 | 44979 | 100% | 100% | 100% | 100% | 100% | 100%
| A.2 | 7 x 5mm Brass strip insert in brushed finish . | 30 | mr | Brass | 5 | 0 | 60 | 60 | 1800 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Toilet
| A.3 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 11 | m2 | Volakas | 20 | 433 | 205 | 638 | 7018 | 80% | 20% | 100% | 5614.4 | 1403.6 | 7018 | 100% | 100% | 100% | 100% | 100% | 100%
| A.4 | Supply & fixing of 20m thk threshold 800mm x 240mm, polished Calacatta Vagli | 5 | No | Volakas | 20 | 124 | 41 | 165 | 825 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Guest WC
| A.5 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 5.5 | m2 | Volakas | 20 | 433 | 205 | 638 | 3509 | 80% | 20% | 100% | 2807.2 | 701.8 | 3509 | 100% | 100% | 100% | 100% | 100% | 100%
| A.6 | 20mm thick polished Crystal White, average 130mm width border. | 5.5 | m2 | Crystal White | 20 | 282 | 206 | 488 | 2684 | 80% | 20% | 100% | 2147.2 | 536.8 | 2684 | 100% | 100% | 100% | 100% | 100% | 100%
| A.7 | 7 x 5mm Brass strip insert in brushed finish . | 22.5 | mr | Brass | 5 | 0 | 60 | 60 | 1350 | 80% | 20% | 100% | 1080 | 270 | 1350 | 100% | 100% | 100% | 100% | 100% | 100%
Wall Finishes
Master Bathroom
| A.8 | Supply and installation of skirting Crystal White 300 x 20 mm thk | 25 | mr | Crystal White | 20 | 111 | 75 | 186 | 4650 | 80% | 0% | 80% | 3720 | 0 | 3720 | 80% | 100% | 100% | 100% | 0% | 100%
| A.9 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 30 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 39360 | 80% | 0% | 80% | 31488 | 0 | 31488 | 80% | 100% | 100% | 100% | 0% | 100%
Toilet
| A.10 | Supply and installation of skirting Victoria falls quartzite, 150+35 x 20 mm thk | 25 | mr | Victoria Falls | 20 | 233 | 53 | 286 | 7150 | 80% | 20% | 100% | 5720 | 1430 | 7150 | 100% | 100% | 100% | 100% | 100% | 100%
| A.11 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick - upto dado level | 27.5 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 36080 | 80% | 20% | 100% | 28864 | 7216 | 36080 | 100% | 100% | 100% | 100% | 100% | 100%
Guest WC
| A.12 | Supply and installation of skirting Victoria falls quartzite, 150+35 x 20 mm thk | 30 | mr | Victoria Falls | 20 | 233 | 53 | 286 | 8580 | 80% | 20% | 100% | 6864 | 1716 | 8580 | 100% | 100% | 100% | 100% | 100% | 100%
| A.13 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick - upto dado level | 32.25 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 42312 | 80% | 20% | 100% | 33849.6 | 8462.4 | 42312 | 100% | 100% | 100% | 100% | 100% | 100%
Lobby
| A.14 | Supply and installation of cladding, 20mm thick polished Saint Laurent Marble, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 79 | m2 | New Saint Laurent | 20 | 369 | 222 | 591 | 46689 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
| A.15 | Supply and installation of cladding on the door, 20mm thick polished Saint Laurent Marble, to be fixed with honey comb with standard cementitious adhesive maximum up to 5mm thick | 22.5 | m2 | New Saint Laurent | 20 | 940 | 283 | 1223 | 27517.5 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Joinery Items
Bathroom
| A.16 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 4566 x 605, with 280mm high fascia and 400x20 mm splashback with 2 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 5 | No | Victoria Falls | 20 | 8307 | 20462 | 28769 | 143845 | 80% | 20% | 100% | 115076 | 28769 | 143845 | 100% | 100% | 100% | 100% | 100% | 100%
Toilet
| A.17 | Cistern Top : Supply and installation of 20mm thick polished Victoria falls, 260mm W x 1250mm length, pencil edge finish. | 5 | No | Victoria Falls | 20 | 375 | 87 | 462 | 2310 | 0% | 100% | 100% | 0 | 2310 | 2310 | 100% | 100% | 100% | 100% | 100% | 100%
| A.18 | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Victoria falls shelf size of 120mm W x 200mm L, edges chamfered. | 5 | No | Victoria Falls | 20 | 41 | 6 | 47 | 235 | 0% | 100% | 100% | 0 | 235 | 235 | 100% | 100% | 100% | 100% | 100% | 100%
Guest WC
| A.19 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 595 x 400, with 400mm high fascia with 1 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 5 | No | Victoria Falls | 20 | 1230 | 2761 | 3991 | 19955 | 80% | 20% | 100% | 15964 | 3991 | 19955 | 100% | 100% | 100% | 100% | 100% | 100%
| A.20 | Cistern Top : Supply and installation of 20mm thick polished Victoria falls, 260mm W x 1250mm length, pencil edge finish. | 5 | No | Victoria Falls | 20 | 375 | 87 | 462 | 2310 | 80% | 20% | 100% | 1848 | 462 | 2310 | 100% | 100% | 100% | 100% | 100% | 100%
| A.21 | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Victoria falls shelf size of 120mm W x 200mm L, edges chamfered. | 5 | No | Victoria Falls | 20 | 41 | 6 | 47 | 235 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Vestibule
| A.22 | Supply and installation of 20mm thick, Counter top polished Saint Laurent Marble, top size 1482 x 555, with 40mm fascia and 2 nos of drawer cladding, size 400 x 100mm. [Inc. ss framing] | 5 | No | New Saint Laurent | 20 | 409 | 1572 | 1981 | 9905 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Walk-In Closet
| A.23 | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 1280 x 690mm, with 40mm fascia. [ Frameworks and back support by others ] | 5 | No | Crystal White | 20 | 397 | 235 | 632 | 3160 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
| A.24 | Counter Top @ Walk-In Closet : Supply and installation of 20mm thick polished Crystal White size of 770 x 690mm, with 40mm fascia. [ Frameworks and back support by others ] | 5 | No | Crystal White | 20 | 256 | 141 | 397 | 1985 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Mini Bar
| A.25 | Supply and installation of Mini Bar 20mm thick Saint Laurent Marble, Counter top size 1560 x 620, with 40mm fascia and 2 nos shelf size 1560 x 250 with 40mm fascia with cladding to front and side of the mini bar including soffit, skirting & drawer cladding. [ Frameworks and back support by others ] | 5 | No | New Saint Laurent | 20 | 4300 | 2534 | 6834 | 34170 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Side Table
| A.26 | Supply and installation of side table 20mm thick Vlota Marble, table top size 1826 x 650. [ Frameworks and back support by others ] | 10 | No | Viola | 20 | 2852 | 313 | 3165 | 31650 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | 0% | 0% | 0% | 0% | 0%
Stair Case
| A.27 | Supply & instllation of staircase 20mm thk. Polished Saint Laurent Marble, tread 300 x 200mm thk & Riser 150x20mm | 102 | mr | New Saint Laurent | 20 | 217 | 113 | 330 | 33660 | 96% | 4% | 100% | 32313.6 | 1346.4 | 33660 | 100% | 100% | 100% | 100% | 100% | 100%
| A.28 | Supply & instllation of stringer 20mm thk. Polished Saint Laurent Marble, size 350 x 20mm | 36.5 | mr | New Saint Laurent | 20 | 146 | 88 | 234 | 8541 | 96% | 0% | 96% | 8199.36 | 0 | 8199.36 | 96% | 100% | 100% | 100% | 80% | 100%
| A.29 | Supply & instllation of mid landing at staircase 20mm thk. Polished Saint Laurent Marble, with 3 nos of tread & Riser. | 16 | m2 | New Saint Laurent | 20 | 354 | 153 | 507 | 8112 | 0% | 20% | 20% | 0 | 1622.4 | 1622.4 | 20% | 100% | 0% | 0% | 0% | 0%
Miscellaneous Items
| A.30 | Extra over charges for standard sealer coating to top surface of stone if required. | 495 | m2 |  |  | 0 | 8 | 8 | 3960 | 100% | 0% | 100% | 3960 | 0 | 3960 | 100% | 100% | 100% | 100% | 100% | 100%
| A.31 | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 93.5 | m2 |  |  | 0 | 8 | 8 | 748 | 100% | 0% | 100% | 748 | 0 | 748 | 100% | 100% | 100% | 100% | 100% | 100%
1 Bed Double Height Suite
| B | TYPE -15A (2 No's)
FLOOR FINISHES
Master Bathroom
| B.1 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 10 | m2 | Volakas | 20 | 433 | 205 | 638 | 6380 | 100% | 0% | 100% | 6380 | 0 | 6380 | 100% | [5 empty] | 100% | 100%
| B.2 | 7 x 5mm Brass strip insert in brushed finish . | 6 | mr | Brass | 5 | 0 | 60 | 60 | 360 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Guest WC
| B.3 | Supply & fixing of 20m thk Calacatta Vagli ( Herring bone pattern ) flooring | 1.7 | m2 | Volakas | 20 | 433 | 205 | 638 | 1084.6 | 100% | 0% | 100% | 1084.6 | 0 | 1084.6 | 100% | [5 empty] | 100% | 100%
| B.4 | 20mm thick polished Crystal White, average 130mm width border. | 2 | m2 | Crystal White | 20 | 282 | 206 | 488 | 976 | 100% | 0% | 100% | 976 | 0 | 976 | 100% | [5 empty] | 100% | 100%
| B.5 | 7 x 5mm Brass strip insert in brushed finish . | 7.6 | mr | Brass | 5 | 0 | 60 | 60 | 456 | 50% | 50% | 100% | 228 | 228 | 456 | 100% | [5 empty] | 100% | 100%
Wall Finishes
Master Bathroom
| B.6 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 30 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 39360 | 100% | 0% | 100% | 39360 | 0 | 39360 | 100% | [5 empty] | 100% | 100%
Guest WC
| B.7 | Supply and installation of skirting Victoria falls quartzite, 150+35 x 20 mm thk | 10 | mr | Victoria Falls | 20 | 233 | 53 | 286 | 2860 | 100% | 0% | 100% | 2860 | 0 | 2860 | 100% | [5 empty] | 100% | 100%
| B.8 | Supply and installation of 20mm thick polished Victoria falls quartzite, to be fixed with standard cementitious adhesive maximum up to 5mm thick - upto dado level | 10.6 | m2 | Victoria Falls | 20 | 1067 | 245 | 1312 | 13907.2 | 100% | 0% | 100% | 13907.2 | 0 | 13907.2 | 100% | [5 empty] | 100% | 100%
Lobby
| B.9 | Supply and installation of cladding, 20mm thick polished Saint Laurent Marble, to be fixed with standard cementitious adhesive maximum up to 5mm thick | 11.6 | m2 | New Saint Laurent | 20 | 369 | 222 | 591 | 6855.6 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.10 | Supply and installation of cladding on the door, 20mm thick polished Saint Laurent Marble, to be fixed with honey comb with standard cementitious adhesive maximum up to 5mm thick | 14.6 | m2 | New Saint Laurent | 20 | 940 | 283 | 1223 | 17855.8 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Joinery Items
Bathroom
| B.11 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 3250 x 605, with 280mm high fascia and 400x20 mm splashback with 2 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 2 | No | Victoria Falls | 20 | 6638 | 16198 | 22836 | 45672 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.12 | Supply and installation of shelf top 20mm thick Victoria falls quartzite, size of 120 x 200mm, chamfered edges . | 2 | No | Victoria Falls | 20 | 41 | 6 | 47 | 94 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Guest WC
| B.13 | Supply and installation of 20mm thick, Vanity counter top polished Victoria falls quartzite, top size 595 x 400, with 400mm high fascia with 1 nos of wash basin with 4 side stone cladding. [Inc. ss framing] | 2 | No | Victoria Falls | 20 | 1230 | 2761 | 3991 | 7982 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.14 | Cistern Top : Supply and installation of 20mm thick polished Victoria falls, 260mm W x 1250mm length, pencil edge finish. | 2 | No | Victoria Falls | 20 | 375 | 87 | 462 | 924 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.15 | Mobile Shelf @ Toilet : Supply and installation of 20mm thick polished Victoria falls shelf size of 120mm W x 200mm L, edges chamfered. | 2 | No | Victoria Falls | 20 | 41 | 6 | 47 | 94 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Vestibule
| B.16 | Supply and installation of 20mm thick, Counter top polished Saint Laurent Marble, top size 1482 x 555, with 40mm fascia and 2 nos of drawer cladding, size 400 x 100mm. [Inc. ss framing] | 2 | No | New Saint Laurent | 20 | 409 | 1572 | 1981 | 3962 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Stone to Doors
Door Architraves : Supply and installation of (20+10)mm thick polished Crystal White as per below details and drawing.
| B.17 | Vestibule : 325mm wide; total size of 1500 x 2400mm high. | 2 | No | Crystal White | 30 | 1126 | 477 | 1603 | 3206 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Mini Bar
| B.18 | Supply and installation of Mini Bar 20mm thick Saint Laurent Marble, Counter top size 1560 x 620, with 40mm fascia and 2 nos shelf size 1560 x 250 with 40mm fascia with cladding to front and side of the mini bar including soffit, skirting & drawer cladding. [ Frameworks and back support by others ] | 2 | No | New Saint Laurent | 20 | 4300 | 2534 | 6834 | 13668 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
Miscellaneous Items
| B.13 | Extra over charges for standard sealer coating to top surface of stone if required. | 122 | m2 |  |  |  | 8 | 8 | 976 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
| B.14 | Extra over charges for protection (Polypropelene corrugated sheet) after completion of flooring. | 14 | m2 |  |  |  | 8 | 8 | 112 | 0% | 0% | 0% | 0 | 0 | 0 | 0% | [5 empty] | 0% | 0%
|  | Total Amount AED | [7 empty] | 746069.7 | 53.75% | 9.342% | 63.1% | 401042.36 | 69696.2 | 470738.56

## VO Summary
SUMMARY - POST WFA VARIATIONS
Vo.No: | Description | Amount Submitted | % Work Done | Amount Submitted | Remark
2 | Variation Orders - Post Sub Contract Agreement - KCE
A.1 | Proceed with supply & installation of balance stone works at lift lobbies basement 1 & 2, Ground lvl, 2nd, 4th, & 23ed floor. DAR/3333/as/mb/0971 Dated 11 Oct 2022 | 617777 | 62.3% | 384864.0086 | Approved E11/K109/KD/SR/304
1 - Rev 1 | Supply & installation of marble floor at corridor ground floor. DAR/3333/as/rj/0772 Dated 5 Aug 2022 | 5502.33 | 100% | 5502.33 | Instrction via e mail Dated 4 Aug 2022 (Mr. Anil Kariyappa)
2 | Supply & installation of marble architrave at lift lobby, Lvl 7 - Lvl . Hotel Area. DAR/3333/as/rj/0975 Dated 12 Oct 2022 | 58140 | 0% | 0 | Instruction Ref: E11/K109/SN/dm/230 Dated 23 Sept 22
3 | Supply and installation of pink onyx cladding at level 2. DAR/3214/as/rj/0982 Dated 13 Oct 2022 | 757050 | 0% | 0 | Instruction Ref: E11/K109/SN/dm/232 Dated 23 Sept 22
4 | Supply and Fixing of SS Strip. DAR/3333/as/rj/1109 Dated 15 Nov 2022 | 21000 | 0% | 0 | Instrction via e mail Dated 10-Nov-22 (Mr. Saman)
| Sub Total | 1459469.33 | 26.75% | 390366.3386
TOTAL AMOUNT |  | 1459469.33 | Dhs. | #REF!

## AHK Balance Work
SUBJECT | Supply & Installation Of Balance Stone Works At Lift Lobbies Basement 1 & 2, Ground Lvl, 2nd, 4th, & 23ed Floor.
BILL OF QUANTITIES
[9 empty] | Payment Upto End Of | : Nov 2022
Bill No. | Item No. | Description | Unit | Quantity | Unit Rate | Amount | Balance Works | Amount Balance Work | % Of Work Completed | Amount
STONE WORKS
RESIDENTIAL AMENITIES, LOBBIES AND LIFT LOBBIES (B1, B2, GF, L2, L4 and L23)
FLOOR FINISHES
Stone floor finish laid on cement and sand screed including all necessary grouting, movement joints, pointing, polishing, dry set mortar or adhesive and the like; all in accordance with the drawings and specification
Residential - Basement 1 Lift Lobby
| A | Type RES-ST-16; Stone border to lift lobby | m2 | 13 | 479 | 6227 | 23.7% | 1476.03 | 95% | 1402.2285
Residential - Basement 2 Lift Lobby
| B | Type RES-ST-16; Stone border to lift lobby | m2 | 13 | 479 | 6227 | 23.7% | 1476.03 | 95% | 1402.2285
Residential - Ground Floor Lobby
| C | Type RES-ST-16; Stone border to concierge and corridor | m2 | 59 | 479 | 28261 | 23.7% | 6698.89 | 95% | 6363.9455
| D | Type RES-ST-16; Stone border to lift lobby | m2 | 13 | 479 | 6227 | 23.7% | 1476.03 | 95% | 1402.2285
| D1 | Type RES-ST-26; Stone border to Main Entrance | m2 | 6 | 557 | 3342 | 100% | 3342 | 95% | 3174.9
| D2 | Type RES-ST-27; Stone border to Main Entrance | m2 | 6 | 557 | 3342 | 100% | 3342 | 95% | 3174.9
Residential - Level 2 Lobby and Corridor
| E | Type RES-ST-16; Stone border to lobby | m2 | 39 | 479 | 18681 | 23.7% | 4428.09 | 95% | 4206.6855
| F | Type RES-ST-16; Stone border to lift lobby | m2 | 9 | 479 | 4311 | 23.7% | 1021.8669 | 95% | 970.7736
Residential - Level 4 Amenities, Corridor and Lift Lobby
| A | Type RES-ST-16; Stone flooring to reception | m2 | 65 | 479 | 31135 | 23.7% | 7380.15 | 95% | 7011.1425
| B | Type RES-ST-16; Stone flooring to lift lobby | m2 | 10 | 479 | 4790 | 23.7% | 1135.4077 | 95% | 1078.6373
| C | Type RES-ST-24; Stone flooring to men's changing room | m2 | 23 | 625 | 14375 | 23.7% | 3407.4083 | 95% | 3237.0378
| D | Type RES-ST-24; Stone flooring to women's changing room | m2 | 31 | 625 | 19375 | 23.7% | 4592.5937 | 95% | 4362.9641
| E | Type RES-ST-25; Stone flooring to shower room at men's changing room | m2 | 6 | 625 | 3750 | 23.7% | 888.8891 | 95% | 844.4447
| F | Type RES-ST-25; Stone flooring to shower room at women's changing room | m2 | 6 | 625 | 3750 | 23.7% | 888.8891 | 95% | 844.4447
Residential - Level 23 Amenities, Corridor and Lift Lobby
| G | Type RES-ST-02; Stone border to lift lobby | m2 | 9 | 805 | 7245 | 23.7% | 1717.3338 | 95% | 1631.4671
| H | Type RES-ST-02; Stone border to corridor | m2 | 31 | 805 | 24955 | 23.7% | 5915.2607 | 95% | 5619.4977
| J | Type RES-ST-02; Stone border to meeting room | m2 | 14 | 805 | 11270 | 23.7% | 2671.4081 | 95% | 2537.8377
| K | Type RES-ST-02; Stone border to multifunction room | m2 | 12 | 805 | 9660 | 23.7% | 2289.7784 | 95% | 2175.2894
| L | Type RES-ST-21; Stone flooring to men's restroom | m2 | 21 | 512 | 10752 | 23.7% | 2548.6229 | 95% | 2421.1917
| M | Type RES-ST-21; Stone flooring to women's restroom | m2 | 21 | 512 | 10752 | 23.7% | 2548.6229 | 95% | 2421.1917
WALL FINISHES
Stone wall finish including all necessary supports, framing, backing, fixings, fittings, accessories, etc. and the like; all in accordance with the drawings and specification (linear lighting by others)
Residential - Basement 1 Lift Lobby
| N | Type RES-ST-26; Stone cladding in open book to lift lobby | m2 | 30 | 744 | 22320 | 100% | 22320 | 50% | 11160
| A | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 50% | 4687
Residential - Basement 2 Lift Lobby
| B | Type RES-ST-26; Stone cladding in open book to lift lobby | m2 | 30 | 744 | 22320 | 23.7% | 5290.668 | 95% | 5026.1346
| C | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 95% | 8905.3
Residential - Ground Floor Lobby
| D | Type RES-ST-16; Stone cladding to cloakroom | m2 | 14 | 598 | 8372 | 23.7% | 1984.4746 | 95% | 1885.2508
| E | Type RES-ST-16; Stone cladding to concierge area | m2 | 53 | 598 | 31694 | 23.7% | 7512.6537 | 95% | 7137.0211
| F | Type RES-ST-16; Stone pillars with lit surface to corridor including metal structure | m2 | 175 | 626 | 109550 | 23.7% | 25967.4139 | 95% | 24669.0432
| G | Type RES-ST-16; Backlit stone cladding to corridor | m2 | 2 | 598 | 1196 | 23.7% | 283.4964 | 95% | 269.3215
| H | Type RES-ST-16; Stone fascia 250mm wide to corridor (refer Drawing 120) | mr | 4 | 214 | 856 | 23.7% | 202.9038 | 95% | 192.7586
| J | Type RES-ST-16; Stone fascia 250mm wide to cloakroom (refer Drawing 120) | mr | 2 | 214 | 428 | 23.7% | 101.4519 | 95% | 96.3793
| K | Type RES-ST-26; Stone cladding in open book to lift lobby | m2 | 61 | 676 | 41236 | 23.7% | 9774.4617 | 95% | 9285.7386
| L | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4497 | 8994 | 100% | 8994 |  | 0
Residential - Level 2 Lobby and Corridor
| M | Type RES-ST-16; Stone pillars with lit surface to lobby including metal structure | m2 | 49 | 626 | 30674 | 23.7% | 7270.8759 | 95% | 6907.3321
| N | Type RES-ST-26; Stone cladding to lift lobby | m2 | 24 | 744 | 17856 | 23.7% | 4232.5344 | 95% | 4020.9077
| S | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 95% | 8905.3
Residential - Level 4 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-16; Stone cladding to corridor (wooden stiles and rails measured separately) | m2 | 83 | 598 | 49634 | 23.7% | 11765.0992 | 95% | 11176.8443
| C | Type RES-ST-23; Stone screen (2 layers of stone) 2100mm high to men's changing room (refer Drawings 315 to 318) | m2 | 21 | 842 | 17682 | 23.7% | 4191.2899 | 95% | 3981.7254
| D | Type RES-ST-23; Stone screen (2 layers of stone) 2100mm high to women's changing room (refer Drawings 310 to 313) | m2 | 23 | 842 | 19366 | 23.7% | 4590.4604 | 95% | 4360.9374
| E | Type RES-ST-23; Stone fluted walls to men's changing room | m2 | 19 | 954 | 18126 | 23.7% | 4296.5344 | 95% | 4081.7077
| F | Type RES-ST-23; Stone fluted walls to women's changing room | m2 | 31 | 954 | 29574 | 23.7% | 7010.1351 | 95% | 6659.6283
| G | Type RES-ST-23; Stone cladding to men's changing room | m2 | 7 | 744 | 5208 | 23.7% | 1234.4892 | 95% | 1172.7647
| H | Type RES-ST-23; Stone cladding to shower room at men's changing room | m2 | 35 | 744 | 26040 | 23.7% | 6172.446 | 95% | 5863.8237
| J | Type RES-ST-23; Stone cladding to shower room at women's changing room | m2 | 36 | 744 | 26784 | 23.7% | 6348.8016 | 95% | 6031.3615
| K | Type RES-ST-23; Stone wall to cistern enclosure overall size 1020mm (L) x 1080mm (H) at men's changing room (refer Drawing 322) | No | 2 | 1021 | 2042 | 23.7% | 484.0298 | 95% | 459.8283
| L | Type RES-ST-23; Stone wall to cistern enclosure overall size 1020mm (L) x 1080mm (H) at women's changing room (refer Drawing 322) | No | 2 | 1021 | 2042 | 23.7% | 484.0298 | 95% | 459.8283
| M | Type RES-ST-26; Stone cladding to lift lobby | m2 | 46 | 954 | 43884 | 100% | 43884 | 60% | 26330.4
| A | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 60% | 5624.4
Residential - Level 23 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-26; Stone cladding to lift lobby | m2 | 38 | 954 | 36252 | 100% | 36252 | 60% | 21751.2
| C | Type RES-ST-26; Stone cladding to single leaf door size 1100 x 2550mm high (refer Drawing 309) (Jib door and ironmongery are by others) | No | 2 | 4687 | 9374 | 100% | 9374 | 50% | 4687
| D | Type RES-ST-22; Stone wall to men's restroom (refer Detail 12 & 13 of Drawing 33) (metal strips measured separately) | m2 | 36 | 1466 | 52776 | 100% | 52776 | 60% | 31665.6
| E | Type RES-ST-22; Stone wall to women's restroom (refer Detail 12 & 13 of Drawing 33) (metal strips measured separately) | m2 | 40 | 1466 | 58640 | 100% | 58640 | 60% | 35184
| F | Type RES-ST-21; Stone wall to cistern enclosure overall size 1270mm (L) x 1080mm (H) at men's changing room (refer Drawing 354) | No | 2 | 860 | 1720 | 100% | 1720 | 40% | 688
| G | Type RES-ST-21; Stone wall to cistern enclosure overall size 1270mm (L) x 1080mm (H) at women's changing room (refer Drawing 354) | No | 2 | 860 | 1720 | 100% | 1720 | 50% | 860
SKIRTING
Stone skirting finish including all necessary supports, framing, backing, fixings, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| H | Type RES-ST-16; Stone skirting 250mm high to cloakroom (refer Detail 03 of Drawing 301) | mr | 6 | 360 | 2160 | 23.7% | 512.0001 | 95% | 486.4001
| J | Type RES-ST-16; Stone skirting 250mm high to concierge (refer Detail 05 of Drawing 300) | mr | 10 | 360 | 3600 | 23.7% | 853.3335 | 95% | 810.6669
Residential - Level 2 Lobby and Corridor
| A | Type RES-ST-02; Stone skirting 250mm high to lobby (refer Detail 08 of Drawing 300) | mr | 19 | 458 | 8702 | 23.7% | 2062.6968 | 95% | 1959.562
Residential - Level 4 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-23; Stone skirting 150mm high to men's changing room | mr | 7 | 288 | 2016 | 23.7% | 477.8668 | 95% | 453.9734
| C | Type RES-ST-23; Stone skirting 200mm high to men's changing room inside cubicles (refer Detail 02 of Drawing 301) | mr | 5 | 346 | 1730 | 23.7% | 410.0742 | 95% | 389.5705
| D | Type RES-ST-23; Stone skirting 150mm high to women's changing room | mr | 5 | 288 | 1440 | 23.7% | 341.3334 | 95% | 324.2667
| E | Type RES-ST-23; Stone skirting 200mm high to women's changing room inside cubicles (refer Detail 02 of Drawing 301) | mr | 15 | 346 | 5190 | 23.7% | 1230.2225 | 95% | 1168.7114
Residential - Level 23 Amenities, Corridor and Lift Lobby
| F | Type RES-ST-11; Stone skirting 300mm high to meeting room (refer Detail 02 of Drawing 336) | mr | 3 | 449 | 1347 | 100% | 1347 | 50% | 673.5
| G | Type RES-ST-11; Stone skirting 300mm high to mulfunction room (refer Detail 02 of Drawing 336) | mr | 2 | 449 | 898 | 100% | 898 | 50% | 449
| H | Type RES-ST-21; Stone skirting 300mm high to men's restroom (refer Detail 02 of Drawing 336) | mr | 2 | 433 | 866 | 100% | 866 | 50% | 433
| J | Type RES-ST-21; Stone skirting 300mm high to women's restroom (refer Detail 02 of Drawing 336) | mr | 2 | 433 | 866 | 100% | 866 | 50% | 433
THRESHOLD
Supply and fixing of stone threshold, including all necessary grouting, polishing, adhesives, etc. and the like; all in accordance with the drawings and specification
Residential - Basement 1 Lift Lobby
| A | Type RES-ST-16; Stone threshold 225mm wide to lift lobby | mr | 2 | 164 | 328 | 23.7% | 77.7482 | 95% | 73.8608
| B | Type RES-ST-16; Stone threshold 305mm wide to lift lobby | mr | 5 | 207 | 1035 | 23.7% | 245.3334 | 95% | 233.0667
Residential - Basement 2 Lift Lobby
| C | Type RES-ST-16; Stone threshold 225mm wide to lift lobby | mr | 2 | 164 | 328 | 23.7% | 77.7482 | 95% | 73.8608
| D | Type RES-ST-16; Stone threshold 305mm wide to lift lobby | mr | 5 | 207 | 1035 | 23.7% | 245.3334 | 95% | 233.0667
Residential - Ground Floor Lobby
| E | Type RES-ST-16; Stone threshold 225mm wide to lift lobby | mr | 3 | 164 | 492 | 23.7% | 116.6223 | 95% | 110.7911
| F | Type RES-ST-16; Stone threshold 305mm wide to lift lobby | mr | 5 | 207 | 1035 | 23.7% | 245.3334 | 95% | 233.0667
| G | Type RES-ST-16; Stone threshold 500mm wide to BOH door | mr | 2 | 307 | 614 | 23.7% | 145.5408 | 95% | 138.2637
| H | Type RES-ST-26; Stone threshold 250mm wide to airlock | mr | 21 | 211 | 4431 | 23.7% | 1050.3114 | 95% | 997.7958
| J | Type RES-ST-27; Stone threshold 250mm wide to airlock | mr | 20 | 211 | 4220 | 23.7% | 1000.2965 | 95% | 950.2817
| K | Type RES-ST-27; Stone threshold 315mm wide to concierge | mr | 2 | 258 | 516 | 23.7% | 122.3111 | 95% | 116.1956
Residential - Level 2 Lobby and Corridor
| A | Type RES-ST-16; Stone threshold 375mm wide to lift lobby | mr | 3 | 244 | 732 | 23.7% | 173.5112 | 95% | 164.8356
| B | Type RES-ST-16; Stone threshold 415mm wide to lift lobby | mr | 5 | 264 | 1320 | 23.7% | 312.889 | 95% | 297.2445
| C | Type RES-ST-16; Stone threshold 1450mm wide to lift lobby | mr | 3 | 809 | 2427 | 23.7% | 575.289 | 95% | 546.5246
Residential - Level 4 Amenities, Corridor and Lift Lobby
| D | Type RES-ST-16; Stone threshold 375mm wide to lift lobby | mr | 2 | 244 | 488 | 23.7% | 115.6741 | 95% | 109.8904
| E | Type RES-ST-16; Stone threshold 415mm wide to lift lobby | mr | 5 | 264 | 1320 | 23.7% | 312.889 | 95% | 297.2445
| F | Type RES-ST-16; Stone threshold 1180mm wide to lift lobby | mr | 3 | 666 | 1998 | 23.7% | 473.6001 | 95% | 449.9201
| G | Type RES-ST-24; Stone threshold 100mm wide to men's and women's changing room | mr | 4 | 110 | 440 | 23.7% | 104.2963 | 95% | 99.0815
| H | Type RES-ST-25; Stone threshold 100mm wide to men's and women's changing room | mr | 4 | 110 | 440 | 23.7% | 104.2963 | 95% | 99.0815
Residential - Level 23 Amenities, Corridor and Lift Lobby
| J | Type RES-ST-02; Stone threshold 200mm wide to corridor | mr | 2 | 213 | 426 | 100% | 426 | 50% | 213
| K | Type RES-ST-02; Stone threshold 285mm wide to lift lobby | mr | 5 | 291 | 1455 | 100% | 1455 | 95% | 1382.25
| L | Type RES-ST-02; Stone threshold 340mm wide to meeting and multifunction room | mr | 7 | 334 | 2338 | 100% | 2338 | 50% | 1169
| M | Type RES-ST-02; Stone threshold 500mm wide to BOH doors | mr | 4 | 470 | 1880 | 100% | 1880 | 50% | 940
| N | Type RES-ST-21; Stone threshold 250mm wide to men's and women's restrooms | mr | 2 | 183 | 366 | 100% | 366 | 50% | 183
ARCHITRAVE FINISHES
Stone architrave finishes including all necessary supports, framing, backing, fixings, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Basement 1 Lift Lobby
| A | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 100% | 7175 | 50% | 3587.5
| B | Type RES-ST-02; Stone architrave size 1450mm wide (refer Drawing 202) | mr | 15 | 1295 | 19425 | 100% | 19425 | 50% | 9712.5
Residential - Basement 2 Lift Lobby
| C | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 23.7% | 1700.7412 | 95% | 1615.7041
| D | Type RES-ST-02; Stone architrave size 1450mm wide (refer Drawing 202) | mr | 15 | 1295 | 19425 | 23.7% | 4604.4456 | 95% | 4374.2233
Residential - Ground Floor Lobby
| E | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby (refer Drawing 310) | mr | 25 | 287 | 7175 | 23.7% | 1700.7412 | 95% | 1615.7041
| F | Type RES-ST-16; Stone architrave size 400mm wide (refer Drawing 305) (linear lighting by others) | mr | 39 | 268 | 10452 | 23.7% | 2477.5117 | 95% | 2353.6361
| G | Type RES-ST-16; Stone architrave size 400mm wide (refer Drawing 306) (linear lighting by others) | mr | 29 | 268 | 7772 | 23.7% | 1842.2523 | 95% | 1750.1397
| H | Type RES-ST-16; Stone architrave size 400mm wide (refer Drawing 307) (linear lighting by others) | mr | 10 | 268 | 2680 | 23.7% | 635.2594 | 95% | 603.4964
Residential - Level 2 Lobby and Corridor
| J | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby (refer Drawing 310) | mr | 25 | 287 | 7175 | 23.7% | 1700.7412 | 95% | 1615.7041
| K | Type RES-ST-02; Stone architrave size 1450mm wide (refer Drawing 202) | mr | 8 | 1295 | 10360 | 23.7% | 2455.7043 | 95% | 2332.9191
| A | Type RES-ST-16; Stone architrave size 1800mm wide (refer Drawing 201) | mr | 16 | 1008 | 16128 | 23.7% | 3822.9343 | 95% | 3631.7876
Residential - Level 4 Amenities, Corridor and Lift Lobby
| B | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 100% | 7175 | 95% | 6816.25
Residential - Level 23 Amenities, Corridor and Lift Lobby
| C | Type RES-ST-02; Stone architrave size 265mm wide to lift lobby | mr | 25 | 287 | 7175 | 100% | 7175 | 95% | 6816.25
STONE VANITY
Supply and installation of stone vanity counter top with fascia and splash back, including all necessary supports, framing, backing, fittings, accessories, cut-out hole for basin, etc. and the like; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| D | Vanity counter with finish Type RES-ST-23; overall size 4300mm (L) x 600mm (W) x 290mm (H) to women's changing room (refer Drawings 310, 311 and 313) | No | 1 | 3697 | 3697 | 100% | 3697 | 95% | 3512.15
| E | Towel hamper with finish Type RES-ST-23; overall size 605mm (L) x 560mm (W) x 565mm (H) to women's changing room (refer Drawings 310, 311 and 313) | No | 1 | 908 | 908 | 100% | 908 | 95% | 862.6
| F | Vanity counter with finish Type RES-ST-23; overall size 3320mm (L) x 600mm (W) x 280mm (H) to men's changing room (refer Drawings 315, 316 and 318) | No | 1 | 2982 | 2982 | 100% | 2982 | 95% | 2832.9
| G | Vanity counter with finish Type RES-ST-23; overall size 640mm (L) x 360mm (W) x 850mm (H) to men's changing room (refer Drawing 319) | No | 1 | 2988 | 2988 | 100% | 2988 | 95% | 2838.6
Residential - Level 23 Amenities, Corridor and Lift Lobby
| A | Vanity with finish Type RES-ST-21; overall size 2700mm (L) x 460 / 480 mm (W) x 800 / 850 mm (H) to men's restroom (refer Drawing 355 to 357) | No | 1 | 2767 | 2767 | 100% | 2767 |  | 0
| A1 | Vanity basin with finish Type RES-ST-21; overall size 420mm (L) x 420mm (W) x 160 mm (H) to men's restroom | No | 2 | 2017 | 4034 | 100% | 4034 |  | 0
| A2 | Vanity cladding with finish Type RES-ST-21; overall size 1510mm (L) x 850 mm (H) to men's restroom | No | 2 | 966 | 1932 | 100% | 1932 |  | 0
| B | Vanity with finish Type RES-ST-21; overall size 2700mm (L) x 460 / 480 mm (W) x 800 / 850 mm (H) to women's restroom (refer Drawing 355 to 357) | No | 1 | 4733 | 4733 | 100% | 4733 |  | 0
| B1 | Vanity basin with finish Type RES-ST-21; overall size 420mm (L) x 420mm (W) x 160 mm (H) to women's restroom | No | 2 | 2017 | 4034 | 100% | 4034 |  | 0
| B2 | Vanity cladding with finish Type RES-ST-21; overall size 1510mm (L) x 850 mm (H) to women's restroom | No | 2 | 966 | 1932 | 100% | 1932 |  | 0
STONE LEDGE TOP
Supply and installation of stone ledge top at wc cistern including all necessary supports, framing, backing, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| C | Ledge top with finish Type RES-ST-23; overall size 1020mm (L) x 230mm (W) to men's changing room (refer Drawing 322) | No | 2 | 267 | 534 | 23.7% | 126.5778 | 95% | 120.2489
| D | Ledge top with finish Type RES-ST-23; overall size 1020mm (L) x 230mm (W) to women's changing room (refer Drawing 322) | No | 2 | 267 | 534 | 23.7% | 126.5778 | 95% | 120.2489
Residential - Level 23 Amenities, Corridor and Lift Lobby
| E | Ledge top with finish Type RES-ST-21; overall size 1270mm (L) x 230mm (W) to men's changing room (refer Drawing 354) | No | 2 | 299 | 598 | 100% | 598 |  | 0
| F | Ledge top with finish Type RES-ST-21; overall size 1270mm (L) x 230mm (W) to women's changing room (refer Drawing 354) | No | 2 | 299 | 598 | 100% | 598 |  | 0
STONE TOP
Supply and installation of stone top including all necessary supports, framing, backing, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| A | Stone top and cladding finish RES-ST-10 to concierge desk; overall size 3000mm (L) x 600mm (W) x 1100mm (H) (Drawing 302) | No | 1 | 5291 | 5291 | 100% | 5291 |  | 0
| B | Stone top to concierge station; overall size 1370mm (L) x 720mm (W) x 2215mm (H) (Drawing 303) | No | 1 | 884 | 884 | 100% | 884 |  | 0
Residential - Level 4 Amenities, Corridor and Lift Lobby
| C | Stone top with finish Type RES-ST-02; overall size 2205mm (L) x 505mm (W) to refreshment cabinet at fitness room (refer Drawing 326 and 327) (timber cabinet measured separately) | No | 1 | 1334 | 1334 | 100% | 1334 |  | 0
Residential - Level 23 Amenities, Corridor and Lift Lobby
| D | Stone top with finish Type RES-ST-07b to Meeting room cupboard; overall size 2670mm (L) x 580mm (W) (refer Drawing 349 to 351) | No | 2 | 4279 | 8558 | 100% | 8558 |  | 0
| D1 | Stone top with finish Type RES-ST-07b to Meeting room TV cupboard; overall size 1900mm (L) x 580mm (W) | No | 1 | 3125 | 3125 | 100% | 3125 |  | 0
| E | Stone top with finish Type RES-ST-07b to Multifunction room cupboard; overall size 2590mm (L) x 580mm (W) (refer Drawing 350 to 352) | No | 2 | 4151 | 8302 | 100% | 8302 |  | 0
| E1 | Stone top with finish Type RES-ST-07b to Multifunction room TV cupboard; overall size 1900mm (L) x 580mm (W) | No | 1 | 3125 | 3125 | 100% | 3125 |  | 0
STONE SHELF
Supply and installation of stone shelf including all necessary supports, framing, backing, fittings, accessories, etc. and the like; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| A | Shelf with finish Type RES-ST-23; overall size 640mm (L) x 340mm (W) fixed to the wall at men's changing room (refer Drawing 319) | No | 1 | 5140 | 5140 | 100% | 5140 | 95% | 4883
| B | Shelf with finish Type RES-ST-23; overall size 600mm (L) x 530mm (W) fixed to the wall to women's changing room (refer Drawings 310, 311 and 313) | No | 1 | 479 | 479 | 100% | 479 | 95% | 455.05
STONE BENCH
Supply and installation of stone bench including all necessary supports, framing, backing, fixings, fittings, accessories, finishes, etc. and the like complete; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| C | Entrance bench with finish Type RES-ST-16; overall size 1965mm (L) x 340mm (W) x 450mm (H) fixed to the wall (refer Drawing 301) | No | 2 | 946 | 1892 | 100% | 1892 |  | 0
STONE WATER FEATURE
Supply and installation of stone water feature including all necessary supports, framing, backing, fixings, fittings, accessories, finishes, etc. and the like complete; all in accordance with the drawings and specification
Residential - Ground Floor Lobby
| D | Water feature with finish Type RES-ST-16; overall size 1550mm (D) x 500mm (H) to corridor (refer Drawing 308) | No | 1 | 4767 | 4767 | 100% | 4767 |  | 0
STONE WELCOME DESK
Supply and installation of stone welcome desk including all necessary supports, framing, backing, fixings, fittings, accessories, finishes, etc. and the like complete; all in accordance with the drawings and specification
Residential - Level 4 Amenities, Corridor and Lift Lobby
| A | Welcome desk with finish Type RES-ST-16; overall size 1300mm (L) x 500mm (W) x 1100mm (H) to corridor (refer Drawing 303 to 305) | No | 1 | 3918 | 3918 | 100% | 3918 |  | 0
| Add | LIFT CAR
LIFT CAR (4 NOS.)
| 1 | Type RES-ST-03; Stone border to lift car | m2 | 6 | 805 | 4830 | 100% | 4830 |  | 0
| 2 | Type RES-ST-03; Stone threshold 120mm wide | mr | 1 | 154 | 154 | 100% | 154 |  | 0
| 3 | Type RES-ST-03; Stone skirting 250mm high | mr | 7 | 458 | 3206 | 100% | 3206 |  | 0
| 4 | Type RES-ST-16; Stone wall | m2 | 41 | 542 | 22222 | 100% | 22222 |  | 0
| 5 | Type RES-ST-03; Stone lit cornice | m2 | 9 | 994 | 8946 | 100% | 8946 |  | 0
LIFT CAR (1 NO.)
| 1 | Type RES-ST-03; Stone border to lift car | m2 | 2 | 805 | 1610 | 23.7% | 381.6297 | 95% | 362.5482
| 2 | Type RES-ST-03; Stone threshold 120mm wide | mr | 1 | 154 | 154 | 23.7% | 36.5037 | 95% | 34.6785
| 3 | Type RES-ST-03; Stone skirting 250mm high | mr | 3 | 458 | 1374 | 23.7% | 325.689 | 95% | 309.4045
| 4 | Type RES-ST-16; Stone wall | m2 | 13 | 542 | 7046 | 23.7% | 1670.1634 | 95% | 1586.6552
| 5 | Type RES-ST-03; Stone lit cornice | m2 | 2 | 994 | 1988 | 23.7% | 471.2297 | 95% | 447.6683
|  | Total Amount in AED |  |  |  | 1280670 |  | 645852.8045 |  | 402354.1143
|  | Less Special Discount | -0.043469 |  |  | -55670 |  | -28074.8558 |  | -17490.1056 | -4.347%
|  | Total Amount in AED |  |  |  | 1225000 |  | 617777.9486 |  | 384864.0086
50.43%
317606
[8 empty] | 245000 |  | -67258.0086

## 7A and 15A (hidden)
| 7A and 15A | Dar Al Rokham
Level | Room | Floor | Wall | Architrave | Joinery | Total Progress | Remark
|  | 19.61% | 53.31% | 5.224% | 21.86% | 100%
7-8 | 7A | 100% | 100% |  |  | 72.91% | Wet area floor done
10-11 | 15A | 100% | 100% |  |  | 72.91%
13-14 | 7A | 100% | 100% |  |  | 72.91%
15-16 | 7A | 100% | 100% |  |  | 72.91%
20-21 | 7A |  |  |  |  | 0%
22-23 | 15A |  |  |  |  | 0%
24-25 | 7A | 100% | 100% |  |  | 72.91%
|  | Overall progress for 7A and 15A |  |  |  | 52.08%

## Weightage caluclation
11A Guest Room
| Amount | Weightage
Floor | 307943.45 | 19.61%
Wall | 837223.6 | 53.31%
Architraves | 82042 | 5.224%
Joinery Works | 343380.35 | 21.86%
Total | 1570589.4 | 100%

## Vo Sum (hidden)
PROJECT | : Plot 18, Plot BB.B03.018, Business Bay, Dubai, UAE.
CLIENT | : Roberts - Pizzarotti JV
SITE NO | : 3140
PAYMENT APPLICATION NO. 5 |  |  |  | Payment Upto End Of | : April 2020
LIST OF VARATION ORDER APPLICATIONS
Vo.No: | Description | Amount Submitted | % Work Done | Amount Submitted | Remark
1 Rev 3 - Part A | Supply & installation of steel frame - lvl 8,9 & 10 DAR/3140/m/rj/0299 Dated 30 Jan 2020. | 124139.48 | 100% | 124139.48 | Approved
1 Rev 3 - Part B | Supply & installation of steel frame - lvl 11 to 16 DAR/3140/m/rj/0962 Dated 24 March 2020. | 462929.09 | 100% | 462929.0875 | Work Progress As Per The Attached List
2 | Supply & installation of stone works at guest room corridor. DAR/3140/m/rj/0516 Dated 17 Feb 2020. | 1876688 | 0% | 0
.
TOTAL AMOUNT |  |  | Dhs. | 587068.5675

## VO # 01 rev 3 part B (hidden)
PROJECT | : Dorchester Hotel at Business Bay - Dubai
Client | : Sky Palaces Real Estate Development LLC / Omniyat Properties Fifteen Limited
MAIN CONT. | : Roberts - Pizzarotti JV
SITE NO | : 3140
SUBJECT | : Supply & Installation Of Steel Frame Support - Lvl 11 To 16
VARIATION ORDER APPLICATION # 1 Rev 3 - Part B [ WORK PROGRESS ]
Sr. No: | Type | Item Description | Lvl 11 | Lvl 12 | Lvl 13 | Lvl 14 | Lvl 15 | Lvl 16 | Total No Of Room Work Completed | Unit | Rate | Amount (AED) | Notes
1 | TYPE -01A (6 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  |  |  | 1 | 1 |  | 2 | No | 2716.4 | 5432.8 |  | V - Type 1
2 | TYPE -01C (8 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 1 | 1 | 1 |  |  | 1 | 4 | No | 2716.4 | 10865.6 |  | V - Type 1
3 | TYPE -2A/2B/2C/2D (44 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | No | 2716.4 | 48895.2 |  | V - Type 1
4 | TYPE -2A/2B/2C/2D (44 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 | 3 | 3 | 3 | 3 | 3 | 3 | 18 | No | 2700 | 48600
5 | TYPE -2E/2F/2G/2H (27 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 3 | 3 | 3 | 3 | 3 | 15 | No | 2716.4 | 40746 |  | V - Type 1
6 | TYPE -2E/2F/2G/2H (27 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 3 | 3 | 3 | 3 | 3 | 15 | No | 2700 | 40500
7 | TYPE -3A/3B/3D/3E/3G (39 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 2 | 3 | 3 | 3 | 3 | 3 | 17 | No | 4705.2 | 79988.4 |  | V - Type 2
8 | TYPE -03C/03F (18 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 4705.2 | 47052 |  | V - Type 2
9 | TYPE -04A/4B (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 1 | [5 empty] | 1 | No | 3716.4 | 3716.4 |  | V - Type 2
10 | TYPE -05A (9 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 3716.4 | 18582 |  | V - Type 2
11 | TYPE -08A (5 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A | 1 | [5 empty] | 1 | No | 3716.4 | 3716.4 |  | V - Type 2
12 | TYPE -08A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 | 1 | [5 empty] | 1 | No | 1041.6562 | 1041.6562 |  | V - Type 3
13 | TYPE -09A (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 1 |  |  |  |  | 1 | No | 3177.2 | 3177.2 |  | V - Type 1
14 | TYPE -09A (2 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 1 |  |  |  |  | 1 | No | 2700 | 2700
15 | TYPE -09A (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 1 |  |  |  |  | 1 | No | 1041.6562 | 1041.6562 |  | V - Type 3
16 | TYPE -09B (2 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 1 |  |  |  |  | 1 | No | 2927.6 | 2927.6 |  | V - Type 1
17 | TYPE -09B (2 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 1 |  |  |  |  | 1 | No | 2700 | 2700
18 | TYPE -09B (2 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 1 |  |  |  |  | 1 | No | 1041.6562 | 1041.6562 |  | V - Type 3
19 | TYPE -10A (5 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 2927.6 | 14638 |  | V - Type 1
20 | TYPE -10A (5 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 2700 | 13500
21 | TYPE -10A (5 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 1 | 1 | 1 | 1 | 1 | 5 | No | 1041.6562 | 5208.2812 |  | V - Type 3
22 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 938.3438 | 9383.4375 |  | V - Type 3
23 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 575.25 | 5752.5 |  | V - Type 3
24 | TYPE -11A/11B/11C/11D (19 No's) | Vanity Top , V - Type 3 as per the attached sketch ref. DAR/3140/SK/003 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 989.55 | 9895.5 |  | V - Type 3
25 | TYPE -11A/11B/11C/11D (19 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 |  | 2 | 2 | 2 | 2 | 2 | 10 | No | 2700 | 27000
26 | TYPE -16A (3 No's) | Vanity Top / Side Walls, V - Type 1 as per the attached sketch ref. DAR/3140/SK/001 | 1 | [5 empty] | 1 | No | 2716.4 | 2716.4 |  | V - Type 1
27 | TYPE -16A (3 No's) | Bath Tub Top / Side Walls, B - Type 1&2 as per the attached sketch ref. DAR/3140/SK/005 | 1 | [5 empty] | 1 | No | 2700 | 2700
28 | TYPE -19A (6 No's) | Vanity Top / walls, V - Type 2 as per the attached sketch ref. DAR/3140/SK/002 & 002A |  |  | 1 |  | 1 |  | 2 | No | 4705.2 | 9410.4 |  | V - Type 2
|  | TOTAL AMOUNT | [8 empty] | Aed. | 462929.0875
Notes : | * This Submittal is for Steel Frames Support Only - Cement board / Gypsum board are not under DAR scope of work.
* Limit of Scope is as indicated in "Notes" Column
* Back Wall for Bath Tub and V - Type 1 are assumed to be safely carry the load of of stone as advised by Wall Partion's Sub Contractor thru the Contractor.
* Walls to V - Type 3 are assumed to be safely carry the load of stone as advised by Wall Partion's Sub Contractor thru the Contractor.
* Rates / Amounts excludes VAT
* This variation is the extracted portion ( Lvl 11,12,13,14,15 & 16 ) of DAR variation 1 rev 3 ( Ref. DAR/3140/m/mh/0022, Dated 5th Jan 2020 )
Verify Basic Data