## IPA
| EMPLOYER |  | : | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE |  | : | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER |  | : | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR |  | : | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| PROJECT |  | : | DORCHESTER HOTEL AND RESIDENCES
| KHANSAHEB JOB REF. NO. |  | : | 201A22002
| APPLICATION FOR PAYMENT NO. 11 | [6 empty] | FOR THE PERIOD ENDING: 31ST DECEMBER 2022
|  | Description |  | Contract Value Amount (AED) | Previous (AED) | This (AED) | Cumulative (AED)
|  | Total Value of Workdone |  | 194951734.5 | 122472285.9564 | 22817074.2414 | 145289360.1978
|  |  |  | 0 | 0 | 0 | 0
|  | Total |  | 194951734.5 | 122472285.9564 | 22817074.2414 | 145289360.1978
SUMMARY
| (i) | Total Value of Workdone |  |  |  |  | 145289360.1978 |  |  | 56294044.2448 | -88995315.953
|  | Sub Total 01 |  |  |  |  | 145289360.1978
0
| (ii) | Add Mobilisation Payment 01 & 02 |  |  |  |  | 12000000
|  | Sub Total 2 |  |  |  |  | 157289360.1978 |  |  | 68294044.2448 | -88995315.953
| (iii) | Less Retention @ 10% on Provisional Sums & MEP (Except prelims & OHP ) |  |  |  |  | -6598238.9366 |  | KCE retention | 35155384.4262 | -3515538.4426
| (iv) | Less Amount Certified Previously |  |  |  |  | -125482803.9092 |  | KMEP retention | 30827004.94 | -3082700.494
[10 empty] | 65982389.3662 | -6598238.9366
| (v) | Amount due for Payment |  |  |  |  | 25208317.352
157289360.1978
-3191697.0765
-397333
06.01.23
| Signature | [5 empty] | Date
Note: |  | Mobilisation payments (AED 12 million) to be recovered from subsequent payments as LOA clause 30. | [7 empty] | -448628.7596
153251701.3618
130255895.9809
-22995805.3809
86791925.909
-70497434.2888

## Summary
APPLICATION FOR PAYMENT - SUMMARY
| PROJECT | DORCHESTER HOTEL AND RESIDENCES | [5 empty] | FOR THE PERIOD ENDING: 31ST DECEMBER 2022
| EMPLOYER | SKY PALACES REAL ESTATE DEVELOPMENT LLC
| EMPLOYER'S REPRESENTATIVE | OMNIYAT CONCEPT INVESTMENTS LLC
| ENGINEER | BREWER SMITH BREWER GULF ( BSBG )
| MAIN CONTRACTOR | KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
| CONTRACT NO. | 201A22002
| Item | Contract Amount | Percentage Complete |  |  | Value Complete |  |  |  | 461823.5938
|  |  | Previous Certificate | This Month | To Date | Previous Valuation | This Month | To Date |  |  |  | Total Certified |  | Variance
| Main Contract Value | 194951734.5 | [6 empty] | 6053836.2575 | 1013274.3962
1 | Civil Works
1.1 | Contract Cost - Direct Work |  |  |  |  | 72387369.7268 | 14145519.7101 | 86532889.437 | 48430690.06 | 8106195.17 |  | 56536885.23 |  | -29996004.207
1.2 | Cost Adjustments |  |  |  |  | -88410.73 | -23775.399 | -112186.129 | -1208 |  |  |  |  | 112186.129
1.3 | Main Contractor OH & Profit (12.5%) |  |  |  |  | 8375680.0796 | 1714954.1859 | 10090634.2655 | 6445740.61 |  |  | 6445740.61 |  | -3644893.6555
( Exc. KID Value )
| Sub Total 1 |  |  |  |  | 80674639.0764 | 15836698.497 | 96511337.5734 |  |  |  | 62982625.84 | 0 | -33528711.7334
2 | Provisional Sums (excl MEP)
2.1 | Subcontract Cost
2.2 | Main Contractor OH & Profit (12.5%)
| Sub Total 2 |  |  |  |  | 0 | 0 | 0
3 | MEP Works
3.1 | Subcontract Cost (incl KMEP oh&p of 12.5%) |  |  |  |  | 37997860.8 | 6345796.1313 | 44343656.9313 | 39416583.9389 |  | Correction: Apply retention only on KMEP SC works | 30299794.5825 |  | -14043862.3488
3.2 | Main Contractor OH & Profit on MEP (10%) |  |  |  |  | 3799786.08 | 634579.6131 | 4434365.6931 | 4031241.5392 |  |  | 2797241.92 |  | -1637123.7731
| Sub Total 3 |  |  |  |  | 41797646.8799 | 6980375.7444 | 48778022.6244 |  |  |  | 33097036.5025 | 0 | -15680986.1219
|  | 194951734.5 |  |  |  | 122472285.9564 | 22817074.2414 | 145289360.1978 |  |  |  | 96079662.3425 |  | -49209697.8553
130876546.3682
85904689.09
8106195.17
96079662.3497
0.0072381

## Pre Cert
APPLICATION FOR PAYMENT NO. 11
PREVIOUSLY CERTIFIED AMOUNTS
Certificate No. | Description | Certified Amount (AED)
1 | Payment Certificate 01 | 6000000
2 | Payment Certificate 02 | 6000000
3 | Payment Certificate 03 | 2104452.12
4 | Payment Certificate 04 | 11118319.2
5 | Payment Certificate 05 | 11047382.21
6 | Payment Certificate 06 | 12807977.89
7 | Payment Certificate 07 | 19982204.03
8 | Payment Certificate 08 | 15491078.95
9 | Payment Certificate 09 | 19804921.87
10 | Payment Certificate 10 | 21126467.6392
11 | Payment Certificate 11
12
13
14
15
16
17
18
19
20
21
22
| TOTAL AMOUNT | 125482803.9092

## Cover
201A22002 - DORCHESTER HOTEL AND RESIDENCES
CONTRACTOR
KHANSAHEB CIVIL ENGINEERING L.L.C.
APPLICATION FOR PAYMENT NO. 11
201A22002 - DORCHESTER HOTEL AND RESIDENCES
APPLICATION FOR PAYMENT NO. 11
| Section 1 | Certificate / Summary
| Section 2 | Cost breakdown Summary
| Section 3 | Labour Cost & Backup
| Section 4 | Material Cost & Backup
| Section 5 | Plant Cost & Backup
| Section 6 | Subcontractor Cost & Backup
| Section 7 | Prelim & General Cost & Backup
| Section 8 | Salary Cost & Backup
| Section 9 | Committed Orders
| Section 10 | MEP Payment Application
| Section 11 | Cost Adjustments
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 1
Certificate / Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 2
Cost breakdown Summary
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 3
Labour Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 4
Material Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 5
Plant Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 6
Subcontractor Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 7
Prelim & General Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 8
Salary Cost & Backup
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 9
Committed Orders
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 10
MEP Payment Application
201A22002 - DORCHESTER HOTEL AND RESIDENCES
Section 11
Cost Adjustments

## SC Summary
SUBCONTRACTOR PAYMENT APPLICATION (CIVIL WORKS) - SUMMARY
PROJECT : DORCHESTER HOTEL AND RESIDENCES | [6 empty] | 2022-12-31
EMPLOYER : SKY PALACES REAL ESTATE DEVELOPMENT LLC
MAIN CONTRACTOR : KHANSAHEB CIVIL ENGINEERING - CONSTRUCTION DIVISION
CONTRACT NO : 201A22002
Sl No | Item | Scope of work | Work Approval Amount | Work Approval Reference | Value Complete |  |  | WD inc. Ad R. | Recovery | Advance P |  | Certified- Nov 22 |  | Variance in certifications
[5 empty] | Previous Valuation | This Month | To Date
| Subcontractors ( PS ) | [6 empty] | 0 |  | 0
1 | Watermaster Technical Services LLC | Swimming Pool & Water Feature works | 2128651 |  | 1650462.71 | 0 | 1650462.71 | 1650462.71 |  |  | 0 | 1345291.0508 |  | -305171.6592
2 | Arcadia Metal Industries | External Metal works | 3330440 |  | 2364551.17 | 1318492.75 | 3683043.92 | 3683043.92 | 499566 | 499566 | 0 | 2354716.13 |  | -1328327.79
3 | Dar Al Rokham LLC | Internal Stone works | 4111821 |  | 3722007.21 | 299560.8 | 4021568.01 | 4021568.01 |  | 0 | 0 | 3136288.1645 |  | -885279.8455
4 | Al Shirawi Contracting Co LLC | Waterproofing works | 1391469 |  | 463285 | 197403 | 660688 | 660688 |  |  | 0 | 409986.6913 |  | -250701.3087
5 | Alshafar Interiors Co LLC | Joinery to Guest Rooms | 5919164.28 |  | 2692361.9978 | 126347.6445 | 2818709.6423 | 2340405.9323 | 409571.04 | 887874.75 | 478303.71 | 2571920.8521 |  | -246788.7901
6 | Isam Kabbani & Partners | Guniting & Waterproofing works | 1155933 |  | 436014.05 | 4795.77 | 440809.82 | 440809.82 |  |  | 0 | 431718.9156 |  | -9090.9044
7 | Fiona Environs UAE | Soft Landscaping & Irrigation works | 3313028.6 |  | 1665912.56 | 314185.9 | 1980098.46 | 1980098.46 |  |  | 0 | 1576197.1379 |  | -403901.3221
8 | Al Reem Marble & Granite LLC | External Stoneworks | 4556481 |  | 2522045.54 | 751792.18 | 3273837.72 | 3070731.13 | 13848.56 | 216955.15 | 203106.59 | 2377393.6246 |  | -896444.0954
9 | Joyz Overseas Technical Services LLC | EIFS works | 1538156.94 |  | 919979.237 | 391695.624 | 1311674.861 | 1286510.191 | 128651.02 | 153815.69 | 25164.67 | 814522.5937 |  | -497152.2673
10 | Bond Interiors Design LLC | Fitout of Hotel Lobby, All Day Dining & Spa Works | 4325954.46 |  | 1885305.72 | 561705.45 | 2447011.17 | 2447011.17 |  |  | 0 | 1740647.89 |  | -706363.28
11 | Al Rawda General Maint. & Decoration Co LLC | Partition & Ceiling works | 1954843 |  | 2206968.81 | 568843.66 | 2775812.47 | 2775812.47 |  |  |  | 2014319.4658 |  | -761493.0042
12 | Joseph Advertisers LLC | Signage works | 999150 |  | 199830 | 0 | 199830 | 0 |  | 199830 | 199830 | 199830 |  | 0
13 | Joseph Decorative Glass | Internal Glazing works | 1262387 |  | 712175.424 | 23698.4 | 735873.824 | 604245.534 | 120849.11 | 252477.4 | 131628.29 | 559636.4144 |  | -176237.4096
14 | Walltracts | Wall Coverings | 712173.7 |  | 664277.335 | 0 | 664277.335 | 381900.395 | 0 | 282376.94 | 282376.94 | 664277.34 |  | 0.005
15 | Goodrich Global Trading LLC | Carpets to Guest Rooms | 839675.05 |  | 274980.8 | 342340.91 | 617321.71 | 617321.71 |  |  |  | 274980.8 |  | -342340.91
16 | Arabian Profile Company Ltd | GRC Works | 4155655 |  | 1063062.9 | 223170 | 1286232.9 | 1286232.9 |  |  |  | 830524.4 |  | -455708.5
17 | Glass Line Aluminium LLC | Aluminium & Glazing Façade works | 10273402 |  | 4512200.62 | 1767889.87 | 6280090.49 | 6280090.49 |  |  |  | 3997115.7277 |  | -2282974.7623
18 | EW COX Middle East LLC | BMU System | 628861 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
19 | Mohammed Tayyeb Khoory & Sons | Garbage & Linen Chutes | 287122 |  | 163261.6 | 0 | 163261.6 | 163261.6 |  |  |  | 140609.4 |  | -22652.2
20 | HTS Carpets Trading LLC | Carpets to lift lobbies & Corridors | 356512.42 |  |  | 0 |  | 0 |  |  |  | 0 |  | 0
21 | Khansaheb Interior DIvision ( KID ) | Restaurant Works |  |  | 5293518.36 | 402110.824 | 5695629.184 | 1465189.984 | 293038 | 4523477.2 |  | 5293518.36 |  | -402110.824
| Subcontractors ( PS ) |  |  |  | 33412201.0437 | 7294032.7825 | 40706233.8263 | 35155384.4262 | 1465523.73 | 7016373.13 | 1320410.2 | 30733494.9582 | 0 | -9972738.868
| Subcontractors (Domestic) | [8 empty] | 2492895.93
1 | Blue Sky LLC | Supply of MEP Maintenance team | 1071950 | P-006 | 694147.04 | 42300 | 736447.04 |  |  |  |  | 681891.51 |  | -54555.53
2 | Data Link Technical Services LLC | Wild Air Partitions | 241882.91 | C-006 | 327917 | 73621 | 401538 |  |  |  |  | 327505.934 |  | -74032.066
3 | Al Rawda General Maint. & Decoration Co LLC | Ceiling & Partition repairs, painting works | 26960 | P-001 | 45698.1 | 0 | 45698.1 |  |  |  |  | 45448 |  | -250.1
4 | Firestop Middle East | Firestopping works | 441760 | C-001, 002 R1 | 146797.0969 | 21361.7031 | 168158.8 |  |  |  |  | 120749.016 |  | -47409.784
5 | Creative House Scaffolding | Scaffolding | 1931942.08 | C-01 & 02 | 2279317.6 | 286319.52 | 2565637.12 |  |  |  |  | 2217615.6388 |  | -348021.4812
6 | Corecut Engineering LLC | Coring & Scanning | 383133 | C-015, 016 | 403786.45 | 55405 | 459191.45 |  |  |  |  | 398708.45 |  | -60483
7 | Inventure Façade Contracting LLC | Glass Balustrade works | 2703097 | C-011 | 1658256.323 | 320642.557 | 1978898.88 |  |  |  |  | 1665104.24 |  | -313794.64
8 | TWIC Insulation Materials Supply LLC | Epoxy Coating & Dust Sealer works | 778544.8 | C-015, 16 R1 | 276899.56 | 35689.9 | 312589.46 |  |  |  |  | 263347.1475 |  | -49242.3125
9 | Al Maraya Marble & Granite Factory LLC | Tile Installation | 514481.6 | C-017 | 251163.76 | 6063.23 | 257226.99 |  |  |  |  | 244297.8528 |  | -12929.1372
10 | German Concrete Works & Building Contracting LLC | Screed & Insulation works | 796114.2 | C-018 R1 | 384050.93 | 2350.84 | 386401.77 |  |  |  |  | 376545.9998 |  | -9855.7702
11 | Greenwood General Trading LLC | Wooden Flooring | 353975.01 | C-005 | 176987.51 | 0 | 176987.51 |  |  |  |  | 176987.51 |  | 0
12 | Al Hayat Fiberglass Ind LLC | GRP Lining works | 313333.4 | C-027 | 118320 | 0 | 118320 |  |  |  |  | 118320 |  | 0
13 | Vulcan Industries LLC | Steel Doors | 685405 | C-032 | 226345 | -25964.31 | 200380.69 |  |  |  |  | 143492.5 |  | -56888.19
14 | Polaris International Industries LLC | Timber Doors | 1008983.76 | C-029 | 411726.0992 | 283745.4136 | 695471.5128 |  |  |  |  | 386045.42 |  | -309426.0928
15 | Center Core Professional Technical Services LLC | Slab cutting & strengthening works | 88900 | C-033 | 88900 | 0 | 88900 |  |  |  |  | 88900 |  | 0
16 | Weserve Technical Services LLC | Miscellaneous Steel works | 1147041.3 | C-052 | 237860.85 | 247596.45 | 485457.3 |  |  |  |  | 237860.85 |  | -247596.45
17 | Venus Engineering LLC | RC column removal & strengthening works | 110965 | C-039 | 77965 | 0 | 77965 |  |  |  |  | 77965 |  | 0
18 | Global Composites Solutions LLC | GRP Cladding to Planter Wall | 225683 | C-053 | 45136.6 | 0 | 45136.6 |  |  |  |  | 45136.6 |  | 0
19 | Indiga Tech Trading LLC | Steel Doors | 154496.05 | C-047 | 24449.21 | 18082.28 | 42531.49 |  |  |  |  | 24449.21 |  | -18082.28
20 | Monrac LLC | Ceiling & Partition repairs, painting works | 918183.61 | PS-021 | 627634.092 | 114043.708 | 741677.8 |  |  |  |  | 556253.9625 |  | -185423.8375
21 | Hygenic Solutions LLC | MMA Flooring | 474794 | C-016 | 274196.05 | 0 | 274196.05 |  |  |  |  | 274195.05 |  | -1
22 | Technical Access Services (L.L.C.) | Scaffolding Works | 1580356.14 | C-065 | 603871.91 | 424198.15 | 1028070.06 |  |  |  |  | 602628.02 |  | -425442.04
23 | Progress Fabrication | Metal Cladding Works and Misc Metal Works | 1264100.14 | C-078 | 322278.25 | 54000 | 376278.25 |  |  |  |  | 227778.25 |  | -148500
24 | Ferco Shutters LLC | Fire Curtains | 33685 | P-027 | 3368.5 | 0 | 3368.5 |  |  |  |  | 3368.5 |  | 0
25 | Jeel Alfan Technical Services | Decorative Paint | 128266 | P-015 | 32066.5 | 0 | 32066.5 |  |  |  |  | 32066.5 |  | 0
26 | Technoserve Technical works LLC | Painting works | 73379.6 | P-012 | 17586.552 | 0 | 17586.552 |  |  |  |  | 17586.552 |  | 0
27 | Dormakaba Middle East | Movable Partition Works- AHK Balance | 366250 | PS-025 | 109875 | 0 | 109875 | 0 |  | 109875 |  | 109875 |  | 0
28 | Khansaheb Joinery DIvision ( KJD ) | Joinery Works- AHK Balance | 2105729.87 | PS-023 | 421145.97 | 256601.6759 | 677747.6459 | 256601.6759 |  | 421145.97 |  | 421145.97 |  | -256601.6759
29 | Al Burhani General Trading LLC | Wooden Flooring & Carpet works- AHK | 133457 | PS-032 | 53002.5 | 0 | 53002.5 | 0 |  | 53002.5 |  | 53002.5 |  | 0
30 | Rattan House Factory for Furniture and Decoration | Res Lobbies, Joinery works- AHK Balance | 279759 | PS-044 | 102424 | 22594.56 | 125018.56 | 125018.56 |  |  |  | 102424 |  | -22594.56
31 | International Foundation Group LLC | Waterproofing Concrete works | 450000 | C-061 R4 | 450000 | 0 | 450000 |  |  |  |  | 450000 |  | 0
32 | X-Calibur Emirates LLC | Stair nosing works | 221889 | C-064 | 52173.9 | 121739.1 | 173913 |  |  |  |  | 52173.9 |  | -121739.1
33 | Master Rubber Manufacturing | Wall & Corner Guard works | 169068.5 | C-062 | 50720.55 | 0 | 50720.55 |  |  |  |  | 50720.55 |  | 0
34 | DNK Engineering Equipment Trading LLC | Rolling Shutter works | 75530 | C-026 | 37765 | 0 | 37765 |  |  |  |  | 37765 |  | 0
35 | Vijayraj Contracting Co LLC | Plastering works | 206250 | C-019 | 151575.25 | 7511.8 | 159087.05 |  |  |  |  | 151575.26 |  | -7511.79
36 | Doormax Building Material Trading LLC | Glass Door works | 128000 | C-090 |  | 32000 | 32000
37 | KTC International Cont LLC | RTA works | 1043942 | C-091 |  | 208788.4 | 208788.4
38 | Urban Science Building Contracting LLC | Joinery- Cupboards | 533125 | C-097 |  | 106625 | 106625
| Subcontractors (Domestic) |  |  |  | 11185408.1531 | 2715315.9776 | 13900724.1307 |  |  |  |  | 10782929.8934 |  | -2770380.8373
| Subcontractors (Domestic & PS ) |  |  |  | 44597609.1968 | 10009348.7601 | 54606957.957 |  |  |  |  | 41516424.8516 |  | -12743119.7054
Subcontractors ( Labour Only )
1 | Al Qannati Electromechanical LLC | Labour Supply ( Block Works ) |  |  | 672765 | 157520 | 830285 |  |  |  |  | 672765 |  | -157520
2 | Focus Power Security Services LLC | Supply of Site Security Service | 252000 | P-004 | 161000 | 21000 | 182000 |  |  |  |  | 161000 |  | -21000
3 | Service plus Technical Services LLC | Cleaning Service | 162400 | P-005 | 96587.96 | 16800 | 113387.96 |  |  |  |  | 96587.96 |  | -16800
| Subcontractors (Labour Only) |  |  |  | 930352.96 | 195320 | 1125672.96 |  |  |  |  | 930352.96 |  | -195320
[7 empty] | 55732630.917 |  |  |  |  | 42446777.8116

## Staff Cost
FOR THE PERIOD ENDING: 31ST DECEMBER 2022
SALARY COST & BACKUPS
Certificate No. | Description | Applied Amount (AED)
1 | 2022-03-01 | 16639.13 | 16639.13 | 0
2 | 2022-04-01 | 438092.619 | 438092.619 | 0
3 | 2022-05-01 | 772560.2273 | 772560.2273 | 0
4 | 2022-06-01 | 991945.4545 | 981763.6364 | -10181.8182
5 | July-22 | 1042220 | 1030430.5263 | -11789.4737
6 | August-22 | 1160798.7391 | 1137101.7391 | -23697
7 | September-22 | 1257377 | 1228858.1818 | -28518.8182
8 | October-22 | 1266237 | 1236938.0952 | -29298.9048
9 | November-22 | 1303682.27
10 | December-22 | 1299435.18
11
12
13
14
15
16
17
18
19
| TOTAL AMOUNT | 9548987.62 | 6842384.1552 | -103486.0148

## Cost Adust't
FOR THE PERIOD ENDING: 31ST DECEMBER 2022
Cost Adjustments
Certificate No. | Description | Applied Amount (AED)
1 | Petty Cash Gifts to Arjun | -1208
2 | TXM Manpower cost adjustment from material transaction- August 22 | -9071.54
3 | TXM Manpower cost adjustment from material transaction- September 22 | -9384.76
4 | TXM Manpower cost adjustment from material transaction- October 22 | -9051.18
5 | TXM Manpower cost adjustment from material transaction- November 22 | -9951.73
6 | TXM Manpower cost adjustment from material transaction- November 22 | -1583.52
7 | TXM Manpower cost adjustment from material transaction- December 22 | -19197
8 | IT costs adjustment from Overhead transaction for June 22 | -10220
9 | IT costs adjustment from Overhead transaction July 22 | -11760
10 | IT costs adjustment from Overhead transaction August 22 | -12180
11 | IT costs adjustment from Overhead transaction September 22 | -14000
12 | Visa Cost of labours | -2797.41
13 | Visa Cost of labours | -1259.8
14 | Included VAT adjustment | -521.189
15
16
17
18
19
20
| TOTAL AMOUNT | -112186.129

## Com or's
APPLICATION FOR PAYMENT NO. 11
COMMITTED ORDERS
Certificate No. | Description | Total Amount (AED ) | Applied Amount (AED)
1 | Kone (LPO HM-201A22002/0002) - CTU use Lifts (2 Nos)- Dec. 22 | 160000 | 16000
2 | IT infra-strucure set up to Offices | 10000 | 10000
3 | Kone (LPO HM-201A22002/0048)- CTU use Lifts no 10 & 21 (2 Nos)- Dec 22 | 128000 | 16000
4 | Al Ihsan Building Materials Trading (LPO HM-201A22002/0056)- Balcony Tiles | 154032 | 30240
5 | Schirmer Safety Consultants (LPO HM-201A22002/0065)- Façade Inspection Services | 11500 | 11500
6 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0069)- Scissor Lift | 72900 | 72900
7 | High Glass Decor & Curtain Works LLC (LPO HM-201A22002/0080)- Turkish Acrylic carpet | 19435 | 19435
8 | Kone (LPO HM-201A22002/0086) - CTU Lifts (1 Nos)- for Oct 22 | 64000 | 16000
9 | Indigatech (LPO HM-201A22002/0095)- Fire rated Windows | 91817 | 64271.9
10 | New Era Construction (LPO HM-201A22002/00113)- Cobiax Permanent Formwork | 67371.21 | 51376.14
11 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0117)- Scissor Lift | 72900 | 72900
12 | Spider Access (LPO HM-201A22002/0130)- Column rectification & paint Mock up | 15300 | 0
13 | Carpet Land LLC (LPO HM-201A22002/0151) - Carpet | 13790 | 0
14 | Dutco LLC (LPO HM-201A22002/0155) - Modular Seal | 7600 | 0
15 | Master Builders Solutions LLC (LPO HM-201A22002/0159) - Emaco | 8400 | 0
16 | Jabel Ali Tra. LLC (LPO HM-201A22002/0161 ) -Dune Sand | 11110 | 2110.9
17 | Al Najar LLC (LPO HM-201A22002/0162 ) - DC Furniture | 4900 | 0
18 | Osler Access LLC (LPO HM-201A22002/0166 ) - Cradle Works | 12760 | 0
19 | Al Majid LLC (LPO HM-201A22002/0167 ) - GRP Tank | 6500 | 6500
20 | Inter Metal LLC (LPO HM-201A22002/0168 ) - DC Furniture | 5350 | 0
21 | Smart Office LLC (LPO HM-201A22002/169 ) - DC Furnitire | 9742 | 0
22 | Master Builders Solutions LLC (LPO HM-201A22002/0170) - Mater top | 18000 | 0
23 | Consent (LPO HM-201A22002/0172) - Tile & Coping | 166700 | 98422.2
24 | Momentum (LPO HM-201A22002/0179)- Ironmongery | 62299.3 | 32454.8 | Part cost booked.
25 | Indigatech (LPO HM-201A22002/0132)- Window Glass | 42920 | 42920
26 | Laidlow (LPO HM-201A22002/0176)- Ironmongery | 240812.4 | 88258
27 | Kone (LPO HM-201A22002/0138) - CTU Lifts (2 Nos)- for Dec 22 | 96000 | 16000
28 | Fluid Codes Testing- (LPO HM-201A22002/0149) | 28207 | 0
29 | AST Digital Print Centre (LPO HM-201A22002/0037)- Printer charges | 15000 | 3438.16 | Registered Invoice
30 | Golden Ready Mix LLC (LPO HM-201A22002/0023 R1)- Concrete supply | 587200 | 78601 | Registered Invoice
31 | High Class Decor & Curtains Works LLC ( HM-201A22002/0080 ) | 19435 | 9717.5 | Registered Invoice
32 | AHK Works- Alternatives SC's | 528371.34 | 83360
33 | Ostermeier- Supply of manhole covers ( HM-201A22002/0277) | 420090
34 | Hilti RE 500V4 ( HM-201A22002/0183) | 18900 | 0
35 | Mobility General- Ironmongery ( HM-201A22002/0185) | 150516 | 11129
36 | Osler- Cradle ( HM-201A22002/0188) | 137000 | 137000
37 | Momentum- Ironmongery ( HM-201A22002/0192) | 12202 | 11952
38 | Master Emaco ( HM-201A22002/0195) | 9000 | 2952
39 | Door Controls Glass Trading( HM-201A22002/0206) | 57018
40 | Osler- Cradle Maintenance ( HM-201A22002/0207) | 14928.57 | 11428.57
41 | Amalgam- Traffic Signs ( HM-201A22002/0210) | 3003 | 0
42 | Al Areej AC- Temp AC's ( HM-201A22002/0216) | 26500 | 0
43 | Mobility General- Ironmongery ( HM-201A22002/0222) | 13640 | 13640
44 | Schirmer- Façade Testing( HM-201A22002/0224) | 5000 | 5000
45 | Neotech Engineering ( HM-201A22002/0228) | 8518 | 0
46 | Neotech Engineering ( HM-201A22002/0229) | 2770 | 0
47 | Hilti RE 500V4 ( HM-201A22002/0231) | 31500 | 12600
48 | Styro polystyrene ( HM-201A22002/0234) | 6875 | 3079.99
49 | Arabuild Tiles ( HM-201A22002/0237) | 480000 | 358694.4
50 | Smart Office Furnitures ( HM-201A22002/0240) | 1439 | 0
51 | Doormax Ironmongery (HM-201A22002/0252) | 223860.28 | 99628.28
52 | Betec CAD Louvers (HM-201A22002/0267) | 90586.4 | 90586.4
53 | Mobility General Trading (HM-201A22002/0273) | 17100 | 17100
54 | Doormax Ironmongery (HM-201A22002/0280) | 13148 | 13148
55 | Styro Polystyrene (HM-201A22002/0281) | 46000 | 46000
56 | Carpets BSH Trading (HM-201A22002/0116) | 98548.1 | 78838.48
| TOTAL AMOUNT | 4541946.5 | 1676344.24

## K Summary
COINS - FINANCE
Contract Cost Breakdown 201A22002 Dorchester Hotel & Residences
Period December 2022
|  |  | Previous Cum | Current Month
Ledger | Current Period | Total to Date |  |  | Certified
Labour | 1636648.68 | 9268743.12 | 7632094.44 | -1636648.68 | 7628037.26 | -1640705.86
Payroll | 1441328.68 | 8141645.16 | 6700316.48 | -1441328.68 | 6696259.3
Manual Journal |  |  |  | 0
Purchase Orders |  |  |  | 0
Direct Invoices |  |  |  | 0
Petty Cash Charges |  | 1425 | 1425 | 0 | 1425
Subcontractor Costs | 195320 | 1125672.96 | 930352.96 | -195320 | 930352.96
Material | 1192972.53 | 7543705.52 | 6350732.99 | -1192972.53 | 6311690.05 | -1232015.47
Purchase Orders | 779756.87 | 4053367.39 | 3273610.52 | -779756.87
Stock Issues | 412781.1 | 3341555.36 | 2928774.26 | -412781.1
Manual Journals | 0 | 4371 | 4371 | 0
Petty Cash Charges | 434.56 | 11319.67 | 10885.11 | -434.56
Plant Charges |  | 132712.5 | 132712.5 | 0
Direct Invoices |  | 379.6 | 379.6 | 0
Plant | 455699.06 | 2756232.69 | 2300533.63 | -455699.06 | 2300533.63 | -455699.06
Plant Charges | 435644.54 | 2595987.52 | 2160342.98 | -435644.54
Manual Journals | 19654.52 | 152343.67 | 132689.15 | -19654.52
Petty Cash Charges |  |  |  | 0
Direct Invoices | 400 | 7901.5 | 7501.5 | -400
Subcontractor | 10010548.7601 | 54614577.957 | 44604029.1968 | -10010548.7601 | 41412331.2124 | -13202246.7446
Subcontract Costs | 10009348.7601 | 54606957.957 | 44597609.1968 | -10009348.7601 | 41405911.2124 | -13201046.7446
CVR Items |  | 0 | 0 | 0
Purchase Orders | 1200 | 7620 | 6420 | -1200 | 6420 | -1200
Direct Invoices | 0 | 0 | 0 | 0
Manual Journals |  |  |  | 0
Overhead | 99227.45 | 1122567.77 | 1023340.32 | -99227.45 | 973013.62 | -149554.15
CVR Items |  | 0 | 0 | 0
Purchase Orders | 38851.28 | 561147.05 | 522295.77 | -38851.28
Direct Invoices | 18810.67 | 108163.67 | 89353 | -18810.67
Petty Cash Charges | 3723.8 | 101697.69 | 97973.89 | -3723.8
Manual Journals | 17463.2 | 158411.45 | 140948.25 | -17463.2
Plant Charges | 1085 | 8827 | 7742 | -1085
Stock Issues | 19293.5 | 184320.91 | 165027.41 | -19293.5
Salaries | 1299435.18 | 9550718.14 | 8251282.96 | -1299435.18 | 8251283.44 | -1299434.7
Payroll Charges | 1299435.18 | 9548987.62 | 8249552.44 | -1299435.18 | 8249552.44
Manual Journals |  | 1730.52 | 1730.52 | 0 | 1731
Direct Invoices |  |  |  | 0
Commited Orders | -549012 | 1676344.24 | 2225356.19 | 549011.95
Commited Orders | -549012 | 1676344.24 | 2225356.19 | 549011.95 | 2225356.19 | 549011.95
0
0
Total | 14145519.6601 | 86532889.437 | 72387369.7268 | -14145519.7101 | 69102245.4024 | -17430644.0346
|  |  |  | -0.05 |  | -2178830.5043
-19609474.5389

## Labour
COINS - FINANCE
Labour Cost 201A22002 Dorchester Hotel & Residences
Period December 2022
Payroll
Cost Head | Description |  | Normal Hours | OT Hours | EOT Hours | Current | TTD
10100 | Unskilled labour costs - internal |  | 32859 | 3334.5 | 5048 | 386040.11 | 2085407.1
10200 | Skilled labour costs - internal |  | 22628 | 2378 | 4093 | 292071.18 | 1721938.69
10300 | Operators costs - internal |  | 5570 | 528.5 | 1353.5 | 96434.77 | 540172.84
10400 | Tradesmen costs - internal |  | 49626 | 5144.5 | 8295.5 | 633383.06 | 3603328.51
10500 | Charge hand labour costs - internal |  | 2272 | 252 | 461.5 | 33399.56 | 190798.02
Total |  |  | 112955 | 11637.5 | 19251.5 | 1441328.68 | 8141645.16
Manual Journals
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Purchase Orders
Commodity | Description |  |  | Invoiced | Accrual / Rev | Current | TTD
Total | [5 empty] | 0
Direct Invoices
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
Total
Petty Cash Charges
Cost Head | Description |  |  | Type | Int Ref | Current | TTD
10200 | Skilled labour costs - internal | [5 empty] | 1425
Total | [6 empty] | 1425
Subcontract Costs
Cost Head | Description |  |  | Int Ref | Ext Ref | Current | TTD
11400 | Tradesmen costs - external |  |  |  |  | 274405.83 | 1549453.37
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 178856 | 721691
721691
| BLUE008 | Blue Sky Middle East Contracting (LLC) |  |  |  | 57749.83 | 570174.41
570174.41
| FOCU003 | Focus Power Security Services (LLC) |  |  |  | 21000 | 161000
161000
| SERV004 | Service Plus Technical Services LLC |  |  |  | 16800 | 96587.96
96587.96
| ALQA002 | Al Qannati Electromechanical and Plumbing Co LLC |  |  |  | 274405.83 | 1549453.37
1549453.37
Total | [5 empty] | 274405.83 | 1549453.37
[6 empty] | 1715734.51 | 9691098.53

## Material
COINS - FINANCE
Material Cost 201A22002 Dorchester Hotel & Residences
Period December 2022
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
21110A01 | Reinforcement - Bars Mesh Bending Sched |  |  | 20193.92 | 20193.92 | 143322.22
| CICO001 | Cicon Building Materials |  | 20193.92 | 20193.92 | 143322.22
21110A02 | Reinforcing Sundries |  |  | 2250 | 2250 | 5040
| ALAB003 | Al Abbasi Fasteners and Hardware |  | 2250 | 2250 | 4750
| MODE002 | Modern Building Materials Trad |  |  | 0 | 290
21111A01 | Aggregates |  |  | 0 | 0 | 8999.1
| JABE002 | Jabel Ali General Transport En |  | 0 | 0 | 8999.1
21112A01 | Timber/Plywood/Nails |  | 9600 |  | 9600 | 56350
| ABUA004 | Abu Al Hassan Building Material Co. (ABCO) LLC - Foreign Direct Investment | 7500 |  | 7500 | 25500
| ACME001 | Acme Building Materials Trading LLC |  |  | 0 | 25850
| SRRB001 | SRR Building Material Trading LLC | 2100 |  | 2100 | 5000
22317A01 | Vehicle Plant and Spares |  | 56000 | 36000 | 92000 | 334933.64
| KONE001 | Kone Middle East LLC | 56000 | 36000 | 92000 | 334933.64
22711A01 | Consumable Tooling |  |  | 440 | 440 | 40335.62
| ALAB003 | Al Abbasi Fasteners and Hardware |  | 440 | 440 | 3915
| DUTI001 | Dutest Industrial Est |  |  | 0 | 600
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 700
| HILT001 | Hilti Emirates LLC |  | 0 | 0 | 28440.62
| NASE001 | Naser Al Sayer and Co LLC |  |  | 0 | 6680
23011A01 | Blockwork/Masonry/Mortar |  | 3221.6 | 6.4 | 3228 | 67804.4
| ARKA003 | Arkan Building Materials Co Arkan PJSC - Dubai Bramch | 2300 | -3680 | -1380 | 34270
| MAST005 | Master Builders Solutions Construction Chemicals LLC |  |  | 0 | 8400
| UNIM005 | Uni Mix Block Industry (LLC) | 921.6 | 3686.4 | 4608 | 25134.4
23011A02 | Blockwork Sundry Material |  | 1728 | 22356 | 24084 | 155779.4
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 1600
| CORE004 | Core Metallic Ind LLC |  |  | 0 | 23379
| HILT001 | Hilti Emirates LLC |  | 18900 | 18900 | 69300
| MODE002 | Modern Building Materials Trad |  |  | 0 | 720
| PALL001 | Palletco LLC |  |  | 0 | 26000
| UNIM005 | Uni Mix Block Industry (LLC) | 1728 | 3456 | 5184 | 34780.4
23011A03 | Concrete |  | 140512.5 | -126320 | 14192.5 | 175182.5
| GOLD026 | Golden Ready Mix LLC | 140512.5 | -126320 | 14192.5 | 175182.5
23011A04 | Concrete Sundries |  | 60280.01 | -18787 | 41493.01 | 177280.01
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 8600
| KING003 | Kingspan Insulation (LLC) |  | 0 | 0 | 12000
| MAPE001 | Mapei Construction Chemicals LLC | 460 | -460 | 0 | 460
| MAST005 | Master Builders Solutions Construction Chemicals LLC | 56025 | -18327 | 37698 | 152425
| STYR002 | Styro Insulation Materials Trading LLC | 3795.01 |  | 3795.01 | 3795.01
23011A05 | Plaster Screed Rush Coat |  | 15920 | -15920 | 0 | 36720
| CONM001 | Conmix Ltd | 15920 | -15920 | 0 | 36720
23011A06 | Plaster Sundries |  | 1920 | -1920 | 0 | 4317
| CONM001 | Conmix Ltd | 1920 | -1920 | 0 | 1920
| CORE004 | Core Metallic Ind LLC |  | 0 | 0 | 2397
23011A07 | Precast Concrete |  | 102249 | -50034 | 52215 | 145514
| ALSE002 | Al Serkal and Assarain Concret | 93299 | -50034 | 43265 | 136564
| CONS001 | Consent LLC | 8950 |  | 8950 | 8950
23012A01 | Road Base |  | 30781.8 | -26367.6 | 4414.2 | 30781.8
| JABE002 | Jabel Ali General Transport En | 30781.8 | -26367.6 | 4414.2 | 30781.8
23016A01 | Tiling Material |  | 208230.08 | -140503.38 | 67726.7 | 422215.9
| ALIH002 | Al Ihsan Building Materials Trading |  | 0 | 0 | 123792
| ARAB017 | Arabuild LLC | 121305.6 | -121305.6 | 0 | 132285.6
| CONS001 | Consent LLC | 86556.48 | -19749.78 | 66806.7 | 164850.3
| MAPE001 | Mapei Construction Chemicals LLC | 368 | 552 | 920 | 1288
23019A01 | Formwork/Falsework |  |  |  | 0 | 22306.58
| ALQU003 | Al Quebeisi SGB LLC |  |  | 0 | 111.51
| FISC002 | Fischer Fixing LLC |  |  | 0 | 2700
| NEXT004 | Next Era Construction Materials Trading One Person Company LLC |  |  | 0 | 15995.07
| TRAD004 | Tradex LLC |  |  | 0 | 3500
23121A01 | Painting & Decorating Materials/Sealants |  |  | 0 | 0 | 10053
| DUTC004 | Dutco Tennant LLC |  |  | 0 | 7600
| QCON001 | Q Con General Trading LLC |  | 0 | 0 | 2453
23123A01 | Ironmongery |  | 220998.4 | 52754.9 | 273753.3 | 896000.32
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 1570
| DOOR001 | Doormax Building Material Trading (LLC) |  | 124232 | 124232 | 124232
| FINE001 | Fine Tools Trading LLC |  |  | 0 | 840
| LAID001 | Laidlaw Gulf LLC | 152554.4 | -141742.1 | 10812.3 | 426715.34
| MOBI002 | Mobility General Trading LLC |  | 133034 | 133034 | 139387
| MOME001 | Momentum Fireguard LLC | 62244 | -62769 | -525 | 197055.98
| QUAL010 | Quality Metal Works Manufacturing LLC | 6200 |  | 6200 | 6200
23912A02 | Electrical Items |  |  |  | 0 | 16635
| ALBA003 | Al Bajaa Lighting Equipment Trading LLC |  |  | 0 | 6835
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 9800
24713A01 | Cleaning Materials |  |  | 0 | 0 | 600
| ALBA009 | Al Bariq Equipment LLC |  | 0 | 0 | 600
29901A02 | Other Consumables |  | 2016 | 17771.25 | 19787.25 | 176128.53
| ALAB003 | Al Abbasi Fasteners and Hardware |  | 17771.25 | 17771.25 | 134799.53
| ALBA009 | Al Bariq Equipment LLC |  | 0 | 0 | 1700
| ALSH004 | Al Sham Star Trading LLC |  |  | 0 | 945
| ASCE001 | Ascend Access System Scaffoldi |  |  | 0 | 17582
| CHEM001 | Chemex Hygiene Concepts LLC |  |  | 0 | 4642.5
| CRES002 | Crescent Scaffolding Industrie |  |  | 0 | 6600
| FAIS001 | Faisal Ali Juma Trading LLC |  |  | 0 | 5903.5
| HEPW001 | Corys Piping Systems LLC | 2016 |  | 2016 | 2016
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 1940
41540A01 | External Works through LPO's |  | 79676.39 | 74702.6 | 154378.99 | 1127068.37
| ALNA007 | Al Najah Furnishings LLC | 4900 |  | 4900 | 4900
| BSHT001 | BSH Trading (LLC) |  | 98548.1 | 98548.1 | 98548.1
| CARP001 | Carpet Land LLC |  |  | 0 | 13790
| CULL001 | Culligan International Emirate |  |  | 0 | 218423.22
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 5550
| FLUI002 | Fluid Codes DMCC | 28207 | -14103.5 | 14103.5 | 28207
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 1225
| INDI003 | Indiga Tech Trading (LLC) |  | 0 | 0 | 40421.1
| INTE009 | Intermetal (LLC) Dubai Br |  | 0 | 0 | 7350
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 1248.54
| NATI010 | National Services for Carpet a |  |  | 0 | 2686.2
| OSLE001 | Osler Access Equipment LLC | 16260 |  | 16260 | 616260.09
| OSTE001 | Ostermeier FZE |  |  | 0 | 13357
| SCHI004 | Schirmer Safety Consultants |  |  | 0 | 5750
| SMAR015 | Smart Space Office Furniture Trading | 11112.39 | -9742 | 1370.39 | 11112.39
| TXML001 | TXM Labour Supply LLC | 19197 |  | 19197 | 58239.73
Total |  |  | 933133.78 | -153376.91 | 779756.87 | 4053367.39
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
21112 | Wood Products |  |  |  |  | 38201.65
| 11121609-A03989 | Plywood - Film Faced - 18Mm - Fsc - Popalr Core |  |  |  | 38201.65
21510 | Fuels |  |  |  | 400706.1 | 3106598.36
| 15101501-A18400 | Fuel - Petrol |  |  |  | 1234.12
| 15101501-A18401 | Fuel - Diesel | ISS |  | 400706.1 | 3105364.24
22210 | Heavy construction machinery and equipment |  |  |  | 5184 | 44784
| 22101701-A04048 | Floor Protection Sheet Polypro Corrugated 4Mm |  |  | 5184 | 44784
22711 | Hand tools |  |  |  | 4440 | 113522
| 22711H02-010001 | Floor Cleaning Machine |  |  | 4440 | 4440
| 27112702-A20393 | Angle Grinder |  |  |  | 27722
| 27112702-A20412 | Concrete Mixer |  |  |  | 2350
| 27112702-A20424 | Drill |  |  |  | 9510
| 27112702-A20504 | Stepdown Transformer |  |  |  | 34875
| 27112702-A20516 | Vacuum Cleaner |  |  |  | 11125
| 27112702-A20520 | Wall Chasing Machine |  |  |  | 23500
24325 | Project IT Infrastructure |  |  |  |  | 2796
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 2598
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 198
| 24325V01-020001 | Firewall SonicWall TZ400 - Used |  |  |  | 0
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 24325V01-020007 | Wireless Router D-Link 4G - Used |  |  |  | 0
24618 | Personal safety and protection |  |  |  | 1615.96 | 12478.71
| 46181507-A04452 | Safety Vest 90 Gsm Florescent Green - Large (Rigger) |  |  |  | 102.93
| 46181507-A04459 | Safety Vest 90 Gsm M Green - Staff Vest - 2XL |  |  |  | 105.56
| 46181507-A04460 | Safety Vest 90 Gsm M Green - 2Xl |  |  |  | 387.51
| 46181507-A04461 | Safety Vest 90 Gsm M Green - Staff Vest - 3XL |  |  |  | 9
| 46181507-A04462 | Safety Vest 90 Gsm M Green - Large |  |  |  | 917.89
| 46181507-A04463 | Safety Vest 90 Gsm M Green - Staff Vest - M |  |  | 75.25 | 226.47
| 46181507-A04464 | Safety Vest 90 Gsm M Green - Staff Vest - L | ISS |  | 90 | 316.66
| 46181507-A04465 | Safety Vest 90 Gsm M Green - Medium |  |  |  | 595.69
| 46181507-A04466 | Safety Vest 90 Gsm M Green - Staff Vest - XL |  |  | 45.07 | 364.27
| 46181507-A04467 | Safety Vest 90 Gsm M Green - Xl |  |  |  | 794.02
| 46181507-A20681 | Traffic Marshall Safety Jacket Size- XL |  |  |  | 75
| 46181507-A20695 | Rigger Safety Jacket Size - XL |  |  |  | 37.5
| 46181507-A20696 | Rigger Safety Jacket Size - 2XL |  |  |  | 37.5
| 46181701-A04400 | Safety Helmet For Staff Mk7 | ISS |  | 1120 | 3325
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  | 273 | 4667
| 46181701-A04404 | Safety Helmet High Ev Red - 6 Point Textile Tapes System. Slip Ratchet T |  |  | 12.64 | 456.71
| 46181701-A20074 | Safety Helmet High Ev Green - 6 Point Textile Tapes System. Slip Ratchet |  |  |  | 60
25213 | Window treatments |  |  |  |  | 13724.91
| 52131602-A18941 | Shade Net - 100% new HDPE with UV protection - 285 GSM - 3.66X100Mtr - |  |  |  | 13724.91
25310 | Clothing |  |  |  | 835.04 | 7604.31
| 53101602-A04981 | Shirt Cotton Full Sleeve White - 2Xl |  |  |  | 380.04
| 53101602-A04984 | Shirt Cotton Full Sleeve White - Large | ISS |  | 192 | 816
| 53101602-A04985 | Shirt Cotton Full Sleeve White - Medium |  |  | 96 | 720
| 53101602-A04986 | Shirt Cotton Full Sleeve White - Small |  |  |  | 1132.71
| 53101602-A04987 | Shirt Cotton Full Sleeve White - Xl |  |  | 235.06 | 376.09
| 53101602-A04988 | Shirt Formal Half Sleeve White - 2Xl |  |  |  | 105.56
| 53101602-A04989 | Shirt Formal Half Sleeve White - 3Xl |  |  |  | 360
| 53101602-A04991 | Shirt Formal Half Sleeve White - Large |  |  |  | 298.42
| 53101602-A04992 | Shirt Formal Half Sleeve White - Medium |  |  |  | 106.7
| 53101602-A04993 | Shirt Formal Half Sleeve White - Small |  |  |  | 120.71
| 53101602-A04994 | Shirt Formal Half Sleeve White - Xl |  |  |  | 383.29
| 53103001-A05701 | T-Shirt 220 Gsm Half Sleeve White - 2Xl |  |  |  | 257.29
| 53103001-A05702 | T-Shirt 220 Gsm Half Sleeve White - 3Xl |  |  |  | 52
| 53103001-A05704 | T-Shirt 220 Gsm Half Sleeve White - Large |  |  |  | 208
| 53103001-A05705 | T-Shirt 220 Gsm Half Sleeve White - Medium | ISS |  | 234 | 1326
| 53103001-A05706 | T-Shirt 220 Gsm Half Sleeve White - Small |  |  |  | 312
| 53103001-A05707 | T-Shirt 220 Gsm Half Sleeve White - Xl | ISS |  | 77.98 | 649.5
60905 | Computers & Accessories |  |  |  |  | 1845.42
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New |  |  |  | 125
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 55
| 60905V01-010032 | Microsoft Display Adapter 1080p - New |  |  |  | 330
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 652.42
| 60905V01-010043 | Laptop Bag HP - New |  |  |  | 198
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 485
Total |  |  |  |  | 412781.1 | 3341555.36
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
29910 | Internal division - material costs |  |  |  |  | 4371
29951 | Materials cost accruals - CVR |  |  |  |  | 0
|  | CVR Item Cost Code Manual Accruals Material | JCV | 154896 | -438614
Total | [5 empty] | 4371
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
23116 | Hardware |  |  |  | 434.56 | 11319.67
|  | 27743-CHRIS McCANN-201A22002 | PCP | DEC/11613/07 | 359.56
|  | 27743-CHRIS McCANN-P CASH RETURNED | RDC | 19531 | 75
Total |  |  |  |  | 434.56 | 11319.67
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
22711 | Hand tools |  |  |  |  | 2850
| 27112217-A19363 | LT 53/2-Block Cutter |  |  |  | 2850
24619 | Fire protection |  |  |  |  | 2040
| PTLT150045 | PTLT150045 Building Dryer Machine |  |  |  | 150
| PTLT150092 | PTLT150092 Ventilation Fan 18" |  |  |  | 315
| PTLT150097 | PTLT150097 Ventilation Fan 18" |  |  |  | 315
| PTLT150113 | PTLT150113 Ventilation Fan 18" |  |  |  | 315
| PTLT150142 | PTLT150142 Ventilation Fan 18" |  |  |  | 315
| PTLT150143 | PTLT150143 Ventilation Fan 18" |  |  |  | 315
| PTLT150144 | PTLT150144 Ventilation Fan 18" |  |  |  | 315
29900 | EHD Materials |  |  |  |  | 127822.5
| 99000101-A18468 | Pedestrian Barrier Steel Branded (2.5 x 1.2mtr) |  |  |  | 41000
| 99000201-A18478 | Metal Hordings (2.2 x 2 mtr) K standard |  |  |  | 5775
| 99000601-A18491 | TYPE 1 - 3 Cooler Stand |  |  |  | 8612.5
| 99000701-A18494 | Cable Management Stand |  |  |  | 14625
| 99000701-A18496 | Cable Management Hooks-double hooks ( type 2) |  |  |  | 3375
| 99000701-A18497 | Cable Management Hooks three hooks ( type 3) |  |  |  | 1600
| 99000901-A18510 | Man Basket |  |  |  | 7575
| 99001001-A18505 | Concrete Bucket - 1m3 |  |  |  | 960
| 99001001-A18669 | 1.5 CBM (3T) Self Dumping Skip |  |  |  | 5500
| 99001101-A18509 | Tripod |  |  |  | 2800
| 99001201-A18840 | EHD Security Cabin |  |  |  | 2600
| 99001401-A18842 | EHD Gas Monitor |  |  |  | 5400
| 99001601-A19775 | Large Industrial Evaporative Outdoor Air Cooler |  |  |  | 28000
Total | [5 empty] | 132712.5
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
21510 | Fuels |  |  |  |  | 379.6
| ALFU013 | Al Futtaim Transport and Renta |  |  |  | 379.6
Total | [5 empty] | 379.6
[5 empty] | 1192972.53 | 7543705.52

## Plant
COINS - FINANCE
Plant Cost 201A22002 Dorchester Hotel & Residences
Period December 2022
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
30010 | I-Earth moving machinery |  |  |  | 9792.69 | 68474.53
| 2210150902 | Backhoe Loader (3CX) With Operator-Working |  |  |  | 4147
| 2210152614 | Mini Excavator 3 Ton with Breaker-Working |  |  |  | 3960
| P000220111 | P000220111 Case Sr150 Skid Steer Loader |  |  |  | 560.77
| P000220115 | P000220115 Case Sr150 Skid Steer Loader |  |  |  | 93.46
| P000220119 | P000220119 Case Sr150 Skid Steer Loader |  |  |  | 2710.39
| P000220120 | P000220120 Case Sr200 Skid Steer Loader |  |  | 3946.15 | 27915.38
| P000220123 | P000220123 Case Sr150 Skid Steer Loader |  |  | 2523.46 | 12243.46
| P000500132 | P000500132 Bomag Plate Compactor Bpr25/50 |  |  | 1938.46 | 9484.61
| P000500133 | P000500133 Bomag Plate Compactor Bpr25/50 |  |  | -69.23 | 553.85
| P000610012 | P000610012 Sb Hopper Broom Attachment |  |  | 1453.85 | 3392.31
| P000610041 | P000610041 Hydraulic Breaker CB 37S for Skid Steer Loader |  |  |  | 3413.3
30020 | I-Aerial lifts |  |  |  | 23100 | 30525
| 2210180513 | Spider Lift - 26 Mtr (X26J) with Sky Guard-Working |  |  | 23100 | 30525
30030 | I-Building construction machinery and accessories |  |  |  | 27940 | 162682.48
| KSFT000027 | KSFT000027 Diesel Storage Tank 1800 Ltrs(Original) |  |  |  | 138.48
| P000090078 | P000090078 Diesel Tanker- Dorchester Hotel & Residences (Completion Works) Scania Fuel Tanker |  |  |  | 1044
| P000490100 | P000490100 Livers Hf 4Kva Converter |  |  | 1093.5 | 8667
| W000020068 | W000020068 Diesel Tanker 9/68 Mercedes Fuel Tanker - DXB64273 |  |  | 1566 | 8874
| W000020069 | W000020069 Diesel Tanker - 9/69 - Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB63219 |  |  |  | 41238
| W000020070 | W000020070 9/70 Diesel Tanker Dorchester Hotel & Residences (Completion Works) Mercedes Fuel Tanker - DXB65028 |  |  | 14094 | 84564
| W000020071 | W000020071 Mercdes Water Tanker - DXB64272 |  |  | 4167 | 6945
| W000020072 | W000020072 9/72 Sweet Water Tanker 1-Trip Mercdes Water Tanker - DXB62723 |  |  | 6482 | 10674.5
| W000020073 | W000020073 9/73 Sweet Water Tanker 1-Trip Mercedes Water Tanker-DXB62979 |  |  | 537.5 | 537.5
30100 | I-Lifting equipment and accessories |  |  |  | 160101.97 | 1002759.97
| 2410160302 | Forklift - 5 Ton With Operator-Working |  |  |  | 19580
| 2410160315 | Forklift 3 Ton With Long Fork-Working |  |  | 20985.14 | 96463.95
| 2410160402 | Mast Climber-Working |  |  | 27923.42 | 29615.75
| 2410161727 | Power Tower Duo - 5.1 Mtr-Working |  |  | 1658.9 | 5035.94
| 2410162303 | Derrick Crane |  |  | 26061.74 | 375143.85
| 2410162304 | Derrick Crane - 12 Ton |  |  | 32788.88 | 185097.11
| 2410162402 | Mobile Crane - 50 Ton-Working |  |  |  | 2640
| 2410162404 | Mobile Crane - 70 Ton With Fly Jib & Skidding |  |  | 21450 | 21450
| 2410162405 | Mobile Crane - 100 Ton-Working |  |  |  | 6600
| 2410162414 | Mini Crane (JEKKO SPX532) - 3.2 Ton With Operator-Working |  |  | 8250.55 | 47337.29
| 2410162415 | Jekko Mini Picker-1000kg-Working |  |  | 7615.41 | 7615.41
| MOB001 | Calculation For Special Bracket with 3rd Party Approval |  |  | 660 | 123090
| P000250049 | P000250049 Liebherr Mobile Crane-55 Ton(1055-32) |  |  |  | 1246.15
| P000260029 | P000260029 Skyjack 8841Rt Scissor Lift |  |  |  | 211.54
| P000260049 | P000260049 Scissor Lift Electric- 8m |  |  | 2200 | 14718.9
| P000260050 | P000260050 Scissor Lift - 8m |  |  | 2284.74 | 5161.82
| P000260081 | P000260081 Scissor Lift Electric- 8m |  |  | 2284.74 | 15654.7
| P000260082 | P000260082 Scissor Lift Electric- 8m |  |  | 2200 | 14284.93
| P000260087 | P000260087 Nano Lift 4.5 Meter |  |  | 1246.15 | 8123.07
| P000260088 | P000260088 Nano Lift 4.5 Meter |  |  | 1246.15 | 7430.76
| P000260092 | P000260092 Nano Lift 4.5 Meter |  |  | 1246.15 | 7892.3
| W000180014 | W000180014 TCM Forklift - DXB 41076-Working |  |  |  | 8366.5
30110 | I-Passenger motor vehicles |  |  |  | 50498.87 | 335299.65
| 2510150704 | Pick Up - 3 Ton Double CabinWithout Driver-Working |  |  | 5330.87 | 42646.96
| 2510150705 | Recovery Vehicle 3 Ton |  |  |  | 3190
| P000080661 | P000080661 Ashok Leyland Bus - Dxb 36303H |  |  |  | 1512
| P000080664 | P000080664 Ashok Leyland Bus - Dxb 52753J |  |  | 3360 | 23394
| P000080666 | P000080666 Ashok Leyland Bus - Dxb 53795I |  |  |  | 168
| P000080681 | P000080681 Ashok Leyland Bus - DXB 86848H |  |  | 5110 | 29176
| P000080682 | P000080682 Ashok Leyland Bus - DXB 87476H |  |  |  | 840
| P000080683 | P000080683 Ashok Leyland Bus - DXB 15614M |  |  |  | 1176
| P000080685 | P000080685 Ashok Leyland Bus - DXB 86783H With IVMS |  |  | 5110 | 20034
| P000080686 | P000080686 Ashok Leyland Bus - DXB 15496M |  |  | 1848 | 1848
| P000080687 | P000080687 Ashok Leyland Bus - DXB 85148H |  |  | 5110 | 37982
| P000080690 | P000080690 Ashok Leyland Bus - DXB 15611M |  |  | 5110 | 40768
| P000080692 | P000080692 Ashok Leyland 59 Seat Bus-DXB 72359 W |  |  |  | 184.44
| P000080696 | P000080696 Ashok Leyland 59 Seat Bus-DXB 72353 W |  |  | 5610 | 26974.11
| P000080701 | P000080701 Ashok Leyland 71 Seat Bus |  |  | 5850 | 39331.23
| TA00033109 | TA00033109 TOYOTA COASTER HI ROOF 23STR 4.0D MANUAL |  |  | 4680 | 39747.95
| TA00043000 | TA00043000 TOYOTA HIACE 13 SEAT BUS |  |  | 3380 | 26326.96
30120 | I-Product and material transport vehicles |  |  |  |  | 16019.78
| P000320042 | P000320042 Thwaites Dumper - P 22157 |  |  |  | 16019.78
30130 | I-Specialized and recreational vehicles |  |  |  | 28589.64 | 171178.44
| P000100022 | P000100022 Nissan Truck With Hiab Crane With IVMS |  |  |  | 1540
| P000100023 | P000100023 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000100025 | P000100025 Mercedes Truck With Crane With IVMS |  |  |  | 2480
| P000120019 | P000120019 12/19 Skip Truck 1-Trip ( 59254 ) Isuzu 12Ton Truck - Dxb 83254O |  |  | 10374 | 60562
| P000120020 | P000120020 1 Trip 12/20 Skip Truck ( 59844 ) Hino 13.5 Ton Skip Truck |  |  | 1911 | 13386
| W000030018 | W000030018 Nissan Truck with Hiab Crane With IVMS |  |  | 3473.64 | 6023.44
| W000030020 | W000030020 Nissan Truck with Hiab Crane With IVMS |  |  |  | 3080
| W000050017 | W000050017 12/17 Skip Truck 1-Trip ( 59984 ) Isuzu with Hiab Skip Loader - Dxb 70086 D |  |  | 12831 | 81627
30140 | I-Truck tractors |  |  |  |  | 4020
| W000070021 | W000070021 MAN Tractor Unit - DXB 66748 |  |  |  | 2010
| W000070022 | W000070022 MAN Tractor Unit - DXB 66768 |  |  |  | 2010
30160 | I-Product and material trailers |  |  |  |  | 1280
| W000320035 | W000320035 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
| W000320037 | W000320037 Flat Bed Semi Trailer - 55Ton |  |  |  | 640
30170 | I-Power generators |  |  |  | 113250.41 | 653785.43
| 2611160108 | Generator - 350 KVA-Working |  |  |  | 17769.86
| 2611160109 | Generator - 500 KVA-Working |  |  | 39634.78 | 192024.84
| 2611160110 | Generator - 650 KVA-Working |  |  | 73615.63 | 443990.73
30230 | I-Compressors |  |  |  |  | 11894.43
| P000330091 | P000330091 Atlas Copco Air Compressor |  |  |  | 11682.9
| PTLT250022 | PTLT250022 Electric Compressor |  |  |  | 211.53
30510 | I-Plant repair & maintenance |  |  |  | 22370.96 | 138067.81
| K000010027 | K000010027 Eco Cabin Type 1 - Ablution |  |  | -416.7 | 6292.17
| KA00010006 | KA00010006 Eco Cabin Type 1 - Ablution-Holiday |  |  | -416.7 | 7625.61
| KVS0010004 | KVS0010004 CAT & Ginny Cable Locator M/Kit |  |  | 486 | 3474
| PTLT260006 | PTLT260006 Floor Polishing Machine |  |  | 4440 | 4440
| PTLT530006 | PTLT530006 Block Cutter |  |  | 2850 | 2850
| S3131298 | S3131298-Fuel RFID Tag Installation |  |  |  | 161
| S3131331 | S3131331-Fuel RFID Tag Installation |  |  |  | 322
| S3131479 | S3131479-Fuel RFID Tag Installation / Metal Jerry Can |  |  |  | 472
| S3131494 | S3131494-Third party inspection & Certification |  |  |  | 100
| S3131597 | S3131597-PAT Test |  |  |  | 1850
| S3131609 | S3131609-Fabrication of Steel Ramp Dorchester Hotel |  |  |  | 7374
| S3131631 | S3131631-Electrical Repairs |  |  |  | 500
| S3131666 | S3131666-Dorchester Hotel -Third party inspection & Certification |  |  |  | 770
| S3131668 | S3131668-Electrical Repairs |  |  |  | 400
| S3131730 | S3131730-Electrical Repairs |  |  |  | 25
| S3131828 | S3131828-Electrical Repairs |  |  |  | 2225
| S3131868 | S3131868-DORCHESTER Hotel - Third party inspection & Certification |  |  |  | 860
| S3131933 | S3131933-Fuel RFID Tag Installation |  |  |  | 161
| S3131942 | S3131942-Electrical Repairs |  |  |  | 1431.19
| S3131975 | S3131975-PAT Test and Plugs |  |  |  | 1020
| S3132009 | S3132009-PAT Test |  |  |  | 350
| S3132054 | S3132054-Electrical Repairs |  |  |  | 1255.29
| S3132108 | S3132108-DORCHESTER Hotel- Water pump Replaced |  |  |  | 581
| S3132186 | S3132186-Electrical Repairs |  |  |  | 2619.96
| S3132199 | S3132199-DORCHESTER HOTEL Third party inspection & Certification |  |  |  | 200
| S3132235 | S3132235-Fuel RFID Tag Installation |  |  |  | 161
| S3132242 | S3132242-Electrical Repairs |  |  |  | 1694.02
| S3132281 | S3132281-Electrical Repairs |  |  |  | 175
| S3132299 | S3132299-DORCHESTER Hotel- Beam Cutting |  |  |  | 5510
| S3132316 | S3132316-Electrical Repairs |  |  |  | 666.32
| S3132327 | S3132327-Electrical Repairs |  |  |  | 1082.53
| S3132436 | S3132436-DORCHESTER Hotel Third party inspection & Certification |  |  |  | 2100
| S3132513 | S3132513-Refurbishment of KA1/6 & KA1/27 Ablution units |  |  |  | 418.8
| S3132579 | S3132579-Electrical Repairs |  |  |  | 1569.31
| S3132712 | S3132712-Electrical Repairs |  |  |  | 421
| S3132715 | S3132715-Electrical Repairs |  |  |  | 183.1
| S3132769 | S3132769-Electrical Repairs |  |  |  | 286.67
| S3132770 | S3132770-Electrical Repairs |  |  |  | 504.57
| S3132873 | S3132873-Electrical Repairs |  |  |  | 199.97
| S3132874 | S3132874-Electrical Repairs |  |  |  | 269.22
| S3132898 | S3132898-Electrical Repairs |  |  |  | 400
| S3132899 | S3132899-Electrical Repairs |  |  |  | 504.57
| S3132900 | S3132900-Electrical Repairs |  |  |  | 1158.48
| S3132901 | S3132901-Electrical Repairs |  |  |  | 1169.59
| S3132903 | S3132903-Electrical Repairs |  |  |  | 1189.12
| S3133002 | S3133002-Signboard Cutting Remove |  |  |  | 640.67
| S3133036 | S3133036-Electrical Repairs |  |  |  | 30.6
| S3133037 | S3133037-Electrical Repairs |  |  |  | 357
| S3133131 | S3133131-Electrical Repairs |  |  |  | 131.81
| S3133139 | S3133139-Electrical Repairs |  |  |  | 400
| S3133140 | S3133140-Electrical Repairs |  |  |  | 268.05
| S3133143 | S3133143-Electrical Repairs |  |  |  | 1346.55
| S3133145 | S3133145-Electrical Repairs |  |  |  | 836.5
| S3133262 | S3133262-Electrical Repairs |  |  |  | 400
| S3133263 | S3133263-Electrical Repairs |  |  |  | 434.9
| S3133265 | S3133265-Electrical Repairs |  |  |  | 354.19
| S3133266 | S3133266-Electrical Repairs |  |  |  | 1293.47
| S3133267 | S3133267-Electrical Repairs |  |  |  | 566.71
| S3133473 | S3133473-Electrical Repairs |  |  |  | 172
| S3133475 | S3133475-Electrical Repairs |  |  |  | 162
| S3133481 | S3133481-Electrical Repairs |  |  |  | 822.69
| S3133483 | S3133483-Electrical Repairs |  |  |  | 362.82
| S3133486 | S3133486-Electrical Repairs |  |  |  | 196
| S3133536 | S3133536-Electrical Repairs |  |  |  | 393.04
| S3133537 | S3133537-Electrical Repairs |  |  |  | 180.55
| S3133538 | S3133538-Electrical Repairs |  |  |  | 530.48
| S3133539 | S3133539-Electrical Repairs |  |  |  | 1486.78
| S3133581 | S3133581-Electrical Repairs |  |  |  | 155
| S3133592 | S3133592-Electrical Repairs |  |  | 100 | 100
| S3133645 | S3133645-Electrical Repairs |  |  | 62.53 | 62.53
| S3133646 | S3133646-Electrical Repairs |  |  |  | 400
| S3133685 | S3133685-Fuel RFID Tag Installation |  |  |  | 161
| S3133755 | S3133755-Electrical Repairs |  |  |  | 50
| S3133756 | S3133756-Electrical Repairs |  |  |  | 65
| S3133757 | S3133757-Electrical Repairs |  |  |  | 325
| S3133780 | S3133780-Light Tool Repair |  |  | 655.63 | 655.63
| S3133781 | S3133781-Light Tool Repair |  |  | 643.47 | 643.47
| S3133782 | S3133782-Light Tool Repair |  |  |  | 295.49
| S3133827 | S3133827-Electrical Repairs |  |  |  | 65
| S3133858 | S3133858-Light Tool Repair |  |  |  | 55
| S3133859 | S3133859-Light Tool Repair |  |  |  | 55
| S3133911 | S3133911-Light Tool Repair |  |  |  | 320
| S3133976 | S3133976-Light Tool Repair |  |  |  | 2095.73
| S3133979 | S3133979-Light Tool Repair |  |  |  | 172.85
| S3134028 | S3134028-Light Tool Repair |  |  |  | 269.31
| S3134029 | S3134029-Light Tool Repair |  |  |  | 201
| S3134116 | S3134116-Light Tool Repair |  |  | 467.97 | 467.97
| S3134136 | S3134136-Light Tool Repair |  |  |  | 177.38
| S3134137 | S3134137-Light Tool Repair |  |  |  | 177.38
| S3134138 | S3134138-Light Tool Repair |  |  |  | 177.38
| S3134139 | S3134139-Light Tool Repair |  |  |  | 177.38
| S3134177 | S3134177-Fuel RFID Tag Installation |  |  | 161 | 161
| S3134245 | S3134245-Fuel RFID Tag Installation |  |  | 161 | 161
| S3134278 | S3134278-Light Tool Repair |  |  | 174.2 | 174.2
| S3134352 | S3134352-Fuel RFID Tag Installation |  |  | 161 | 161
| S3134368 | S3134368-Supply of Safety Net |  |  |  | 800
| S3134492 | S3134492-Gas Cutting Work |  |  | 2185 | 2185
| S3134653 | S3134653-Light Tool Repair / Pat Test |  |  | 5625 | 5625
| S3134654 | S3134654-Light Tool Repair / Pat Test |  |  | 1140 | 1140
| S3304180 | S3304180-Ac Service & Repair |  |  |  | 5580
| S3304218 | S3304218-Additional Paint Requirement for the New Project - Dorchester |  |  |  | 946
| S3304220 | S3304220-Ac Repairs & Service |  |  |  | 4490
| S3304230 | S3304230-Ac Repair & Service - Client Room |  |  |  | 2220
| S3304236 | S3304236-Third Party Certificate for Concrete Bucket (KCB010) |  |  |  | 50
| S3304239 | S3304239-Ac Repairs & Service |  |  |  | 4400
| S3304272 | S3304272-Ac Repair & Service (Non KCE Asset) |  |  |  | 1830
| S3304302 | S3304302-Ac Repairs & Service (Non KCE Asset) |  |  |  | 1980
| S3304317 | S3304317-Replacement of Asian Ablution ? Bottom and Top (KA1/27) |  |  |  | 834.25
| S3304379 | S3304379-Ac Repairs & Service for client office & KCE office |  |  |  | 1120
| S3304387 | S3304387-AC Repair & Service for client office & KCE office |  |  | 2490 | 2490
| S3304411 | S3304411-AC Repair & Service for Site office. |  |  |  | 8280
| S3304437 | S3304437-Inspection & Servicing of Fire Extinguishers |  |  |  | 6000
| S3304536 | S3304536-Forklift Charges - Material Offloading |  |  |  | 65
| S3304579 | S3304579-Forklift Charges |  |  |  | 65
| S3304589 | S3304589-Forklift Charge |  |  |  | 65
| S3304597 | S3304597-Forklift Charge |  |  |  | 65
| S3304601 | S3304601-Forklift Charge |  |  |  | 65
| S3304666 | S3304666-Cubicle Door Locks |  |  | 424.08 | 424.08
| S3304667 | S3304667-Urinal Push Tap Leak Rectification |  |  | 977.48 | 977.48
Total |  |  |  |  | 435644.54 | 2595987.52
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
30295 | I-Waste skip |  |  |  | 16319.92 | 131200.67
|  | Mixed Waste-December 2022 | JNL | 156613 | 2670
|  | Mixed Waste-December 2022 | JNL | 156613 | 5890
|  | Demolition Waste-December 2022 | JNL | 156613 | 730
|  | Demolition Waste-December 2022 | JNL | 156613 | 6710
|  | Concrete Waste-December 2022 | JNL | 156613 | 265.92
|  | Concrete Waste-December 2022 | JNL | 156613 | 54
30951 | Plant cost accruals - CVR |  |  |  |  | 0
34110 | E-Passenger motor vehicles |  |  |  | 2096 | 12568
|  | P000080664-KCE Salik Month Of December 2022 | JNL | 156738 | 112
|  | P000080687-KCE Salik Month Of December 2022 | JNL | 156738 | 352
|  | P000080685-KCE Salik Month Of December 2022 | JNL | 156738 | 328
|  | P000080686-KCE Salik Month Of December 2022 | JNL | 156738 | 80
|  | P000080690-KCE Salik Month Of December 2022 | JNL | 156738 | 240
|  | P000080681-KCE Salik Month Of December 2022 | JNL | 156738 | 308
|  | P000080696-KCE Salik Month Of December 2022 | JNL | 156738 | 308
|  | P000080701-KCE Salik Month Of December 2022 | JNL | 156738 | 368
34120 | E-Product and material transport vehicles |  |  |  | 1238.6 | 8575
|  | W000020072-KCE Salik Month Of December 2022 | JNL | 156738 | 176
|  | TA00033109-Salik For November 2022 | JNL | 155828 | 655.2
|  | TA00043000-Salik For November 2022 | JNL | 155828 | 407.4
Total |  |  |  |  | 19654.52 | 152343.67
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
Total
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
30100 | I-Lifting equipment and accessories |  |  |  | 400 | 400
| KCEE004 | KCE (LLC) - Equipment Hire Div |  |  | 400 | 400
|  | FORKLIFT MOBILIZATION CHGS FROM JEBEL ALI YARD TO DORCHESTER PROJECT | PINN | 2212PL002263 | 400
34120 | E-Product and material transport vehicles |  |  |  |  | 7501.5
| GOLD010 | Golden Palace Heavy and Light |  |  |  | 7501.5
Total |  |  |  |  | 400 | 7901.5
[5 empty] | 455699.06 | 2756232.69

## Subcontractor
COINS - FINANCE
Subcontract Cost 201A22002 Dorchester Hotel & Residences
Period December 2022
Subcontract Costs
Cost Head |  | Description |  |  | Int Ref |  | Ext Ref |  | Current |  | TTD
Total
Manual Journals
| Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total
CVR Items
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total | [10 empty] | 0
Purchase Orders
Commodity |  | Description |  |  | Invoiced |  | Accrual / Rev |  | Current |  | TTD
62001A01 |  | Pest control |  |  | 1200 |  |  |  | 1200 |  | 7620
|  | CITY003 |  | City Pest Control and Building | 1200 |  |  |  | 1200 |  | 7620
Total |  |  |  |  | 1200 |  |  |  | 1200 |  | 7620
Direct Invoices
Cost Head |  | Description |  |  | Type |  | Int Ref |  | Current |  | TTD
Total

## Overhead
COINS - FINANCE
Overhead Cost 201A22002 Dorchester Hotel & Residences
Period December 2022
Purchase Orders
Commodity | Description |  | Invoiced | Accrual / Rev | Current | TTD
25512A01 | Project Sign Boards |  | 750 | -750 | 0 | 8303
| ABDU011 | Abdulrahman Al Abdooli Adverti |  | 0 | 0 | 890
| AMAL002 | Amalgam Ind. LLC |  |  | 0 | 3003
| KCEJ001 | KCE (LLC) - Joinery Division |  |  | 0 | 3660
| SALE001 | Saleem Jacobson Trading | 750 | -750 | 0 | 750
29901A01 | Small Tools/Equipment |  |  |  | 0 | 9035
| ALJA007 | Al Jas Technical Services LLC |  |  | 0 | 9035
60803A01 | Water and Electricity Charges |  |  |  | 0 | 24200
| DANL001 | Danlesco Gulf LLC |  |  | 0 | 24200
60905V02 | IT Equipment Printer Cameras etc |  | 11288 |  | 11288 | 49912.7
| ASTD001 | AST Digital Print Centre |  |  | 0 | 11561.84
| NEOT001 | Neo Tech Engineering LLC | 11288 |  | 11288 | 24508
| SCRE002 | Screencheck Technology Trading |  |  | 0 | 11300
| SHAR005 | Sharaf DG LLC |  |  | 0 | 2542.86
61001A01 | Safety Clothing and Equipment / PPE |  | 3061 |  | 3061 | 52117
| AGSO001 | AGS Office Supplies and Tradin |  |  | 0 | 250
| ALAB003 | Al Abbasi Fasteners and Hardware |  |  | 0 | 14750
| ALJA007 | Al Jas Technical Services LLC | 3061 |  | 3061 | 8991
| GULF019 | Gulf Metal Wires Industry LLC |  |  | 0 | 800
| KENT002 | Kent Star General Trading LLC |  |  | 0 | 2000
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 12526
| TULI001 | Tulip Trading LLC |  |  | 0 | 12800
61003A01 | Health and Safety expenses |  | 8000 | -8000 | 0 | 39324.92
| ALAM004 | Al Ameen Pharmacy LLC |  |  | 0 | 7504.92
| ASGC002 | ASGC Trading Building Machines & Equipment Rental LLC | 8000 | -8000 | 0 | 8000
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 23820
61111A01 | Refreshments (snacks tea coffee etc.) |  | 7529.5 | 175.1 | 7704.6 | 64447.25
| ALSH022 | Al Shalal Pure Drinking Water LLC | 1588 | -408 | 1180 | 11928
| CHOI001 | T Choithram and Sons LLC | 5941.5 | 583.1 | 6524.6 | 48704.25
| CLEA003 | Clear Ice LLC |  |  | 0 | 750
| FIND001 | Find General Trading LLC |  |  | 0 | 785
| JACK001 | Jackys Electronics LLC |  |  | 0 | 2280
61441A01 | Site Office Consumables |  | 2950 | 6880 | 9830 | 42112
| ALAB003 | Al Abbasi Fasteners and Hardware |  | 6880 | 6880 | 24080
| ALBA009 | Al Bariq Equipment LLC |  | 0 | 0 | 3832
| MANG001 | Mangal Trading Co LLC | 2950 |  | 2950 | 14200
61511A01 | Laboratory Testing & Calibaration Charges |  | 500 |  | 500 | 3930
| ALFA021 | Al Fajer Trading LLC |  |  | 0 | 330
| DANA002 | Danat Alkhaleej for Safety Consultancy |  |  | 0 | 2650
| GLOB007 | G Global Technologies LLC | 500 |  | 500 | 500
| WIMP001 | Wimpey Laboratories LLC |  |  | 0 | 450
61521A01 | Rubbish Removal |  | 3842.68 |  | 3842.68 | 125235.28
| GREE044 | Green Earth Waste Collection & Transportation Services | 3842.68 |  | 3842.68 | 49235.28
| STUR001 | Sturdy Products UAE Limited |  |  | 0 | 76000
61531A01 | Office & Site Furniture - Including ACs |  |  |  | 0 | 76990
| ALAR007 | Al Areej AC Units Fix Cont |  |  | 0 | 31625
| SABI001 | Sabi Air Conditioning Trading |  |  | 0 | 45365
61531A02 | Site Est (Offices Ablutions Stores Etc) |  |  |  | 0 | 22930.5
| ALME003 | Al Mesmar Trading Co LLC |  |  | 0 | 5025
| NATI010 | National Services for Carpet a |  |  | 0 | 10368.5
| SALE001 | Saleem Jacobson Trading |  |  | 0 | 6705
| TULI001 | Tulip Trading LLC |  |  | 0 | 832
61701A01 | Printing and Stationery |  | 2625 |  | 2625 | 42609.4
| AGSO001 | AGS Office Supplies and Tradin |  |  | 0 | 16515
| ALWA002 | Al Waha Stamps LLC |  |  | 0 | 670
| ASTD001 | AST Digital Print Centre | 2625 |  | 2625 | 24509.4
| SILV004 | Silver Screen Advertising Gift |  |  | 0 | 915
Total |  |  | 40546.18 | -1694.9 | 38851.28 | 561147.05
Direct Invoices
Cost Head | Description |  | Type | Int Ref | Current | TTD
29955 | Profit Abatement-CVR |  |  |  |  | 0
| ACC | Accruals
60624 | Penalties & Violations-Costed to Company |  |  |  | 1084.5 | 1872
| GOLD010 | Golden Palace Heavy and Light |  |  | 1084.5 | 1872
|  | Salik Month Of November 2022 | PINN | 2212PL001210 | 1084.5
60701 | Communication expense - landline and fax usage |  |  |  | 5411.63 | 45950.57
| EMIR032 | Emirates Integrated Telecommun |  |  | 4600 | 43784.76
|  | DU-NOV 2022 (Internet broad band-1) | PINN | 2212PL000548 | 3020
|  | DU-NOV 2022 (Internet broad band-2) | PINN | 2212PL000548 | 1580
| ETIS001 | Emirates Telecommunications Gr |  |  | 811.63 | 2165.81
|  | Tel Cost-0509394368- FACE STATION (NOV-2022) | PINN | 2212PL000541 | 105
|  | Tel Cost-0501894373- FACE STATION (NOV-2022) | PINN | 2212PL000541 | 63.8
|  | Tel Cost-0565456086--HIRED--SANEESH MOHAN (NOV-2022) | PINN | 2212PL000541 | 42.83
|  | Tel cost-0566869731-ROAMING CHARGES-20374--DARREN COOK (NOV-2022) | PINN | 2212PL000391 | 600
60703 | Communication expense - internet and data |  |  |  |  | 3750
| EMIR032 | Emirates Integrated Telecommun |  |  |  | 3750
60803 | Utilities - water external supply |  |  |  | 3300 | 3575
| DUBA003 | Dubai Aluminium PJSC |  |  | 3300 | 3575
|  | SWEET WATER SUPPLY - NOV'2022 | PINN | 2212PL001060 | 3300
60901 | Printers & Photocopiers |  |  |  | 9014.54 | 50186.1
| NEWS001 | New Smart Office Automation LL |  |  | 9014.54 | 50186.1
|  | B/W AND COLOR COPY CHGS - NOV'2022 | PINN | 2212PL001983 | 2915.58
|  | B/W AND COLOR COPY CHGS - NOV'2022 | PINN | 2212PL001983 | 2976.93
|  | B/W AND COLOR COPY CHGS - NOV'2022 | PINN | 2212PL001983 | 730.29
|  | B/W AND COLOR COPY CHGS - NOV'2022 | PINN | 2212PL001983 | 2391.74
61201 | Recruitment expenses |  |  |  |  | 2830
| EISA001 | Eisa Travels Agency LLC |  |  |  | 2830
Total |  |  |  |  | 18810.67 | 108163.67
Petty Cash Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  |  | 29852.52
60811 | Utilities - office and factory electricity and water |  |  |  |  | 46680
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 3723.8 | 21602.05
|  | 27743-CHRIS McCANN-201A22002 | PCP | DEC/11613/07 | 1501
|  | 27743-CHRIS McCANN-P CASH RETURNED | RDC | 19531 | 1757.8
|  | 31671-ISHITA JOSHI-201A22002 | PCP | DEC/11617/20 | 465
61131 | COS Staff welfare expense |  |  |  |  | 3213.12
62001 | Miscellaneous expenses |  |  |  |  | 350
Total |  |  |  |  | 3723.8 | 101697.69
Manual Journals
Cost Head | Description |  | Type | Int Ref | Current | TTD
60621 | Other fee - charges |  |  |  | 15435 | 77008.81
|  | Credit Card Transactions for Card_9134-DM - Fees paid for temp. completion cer.-202200633082-09/12/2022-201A22002 (DEC-2022) | JNL |  | 120
|  | Credit Card Transactions for Card_9134-RTA - Fees to obtain a road permit-1426439655-28/12/2022-201A22002 (DEC-2022) | JNL |  | 95
|  | Credit Card Transactions for Card_9134-RTA - Fees for road diversion NOC-1424819619-26/12/2022-201A22002 (DEC-2022) | JNL |  | 220
|  | RTA Deposit to obtain NOC - Dorchester Project | JNL |  | 15000
60701 | Communication expense - landline and fax usage |  |  |  |  | 25203
60703 | Communication expense - internet and data |  |  |  |  | 1079.17
60811 | Utilities - office and factory electricity and water |  |  |  |  | 5064.85
60902 | Specialist Software |  |  |  | 140 | 49280
|  | MAIL BOX SERVICES - DEC 2022 | JNL |  | 140
61001 | Health and safety - material items |  |  |  | 1490 | 1490
|  | HSE Shirt cost transfer from HO LPO | JNL |  | 1490
61111 | Refreshments (snacks, tea, coffee etc.) |  |  |  | 398.2 | 1896.59
|  | Unclaimed VAT Nov'22 W/Off | JNL |  | 180.62
|  | Unclaimed VAT Nov'22 W/Off | JNL |  | 27
|  | Unclaimed VAT Nov'22 W/Off | JNL |  | 54.75
|  | Unclaimed VAT Nov'22 W/Off | JNL |  | 135.83
61201 | Recruitment expenses |  |  |  |  | -2830
61311 | Rent - accommodation |  |  |  |  | 119.03
62001 | Miscellaneous expenses |  |  |  |  | 100
Total |  |  |  |  | 17463.2 | 158411.45
Plant Charges
Cost Head | Description |  | Type | Int Ref | Current | TTD
60905 | Computers & Accessories |  |  |  | 1085 | 8827
| ITA0002123 | ITA0002123 Samsung Galaxy Tab Active Pro |  |  | 0 | 0
| ITA0003005 | ITA0003005 Face Station 2 - Identification Device |  |  | 217 | 1890
| ITA0003060 | ITA0003060 Face Station 2 - Identification Device |  |  | 217 | 1785
| ITA0003063 | ITA0003063 Face Station 2 - Identification Device |  |  | 217 | 1582
| ITA0003075 | ITA0003075 Face Station 2 - Identification Device |  |  | 217 | 1785
| ITA0003084 | ITA0003084 Face Station 2 - Identification Device |  |  | 217 | 1785
Total |  |  |  |  | 1085 | 8827
Stock Issues
Cost Head | Description |  | Type | Int Ref | Current | TTD
60902 | Specialist Software |  |  |  |  | 2399
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 2399
60905 | Computers & Accessories |  |  |  | 1216.4 | 24176.92
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-020002 | Access Point Aruba AP 515 - Used |  |  |  | 0
| 60905V01-010006 | Keyboard & Mouse Logitec Wireless Black - New | ISS |  | 125 | 1375
| 60905V01-010008 | Mouse Logitec Wireless Black - New |  |  | 250 | 950
| 60905V01-010011 | Cable HDMI 2m - New |  |  |  | 72.5
| 60905V01-010013 | Cable HDMI 5m - New |  |  |  | 110
| 60905V01-010019 | Cable Cat6 5m - New |  |  |  | 70.44
| 60905V01-010020 | Cable Roll 305m - New |  |  |  | 1835.9
| 60905V01-010031 | RJ45 connector - New |  |  |  | 8.26
| 60905V01-010037 | Monitor 24" 1080p E Series - New |  |  |  | 4887.75
| 60905V01-010038 | Monitor HP E22 G4 FHD - New |  |  |  | 4566.94
| 60905V01-010041 | Samsung Tablet Case Cover - New |  |  | 380 | 380
| 60905V01-010043 | Laptop Bag HP - New |  |  | 461.4 | 2540.4
| 60905V01-010045 | EVOLIS-YMCKO Color Ribbon - New |  |  |  | 220
| 60905V01-010046 | EVOLIS Smart Cards - Mifare 1K - New |  |  |  | 1120.02
| 60905V01-010050 | USB A Wi-Fi adapter - New |  |  |  | 582
| 60905V01-010052 | Crucial SSD Hard disk - New |  |  |  | 786.28
| 60905V01-010053 | Bracket for Crucial SSD Hard disk - New |  |  |  | 17.5
| 60905V01-010054 | New Onsite installation of new SSD with OS |  |  |  | 95
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New |  |  |  | 595.93
60906 | Standard Software |  |  |  |  | 8847
| 60906V01-010017 | Bluebeam Revu Extreme Perpetual License Windows OS |  |  |  | 7197
| 60906V01-010018 | Bluebeam Revu Extreme Annual Maintenance & Support Windows OS |  |  |  | 1650
60909 | Telecomunication Services |  |  |  | 3562.86 | 36161.86
| 24325V01-010002 | Access Point Aruba AP 515 - New |  |  |  | 3897
| 24325V01-010004 | Mounting Kit Aruba AP 515 - New |  |  |  | 66
| 24325V01-010012 | Aruba Central AP Foundation 1y Subscription - New |  |  |  | 3651.91
| 24325V01-020005 | Network Switch Cisco SG350 28 Port - Used |  |  |  | 0
| 60909V01-010008 | Sim Card Etisalat Standard - New |  |  |  | 0
| 60909V01-010012 | Mobile Handset Samsung A12 Black - New |  |  |  | 4910.1
| 60909V01-010014 | Mobile Handset Samsung A52 Black - New |  |  |  | 1255.24
| 60909V01-010015 | Mobile Handset Nokia 225 - New |  |  |  | 340
| 60909V01-010018 | Mobile Handset Samsung A13 Black ? New | ISS |  | 3562.86 | 20806.61
| 60909V01-010019 | Mobile Handset Samsung A53 ? New |  |  |  | 1235
61001 | Health and safety - material items |  |  |  | 14514.24 | 99879.31
| 46181503-A01361 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | ISS |  | 210.58 | 3369.24
| 46181503-A01362 | Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | ISS |  | 141.12 | 1128.96
| 46181503-A01363 | Blue Pant/Shirt 180 Gsm Full Sleeve -4XL | ISS |  | 77.49 | 309.96
| 46181503-A01364 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | ISS |  | 631.73 | 6130.16
| 46181503-A01365 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | ISS |  | 2719.48 | 13453.38
| 46181503-A01366 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | ISS |  | 2277 | 5908.75
| 46181503-A01367 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | ISS |  | 631.07 | 4744.71
| 46181503-A01383 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - 2XL | ISS |  | 114 | 456
| 46181503-A01386 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Large |  |  |  | 342
| 46181503-A01387 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Medium | ISS |  | 342 | 1368
| 46181503-A01388 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Small |  |  |  | 114
| 46181503-A01389 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - XL |  |  |  | 342
| 46181504-A20645 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | ISS |  | 743.78 | 4287.26
| 46181504-A20646 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | ISS |  | 2625 | 15679.86
| 46181504-A20647 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 | ISS |  | 1500 | 6750
| 46181605-A04415 | Safety Shoe For Staff 59351 Size 38 |  |  |  | 240
| 46181605-A04416 | Safety Shoe For Staff 59351 Size 39 |  |  |  | 80
| 46181605-A04418 | Safety Shoe For Staff 59351 Size 41 | ISS |  | 160 | 640
| 46181605-A04419 | Safety Shoe For Staff 59351 Size 42 | ISS |  | 160 | 1040
| 46181605-A04420 | Safety Shoe For Staff 59351 Size 43 |  |  |  | 880
| 46181605-A04421 | Safety Shoe For Staff 59351 Size 44 | ISS |  | 240 | 560
| 46181605-A04422 | Safety Shoe For Staff 59351 Size 45 |  |  |  | 160
| 46181605-A04423 | Safety Shoe For Staff 59351 Size 46 |  |  |  | 80
| 46181605-A18968 | Safety Shoe For Staff 59351 Size 40 |  |  |  | 560
| 46181605-A18970 | Safety Shoe for workers Saudi 59102 SIZE 38 |  |  | 130 | 390
| 46181605-A18971 | Safety Shoe for workers Saudi 59102 SIZE 39 | ISS |  | 130 | 1755
| 46181605-A18972 | Safety Shoe for workers Saudi 59102 SIZE 40 | ISS |  | 650 | 4030
| 46181605-A18973 | Safety Shoe for workers Saudi 59102 SIZE 41 |  |  | 130 | 3120
| 46181605-A18974 | Safety Shoe for workers Saudi 59102 SIZE 42 | ISS |  | 325 | 7865
| 46181605-A18975 | Safety Shoe for workers Saudi 59102 SIZE 43 |  |  | 65 | 4030
| 46181605-A18976 | Safety Shoe for workers Saudi 59102 SIZE 44 |  |  | 65 | 1755
| 46181605-A18977 | Safety Shoe for workers Saudi 59102 SIZE 45 |  |  |  | 455
| 46181605-A18978 | Safety Shoe for workers Saudi 59102 SIZE 46 | ISS |  | 65 | 195
| 46181701-A04402 | Safety Helmet High Ev Yellow - 6 Point Textile Tapes System. Slip Ratche |  |  |  | 26
| 46181804-A04397 | Safety Goggles - Clear - Globus - Riley - Bm08 |  |  |  | 2210.98
| 46181804-A04398 | Safety Goggles - Grey - Globus - Riley - Bm08 |  |  |  | 65.56
| 46181804-A19383 | Safety Goggles - Clear - Bm10 |  |  |  | 51.47
| 46181804-A19384 | Safety Goggles - Clear - Riley - Pn-RLY00071 |  |  |  | 760.21
| 46181804-A19385 | Safety Goggles - Grey - Riley - Pn-RLY00072 |  |  |  | 509.49
| 46182001-A20175 | Disposable Face Mask Blue 3 Ply (1x50) Local |  |  | 380.99 | 3781.32
| 71001Z01-010011 | Fire Extinguisher Inspection Tag |  |  |  | 255
61131 | COS Staff welfare expense |  |  |  |  | 12314.32
| 51211706-A00348 | Aqualyte Solution 80Grmx100Satchets/Ct |  |  |  | 230.35
| 51211706-A00349 | Aqualyte Solution 800Grmx10Satchets/Ct |  |  |  | 12083.97
61701 | Stationary |  |  |  |  | 542.5
| 14111509-A19706 | Business Cards |  |  |  | 120
| 71701Z01-01005 | Khansaheb Note Pad A5 |  |  |  | 275
| 71701Z01-01006 | Khansaheb Note Pad A4 |  |  |  | 147.5
Total |  |  |  |  | 19293.5 | 184320.91
[5 empty] | 99227.45 | 1122567.77