## Summary
No | Description | Previous | This Month | Cumulative
| Original Scope | 270000 | 37464 | 307464
|  | 0 | 103738.271 | 103738.271
|  | 270000 | 141202.271 | 411202.271
| Advance Payment | 133278.25 |  | 133278.25
| Advance Payment Recovery | -27000 | -14120.2271 | -41120.2271
|  | 376278.25 | 127082.0439 | 503360.2939

## P.A. 001
KHANSAHEB CIVIL ENGINEERING L.L.C. / CONSTRUCTION DIVISION
CONTRACT NAME : Dorchester Hotel & Residences
CONTRACT NO. 201A22002
SUBCONTRACTOR : PROGRESS FABRICATION for STEEL CONSTRUCTION CONTRACTING CO. LLC
PAYMENT APPLICATION NO. 001
PROJECT CONTACT BOQ : (MARBLE STEEL SUPPORT) | [5 empty] | PROGESS BILL OF WORKS BREAKDOWN
ITEM NO. | DESCRIPTION | QTY. | UNIT | RATE : AED | AMOUNT : AED | SUPPLY ACCOMPLISHMENT |  |  |  | INSTALLATION ACCOMPLISHMENT |  |  |  | SUPPLY + INSTALLATION : TOTAL - % | SUPPLY + INSTALLATION : TOTAL AMOUNT | REMARKS
[6 empty] | Last Month - % | This Month - % | Up to Date - % | AMOUNT : AED | Last Month - % | This Month - % | Up to Date - % | AMOUNT : AED
Design, Supply, Fabrication, Delivery and Installation of Steel support for stone cladding and as per attached drawing.
A | Material Considered : Hot Rolled Steel S275JR or Equivalent. Steel material sections as mentioned on the attached drawings. Anchor bolts / bolts considered G.I. Mechanical of max. grade 8.8. Coating : Zinc Rich Epoxy primer 50-75 microns dft. Unistrut size 41 x 21x 2 mm thk. will be supplied with self tapping screw to the marble contractor. All other neighbour items are excluded in our scope. | 1 | Set | 300000 | 300000 | 70% | 0% | 70% | 210000 | 20% | 10% | 30% | 90000 | 100% | 300000 | 100 % Done
PROJECT CONTACT BOQ : (AUTOMATIC SLIDING DOOR) | [5 empty] | PROGESS BILL OF WORKS BREAKDOWN
ITEM NO. | DESCRIPTION | QTY. | UNIT | RATE : AED | AMOUNT : AED | SUPPLY ACCOMPLISHMENT |  |  |  | INSTALLATION ACCOMPLISHMENT |  |  |  | SUPPLY + INSTALLATION : TOTAL - % | SUPPLY + INSTALLATION : TOTAL AMOUNT | REMARKS
[6 empty] | Last Month - % | This Month - % | Up to Date - % | AMOUNT : AED | Last Month - % | This Month - % | Up to Date - % | AMOUNT : AED
| ENTRANCE LOBBY AUTOMATIC GLASS SLIDING DOOR @ RESIDENTIAL GROUND FLOOR ZONE - A : Size 2350 x 4350 mm Overall Height | 1 | NO | 24880 | 24880 | 0% | 25% | 25% | 6220 | 0% | 5% | 5% | 1244 | 30% | 7464 | Steel Support Completed
Fabrication, supply, delivery and installation of Automatic Glass Sliding Door comprising of the ffg. Scope of works & as per the e nclosed drawings.
1 | Fabrication, supply and installation of steel support based on final drawings. (Column, Beam & Hanger). Hot rolled steel material grade S275JR with 2 - coats of Epoxy paint.
2 | Supply and installation of 12 mm thk fixed glass panel & 8 mm thk sliding door panel, crystal clear tempered glass including aluminum frame and cladded by 0.8 mm thk. SS sheet grade 304 in brushed finish.
3 | Supply and installation of ES-200 Dormakaba Automatic Sliding Door Mechanism or Equivalent with Salient features & covered by 1.0 mm thk grade 304 SS sheet in brushed finish.
PROJECT CONTACT BOQ : LUMPSUM PACKAGE - 5 | [5 empty] | PROGESS BILL OF WORKS BREAKDOWN
ITEM NO. | DESCRIPTION | UNIT | QTY. | RATE : AED | AMOUNT : AED | SUPPLY ACCOMPLISHMENT |  |  |  | INSTALLATION ACCOMPLISHMENT |  |  |  | SUPPLY + INSTALLATION : TOTAL - % | SUPPLY + INSTALLATION : TOTAL AMOUNT | REMARKS
[6 empty] | Last Month - % | This Month - % | Up to Date - % | AMOUNT : AED | Last Month - % | This Month - % | Up to Date - % | AMOUNT : AED
REF. : QUOTATION/PFSC/QTN/08/22/10249 REV. 1A
1 | Metal Architrave cladding for TB-21 Door ME-01 340mm width 2400mm H x 1920mm (10mm thick) | Set | 25 | 4144 | 103600
2 | Metal Architrave cladding for TB-22 ME-03 50mm Width 2250mm Hx 1100mm (10mm thickness) | Set | 95 | 479 | 45505
REF. : QUOTATION/PFSC/QTN/08/22/10249 REV. 1A
3 | Metal cladding around the wooden panel ME-01 85mm Width 2405mm Hx 1244mm (10mm thickness) | Set | 9 | 777 | 6993
4 | Metal cladding around the wooden panel ME-01 85mm Width 2405mm Hx 940mm (10mm thickness) | Set | 2 | 752 | 1504
5 | Metal cladding around the wooden panel ME-01 85mm width 2510mm Hx750mm (10mm thickness) | Set | 126 | 741 | 93366
6 | Metal cladding around the Ceiling wooden panel ME-01 85mm width 2200m Lx750mm (10mm thickness) | m | 268 | 174 | 46632
7 | Metal cladding around the Wall Paper/Stone fature ME-01 108/126mm width 2510mm H (TYPE- 7B) | m | 2665 | 176 | 469040 | 0% | 12.48% | 12.48% | 58536.192 | 0% | 0.76% | 0.76% | 3564.704 | 13.24% | 62100.896 | 475 M X 70% / 2665 M = 12.48 % & 67.5 M X 30 % / 2665 M = 0.76 %
8 | Metal Architraves in the Room Entrance Doors ME-01 130mm Width 2440mm Hx1100mm (TYPE-08) | Set | 225 | 975 | 219375 | 0% | 18.98% | 18.98% | 41637.375 | 0% | 0% | 0% | 0 | 18.98% | 41637.375 | 61 SET X 70 % / 225 SET = 18.98 %
| TOTAL AMOUNT EXCLUDING VAT (AED) |  |  |  | 1310895 |  |  |  |  | TOTAL AMOUNT EXCLUDING VAT IN AED |  |  |  |  | 411202.271
| VALUE ADDED TAX (VAT - 5 %) |  |  | 5% | 65544.75 |  |  |  |  | VALUE ADDED TAX (5 %) IN AED |  |  |  | 5% | 20560.1136
| GRAND TOTAL TOTAL AMOUNT INCLUDING VAT (AED) |  |  |  | 1376439.75 |  |  |  |  | GRAND TOTAL AMOUNT DUE FOR PAYMENT |  |  |  |  | 431762.3846