## Summary
No | Description | BOQ | Workdone % | Previous Certified | Current | Cumulative Amount | Remark
Original Scope
A | Installation of Steel Beam | 77965 | 95% | 74066.75 | 0 | 74066.75 | WIR VE-SX-WR-PW-00003 not approved
| Demolition | 33000 | 95% | 31350 | 0 | 31350 | WIR VE-SX-WR-PW-00004 not approved
| Total Amount | 110965 |  | 105416.75 | 0 | 105416.75
Variation
B | Design Calcuation | 10000 | 90% | 9000 | 0 | 9000 | Only 90% until variation approval
| Slab Trimming | 89000 | 90% | 80100 | 0 | 80100 | Only 90% until variation approval
| Fire Proofing | 34500 | 90% | 31050 | 0 | 31050 | Only 90% until variation approval, WIR VE-SX-WR-PW-00005 not approved
| Strengthening of new slab opening at Level 29 | 32000 | 0% | 0 | 0 | 0 | Only 90% until variation approval, WIR VE-SX-WR-PW-00005 not approved
|  | 165500 | 2.7 | 120150 | 0 | 120150 |  | 276465 | 225566.75
|  |  |  | 225566.75 | 0 | 225566.75
| Advance Payment |  |  | 204175.4 |  | 204175.4
| Advance Payment Recovery |  |  | -33290 | -85442.4 | -118732.4
| Total |  |  | 396452.15 | -85442.4 | 311009.75
|  | KCE Claim | 244465 |  |  | 170885.4 | 415350.4
|  | Difference | #REF! |  |  | 140124.35 | -415350.4