## Sheet3
Plot-18
Estimated Final Cost Difference between Feb 23 and Jan 23 FCR
REF | FCR COST HEADING | FCR Feb 23 | FCR Jan 23 | Difference | Reason
1 | ONGOING CONSULTANCY AGREEMENTS | 102288347.5 | 99009553.1407 | 3278794.3593 | Extension of Services to June 23
2 | LOCAL AUTHORITY FEES | 28503463.9 | 51467686.73 | -22964222.83 | Moving Authority fees paid by RPJV under payments to RPJV (Item 4)
3 | FACILITATING WORKS | 40587829 | 40587829 | 0
4 | RP TOTAL - MAIN WORKS | 532161640 | 507541747 | 24619893 | As for comment of item 2
5 | Hotel LOOSE FF&E |  |  | 0
| LOOSE FF&E FOR HOTEL | 36277033 | 26300000 | 9977033 | Actual estimate of final cost
| BOH EQUIPMENT-Commercial Kitchen and Laundry | 10554432 | 7162178 | 3392254 | Actual estimate of final cost
6 | RESIDENCES FIT-OUT | 98000052 | 98904455.83 | -904403.83 | Actual estimate of final cost
7 | Residences - Furniture Package | 30759933 | 53828987.2 | -23069054.2 | Actual estimate of final cost
8 | NEW CONTRACTOR - KHANSAHEB | 317108998 | 194951734 | 122157264 | Actual estimate of final cost
9 | PAYMENTS TO RPJV SUBCONTRACTORS | 37419805 | 33400000 | 4019805 | Actual estimate of final cost
| Total | 1233661533.4 | 1113154170.9007 | 120507362.4993