## PA Front Sheet
PAYMENT APPLICATION
Application # 7
Khansaheb Civil Engineering L.L.C. |  | Date | 2023-03-30 |  |  | HOTEL
PO Box - 2716 |  | Period As on | 2023-03-25 |  |  | RESIDENCE
Dubai |  | Type | Scaffolding Services
United Arab Emirates |  | Our Bankers | Bank Of Sharjah
Tel : 971 04 605 7200
Fax : 971 04 285 7539 |  | Account No. | 013 06 278065 01
Attn: Mr. Saman Kulasooriya
Dorchester Hotel & Residences (Completion Works) - 201A22002/49
Description |  | Previous Invoiced (AED) | This Application Value (AED) | Total Invoiced Net To Date (AED)
Contract Ref 201A22002/49
Scope Of Work |  | 552708.02 | 50491.82 | 603199.84
Variations |  | 1072056.57 | 119119.608 | 1191176.178
Dayworks |  | 13530 | 2509.2 | 16039.2 | 1207215.378
*** September to February payments only 95% paid for varitaions, but from March 2023 onward 90% will be certified for variation and dayworks
Total |  | 1638294.59 | 172120.628 | 1810415.218
AED : one hundred ninety-five thousand four hundred ninety-two and forty-six fils only
(for Client use only) |  | Authorized Signatory
Technical Access Services LLC
The above amount is not inclusive of VAT
| KCE Claim | 1698664.4 | 195492.46 | 1894156.86
| Difference | -60369.81 | -23371.832 | -83741.642

## Evaluation
Invoice Schedule
Khansaheb Civil Engineering LLC
Application No.: | 7
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2023-03-25
Billing Reference | Location | Tag No. | HOC | OHC | Description | Founding Level | Scaffold Type | Number | Length | Width | Height | Board Lift | Unit of Measure | Quantity | HOC Date | OHC Date | Erection % | Hire % | Dismantle % | Hire Weeks | E&D Rate per unit | Hire Rate per week | Erect Charges | Hire Charges | Dismantle Charges | Total Amount | Previous Amount | Net Amount | Remarks | Previous Certified | This Month | Cumulative Certified |  | Erection |  |  | Hire |  |  | Dismantle |  |  | Net Payment
E11/K149/SK/dm/257 | HOTEL | 1 | 74602 | 79905 | Level-28/29 Block & Glass Work | Level 28-29 | Design-1399-02 rev-D | 1 |  |  |  |  | unit | 1 | 2022-09-26 | 2023-03-01 | 100% | 100% | 50% | 22.4286 | 50703.26 | 2807 | 35492.28 | 62957 | 7605.49 | 106054.77 | 96845.28 | 9209.49 | Tas Quote-2439-4-3 rev1/Partially Dismantled | 96845.28 | 9209.49 | 106054.77 | 0 | 35492.28 | 35492.28 | 0 | 67769 | 61353 | 6416 | 7605.49 | 0 | 7605.49 | 14021.49 | 14021.49 | 0
E11/K149/SK/dm/257 | HOTEL | 1 | 74602 |  | Level-28/29 Block & Glass Work | Level 28-29 | Design-1399-02 rev-D | 1 |  |  |  |  | unit | 1 | 2023-03-02 |  | 0% | 50% | 0% | 3.4286 | 50703.26 | 2807 | 0 | 4812 | 0 | 4812 |  | 4812 | Tas Quote-2439-4-3 rev1/Partially Dismantled |  | 4812 | 4812 | 0 | 35492.28 | 35492.28 | 0 | 67769 | 61353 | 6416 | 7605.49 | 0 | 7605.49 | 14021.49 | 14021.49 | 0
E11/K149/SK/dm/216 | RESIDENCE |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-09-15 | 2022-10-01 | 0% | 100% | 0% | 2.4286 | 0 | 200 | 0 | 485.71 | 0 | 485.71 | 485.71 | 0 | TAS/HIRE/4969/SM | 485.71 | 0 | 485.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 | 2022-11-25 | 95% | 95% | 0% | 9.5714 | 191160 | 6716 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Contract Scope - Progressive Billing |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 100% | 0% | 0% | 26.7143 | 256937.1474 |  | 179856 | 0 | 0 | 179856 | 179856 | 0 | Tas Quote -2439-2-2 rev1 | 179856 | 0 | 179856 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Item - 9,10,11,12 |  |  | 1 |  |  |  |  | unit | 1 | 2022-09-20 |  | 100% | 0% | 0% | 26.7143 | 80440 |  | 56308 | 0 | 0 | 56308 | 56308 | 0 | Tas Quote -2439-2-2 rev1 | 56308 | 0 | 56308 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 34.2 | 1.3 | 5 | 1 | m2-LxH | 171 | 2022-09-20 |  | 0% | 100% | 0% | 26.7143 | 0 | 0.49 | 0 | 2238.39 | 0 | 2238.39 | 1903.23 | 335.16 | Tas Quote -2439-2-2 rev1 | 1903.23 | 335.16 | 2238.39 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82111-82112-82136 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 25.2 | 1.8 | 10.5 | 5 | m2-LxH | 264.6 | 2022-09-20 | 2023-03-20 | 0% | 100% | 100% | 26 | 0 | 0.77 | 0 | 5297.29 | 0 | 5297.29 | 4627.85 | 669.44 | Tas Quote -2439-2-2 rev1 | 4627.85 | 669.44 | 5297.29 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82111-82112-82136 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 4 | 25.2 | 1.8 | 1 | 4 | m2-LxW | 181.44 | 2022-09-20 | 2023-03-20 | 0% | 100% | 100% | 26 | 0 | 0.7 | 0 | 3302.21 | 0 | 3302.21 | 2884.9 | 417.31 | Tas Quote -2439-2-2 rev1 | 2884.9 | 417.31 | 3302.21 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 |  | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 7.2 | 1.8 | 15.5 | 1 | m2-LxH | 111.6 | 2022-09-20 |  | 0% | 100% | 0% | 26.7143 | 0 | 0.77 | 0 | 2295.61 | 0 | 2295.61 | 1951.88 | 343.73 | Tas Quote -2439-2-2 rev1 | 1951.88 | 343.73 | 2295.61 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82137 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 4.2 | 1 | m2-LxH | 60.48 | 2022-09-20 | 2023-03-25 | 0% | 100% | 100% | 26.7143 | 0 | 0.77 | 0 | 1244.07 | 0 | 1244.07 | 1057.8 | 186.27 | Tas Quote -2439-2-2 rev1 | 1057.8 | 186.27 | 1244.07 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82138 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 6 | 2 | m2-LxH | 86.4 | 2022-09-20 | 2023-03-25 | 0% | 100% | 100% | 26.7143 | 0 | 0.77 | 0 | 1777.25 | 0 | 1777.25 | 1511.14 | 266.11 | Tas Quote -2439-2-2 rev1 | 1511.14 | 266.11 | 1777.25 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82138 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 14.4 | 1.8 | 1 | 1 | m2-LxW | 25.92 | 2022-09-20 | 2023-03-25 | 0% | 100% | 100% | 26.7143 | 0 | 0.7 | 0 | 484.7 | 0 | 484.7 | 412.13 | 72.57 | Tas Quote -2439-2-2 rev1 | 412.13 | 72.57 | 484.7 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1g | 74656 | 82140 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 9 | 1.8 | 10.5 | 1 | m2-LxH | 94.5 | 2022-09-21 | 2023-03-24 | 0% | 100% | 100% | 26.4286 | 0 | 0.77 | 0 | 1923.08 | 0 | 1923.08 | 1642.41 | 280.67 | Tas Quote -2439-2-2 rev1 | 1642.41 | 280.67 | 1923.08 | 0 | 0 | 0 | 0 | 1923.08 | 1642.41 | 280.67 | 0 | 0 | 0 | 280.67 | 280.67 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1m | 74674 | 79881 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 23.4 | 2.75 | 1 | 1 | m2-LxW | 64.35 | 2022-10-01 | 2023-03-06 | 0% | 100% | 100% | 22.4286 | 0 | 6.72 | 0 | 9698.83 | 0 | 9698.83 | 9142.85 | 555.98 | Tas Quote -2439-2-2 rev1 | 9142.85 | 555.98 | 9698.83 | 0 | 0 | 0 | 0 | 9698.83 | 9142.85 | 555.98 | 0 | 0 | 0 | 555.98 | 555.98 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1u | 79101 | 82122 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 20 | 2.75 | 1 | 1 | m2-LxW | 55 | 2022-12-06 | 2023-03-15 | 0% | 100% | 100% | 14.2857 | 0 | 6.72 | 0 | 5280 | 0 | 5280 | 4329.6 | 950.4 | Tas Quote -2439-2-2 rev1 | 4329.6 | 950.4 | 5280 | 0 | 0 | 0 | 0 | 5280 | 4329.6 | 950.4 | 0 | 0 | 0 | 950.4 | 950.4 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8w | 79146 | 79889 | Glass Work | 29 to 31 | Design-1399-01 rev-G | 1 | 6 | 2.5 | 1 | 1 | m2-LxW | 15 | 2022-12-15 | 2023-03-13 | 0% | 100% | 100% | 12.7143 | 0 | 6.72 | 0 | 1281.6 | 0 | 1281.6 | 1051.2 | 230.4 | Tas Quote -2439-2-2 rev1 | 1051.2 | 230.4 | 1281.6 | 0 | 0 | 0 | 0 | 1281.6 | 1051.2 | 230.4 | 0 | 0 | 0 | 230.4 | 230.4 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82111-82112-82136 | Glass Work | 29 to 31 | H20 Beam - Bottom | 1 | 50.4 | 1.3 | 1 |  | m3 | 65.52 | 2022-09-20 | 2023-03-25 | 0% | 100% | 100% | 26.7143 | 0 | 10.15 | 0 | 17765.75 | 0 | 17765.75 | 15105.64 | 2660.11 | Tas Quote -2439-2-2 rev1 | 15105.64 | 2660.11 | 17765.75 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1 | 74652 | 82111-82112-82136 | Glass Work | 29 to 31 | Hilti | 1 | 224 | 1 | 1 |  | lm | 224 | 2022-09-20 | 2023-03-25 | 0% | 100% | 100% | 26.7143 | 0 | 17.15 | 0 | 102625.6 | 0 | 102625.6 | 87259.2 | 15366.4 | Tas Quote -2439-2-2 rev1 | 87259.2 | 15366.4 | 102625.6 | 0 | 0 | 0 | 0 | 137030.87 | 116713.77 | 20317.1 | 0 | 0 | 0 | 20317.1 | 20317.1 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3d | 79109 | 82121 | Glass Work | 31to32 | Design-1399-03 | 1 | 20 | 2.75 | 1 | 1 | m2-LxW | 0 | 2022-12-07 | 2023-03-16 | 0% | 100% | 100% | 14.2857 | 0 | 6.72 | 0 | 0 | 0 | 0 | 4276.8 | -4276.8 | Tas Quote -2439-2-2 rev1 | 4276.8 | -4276.8 | 0 | 0 | 0 | 0 | 0 | 10500 | 12781.8 | -2281.8 | 0 | 0 | 0 | -2281.8 | -2281.8 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 2h | 79158 | 82117 | Glass Work | 31 | Design-1399-03 | 1 | 5 | 2.75 | 1 | 1 | m2-LxW | 13.75 | 2022-12-16 | 2023-03-18 | 0% | 100% | 100% | 13.2857 | 0 | 6.72 | 0 | 1227.6 | 0 | 1227.6 | 950.4 | 277.2 | Tas Quote -2439-2-2 rev1 | 950.4 | 277.2 | 1227.6 | 0 | 0 | 0 | 0 | 1227.6 | 950.4 | 277.2 | 0 | 0 | 0 | 277.2 | 277.2 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3f | 79143 | 82119 | Glass Work | 31 | Design-1399-03 | 1 | 12 | 2.75 | 1 | 1 | m2-LxW | 33 | 2022-12-14 | 2023-03-18 | 0% | 100% | 100% | 13.5714 | 0 | 6.72 | 0 | 3009.6 | 0 | 3009.6 | 2344.32 | 665.28 | Tas Quote -2439-2-2 rev1 | 2344.32 | 665.28 | 3009.6 | 0 | 0 | 0 | 0 | 3009.6 | 5347.98 | -2338.38 | 0 | 0 | 0 | -2338.38 | -2338.38 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3d | 79109 | 82121 | Glass Work | 31to32 | Design-1399-03 | 1 | 12 | 5 | 1 | 1 | m2-LxW | 60 | 2022-12-07 | 2023-03-16 | 0% | 100% | 100% | 14.2857 | 0 | 12.25 | 0 | 10500 | 0 | 10500 | 8505 | 1995 | Tas Quote -2439-2-2 rev1 | 8505 | 1995 | 10500 | 0 | 0 | 0 | 0 | 10500 | 12781.8 | -2281.8 | 0 | 0 | 0 | -2281.8 | -2281.8 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3f | 79143 | 82119 | Glass Work | 31 | Design-1399-03 | 1 | 12 | 2.75 | 1 | 1 | m2-LxW | 0 | 2022-12-14 | 2023-03-18 | 0% | 100% | 100% | 13.5714 | 0 | 8.61 | 0 | 0 | 0 | 0 | 3003.66 | -3003.66 | Tas Quote -2439-2-2 rev1 | 3003.66 | -3003.66 | 0 | 0 | 0 | 0 | 0 | 3009.6 | 5347.98 | -2338.38 | 0 | 0 | 0 | -2338.38 | -2338.38 | 0
CONTRACT - 201A22002/49 | RESIDENCE |  |  |  | Glass Work | 31 | Sheeting-22 | 1 | 52 | 1 | 1 |  | m2-LxH | 52 | 2022-12-14 |  | 0% | 100% | 0% | 14.5714 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 6.8 | 1.8 | 4 | 1 | m2-LxH | 27.2 | 2022-10-10 |  | 0% | 100% | 0% | 23.8571 | 0 | 0.77 | 0 | 499.66 | 0 | 499.66 | 415.89 | 83.77 | Tas Quote -2439-2-2 rev1 | 415.89 | 83.77 | 499.66 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8a | 77651 | 79897-82142 | Glass Work | Level 26 to 31 | Design-1399-04 | 1 | 23.4 | 3.6 | 24 | 1 | m3 | 2021.76 | 2022-10-10 | 2023-03-24 | 0% | 100% | 100% | 23.7143 | 0 | 0.49 | 0 | 23492.85 | 0 | 23492.85 | 19671.72 | 3821.13 | Tas Quote -2439-2-2 rev1 | 19671.72 | 3821.13 | 23492.85 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8b | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 18.6 | 0.6 | 4 | 1 | m2-LxH | 74.4 | 2022-10-10 |  | 0% | 100% | 0% | 23.8571 | 0 | 0.49 | 0 | 869.74 | 0 | 869.74 | 723.91 | 145.83 | Tas Quote -2439-2-2 rev1 | 723.91 | 145.83 | 869.74 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8c | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 10.8 | 0.6 | 4 | 1 | m2-LxH | 43.2 | 2022-10-10 |  | 0% | 100% | 0% | 23.8571 | 0 | 0.49 | 0 | 505.01 | 0 | 505.01 | 420.34 | 84.67 | Tas Quote -2439-2-2 rev1 | 420.34 | 84.67 | 505.01 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8d | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 6.8 | 0.9 | 4 | 1 | m2-LxH | 27.2 | 2022-10-10 |  | 0% | 100% | 0% | 23.8571 | 0 | 0.49 | 0 | 317.97 | 0 | 317.97 | 264.66 | 53.31 | Tas Quote -2439-2-2 rev1 | 264.66 | 53.31 | 317.97 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8e | 77651 |  | Glass Work | Level 26 to 31 | Design-1399-04 | 6 | 23.4 | 0.5 | 1 | 6 | m2-LxW | 70.2 | 2022-10-10 | 2023-03-13 | 0% | 100% | 100% | 22.1429 | 0 | 1.05 | 0 | 1632.15 | 0 | 1632.15 | 1463.67 | 168.48 | Tas Quote -2439-2-2 rev1 | 1463.67 | 168.48 | 1632.15 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8f | 77651 | 82129 | Glass Work | Level 26 to 31 | Design-1399-04 | 5 | 23.4 | 1.8 | 1 | 5 | m2-LxW | 210.6 | 2022-10-10 | 2023-03-13 | 0% | 100% | 100% | 22.1429 | 0 | 0.7 | 0 | 3264.3 | 0 | 3264.3 | 2927.34 | 336.96 | Tas Quote -2439-2-2 rev1 | 2927.34 | 336.96 | 3264.3 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8g | 77651 |  | Glass Work | Level 26 | Design-1399-04 | 1 | 22.5 | 2.5 | 9 |  | m3 | 506.25 | 2022-10-10 |  | 0% | 100% | 0% | 23.8571 | 0 | 0.35 | 0 | 4227.19 | 0 | 4227.19 | 3518.44 | 708.75 | Tas Quote -2439-2-2 rev1 | 3518.44 | 708.75 | 4227.19 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1p | 77528 | 82124 | Glass Work | Level 3 to 31 | Design-1399-04 | 1 | 5 | 1.8 | 8.8 | 1 | m2-LxH | 44 | 2022-11-23 | 2023-03-13 | 0% | 100% | 100% | 15.8571 | 0 | 0.77 | 0 | 537.24 | 0 | 537.24 | 459.8 | 77.44 | Tas Quote -2439-2-2 rev1 | 459.8 | 77.44 | 537.24 | 0 | 0 | 0 | 0 | 2588.52 | 2215.4 | 373.12 | 0 | 0 | 0 | 373.12 | 373.12 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 1q | 77528 | 82124 | Glass Work | Level 3 to 31 | Design-1399-04 | 1 | 7 | 2.75 | 1 | 1 | m2-LxW | 19.25 | 2022-11-23 | 2023-03-13 | 0% | 100% | 100% | 15.8571 | 0 | 6.72 | 0 | 2051.28 | 0 | 2051.28 | 1755.6 | 295.68 | Tas Quote -2439-2-2 rev1 | 1755.6 | 295.68 | 2051.28 | 0 | 0 | 0 | 0 | 2588.52 | 2215.4 | 373.12 | 0 | 0 | 0 | 373.12 | 373.12 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 | 79897-82142 | Glass Work | Level 26 | Design-1399-04 | 1 | 152.4 | 1 | 1 |  | lm | 152.4 | 2022-10-10 | 2023-03-24 | 0% | 100% | 100% | 23.7143 | 0 | 1.4 | 0 | 5059.68 | 0 | 5059.68 | 4236.72 | 822.96 | Tas Quote -2439-2-2 rev1 | 4236.72 | 822.96 | 5059.68 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 | 79897-82142 | Glass Work | Level 26 | Sheeting | 1 | 280.8 | 1 | 1 |  | m2-LxH | 280.8 | 2022-10-10 | 2023-03-24 | 0% | 100% | 100% | 23.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8 | 77651 | 79897-82142 | Glass Work | Level 26 | Hilti | 1 | 80 | 1 | 1 |  | lm | 80 | 2022-10-10 | 2023-03-24 | 0% | 100% | 100% | 23.7143 | 0 | 17.15 | 0 | 32536 | 0 | 32536 | 27244 | 5292 | Tas Quote -2439-2-2 rev1 | 27244 | 5292 | 32536 | 0 | 0 | 0 | 0 | 72404.55 | 60886.69 | 11517.86 | 0 | 0 | 0 | 11517.86 | 11517.86 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 8l | 77660 | 79897-82142 | Glass Lifting Frame | Level 26 | Design-1399-04 | 1 | 6 | 1 | 1 |  | lm | 6 | 2022-10-10 | 2023-03-24 | 0% | 100% | 100% | 23.7143 | 0 | 1.4 | 0 | 199.2 | 0 | 199.2 | 166.8 | 32.4 | Tas Quote -2439-2-2 rev1 | 166.8 | 32.4 | 199.2 | 0 | 0 | 0 | 0 | 199.2 | 166.8 | 32.4 | 0 | 0 | 0 | 32.4 | 32.4 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 2 | 74661 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 21.1 | 9 | 9.2 | 1 | m3 | 1747.08 | 2022-09-22 |  | 0% | 100% | 0% | 26.4286 | 0 | 0.49 | 0 | 22624.69 | 0 | 22624.69 | 19200.41 | 3424.28 | Tas Quote -2439-2-2 rev1 | 19200.41 | 3424.28 | 22624.69 | 0 | 0 | 0 | 0 | 22624.69 | 19200.41 | 3424.28 | 0 | 0 | 0 | 3424.28 | 3424.28 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 29 | Design -1399-05 | 1 | 22.9 | 3.4 | 14 | 1 | m3 | 1090.04 | 2022-09-27 |  | 0% | 100% | 0% | 25.7143 | 0 | 0.49 | 0 | 13734.5 | 0 | 13734.5 | 11598.03 | 2136.47 | Tas Quote -2439-2-2 rev1 | 11598.03 | 2136.47 | 13734.5 | 0 | 0 | 0 | 0 | 46252.22 | 39057.43 | 7194.79 | 0 | 0 | 0 | 7194.79 | 7194.79 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 22.9 | 7.2 | 7.5 | 1 | m3 | 1236.6 | 2022-09-27 |  | 0% | 100% | 0% | 25.7143 | 0 | 0.49 | 0 | 15581.16 | 0 | 15581.16 | 13157.42 | 2423.74 | Tas Quote -2439-2-2 rev1 | 13157.42 | 2423.74 | 15581.16 | 0 | 0 | 0 | 0 | 46252.22 | 39057.43 | 7194.79 | 0 | 0 | 0 | 7194.79 | 7194.79 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | Design -1399-05 | 1 | 72 | 11 | 1 |  | lm | 72 | 2022-09-27 |  | 0% | 100% | 0% | 25.7143 | 0 | 1.4 | 0 | 2592 | 0 | 2592 | 2188.8 | 403.2 | Tas Quote -2439-2-2 rev1 | 2188.8 | 403.2 | 2592 | 0 | 0 | 0 | 0 | 46252.22 | 39057.43 | 7194.79 | 0 | 0 | 0 | 7194.79 | 7194.79 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3 | 74667 |  | Ceiling Work | Level 30 | H20 Beam - Bottom | 1 | 22.9 | 2.4 | 1 |  | m3 | 54.96 | 2022-09-27 |  | 0% | 100% | 0% | 25.7143 | 0 | 10.15 | 0 | 14344.56 | 0 | 14344.56 | 12113.18 | 2231.38 | Tas Quote -2439-2-2 rev1 | 12113.18 | 2231.38 | 14344.56 | 0 | 0 | 0 | 0 | 46252.22 | 39057.43 | 7194.79 | 0 | 0 | 0 | 7194.79 | 7194.79 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 10 | 74681 |  | Back Propping | Level 28 | Design - 1399-15 | 1 | 24.7 | 1.3 | 4.2 | 1 | m2-LxH | 103.74 | 2022-10-12 |  | 0% | 100% | 0% | 23.5714 | 0 | 0.49 | 0 | 1198.2 | 0 | 1198.2 | 994.87 | 203.33 | Tas Quote -2439-2-2 rev1 | 994.87 | 203.33 | 1198.2 | 0 | 0 | 0 | 0 | 8880.52 | 7373.52 | 1507 | 0 | 0 | 0 | 1507 | 1507 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 10 | 74681 |  | Back Propping | Level 28 | H20 Beam - Bottom | 1 | 24.7 | 1.3 | 1 |  | m3 | 32.11 | 2022-10-12 |  | 0% | 100% | 0% | 23.5714 | 0 | 10.15 | 0 | 7682.32 | 0 | 7682.32 | 6378.65 | 1303.67 | Tas Quote -2439-2-2 rev1 | 6378.65 | 1303.67 | 7682.32 | 0 | 0 | 0 | 0 | 8880.52 | 7373.52 | 1507 | 0 | 0 | 0 | 1507 | 1507 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 9 | 74680 |  | Back Propping | Level 29 | Design -1399-16 | 1 | 18.8 | 3.6 | 4.7 |  | m3 | 318.1 | 2022-10-12 |  | 0% | 100% | 0% | 23.5714 | 0 | 0.49 | 0 | 3674.06 | 0 | 3674.06 | 3050.58 | 623.48 | Tas Quote -2439-2-2 rev1 | 3050.58 | 623.48 | 3674.06 | 0 | 0 | 0 | 0 | 19866.5 | 16495.21 | 3371.29 | 0 | 0 | 0 | 3371.29 | 3371.29 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 9 | 74680 |  | Back Propping | Level 29 | H20 Beam - Bottom | 1 | 18.8 | 3.6 | 1 |  | m3 | 67.68 | 2022-10-12 |  | 0% | 100% | 0% | 23.5714 | 0 | 10.15 | 0 | 16192.44 | 0 | 16192.44 | 13444.63 | 2747.81 | Tas Quote -2439-2-2 rev1 | 13444.63 | 2747.81 | 16192.44 | 0 | 0 | 0 | 0 | 19866.5 | 16495.21 | 3371.29 | 0 | 0 | 0 | 3371.29 | 3371.29 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 108 | 77542 |  | Canal side Balcony Back Propping | Level 27 to 28 | Design -1399-28 | 1 | 12.6 | 1.3 | 8.8 | 1 | m2-LxH | 110.88 | 2022-11-30 |  | 0% | 100% | 0% | 16.5714 | 0 | 0.49 | 0 | 900.35 | 0 | 900.35 | 683.02 | 217.33 | Tas Quote -2439-2-2 rev1 | 683.02 | 217.33 | 900.35 | 0 | 0 | 0 | 0 | 3655.47 | 2773.11 | 882.36 | 0 | 0 | 0 | 882.36 | 882.36 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 108 | 77542 |  | Canal side Balcony Back Propping | Level 27 to 28 | H20 Beam - Bottom | 1 | 12.6 | 1.3 | 1 |  | m3 | 16.38 | 2022-11-30 |  | 0% | 100% | 0% | 16.5714 | 0 | 10.15 | 0 | 2755.12 | 0 | 2755.12 | 2090.09 | 665.03 | Tas Quote -2439-2-2 rev1 | 2090.09 | 665.03 | 2755.12 | 0 | 0 | 0 | 0 | 3655.47 | 2773.11 | 882.36 | 0 | 0 | 0 | 882.36 | 882.36 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77543 |  | Canal side Balcony Back Propping | Level 27 | Design -1399-28 | 1 | 3.6 | 1.8 | 3 |  | m2-LxH | 10.8 | 2022-11-30 |  | 0% | 100% | 0% | 16.5714 | 0 | 0.49 | 0 | 87.7 | 0 | 87.7 | 66.53 | 21.17 | Tas Quote -2439-2-2 rev1 | 66.53 | 21.17 | 87.7 | 0 | 0 | 0 | 0 | 87.7 | 66.53 | 21.17 | 0 | 0 | 0 | 21.17 | 21.17 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77542 |  | Canal side Balcony Back Propping | Level 27 | H20 Beam - Bottom | 1 | 3.6 | 1.3 | 1 |  | m3 | 4.68 | 2022-11-30 |  | 0% | 0% | 0% | 16.5714 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3655.47 | 2773.11 | 882.36 | 0 | 0 | 0 | 882.36 | 882.36 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 109&a | 77542 |  | Canal side Balcony Back Propping | Level 27 | H20 Beam - Bottom | 1 | 3.6 | 1.8 | 1 |  | m3 | 6.48 | 2022-11-30 |  | 0% | 0% | 0% | 16.5714 | 0 | 10.15 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote -2439-2-2 rev1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3655.47 | 2773.11 | 882.36 | 0 | 0 | 0 | 882.36 | 882.36 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 | 82118 | Canopy Work | Level 31 | Design -1399 -19 | 1 | 11 | 3.5 | 1 | 1 | m2-LxW | 38.5 | 2022-12-14 | 2023-03-18 | 0% | 100% | 100% | 13.5714 | 0 | 8.61 | 0 | 4498.73 | 0 | 4498.73 | 3504.27 | 994.46 | Tas Quote -2439-2-2 rev1 | 3504.27 | 994.46 | 4498.73 | 0 | 0 | 0 | 0 | 8896.09 | 6929.58 | 1966.51 | 0 | 0 | 0 | 1966.51 | 1966.51 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 | 82118 | Canopy Work | Level 31 | Design -1399 -19 | 6 | 10.8 | 1 | 1 |  | lm | 64.8 | 2022-12-14 | 2023-03-18 | 0% | 100% | 100% | 13.5714 | 0 | 1.4 | 0 | 1231.2 | 0 | 1231.2 | 959.04 | 272.16 | Tas Quote -2439-2-2 rev1 | 959.04 | 272.16 | 1231.2 | 0 | 0 | 0 | 0 | 8896.09 | 6929.58 | 1966.51 | 0 | 0 | 0 | 1966.51 | 1966.51 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 | 82118 | Canopy Work | Level 31 | Design -1399 -19 | 12 | 6 | 1 | 1 |  | lm | 72 | 2022-12-14 | 2023-03-18 | 0% | 100% | 100% | 13.5714 | 0 | 1.4 | 0 | 1368 | 0 | 1368 | 1065.6 | 302.4 | Tas Quote -2439-2-2 rev1 | 1065.6 | 302.4 | 1368 | 0 | 0 | 0 | 0 | 8896.09 | 6929.58 | 1966.51 | 0 | 0 | 0 | 1966.51 | 1966.51 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3e | 79142 | 82118 | Canopy Work | Level 31 | Design -1399 -19 | 1 | 8 | 2.6 | 1 |  | m2-LxW | 20.8 | 2022-12-14 | 2023-03-18 | 0% | 100% | 100% | 13.5714 | 0 | 6.37 | 0 | 1798.16 | 0 | 1798.16 | 1400.67 | 397.49 | Tas Quote -2439-2-2 rev1 | 1400.67 | 397.49 | 1798.16 | 0 | 0 | 0 | 0 | 8896.09 | 6929.58 | 1966.51 | 0 | 0 | 0 | 1966.51 | 1966.51 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 | 82120 | Canopy Work | Level 31 to 32 | Design -1399 -19 | 6 | 10.8 | 1 | 1 |  | lm | 64.8 | 2022-12-07 | 2023-03-16 | 0% | 100% | 100% | 14.2857 | 0 | 1.4 | 0 | 1296 | 0 | 1296 | 1049.76 | 246.24 | Tas Quote -2439-2-2 rev1 | 1049.76 | 246.24 | 1296 | 0 | 0 | 0 | 0 | 11628.8 | 9419.33 | 2209.47 | 0 | 0 | 0 | 2209.47 | 2209.47 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 | 82120 | Canopy Work | Level 31 to 32 | Design -1399 -19 | 1 | 8 | 5 | 1 |  | m2-LxW | 40 | 2022-12-07 | 2023-03-16 | 0% | 100% | 100% | 14.2857 | 0 | 12.25 | 0 | 7000 | 0 | 7000 | 5670 | 1330 | Tas Quote -2439-2-2 rev1 | 5670 | 1330 | 7000 | 0 | 0 | 0 | 0 | 11628.8 | 9419.33 | 2209.47 | 0 | 0 | 0 | 2209.47 | 2209.47 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 | 82120 | Canopy Work | Level 31 to 32 | Design -1399 -19 | 12 | 6 | 1 | 1 |  | lm | 72 | 2022-12-07 | 2023-03-16 | 0% | 100% | 100% | 14.2857 | 0 | 1.4 | 0 | 1440 | 0 | 1440 | 1166.4 | 273.6 | Tas Quote -2439-2-2 rev1 | 1166.4 | 273.6 | 1440 | 0 | 0 | 0 | 0 | 11628.8 | 9419.33 | 2209.47 | 0 | 0 | 0 | 2209.47 | 2209.47 | 0
CONTRACT - 201A22002/49 | RESIDENCE | 3c | 79108 | 82120 | Canopy Work | Level 31 to 32 | Design -1399 -19 | 1 | 8 | 2.6 | 1 |  | m2-LxW | 20.8 | 2022-12-07 | 2023-03-16 | 0% | 100% | 100% | 14.2857 | 0 | 6.37 | 0 | 1892.8 | 0 | 1892.8 | 1533.17 | 359.63 | Tas Quote -2439-2-2 rev1 | 1533.17 | 359.63 | 1892.8 | 0 | 0 | 0 | 0 | 11628.8 | 9419.33 | 2209.47 | 0 | 0 | 0 | 2209.47 | 2209.47 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1b | 74653 | 76751 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 25.2 | 1.2 | 1 | 1 | m2-LxW | 30.24 | 2022-09-20 | 2022-09-26 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 773.06 | 88.91 | 331.31 | 1193.28 | 1193.28 | 0 |  | 1193.28 | 0 | 1193.28 | 0 | 773.06 | 773.06 | 0 | 88.91 | 88.91 | 0 | 331.31 | 331.31 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1f | 74654 | 82139 | Glass Channel Fixing | Level 29 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.5 | 1 | 1 | m2-LxW | 2.5 | 2022-09-20 | 2023-03-24 | 100% | 100% | 100% | 26.5714 | 32.75 | 1.05 | 57.31 | 69.75 | 24.56 | 151.62 | 116.94 | 34.68 |  | 116.94 | 34.68 | 151.62 | 0 | 57.31 | 57.31 | 0 | 69.75 | 59.63 | 10.12 | 24.56 | 0 | 24.56 | 34.68 | 34.68 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1h | 74655 | 76752 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 | 1 | 1 | m2-LxW | 8.1 | 2022-09-21 | 2022-09-27 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 185.69 | 8.51 | 79.58 | 273.78 | 273.78 | 0 |  | 273.78 | 0 | 273.78 | 0 | 185.69 | 185.69 | 0 | 8.51 | 8.51 | 0 | 79.58 | 79.58 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1i | 74660 | 76753 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-09-24 | 2022-09-26 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 46.02 | 2.27 | 19.72 | 68.01 | 68.01 | 0 |  | 68.01 | 0 | 68.01 | 0 | 46.02 | 46.02 | 0 | 2.27 | 2.27 | 0 | 19.72 | 19.72 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1j | 74666 | 76754 | Glass Channel Fixing | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 23.4 | 0.75 | 1 | 1 | m2-LxW | 17.55 | 2022-09-26 | 2022-09-28 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 448.65 | 22.11 | 192.28 | 663.04 | 663.04 | 0 |  | 663.04 | 0 | 663.04 | 0 | 448.65 | 448.65 | 0 | 22.11 | 22.11 | 0 | 192.28 | 192.28 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1k | 74670 | 82126 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 2 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 9.8 | 2022-09-28 | 2023-03-22 | 100% | 100% | 100% | 25.1429 | 32.75 | 1.05 | 224.67 | 258.72 | 96.29 | 579.68 | 446.64 | 133.04 |  | 446.64 | 133.04 | 579.68 | 0 | 224.67 | 224.67 | 0 | 258.72 | 221.97 | 36.75 | 96.29 | 0 | 96.29 | 133.04 | 133.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1l | 74671 | 79900 | Glass Channel Fixing | Level 30 | Cantilever (0 < 0.5m width) | 1 | 13.8 | 0.5 | 1 | 1 | m2-LxW | 6.9 | 2022-09-28 | 2023-03-15 | 100% | 100% | 100% | 24.1429 | 32.75 | 1.05 | 158.18 | 174.92 | 67.79 | 400.89 | 314.47 | 86.42 |  | 314.47 | 86.42 | 400.89 | 0 | 158.18 | 158.18 | 0 | 174.92 | 156.29 | 18.63 | 67.79 | 0 | 67.79 | 86.42 | 86.42 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2a | 74662 |  | Glass Channel Fixing | Level 30 | Additional Boarding | 4 | 10.8 | 1.8 | 1 | 4 | m2-LxW | 77.76 | 2022-09-22 |  | 100% | 100% | 0% | 26.4286 | 6.63 | 0.7 | 360.88 | 1438.56 | 0 | 1799.44 | 1581.71 | 217.73 |  | 1581.71 | 217.73 | 1799.44 | 0 | 360.88 | 360.88 | 0 | 1438.56 | 1220.83 | 217.73 | 0 | 0 | 0 | 217.73 | 217.73 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2b | 74663 | 76758 | Colum G-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 468.12 | 0 | 240.59 | 240.59 | 0 | 124.42 | 124.42 | 0 | 103.11 | 103.11 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2c | 74664 | 76759 | Colum F-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 468.12 | 0 | 240.59 | 240.59 | 0 | 124.42 | 124.42 | 0 | 103.11 | 103.11 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2d | 74665 | 76760 | Colum D-3 Painting Works | Level 30 | Additional Boarding | 4 | 3.6 | 3.6 | 1 | 4 | m2-LxW | 51.84 | 2022-09-22 | 2022-10-15 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 240.59 | 124.42 | 103.11 | 468.12 | 468.12 | 0 |  | 468.12 | 0 | 468.12 | 0 | 240.59 | 240.59 | 0 | 124.42 | 124.42 | 0 | 103.11 | 103.11 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3a | 74668 | 76761 | Colum D-2 Painting Works | Level 29 | Additional Boarding | 6 | 3.5 | 3.5 | 1 | 6 | m2-LxW | 73.5 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 341.11 | 139.65 | 146.19 | 626.95 | 626.95 | 0 |  | 626.95 | 0 | 626.95 | 0 | 341.11 | 341.11 | 0 | 139.65 | 139.65 | 0 | 146.19 | 146.19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3b | 74669 | 76762 | Colum F-G/2 Painting Works | Level 29 | Additional Boarding | 6 | 9 | 3.5 | 1 | 6 | m2-LxW | 189 | 2022-09-27 | 2022-10-15 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 877.15 | 359.1 | 375.92 | 1612.17 | 1612.17 | 0 |  | 1612.17 | 0 | 1612.17 | 0 | 877.15 | 877.15 | 0 | 359.1 | 359.1 | 0 | 375.92 | 375.92 | 0 | 0 | 0 | 0
E11/K149/SK/dm/239 | RESIDENCE | 4 | 74673 | 76788 | EIFS Removel & Reinstate Works | Ramp | Design-1399-07 rev-B | 1 |  |  |  |  | unit | 1 | 2022-10-01 | 2022-11-05 | 100% | 100% | 100% | 5.1429 | 15626.48 | 625.97 | 10938.54 | 3219.27 | 4687.94 | 18845.75 | 18845.75 | 0 | Tas Quote - 2439-8-2 | 18845.75 | 0 | 18845.75 | 0 | 10938.54 | 10938.54 | 0 | 3219.27 | 3219.27 | 0 | 4687.94 | 4687.94 | 0 | 0 | 0 | 0
E11/K149/SK/dm/238 | RESIDENCE | 5 | 74675 | 76768 | Level -30 Lobby Room Shaft-09 | Level 30 | Design -1399-10 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-03 | 2022-10-22 | 100% | 100% | 100% | 2.8571 | 5727.13 | 317.71 | 4008.99 | 907.74 | 1718.14 | 6634.87 | 6634.87 | 0 | Tas Quote - 2439-5-1 | 6634.87 | 0 | 6634.87 | 0 | 4008.99 | 4008.99 | 0 | 907.74 | 907.74 | 0 | 1718.14 | 1718.14 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2e | 74676 | 76755 | Level - 30 Balcony Side Glass frame work | Level 30 | Additional Boarding | 1 | 3.6 | 1.8 | 1 | 1 | m2-LxW | 6.48 | 2022-10-04 | 2022-10-07 | 100% | 100% | 100% | 0.57143 | 6.63 | 0.7 | 30.07 | 2.59 | 12.89 | 45.55 | 45.55 | 0 |  | 45.55 | 0 | 45.55 | 0 | 30.07 | 30.07 | 0 | 2.59 | 2.59 | 0 | 12.89 | 12.89 | 0 | 0 | 0 | 0
E11/K149/HN/dm/285 | RESIDENCE | 6 | 74677 | 80851 | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-10 | 2023-01-02 | 100% | 100% | 100% | 12.1429 | 4959.77 | 123.48 | 3471.84 | 1499.4 | 1487.93 | 6459.17 | 6459.17 | 0 | Tas Quote - 2439-10-1 | 6459.17 | 0 | 6459.17 | 0 | 3471.84 | 3471.84 | 0 | 1499.4 | 1499.4 | 0 | 1487.93 | 1487.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 7 | 74678 | 80573 | Level -4 Planter Box Soil Filling | Level 4 | Independent | 1 | 15 | 1.5 | 0.8 | 1 | m2-LxH | 12 | 2022-10-10 | 2022-12-16 | 100% | 100% | 100% | 9.7143 | 12.01 | 0.49 | 100.88 | 57.12 | 43.24 | 201.24 | 201.24 | 0 |  | 201.24 | 0 | 201.24 | 0 | 100.88 | 100.88 | 0 | 57.12 | 57.12 | 0 | 43.24 | 43.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8h | 74679 | 76756 | Pool Area Glass work | Level 26 | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-10-10 | 2022-10-11 | 100% | 100% | 100% | 0.28571 | 6.63 | 0.7 | 18.56 | 0.8 | 7.96 | 27.32 | 27.32 | 0 |  | 27.32 | 0 | 27.32 | 0 | 18.56 | 18.56 | 0 | 0.8 | 0.8 | 0 | 7.96 | 7.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8i | 74682 | 82116 | Level -30 Glass Frame work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 19 | 0.75 | 1 | 1 | m2-LxW | 14.25 | 2022-10-12 | 2023-03-15 | 100% | 100% | 100% | 22.1429 | 36.52 | 2.94 | 364.29 | 927.68 | 156.12 | 1448.09 | 1184.24 | 263.85 |  | 1184.24 | 263.85 | 1448.09 | 0 | 364.29 | 364.29 | 0 | 927.68 | 819.95 | 107.73 | 156.12 | 0 | 156.12 | 263.85 | 263.85 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8j | 74683 | 76764 | Level -30 Glass Frame work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 19.8 | 0.5 | 1 | 1 | m2-LxW | 9.9 | 2022-10-12 | 2022-10-21 | 100% | 100% | 100% | 1.4286 | 32.75 | 1.05 | 226.96 | 14.85 | 97.27 | 339.08 | 339.08 | 0 |  | 339.08 | 0 | 339.08 | 0 | 226.96 | 226.96 | 0 | 14.85 | 14.85 | 0 | 97.27 | 97.27 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 11 | 74684 | 76757 | Level -30 Shaft Mep Services | Level 30 | Independent | 1 | 3.6 | 1.2 | 2.5 | 1 | m2-LxH | 9 | 2022-10-13 | 2022-10-15 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 75.66 | 1.89 | 32.43 | 109.98 | 109.98 | 0 |  | 109.98 | 0 | 109.98 | 0 | 75.66 | 75.66 | 0 | 1.89 | 1.89 | 0 | 32.43 | 32.43 | 0 | 0 | 0 | 0
E11/K149/HN/dm/285 | RESIDENCE | 12 | 74685 | 80889 | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-14 | 2023-01-17 | 100% | 100% | 100% | 13.7143 | 4959.77 | 123.48 | 3471.84 | 1693.44 | 1487.93 | 6653.21 | 6653.21 | 0 | Tas Quote - 2439-10-1 | 6653.21 | 0 | 6653.21 | 0 | 3471.84 | 3471.84 | 0 | 1693.44 | 1693.44 | 0 | 1487.93 | 1487.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 13 | 74686 | 80503 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 7.3 | 1.3 | 1.7 | 1 | m2-LxH | 12.41 | 2022-10-14 | 2022-11-10 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 104.33 | 24.32 | 44.71 | 173.36 | 173.36 | 0 | KMEP | 173.36 | 0 | 173.36 | 0 | 104.33 | 104.33 | 0 | 24.32 | 24.32 | 0 | 44.71 | 44.71 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 14 | 74687 | 76763 | Colum Nut bolt Installation | Level 3 | Independent | 1 | 5.1 | 1.3 | 1.6 | 1 | m2-LxH | 8.16 | 2022-10-15 | 2022-10-17 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 68.6 | 1.71 | 29.4 | 99.71 | 99.71 | 0 |  | 99.71 | 0 | 99.71 | 0 | 68.6 | 68.6 | 0 | 1.71 | 1.71 | 0 | 29.4 | 29.4 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 15 | 74688 | 80504 | Pool Plant Room (KMEP Work) | Level 3 | Independent | 1 | 5 | 1.2 | 2 | 1 | m2-LxH | 10 | 2022-10-17 | 2022-11-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 84.07 | 17.5 | 36.03 | 137.6 | 137.6 | 0 | KMEP | 137.6 | 0 | 137.6 | 0 | 84.07 | 84.07 | 0 | 17.5 | 17.5 | 0 | 36.03 | 36.03 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Tower | 1 | 2.5 | 1.8 | 2.3 | 1 | rm | 2.3 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 101.98 | 14.35 | 43.7 | 160.03 | 160.03 | 0 | KMEP | 160.03 | 0 | 160.03 | 0 | 122.86 | 122.86 | 0 | 17.05 | 17.05 | 0 | 52.65 | 52.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16 | 74689 | 76766 | Shaft -6 Kmep Duct Extension | Level 31 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-10-17 | 2022-10-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 20.88 | 2.7 | 8.95 | 32.53 | 32.53 | 0 | KMEP | 32.53 | 0 | 32.53 | 0 | 122.86 | 122.86 | 0 | 17.05 | 17.05 | 0 | 52.65 | 52.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 17 | 74690 | 76769 | Level -2 Retail Unit 34 For (Kmep) | Level 2 | Birdcage | 1 | 17.5 | 10 | 6.2 | 1 | m3 | 1085 | 2022-10-18 | 2022-10-26 | 100% | 100% | 100% | 1.2857 | 7.08 | 0.49 | 5377.26 | 683.55 | 2304.54 | 8365.35 | 8365.35 | 0 | KMEP | 8365.35 | 0 | 8365.35 | 0 | 5377.26 | 5377.26 | 0 | 683.55 | 683.55 | 0 | 2304.54 | 2304.54 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 18 | 74691 | 80506 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-18 | 2022-11-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 110.85 | 67.6 | 47.51 | 225.96 | 225.96 | 0 | KMEP | 225.96 | 0 | 225.96 | 0 | 110.85 | 110.85 | 0 | 67.6 | 67.6 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19 | 74692 | 80535 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 6.3 | 1 | m2-LxH | 25.2 | 2022-10-18 | 2022-11-28 | 100% | 100% | 100% | 6 | 12.01 | 0.49 | 211.86 | 74.09 | 90.8 | 376.75 | 376.75 | 0 |  | 376.75 | 0 | 376.75 | 0 | 211.86 | 211.86 | 0 | 74.09 | 74.09 | 0 | 90.8 | 90.8 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19a | 74700 | 76793 | Staircase -4 For Water coring tank work | Level 31 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2022-10-19 | 2022-11-05 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 67.26 | 10.08 | 28.82 | 106.16 | 106.16 | 0 |  | 106.16 | 0 | 106.16 | 0 | 67.26 | 67.26 | 0 | 10.08 | 10.08 | 0 | 28.82 | 28.82 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 20 | 74693 | 80515 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-10-18 | 2022-11-15 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 133.01 | 90.48 | 57.01 | 280.5 | 280.5 | 0 |  | 280.5 | 0 | 280.5 | 0 | 133.01 | 133.01 | 0 | 90.48 | 90.48 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 16a | 74694 | 76767 | Second Lift Duct Extension work | Level 31 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-10-22 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 135 | 0 | 135 | 0 | 88.68 | 88.68 | 0 | 8.32 | 8.32 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1n | 74695 | 76771 | Fire Fifhting Sprinkler Work | Level 31 | Additional Boarding | 1 | 11.5 | 1.8 | 1 | 1 | m2-LxW | 20.7 | 2022-10-19 | 2022-10-26 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 96.07 | 16.56 | 41.17 | 153.8 | 153.8 | 0 |  | 153.8 | 0 | 153.8 | 0 | 96.07 | 96.07 | 0 | 16.56 | 16.56 | 0 | 41.17 | 41.17 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 21 | 74696 | 76792 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3 | 1 | rm | 3 | 2022-10-19 | 2022-11-07 | 100% | 100% | 100% | 2.8571 | 63.34 | 7.28 | 133.01 | 62.4 | 57.01 | 252.42 | 252.42 | 0 | KMEP | 252.42 | 0 | 252.42 | 0 | 133.01 | 133.01 | 0 | 62.4 | 62.4 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 22 | 74697 | 76776 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 3.1 | 1.3 | 3 | 1 | m2-LxH | 9.3 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 78.19 | 9.77 | 33.51 | 121.47 | 121.47 | 0 | KMEP | 121.47 | 0 | 121.47 | 0 | 78.19 | 78.19 | 0 | 9.77 | 9.77 | 0 | 33.51 | 33.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 23 | 74698 | 80538 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.1 | 1.8 | 4.5 | 1 | m2-LxH | 13.95 | 2022-10-19 | 2022-11-26 | 100% | 100% | 100% | 5.5714 | 12.01 | 0.77 | 117.28 | 59.85 | 50.26 | 227.39 | 227.39 | 0 | KMEP | 227.39 | 0 | 227.39 | 0 | 117.28 | 117.28 | 0 | 59.85 | 59.85 | 0 | 50.26 | 50.26 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 24 | 74699 | 80516 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2022-10-19 | 2022-11-15 | 100% | 100% | 100% | 4 | 63.34 | 7.28 | 199.52 | 131.04 | 85.51 | 416.07 | 416.07 | 0 | KMEP | 416.07 | 0 | 416.07 | 0 | 199.52 | 199.52 | 0 | 131.04 | 131.04 | 0 | 85.51 | 85.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 25 | 77652 | 76777 | Basement 1 (Kmep work) | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-10-19 | 2022-11-02 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 200.62 | 28.22 | 85.98 | 314.82 | 314.82 | 0 | KMEP | 314.82 | 0 | 314.82 | 0 | 200.62 | 200.62 | 0 | 28.22 | 28.22 | 0 | 85.98 | 85.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8k | 77653 | 76775 | Glass Channel Fixing | Level 31 | Cantilever (0 < 0.5m width) | 1 | 18 | 0.5 | 1 | 1 | m2-LxW | 9 | 2022-10-19 | 2022-10-29 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 206.33 | 14.85 | 88.43 | 309.61 | 309.61 | 0 |  | 309.61 | 0 | 309.61 | 0 | 206.33 | 206.33 | 0 | 14.85 | 14.85 | 0 | 88.43 | 88.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 26 | 77654 | 80501 | Mockup For Bracket Fixing | Level 6 | Tower | 1 | 1.8 | 1 | 2 | 1 | rm | 2 | 2022-10-19 | 2022-11-04 | 100% | 100% | 100% | 2.4286 | 63.34 | 7.28 | 88.68 | 35.36 | 38 | 162.04 | 162.04 | 0 |  | 162.04 | 0 | 162.04 | 0 | 88.68 | 88.68 | 0 | 35.36 | 35.36 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 27 | 77655 | 80525 | Basement 1 (Kmep work) | Basement 1 | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2022-10-19 | 2022-11-16 | 100% | 100% | 100% | 4.1429 | 12.01 | 0.49 | 189.16 | 45.68 | 81.07 | 315.91 | 315.91 | 0 | KMEP | 315.91 | 0 | 315.91 | 0 | 189.16 | 189.16 | 0 | 45.68 | 45.68 | 0 | 81.07 | 81.07 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 199.52 | 107.64 | 85.51 | 392.67 | 392.67 | 0 | KMEP | 392.67 | 0 | 392.67 | 0 | 220.4 | 220.4 | 0 | 117.99 | 117.99 | 0 | 94.46 | 94.46 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 28 | 77656 | 80507 | Basement 1 (Kmep work) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2022-10-20 | 2022-11-11 | 100% | 100% | 100% | 3.2857 | 6.63 | 0.7 | 20.88 | 10.35 | 8.95 | 40.18 | 40.18 | 0 | KMEP | 40.18 | 0 | 40.18 | 0 | 220.4 | 220.4 | 0 | 117.99 | 117.99 | 0 | 94.46 | 94.46 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 29 | 77657 | 80557 | Basement 1 (Kmep work) | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2022-10-20 | 2022-12-10 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 199.52 | 243.36 | 85.51 | 528.39 | 528.39 | 0 | KMEP | 528.39 | 0 | 528.39 | 0 | 199.52 | 199.52 | 0 | 243.36 | 243.36 | 0 | 85.51 | 85.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2g | 77661 | 76774 | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-21 | 2022-10-29 | 100% | 100% | 100% | 1.2857 | 32.75 | 1.05 | 123.8 | 7.29 | 53.06 | 184.15 | 184.15 | 0 |  | 184.15 | 0 | 184.15 | 0 | 123.8 | 123.8 | 0 | 7.29 | 7.29 | 0 | 53.06 | 53.06 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 2f | 77662 | 82127 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.6 | 0.75 | 1 | 1 | m2-LxW | 2.7 | 2022-10-21 | 2023-03-16 | 100% | 100% | 100% | 21 | 36.52 | 2.94 | 69.02 | 166.7 | 29.58 | 265.3 | 214.17 | 51.13 |  | 214.17 | 51.13 | 265.3 | 0 | 69.02 | 69.02 | 0 | 166.7 | 145.15 | 21.55 | 29.58 | 0 | 29.58 | 51.13 | 51.13 | 0
E11/K149/SK/dm/365 | RESIDENCE | 30 | 77667 | 80865 | EIFS Fixing Work | Level 23 | Independent | 1 | 4 | 1.3 | 2 | 1 | unit | 1 | 2022-10-21 | 2023-01-04 | 100% | 100% | 100% | 10.8571 | 916.08 | 3.92 | 641.26 | 42.56 | 274.82 | 958.64 | 958.64 | 0 | Tas Quote - 2439-14-1 (item-1) | 958.64 | 0 | 958.64 | 0 | 641.26 | 641.26 | 0 | 42.56 | 42.56 | 0 | 274.82 | 274.82 | 0 | 0 | 0 | 0
E11/K149/SK/dm/365 | RESIDENCE | 30a | 77668 | 80867 | EIFS Fixing Work | Level 23 | Independent | 1 | 8 | 1.3 | 3 | 2 | unit | 1 | 2022-10-21 | 2023-01-04 | 100% | 100% | 100% | 10.8571 | 2093.27 | 22.96 | 1465.29 | 249.28 | 627.98 | 2342.55 | 2342.55 | 0 | Tas Quote - 2439-14-1 (item-2) | 2342.55 | 0 | 2342.55 | 0 | 1465.29 | 1465.29 | 0 | 249.28 | 249.28 | 0 | 627.98 | 627.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/350 | RESIDENCE | 31 | 77669 | 82105 | Above Air Extract trench Loading Bay | Ground Level | Design 1399-14 | 1 | 22.5 | 3.6 |  | 1 | unit | 1 | 2022-10-21 | 2023-03-18 | 100% | 100% | 100% | 21.2857 | 13343.06 | 660.1 | 9340.14 | 14050.7 | 4002.92 | 27393.76 | 21410.54 | 5983.22 | Tas Quote - 2439-13-1 | 21410.54 | 5983.22 | 27393.76 | 0 | 9340.14 | 9340.14 | 0 | 14050.7 | 12070.4 | 1980.3 | 4002.92 | 0 | 4002.92 | 5983.22 | 5983.22 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 121.06 | 13.1 | 51.88 | 186.04 | 186.04 | 0 |  | 186.04 | 0 | 186.04 | 0 | 142.78 | 142.78 | 0 | 19.18 | 19.18 | 0 | 61.19 | 61.19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32 | 77663 | 76779 | Hotel Side Block Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 | 1 | 1 | m2-LxW | 4.68 | 2022-10-22 | 2022-11-03 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 21.72 | 6.08 | 9.31 | 37.11 | 37.11 | 0 |  | 37.11 | 0 | 37.11 | 0 | 142.78 | 142.78 | 0 | 19.18 | 19.18 | 0 | 61.19 | 61.19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 33 | 77664 | 76772 | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 | 2022-10-27 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 44.34 | 6.24 | 19 | 69.58 | 69.58 | 0 |  | 69.58 | 0 | 69.58 | 0 | 44.34 | 44.34 | 0 | 6.24 | 6.24 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 34 | 77665 | 80871 | Canal Side wall Cladding opening Work | Level 14 | Tower | 1 | 1.8 | 1.3 | 1 | 1 | rm | 1 | 2022-10-22 | 2023-01-06 | 100% | 100% | 100% | 11 | 63.34 | 7.28 | 44.34 | 80.08 | 19 | 143.42 | 143.42 | 0 |  | 143.42 | 0 | 143.42 | 0 | 44.34 | 44.34 | 0 | 80.08 | 80.08 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 4d | 77670 | 76786 | EIFS work | Ground Level to Level 2 | Additional Boarding | 3 | 1.8 | 1.8 | 1 | 3 | m2-LxW | 9.72 | 2022-10-25 | 2022-11-05 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 45.11 | 11.66 | 19.33 | 76.1 | 76.1 | 0 |  | 76.1 | 0 | 76.1 | 0 | 45.11 | 45.11 | 0 | 11.66 | 11.66 | 0 | 19.33 | 19.33 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 2 | 74603 | 76828 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 4.9 | 1.8 | 4.2 | 1 | m2-LxH | 20.58 | 2022-10-04 | 2022-11-21 | 100% | 100% | 100% | 7 | 16.76 | 0.77 | 241.44 | 110.93 | 103.48 | 455.85 | 455.85 | 0 |  | 455.85 | 0 | 455.85 | 0 | 241.44 | 241.44 | 0 | 110.93 | 110.93 | 0 | 103.48 | 103.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 2a | 74604 | 79921 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 15.1 | 1.8 | 4.2 | 1 | m2-LxH | 63.42 | 2022-10-05 | 2023-03-06 | 100% | 100% | 100% | 21.8571 | 16.76 | 0.77 | 744.04 | 1067.36 | 318.88 | 2130.28 | 1748.61 | 381.67 |  | 1748.61 | 381.67 | 2130.28 | 0 | 744.04 | 744.04 | 0 | 1067.36 | 1004.57 | 62.79 | 318.88 | 0 | 318.88 | 381.67 | 381.67 | 4.5475e-13
E11/K149/SK/dm/213 | HOTEL | 2b | 74605 | 80819 | Plant Room For AC Duct Work | Level 5 | Additional Boarding | 1 | 6.8 | 1.8 | 1 | 1 | m2-LxW | 12.24 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 6.63 | 0.7 | 56.81 | 94.25 | 24.35 | 175.41 | 175.41 | 0 |  | 175.41 | 0 | 175.41 | 0 | 56.81 | 56.81 | 0 | 94.25 | 94.25 | 0 | 24.35 | 24.35 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 2c | 74606 | 80818 | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 36.52 | 2.94 | 19.17 | 24.26 | 8.22 | 51.65 | 51.65 | 0 |  | 51.65 | 0 | 51.65 | 0 | 19.17 | 19.17 | 0 | 24.26 | 24.26 | 0 | 8.22 | 8.22 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 3 | 74607 | 80820 | Plant Room Façade Fin Supporting work | Level 5 | Independent 1.8m wide | 1 | 7.5 | 1.8 | 4.2 | 1 | m2-LxH | 31.5 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 16.76 | 0.77 | 369.56 | 266.81 | 158.38 | 794.75 | 794.75 | 0 |  | 794.75 | 0 | 794.75 | 0 | 369.56 | 369.56 | 0 | 266.81 | 266.81 | 0 | 158.38 | 158.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 3a | 74608 | 80821 | Plant Room Façade Fin Supporting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 | 1 | 1 | m2-LxW | 1.25 | 2022-10-05 | 2022-12-20 | 100% | 100% | 100% | 11 | 32.75 | 1.05 | 28.66 | 14.44 | 12.28 | 55.38 | 55.38 | 0 |  | 55.38 | 0 | 55.38 | 0 | 28.66 | 28.66 | 0 | 14.44 | 14.44 | 0 | 12.28 | 12.28 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 4 | 74609 | 76802 | Air Extract Gratting Installation | Basement 1 | Independent | 1 | 9.3 | 1.3 | 5.9 | 1 | m2-LxH | 54.87 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 461.29 | 23.05 | 197.7 | 682.04 | 682.04 | 0 |  | 682.04 | 0 | 682.04 | 0 | 461.29 | 461.29 | 0 | 23.05 | 23.05 | 0 | 197.7 | 197.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 4a | 74610 | 76803 | Air Extract Gratting Installation | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 9.8 | 0.5 | 1 | 1 | m2-LxW | 4.9 | 2022-10-07 | 2022-10-12 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 112.33 | 4.41 | 48.14 | 164.88 | 164.88 | 0 |  | 164.88 | 0 | 164.88 | 0 | 112.33 | 112.33 | 0 | 4.41 | 4.41 | 0 | 48.14 | 48.14 | 0 | 0 | 0 | 0
E11/K149/SK/dm/300 | HOTEL | 5 | 74611 | 76801 | Cradle Beam Support | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-07 | 2022-10-10 | 100% | 100% | 100% | 0.57143 | 4033.1 | 49.28 | 2823.17 | 28.16 | 1209.93 | 4061.26 | 4061.26 | 0 | Tas Quote - 2439-11-2 | 4061.26 | 0 | 4061.26 | 0 | 2823.17 | 2823.17 | 0 | 28.16 | 28.16 | 0 | 1209.93 | 1209.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/300 | HOTEL | 6 | 74612 | 76804 | Cradle Beam Support (Re-erction) | Roof | Design 1399-13 rev-A | 1 | 4 | 2.5 | 2 | 1 | unit | 1 | 2022-10-10 | 2022-10-26 | 100% | 100% | 100% | 2.4286 | 4033.1 | 49.28 | 2823.17 | 119.68 | 1209.93 | 4152.78 | 4152.78 | 0 | Tas Quote - 2439-11-2 | 4152.78 | 0 | 4152.78 | 0 | 2823.17 | 2823.17 | 0 | 119.68 | 119.68 | 0 | 1209.93 | 1209.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 7 | 74613 | 76807 | Planter Drain Connection (mep) | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-12 | 2022-11-03 | 100% | 100% | 100% | 3.2857 | 63.34 | 7.28 | 110.85 | 59.8 | 47.51 | 218.16 | 218.16 | 0 |  | 218.16 | 0 | 218.16 | 0 | 110.85 | 110.85 | 0 | 59.8 | 59.8 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 2d | 74614 | 80822 | Planter Room Fin Supportting work | Level 5 | Additional Boarding | 1 | 4.3 | 1.5 | 1 | 1 | m2-LxW | 6.45 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 6.63 | 0.7 | 29.93 | 45.15 | 12.83 | 87.91 | 87.91 | 0 |  | 87.91 | 0 | 87.91 | 0 | 29.93 | 29.93 | 0 | 45.15 | 45.15 | 0 | 12.83 | 12.83 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 3b | 74615 | 80823 | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 3 | 1.8 | 4.2 | 1 | m2-LxH | 12.6 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 16.76 | 0.77 | 147.82 | 97.02 | 63.35 | 308.19 | 308.19 | 0 |  | 308.19 | 0 | 308.19 | 0 | 147.82 | 147.82 | 0 | 97.02 | 97.02 | 0 | 63.35 | 63.35 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 3c | 74616 | 80824 | Planter Room Fin Supportting work | Level 5 | Independent | 1 | 5 | 1.3 | 4.2 | 1 | m2-LxH | 21 | 2022-10-12 | 2022-12-20 | 100% | 100% | 100% | 10 | 12.01 | 0.49 | 176.55 | 102.9 | 75.66 | 355.11 | 355.11 | 0 |  | 355.11 | 0 | 355.11 | 0 | 176.55 | 176.55 | 0 | 102.9 | 102.9 | 0 | 75.66 | 75.66 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 8 | 74617 | 80813 | Planter Room Fin Supportting work | Level 5 | Independent 1.8m wide | 1 | 10.8 | 1.8 | 3.8 | 1 | m2-LxH | 41.04 | 2022-10-13 | 2022-12-20 | 100% | 100% | 100% | 9.8571 | 16.76 | 0.77 | 481.48 | 311.49 | 206.35 | 999.32 | 999.32 | 0 |  | 999.32 | 0 | 999.32 | 0 | 481.48 | 481.48 | 0 | 311.49 | 311.49 | 0 | 206.35 | 206.35 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 8a | 74618 | 80814 | Planter Room Fin Supportting work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-13 | 2022-12-20 | 100% | 100% | 100% | 9.8571 | 32.75 | 1.05 | 123.8 | 55.89 | 53.06 | 232.75 | 232.75 | 0 |  | 232.75 | 0 | 232.75 | 0 | 123.8 | 123.8 | 0 | 55.89 | 55.89 | 0 | 53.06 | 53.06 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 3d | 74619 | 80817 | Plant Room For Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 36.52 | 2.94 | 38.35 | 42.21 | 16.43 | 96.99 | 96.99 | 0 | KMEP | 96.99 | 0 | 96.99 | 0 | 38.35 | 38.35 | 0 | 42.21 | 42.21 | 0 | 16.43 | 16.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 8b | 74620 | 80815 | Plant Room For Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 63.34 | 7.28 | 155.18 | 243.88 | 66.51 | 465.57 | 465.57 | 0 | KMEP | 465.57 | 0 | 465.57 | 0 | 155.18 | 155.18 | 0 | 243.88 | 243.88 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 8c | 74621 | 80816 | Plant Room For Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 4.8 | 0.5 | 1 | 1 | m2-LxW | 2.4 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 32.75 | 1.05 | 55.02 | 24.12 | 23.58 | 102.72 | 102.72 | 0 | KMEP | 102.72 | 0 | 102.72 | 0 | 55.02 | 55.02 | 0 | 24.12 | 24.12 | 0 | 23.58 | 23.58 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 9 | 74622 | 80825 | Plant Room For Kmep Work | Level 5 | Independent | 1 | 4.5 | 1.5 | 2.3 | 1 | m2-LxH | 10.35 | 2022-10-15 | 2022-12-20 | 100% | 100% | 100% | 9.5714 | 12.01 | 0.49 | 87.01 | 48.54 | 37.29 | 172.84 | 172.84 | 0 | KMEP | 172.84 | 0 | 172.84 | 0 | 87.01 | 87.01 | 0 | 48.54 | 48.54 | 0 | 37.29 | 37.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 10 | 74633 | 80937 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 50 | 1.8 | 4 | 1 | lm | 50 | 2022-10-20 | 2023-01-31 | 100% | 100% | 100% | 14.8571 | 1002.22 | 98.12 | 35077.7 | 72889.14 | 15033.3 | 123000.14 | 123000.14 | 0 | Tas Quote - 2439-6-1 | 123000.14 | 0 | 123000.14 | 0 | 35077.7 | 35077.7 | 0 | 72889.14 | 72889.14 | 0 | 15033.3 | 15033.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/341 | HOTEL | 11 | 74623 | 80803 | Balcony Floor Drain Work | Level 13 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 | 2022-12-15 | 100% | 100% | 100% | 8.1429 | 1368.99 | 6.17 | 958.29 | 50.24 | 410.7 | 1419.23 | 1419.23 | 0 | Tas Quote - 2439-12-2 (item-2) | 1419.23 | 0 | 1419.23 | 0 | 958.29 | 958.29 | 0 | 50.24 | 50.24 | 0 | 410.7 | 410.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/341 | HOTEL | 12 | 74625 | 80834 | Balcony Floor Drain Work | Level 12 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-20 | 2022-12-21 | 100% | 100% | 100% | 9 | 1368.99 | 6.17 | 958.29 | 55.53 | 410.7 | 1424.52 | 1424.52 | 0 | Tas Quote - 2439-12-2 (item-2) | 1424.52 | 0 | 1424.52 | 0 | 958.29 | 958.29 | 0 | 55.53 | 55.53 | 0 | 410.7 | 410.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/341 | HOTEL | 13 | 74624 | 80809 | Balcony Floor Drain Work | Level 14 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 | 2022-12-17 | 100% | 100% | 100% | 8.2857 | 1368.99 | 6.17 | 958.29 | 51.12 | 410.7 | 1420.11 | 1420.11 | 0 | Tas Quote - 2439-12-2 (item-2) | 1420.11 | 0 | 1420.11 | 0 | 958.29 | 958.29 | 0 | 51.12 | 51.12 | 0 | 410.7 | 410.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/341 | HOTEL | 14 | 74626 | 80804 | Balcony Floor Drain Work | Level 15 | Independent | 1 | 5.7 | 1.3 | 1.5 | 1 | unit | 1 | 2022-10-21 | 2022-12-15 | 100% | 100% | 100% | 8 | 1368.99 | 6.17 | 958.29 | 49.36 | 410.7 | 1418.35 | 1418.35 | 0 | Tas Quote - 2439-12-2 (item-2) | 1418.35 | 0 | 1418.35 | 0 | 958.29 | 958.29 | 0 | 49.36 | 49.36 | 0 | 410.7 | 410.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 10a | 74635 | 76805 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 50 | 1 | 1 | 1 | m2-LxW | 50 | 2022-10-20 | 2022-10-31 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 232.05 | 60 | 99.45 | 391.5 | 391.5 | 0 |  | 391.5 | 0 | 391.5 | 0 | 232.05 | 232.05 | 0 | 60 | 60 | 0 | 99.45 | 99.45 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 | 78553 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 33 | 1.8 | 4 | 1 | lm | 33 | 2022-10-22 | 2023-02-04 | 100% | 100% | 100% | 15.1429 | 1002.22 | 98.12 | 23151.28 | 49031.97 | 9921.98 | 82105.23 | 82105.23 | 0 | Tas Quote - 2439-6-1 | 82105.23 | 0 | 82105.23 | 0 | 24381.28 | 24381.28 | 0 | 49031.97 | 49031.97 | 0 | 9921.98 | 9921.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 15 | 74634 |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-22 | 2022-10-22 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 1230 | 0 | Additional Inspection | 1230 | 0 | 1230 | 0 | 24381.28 | 24381.28 | 0 | 49031.97 | 49031.97 | 0 | 9921.98 | 9921.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 15a | 74636 | 76806 | Trench Inside for Parapet Cutting | Level 29 | Additional Boarding | 1 | 33 | 1 | 1 | 1 | m2-LxW | 33 | 2022-10-22 | 2022-11-01 | 100% | 100% | 100% | 1.5714 | 6.63 | 0.7 | 153.15 | 36.3 | 65.64 | 255.09 | 255.09 | 0 |  | 255.09 | 0 | 255.09 | 0 | 153.15 | 153.15 | 0 | 36.3 | 36.3 | 0 | 65.64 | 65.64 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 16 | 74627 | 76810 | EIFS work Damac side Elevation | Level 2 | Independent 1.8m wide | 1 | 6.8 | 1.8 | 8 | 1 | m2-LxH | 54.4 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 16.76 | 0.77 | 638.22 | 101.73 | 273.52 | 1013.47 | 1013.47 | 0 |  | 1013.47 | 0 | 1013.47 | 0 | 638.22 | 638.22 | 0 | 101.73 | 101.73 | 0 | 273.52 | 273.52 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 16a | 74628 | 76811 | EIFS work Damac side Elevation | Level 4 | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1 | 1 | 1 | m2-LxW | 6.8 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 173.84 | 48.55 | 74.5 | 296.89 | 296.89 | 0 |  | 296.89 | 0 | 296.89 | 0 | 173.84 | 173.84 | 0 | 48.55 | 48.55 | 0 | 74.5 | 74.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 16b | 74629 | 76812 | EIFS work Damac side Elevation | Level 2 | Buttress | 1 | 2.5 | 1.8 | 5 |  | m3 | 22.5 | 2022-10-24 | 2022-11-09 | 100% | 100% | 100% | 2.4286 | 5.29 | 0.35 | 83.32 | 19.13 | 35.71 | 138.16 | 138.16 | 0 |  | 138.16 | 0 | 138.16 | 0 | 83.32 | 83.32 | 0 | 19.13 | 19.13 | 0 | 35.71 | 35.71 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 9a | 74630 | 80826 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 4.5 | 1 | 1 | 1 | m2-LxW | 4.5 | 2022-10-24 | 2022-12-20 | 100% | 100% | 100% | 8.2857 | 6.63 | 0.7 | 20.88 | 26.1 | 8.95 | 55.93 | 55.93 | 0 | KMEP | 55.93 | 0 | 55.93 | 0 | 20.88 | 20.88 | 0 | 26.1 | 26.1 | 0 | 8.95 | 8.95 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 9b | 74632 | 80827 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-10-24 | 2022-12-20 | 100% | 100% | 100% | 8.2857 | 6.63 | 0.7 | 8.73 | 10.9 | 3.74 | 23.37 | 23.37 | 0 | KMEP | 23.37 | 0 | 23.37 | 0 | 8.73 | 8.73 | 0 | 10.9 | 10.9 | 0 | 3.74 | 3.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 17 | 74637 | 80828 | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-10-25 | 2022-12-20 | 100% | 100% | 100% | 8.1429 | 63.34 | 7.28 | 110.85 | 148.2 | 47.51 | 306.56 | 306.56 | 0 | KMEP | 306.56 | 0 | 306.56 | 0 | 110.85 | 110.85 | 0 | 148.2 | 148.2 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 17a | 74638 | 80829 | Plant Room Kmep Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-10-25 | 2022-12-20 | 100% | 100% | 100% | 8.1429 | 32.75 | 1.05 | 17.19 | 6.41 | 7.37 | 30.97 | 30.97 | 0 | KMEP | 30.97 | 0 | 30.97 | 0 | 17.19 | 17.19 | 0 | 6.41 | 6.41 | 0 | 7.37 | 7.37 | 0 | 0 | 0 | 0
E11/K149/MS/dm/396 | RESIDENCE | 35 | 77666 | 80509 | Master Pump Room Work | Level 23 | Birdcage | 1 | 5 | 4.3 | 3 | 2 | unit | 1 | 2022-10-24 | 2022-11-12 | 100% | 100% | 100% | 2.8571 | 2391.43 | 57.19 | 1674 | 163.4 | 717.43 | 2554.83 | 2554.83 | 0 | Tas Quote - 2439-18-1 (item-1) | 2554.83 | 0 | 2554.83 | 0 | 1674 | 1674 | 0 | 163.4 | 163.4 | 0 | 717.43 | 717.43 | 0 | 0 | 0 | 0
E11/K149/HN/dm/285 | RESIDENCE | 36 | 77671 | 80894 | Loading Bay Above Planter Trench | Ground Level | Design -1399-12 rev-A | 1 |  |  |  |  | unit | 1 | 2022-10-26 | 2023-01-23 | 100% | 100% | 100% | 12.8571 | 4959.77 | 123.48 | 3471.84 | 1587.6 | 1487.93 | 6547.37 | 6547.37 | 0 | Tas Quote - 2439-10-1 | 6547.37 | 0 | 6547.37 | 0 | 3471.84 | 3471.84 | 0 | 1587.6 | 1587.6 | 0 | 1487.93 | 1487.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8m | 77672 | 76773 | Glass Fixing work | Level 31 | Additional Boarding | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-26 | 2022-10-28 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 25.06 | 1.62 | 10.74 | 37.42 | 37.42 | 0 |  | 37.42 | 0 | 37.42 | 0 | 25.06 | 25.06 | 0 | 1.62 | 1.62 | 0 | 10.74 | 10.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8n | 77673 | 79892 | Glass Fixing work | Level 31 | Additional Boarding | 2 | 10.8 | 0.25 | 1 | 2 | m2-LxW | 5.4 | 2022-10-26 | 2023-03-13 | 100% | 100% | 100% | 19.8571 | 6.63 | 0.7 | 25.06 | 75.06 | 10.74 | 110.86 | 91.48 | 19.38 |  | 91.48 | 19.38 | 110.86 | 0 | 25.06 | 25.06 | 0 | 75.06 | 66.42 | 8.64 | 10.74 | 0 | 10.74 | 19.38 | 19.38 | 0
E11/K149/SK/dm/213 | RESIDENCE | 37 | 77674 |  | Glass Fixing work | Level 7 | Tower | 1 | 2.5 | 1.3 | 1 | 1 | rm | 1 | 2022-10-28 |  | 100% | 100% | 0% | 21.2857 | 63.34 | 7.28 | 44.34 | 154.96 | 0 | 199.3 | 170.18 | 29.12 |  | 170.18 | 29.12 | 199.3 | 0 | 44.34 | 44.34 | 0 | 154.96 | 125.84 | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Independent | 1 | 3.1 | 1.3 | 4.2 | 1 | m2-LxH | 13.02 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 109.46 | 7.29 | 46.91 | 163.66 | 163.66 | 0 |  | 163.66 | 0 | 163.66 | 0 | 128.16 | 128.16 | 0 | 10.51 | 10.51 | 0 | 54.93 | 54.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38 | 77675 | 76795 | Entrance Lobby Block Demolishing Work | Ground Level | Additional Boarding | 1 | 3.1 | 1.3 |  | 1 | m2-LxW | 4.03 | 2022-10-28 | 2022-11-04 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 18.7 | 3.22 | 8.02 | 29.94 | 29.94 | 0 |  | 29.94 | 0 | 29.94 | 0 | 128.16 | 128.16 | 0 | 10.51 | 10.51 | 0 | 54.93 | 54.93 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 39 | 77676 |  | Existing Pipe Removal Work | Basement 1 | Birdcage | 1 | 3 | 3 | 5 | 1 | m3 | 45 | 2022-10-28 |  | 100% | 100% | 0% | 21.2857 | 7.08 | 0.49 | 223.02 | 469.35 | 0 | 692.37 | 604.17 | 88.2 |  | 604.17 | 88.2 | 692.37 | 0 | 223.02 | 223.02 | 0 | 469.35 | 381.15 | 88.2 | 0 | 0 | 0 | 88.2 | 88.2 | 0
E11/K149/SK/dm/213 | RESIDENCE | 40 | 77677 | 82125 | Edge Protection | Level 31 | Double Handrail | 1 | 10 |  | 1 |  | lm | 10 | 2022-10-29 | 2023-03-15 | 100% | 100% | 100% | 19.7143 | 12 | 0.7 | 84 | 138 | 36 | 258 | 204 | 54 |  | 204 | 54 | 258 | 0 | 84 | 84 | 0 | 138 | 120 | 18 | 36 | 0 | 36 | 54 | 54 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8o | 77678 | 79898 | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-10-29 | 2023-03-15 | 100% | 100% | 100% | 19.7143 | 32.75 | 1.05 | 123.8 | 111.78 | 53.06 | 288.64 | 221 | 67.64 |  | 221 | 67.64 | 288.64 | 0 | 123.8 | 123.8 | 0 | 111.78 | 97.2 | 14.58 | 53.06 | 0 | 53.06 | 67.64 | 67.64 | 0
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 12.01 | 0.49 | 181.59 | 18.14 | 77.82 | 277.55 | 277.55 | 0 |  | 277.55 | 0 | 277.55 | 0 | 214.17 | 214.17 | 0 | 26.56 | 26.56 | 0 | 91.78 | 91.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 41 | 77679 | 76796 | Block Demolishing Work | Ground Level | Additional Boarding | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxW | 7.02 | 2022-10-29 | 2022-11-09 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 32.58 | 8.42 | 13.96 | 54.96 | 54.96 | 0 |  | 54.96 | 0 | 54.96 | 0 | 214.17 | 214.17 | 0 | 26.56 | 26.56 | 0 | 91.78 | 91.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 41a | 77680 | 76785 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 32.75 | 1.05 | 45.85 | 1.8 | 19.65 | 67.3 | 67.3 | 0 |  | 67.3 | 0 | 67.3 | 0 | 45.85 | 45.85 | 0 | 1.8 | 1.8 | 0 | 19.65 | 19.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38a | 77681 | 76778 | Block Demolishing Work | Ground Level | Cantilever (0 < 0.5m width) | 2 | 2 | 0.5 | 1 | 2 | m2-LxW | 2 | 2022-10-29 | 2022-11-02 | 100% | 100% | 100% | 0.71429 | 32.75 | 1.05 | 45.85 | 1.5 | 19.65 | 67 | 67 | 0 |  | 67 | 0 | 67 | 0 | 45.85 | 45.85 | 0 | 1.5 | 1.5 | 0 | 19.65 | 19.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 39a | 77682 |  | Existing Pipe Removal Work | Basement 1 | Additional Boarding | 1 | 3 | 1.5 | 1 | 1 | m2-LxW | 4.5 | 2022-10-29 |  | 100% | 100% | 0% | 21.1429 | 6.63 | 0.7 | 20.88 | 66.6 | 0 | 87.48 | 74.88 | 12.6 |  | 74.88 | 12.6 | 87.48 | 0 | 20.88 | 20.88 | 0 | 66.6 | 54 | 12.6 | 0 | 0 | 0 | 12.6 | 12.6 | 1.4211e-14
E11/K149/SK/dm/213 | RESIDENCE | 32a | 77683 | 76780 | Block Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-10-29 | 2022-11-03 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 38.35 | 3.78 | 16.43 | 58.56 | 58.56 | 0 |  | 58.56 | 0 | 58.56 | 0 | 38.35 | 38.35 | 0 | 3.78 | 3.78 | 0 | 16.43 | 16.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Tower | 1 | 1.8 | 0.9 | 12.3 | 1 | rm | 12.3 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 545.36 | 102.34 | 233.72 | 881.42 | 881.42 | 0 |  | 881.42 | 0 | 881.42 | 0 | 582.95 | 582.95 | 0 | 108.82 | 108.82 | 0 | 249.83 | 249.83 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 4i | 77686 | 76787 | EIFS Painting up to Groove | Ground Level | Additional Boarding | 5 | 1.8 | 0.9 | 1 | 5 | m2-LxW | 8.1 | 2022-10-29 | 2022-11-05 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 37.59 | 6.48 | 16.11 | 60.18 | 60.18 | 0 |  | 60.18 | 0 | 60.18 | 0 | 582.95 | 582.95 | 0 | 108.82 | 108.82 | 0 | 249.83 | 249.83 | 0 | 0 | 0 | 0
E11/K149/JJ/dm/377 | RESIDENCE | 42 | 77687 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 20.8571 | 7695.22 | 511.06 | 5386.65 | 10659.25 | 0 | 16045.9 | 14001.66 | 2044.24 | Tas Quote 2439-16-3 (item-1) | 14001.66 | 2044.24 | 16045.9 | 0 | 5386.65 | 5386.65 | 0 | 10659.25 | 8615.01 | 2044.24 | 0 | 0 | 0 | 2044.24 | 2044.24 | 0
E11/K149/JJ/dm/377 | RESIDENCE | 43 | 77688 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 20.8571 | 7695.22 | 511.06 | 5386.65 | 10659.25 | 0 | 16045.9 | 14001.66 | 2044.24 | Tas Quote 2439-16-3 (item-1) | 14001.66 | 2044.24 | 16045.9 | 0 | 5386.65 | 5386.65 | 0 | 10659.25 | 8615.01 | 2044.24 | 0 | 0 | 0 | 2044.24 | 2044.24 | 0
E11/K149/JJ/dm/377 | RESIDENCE | 44 | 77689 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-10-31 |  | 100% | 100% | 0% | 20.8571 | 7695.22 | 511.06 | 5386.65 | 10659.25 | 0 | 16045.9 | 14001.66 | 2044.24 | Tas Quote 2439-16-3 (item-1) | 14001.66 | 2044.24 | 16045.9 | 0 | 5386.65 | 5386.65 | 0 | 10659.25 | 8615.01 | 2044.24 | 0 | 0 | 0 | 2044.24 | 2044.24 | 0
E11/K149/SK/dm/213 | RESIDENCE | 32b | 77690 | 76781 | Block Shifting Work | Level 31 | Tower | 1 | 1.5 | 1.5 | 1 | 1 | rm | 1 | 2022-11-01 | 2022-11-03 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 44.34 | 3.12 | 19 | 66.46 | 66.46 | 0 |  | 66.46 | 0 | 66.46 | 0 | 44.34 | 44.34 | 0 | 3.12 | 3.12 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/JJ/dm/377 | RESIDENCE | 45 | 77691 |  | Back Propping For Mast Climber | Ground Level | Design - 1399-20 | 1 |  |  |  |  | unit | 1 | 2022-11-01 |  | 100% | 100% | 0% | 20.7143 | 7695.22 | 511.06 | 5386.65 | 10586.24 | 0 | 15972.89 | 13928.65 | 2044.24 | Tas Quote 2439-16-3 (item-1) | 13928.65 | 2044.24 | 15972.89 | 0 | 5386.65 | 5386.65 | 0 | 10586.24 | 8542 | 2044.24 | 0 | 0 | 0 | 2044.24 | 2044.24 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19b | 77692 | 80536 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 0.75 | 1 | 2 | m2-LxW | 1.13 | 2022-10-29 | 2022-11-28 | 100% | 100% | 100% | 4.4286 | 36.52 | 2.94 | 28.89 | 14.71 | 12.38 | 55.98 | 55.98 | 0 |  | 55.98 | 0 | 55.98 | 0 | 28.89 | 28.89 | 0 | 14.71 | 14.71 | 0 | 12.38 | 12.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19c | 77693 | 76790 | Shaft -9 For Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-02 | 2022-11-04 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 38.35 | 1.89 | 16.43 | 56.67 | 56.67 | 0 |  | 56.67 | 0 | 56.67 | 0 | 38.35 | 38.35 | 0 | 1.89 | 1.89 | 0 | 16.43 | 16.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 | 80539 | Electrical & Plumbing Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-03 | 2022-11-26 | 100% | 100% | 100% | 3.4286 | 63.34 | 7.28 | 177.35 | 99.84 | 76.01 | 353.2 | 353.2 | 0 |  | 353.2 | 0 | 353.2 | 0 | 192.43 | 192.43 | 0 | 107.64 | 107.64 | 0 | 82.47 | 82.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 46 | 77694 | 80539 | Electrical & Plumbing Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-26 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 15.08 | 7.8 | 6.46 | 29.34 | 29.34 | 0 |  | 29.34 | 0 | 29.34 | 0 | 192.43 | 192.43 | 0 | 107.64 | 107.64 | 0 | 82.47 | 82.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 47 | 77695 | 80578 | Block Work | Basement 1 | Tower | 1 | 2.5 | 1.5 | 3 | 1 | rm | 3 | 2022-11-03 | 2022-12-20 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 133.01 | 149.76 | 57.01 | 339.78 | 339.78 | 0 |  | 339.78 | 0 | 339.78 | 0 | 133.01 | 133.01 | 0 | 149.76 | 149.76 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 48 | 77696 | 80526 | Column Cove Installation Work | Ground Level | Birdcage | 1 | 11.8 | 3.8 | 3.5 | 1 | m3 | 156.94 | 2022-11-03 | 2022-11-17 | 100% | 100% | 100% | 2.1429 | 7.08 | 0.49 | 777.79 | 164.79 | 333.34 | 1275.92 | 1275.92 | 0 |  | 1275.92 | 0 | 1275.92 | 0 | 777.79 | 777.79 | 0 | 164.79 | 164.79 | 0 | 333.34 | 333.34 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4.2 | 1 | rm | 4.2 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 186.22 | 43.68 | 79.81 | 309.71 | 309.71 | 0 |  | 309.71 | 0 | 309.71 | 0 | 201.3 | 201.3 | 0 | 46.93 | 46.93 | 0 | 86.27 | 86.27 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 49 | 77697 | 80508 | Electrical Service Work (BMS) | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-03 | 2022-11-12 | 100% | 100% | 100% | 1.4286 | 6.63 | 0.7 | 15.08 | 3.25 | 6.46 | 24.79 | 24.79 | 0 |  | 24.79 | 0 | 24.79 | 0 | 201.3 | 201.3 | 0 | 46.93 | 46.93 | 0 | 86.27 | 86.27 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 50 | 77698 | 80529 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-18 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 279.93 | 279.93 | 0 |  | 279.93 | 0 | 279.93 | 0 | 155.18 | 155.18 | 0 | 58.24 | 58.24 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 51 | 77699 | 80510 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-03 | 2022-11-11 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 155.18 | 32.76 | 66.51 | 254.45 | 254.45 | 0 |  | 254.45 | 0 | 254.45 | 0 | 155.18 | 155.18 | 0 | 32.76 | 32.76 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8p | 77700 | 79891 | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 9 | 0.25 | 1 | 2 | m2-LxW | 2.25 | 2022-11-03 | 2023-03-13 | 100% | 100% | 100% | 18.7143 | 32.75 | 1.05 | 51.58 | 44.21 | 22.11 | 117.9 | 90.39 | 27.51 |  | 90.39 | 27.51 | 117.9 | 0 | 51.58 | 51.58 | 0 | 44.21 | 38.81 | 5.4 | 22.11 | 0 | 22.11 | 27.51 | 27.51 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8q | 77551 | 76791 | Glass Fixing work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-03 | 2022-11-05 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 276.09 | 13.61 | 118.32 | 408.02 | 408.02 | 0 |  | 408.02 | 0 | 408.02 | 0 | 276.09 | 276.09 | 0 | 13.61 | 13.61 | 0 | 118.32 | 118.32 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38b | 77552 | 76797 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 105.93 | 105.93 | 0 |  | 105.93 | 0 | 105.93 | 0 | 66.51 | 66.51 | 0 | 10.92 | 10.92 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38c | 77553 | 76798 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-03 | 2022-11-09 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 66.51 | 10.92 | 28.5 | 105.93 | 105.93 | 0 |  | 105.93 | 0 | 105.93 | 0 | 66.51 | 66.51 | 0 | 10.92 | 10.92 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 52 | 77554 | 80523 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-16 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 155.18 | 47.32 | 66.51 | 269.01 | 269.01 | 0 |  | 269.01 | 0 | 269.01 | 0 | 155.18 | 155.18 | 0 | 47.32 | 47.32 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19d | 77555 | 80502 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-11-04 | 2022-11-09 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 76.69 | 7.56 | 32.87 | 117.12 | 117.12 | 0 |  | 117.12 | 0 | 117.12 | 0 | 76.69 | 76.69 | 0 | 7.56 | 7.56 | 0 | 32.87 | 32.87 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 53 | 77556 | 80511 | Balcony Side Edge Protection | Level 27 | Buttress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 5.29 | 0.35 | 33.33 | 3.6 | 14.28 | 51.21 | 51.21 | 0 |  | 51.21 | 0 | 51.21 | 0 | 33.33 | 33.33 | 0 | 3.6 | 3.6 | 0 | 14.28 | 14.28 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 53a | 77557 | 80511 | Balustrade Glass Edge Protection | Level 27 | Tripple Hnadrail | 1 | 6 |  | 1.5 |  | lm | 6 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 15 | 0.91 | 63 | 6.24 | 27 | 96.24 | 96.24 | 0 |  | 96.24 | 0 | 96.24 | 0 | 63 | 63 | 0 | 6.24 | 6.24 | 0 | 27 | 27 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 54 | 77558 | 80527 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2022-11-04 | 2022-11-17 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 155.18 | 50.96 | 66.51 | 272.65 | 272.65 | 0 |  | 272.65 | 0 | 272.65 | 0 | 155.18 | 155.18 | 0 | 50.96 | 50.96 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 46a | 77559 | 80540 | Electrical Services Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-05 | 2022-11-26 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 177.35 | 91.52 | 76.01 | 344.88 | 344.88 | 0 |  | 344.88 | 0 | 344.88 | 0 | 177.35 | 177.35 | 0 | 91.52 | 91.52 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 55 | 77560 | 80517 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-05 | 2022-11-15 | 100% | 100% | 100% | 1.5714 | 12.01 | 0.49 | 79.87 | 7.32 | 34.23 | 121.42 | 121.42 | 0 |  | 121.42 | 0 | 121.42 | 0 | 79.87 | 79.87 | 0 | 7.32 | 7.32 | 0 | 34.23 | 34.23 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 | 78638 | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-05 | 2023-02-06 | 100% | 100% | 100% | 13.4286 | 63.34 | 7.28 | 177.35 | 391.04 | 76.01 | 644.4 | 644.4 | 0 |  | 644.4 | 0 | 644.4 | 0 | 198.23 | 198.23 | 0 | 433.34 | 433.34 | 0 | 84.96 | 84.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 56 | 77561 | 78638 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-05 | 2023-02-06 | 100% | 100% | 100% | 13.4286 | 6.63 | 0.7 | 20.88 | 42.3 | 8.95 | 72.13 | 72.13 | 0 |  | 72.13 | 0 | 72.13 | 0 | 198.23 | 198.23 | 0 | 433.34 | 433.34 | 0 | 84.96 | 84.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38d | 77562 | 76799 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 102.81 | 102.81 | 0 |  | 102.81 | 0 | 102.81 | 0 | 66.51 | 66.51 | 0 | 7.8 | 7.8 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 38e | 77563 | 76800 | Entrance Lobby Block Work | Ground Level | Tower | 1 | 1 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-05 | 2022-11-09 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 28.5 | 102.81 | 102.81 | 0 |  | 102.81 | 0 | 102.81 | 0 | 66.51 | 66.51 | 0 | 7.8 | 7.8 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 57 | 77564 | 80549 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.8 | 1 | rm | 3.8 | 2022-11-05 | 2022-12-05 | 100% | 100% | 100% | 4.4286 | 63.34 | 7.28 | 168.48 | 122.51 | 72.21 | 363.2 | 363.2 | 0 |  | 363.2 | 0 | 363.2 | 0 | 168.48 | 168.48 | 0 | 122.51 | 122.51 | 0 | 72.21 | 72.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 58 | 77565 | 80528 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3.5 | 1 | m2-LxH | 13.3 | 2022-11-07 | 2022-11-17 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 156.04 | 16.09 | 66.87 | 239 | 239 | 0 |  | 239 | 0 | 239 | 0 | 156.04 | 156.04 | 0 | 16.09 | 16.09 | 0 | 66.87 | 66.87 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 59 | 77566 | 76794 | Cable Tray Removal Work | Basement 1 | Independent | 1 | 8.1 | 1.3 | 3 | 1 | m2-LxH | 24.3 | 2022-11-07 | 2022-11-08 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 204.29 | 3.4 | 87.55 | 295.24 | 295.24 | 0 |  | 295.24 | 0 | 295.24 | 0 | 204.29 | 204.29 | 0 | 3.4 | 3.4 | 0 | 87.55 | 87.55 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8r | 77567 | 80533 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 10.8 | 1 | 1 | 1 | m2-LxW | 10.8 | 2022-11-05 | 2022-11-25 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 276.09 | 95.26 | 118.32 | 489.67 | 489.67 | 0 |  | 489.67 | 0 | 489.67 | 0 | 276.09 | 276.09 | 0 | 95.26 | 95.26 | 0 | 118.32 | 118.32 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 60 | 77568 | 80512 | Balustrade Glass Edge Protection | Level 25 | Buttress | 1 | 2.5 | 1.8 | 2 |  | m3 | 9 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 5.29 | 0.35 | 33.33 | 2.25 | 14.28 | 49.86 | 49.86 | 0 |  | 49.86 | 0 | 49.86 | 0 | 33.33 | 33.33 | 0 | 2.25 | 2.25 | 0 | 14.28 | 14.28 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 60a | 77569 | 80512 | Balustrade Glass Edge Protection | Level 25 | Tripple Hnadrail | 1 | 3 |  | 1.5 |  | lm | 3 | 2022-11-07 | 2022-11-11 | 100% | 100% | 100% | 0.71429 | 15 | 0.91 | 31.5 | 1.95 | 13.5 | 46.95 | 46.95 | 0 |  | 46.95 | 0 | 46.95 | 0 | 31.5 | 31.5 | 0 | 1.95 | 1.95 | 0 | 13.5 | 13.5 | 0 | 0 | 0 | 0
E11/K149/PK/dm/400 | RESIDENCE | 61 | 77578 | 80513 | OME Corridoor Mep Work | Ground Level | Design - 1399-22 | 1 | 24.3 | 1 | 4 | 1 | m2-LxH | 97.2 | 2022-11-07 | 2022-11-14 | 100% | 100% | 100% | 1.1429 | 115.4699 | 2.27 | 7856.57 | 252.16 | 3367.1 | 11475.83 | 11475.83 | 0 | Prorate Tas Quote - 2439-19-1 | 11475.83 | 0 | 11475.83 | 0 | 7856.57 | 7856.57 | 0 | 252.16 | 252.16 | 0 | 3367.1 | 3367.1 | 0 | 0 | 0 | 0
| RESIDENCE | 62 | 77570 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 19.7143 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RESIDENCE | 63 | 77571 |  | Back Propping For Mast Climber | Basement 1 | Design - 1399-24 | 1 |  |  |  |  | unit | 1 | 2022-11-08 |  | 100% | 100% | 0% | 19.7143 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RESIDENCE | 64 | 77572 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 19.5714 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| RESIDENCE | 65 | 77573 |  | Back Propping For Mast Climber | Basement 2 | Design - 1399-20E | 1 |  |  |  |  | unit | 1 | 2022-11-09 |  | 100% | 100% | 0% | 19.5714 |  |  | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19e | 77574 | 80522 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1 | 1 | 1 | m2-LxW | 2 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 51.13 | 5.04 | 21.91 | 78.08 | 78.08 | 0 |  | 78.08 | 0 | 78.08 | 0 | 51.13 | 51.13 | 0 | 5.04 | 5.04 | 0 | 21.91 | 21.91 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 61a | 77582 | 80514 | Corridor KMEP Work | Ground Level | Independent 1.8m wide | 1 | 4 | 2.5 | 4 | 1 | m2-LxH | 16 | 2022-11-09 | 2022-11-14 | 100% | 100% | 100% | 0.85714 | 16.76 | 0.77 | 187.71 | 10.56 | 80.45 | 278.72 | 278.72 | 0 |  | 278.72 | 0 | 278.72 | 0 | 187.71 | 187.71 | 0 | 10.56 | 10.56 | 0 | 80.45 | 80.45 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19f | 77575 | 80505 | Shaft - 9 Ducting Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-10 | 2022-11-10 | 100% | 100% | 100% | 0.14286 | 36.52 | 2.94 | 38.35 | 0.63 | 16.43 | 55.41 | 55.41 | 0 |  | 55.41 | 0 | 55.41 | 0 | 38.35 | 38.35 | 0 | 0.63 | 0.63 | 0 | 16.43 | 16.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 66 | 77576 | 80872 | Pool Plant Room (KMEP Work) | Level 3 | Tower | 1 | 2.5 | 1.8 | 2 | 1 | rm | 2 | 2022-11-10 | 2023-01-09 | 100% | 100% | 100% | 8.7143 | 63.34 | 7.28 | 88.68 | 126.88 | 38 | 253.56 | 253.56 | 0 | (BW-0754) | 253.56 | 0 | 253.56 | 0 | 88.68 | 88.68 | 0 | 126.88 | 126.88 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 67 | 77577 | 80530 | Entrance Area Glass Work | Ground Level | Birdcage | 1 | 3.1 | 2.6 | 4 | 1 | m3 | 32.24 | 2022-11-10 | 2022-11-19 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 159.78 | 22.57 | 68.48 | 250.83 | 250.83 | 0 | (Glass Line - BW-002) | 250.83 | 0 | 250.83 | 0 | 159.78 | 159.78 | 0 | 22.57 | 22.57 | 0 | 68.48 | 68.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 68 | 77579 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 6.3 | 1.3 | 3 | 1 | m2-LxH | 18.9 | 2022-11-10 |  | 100% | 100% | 0% | 19.4286 | 12.01 | 0.49 | 158.89 | 179.93 | 0 | 338.82 | 301.77 | 37.05 | (BW-0754) | 301.77 | 37.05 | 338.82 | 0 | 158.89 | 158.89 | 0 | 179.93 | 142.88 | 37.05 | 0 | 0 | 0 | 37.05 | 37.05 | 0
E11/K149/SK/dm/213 | RESIDENCE | 68a | 77580 |  | Staircase - Electrical Work | Level 2 to 3 | Independent | 1 | 3.5 | 1.3 | 4.5 | 1 | m2-LxH | 15.75 | 2022-11-10 |  | 100% | 100% | 0% | 19.4286 | 12.01 | 0.49 | 132.41 | 149.94 | 0 | 282.35 | 251.48 | 30.87 | (BW-0754) | 251.48 | 30.87 | 282.35 | 0 | 132.41 | 132.41 | 0 | 149.94 | 119.07 | 30.87 | 0 | 0 | 0 | 30.87 | 30.87 | 2.8422e-14
E11/K149/SK/dm/213 | RESIDENCE | 69 | 77581 | 80518 | Electrical Service Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-14 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 76.01 | 270 | 270 | 0 |  | 270 | 0 | 270 | 0 | 177.35 | 177.35 | 0 | 16.64 | 16.64 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 | 80554 | Entrance Storage room (KMEP) | Ground Level | Tower | 1 | 1.3 | 0.9 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-12-06 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 177.35 | 108.16 | 76.01 | 361.52 | 361.52 | 0 |  | 361.52 | 0 | 361.52 | 0 | 182.78 | 182.78 | 0 | 111.2 | 111.2 | 0 | 78.34 | 78.34 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 70 | 77583 | 80554 | Entrance Storage room (KMEP) | Ground Level | Additional Boarding | 1 | 1.3 | 0.9 | 1 | 1 | m2-LxW | 1.17 | 2022-11-11 | 2022-12-06 | 100% | 100% | 100% | 3.7143 | 6.63 | 0.7 | 5.43 | 3.04 | 2.33 | 10.8 | 10.8 | 0 |  | 10.8 | 0 | 10.8 | 0 | 182.78 | 182.78 | 0 | 111.2 | 111.2 | 0 | 78.34 | 78.34 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 177.35 | 20.8 | 76.01 | 274.16 | 274.16 | 0 |  | 274.16 | 0 | 274.16 | 0 | 192.43 | 192.43 | 0 | 22.43 | 22.43 | 0 | 82.47 | 82.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 71 | 77584 | 80520 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 15.08 | 1.63 | 6.46 | 23.17 | 23.17 | 0 |  | 23.17 | 0 | 23.17 | 0 | 192.43 | 192.43 | 0 | 22.43 | 22.43 | 0 | 82.47 | 82.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 72 | 77585 | 80890 | Lift Lobby Fire Curtain Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 1 | rm | 2.2 | 2022-11-11 | 2023-01-17 | 100% | 100% | 100% | 9.7143 | 63.34 | 7.28 | 97.54 | 155.58 | 41.8 | 294.92 | 294.92 | 0 |  | 294.92 | 0 | 294.92 | 0 | 97.54 | 97.54 | 0 | 155.58 | 155.58 | 0 | 41.8 | 41.8 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 199.52 | 23.4 | 85.51 | 308.43 | 308.43 | 0 |  | 308.43 | 0 | 308.43 | 0 | 210.38 | 210.38 | 0 | 24.57 | 24.57 | 0 | 90.16 | 90.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 73 | 77586 | 80521 | BOH Corridor Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 1 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-15 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 10.86 | 1.17 | 4.65 | 16.68 | 16.68 | 0 |  | 16.68 | 0 | 16.68 | 0 | 210.38 | 210.38 | 0 | 24.57 | 24.57 | 0 | 90.16 | 90.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 177.35 | 24.96 | 76.01 | 278.32 | 278.32 | 0 |  | 278.32 | 0 | 278.32 | 0 | 188.21 | 188.21 | 0 | 26.36 | 26.36 | 0 | 80.66 | 80.66 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 74 | 77587 | 80524 | BOH Corridor Shaft Block Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 2 | m2-LxW | 2.34 | 2022-11-11 | 2022-11-16 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 10.86 | 1.4 | 4.65 | 16.91 | 16.91 | 0 |  | 16.91 | 0 | 16.91 | 0 | 188.21 | 188.21 | 0 | 26.36 | 26.36 | 0 | 80.66 | 80.66 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 75 | 77588 | 80519 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-11-12 | 2022-11-15 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 135 | 0 | 135 | 0 | 88.68 | 88.68 | 0 | 8.32 | 8.32 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 76 | 77589 | 80546 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-14 | 2022-11-29 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 279.93 | 279.93 | 0 |  | 279.93 | 0 | 279.93 | 0 | 155.18 | 155.18 | 0 | 58.24 | 58.24 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1o | 77501 | 80556 | Drainge Pipe Connection | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-11-14 | 2022-12-06 | 100% | 100% | 100% | 3.2857 | 36.52 | 2.94 | 46.02 | 17.39 | 19.72 | 83.13 | 83.13 | 0 |  | 83.13 | 0 | 83.13 | 0 | 46.02 | 46.02 | 0 | 17.39 | 17.39 | 0 | 19.72 | 19.72 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 77 | 77503 | 80564 | Chill Water Pipe For (KMEP) | Level 2 | Independent 1.8m wide | 1 | 4 | 2.5 | 1.5 | 1 | m2-LxH | 6 | 2022-11-15 | 2022-12-10 | 100% | 100% | 100% | 3.7143 | 16.76 | 0.77 | 70.39 | 17.16 | 30.17 | 117.72 | 117.72 | 0 |  | 117.72 | 0 | 117.72 | 0 | 70.39 | 70.39 | 0 | 17.16 | 17.16 | 0 | 30.17 | 30.17 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 78 | 77504 | 80532 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-11-15 | 2022-11-19 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 88.68 | 10.4 | 38 | 137.08 | 137.08 | 0 |  | 137.08 | 0 | 137.08 | 0 | 88.68 | 88.68 | 0 | 10.4 | 10.4 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 79 | 77590 | 80551 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 2.5 | 1 | rm | 2.5 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 110.85 | 54.6 | 47.51 | 212.96 | 212.96 | 0 |  | 212.96 | 0 | 212.96 | 0 | 110.85 | 110.85 | 0 | 54.6 | 54.6 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 79a | 77591 | 80552 | Cable Pulling Work | Basement 1 | Tower | 1 | 2 | 1 | 3 | 1 | rm | 3 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 133.01 | 65.52 | 57.01 | 255.54 | 255.54 | 0 |  | 255.54 | 0 | 255.54 | 0 | 133.01 | 133.01 | 0 | 65.52 | 65.52 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 80 | 77592 | 80550 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-15 | 2022-12-05 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 164.05 | 80.81 | 70.31 | 315.17 | 315.17 | 0 |  | 315.17 | 0 | 315.17 | 0 | 164.05 | 164.05 | 0 | 80.81 | 80.81 | 0 | 70.31 | 70.31 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 | 80543 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | rm | 3.7 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 164.05 | 57.72 | 70.31 | 292.08 | 292.08 | 0 |  | 292.08 | 0 | 292.08 | 0 | 179.13 | 179.13 | 0 | 62.6 | 62.6 | 0 | 76.77 | 76.77 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 81 | 77593 | 80543 | Cable Pulling Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 15.08 | 4.88 | 6.46 | 26.42 | 26.42 | 0 |  | 26.42 | 0 | 26.42 | 0 | 179.13 | 179.13 | 0 | 62.6 | 62.6 | 0 | 76.77 | 76.77 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 82 | 77594 | 80544 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 133.01 | 46.8 | 57.01 | 236.82 | 236.82 | 0 |  | 236.82 | 0 | 236.82 | 0 | 133.01 | 133.01 | 0 | 46.8 | 46.8 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 83 | 77595 | 80547 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 155.18 | 54.6 | 66.51 | 276.29 | 276.29 | 0 |  | 276.29 | 0 | 276.29 | 0 | 155.18 | 155.18 | 0 | 54.6 | 54.6 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 19g | 77502 | 80537 | Shaft 9 Duct Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 4.5 | 0.5 | 1 | 1 | m2-LxW | 2.25 | 2022-11-14 | 2022-11-28 | 100% | 100% | 100% | 2.1429 | 32.75 | 1.05 | 51.58 | 5.06 | 22.11 | 78.75 | 78.75 | 0 |  | 78.75 | 0 | 78.75 | 0 | 51.58 | 51.58 | 0 | 5.06 | 5.06 | 0 | 22.11 | 22.11 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 84 | 77505 | 80892 | Ceiling Opening and Closing for (KMEP) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-16 | 2023-01-17 | 100% | 100% | 100% | 9 | 103.33 | 10.29 | 267.62 | 342.66 | 114.7 | 724.98 | 724.98 | 0 |  | 724.98 | 0 | 724.98 | 0 | 267.62 | 267.62 | 0 | 342.66 | 342.66 | 0 | 114.7 | 114.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 85 | 77506 | 80560 | Duct Fixing Work | Basement 1 | Independent | 1 | 6.3 | 1.3 | 2 | 1 | m2-LxH | 12.6 | 2022-11-16 | 2022-12-10 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 105.93 | 22.05 | 45.4 | 173.38 | 173.38 | 0 |  | 173.38 | 0 | 173.38 | 0 | 105.93 | 105.93 | 0 | 22.05 | 22.05 | 0 | 45.4 | 45.4 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 86 | 77507 | 80531 | Lift 3 Gypsum Work | Level 2 | Tower | 1 | 1.3 | 0.9 | 2 | 1 | rm | 2 | 2022-11-16 | 2022-11-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 135 | 0 | 135 | 0 | 88.68 | 88.68 | 0 | 8.32 | 8.32 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 | 80572 | Lift Lobby Glass Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-17 | 2022-12-13 | 100% | 100% | 100% | 3.8571 | 63.34 | 7.28 | 177.35 | 112.32 | 76.01 | 365.68 | 365.68 | 0 |  | 365.68 | 0 | 365.68 | 0 | 192.43 | 192.43 | 0 | 121.1 | 121.1 | 0 | 82.47 | 82.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 87 | 77508 | 80572 | Lift Lobby Glass Line Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-11-17 | 2022-12-13 | 100% | 100% | 100% | 3.8571 | 6.63 | 0.7 | 15.08 | 8.78 | 6.46 | 30.32 | 30.32 | 0 |  | 30.32 | 0 | 30.32 | 0 | 192.43 | 192.43 | 0 | 121.1 | 121.1 | 0 | 82.47 | 82.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 | 79876 | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent | 1 | 14.6 | 1.3 | 4 | 1 | m2-LxH | 58.4 | 2022-11-17 | 2023-03-10 | 100% | 100% | 100% | 16.2857 | 12.01 | 0.49 | 490.97 | 466.03 | 210.42 | 1167.42 | 903.86 | 263.56 |  | 903.86 | 263.56 | 1167.42 | 0 | 579.06 | 579.06 | 0 | 682.4 | 604.59 | 77.81 | 248.17 | 0 | 248.17 | 325.98 | 325.98 | 0
E11/K149/SK/dm/213 | RESIDENCE | 88 | 77509 | 79876 | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 14.6 | 1.3 | 1 | 1 | m2-LxW | 18.98 | 2022-11-17 | 2023-03-10 | 100% | 100% | 100% | 16.2857 | 6.63 | 0.7 | 88.09 | 216.37 | 37.75 | 342.21 | 279.79 | 62.42 |  | 279.79 | 62.42 | 342.21 | 0 | 579.06 | 579.06 | 0 | 682.4 | 604.59 | 77.81 | 248.17 | 0 | 248.17 | 325.98 | 325.98 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8s | 77510 | 78609 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 3.5 | 1 | 1 | 1 | m2-LxW | 3.5 | 2022-11-17 | 2023-01-28 | 100% | 100% | 100% | 10.4286 | 36.52 | 2.94 | 89.47 | 107.31 | 38.35 | 235.13 | 235.13 | 0 |  | 235.13 | 0 | 235.13 | 0 | 89.47 | 89.47 | 0 | 107.31 | 107.31 | 0 | 38.35 | 38.35 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 | 79877 | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Independent 1.8m wide | 1 | 5.8 | 2.5 | 4 | 1 | m2-LxH | 23.2 | 2022-11-18 | 2023-03-10 | 100% | 100% | 100% | 16.1429 | 16.76 | 0.77 | 272.18 | 288.38 | 116.65 | 677.21 | 527.38 | 149.83 |  | 527.38 | 149.83 | 677.21 | 0 | 339.47 | 339.47 | 0 | 452.23 | 400.2 | 52.03 | 145.49 | 0 | 145.49 | 197.52 | 197.52 | 0
E11/K149/SK/dm/213 | RESIDENCE | 89 | 77511 | 79877 | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 5.8 | 2.5 | 1 | 1 | m2-LxW | 14.5 | 2022-11-18 | 2023-03-10 | 100% | 100% | 100% | 16.1429 | 6.63 | 0.7 | 67.29 | 163.85 | 28.84 | 259.98 | 212.29 | 47.69 |  | 212.29 | 47.69 | 259.98 | 0 | 339.47 | 339.47 | 0 | 452.23 | 400.2 | 52.03 | 145.49 | 0 | 145.49 | 197.52 | 197.52 | 0
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 | 79878 | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Tower | 1 | 1 | 0.9 | 4 | 1 | rm | 4 | 2022-11-18 | 2023-03-10 | 100% | 100% | 100% | 16.1429 | 63.34 | 7.28 | 177.35 | 470.08 | 76.01 | 723.44 | 593.35 | 130.09 |  | 593.35 | 130.09 | 723.44 | 0 | 181.53 | 181.53 | 0 | 480.25 | 425 | 55.25 | 77.8 | 0 | 77.8 | 133.05 | 133.05 | 0
E11/K149/SK/dm/213 | RESIDENCE | 89a | 77512 | 79878 | BOH Corridor Lift 1&2 Wall Finishing Work | Ground Level | Additional Boarding | 1 | 1 | 0.9 | 1 | 1 | m2-LxW | 0.9 | 2022-11-18 | 2023-03-10 | 100% | 100% | 100% | 16.1429 | 6.63 | 0.7 | 4.18 | 10.17 | 1.79 | 16.14 | 13.18 | 2.96 |  | 13.18 | 2.96 | 16.14 | 0 | 181.53 | 181.53 | 0 | 480.25 | 425 | 55.25 | 77.8 | 0 | 77.8 | 133.05 | 133.05 | 0
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 | 80574 | Chill Water Pipe For (KMEP) | Ground Level | Birdcage | 1 | 5 | 3.1 | 4 | 1 | m3 | 62 | 2022-11-19 | 2022-12-16 | 100% | 100% | 100% | 4 | 7.08 | 0.49 | 307.27 | 121.52 | 131.69 | 560.48 | 560.48 | 0 |  | 560.48 | 0 | 560.48 | 0 | 379.21 | 379.21 | 0 | 164.92 | 164.92 | 0 | 162.52 | 162.52 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 90 | 77513 | 80574 | Chill Water Pipe For (KMEP) | Ground Level | Additional Boarding | 1 | 5 | 3.1 | 1 | 1 | m2-LxW | 15.5 | 2022-11-19 | 2022-12-16 | 100% | 100% | 100% | 4 | 6.63 | 0.7 | 71.94 | 43.4 | 30.83 | 146.17 | 146.17 | 0 |  | 146.17 | 0 | 146.17 | 0 | 379.21 | 379.21 | 0 | 164.92 | 164.92 | 0 | 162.52 | 162.52 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 91 | 77514 | 80541 | Lift Lobby Block Shifting Work | Ground Level | Tower | 1 | 1.3 | 0.9 | 1 | 1 | rm | 1 | 2022-11-19 | 2022-11-28 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 44.34 | 10.4 | 19 | 73.74 | 73.74 | 0 |  | 73.74 | 0 | 73.74 | 0 | 44.34 | 44.34 | 0 | 10.4 | 10.4 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 87a | 77515 | 80542 | Block Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-19 | 2022-11-28 | 100% | 100% | 100% | 1.4286 | 36.52 | 2.94 | 48.06 | 7.9 | 20.6 | 76.56 | 76.56 | 0 |  | 76.56 | 0 | 76.56 | 0 | 48.06 | 48.06 | 0 | 7.9 | 7.9 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 90a | 77516 | 80575 | BOH Corridor For Chill Pipe (KMEP) | Ground Level | Tower | 1 | 2 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-21 | 2022-12-16 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 155.18 | 94.64 | 66.51 | 316.33 | 316.33 | 0 |  | 316.33 | 0 | 316.33 | 0 | 155.18 | 155.18 | 0 | 94.64 | 94.64 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 | 78610 | Balcony Side Glass Installation | Level 1 | Tower | 1 | 2.5 | 1.8 | 5.5 | 1 | rm | 5.5 | 2022-11-21 | 2023-01-30 | 100% | 100% | 100% | 10.1429 | 63.34 | 7.28 | 243.86 | 406.12 | 104.51 | 754.49 | 754.49 | 0 |  | 754.49 | 0 | 754.49 | 0 | 264.74 | 264.74 | 0 | 438.07 | 438.07 | 0 | 113.46 | 113.46 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 92 | 77517 | 78610 | Balcony Side Glass Installation | Level 1 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-11-21 | 2023-01-30 | 100% | 100% | 100% | 10.1429 | 6.63 | 0.7 | 20.88 | 31.95 | 8.95 | 61.78 | 61.78 | 0 |  | 61.78 | 0 | 61.78 | 0 | 264.74 | 264.74 | 0 | 438.07 | 438.07 | 0 | 113.46 | 113.46 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 93 | 77518 | 80883 | Canal Side For Ceiling Work (KMEP- BW 0804) | Ground Level | Mobile Tower | 1 | 2.5 | 1.8 | 3.7 | 1 | rm | 3.7 | 2022-11-22 | 2023-01-10 | 100% | 100% | 100% | 7.1429 | 103.33 | 10.29 | 267.62 | 271.95 | 114.7 | 654.27 | 654.27 | 0 |  | 654.27 | 0 | 654.27 | 0 | 267.62 | 267.62 | 0 | 271.95 | 271.95 | 0 | 114.7 | 114.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 94 | 77519 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent | 1 | 5.4 | 1.3 | 4 | 1 | m2-LxH | 21.6 | 2022-11-22 |  | 100% | 100% | 0% | 17.7143 | 12.01 | 0.49 | 181.59 | 187.49 | 0 | 369.08 | 326.74 | 42.34 |  | 326.74 | 42.34 | 369.08 | 0 | 181.59 | 181.59 | 0 | 187.49 | 145.15 | 42.34 | 0 | 0 | 0 | 42.34 | 42.34 | 0
E11/K149/SK/dm/213 | RESIDENCE | 94a | 77520 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 | 1 | 1 | m2-LxW | 4.05 | 2022-11-22 |  | 100% | 100% | 0% | 17.7143 | 36.52 | 2.94 | 103.53 | 210.92 | 0 | 314.45 | 266.83 | 47.62 |  | 266.83 | 47.62 | 314.45 | 0 | 103.53 | 103.53 | 0 | 210.92 | 163.3 | 47.62 | 0 | 0 | 0 | 47.62 | 47.62 | 0
E11/K149/SK/dm/213 | RESIDENCE | 94b | 77521 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Independent 1.8m wide | 1 | 4.9 | 2.5 | 4 | 1 | m2-LxH | 19.6 | 2022-11-22 |  | 100% | 100% | 0% | 17.7143 | 16.76 | 0.77 | 229.95 | 267.34 | 0 | 497.29 | 436.93 | 60.36 |  | 436.93 | 60.36 | 497.29 | 0 | 229.95 | 229.95 | 0 | 267.34 | 206.98 | 60.36 | 0 | 0 | 0 | 60.36 | 60.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 94c | 77522 |  | KCE Site Office area Chill Water Pipe (KMEP-BW 767) | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-22 |  | 100% | 100% | 0% | 17.7143 | 63.34 | 7.28 | 177.35 | 515.84 | 0 | 693.19 | 576.71 | 116.48 |  | 576.71 | 116.48 | 693.19 | 0 | 177.35 | 177.35 | 0 | 515.84 | 399.36 | 116.48 | 0 | 0 | 0 | 116.48 | 116.48 | 0
E11/K149/SK/dm/213 | RESIDENCE | 95 | 77523 | 80873 | Shaft Water Meter Room For (KMEP-BW 797) | Level 4 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 | 2023-01-09 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 88.68 | 99.84 | 38 | 226.52 | 226.52 | 0 |  | 226.52 | 0 | 226.52 | 0 | 88.68 | 88.68 | 0 | 99.84 | 99.84 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 96 | 77524 | 80874 | Pump Room For Water Master (BW 024) | Level 3 | Independent 1.8m wide | 1 | 8 | 2.5 | 1.5 | 1 | m2-LxH | 12 | 2022-11-23 | 2023-01-09 | 100% | 100% | 100% | 6.8571 | 16.76 | 0.77 | 140.78 | 63.36 | 60.34 | 264.48 | 264.48 | 0 |  | 264.48 | 0 | 264.48 | 0 | 140.78 | 140.78 | 0 | 63.36 | 63.36 | 0 | 60.34 | 60.34 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 97 | 77525 | 80569 | Pump Room For Water Master (BW 024) | Level 3 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-23 | 2022-12-14 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 66.51 | 34.32 | 28.5 | 129.33 | 129.33 | 0 |  | 129.33 | 0 | 129.33 | 0 | 66.51 | 66.51 | 0 | 34.32 | 34.32 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 98 | 77526 | 80876 | Shaft Water Meter Room For (KMEP-BW 797) | Level 2 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2022-11-23 | 2023-01-09 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 88.68 | 99.84 | 38 | 226.52 | 226.52 | 0 |  | 226.52 | 0 | 226.52 | 0 | 88.68 | 88.68 | 0 | 99.84 | 99.84 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 92a | 77527 | 80534 | Road Side Access For Glass Fixing | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 | 1 | 1 | m2-LxW | 1.25 | 2022-11-23 | 2022-11-24 | 100% | 100% | 100% | 0.28571 | 32.75 | 1.05 | 28.66 | 0.38 | 12.28 | 41.32 | 41.32 | 0 |  | 41.32 | 0 | 41.32 | 0 | 28.66 | 28.66 | 0 | 0.38 | 0.38 | 0 | 12.28 | 12.28 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 99 | 77529 | 80553 | Canal Side For Excavation Access | Ground Level | Tower | 1 | 1.3 | 1.3 | 1 | 1 | rm | 1 | 2022-11-24 | 2022-12-06 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 44.34 | 13.52 | 19 | 76.86 | 76.86 | 0 |  | 76.86 | 0 | 76.86 | 0 | 44.34 | 44.34 | 0 | 13.52 | 13.52 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 100 | 77530 | 78604 | Shaft Water Meter Room For (KMEP-BW 797) | Ground Level | Tower | 1 | 1 | 0.75 | 4 | 2 | rm | 4 | 2022-11-24 | 2023-01-26 | 100% | 100% | 100% | 9.1429 | 63.34 | 7.28 | 177.35 | 266.24 | 76.01 | 519.6 | 519.6 | 0 |  | 519.6 | 0 | 519.6 | 0 | 177.35 | 177.35 | 0 | 266.24 | 266.24 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 72a | 77531 | 80887 | Lift Lobby For Fire Curtain Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 | 1 | 1 | m2-LxW | 1.88 | 2022-11-24 | 2023-01-16 | 100% | 100% | 100% | 7.7143 | 36.52 | 2.94 | 48.06 | 42.64 | 20.6 | 111.3 | 111.3 | 0 |  | 111.3 | 0 | 111.3 | 0 | 48.06 | 48.06 | 0 | 42.64 | 42.64 | 0 | 20.6 | 20.6 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 101 | 77532 | 80885 | Shaft Water Meter Room For (KMEP-BW 797) | Level 5 | Tower | 1 | 1 | 0.5 | 4 | 2 | rm | 4 | 2022-11-25 | 2023-01-12 | 100% | 100% | 100% | 7 | 63.34 | 7.28 | 177.35 | 203.84 | 76.01 | 457.2 | 457.2 | 0 |  | 457.2 | 0 | 457.2 | 0 | 177.35 | 177.35 | 0 | 203.84 | 203.84 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8t | 77533 | 82115 | Glass Fixing work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 10.8 | 0.5 | 1 | 1 | m2-LxW | 5.4 | 2022-11-25 | 2023-03-15 | 100% | 100% | 100% | 15.8571 | 32.75 | 1.05 | 123.8 | 89.91 | 53.06 | 266.77 | 199.13 | 67.64 |  | 199.13 | 67.64 | 266.77 | 0 | 123.8 | 123.8 | 0 | 89.91 | 75.33 | 14.58 | 53.06 | 0 | 53.06 | 67.64 | 67.64 | 0
E11/K149/SK/dm/213 | HOTEL | 18 | 74639 | 76808 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 88.68 | 20.8 | 38 | 147.48 | 147.48 | 0 |  | 147.48 | 0 | 147.48 | 0 | 88.68 | 88.68 | 0 | 20.8 | 20.8 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 19 | 74640 | 76809 | Staircase 7 For Electrical Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-10-27 | 2022-11-05 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 101.98 | 23.92 | 43.7 | 169.6 | 169.6 | 0 |  | 169.6 | 0 | 169.6 | 0 | 101.98 | 101.98 | 0 | 23.92 | 23.92 | 0 | 43.7 | 43.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 20 | 74641 | 76817 | Canal Side Column Cove Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 417.01 | 417.01 | 0 |  | 417.01 | 0 | 417.01 | 0 | 243.86 | 243.86 | 0 | 68.64 | 68.64 | 0 | 104.51 | 104.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 21 | 74644 | 80946 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 23.5 | 1.8 | 4 | 1 | lm | 23.5 | 2022-10-31 | 2023-02-02 | 100% | 100% | 100% | 13.5714 | 1002.22 | 98.12 | 16486.52 | 31293.27 | 7065.65 | 54845.44 | 54845.44 | 0 | Tas Quote - 2439-6-1 | 54845.44 | 0 | 54845.44 | 0 | 16486.52 | 16486.52 | 0 | 31293.27 | 31293.27 | 0 | 7065.65 | 7065.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 21 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-10-31 | 2022-10-31 | 100% | 100% | 100% | 0.14286 | 1230 | 0 | 1230 | 0 | 0 | 1230 | 1230 | 0 | Additional Inspection | 1230 | 0 | 1230 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 22 | 74642 | 76818 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 243.86 | 68.64 | 104.51 | 417.01 | 417.01 | 0 |  | 417.01 | 0 | 417.01 | 0 | 243.86 | 243.86 | 0 | 68.64 | 68.64 | 0 | 104.51 | 104.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 23 | 74643 | 76819 | Column Cove Installation Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2022-10-31 | 2022-11-12 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 243.86 | 74.36 | 104.51 | 422.73 | 422.73 | 0 |  | 422.73 | 0 | 422.73 | 0 | 243.86 | 243.86 | 0 | 74.36 | 74.36 | 0 | 104.51 | 104.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 21a | 74645 | 76821 | Canal Side for Wall Cutting Work | Level 29 | Additional Boarding | 1 | 23.5 | 1 | 1 | 1 | m2-LxW | 23.5 | 2022-10-31 | 2022-11-11 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 109.06 | 28.2 | 46.74 | 184 | 184 | 0 |  | 184 | 0 | 184 | 0 | 109.06 | 109.06 | 0 | 28.2 | 28.2 | 0 | 46.74 | 46.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 24 | 74646 | 76820 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4.5 | 1 | m2-LxH | 17.1 | 2022-11-01 | 2022-11-11 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 200.62 | 20.69 | 85.98 | 307.29 | 307.29 | 0 |  | 307.29 | 0 | 307.29 | 0 | 200.62 | 200.62 | 0 | 20.69 | 20.69 | 0 | 85.98 | 85.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 12a | 74647 | 80835 | Balcony Side Grc Removel & Pipe Connection | Level 12 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 | 2022-12-21 | 100% | 100% | 100% | 7.2857 | 32.75 | 1.05 | 17.19 | 5.74 | 7.37 | 30.3 | 30.3 | 0 |  | 30.3 | 0 | 30.3 | 0 | 17.19 | 17.19 | 0 | 5.74 | 5.74 | 0 | 7.37 | 7.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 11a | 74648 | 80805 | Balcony Side Grc Work | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-01 | 2022-12-15 | 100% | 100% | 100% | 6.4286 | 32.75 | 1.05 | 17.19 | 5.06 | 7.37 | 29.62 | 29.62 | 0 |  | 29.62 | 0 | 29.62 | 0 | 17.19 | 17.19 | 0 | 5.06 | 5.06 | 0 | 7.37 | 7.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 14a | 74649 | 80806 | Balcony Side RFI-130 | Level 15 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 32.75 | 1.05 | 17.19 | 4.95 | 7.37 | 29.51 | 29.51 | 0 |  | 29.51 | 0 | 29.51 | 0 | 17.19 | 17.19 | 0 | 4.95 | 4.95 | 0 | 7.37 | 7.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 | 80807 | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 9.3 | 1.3 | 6 | 1 | m2-LxH | 55.8 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 12.01 | 0.49 | 469.11 | 171.86 | 201.05 | 842.02 | 842.02 | 0 |  | 842.02 | 0 | 842.02 | 0 | 525.22 | 525.22 | 0 | 225.06 | 225.06 | 0 | 225.1 | 225.1 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 25 | 77601 | 80807 | EIFS & Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 9.3 | 1.3 | 1 | 1 | m2-LxW | 12.09 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 6.63 | 0.7 | 56.11 | 53.2 | 24.05 | 133.36 | 133.36 | 0 |  | 133.36 | 0 | 133.36 | 0 | 525.22 | 525.22 | 0 | 225.06 | 225.06 | 0 | 225.1 | 225.1 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 25a | 77602 | 80808 | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 10.5 | 1.3 | 4 | 1 | m2-LxH | 42 | 2022-11-02 | 2022-12-15 | 100% | 100% | 100% | 6.2857 | 12.01 | 0.49 | 353.09 | 129.36 | 151.33 | 633.78 | 633.78 | 0 |  | 633.78 | 0 | 633.78 | 0 | 353.09 | 353.09 | 0 | 129.36 | 129.36 | 0 | 151.33 | 151.33 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 26 | 77604 | 80839 | Plant Room For CHW Pipe | Level 5 | Independent | 1 | 6 | 1.5 | 2 | 1 | m2-LxH | 12 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 12.01 | 0.49 | 100.88 | 40.32 | 43.24 | 184.44 | 184.44 | 0 |  | 184.44 | 0 | 184.44 | 0 | 100.88 | 100.88 | 0 | 40.32 | 40.32 | 0 | 43.24 | 43.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 26a | 77605 | 80840 | Plant Room For CHW Pipe | Level 5 | Independent 1.8m wide | 1 | 6 | 2 | 2.5 | 1 | m2-LxH | 15 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 16.76 | 0.77 | 175.98 | 79.2 | 75.42 | 330.6 | 330.6 | 0 |  | 330.6 | 0 | 330.6 | 0 | 175.98 | 175.98 | 0 | 79.2 | 79.2 | 0 | 75.42 | 75.42 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 26b | 77606 | 80841 | Plant Room For CHW Pipe | Level 5 | Tower | 1 | 1.8 | 1.8 | 1 | 1 | rm | 1 | 2022-11-04 | 2022-12-21 | 100% | 100% | 100% | 6.8571 | 63.34 | 7.28 | 44.34 | 49.92 | 19 | 113.26 | 113.26 | 0 |  | 113.26 | 0 | 113.26 | 0 | 44.34 | 44.34 | 0 | 49.92 | 49.92 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 27 | 77607 | 76816 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 76.01 | 286.64 | 286.64 | 0 |  | 286.64 | 0 | 286.64 | 0 | 177.35 | 177.35 | 0 | 33.28 | 33.28 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 28 | 77608 | 76824 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 | 85.99 | 0 |  | 85.99 | 0 | 85.99 | 0 | 53.21 | 53.21 | 0 | 9.98 | 9.98 | 0 | 22.8 | 22.8 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 29 | 77609 | 76825 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 | 85.99 | 0 |  | 85.99 | 0 | 85.99 | 0 | 53.21 | 53.21 | 0 | 9.98 | 9.98 | 0 | 22.8 | 22.8 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 30 | 77610 | 76826 | Bond Ceiling Work | Level 4 | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 53.21 | 9.98 | 22.8 | 85.99 | 85.99 | 0 |  | 85.99 | 0 | 85.99 | 0 | 53.21 | 53.21 | 0 | 9.98 | 9.98 | 0 | 22.8 | 22.8 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 31 | 77611 | 78577 | Inverted Scaffold | Level 29 | Design 1399 -06 rev-B | 1 | 22 | 1.8 | 4 | 1 | lm | 22 | 2022-11-04 | 2023-02-14 | 100% | 100% | 100% | 14.7143 | 1002.22 | 98.12 | 15434.19 | 31762.85 | 6614.65 | 53811.69 | 53811.69 | 0 | Tas Quote - 2439-6-1 | 53811.69 | 0 | 53811.69 | 0 | 15434.19 | 15434.19 | 0 | 31762.85 | 31762.85 | 0 | 6614.65 | 6614.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 31 |  |  | Inverted Scaffold | Level 29 | Third Party Inspection ( Additional) | 1 |  |  |  |  | unit | 1 | 2022-11-04 | 2023-11-04 | 100% | 100% | 100% | 52.2857 | 1230 | 0 | 1230 | 0 | 369 | 1599 | 1230 | 369 | Additional Inspection | 1230 | 369 | 1599 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 31a | 77612 | 76822 | Inverted Scaffold | Level 29 | Additional Boarding | 1 | 22 | 1 | 1 | 1 | m2-LxW | 22 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 102.1 | 17.6 | 43.76 | 163.46 | 163.46 | 0 |  | 163.46 | 0 | 163.46 | 0 | 102.1 | 102.1 | 0 | 17.6 | 17.6 | 0 | 43.76 | 43.76 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 32 | 77613 | 76814 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 79.87 | 4.66 | 34.23 | 118.76 | 118.76 | 0 |  | 118.76 | 0 | 118.76 | 0 | 79.87 | 79.87 | 0 | 4.66 | 4.66 | 0 | 34.23 | 34.23 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 32a | 77614 | 76815 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 2.3 | 1 | rm | 2.3 | 2022-11-04 | 2022-11-10 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 101.98 | 16.74 | 43.7 | 162.42 | 162.42 | 0 |  | 162.42 | 0 | 162.42 | 0 | 101.98 | 101.98 | 0 | 16.74 | 16.74 | 0 | 43.7 | 43.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 33 | 77615 | 76827 | Bond Ceiling Work | Level 4 | Independent | 1 | 3 | 0.5 | 1.5 | 1 | m2-LxH | 4.5 | 2022-11-04 | 2022-11-11 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 37.83 | 2.52 | 16.21 | 56.56 | 56.56 | 0 |  | 56.56 | 0 | 56.56 | 0 | 37.83 | 37.83 | 0 | 2.52 | 2.52 | 0 | 16.21 | 16.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 34 | 77616 | 80844 | Electrical Services Work | Basement 1 | Independent 1.8m wide | 1 | 3.8 | 2.5 | 3 | 1 | m2-LxH | 11.4 | 2022-11-07 | 2022-12-29 | 100% | 100% | 100% | 7.5714 | 16.76 | 0.77 | 133.74 | 66.46 | 57.32 | 257.52 | 257.52 | 0 |  | 257.52 | 0 | 257.52 | 0 | 133.74 | 133.74 | 0 | 66.46 | 66.46 | 0 | 57.32 | 57.32 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 35 | 77617 | 80845 | Electrical Services Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.2 | 1 | rm | 3.2 | 2022-11-08 | 2022-12-29 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 141.88 | 173.06 | 60.81 | 375.75 | 375.75 | 0 |  | 375.75 | 0 | 375.75 | 0 | 141.88 | 141.88 | 0 | 173.06 | 173.06 | 0 | 60.81 | 60.81 | 0 | 0 | 0 | 0
E11/K149/SK/dm/341 | HOTEL | 36 | 77618 | 76847 | Balcony Floor Drain Work | Level 18 to 20 | Independent 1.8m wide | 1 | 6 | 1.8 | 7 | 1 | unit | 1 | 2022-11-09 | 2022-12-12 | 100% | 100% | 100% | 4.8571 | 5277.5 | 48.26 | 3694.25 | 234.41 | 1583.25 | 5511.91 | 5511.91 | 0 | Tas Quote - 2439-12-2 (item-1) | 5511.91 | 0 | 5511.91 | 0 | 3694.25 | 3694.25 | 0 | 234.41 | 234.41 | 0 | 1583.25 | 1583.25 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 13a | 77619 | 80810 | Balcony Side Grc Removel & Ceiling Board Work | Level 14 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 | 1 | 1 | m2-LxW | 0.75 | 2022-11-09 | 2022-12-17 | 100% | 100% | 100% | 5.5714 | 32.75 | 1.05 | 17.19 | 4.39 | 7.37 | 28.95 | 28.95 | 0 |  | 28.95 | 0 | 28.95 | 0 | 17.19 | 17.19 | 0 | 4.39 | 4.39 | 0 | 7.37 | 7.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 21b | 77620 | 80946 | Inverted Scaffold | Level 29 | Design 1399 -23 | 1 | 3 | 1.8 | 1 | 1 | m2-LxW | 5.4 | 2022-11-09 | 2023-02-02 | 100% | 100% | 100% | 12.2857 | 36.52 | 2.94 | 138.05 | 195.05 | 59.16 | 392.26 | 392.26 | 0 |  | 392.26 | 0 | 392.26 | 0 | 138.05 | 138.05 | 0 | 195.05 | 195.05 | 0 | 59.16 | 59.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 10b | 77621 | 80938 | Inverted Scaffold | Level 29 | Design 1399 -23 | 1 | 1.8 | 1.5 | 1 | 1 | m2-LxW | 2.7 | 2022-11-09 | 2023-01-31 | 100% | 100% | 100% | 12 | 36.52 | 2.94 | 69.02 | 95.26 | 29.58 | 193.86 | 193.86 | 0 |  | 193.86 | 0 | 193.86 | 0 | 69.02 | 69.02 | 0 | 95.26 | 95.26 | 0 | 29.58 | 29.58 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 31b | 77622 | 76823 | Edge Protection | Level 29 | Single Handrail | 1 | 41 | 1 | 1 |  | lm | 41 | 2022-11-09 | 2022-11-11 | 100% | 100% | 100% | 0.42857 | 7 | 0.42 | 200.9 | 7.38 | 86.1 | 294.38 | 294.38 | 0 |  | 294.38 | 0 | 294.38 | 0 | 200.9 | 200.9 | 0 | 7.38 | 7.38 | 0 | 86.1 | 86.1 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 37 | 77623 | 76813 | Chill Water line Pipe For Water Proof | Ground Level | Independent | 1 | 3 | 1.5 | 1 | 1 | m2-LxH | 3 | 2022-11-09 | 2022-11-10 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 25.22 | 0.42 | 10.81 | 36.45 | 36.45 | 0 |  | 36.45 | 0 | 36.45 | 0 | 25.22 | 25.22 | 0 | 0.42 | 0.42 | 0 | 10.81 | 10.81 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 25b | 77624 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 5 | 1.3 | 2.2 | 1 | m2-LxH | 11 | 2022-11-10 |  | 100% | 100% | 0% | 19.4286 | 12.01 | 0.49 | 92.48 | 104.72 | 0 | 197.2 | 175.64 | 21.56 |  | 175.64 | 21.56 | 197.2 | 0 | 92.48 | 92.48 | 0 | 104.72 | 83.16 | 21.56 | 0 | 0 | 0 | 21.56 | 21.56 | 0
E11/K149/SK/dm/213 | HOTEL | 25c | 77625 |  | EIFS & Wall Finishing Work | Basement 1 | Independent | 1 | 8.3 | 1.3 | 2.2 | 1 | m2-LxH | 18.26 | 2022-11-10 |  | 100% | 100% | 0% | 19.4286 | 12.01 | 0.49 | 153.51 | 173.84 | 0 | 327.35 | 291.56 | 35.79 |  | 291.56 | 35.79 | 327.35 | 0 | 153.51 | 153.51 | 0 | 173.84 | 138.05 | 35.79 | 0 | 0 | 0 | 35.79 | 35.79 | 0
E11/K149/SK/dm/213 | HOTEL | 38 | 77626 | 76839 | Electrical Services Work | Basement 1 | Independent | 1 | 3.8 | 1.3 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-11 | 2022-12-05 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 89.45 | 18.62 | 38.34 | 146.41 | 146.41 | 0 |  | 146.41 | 0 | 146.41 | 0 | 89.45 | 89.45 | 0 | 18.62 | 18.62 | 0 | 38.34 | 38.34 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 39 | 77627 | 80801 | Column Cove Installation Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-11-11 | 2022-11-17 | 100% | 100% | 100% | 1 | 16.76 | 0.77 | 178.33 | 11.7 | 76.43 | 266.46 | 266.46 | 0 |  | 266.46 | 0 | 266.46 | 0 | 178.33 | 178.33 | 0 | 11.7 | 11.7 | 0 | 76.43 | 76.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 40 | 77628 | 76833 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 287.21 | 0 |  | 287.21 | 0 | 287.21 | 0 | 155.18 | 155.18 | 0 | 65.52 | 65.52 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 41 | 77629 | 76834 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 133.01 | 56.16 | 57.01 | 246.18 | 246.18 | 0 |  | 246.18 | 0 | 246.18 | 0 | 133.01 | 133.01 | 0 | 56.16 | 56.16 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 42 | 77630 | 76829 | Cable Pulling Work | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2.5 | 1 | rm | 2.5 | 2022-11-12 | 2022-11-29 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 110.85 | 46.8 | 47.51 | 205.16 | 205.16 | 0 |  | 205.16 | 0 | 205.16 | 0 | 110.85 | 110.85 | 0 | 46.8 | 46.8 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/PK/dm/378 | HOTEL | 43&43a | 77633 | 80931 | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 9.1 | 1.3 | 5 | 1 | m2-LxH | 45.5 | 2022-11-14 | 2023-01-30 | 100% | 100% | 100% | 11.1429 | 95.9 | 13.9 | 3054.42 | 7047.3 | 1309.04 | 11410.76 | 11410.76 | 0 | Tas Quote - 2439-15-1 (item-1 Prorate) | 11410.76 | 0 | 11410.76 | 0 | 3054.42 | 3054.42 | 0 | 7047.3 | 7047.3 | 0 | 1309.04 | 1309.04 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 44 | 77631 | 76835 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 177.35 | 62.4 | 76.01 | 315.76 | 315.76 | 0 |  | 315.76 | 0 | 315.76 | 0 | 177.35 | 177.35 | 0 | 62.4 | 62.4 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 45 | 77632 | 76830 | Cable Pulling Work | Basement 1 | Independent 1.8m wide | 1 | 5 | 2.5 | 3.25 | 1 | m2-LxH | 16.25 | 2022-11-15 | 2022-11-29 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 190.65 | 26.81 | 81.71 | 299.17 | 299.17 | 0 |  | 299.17 | 0 | 299.17 | 0 | 190.65 | 190.65 | 0 | 26.81 | 26.81 | 0 | 81.71 | 81.71 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 2e | 77634 | 80830 | Duct Fixing Work (KMEP) | Level 5 | Additional Boarding | 1 | 3 | 1 | 1 | 1 | m2-LxW | 3 | 2022-11-16 | 2022-12-20 | 100% | 100% | 100% | 5 | 6.63 | 0.7 | 13.92 | 10.5 | 5.97 | 30.39 | 30.39 | 0 |  | 30.39 | 0 | 30.39 | 0 | 13.92 | 13.92 | 0 | 10.5 | 10.5 | 0 | 5.97 | 5.97 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 46 | 77635 | 76831 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 133.01 | 40.56 | 57.01 | 230.58 | 230.58 | 0 |  | 230.58 | 0 | 230.58 | 0 | 133.01 | 133.01 | 0 | 40.56 | 40.56 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 46a | 77636 | 76832 | Cable Pulling Work | Basement 1 | Buttress | 1 | 2.5 | 2.5 | 3 |  | m3 | 18.75 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 5.29 | 0.35 | 69.43 | 12.19 | 29.76 | 111.38 | 111.38 | 0 |  | 111.38 | 0 | 111.38 | 0 | 69.43 | 69.43 | 0 | 12.19 | 12.19 | 0 | 29.76 | 29.76 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 47 | 77637 | 76836 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4.2 | 1 | rm | 4.2 | 2022-11-17 | 2022-11-29 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 186.22 | 56.78 | 79.81 | 322.81 | 322.81 | 0 |  | 322.81 | 0 | 322.81 | 0 | 186.22 | 186.22 | 0 | 56.78 | 56.78 | 0 | 79.81 | 79.81 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 48 | 77638 | 80837 | GRC Divider Removel | Level 12 | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 63.34 | 7.28 | 66.51 | 54.6 | 28.5 | 149.61 | 149.61 | 0 |  | 149.61 | 0 | 149.61 | 0 | 160.31 | 160.31 | 0 | 63.79 | 63.79 | 0 | 68.69 | 68.69 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 | 80837 | GRC Divider Removel | Level 12 | Cantilever (0 < 0.5m width) | 1 | 3.5 | 0.5 | 1 | 1 | m2-LxW | 1.75 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 40.12 | 9.19 | 17.19 | 66.5 | 66.5 | 0 |  | 66.5 | 0 | 66.5 | 0 | 160.31 | 160.31 | 0 | 63.79 | 63.79 | 0 | 68.69 | 68.69 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 48a | 77638 | 80837 | GRC Divider Removel | Level 12 | Netting Supply & Install | 1 | 9 | 1 | 1 | 1 | m2-LxH | 9 | 2022-11-17 | 2022-12-21 | 100% | 100% | 100% | 5 | 8.52 | 0 | 53.68 | 0 | 23 | 76.68 | 76.68 | 0 |  | 76.68 | 0 | 76.68 | 0 | 160.31 | 160.31 | 0 | 63.79 | 63.79 | 0 | 68.69 | 68.69 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 36a | 77639 | 76848 | GRC Divider Removel | Level 18 to 20 | Tower | 1 | 1.8 | 1.8 | 7 | 1 | rm | 7 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 310.37 | 189.28 | 133.01 | 632.66 | 632.66 | 0 |  | 632.66 | 0 | 632.66 | 0 | 570.2 | 570.2 | 0 | 195.13 | 195.13 | 0 | 244.37 | 244.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 | 76849 | GRC Divider Removel | Level 18 to 20 | Cantilever (0 < 0.5m width) | 1 | 3 | 0.5 | 1 | 1 | m2-LxW | 1.5 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 32.75 | 1.05 | 34.39 | 5.85 | 14.74 | 54.98 | 54.98 | 0 |  | 54.98 | 0 | 54.98 | 0 | 570.2 | 570.2 | 0 | 195.13 | 195.13 | 0 | 244.37 | 244.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 36b | 77639 | 76849 | GRC Divider Removel | Level 18 to 20 | Netting Supply & Install | 1 | 37.8 | 1 | 1 |  | m2-LxH | 37.8 | 2022-11-17 | 2022-12-12 | 100% | 100% | 100% | 3.7143 | 8.52 |  | 225.44 | 0 | 96.62 | 322.06 | 322.06 | 0 |  | 322.06 | 0 | 322.06 | 0 | 570.2 | 570.2 | 0 | 195.13 | 195.13 | 0 | 244.37 | 244.37 | 0 | 0 | 0 | 0
E11/K149/SK/dm/259 | HOTEL | 49 | 77640 | 78551 | Inverted Scaffold | Level 29 | Design 1399-26 | 1 | 21 | 1.8 | 4 | 1 | lm | 21 | 2022-11-17 | 2023-02-06 | 100% | 100% | 100% | 11.7143 | 1002.22 | 98.12 | 14732.63 | 24137.52 | 6313.99 | 45184.14 | 45184.14 | 0 | Tas Quote - 2439-6-1 | 45184.14 | 0 | 45184.14 | 0 | 14732.63 | 14732.63 | 0 | 24137.52 | 24137.52 | 0 | 6313.99 | 6313.99 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 49a | 77641 | 78551 | Wall Cutting Work | Level 29 | Additional Boarding | 1 | 15 | 1 | 1 | 1 | m2-LxW | 15 | 2022-11-17 | 2023-02-06 | 100% | 100% | 100% | 11.7143 | 6.63 | 0.7 | 69.62 | 123 | 29.84 | 222.46 | 222.46 | 0 |  | 222.46 | 0 | 222.46 | 0 | 69.62 | 69.62 | 0 | 123 | 123 | 0 | 29.84 | 29.84 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 50 | 77642 | 76837 | Cable Pulling Work | Basement 1 | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-11-18 | 2022-11-29 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 177.35 | 49.92 | 76.01 | 303.28 | 303.28 | 0 |  | 303.28 | 0 | 303.28 | 0 | 177.35 | 177.35 | 0 | 49.92 | 49.92 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 51 | 77643 | 79801 | Staircase 7 For Electrical Work | Ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 2.8 | 1 | m2-LxH | 10.64 | 2022-11-18 | 2023-02-22 | 100% | 100% | 100% | 13.8571 | 16.76 | 0.77 | 124.83 | 113.53 | 53.5 | 291.86 | 291.86 | 0 |  | 291.86 | 0 | 291.86 | 0 | 124.83 | 124.83 | 0 | 113.53 | 113.53 | 0 | 53.5 | 53.5 | 0 | 0 | 0 | 0
E11/K149/JA/dm/429 | HOTEL | 52 | 77645 |  | Balcony Access | Level 20 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-11-18 |  | 100% | 100% | 0% | 18.2857 | 1118.57 | 25.48 | 783 | 465.92 | 0 | 1248.92 | 1147 | 101.92 | Tas Quote -2439-20-1 (item#7) | 1147 | 101.92 | 1248.92 | 0 | 808.05 | 808.05 | 0 | 518.6 | 405.16 | 113.44 | 0 | 0 | 0 | 113.44 | 113.44 | 0
E11/K149/SK/dm/213 | HOTEL | 52a | 77645 |  | Balcony Access | Level 21 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 0.75 | 1 | 1 | m2-LxW | 0.98 | 2022-11-18 |  | 100% | 100% | 0% | 18.2857 | 36.52 | 2.94 | 25.05 | 52.68 | 0 | 77.73 | 66.21 | 11.52 |  | 66.21 | 11.52 | 77.73 | 0 | 808.05 | 808.05 | 0 | 518.6 | 405.16 | 113.44 | 0 | 0 | 0 | 113.44 | 113.44 | 0
E11/K149/SK/dm/213 | HOTEL | 13b | 77646 | 80811 | GRC Divider Removel | Level 14 | Tower | 1 | 1.5 | 0.5 | 1.5 | 1 | rm | 1.5 | 2022-11-18 | 2022-12-17 | 100% | 100% | 100% | 4.2857 | 63.34 | 7.28 | 66.51 | 46.8 | 28.5 | 141.81 | 141.81 | 0 |  | 141.81 | 0 | 141.81 | 0 | 66.51 | 66.51 | 0 | 46.8 | 46.8 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 25d | 77647 | 76845 | Wall Finishing Work | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-19 | 2022-12-10 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 38.35 | 13.86 | 16.43 | 68.64 | 68.64 | 0 |  | 68.64 | 0 | 68.64 | 0 | 38.35 | 38.35 | 0 | 13.86 | 13.86 | 0 | 16.43 | 16.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 51a | 77644 | 79802 | Staircase 7 For Electrical Work | Ground Level | Tower | 1 | 2.5 | 0.9 | 2.5 | 1 | rm | 2.5 | 2022-11-18 | 2023-02-22 | 100% | 100% | 100% | 13.8571 | 63.34 | 7.28 | 110.85 | 252.2 | 47.51 | 410.56 | 410.56 | 0 |  | 410.56 | 0 | 410.56 | 0 | 110.85 | 110.85 | 0 | 252.2 | 252.2 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/PK/dm/378 | HOTEL | 43b&43c | 77648 | 80931 | Ramp Area GRC Pannel Fixing Work | Ground Level | Design 1399-21 | 1 | 5.1 | 1.3 | 5 | 1 | m2-LxH | 25.5 | 2022-11-21 | 2023-01-30 | 100% | 100% | 100% | 10.1429 | 95.9 | 13.9 | 1711.82 | 3595.14 | 733.64 | 6040.6 | 6040.6 | 0 | Tas Quote - 2439-15-1 (item-1 Prorate) | 6040.6 | 0 | 6040.6 | 0 | 1711.82 | 1711.82 | 0 | 3595.14 | 3595.14 | 0 | 733.64 | 733.64 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 53 | 77649 | 80831 | Plant Room For Duct Work | Level 5 | Independent 1.8m wide | 1 | 4.3 | 1.8 | 4.5 | 1 | m2-LxH | 19.35 | 2022-11-21 | 2022-12-20 | 100% | 100% | 100% | 4.2857 | 16.76 | 0.77 | 227.01 | 63.86 | 97.29 | 388.16 | 388.16 | 0 |  | 388.16 | 0 | 388.16 | 0 | 227.01 | 227.01 | 0 | 63.86 | 63.86 | 0 | 97.29 | 97.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 53a | 79051 | 80832 | Plant Room For Duct Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-22 | 2022-12-20 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 110.85 | 75.4 | 47.51 | 233.76 | 233.76 | 0 |  | 233.76 | 0 | 233.76 | 0 | 110.85 | 110.85 | 0 | 75.4 | 75.4 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/JA/dm/429 | HOTEL | 54 | 79052 |  | Balcony Access | Level 10 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | unit | 1 | 2022-11-22 |  | 100% | 100% | 0% | 17.7143 | 1278.36 | 29.12 | 894.85 | 515.84 | 0 | 1410.69 | 1294.21 | 116.48 | Tas Quote -2439-20-1 (item#2) | 1294.21 | 116.48 | 1410.69 | 0 | 944.7 | 944.7 | 0 | 617.4 | 477.98 | 139.42 | 0 | 0 | 0 | 139.42 | 139.42 | 0
E11/K149/SK/dm/213 | HOTEL | 54a | 79052 |  | Balcony Access | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 | 1 | 1 | m2-LxW | 1.95 | 2022-11-22 |  | 100% | 100% | 0% | 17.7143 | 36.52 | 2.94 | 49.85 | 101.56 | 0 | 151.41 | 128.47 | 22.94 |  | 128.47 | 22.94 | 151.41 | 0 | 944.7 | 944.7 | 0 | 617.4 | 477.98 | 139.42 | 0 | 0 | 0 | 139.42 | 139.42 | 0
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 | 80812 | GRC Divider Removel | Level 13 | Tower | 1 | 2.5 | 1 | 4.7 | 1 | rm | 4.7 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 208.39 | 127.09 | 89.31 | 424.79 | 424.79 | 0 |  | 424.79 | 0 | 424.79 | 0 | 368.95 | 368.95 | 0 | 129.04 | 129.04 | 0 | 158.12 | 158.12 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 55a | 79053 | 80812 | GRC Divider Removel | Level 13 | Cantilever (0 < 0.5m width) | 1 | 1 | 0.5 | 1 | 1 | m2-LxW | 0.5 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 32.75 | 1.05 | 11.46 | 1.95 | 4.91 | 18.32 | 18.32 | 0 |  | 18.32 | 0 | 18.32 | 0 | 368.95 | 368.95 | 0 | 129.04 | 129.04 | 0 | 158.12 | 158.12 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 55 | 79053 | 80812 | GRC Divider Removel | Level 13 | Netting Supply & Install | 1 | 25 | 1 | 1 | 1 | m2-LxH | 25 | 2022-11-22 | 2022-12-17 | 100% | 100% | 100% | 3.7143 | 8.52 | 0 | 149.1 | 0 | 63.9 | 213 | 213 | 0 |  | 213 | 0 | 213 | 0 | 368.95 | 368.95 | 0 | 129.04 | 129.04 | 0 | 158.12 | 158.12 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 36c | 79054 | 76850 | GRC Divider Removel | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.2 | 1 | 1 | m2-LxW | 1.8 | 2022-11-22 | 2022-12-12 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 46.02 | 15.88 | 19.72 | 81.62 | 81.62 | 0 |  | 81.62 | 0 | 81.62 | 0 | 46.02 | 46.02 | 0 | 15.88 | 15.88 | 0 | 19.72 | 19.72 | 0 | 0 | 0 | 0
E11/K149/JA/dm/429 | HOTEL | 56 | 79055 |  | Balcony Access | Level 15 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 17.5714 | 1246.69 | 25.48 | 872.68 | 447.72 | 0 | 1320.4 | 1218.48 | 101.92 | Tas Quote -2439-20-1 (item#4) | 1218.48 | 101.92 | 1320.4 | 0 | 911.03 | 911.03 | 0 | 525.21 | 405.65 | 119.56 | 0 | 0 | 0 | 119.56 | 119.56 | 0
E11/K149/SK/dm/213 | HOTEL | 56a | 79055 |  | Balcony Access | Level 15 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 17.5714 | 36.52 | 2.94 | 38.35 | 77.49 | 0 | 115.84 | 98.2 | 17.64 |  | 98.2 | 17.64 | 115.84 | 0 | 911.03 | 911.03 | 0 | 525.21 | 405.65 | 119.56 | 0 | 0 | 0 | 119.56 | 119.56 | 0
E11/K149/JA/dm/429 | HOTEL | 57 | 79056 |  | Balcony Access | Level 18 | Tower | 1 | 2.5 | 1 | 6 | 3 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 17.5714 | 1783.37 | 40.04 | 1248.36 | 703.56 | 0 | 1951.92 | 1791.76 | 160.16 | Tas Quote -2439-20-1 (item#6) | 1791.76 | 160.16 | 1951.92 | 0 | 1273.92 | 1273.92 | 0 | 755.22 | 583.3 | 171.92 | 0 | 0 | 0 | 171.92 | 171.92 | 0
E11/K149/SK/dm/213 | HOTEL | 57a | 79056 |  | Balcony Access | Level 18 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 | 1 | 1 | m2-LxW | 1 | 2022-11-23 |  | 100% | 100% | 0% | 17.5714 | 36.52 | 2.94 | 25.56 | 51.66 | 0 | 77.22 | 65.46 | 11.76 |  | 65.46 | 11.76 | 77.22 | 0 | 1273.92 | 1273.92 | 0 | 755.22 | 583.3 | 171.92 | 0 | 0 | 0 | 171.92 | 171.92 | 0
E11/K149/JA/dm/429 | HOTEL | 58 | 79057 |  | Balcony Access | Level 7 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-23 |  | 100% | 100% | 0% | 17.5714 | 1246.69 | 25.48 | 872.68 | 447.72 | 0 | 1320.4 | 1218.48 | 101.92 | Tas Quote -2439-20-1 (item#1) | 1218.48 | 101.92 | 1320.4 | 0 | 911.03 | 911.03 | 0 | 525.21 | 405.65 | 119.56 | 0 | 0 | 0 | 119.56 | 119.56 | 0
E11/K149/SK/dm/213 | HOTEL | 58a | 79057 |  | Balcony Access | Level 7 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-23 |  | 100% | 100% | 0% | 17.5714 | 36.52 | 2.94 | 38.35 | 77.49 | 0 | 115.84 | 98.2 | 17.64 |  | 98.2 | 17.64 | 115.84 | 0 | 911.03 | 911.03 | 0 | 525.21 | 405.65 | 119.56 | 0 | 0 | 0 | 119.56 | 119.56 | 0
E11/K149/JA/dm/429 | HOTEL | 59 | 79058 |  | Balcony Access | Level 13 | Tower | 1 | 2.5 | 1 | 3.5 | 1 | unit | 1 | 2022-11-24 |  | 100% | 100% | 0% | 17.4286 | 1246.69 | 25.48 | 872.68 | 444.08 | 0 | 1316.76 | 1214.84 | 101.92 | Tas Quote -2439-20-1 (item#3) | 1214.84 | 101.92 | 1316.76 | 0 | 911.03 | 911.03 | 0 | 520.94 | 401.38 | 119.56 | 0 | 0 | 0 | 119.56 | 119.56 | 1.279e-13
E11/K149/SK/dm/213 | HOTEL | 59a | 79058 |  | Balcony Access | Level 13 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-24 |  | 100% | 100% | 0% | 17.4286 | 36.52 | 2.94 | 38.35 | 76.86 | 0 | 115.21 | 97.57 | 17.64 |  | 97.57 | 17.64 | 115.21 | 0 | 911.03 | 911.03 | 0 | 520.94 | 401.38 | 119.56 | 0 | 0 | 0 | 119.56 | 119.56 | 1.279e-13
E11/K149/SK/dm/213 | HOTEL | 25e | 79059 | 76846 | Wall Finishing Work | Basement 1 | Independent | 1 | 4.1 | 1.3 | 1.5 | 1 | m2-LxH | 6.15 | 2022-11-24 | 2022-12-10 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 51.7 | 7.32 | 22.16 | 81.18 | 81.18 | 0 |  | 81.18 | 0 | 81.18 | 0 | 51.7 | 51.7 | 0 | 7.32 | 7.32 | 0 | 22.16 | 22.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 102 | 77534 | 79869 | KMEP BW-829 | Ground Level | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2022-11-26 | 2023-03-07 | 100% | 100% | 100% | 14.5714 | 63.34 | 7.28 | 177.35 | 424.32 | 76.01 | 677.68 | 560.07 | 117.61 |  | 560.07 | 117.61 | 677.68 | 0 | 177.35 | 177.35 | 0 | 424.32 | 382.72 | 41.6 | 76.01 | 0 | 76.01 | 117.61 | 117.61 | 0
E11/K149/SK/dm/213 | RESIDENCE | 103 | 77535 | 80591 | Planter Area For Water Tank Access | Ground Level | Independent 1.8m wide | 1 | 3 | 2.5 | 2.5 | 1 | m2-LxH | 7.5 | 2022-11-26 | 2022-12-27 | 100% | 100% | 100% | 4.5714 | 16.76 | 0.77 | 87.99 | 26.4 | 37.71 | 152.1 | 152.1 | 0 |  | 152.1 | 0 | 152.1 | 0 | 87.99 | 87.99 | 0 | 26.4 | 26.4 | 0 | 37.71 | 37.71 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 104 | 77536 | 80548 | Crane Extension Platform | Roof | Birdcage | 1 | 5.4 | 3.8 | 2 | 1 | m3 | 41.04 | 2022-11-26 | 2022-12-05 | 100% | 100% | 100% | 1.4286 | 7.08 | 0.49 | 203.39 | 28.73 | 87.17 | 319.29 | 319.29 | 0 |  | 319.29 | 0 | 319.29 | 0 | 313.13 | 313.13 | 0 | 28.73 | 28.73 | 0 | 134.2 | 134.2 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 104 | 77536 | 80548 | Crane Extension Platform | Roof | Netting Supply & Install | 1 | 18.4 | 1 | 1 |  | m2-LxH | 18.4 | 2022-11-26 | 2022-12-05 | 100% | 100% | 100% | 1.4286 | 8.52 | 0 | 109.74 | 0 | 47.03 | 156.77 | 156.77 | 0 |  | 156.77 | 0 | 156.77 | 0 | 313.13 | 313.13 | 0 | 28.73 | 28.73 | 0 | 134.2 | 134.2 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 105 | 77537 | 80558 | OME Office For Chill Water Pipe Work (KMEP BW-767) | Level 2 | Independent | 1 | 5 | 1.3 | 2.5 | 1 | m2-LxH | 12.5 | 2022-11-26 | 2022-12-10 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 105.09 | 13.13 | 45.04 | 163.26 | 163.26 | 0 |  | 163.26 | 0 | 163.26 | 0 | 105.09 | 105.09 | 0 | 13.13 | 13.13 | 0 | 45.04 | 45.04 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 105a | 77538 | 80559 | OME Office For Chill Water Pipe Work (KMEP BW-767) | Level 2 | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2022-11-26 | 2022-12-10 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 110.85 | 39 | 47.51 | 197.36 | 197.36 | 0 |  | 197.36 | 0 | 197.36 | 0 | 110.85 | 110.85 | 0 | 39 | 39 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 106 | 77539 | 80592 | Planter Area For Water Tank Access | Ground Level | Independent 1.8m wide | 1 | 3 | 2 | 3.5 | 1 | m2-LxH | 10.5 | 2022-11-26 | 2022-12-27 | 100% | 100% | 100% | 4.5714 | 16.76 | 0.77 | 123.19 | 36.96 | 52.79 | 212.94 | 212.94 | 0 |  | 212.94 | 0 | 212.94 | 0 | 123.19 | 123.19 | 0 | 36.96 | 36.96 | 0 | 52.79 | 52.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 107 | 77540 | 80565 | Ramp Area For Wall Concret Work | Ground Level | Independent | 1 | 18.4 | 0.9 | 2 | 1 | m2-LxH | 36.8 | 2022-11-29 | 2022-12-12 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 309.38 | 36.06 | 132.59 | 478.03 | 478.03 | 0 |  | 478.03 | 0 | 478.03 | 0 | 893.26 | 893.26 | 0 | 36.06 | 36.06 | 0 | 382.82 | 382.82 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 107 | 77540 | 80565 | Ramp Area For Wall Concret Work | Ground Level | Netting Supply & Install | 1 | 97.9 | 1 | 1 |  | m2-LxH | 97.9 | 2022-11-29 | 2022-12-12 | 100% | 100% | 100% | 2 | 8.52 | 0 | 583.88 | 0 | 250.23 | 834.11 | 834.11 | 0 |  | 834.11 | 0 | 834.11 | 0 | 893.26 | 893.26 | 0 | 36.06 | 36.06 | 0 | 382.82 | 382.82 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1r | 77541 | 82123 | Canal Side For Glass Frame Installation | Level 30 | Cantilever (0 < 0.5m width) | 2 | 8.5 | 0.5 | 1 | 2 | m2-LxW | 8.5 | 2022-11-29 | 2023-03-16 | 100% | 100% | 100% | 15.4286 | 32.75 | 1.05 | 194.86 | 137.7 | 83.51 | 416.07 | 308.34 | 107.73 |  | 308.34 | 107.73 | 416.07 | 0 | 194.86 | 194.86 | 0 | 137.7 | 113.48 | 24.22 | 83.51 | 0 | 83.51 | 107.73 | 107.73 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1s | 77544 | 82143 | Canal Side Glass Fixing Work | Level 30 to 31 | Additional Boarding | 4 | 5 | 1.8 | 1 | 4 | m2-LxW | 36 | 2022-11-30 | 2023-03-24 | 100% | 100% | 100% | 16.4286 | 6.63 | 0.7 | 167.08 | 414 | 71.6 | 652.68 | 483.88 | 168.8 |  | 483.88 | 168.8 | 652.68 | 0 | 381.78 | 381.78 | 0 | 414 | 316.8 | 97.2 | 163.62 | 0 | 163.62 | 260.82 | 260.82 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1s | 77544 | 82143 | Canal Side Glass Fixing Work | Level 30 to 31 | Netting Supply & Install | 1 | 36 | 1 | 1 |  | m2-LxH | 36 | 2022-11-30 | 2023-03-24 | 100% | 100% | 100% | 16.4286 | 8.52 | 0 | 214.7 | 0 | 92.02 | 306.72 | 214.7 | 92.02 |  | 214.7 | 92.02 | 306.72 | 0 | 381.78 | 381.78 | 0 | 414 | 316.8 | 97.2 | 163.62 | 0 | 163.62 | 260.82 | 260.82 | 0
E11/K149/SK/dm/213 | RESIDENCE | 110 | 77545 | 82132 | KMEP BW | Level 2 | Tower | 1 | 2.5 | 1.3 | 6 | 1 | rm | 6 | 2022-11-30 | 2023-02-26 | 100% | 100% | 100% | 12.7143 | 63.34 | 7.28 | 266.03 | 555.36 | 114.01 | 935.4 | 815.15 | 120.25 |  | 815.15 | 120.25 | 935.4 | 0 | 377.22 | 377.22 | 0 | 654.78 | 647.89 | 6.89 | 161.66 | 34.72 | 126.94 | 133.83 | 133.83 | 0
E11/K149/SK/dm/213 | RESIDENCE | 110 | 77545 | 82132 | KMEP BW | Level 2 | Additional Boarding | 2 | 2.5 | 1.3 | 1 | 2 | m2-LxW | 6.5 | 2022-11-30 | 2023-02-26 | 100% | 100% | 100% | 12.7143 | 6.63 | 0.7 | 30.17 | 57.85 | 12.93 | 100.95 | 87.37 | 13.58 |  | 87.37 | 13.58 | 100.95 | 0 | 377.22 | 377.22 | 0 | 654.78 | 647.89 | 6.89 | 161.66 | 34.72 | 126.94 | 133.83 | 133.83 | 0
E11/K149/SK/dm/213 | RESIDENCE | 110a | 77545 | 80875 | KMEP BW | Level 2 | Buttress | 1 | 2.5 | 2.5 | 3.5 |  | m3 | 21.88 | 2022-11-30 | 2023-01-06 | 100% | 100% | 100% | 5.4286 | 5.29 | 0.35 | 81.02 | 41.57 | 34.72 | 157.31 | 157.31 | 0 |  | 157.31 | 0 | 157.31 | 0 | 377.22 | 377.22 | 0 | 654.78 | 647.89 | 6.89 | 161.66 | 34.72 | 126.94 | 133.83 | 133.83 | 0
E11/K149/SK/dm/213 | RESIDENCE | 110b | 77546 | 82132 | KMEP BW | Level 2 | Cantilever (0 < 0.5m width) | 3 | 1.3 | 0.5 | 1 | 3 | m2-LxW | 1.95 | 2022-11-30 | 2023-02-26 | 100% | 100% | 100% | 12.7143 | 32.75 | 1.05 | 44.7 | 26.03 | 19.16 | 89.89 | 70.44 | 19.45 |  | 70.44 | 19.45 | 89.89 | 0 | 44.7 | 44.7 | 0 | 26.03 | 25.74 | 0.29 | 19.16 | 0 | 19.16 | 19.45 | 19.45 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8u | 77547 |  | Balcony For Access | Level 29 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2022-12-05 |  | 100% | 100% | 0% | 15.8571 | 6.63 | 0.7 | 30.07 | 71.93 | 0 | 102 | 83.85 | 18.15 |  | 83.85 | 18.15 | 102 | 0 | 30.07 | 30.07 | 0 | 71.93 | 53.78 | 18.15 | 0 | 0 | 0 | 18.15 | 18.15 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8v | 77548 |  | Balcony For Access | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.5 | 1 | 1 | m2-LxW | 2.25 | 2022-12-05 |  | 100% | 100% | 0% | 15.8571 | 36.52 | 2.94 | 57.52 | 104.9 | 0 | 162.42 | 135.96 | 26.46 |  | 135.96 | 26.46 | 162.42 | 0 | 57.52 | 57.52 | 0 | 104.9 | 78.44 | 26.46 | 0 | 0 | 0 | 26.46 | 26.46 | -2.8422e-14
E11/K149/SK/dm/213 | RESIDENCE | 1t | 77549 | 82114 | Glass Fixing work | Level 31 | Cantilever (0 < 0.5m width) | 3 | 8.5 | 0.5 | 1 | 3 | m2-LxW | 12.75 | 2022-12-06 | 2023-03-15 | 100% | 100% | 100% | 14.2857 | 32.75 | 1.05 | 292.29 | 191.25 | 125.27 | 608.81 | 449.12 | 159.69 |  | 449.12 | 159.69 | 608.81 | 0 | 292.29 | 292.29 | 0 | 191.25 | 156.83 | 34.42 | 125.27 | 0 | 125.27 | 159.69 | 159.69 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1v | 79102 | 82150 | Canal Side Glass Fixing Work | Level 30 | Additional Boarding | 1 | 7.2 | 1.8 | 1 | 1 | m2-LxW | 12.96 | 2022-12-06 | 2023-03-22 | 100% | 100% | 100% | 15.2857 | 6.63 | 0.7 | 60.15 | 138.67 | 25.78 | 224.6 | 166.42 | 58.18 |  | 166.42 | 58.18 | 224.6 | 0 | 60.15 | 60.15 | 0 | 138.67 | 106.27 | 32.4 | 25.78 | 0 | 25.78 | 58.18 | 58.18 | 0
E11/K149/SK/dm/213 | RESIDENCE | 107a | 79118 | 80555 | Ramp Area For Wall Concret Work | Ground Level | Independent | 1 | 18.4 | 0.9 | 2 | 1 | m2-LxH | 36.8 | 2022-12-06 | 2022-12-07 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 309.38 | 5.15 | 132.59 | 447.12 | 447.12 | 0 |  | 447.12 | 0 | 447.12 | 0 | 309.38 | 309.38 | 0 | 5.15 | 5.15 | 0 | 132.59 | 132.59 | 0 | 0 | 0 | 0
E11/K149/SK/dm/468 | RESIDENCE | 111 | 79106 |  | EIFS Fixing Work | Level 10 | Independent | 1 | 20 | 0.6 | 2.5 | 1 | unit | 1 | 2022-12-07 |  | 100% | 100% | 0% | 15.5714 | 2710.95 | 253.17 | 1897.67 | 3942.22 | 0 | 5839.89 | 4827.21 | 1012.68 | Tas Quote - 2439-21-1 (Item #1) | 4827.21 | 1012.68 | 5839.89 | 0 | 1897.67 | 1897.67 | 0 | 3942.22 | 2929.54 | 1012.68 | 0 | 0 | 0 | 1012.68 | 1012.68 | 0
E11/K149/SK/dm/468 | RESIDENCE | 111a | 79107 |  | EIFS Fixing Work | Level 10 | Independent | 1 | 2.6 | 1.3 | 2.6 | 2 | unit | 1 | 2022-12-07 |  | 100% | 100% | 0% | 15.5714 | 947.74 | 95.55 | 663.42 | 1487.85 | 0 | 2151.27 | 1769.07 | 382.2 | Tas Quote - 2439-21-1 (Item #2) | 1769.07 | 382.2 | 2151.27 | 0 | 663.42 | 663.42 | 0 | 1487.85 | 1105.65 | 382.2 | 0 | 0 | 0 | 382.2 | 382.2 | 0
E11/K149/SK/dm/213 | RESIDENCE | 112 | 79105 | 78611 | House Keeping Lobby (KMEP BW-886) | Level 5 | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-07 | 2023-01-30 | 100% | 100% | 100% | 7.8571 | 63.34 | 7.28 | 155.18 | 200.2 | 66.51 | 421.89 | 421.89 | 0 |  | 421.89 | 0 | 421.89 | 0 | 155.18 | 155.18 | 0 | 200.2 | 200.2 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 113 | 79110 | 80561 | Staircase 3 (KMEP BW-886) | Level 5 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 99.69 | 99.69 | 0 |  | 99.69 | 0 | 99.69 | 0 | 66.51 | 66.51 | 0 | 4.68 | 4.68 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 113a | 79111 | 80562 | Staircase 3 (KMEP BW-886) | Level 5 | Independent | 1 | 3 | 0.6 | 1.5 | 1 | m2-LxH | 4.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 37.83 | 0.95 | 16.21 | 54.99 | 54.99 | 0 |  | 54.99 | 0 | 54.99 | 0 | 37.83 | 37.83 | 0 | 0.95 | 0.95 | 0 | 16.21 | 16.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 114 | 79112 | 80563 | Staircase 3 (KMEP BW-886) | Level 5 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-12-08 | 2022-12-10 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 99.69 | 99.69 | 0 |  | 99.69 | 0 | 99.69 | 0 | 66.51 | 66.51 | 0 | 4.68 | 4.68 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 115 | 79113 | 80852 | Electrical Room - (KMEP BW-882) | Level 4 | Tower | 1 | 1.3 | 1.3 | 2 | 1 | rm | 2 | 2022-12-08 | 2023-01-03 | 100% | 100% | 100% | 3.8571 | 63.34 | 7.28 | 88.68 | 56.16 | 38 | 182.84 | 182.84 | 0 |  | 182.84 | 0 | 182.84 | 0 | 88.68 | 88.68 | 0 | 56.16 | 56.16 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 116 | 79114 | 80570 | Near Gate 1 For Wall Plaster | Ground Level | Independent | 1 | 10 | 1.3 | 1.5 | 1 | m2-LxH | 15 | 2022-12-08 | 2022-12-14 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 126.11 | 7.35 | 54.05 | 187.51 | 187.51 | 0 |  | 187.51 | 0 | 187.51 | 0 | 126.11 | 126.11 | 0 | 7.35 | 7.35 | 0 | 54.05 | 54.05 | 0 | 0 | 0 | 0
E11/K149/MS/dm/497 | RESIDENCE | 117 | 79116 | 80580 | House Keeping Lobby Shaft Lobby | Level 31 | Design 1399-31 | 1 | 3 | 1 | 2.3 | 1 | unit | 1 | 2022-12-08 | 2022-12-19 | 100% | 100% | 100% | 1.7143 | 3467.267 | 51.6733 | 2427.09 | 88.58 | 1040.18 | 3555.85 | 3555.85 | 0 | Tas Quote - 2439-23-1 (Item 3) | 3555.85 | 0 | 3555.85 | 0 | 2427.09 | 2427.09 | 0 | 88.58 | 88.58 | 0 | 1040.18 | 1040.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 118 | 79115 | 79894 | Canal Side For Beam Drilling Work | Level 31 | Tower | 2 | 1 | 0.75 | 1 | 1 | rm | 2 | 2022-12-08 | 2023-03-18 | 100% | 100% | 100% | 14.4286 | 63.34 | 7.28 | 88.68 | 210.08 | 38 | 336.76 | 255.08 | 81.68 |  | 255.08 | 81.68 | 336.76 | 0 | 88.68 | 88.68 | 0 | 210.08 | 166.4 | 43.68 | 38 | 0 | 38 | 81.68 | 81.68 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1w | 79117 | 79890 | Canal Side For Glass Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 2 | 1.8 | 0.5 | 1 | 2 | m2-LxW | 1.8 | 2022-12-08 | 2023-03-13 | 100% | 100% | 100% | 13.7143 | 32.75 | 1.05 | 41.27 | 25.92 | 17.69 | 84.88 | 62.87 | 22.01 |  | 62.87 | 22.01 | 84.88 | 0 | 41.27 | 41.27 | 0 | 25.92 | 21.6 | 4.32 | 17.69 | 0 | 17.69 | 22.01 | 22.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 119 | 79119 | 80579 | Curtain Wall Glass Frame Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2022-12-09 | 2022-12-19 | 100% | 100% | 100% | 1.5714 | 63.34 | 7.28 | 177.35 | 45.76 | 76.01 | 299.12 | 299.12 | 0 |  | 299.12 | 0 | 299.12 | 0 | 191.79 | 191.79 | 0 | 46.8 | 46.8 | 0 | 82.2 | 82.2 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 119a | 79119 | 80579 | Curtain Wall Glass Frame Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.25 | 1 | 1 | m2-LxW | 0.63 | 2022-12-09 | 2022-12-19 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 14.44 | 1.04 | 6.19 | 21.67 | 21.67 | 0 |  | 21.67 | 0 | 21.67 | 0 | 191.79 | 191.79 | 0 | 46.8 | 46.8 | 0 | 82.2 | 82.2 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 120 | 79120 | 80571 | Near Gate 1 For Wall Concret Work | Ground Level | Independent | 1 | 5 | 1.3 | 1.5 | 1 | m2-LxH | 7.5 | 2022-12-09 | 2022-12-14 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 63.05 | 3.15 | 27.02 | 93.22 | 93.22 | 0 |  | 93.22 | 0 | 93.22 | 0 | 63.05 | 63.05 | 0 | 3.15 | 3.15 | 0 | 27.02 | 27.02 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 121 | 79121 | 80566 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 1 | 2.5 | 1 | rm | 2.5 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 | 166.16 | 0 |  | 166.16 | 0 | 166.16 | 0 | 110.85 | 110.85 | 0 | 7.8 | 7.8 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 121a | 79122 | 80567 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 0.6 | 1.5 | 1 | rm | 1.5 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 66.51 | 4.68 | 28.5 | 99.69 | 99.69 | 0 |  | 99.69 | 0 | 99.69 | 0 | 66.51 | 66.51 | 0 | 4.68 | 4.68 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 122 | 79123 | 80568 | Staircase 3 (KMEP BW-885) | Level 4 | Tower | 1 | 2.5 | 1 | 2 | 1 | rm | 2 | 2022-12-10 | 2022-12-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 38 | 132.92 | 132.92 | 0 |  | 132.92 | 0 | 132.92 | 0 | 88.68 | 88.68 | 0 | 6.24 | 6.24 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 123 | 79124 | 80593 | Electrical Work (BW -868) | Ground Level | Independent 1.8m wide | 1 | 5 | 1.8 | 3 | 1 | m2-LxH | 15 | 2022-12-10 | 2022-12-28 | 100% | 100% | 100% | 2.7143 | 16.76 | 0.77 | 175.98 | 31.35 | 75.42 | 282.75 | 282.75 | 0 |  | 282.75 | 0 | 282.75 | 0 | 252.67 | 252.67 | 0 | 54.03 | 54.03 | 0 | 108.29 | 108.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 123a | 79124 | 80594 | Electrical Work (BW -868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-12-10 | 2022-12-27 | 100% | 100% | 100% | 2.5714 | 36.52 | 2.94 | 76.69 | 22.68 | 32.87 | 132.24 | 132.24 | 0 |  | 132.24 | 0 | 132.24 | 0 | 252.67 | 252.67 | 0 | 54.03 | 54.03 | 0 | 108.29 | 108.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 124 | 79125 | 80888 | KMEP - BW 858 | Ground Level | Tower | 1 | 1.8 | 1.3 | 3 | 1 | rm | 3 | 2022-12-12 | 2023-01-16 | 100% | 100% | 100% | 5.1429 | 63.34 | 7.28 | 133.01 | 112.32 | 57.01 | 302.34 | 302.34 | 0 |  | 302.34 | 0 | 302.34 | 0 | 133.01 | 133.01 | 0 | 112.32 | 112.32 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 125 | 79126 | 80590 | LPG Tank For Wall Plaster Work | Ground Level | Independent | 1 | 4.3 | 1.3 | 1.5 | 1 | m2-LxH | 6.45 | 2022-12-12 | 2022-12-26 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 54.23 | 6.77 | 23.24 | 84.24 | 84.24 | 0 |  | 84.24 | 0 | 84.24 | 0 | 54.23 | 54.23 | 0 | 6.77 | 6.77 | 0 | 23.24 | 23.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 126 | 79127 | 82182 | Shaft For (KMEP - BW 892) | Level 5 | Tower | 1 | 1 | 0.6 | 4 | 2 | rm | 4 | 2022-12-12 | 2023-03-02 | 100% | 100% | 100% | 11.5714 | 63.34 | 7.28 | 177.35 | 336.96 | 76.01 | 590.32 | 493.51 | 96.81 |  | 493.51 | 96.81 | 590.32 | 0 | 177.35 | 177.35 | 0 | 336.96 | 316.16 | 20.8 | 76.01 | 0 | 76.01 | 96.81 | 96.81 | 0
E11/K149/SK/dm/213 | RESIDENCE | 127 | 79128 | 82183 | Shaft For (KMEP - BW 892) | Level 4 | Tower | 1 | 1 | 0.6 | 2.5 | 1 | rm | 2.5 | 2022-12-12 | 2023-03-02 | 100% | 100% | 100% | 11.5714 | 63.34 | 7.28 | 110.85 | 210.6 | 47.51 | 368.96 | 308.45 | 60.51 |  | 308.45 | 60.51 | 368.96 | 0 | 110.85 | 110.85 | 0 | 210.6 | 197.6 | 13 | 47.51 | 0 | 47.51 | 60.51 | 60.51 | 0
E11/K149/SK/dm/213 | RESIDENCE | 128 | 79129 | 80585 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent 1.8m wide | 1 | 11.8 | 2.5 | 3 | 1 | m2-LxH | 35.4 | 2022-12-12 | 2022-12-22 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 415.31 | 42.83 | 177.99 | 636.13 | 636.13 | 0 |  | 636.13 | 0 | 636.13 | 0 | 415.31 | 415.31 | 0 | 42.83 | 42.83 | 0 | 177.99 | 177.99 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 128a | 79130 | 80586 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent 1.8m wide | 1 | 4.3 | 2.5 | 2 | 1 | m2-LxH | 8.6 | 2022-12-12 | 2022-12-22 | 100% | 100% | 100% | 1.5714 | 16.76 | 0.77 | 100.9 | 10.41 | 43.24 | 154.55 | 154.55 | 0 |  | 154.55 | 0 | 154.55 | 0 | 100.9 | 100.9 | 0 | 10.41 | 10.41 | 0 | 43.24 | 43.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 129 | 79131 | 80877 | Ramp Area For Access | Ground Level | Tower | 1 | 2.5 | 0.9 | 1.2 | 1 | rm | 1.2 | 2022-12-12 | 2023-01-06 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 53.21 | 32.45 | 22.8 | 108.46 | 108.46 | 0 |  | 108.46 | 0 | 108.46 | 0 | 53.21 | 53.21 | 0 | 32.45 | 32.45 | 0 | 22.8 | 22.8 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 130&130a | 79132 | 80576 | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-13 | 2022-12-17 | 100% | 100% | 100% | 0.71429 | 1772.5845 | 52.192 | 1240.81 | 37.28 | 531.78 | 1809.87 | 1809.87 | 0 | Tas Quote 2439-25-1 (item#5) | 1809.87 | 0 | 1809.87 | 0 | 1240.81 | 1240.81 | 0 | 37.28 | 37.28 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 123b | 79133 | 80595 | Corridor For Electrical Work (BW - 868) | Ground Level | Independent 1.8m wide | 1 | 11.8 | 1.8 | 3 | 1 | m2-LxH | 35.4 | 2022-12-13 | 2022-12-28 | 100% | 100% | 100% | 2.2857 | 16.76 | 0.77 | 415.31 | 62.3 | 177.99 | 655.6 | 655.6 | 0 |  | 655.6 | 0 | 655.6 | 0 | 415.31 | 415.31 | 0 | 62.3 | 62.3 | 0 | 177.99 | 177.99 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 123c | 79134 | 80596 | Corridor For Electrical Work (BW - 868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-13 | 2022-12-27 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 153.38 | 37.8 | 65.74 | 256.92 | 256.92 | 0 |  | 256.92 | 0 | 256.92 | 0 | 153.38 | 153.38 | 0 | 37.8 | 37.8 | 0 | 65.74 | 65.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 131 | 79135 | 80597 | Over Head Protection | Ground Level | Independent 1.8m wide | 1 | 17.5 | 2.5 | 2 | 1 | m2-LxH | 35 | 2022-12-13 | 2022-12-28 | 100% | 100% | 100% | 2.2857 | 16.76 | 0.77 | 410.62 | 61.6 | 175.98 | 648.2 | 648.2 | 0 |  | 648.2 | 0 | 648.2 | 0 | 410.62 | 410.62 | 0 | 61.6 | 61.6 | 0 | 175.98 | 175.98 | 0 | 0 | 0 | 0
E11/K149/MS/dm/497 | RESIDENCE | 132 | 79136 | 80897 | Water Pool Glass Lifting Work | Level 10 | Design 1399-30 | 1 | 10.8 | 1.3 | 4.2 | 1 | unit | 1 | 2022-12-13 | 2023-01-13 | 100% | 100% | 100% | 4.5714 | 6054.579 | 536.9518 | 4238.21 | 2454.64 | 1816.37 | 8509.22 | 8509.22 | 0 | Tas Quote 2439-23-1 (Item #02) | 8509.22 | 0 | 8509.22 | 0 | 4238.21 | 4238.21 | 0 | 2454.64 | 2454.64 | 0 | 1816.37 | 1816.37 | 0 | 0 | 0 | 0
E11/K149/MS/dm/497 | RESIDENCE | 132a | 79137 | 80577 | Water Pool Glass Lifting Work | Level 10 | Design 1399-30 | 1 | 5.4 | 1.3 | 4.2 | 1 | unit | 1 | 2022-12-13 | 2022-12-16 | 100% | 100% | 100% | 0.57143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Tas Quote 2439-23-1 (Item #02) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 133 | 79138 | 80853 | Electrical Work (KMEP - BW 893) | Basement 1 | Independent | 1 | 7.3 | 1.3 | 5 | 1 | m2-LxH | 36.5 | 2022-12-14 | 2023-01-03 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 306.86 | 53.66 | 131.51 | 492.03 | 492.03 | 0 |  | 492.03 | 0 | 492.03 | 0 | 434.58 | 434.58 | 0 | 85.09 | 85.09 | 0 | 186.25 | 186.25 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 133 | 79138 | 80853 | Electrical Work (KMEP - BW 893) | Basement 1 | Additional Boarding | 1 | 7.3 | 1.3 | 1 | 1 | m2-LxW | 9.49 | 2022-12-14 | 2023-01-03 | 100% | 100% | 100% | 3 | 6.63 | 0.7 | 44.04 | 19.93 | 18.88 | 82.85 | 82.85 | 0 |  | 82.85 | 0 | 82.85 | 0 | 434.58 | 434.58 | 0 | 85.09 | 85.09 | 0 | 186.25 | 186.25 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 133a | 79138 | 80853 | Electrical Work (KMEP - BW 893) | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 7.3 | 0.5 | 1 | 1 | m2-LxW | 3.65 | 2022-12-14 | 2023-01-03 | 100% | 100% | 100% | 3 | 32.75 | 1.05 | 83.68 | 11.5 | 35.86 | 131.04 | 131.04 | 0 |  | 131.04 | 0 | 131.04 | 0 | 434.58 | 434.58 | 0 | 85.09 | 85.09 | 0 | 186.25 | 186.25 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 128b | 79139 | 80587 | Mechanical Work (KMEP - BW 887) | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2022-12-14 | 2022-12-22 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 133.01 | 28.08 | 57.01 | 218.1 | 218.1 | 0 |  | 218.1 | 0 | 218.1 | 0 | 133.01 | 133.01 | 0 | 28.08 | 28.08 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 134 | 79140 | 78621 | EIFS Fixing Work | Ground Level | Independent | 1 | 3.8 | 1.3 | 4 | 1 | m2-LxH | 15.2 | 2022-12-14 | 2023-02-02 | 100% | 100% | 100% | 7.2857 | 12.01 | 0.49 | 127.79 | 54.26 | 54.77 | 236.82 | 236.82 | 0 |  | 236.82 | 0 | 236.82 | 0 | 150.72 | 150.72 | 0 | 79.45 | 79.45 | 0 | 64.6 | 64.6 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 134 | 79140 | 78621 | EIFS Fixing Work | Ground Level | Additional Boarding | 1 | 3.8 | 1.3 | 1 | 1 | m2-LxW | 4.94 | 2022-12-14 | 2023-02-02 | 100% | 100% | 100% | 7.2857 | 6.63 | 0.7 | 22.93 | 25.19 | 9.83 | 57.95 | 57.95 | 0 |  | 57.95 | 0 | 57.95 | 0 | 150.72 | 150.72 | 0 | 79.45 | 79.45 | 0 | 64.6 | 64.6 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 135 | 79141 | 78622 | EIFS Fixing Work | Ground Level | Independent | 1 | 11.8 | 1.3 | 4 | 1 | m2-LxH | 47.2 | 2022-12-14 | 2023-02-02 | 100% | 100% | 0% | 7.2857 | 12.01 | 0.49 | 396.81 | 168.5 | 0 | 565.31 | 565.31 | 0 |  | 565.31 | 0 | 565.31 | 0 | 468 | 468 | 0 | 246.73 | 246.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 135 | 79141 | 78622 | EIFS Fixing Work | Ground Level | Additional Boarding | 1 | 11.8 | 1.3 | 1 | 1 | m2-LxW | 15.34 | 2022-12-14 | 2023-02-02 | 100% | 100% | 0% | 7.2857 | 6.63 | 0.7 | 71.19 | 78.23 | 0 | 149.42 | 149.42 | 0 |  | 149.42 | 0 | 149.42 | 0 | 468 | 468 | 0 | 246.73 | 246.73 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 139&139a | 79144 | 80589 | Balcony Ceiling Work | Level 19 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-15 | 2022-12-22 | 100% | 100% | 100% | 1.1429 | 1772.5845 | 52.192 | 1240.81 | 59.65 | 531.78 | 1832.24 | 1832.24 | 0 | Tas Quote 2439-25-1 (item#5) | 1832.24 | 0 | 1832.24 | 0 | 1240.81 | 1240.81 | 0 | 59.65 | 59.65 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 44a | 79147 | 78623 | EIFS Wall Finishing Work | Ground Level | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-12-15 | 2023-02-02 | 100% | 100% | 100% | 7.1429 | 6.63 | 0.7 | 18.56 | 20 | 7.96 | 46.52 | 46.52 | 0 |  | 46.12 | 0.4 | 46.52 | -0.4 | 18.56 | 18.56 | 0 | 20 | 19.6 | 0.4 | 7.96 | 7.96 | 0 | 0 | 0.4 | -0.4
E11/K149/SK/dm/213 | RESIDENCE | 45a | 79148 | 78624 | EIFS Wall Finishing Work | Ground Level | Additional Boarding | 1 | 4 | 1 | 1 | 1 | m2-LxW | 4 | 2022-12-15 | 2023-02-02 | 100% | 100% | 100% | 7.1429 | 6.63 | 0.7 | 18.56 | 20 | 7.96 | 46.52 | 46.52 | 0 |  | 46.52 | 0 | 46.52 | 0 | 18.56 | 18.56 | 0 | 20 | 20 | 0 | 7.96 | 7.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 137 | 79149 | 80854 | Planter Access | Ground Level | Independent | 1 | 3.5 | 1.3 | 1 | 1 | m2-LxH | 3.5 | 2022-12-15 | 2023-01-03 | 100% | 100% | 100% | 2.8571 | 12.01 | 0.49 | 29.42 | 4.9 | 12.61 | 46.93 | 46.93 | 0 |  | 46.93 | 0 | 46.93 | 0 | 29.42 | 29.42 | 0 | 4.9 | 4.9 | 0 | 12.61 | 12.61 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 138 | 79150 |  | Staircase Edge Protection | Ground Level | Double Handrail | 1 | 37.5 |  | 1 |  | lm | 37.5 | 2022-12-15 |  | 100% | 100% | 0% | 14.4286 | 15 | 0.91 | 393.75 | 492.38 | 0 | 886.13 | 749.63 | 136.5 |  | 749.63 | 136.5 | 886.13 | 0 | 393.75 | 393.75 | 0 | 492.38 | 355.88 | 136.5 | 0 | 0 | 0 | 136.5 | 136.5 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136 | 79152 |  | Over Head Protection | Level 2 | Independent 1.8m wide | 1 | 10.8 | 2.5 | 2.5 | 1 | m2-LxH | 27 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 16.76 | 0.77 | 316.76 | 302.94 | 0 | 619.7 | 536.54 | 83.16 |  | 536.54 | 83.16 | 619.7 | 0 | 517.39 | 517.39 | 0 | 579.26 | 420.25 | 159.01 | 0 | 0 | 0 | 159.01 | 159.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136a | 79152 |  | Over Head Protection | Level 2 | Buttress | 1 | 4.3 | 1.8 | 7 |  | m3 | 54.18 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 5.29 | 0.35 | 200.63 | 276.32 | 0 | 476.95 | 401.1 | 75.85 |  | 401.1 | 75.85 | 476.95 | 0 | 517.39 | 517.39 | 0 | 579.26 | 420.25 | 159.01 | 0 | 0 | 0 | 159.01 | 159.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136e | 79162 |  | Over Head Protection | ground Level | Independent 1.8m wide | 1 | 3.8 | 2.5 | 4 | 1 | m2-LxH | 15.2 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 16.76 | 0.77 | 178.33 | 170.54 | 0 | 348.87 | 302.06 | 46.81 |  | 302.06 | 46.81 | 348.87 | 0 | 389.51 | 389.51 | 0 | 372.5 | 270.25 | 102.25 | 0 | 0 | 0 | 102.25 | 102.25 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136f | 79162 |  | Over Head Protection | ground Level | Independent 1.8m wide | 1 | 3.6 | 2.5 | 5 | 1 | m2-LxH | 18 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 16.76 | 0.77 | 211.18 | 201.96 | 0 | 413.14 | 357.7 | 55.44 |  | 357.7 | 55.44 | 413.14 | 0 | 389.51 | 389.51 | 0 | 372.5 | 270.25 | 102.25 | 0 | 0 | 0 | 102.25 | 102.25 | 0
E11/K149/SK/dm/213 | RESIDENCE | 128c | 79154 | 80588 | Mechanical Work (KMEP - BW 887) | Basement 1 | Independent | 1 | 4.3 | 1 | 1.5 | 1 | m2-LxH | 6.45 | 2022-12-15 | 2022-12-22 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 54.23 | 3.61 | 23.24 | 81.08 | 81.08 | 0 |  | 81.08 | 0 | 81.08 | 0 | 54.23 | 54.23 | 0 | 3.61 | 3.61 | 0 | 23.24 | 23.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 140 | 79155 | 80581 | KMEP - BW 797 | Level 5 | Tower | 1 | 1.8 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-12-16 | 2022-12-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 66.51 | 6.24 | 28.5 | 101.25 | 101.25 | 0 |  | 101.25 | 0 | 101.25 | 0 | 66.51 | 66.51 | 0 | 6.24 | 6.24 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 141&141a | 79156 | 80583 | Balcony Ceiling Work | Level 18 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-16 | 2022-12-21 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 142&142a | 79157 | 80584 | Balcony Ceiling Work | Level 18 | Design 1399 - 35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-16 | 2022-12-21 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 143 | 79159 | 79893 | Beam Drilling Work | Level 31 | Tower | 3 | 1 | 0.75 | 0.6 | 1 | rm | 1.8 | 2022-12-17 | 2023-03-18 | 100% | 100% | 100% | 13.1429 | 63.34 | 7.28 | 79.81 | 172.22 | 34.2 | 286.23 | 212.72 | 73.51 |  | 212.72 | 73.51 | 286.23 | 0 | 79.81 | 79.81 | 0 | 172.22 | 132.91 | 39.31 | 34.2 | 0 | 34.2 | 73.51 | 73.51 | 0
E11/K149/SK/dm/480 | RESIDENCE | 144 | 79160 | 808666 | Shaft 9 Slab Concrete | Level 31 | Design 1399 - 25a | 1 |  |  |  |  | unit | 1 | 2022-12-17 | 2023-01-04 | 100% | 100% | 100% | 2.7143 | 3381.02 | 181.02 | 2366.71 | 491.34 | 1014.31 | 3872.36 | 3872.36 | 0 | Tas Quote 2439-22-1 (Item # 1) | 3872.36 | 0 | 3872.36 | 0 | 2366.71 | 2366.71 | 0 | 491.34 | 491.34 | 0 | 1014.31 | 1014.31 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136b | 79161 |  | Over Head Protection | Ground Level | Buttress | 1 | 3.6 | 1.3 | 4 |  | m3 | 18.72 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 5.29 | 0.35 | 69.32 | 95.47 | 0 | 164.79 | 138.58 | 26.21 |  | 138.58 | 26.21 | 164.79 | 0 | 150.64 | 150.64 | 0 | 207.47 | 150.51 | 56.96 | 0 | 0 | 0 | 56.96 | 56.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136c | 79161 |  | Over Head Protection | Ground Level | Buttress | 1 | 3.6 | 1.3 | 2.5 |  | m3 | 11.7 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 5.29 | 0.35 | 43.33 | 59.67 | 0 | 103 | 86.62 | 16.38 |  | 86.62 | 16.38 | 103 | 0 | 150.64 | 150.64 | 0 | 207.47 | 150.51 | 56.96 | 0 | 0 | 0 | 56.96 | 56.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 136d | 79161 |  | Over Head Protection | Ground Level | Buttress | 1 | 3.8 | 0.9 | 3 |  | m3 | 10.26 | 2022-12-14 |  | 100% | 100% | 0% | 14.5714 | 5.29 | 0.35 | 37.99 | 52.33 | 0 | 90.32 | 75.95 | 14.37 |  | 75.95 | 14.37 | 90.32 | 0 | 150.64 | 150.64 | 0 | 207.47 | 150.51 | 56.96 | 0 | 0 | 0 | 56.96 | 56.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 123d | 79163 | 80598 | Electrical Work (BW -868) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-19 | 2022-12-28 | 100% | 100% | 100% | 1.4286 | 36.52 | 2.94 | 153.38 | 25.2 | 65.74 | 244.32 | 244.32 | 0 |  | 244.32 | 0 | 244.32 | 0 | 153.38 | 153.38 | 0 | 25.2 | 25.2 | 0 | 65.74 | 65.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 | 79164 |  | GRC Panel Work | Level 31 | Independent 1.8m wide | 1 | 17.8 | 1.8 | 5 | 1 | m2-LxH | 89 | 2022-12-19 |  | 100% | 100% | 0% | 13.8571 | 12.01 | 0.49 | 748.22 | 604.31 | 0 | 1352.53 | 1178.09 | 174.44 |  | 1178.09 | 174.44 | 1352.53 | 0 | 748.22 | 748.22 | 0 | 604.31 | 429.87 | 174.44 | 0 | 0 | 0 | 174.44 | 174.44 | 0
E11/K149/SK/dm/213 | RESIDENCE | 146 | 79165 | 80882 | Beam Drilling Work | Level 31 | Tower | 1 | 1 | 1 | 1 | 1 | rm | 1 | 2022-12-19 | 2023-01-11 | 100% | 100% | 100% | 3.4286 | 63.34 | 7.28 | 44.34 | 24.96 | 19 | 88.3 | 88.3 | 0 |  | 88.3 | 0 | 88.3 | 0 | 44.34 | 44.34 | 0 | 24.96 | 24.96 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 147 | 79166 | 78602 | Beam Drilling Work | Level 31 | Tower | 1 | 1 | 1 | 1 | 1 | rm | 1 | 2022-12-19 | 2023-01-24 | 100% | 100% | 100% | 5.2857 | 63.34 | 7.28 | 44.34 | 38.48 | 19 | 101.82 | 101.82 | 0 |  | 101.82 | 0 | 101.82 | 0 | 44.34 | 44.34 | 0 | 38.48 | 38.48 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 148 | 79167 | 78625 | EIFS Wall Finishing Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 4 | 1 | m2-LxH | 25.2 | 2022-12-20 | 2023-02-02 | 100% | 100% | 100% | 6.4286 | 12.01 | 0.49 | 211.86 | 79.38 | 90.8 | 382.04 | 382.04 | 0 |  | 382.04 | 0 | 382.04 | 0 | 211.86 | 211.86 | 0 | 79.38 | 79.38 | 0 | 90.8 | 90.8 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 68b | 79168 |  | Electrical Work (KMEP - BW 754) | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-12-20 |  | 100% | 100% | 0% | 13.7143 | 6.63 | 0.7 | 15.08 | 31.2 | 0 | 46.28 | 37.18 | 9.1 |  | 37.18 | 9.1 | 46.28 | 0 | 15.08 | 15.08 | 0 | 31.2 | 22.1 | 9.1 | 0 | 0 | 0 | 9.1 | 9.1 | 0
E11/K149/SK/dm/213 | RESIDENCE | 149 | 79169 | 78644 | Near KCE Office For Access | Ground Level | Tower | 1 | 1.8 | 1.3 | 1.25 | 1 | rm | 1.25 | 2022-12-21 | 2023-02-10 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 55.42 | 67.6 | 23.75 | 146.77 | 146.77 | 0 |  | 146.77 | 0 | 146.77 | 0 | 55.42 | 55.42 | 0 | 67.6 | 67.6 | 0 | 23.75 | 23.75 | 0 | 0 | 0 | 0
E11/K149/SK/SR/503 | RESIDENCE | 150 Ext - a,b | 79170 | 78648 | Block and EIFS Work | Level 10 to 17 | Design 1399 - 29 | 1 |  |  |  |  | unit | 1 | 2022-12-21 | 2023-02-14 | 100% | 100% | 100% | 8 | 34922.6 | 1384.55 | 24445.82 | 11076.4 | 10476.78 | 45999 | 45999 | 0 | Tas Quote 2439-24-1 (Item #4) | 45999 | 0 | 45999 | 0 | 24445.82 | 24445.82 | 0 | 11076.4 | 11076.4 | 0 | 10476.78 | 10476.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8x | 79171 |  | Balcony Access | Level 27/28 | Additional Boarding | 1 | 1.8 | 1.8 | 1 | 1 | m2-LxW | 3.24 | 2022-12-21 |  | 100% | 100% | 0% | 13.5714 | 6.63 | 0.7 | 15.04 | 30.78 | 0 | 45.82 | 36.75 | 9.07 |  | 36.75 | 9.07 | 45.82 | 0 | 15.04 | 15.04 | 0 | 30.78 | 21.71 | 9.07 | 0 | 0 | 0 | 9.07 | 9.07 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8y | 79172 |  | Balcony Access | Level 27/28 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1 | 1 | 1 | m2-LxW | 1.8 | 2022-12-21 |  | 100% | 100% | 0% | 13.5714 | 36.52 | 2.94 | 46.02 | 71.82 | 0 | 117.84 | 96.67 | 21.17 |  | 96.67 | 21.17 | 117.84 | 0 | 46.02 | 46.02 | 0 | 71.82 | 50.65 | 21.17 | 0 | 0 | 0 | 21.17 | 21.17 | 0
E11/K149/SK/dm/213 | RESIDENCE | 151 | 79173 |  | Balcony Ceiling Work | Level 26 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-22 |  | 100% | 100% | 0% | 13.4286 | 63.34 | 7.28 | 88.68 | 195.52 | 0 | 284.2 | 225.96 | 58.24 |  | 225.96 | 58.24 | 284.2 | 0 | 88.68 | 88.68 | 0 | 195.52 | 137.28 | 58.24 | 0 | 0 | 0 | 58.24 | 58.24 | 0
E11/K149/SK/dm/213 | RESIDENCE | 152 | 79174 |  | Balcony Ceiling Work | Level 27 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-22 |  | 100% | 100% | 0% | 13.4286 | 63.34 | 7.28 | 88.68 | 195.52 | 0 | 284.2 | 225.96 | 58.24 |  | 225.96 | 58.24 | 284.2 | 0 | 88.68 | 88.68 | 0 | 195.52 | 137.28 | 58.24 | 0 | 0 | 0 | 58.24 | 58.24 | 0
E11/K149/SK/dm/213 | HOTEL | 48b | 79060 | 80836 | Balcony Floor Drain Work | Level 12 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2022-11-26 | 2022-12-21 | 100% | 100% | 100% | 3.7143 | 63.34 | 7.28 | 66.51 | 40.56 | 28.5 | 135.57 | 135.57 | 0 |  | 135.57 | 0 | 135.57 | 0 | 66.51 | 66.51 | 0 | 40.56 | 40.56 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/JA/dm/429 | HOTEL | 60 | 79061 | 79935 | Balcony Access | Level 22 | Tower | 1 | 2.5 | 1.3 | 3.7 | 1 | unit | 1 | 2022-11-26 | 2023-03-17 | 100% | 100% | 100% | 16 | 1182.48 | 26.94 | 827.74 | 431.04 | 354.74 | 1613.52 | 1181.81 | 431.71 | Tas Quote 2439-20-1 (Item #08) | 1181.81 | 431.71 | 1613.52 | 0 | 894.21 | 894.21 | 0 | 553.34 | 454.53 | 98.81 | 383.23 | 0 | 383.23 | 482.04 | 482.04 | 0
E11/K149/SK/dm/213 | HOTEL | 60a | 79061 | 79935 | Balcony Access | Level 22 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.3 | 1 | 1 | m2-LxW | 2.6 | 2022-11-26 | 2023-03-17 | 100% | 100% | 100% | 16 | 36.52 | 2.94 | 66.47 | 122.3 | 28.49 | 217.26 | 166.93 | 50.33 |  | 166.93 | 50.33 | 217.26 | 0 | 894.21 | 894.21 | 0 | 553.34 | 454.53 | 98.81 | 383.23 | 0 | 383.23 | 482.04 | 482.04 | 0
E11/K149/SK/dm/213 | HOTEL | 61 | 79062 | 76840 | Electrical Service Work | Basement 1 | Independent 1.8m wide | 1 | 29.3 | 2.5 | 2 | 1 | m2-LxH | 58.6 | 2022-11-28 | 2022-12-05 | 100% | 100% | 100% | 1.1429 | 16.76 | 0.77 | 687.5 | 51.57 | 294.64 | 1033.71 | 1033.71 | 0 |  | 1033.71 | 0 | 1033.71 | 0 | 687.5 | 687.5 | 0 | 51.57 | 51.57 | 0 | 294.64 | 294.64 | 0 | 0 | 0 | 0
E11/K149/JA/dm/429 | HOTEL | 62 | 79063 |  | Balcony For Access | Level 17 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | unit | 1 | 2022-11-28 |  | 100% | 100% | 0% | 16.8571 | 1278.36 | 29.12 | 894.85 | 490.88 | 0 | 1385.73 | 1269.25 | 116.48 | Tas Quote 2439-20-1 (Item #05) | 1269.25 | 116.48 | 1385.73 | 0 | 933.2 | 933.2 | 0 | 565.22 | 431.1 | 134.12 | 0 | 0 | 0 | 134.12 | 134.12 | 0
E11/K149/SK/dm/213 | HOTEL | 62a | 79063 |  | Balcony For Access | Level 17 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 | 1 | 1 | m2-LxW | 1.5 | 2022-11-28 |  | 100% | 100% | 0% | 16.8571 | 36.52 | 2.94 | 38.35 | 74.34 | 0 | 112.69 | 95.05 | 17.64 |  | 95.05 | 17.64 | 112.69 | 0 | 933.2 | 933.2 | 0 | 565.22 | 431.1 | 134.12 | 0 | 0 | 0 | 134.12 | 134.12 | 0
E11/K149/SK/dm/213 | HOTEL | 63 | 79064 | 76841 | FAHU Oil Leakge (BW -783) | Basement 1 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2022-11-29 | 2022-12-05 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 155.18 | 25.48 | 66.51 | 247.17 | 247.17 | 0 |  | 247.17 | 0 | 247.17 | 0 | 155.18 | 155.18 | 0 | 25.48 | 25.48 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 61a | 79065 | 76838 | Electrical Service Work | Basement 1 | Independent 1.8m wide | 1 | 15 | 2.5 | 2.3 | 1 | m2-LxH | 34.5 | 2022-11-29 | 2022-11-30 | 100% | 100% | 100% | 0.28571 | 16.76 | 0.77 | 404.75 | 7.59 | 173.47 | 585.81 | 585.81 | 0 |  | 585.81 | 0 | 585.81 | 0 | 404.75 | 404.75 | 0 | 7.59 | 7.59 | 0 | 173.47 | 173.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 62b | 79066 |  | Edge Protection | Level 18 | Double Handrail | 1 | 8 | 1 | 1 |  | lm | 8 | 2022-11-30 |  | 100% | 100% | 0% | 16.5714 | 15 | 0.91 | 84 | 120.64 | 0 | 204.64 | 175.52 | 29.12 |  | 175.52 | 29.12 | 204.64 | 0 | 84 | 84 | 0 | 120.64 | 91.52 | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | -2.8422e-14
E11/K149/SK/dm/213 | HOTEL | 57b | 79067 | 80846 | Balcony Drain Pipe Work | Level 19 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2022-11-30 | 2022-12-29 | 100% | 100% | 100% | 4.2857 | 63.34 | 7.28 | 66.51 | 46.8 | 28.5 | 141.81 | 141.81 | 0 |  | 141.81 | 0 | 141.81 | 0 | 66.51 | 66.51 | 0 | 46.8 | 46.8 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 43d | 79068 | 80932 | EIFS Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 14.5 | 0.75 | 1 | 1 | m2-LxW | 10.88 | 2022-12-05 | 2023-01-30 | 100% | 100% | 100% | 8.1429 | 36.52 | 2.94 | 278.14 | 260.47 | 119.2 | 657.81 | 657.81 | 0 |  | 657.81 | 0 | 657.81 | 0 | 278.14 | 278.14 | 0 | 260.47 | 260.47 | 0 | 119.2 | 119.2 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 64 | 79069 |  | Plant Room For Wall Finishing Work | Ground Level | Independent | 1 | 6.8 | 0.9 | 3 | 1 | m2-LxH | 20.4 | 2022-12-07 |  | 100% | 100% | 0% | 15.5714 | 12.01 | 0.49 | 171.5 | 155.65 | 0 | 327.15 | 287.17 | 39.98 |  | 287.17 | 39.98 | 327.15 | 0 | 181.94 | 181.94 | 0 | 180.18 | 133.9 | 46.28 | 0 | 0 | 0 | 46.28 | 46.28 | 0
E11/K149/SK/dm/213 | HOTEL | 64a | 79069 |  | Plant Room For Wall Finishing Work | Ground Level | Additional Boarding | 1 | 2.5 | 0.9 | 1 | 1 | m2-LxW | 2.25 | 2022-12-07 |  | 100% | 100% | 0% | 15.5714 | 6.63 | 0.7 | 10.44 | 24.53 | 0 | 34.97 | 28.67 | 6.3 |  | 28.67 | 6.3 | 34.97 | 0 | 181.94 | 181.94 | 0 | 180.18 | 133.9 | 46.28 | 0 | 0 | 0 | 46.28 | 46.28 | 0
E11/K149/SK/dm/213 | HOTEL | 65 | 79070 | 80848 | EIFS Finishing Work (Hotel Behind Kitchen) | Level 2 | Independent | 1 | 4 | 1 | 5.5 | 1 | m2-LxH | 22 | 2022-12-09 | 2022-12-30 | 100% | 100% | 100% | 3.1429 | 12.01 | 0.49 | 184.95 | 33.88 | 79.27 | 298.1 | 298.1 | 0 |  | 298.1 | 0 | 298.1 | 0 | 222.08 | 222.08 | 0 | 51.48 | 51.48 | 0 | 95.18 | 95.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 65 | 79070 | 80848 | EIFS Finishing Work (Hotel Behind Kitchen) | Level 2 | Additional Boarding | 2 | 4 | 1 | 1 | 2 | m2-LxW | 8 | 2022-12-09 | 2022-12-30 | 100% | 100% | 100% | 3.1429 | 6.63 | 0.7 | 37.13 | 17.6 | 15.91 | 70.64 | 70.64 | 0 |  | 70.64 | 0 | 70.64 | 0 | 222.08 | 222.08 | 0 | 51.48 | 51.48 | 0 | 95.18 | 95.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 66 | 79071 | 80909 | EIFS Damac Side Elevation | Level 2 | Independent | 1 | 13.6 | 0.9 | 1.5 | 1 | m2-LxH | 20.4 | 2022-12-09 | 2023-01-12 | 100% | 100% | 100% | 5 | 12.01 | 0.49 | 171.5 | 49.98 | 73.5 | 294.98 | 294.98 | 0 |  | 294.98 | 0 | 294.98 | 0 | 171.5 | 171.5 | 0 | 49.98 | 49.98 | 0 | 73.5 | 73.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 66a | 79072 | 80909 | EIFS Damac Side Elevation | Level 2 | Cantilever (0 < 0.5m width) | 1 | 14.5 | 0.5 | 1 | 1 | m2-LxW | 7.25 | 2022-12-09 | 2023-01-12 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 166.21 | 38.06 | 71.23 | 275.5 | 275.5 | 0 |  | 275.5 | 0 | 275.5 | 0 | 166.21 | 166.21 | 0 | 38.06 | 38.06 | 0 | 71.23 | 71.23 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 66b | 79073 | 80910 | EIFS Damac Side Elevation | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1.4 | 1 | 1 | m2-LxW | 2.52 | 2022-12-09 | 2023-01-12 | 100% | 100% | 100% | 5 | 32.75 | 1.05 | 57.77 | 13.23 | 24.76 | 95.76 | 95.76 | 0 |  | 95.76 | 0 | 95.76 | 0 | 57.77 | 57.77 | 0 | 13.23 | 13.23 | 0 | 24.76 | 24.76 | 0 | 0 | 0 | 0
E11/K149/JA/dm/429 | HOTEL | 67 | 79074 |  | Balcony Access | Level 26 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | unit | 1 | 2022-12-09 |  | 100% | 100% | 0% | 15.2857 | 1118.565 | 25.48 | 783 | 389.48 | 0 | 1172.48 | 1070.56 | 101.92 | Tas Quote 2439-20-1 (Item #10) | 1070.56 | 101.92 | 1172.48 | 0 | 851.78 | 851.78 | 0 | 437.63 | 323.11 | 114.52 | 0 | 0 | 0 | 114.52 | 114.52 | 0
E11/K149/SK/dm/213 | HOTEL | 67a | 79074 |  | Balcony Access | Level 27 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2022-12-09 |  | 100% | 100% | 0% | 15.2857 | 32.75 | 1.05 | 68.78 | 48.15 | 0 | 116.93 | 104.33 | 12.6 |  | 104.33 | 12.6 | 116.93 | 0 | 851.78 | 851.78 | 0 | 437.63 | 323.11 | 114.52 | 0 | 0 | 0 | 114.52 | 114.52 | 0
E11/K149/SK/dm/213 | HOTEL | 68 | 79075 | 80842 | Canal Side Balcony For Grc Work | Level 24 | Independent | 1 | 8.1 | 1.5 | 2.5 | 1 | m2-LxH | 20.25 | 2022-12-09 | 2022-12-22 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 170.24 | 19.85 | 72.96 | 263.05 | 263.05 | 0 |  | 263.05 | 0 | 263.05 | 0 | 170.24 | 170.24 | 0 | 19.85 | 19.85 | 0 | 72.96 | 72.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 43e | 79076 | 80933 | Ramp Area For Wall Plaster Work | Ground Level | Independent | 1 | 13 | 1 | 1.5 | 1 | m2-LxH | 19.5 | 2022-12-10 | 2023-01-30 | 100% | 100% | 100% | 7.4286 | 12.01 | 0.49 | 163.94 | 70.98 | 70.26 | 305.18 | 305.18 | 0 |  | 305.18 | 0 | 305.18 | 0 | 163.94 | 163.94 | 0 | 70.98 | 70.98 | 0 | 70.26 | 70.26 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 69 | 79077 | 80849 | Balcony Ceiling Work | Level 7 | Design 1399-35b | 1 | 5.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2022-12-31 | 100% | 100% | 100% | 2.1429 | 2184.8135 | 64.3297 | 1529.37 | 137.85 | 655.44 | 2322.66 | 2322.66 | 0 | Tas Quote 2439-25-1 (item#5) | 2322.66 | 0 | 2322.66 | 0 | 1529.37 | 1529.37 | 0 | 137.85 | 137.85 | 0 | 655.44 | 655.44 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 70 | 79078 | 79906 | Electrical Work For (KMEP - BW917) | Ground Level | Independent | 1 | 6.3 | 1.3 | 4 | 1 | m2-LxH | 25.2 | 2022-12-17 | 2023-03-15 | 100% | 100% | 100% | 12.7143 | 12.01 | 0.49 | 211.86 | 157 | 90.8 | 459.66 | 337.1 | 122.56 |  | 337.1 | 122.56 | 459.66 | 0 | 211.86 | 211.86 | 0 | 157 | 125.24 | 31.76 | 90.8 | 0 | 90.8 | 122.56 | 122.56 | 0
E11/K149/SK/dm/213 | HOTEL | 70a | 79079 | 79907 | Electrical Work For (KMEP - BW917) | Ground Level | Tower | 1 | 2.5 | 2.5 | 4 | 1 | rm | 4 | 2022-12-17 | 2023-03-15 | 100% | 100% | 100% | 12.7143 | 63.34 | 7.28 | 177.35 | 370.24 | 76.01 | 623.6 | 472.71 | 150.89 |  | 472.71 | 150.89 | 623.6 | 0 | 177.35 | 177.35 | 0 | 370.24 | 295.36 | 74.88 | 76.01 | 0 | 76.01 | 150.89 | 150.89 | 0
E11/K149/SK/SR/517 | HOTEL | 71&71a | 79082 | 80850 | Balcony Ceiling Work | Level 9 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2022-12-31 | 100% | 100% | 100% | 2.1429 | 1772.5845 | 52.192 | 1240.81 | 111.84 | 531.78 | 1884.43 | 1884.43 | 0 | Tas Quote 2439-25-1 (item#5) | 1884.43 | 0 | 1884.43 | 0 | 1240.81 | 1240.81 | 0 | 111.84 | 111.84 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 72&72a | 79083 | 80901 | Balcony Ceiling Work | Level 9 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2022-12-31 | 100% | 100% | 100% | 2.1429 | 1772.5845 | 52.192 | 1240.81 | 111.84 | 531.78 | 1884.43 | 1884.43 | 0 | Tas Quote 2439-25-1 (item#5) | 1884.43 | 0 | 1884.43 | 0 | 1240.81 | 1240.81 | 0 | 111.84 | 111.84 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 73&73a | 79084 | 79820 | Balcony Ceiling Work | Level 11 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2023-03-01 | 100% | 100% | 100% | 10.7143 | 1772.5845 | 52.192 | 1240.81 | 559.2 | 531.78 | 2331.79 | 1770.19 | 561.6 | Tas Quote 2439-25-1 (item#5) | 1770.19 | 561.6 | 2331.79 | 0 | 1240.81 | 1240.81 | 0 | 559.2 | 529.38 | 29.82 | 531.78 | 0 | 531.78 | 561.6 | 561.6 | 0
E11/K149/SK/SR/517 | HOTEL | 74&74a | 79085 | 79819 | Balcony Ceiling Work | Level 11 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-17 | 2023-03-01 | 100% | 100% | 100% | 10.7143 | 1772.5845 | 52.192 | 1240.81 | 559.2 | 531.78 | 2331.79 | 1770.19 | 561.6 | Tas Quote 2439-25-1 (item#5) | 1770.19 | 561.6 | 2331.79 | 0 | 1240.81 | 1240.81 | 0 | 559.2 | 529.38 | 29.82 | 531.78 | 0 | 531.78 | 561.6 | 561.6 | 0
E11/K149/SK/dm/213 | HOTEL | 75 | 79086 | 80843 | Staircase 7 For (KMEP - BW 793) | Ground Level | Tower | 1 | 1.8 | 1 | 1.2 | 1 | rm | 1.2 | 2022-12-20 | 2022-12-26 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 53.21 | 8.74 | 22.8 | 84.75 | 84.75 | 0 |  | 84.75 | 0 | 84.75 | 0 | 53.21 | 53.21 | 0 | 8.74 | 8.74 | 0 | 22.8 | 22.8 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 76&76a | 79087 | 80904 | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-21 | 2023-01-11 | 100% | 100% | 100% | 3.1429 | 1772.5845 | 52.192 | 1240.81 | 164.03 | 531.78 | 1936.62 | 1936.62 | 0 | Tas Quote 2439-25-1 (item#5) | 1936.62 | 0 | 1936.62 | 0 | 1240.81 | 1240.81 | 0 | 164.03 | 164.03 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 70b | 79088 | 79908 | Electrical Work (KMEP - BW 917) | Ground Level | Additional Boarding | 1 | 3.8 | 1.3 | 1 | 1 | m2-LxW | 4.94 | 2022-12-21 | 2023-03-15 | 100% | 100% | 100% | 12.1429 | 6.63 | 0.7 | 22.93 | 41.99 | 9.83 | 74.75 | 56.03 | 18.72 |  | 56.03 | 18.72 | 74.75 | 0 | 22.93 | 22.93 | 0 | 41.99 | 33.1 | 8.89 | 9.83 | 0 | 9.83 | 18.72 | 18.72 | 0
E11/K149/SK/dm/213 | HOTEL | 70c | 79089 | 79908 | Electrical Work (KMEP - BW 917) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 4 | 0.5 | 1 | 1 | m2-LxW | 2 | 2022-12-21 | 2023-03-15 | 100% | 100% | 100% | 12.1429 | 32.75 | 1.05 | 45.85 | 25.5 | 19.65 | 91 | 65.95 | 25.05 |  | 65.95 | 25.05 | 91 | 0 | 45.85 | 45.85 | 0 | 25.5 | 20.1 | 5.4 | 19.65 | 0 | 19.65 | 25.05 | 25.05 | 0
E11/K149/SK/dm/213 | HOTEL | 77 | 79090 | 79909 | Entrance Area (KMEP - BW 917) | Ground Level | Tower | 1 | 1.3 | 1.3 | 4 | 2 | rm | 4 | 2022-12-22 | 2023-03-15 | 100% | 100% | 100% | 12 | 63.34 | 7.28 | 177.35 | 349.44 | 76.01 | 602.8 | 451.91 | 150.89 |  | 451.91 | 150.89 | 602.8 | 0 | 177.35 | 177.35 | 0 | 349.44 | 274.56 | 74.88 | 76.01 | 0 | 76.01 | 150.89 | 150.89 | 0
E11/K149/SK/dm/213 | HOTEL | 51b | 79091 | 78600 | Staircase 7 For (KMEP - BW 793) | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2022-12-22 | 2023-02-22 | 100% | 100% | 100% | 9 | 6.63 | 0.7 | 15.08 | 20.48 | 6.46 | 42.02 | 42.02 | 0 |  | 42.02 | 0 | 42.02 | 0 | 15.08 | 15.08 | 0 | 20.48 | 20.48 | 0 | 6.46 | 6.46 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 78&78a | 79092 | 80905 | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-22 | 2023-01-11 | 100% | 100% | 100% | 3 | 1772.5845 | 52.192 | 1240.81 | 156.58 | 531.78 | 1929.17 | 1929.17 | 0 | Tas Quote 2439-25-1 (item#5) | 1929.17 | 0 | 1929.17 | 0 | 1240.81 | 1240.81 | 0 | 156.58 | 156.58 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/550 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-19 |  | 0% | 100% | 0% | 13.8571 | 0 | 200 | 0 | 2771.43 | 0 | 2771.43 | 1971.43 | 800 |  | 1971.43 | 800 | 2771.43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/SR/560 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-21 |  | 0% | 100% | 0% | 13.5714 | 0 | 200 | 0 | 2714.29 | 0 | 2714.29 | 1914.29 | 800 |  | 1914.29 | 800 | 2714.29 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/SR/560 | HOTEL |  |  |  | Hire of Aluminium Tower | NA | NA | 1 |  |  |  |  | unit | 1 | 2022-12-22 |  | 0% | 100% | 0% | 13.4286 | 0 | 200 | 0 | 2685.71 | 0 | 2685.71 | 1885.71 | 800 |  | 1885.71 | 800 | 2685.71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 153 | 79175 | 82181 | Electrical Work (KMEP - BW 0948) | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2022-12-26 | 2023-02-28 | 100% | 100% | 100% | 9.2857 | 63.34 | 7.28 | 177.35 | 270.4 | 76.01 | 523.76 | 435.27 | 88.49 |  | 435.27 | 88.49 | 523.76 | 0 | 177.35 | 177.35 | 0 | 270.4 | 257.92 | 12.48 | 76.01 | 0 | 76.01 | 88.49 | 88.49 | 0
E11/K149/SK/SR/517 | RESIDENCE | 154&154a | 79176 | 80599 | Balcony Ceiling Work | Level 12 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-26 | 2022-12-29 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 1802.41 | 0 | 1802.41 | 0 | 1240.81 | 1240.81 | 0 | 29.82 | 29.82 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 155&155a | 79177 | 80600 | Balcony Ceiling Work | Level 12 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-26 | 2022-12-29 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 1802.41 | 0 | 1802.41 | 0 | 1240.81 | 1240.81 | 0 | 29.82 | 29.82 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 156&156a | 79178 | 80855 | Mechanical Work | Basement 1 | Independent | 1 | 25.1 | 1.3 | 3 | 1 | m2-LxH | 75.3 | 2022-12-26 | 2023-01-02 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 633.05 | 42.17 | 271.31 | 946.53 | 946.53 | 0 |  | 946.53 | 0 | 946.53 | 0 | 660.9 | 660.9 | 0 | 46.97 | 46.97 | 0 | 283.24 | 283.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 156&156a | 79178 | 80856 | Mechanical Work | Basement 1 | Additional Boarding | 1 | 6 | 1 | 1 | 1 | m2-LxW | 6 | 2022-12-26 | 2023-01-02 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 27.85 | 4.8 | 11.93 | 44.58 | 44.58 | 0 |  | 44.58 | 0 | 44.58 | 0 | 660.9 | 660.9 | 0 | 46.97 | 46.97 | 0 | 283.24 | 283.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 156b | 79179 | 80856 | Mechanical Work | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 8 | 0.5 | 1 | 1 | m2-LxW | 4 | 2022-12-26 | 2023-01-02 | 100% | 100% | 100% | 1.1429 | 32.75 | 1.05 | 91.7 | 4.8 | 39.3 | 135.8 | 135.8 | 0 |  | 135.8 | 0 | 135.8 | 0 | 91.7 | 91.7 | 0 | 4.8 | 4.8 | 0 | 39.3 | 39.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 93a | 79180 | 80883 | KMEP Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2022-12-26 | 2023-01-10 | 100% | 100% | 100% | 2.2857 | 6.63 | 0.7 | 20.88 | 7.2 | 8.95 | 37.03 | 37.03 | 0 |  | 37.03 | 0 | 37.03 | 0 | 20.88 | 20.88 | 0 | 7.2 | 7.2 | 0 | 8.95 | 8.95 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 157 | 79181 | 80878 | Electrical Work (KMEP - BW 0948) | Ground Level | Independent 1.8m wide | 1 | 11.8 | 1.8 | 4 | 1 | m2-LxH | 47.2 | 2022-12-27 | 2023-01-09 | 100% | 100% | 100% | 2 | 16.76 | 0.77 | 553.75 | 72.69 | 237.32 | 863.76 | 863.76 | 0 |  | 863.76 | 0 | 863.76 | 0 | 689.01 | 689.01 | 0 | 85.08 | 85.08 | 0 | 295.29 | 295.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 157a | 79181 | 80878 | Electrical Work (KMEP - BW 0948) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 11.8 | 0.5 | 1 | 1 | m2-LxW | 5.9 | 2022-12-27 | 2023-01-09 | 100% | 100% | 100% | 2 | 32.75 | 1.05 | 135.26 | 12.39 | 57.97 | 205.62 | 205.62 | 0 |  | 205.62 | 0 | 205.62 | 0 | 689.01 | 689.01 | 0 | 85.08 | 85.08 | 0 | 295.29 | 295.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8z | 79182 | 79888 | Electrical Work (KMEP - BW 0948) | Level 30 | 1399-37A | 5 | 2 | 1.5 | 1 | 5 | m2-LxW | 15 | 2022-12-27 | 2023-03-16 | 100% | 100% | 100% | 11.4286 | 36.52 | 2.94 | 383.46 | 504 | 164.34 | 1051.8 | 767.76 | 284.04 |  | 767.76 | 284.04 | 1051.8 | 0 | 383.46 | 383.46 | 0 | 504 | 384.3 | 119.7 | 164.34 | 0 | 164.34 | 284.04 | 284.04 | 0
E11/K149/SK/SR/517 | RESIDENCE | 158&158a | 79183 | 80857 | Balcony Ceiling Work | Level 13 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-28 | 2022-12-30 | 100% | 100% | 100% | 0.42857 | 1772.5845 | 52.192 | 1240.81 | 22.37 | 531.78 | 1794.96 | 1794.96 | 0 | Tas Quote 2439-25-1 (item#5) | 1794.96 | 0 | 1794.96 | 0 | 1240.81 | 1240.81 | 0 | 22.37 | 22.37 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 159&159a | 79184 | 80859 | Balcony Ceiling Work | Level 13 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-28 | 2023-01-02 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 160&160a | 79185 | 80858 | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-28 | 2022-12-31 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 1802.41 | 0 | 1802.41 | 0 | 1240.81 | 1240.81 | 0 | 29.82 | 29.82 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 161 | 79186 | 79874 | Electrical Work (KMEP - BW 0948) | Ground Level | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2022-12-28 | 2023-03-14 | 100% | 100% | 100% | 11 | 63.34 | 7.28 | 88.68 | 160.16 | 38 | 286.84 | 213.48 | 73.36 |  | 213.48 | 73.36 | 286.84 | 0 | 88.68 | 88.68 | 0 | 160.16 | 124.8 | 35.36 | 38 | 0 | 38 | 73.36 | 73.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 161a | 79187 | 79875 | Electrical Work (KMEP - BW 0948) | Ground Level | Tower | 1 | 1.5 | 0.9 | 2 | 1 | rm | 2 | 2022-12-28 | 2023-03-14 | 100% | 100% | 100% | 11 | 63.34 | 7.28 | 88.68 | 160.16 | 38 | 286.84 | 213.48 | 73.36 |  | 213.48 | 73.36 | 286.84 | 0 | 107.85 | 107.85 | 0 | 184.42 | 143.7 | 40.72 | 46.22 | 0 | 46.22 | 86.94 | 86.94 | 0
E11/K149/SK/dm/213 | RESIDENCE | 161b | 79187 | 79875 | Electrical Work (KMEP - BW 0948) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2022-12-28 | 2023-03-14 | 100% | 100% | 100% | 11 | 36.52 | 2.94 | 19.17 | 24.26 | 8.22 | 51.65 | 38.07 | 13.58 |  | 38.07 | 13.58 | 51.65 | 0 | 107.85 | 107.85 | 0 | 184.42 | 143.7 | 40.72 | 46.22 | 0 | 46.22 | 86.94 | 86.94 | 0
E11/K149/SK/dm/213 | RESIDENCE | 162 | 79188 | 78626 | Door Frame Fixing Work | Ground Level | Independent | 1 | 4.3 | 1.3 | 4 | 1 | m2-LxH | 17.2 | 2022-12-28 | 2023-02-02 | 100% | 100% | 100% | 5.2857 | 12.01 | 0.49 | 144.6 | 44.55 | 61.97 | 251.12 | 251.12 | 0 |  | 251.12 | 0 | 251.12 | 0 | 174.4 | 174.4 | 0 | 46.11 | 46.11 | 0 | 74.74 | 74.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 162a | 79188 | 80868 | Door Frame Fixing Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2.6 | 0.5 | 1 | 1 | m2-LxW | 1.3 | 2022-12-28 | 2023-01-04 | 100% | 100% | 100% | 1.1429 | 32.75 | 1.05 | 29.8 | 1.56 | 12.77 | 44.13 | 44.13 | 0 |  | 44.13 | 0 | 44.13 | 0 | 174.4 | 174.4 | 0 | 46.11 | 46.11 | 0 | 74.74 | 74.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 163 | 79189 | 79856 | KCE Office Area (KMEP - BW 934) | Ground Level | Birdcage | 1 | 11.1 | 7.5 | 4 | 1 | m3 | 333 | 2022-12-28 | 2023-03-02 | 100% | 100% | 100% | 9.2857 | 7.08 | 0.49 | 1650.35 | 1515.15 | 707.29 | 3872.79 | 3048.95 | 823.84 |  | 3048.95 | 823.84 | 3872.79 | 0 | 1650.35 | 1650.35 | 0 | 1515.15 | 1398.6 | 116.55 | 707.29 | 0 | 707.29 | 823.84 | 823.84 | 0
E11/K149/SK/SR/517 | RESIDENCE | 164&164a | 79190 | 80860 | Balcony Ceiling Work | Level 20 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-29 | 2023-01-03 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 165 | 79191 | 80864 | Entrance Area Frame Fixing Work | Ground Level | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-29 | 2022-12-30 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 155.18 | 7.28 | 66.51 | 228.97 | 228.97 | 0 |  | 228.97 | 0 | 228.97 | 0 | 155.18 | 155.18 | 0 | 7.28 | 7.28 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 166 | 79192 | 80886 | Road Side Overhead Protection | Ground Level | Birdcage | 1 | 30 | 5 | 2 | 1 | m3 | 300 | 2022-12-29 | 2023-01-14 | 100% | 100% | 100% | 2.4286 | 7.08 | 0.49 | 1486.8 | 357 | 637.2 | 2481 | 2481 | 0 |  | 2481 | 0 | 2481 | 0 | 1486.8 | 1486.8 | 0 | 357 | 357 | 0 | 637.2 | 637.2 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 167&167a | 79193 | 80861 | Balcony Ceiling Work | Level 20 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-29 | 2023-01-03 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 168&168a | 79194 | 80862 | Balcony Ceiling Work | Level 15 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-30 | 2023-01-04 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 169&169a | 79195 | 80863 | Balcony Ceiling Work | Level 15 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2022-12-30 | 2023-01-04 | 100% | 100% | 100% | 0.85714 | 1772.5845 | 52.192 | 1240.81 | 44.74 | 531.78 | 1817.33 | 1817.33 | 0 | Tas Quote 2439-25-1 (item#5) | 1817.33 | 0 | 1817.33 | 0 | 1240.81 | 1240.81 | 0 | 44.74 | 44.74 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 150c | 79196 | 78649 | Block Work | Level 17 | Additional Boarding | 1 | 8.8 | 0.75 | 1 | 1 | m2-LxW | 6.6 | 2022-12-30 | 2023-02-14 | 100% | 100% | 100% | 6.7143 | 6.63 | 0.7 | 30.63 | 31.02 | 13.13 | 74.78 | 74.78 | 0 |  | 74.78 | 0 | 74.78 | 0 | 30.63 | 30.63 | 0 | 31.02 | 31.02 | 0 | 13.13 | 13.13 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 170 | 79197 | 80869 | Door Frame Fixing Work | Ground Level | Tower | 1 | 1.8 | 1.8 | 3.5 | 1 | rm | 3.5 | 2022-12-31 | 2023-01-04 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 155.18 | 18.2 | 66.51 | 239.89 | 239.89 | 0 |  | 239.89 | 0 | 239.89 | 0 | 155.18 | 155.18 | 0 | 18.2 | 18.2 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 171&171a | 79198 | 80870 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-02 | 2023-01-05 | 100% | 100% | 100% | 0.57143 | 1772.5845 | 52.192 | 1240.81 | 29.82 | 531.78 | 1802.41 | 1802.41 | 0 | Tas Quote 2439-25-1 (item#5) | 1802.41 | 0 | 1802.41 | 0 | 1240.81 | 1240.81 | 0 | 29.82 | 29.82 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 172 | 79200 | 82103 | Glass Instalation Work | Ground Level | Independent | 1 | 5 | 1.3 | 4.5 | 1 | m2-LxH | 22.5 | 2023-01-03 | 2023-03-17 | 100% | 100% | 100% | 10.5714 | 12.01 | 0.49 | 189.16 | 116.55 | 81.07 | 386.78 | 274.21 | 112.57 |  | 274.21 | 112.57 | 386.78 | 0 | 456.08 | 456.08 | 0 | 298.8 | 205.07 | 93.73 | 81.07 | 0 | 81.07 | 174.8 | 174.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 172a | 79200 |  | Glass Instalation Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 2.5 | 1 | m2-LxH | 15.75 | 2023-01-03 |  | 100% | 100% | 0% | 11.7143 | 12.01 | 0.49 | 132.41 | 90.41 | 0 | 222.82 | 191.95 | 30.87 |  | 191.95 | 30.87 | 222.82 | 0 | 456.08 | 456.08 | 0 | 298.8 | 205.07 | 93.73 | 81.07 | 0 | 81.07 | 174.8 | 174.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 172b | 79200 |  | Glass Instalation Work | Ground Level | Independent | 1 | 8 | 1.3 | 2 | 1 | m2-LxH | 16 | 2023-01-03 |  | 100% | 100% | 0% | 11.7143 | 12.01 | 0.49 | 134.51 | 91.84 | 0 | 226.35 | 194.99 | 31.36 |  | 194.99 | 31.36 | 226.35 | 0 | 456.08 | 456.08 | 0 | 298.8 | 205.07 | 93.73 | 81.07 | 0 | 81.07 | 174.8 | 174.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 173 | 75751 | 82104 | Glass Instalation Work | Ground Level | Independent | 1 | 6.3 | 1.3 | 4.5 | 1 | m2-LxH | 28.35 | 2023-01-03 | 2023-03-17 | 100% | 100% | 100% | 10.5714 | 12.01 | 0.49 | 238.34 | 146.85 | 102.15 | 487.34 | 345.5 | 141.84 |  | 345.5 | 141.84 | 487.34 | 0 | 387.57 | 387.57 | 0 | 248.74 | 174.26 | 74.48 | 102.15 | 0 | 102.15 | 176.63 | 176.63 | 0
E11/K149/SK/dm/213 | RESIDENCE | 173a | 75751 |  | Glass Instalation Work | Ground Level | Independent | 1 | 5 | 1.3 | 2.5 | 1 | m2-LxH | 12.5 | 2023-01-03 |  | 100% | 100% | 0% | 11.7143 | 12.01 | 0.49 | 105.09 | 71.75 | 0 | 176.84 | 152.34 | 24.5 |  | 152.34 | 24.5 | 176.84 | 0 | 387.57 | 387.57 | 0 | 248.74 | 174.26 | 74.48 | 102.15 | 0 | 102.15 | 176.63 | 176.63 | 0
E11/K149/SK/dm/213 | RESIDENCE | 173b | 75751 |  | Glass Instalation Work | Ground Level | Independent | 1 | 3.5 | 1 | 1.5 | 1 | m2-LxH | 5.25 | 2023-01-03 |  | 100% | 100% | 0% | 11.7143 | 12.01 | 0.49 | 44.14 | 30.14 | 0 | 74.28 | 63.99 | 10.29 |  | 63.99 | 10.29 | 74.28 | 0 | 387.57 | 387.57 | 0 | 248.74 | 174.26 | 74.48 | 102.15 | 0 | 102.15 | 176.63 | 176.63 | 0
E11/K149/SK/dm/213 | RESIDENCE | 124a | 75752 | 80888 | Near Shaft 9 (KMEP - BW 0858) | Ground Level | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 | 1 | 1 | m2-LxW | 0.9 | 2023-01-03 | 2023-01-16 | 100% | 100% | 100% | 2 | 32.75 | 1.05 | 20.63 | 1.89 | 8.84 | 31.36 | 31.36 | 0 |  | 31.36 | 0 | 31.36 | 0 | 20.63 | 20.63 | 0 | 1.89 | 1.89 | 0 | 8.84 | 8.84 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 174 | 75753 | 80879 | KMEP Work | Basement 1 | Independent | 1 | 30 | 1.3 | 3 | 1 | m2-LxH | 90 | 2023-01-03 | 2023-01-06 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 756.63 | 25.2 | 324.27 | 1106.1 | 1106.1 | 0 |  | 1106.1 | 0 | 1106.1 | 0 | 940.03 | 940.03 | 0 | 30 | 30 | 0 | 402.87 | 402.87 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 174a | 75753 | 80879 | KMEP Work | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 16 | 0.5 | 1 | 1 | m2-LxW | 8 | 2023-01-03 | 2023-01-06 | 100% | 100% | 100% | 0.57143 | 32.75 | 1.05 | 183.4 | 4.8 | 78.6 | 266.8 | 266.8 | 0 |  | 266.8 | 0 | 266.8 | 0 | 940.03 | 940.03 | 0 | 30 | 30 | 0 | 402.87 | 402.87 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 163a | 75754 | 79855 | KCE Office Area (KMEP - BW 934) | Ground Level | Birdcage | 1 | 15.5 | 3.1 | 4 | 1 | m3 | 192.2 | 2023-01-03 | 2023-03-02 | 100% | 100% | 100% | 8.4286 | 7.08 | 0.49 | 952.54 | 793.79 | 408.23 | 2154.56 | 1679.06 | 475.5 |  | 1679.06 | 475.5 | 2154.56 | 0 | 952.54 | 952.54 | 0 | 793.79 | 726.52 | 67.27 | 408.23 | 0 | 408.23 | 475.5 | 475.5 | 0
E11/K149/SK/dm/213 | RESIDENCE | 163b | 75755 | 79854 | KCE Office Area (KMEP - BW 934) | Ground Level | Birdcage | 1 | 12.2 | 7 | 4 | 1 | m3 | 341.6 | 2023-01-03 | 2023-03-02 | 100% | 100% | 100% | 8.4286 | 7.08 | 0.49 | 1692.97 | 1410.81 | 725.56 | 3829.34 | 2984.22 | 845.12 |  | 2984.22 | 845.12 | 3829.34 | 0 | 1692.97 | 1692.97 | 0 | 1410.81 | 1291.25 | 119.56 | 725.56 | 0 | 725.56 | 845.12 | 845.12 | 0
E11/K149/SK/SR/517 | RESIDENCE | 175&175a | 75756 | 80880 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-03 | 2023-01-07 | 100% | 100% | 100% | 0.71429 | 1772.5845 | 52.192 | 1240.81 | 37.28 | 531.78 | 1809.87 | 1809.87 | 0 | Tas Quote 2439-25-1 (item#5) | 1809.87 | 0 | 1809.87 | 0 | 1240.81 | 1240.81 | 0 | 37.28 | 37.28 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | RESIDENCE | 176&176a | 75757 | 79860 | Balcony Ceiling Work | Level 16 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-04 | 2023-03-04 | 100% | 100% | 100% | 8.5714 | 1772.5845 | 52.192 | 1240.81 | 447.36 | 531.78 | 2219.95 | 1635.98 | 583.97 | Tas Quote 2439-25-1 (item#5) | 1635.98 | 583.97 | 2219.95 | 0 | 1240.81 | 1240.81 | 0 | 447.36 | 395.17 | 52.19 | 531.78 | 0 | 531.78 | 583.97 | 583.97 | 0
E11/K149/SK/dm/213 | RESIDENCE | 177 | 75758 | 80881 | Electrical KMEP-BW 948 | Ground Level | Independent 1.8m wide | 1 | 7 | 1.8 | 4 | 1 | m2-LxH | 28 | 2023-01-04 | 2023-01-09 | 100% | 100% | 100% | 0.85714 | 16.76 | 0.77 | 328.5 | 18.48 | 140.78 | 487.76 | 487.76 | 0 |  | 487.76 | 0 | 487.76 | 0 | 405.19 | 405.19 | 0 | 26.04 | 26.04 | 0 | 173.65 | 173.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 177a | 75758 | 80881 | Electrical KMEP-BW 948 | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2023-01-04 | 2023-01-09 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 76.69 | 7.56 | 32.87 | 117.12 | 117.12 | 0 |  | 117.12 | 0 | 117.12 | 0 | 405.19 | 405.19 | 0 | 26.04 | 26.04 | 0 | 173.65 | 173.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 178 | 75759 | 78647 | Shaft 9 KMEP-BW 0858 | Ground Level | Tower | 1 | 1.8 | 1.8 | 12.5 | 1 | rm | 12.5 | 2023-01-04 | 2023-02-09 | 100% | 100% | 100% | 5.2857 | 63.34 | 7.28 | 554.23 | 481 | 237.53 | 1272.76 | 1272.76 | 0 |  | 1272.76 | 0 | 1272.76 | 0 | 661.38 | 661.38 | 0 | 540.33 | 540.33 | 0 | 283.45 | 283.45 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 178 | 75759 | 78647 | Shaft 9 KMEP-BW 0858 | Ground Level | Additional Boarding | 4 | 1.8 | 1.8 | 1 | 4 | m2-LxW | 12.96 | 2023-01-04 | 2023-02-09 | 100% | 100% | 100% | 5.2857 | 6.63 | 0.7 | 60.15 | 47.95 | 25.78 | 133.88 | 133.88 | 0 |  | 133.88 | 0 | 133.88 | 0 | 661.38 | 661.38 | 0 | 540.33 | 540.33 | 0 | 283.45 | 283.45 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 178a | 75759 | 78647 | Shaft 9 KMEP-BW 0858 | Ground Level | Cantilever (0 < 0.5m width) | 1 | 4.1 | 0.5 | 1 | 1 | m2-LxW | 2.05 | 2023-01-04 | 2023-02-09 | 100% | 100% | 100% | 5.2857 | 32.75 | 1.05 | 47 | 11.38 | 20.14 | 78.52 | 78.52 | 0 |  | 78.52 | 0 | 78.52 | 0 | 661.38 | 661.38 | 0 | 540.33 | 540.33 | 0 | 283.45 | 283.45 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 163c | 75760 | 79853 | KCE Office Area (KMEP - BW 946) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6.8 | 1.2 | 1 | 1 | m2-LxW | 8.16 | 2023-01-04 | 2023-03-02 | 100% | 100% | 100% | 8.2857 | 36.52 | 2.94 | 208.6 | 198.78 | 89.4 | 496.78 | 390.24 | 106.54 |  | 390.24 | 106.54 | 496.78 | 0 | 208.6 | 208.6 | 0 | 198.78 | 181.64 | 17.14 | 89.4 | 0 | 89.4 | 106.54 | 106.54 | 0
E11/K149/SK/dm/213 | RESIDENCE | 163d | 75761 | 79852 | KCE Office Area (KMEP - BW 946) | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 4 | 1.5 | 1 | 1 | m2-LxW | 6 | 2023-01-04 | 2023-03-02 | 100% | 100% | 100% | 8.2857 | 36.52 | 2.94 | 153.38 | 146.16 | 65.74 | 365.28 | 286.94 | 78.34 |  | 286.94 | 78.34 | 365.28 | 0 | 153.38 | 153.38 | 0 | 146.16 | 133.56 | 12.6 | 65.74 | 0 | 65.74 | 78.34 | 78.34 | 0
E11/K149/SK/dm/213 | RESIDENCE | 179 | 75762 | 80884 | Shaft 9 KMEP-BW 0858 | Ground Level | Tower | 1 | 2.5 | 0.6 | 2 | 1 | rm | 2 | 2023-01-05 | 2023-01-11 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 88.68 | 14.56 | 38 | 141.24 | 141.24 | 0 |  | 141.24 | 0 | 141.24 | 0 | 88.68 | 88.68 | 0 | 14.56 | 14.56 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 180 | 75763 | 82133 | Electrical KMEP-BW 0987 | Ground Level | Independent 1.8m wide | 1 | 10 | 2.5 | 6.2 | 1 | m2-LxH | 62 | 2023-01-06 | 2023-02-26 | 100% | 100% | 100% | 7.4286 | 16.76 | 0.77 | 727.38 | 354.64 | 311.74 | 1393.76 | 1075.2 | 318.56 |  | 1075.2 | 318.56 | 1393.76 | 0 | 727.38 | 727.38 | 0 | 354.64 | 347.82 | 6.82 | 311.74 | 0 | 311.74 | 318.56 | 318.56 | 0
E11/K149/SK/dm/213 | RESIDENCE | 181 | 75764 | 82161 | Electrical Work | Ground Level | Tower | 1 | 2 | 0.9 | 2 | 1 | rm | 2 | 2023-01-07 | 2023-02-18 | 100% | 100% | 100% | 6.1429 | 63.34 | 7.28 | 88.68 | 89.44 | 38 | 216.12 | 216.12 | 0 |  | 216.12 | 0 | 216.12 | 0 | 88.68 | 88.68 | 0 | 89.44 | 89.44 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 182 | 75765 | 82172 | Electrical Work | Ground Level | Tower | 1 | 2 | 1.5 | 3.5 | 1 | rm | 3.5 | 2023-01-07 | 2023-02-20 | 100% | 100% | 100% | 6.4286 | 63.34 | 7.28 | 155.18 | 163.8 | 66.51 | 385.49 | 385.49 | 0 |  | 385.49 | 0 | 385.49 | 0 | 169.1 | 169.1 | 0 | 177.3 | 177.3 | 0 | 72.48 | 72.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 182 | 75765 | 82172 | Electrical Work | Ground Level | Additional Boarding | 1 | 2 | 1.5 |  | 1 | m2-LxW | 3 | 2023-01-07 | 2023-02-20 | 100% | 100% | 100% | 6.4286 | 6.63 | 0.7 | 13.92 | 13.5 | 5.97 | 33.39 | 33.39 | 0 |  | 33.39 | 0 | 33.39 | 0 | 169.1 | 169.1 | 0 | 177.3 | 177.3 | 0 | 72.48 | 72.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 180a | 75766 | 82134 | Electrical KMEP-BW 0987 | Ground Level | Independent 1.8m wide | 1 | 15 | 2.5 | 6.2 | 1 | m2-LxW | 37.5 | 2023-01-07 | 2023-02-26 | 100% | 100% | 100% | 7.2857 | 16.76 | 0.77 | 439.95 | 210.38 | 188.55 | 838.88 | 646.2 | 192.68 |  | 646.2 | 192.68 | 838.88 | 0 | 439.95 | 439.95 | 0 | 210.38 | 206.25 | 4.13 | 188.55 | 0 | 188.55 | 192.68 | 192.68 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a1 | 75767 | 78614 | Glass Instalation Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 12.6 | 0.75 | 1 | 1 | m2-LxW | 9.45 | 2023-01-07 | 2023-01-28 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 241.58 | 87.32 | 103.53 | 432.43 | 432.43 | 0 |  | 432.43 | 0 | 432.43 | 0 | 241.58 | 241.58 | 0 | 87.32 | 87.32 | 0 | 103.53 | 103.53 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 183 | 75768 | 78615 | Electrical KMEP-BW 0972 | Basement 1 | Tower | 1 | 2.5 | 2.5 | 2.5 | 1 | rm | 2.5 | 2023-01-10 | 2023-01-31 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 110.85 | 57.2 | 47.51 | 215.56 | 215.56 | 0 |  | 215.56 | 0 | 215.56 | 0 | 110.85 | 110.85 | 0 | 57.2 | 57.2 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 184 | 75769 | 80895 | mechanical Work BW 0972 | Basement 1 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2023-01-10 | 2023-01-23 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 133.01 | 43.68 | 57.01 | 233.7 | 233.7 | 0 |  | 233.7 | 0 | 233.7 | 0 | 148.09 | 148.09 | 0 | 48.23 | 48.23 | 0 | 63.47 | 63.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 184a | 75769 | 80895 | mechanical Work BW 0972 | Basement 1 | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2023-01-10 | 2023-01-23 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 15.08 | 4.55 | 6.46 | 26.09 | 26.09 | 0 |  | 26.09 | 0 | 26.09 | 0 | 148.09 | 148.09 | 0 | 48.23 | 48.23 | 0 | 63.47 | 63.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 185 | 75770 | 78605 | Road Side Access | Level 29 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2023-01-10 | 2023-01-27 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 88.68 | 37.44 | 38 | 164.12 | 164.12 | 0 |  | 164.12 | 0 | 164.12 | 0 | 88.68 | 88.68 | 0 | 37.44 | 37.44 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 186 | 75771 | 80891 | KCE Office Area Access | Ground Level | Independent | 1 | 3.5 | 1.3 | 1 | 1 | m2-LxH | 3.5 | 2023-01-10 | 2023-01-19 | 100% | 100% | 100% | 1.4286 | 12.01 | 0.49 | 29.42 | 2.45 | 12.61 | 44.48 | 44.48 | 0 |  | 44.48 | 0 | 44.48 | 0 | 29.42 | 29.42 | 0 | 2.45 | 2.45 | 0 | 12.61 | 12.61 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a2 | 75772 | 79887 | Glass Fixing work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1.5 | 1 | 1 | m2-LxW | 3 | 2023-01-10 | 2023-03-13 | 100% | 100% | 100% | 9 | 36.52 | 2.94 | 76.69 | 79.38 | 32.87 | 188.94 | 135.91 | 53.03 |  | 135.91 | 53.03 | 188.94 | 0 | 76.69 | 76.69 | 0 | 79.38 | 59.22 | 20.16 | 32.87 | 0 | 32.87 | 53.03 | 53.03 | 0
E11/K149/SK/dm/213 | RESIDENCE | 187 | 75773 | 78616 | mechanical Work BW 0972 | Basement 1 | Independent | 1 | 6.2 | 1 | 3 | 1 | m2-LxH | 18.6 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 156.37 | 27.34 | 67.02 | 250.73 | 250.73 | 0 |  | 250.73 | 0 | 250.73 | 0 | 314.87 | 314.87 | 0 | 82.02 | 82.02 | 0 | 134.95 | 134.95 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 187a | 75773 | 78616 | mechanical Work BW 0972 | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 6.2 | 1 |  | 1 | m2-LxW | 6.2 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 36.52 | 2.94 | 158.5 | 54.68 | 67.93 | 281.11 | 281.11 | 0 |  | 281.11 | 0 | 281.11 | 0 | 314.87 | 314.87 | 0 | 82.02 | 82.02 | 0 | 134.95 | 134.95 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 187b | 75774 | 78617 | mechanical Work BW 0972 | Basement 1 | Tower | 1 | 1.8 | 1.3 | 2 | 1 | rm | 2 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 88.68 | 43.68 | 38 | 170.36 | 170.36 | 0 |  | 170.36 | 0 | 170.36 | 0 | 88.68 | 88.68 | 0 | 43.68 | 43.68 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 188 | 75775 | 79581 | KCE Office Area (KMEP - BW 934) | Level 2 | Independent | 1 | 12.5 | 2.5 | 2.5 | 1 | m2-LxH | 31.25 | 2023-01-11 | 2023-03-02 | 100% | 100% | 100% | 7.2857 | 12.01 | 0.49 | 262.72 | 111.56 | 112.59 | 486.87 | 363.35 | 123.52 |  | 363.35 | 123.52 | 486.87 | 0 | 262.72 | 262.72 | 0 | 111.56 | 100.63 | 10.93 | 112.59 | 0 | 112.59 | 123.52 | 123.52 | 0
E11/K149/SK/dm/213 | RESIDENCE | 188a | 75776 | 82200 | KCE Office Area (KMEP - BW 934) | Level 2 | Independent | 1 | 4 | 1 | 2.5 | 1 | m2-LxH | 10 | 2023-01-11 | 2023-03-02 | 100% | 100% | 100% | 7.2857 | 12.01 | 0.49 | 84.07 | 35.7 | 36.03 | 155.8 | 116.27 | 39.53 |  | 116.27 | 39.53 | 155.8 | 0 | 84.07 | 84.07 | 0 | 35.7 | 32.2 | 3.5 | 36.03 | 0 | 36.03 | 39.53 | 39.53 | 0
E11/K149/SK/dm/598 | RESIDENCE | 189&190 | 75777&78 | 78601&80896 | Concrete Cutting Work | Level 24 | 1399-40 | 1 |  |  |  |  | unit | 1 | 2023-01-11 | 2023-01-23 | 100% | 100% | 100% | 1.8571 | 4657 | 183.44 | 3259.9 | 340.67 | 1397.1 | 4997.67 | 4997.67 | 0 | 2439-31-1 (Item-11) | 4997.67 | 0 | 4997.67 | 0 | 3259.9 | 3259.9 | 0 | 340.67 | 340.67 | 0 | 1397.1 | 1397.1 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 189 | 75777 | 78601&80896 | Concrete Cutting Work | Level 24 | Netting Supply & Install | 1 | 5.5 | 1 | 1 |  | m2-LxH | 5.5 | 2023-01-11 |  | 100% | 100% | 100% | 10.5714 | 8.52 | 0 | 32.8 | 0 | 14.06 | 46.86 | 46.86 | 0 |  | 46.86 | 0 | 46.86 | 0 | 32.8 | 32.8 | 0 | 0 | 0 | 0 | 14.06 | 14.06 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 191 | 75779 |  | GlassFixing Work | Level 28 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-12 |  | 100% | 100% | 0% | 10.4286 | 63.34 | 7.28 | 88.68 | 151.84 | 0 | 240.52 | 182.28 | 58.24 |  | 182.28 | 58.24 | 240.52 | 0 | 88.68 | 88.68 | 0 | 151.84 | 93.6 | 58.24 | 0 | 0 | 0 | 58.24 | 58.24 | 0
E11/K149/SK/dm/213 | RESIDENCE | 192 | 75780 | 78650 | Pipe Cutting Work | Level 5 | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2023-01-13 | 2023-02-14 | 100% | 100% | 100% | 4.7143 | 63.34 | 7.28 | 199.52 | 154.44 | 85.51 | 439.47 | 439.47 | 0 |  | 439.47 | 0 | 439.47 | 0 | 210.38 | 210.38 | 0 | 162.16 | 162.16 | 0 | 90.16 | 90.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 192 | 75780 | 78650 | Pipe Cutting Work | Level 5 | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-13 | 2023-02-14 | 100% | 100% | 100% | 4.7143 | 6.63 | 0.7 | 10.86 | 7.72 | 4.65 | 23.23 | 23.23 | 0 |  | 23.23 | 0 | 23.23 | 0 | 210.38 | 210.38 | 0 | 162.16 | 162.16 | 0 | 90.16 | 90.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/598 | RESIDENCE | 193&193a | 75778 | 78618 | Concrete Cutting Work | Level 23 | 1399-40 | 1 |  |  |  | 1 | unit | 1 | 2023-01-13 | 2023-01-28 | 50% | 50% | 50% | 2.2857 | 4657 | 183.44 | 1629.95 | 209.65 | 698.55 | 2538.15 | 2538.15 | 0 | 2439-31-1 (Item-11) | 2538.15 | 0 | 2538.15 | 0 | 1629.95 | 1629.95 | 0 | 209.65 | 209.65 | 0 | 698.55 | 698.55 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 194 | 75782 | 78619 | GlassFixing Work | Level 26 | Buttress | 1 | 1.3 | 1.3 | 1.5 |  | m3 | 2.54 | 2023-01-13 | 2023-01-28 | 100% | 100% | 100% | 2.2857 | 5.29 | 0.35 | 9.41 | 2.03 | 4.03 | 15.47 | 15.47 | 0 |  | 15.47 | 0 | 15.47 | 0 | 25.16 | 25.16 | 0 | 5.15 | 5.15 | 0 | 10.78 | 10.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 194a | 75782 | 78619 | GlassFixing Work | Level 26 | Tripple Hnadrail | 1 | 1.5 |  | 1.5 |  | lm | 1.5 | 2023-01-13 | 2023-01-28 | 100% | 100% | 100% | 2.2857 | 15 | 0.91 | 15.75 | 3.12 | 6.75 | 25.62 | 25.62 | 0 |  | 25.62 | 0 | 25.62 | 0 | 25.16 | 25.16 | 0 | 5.15 | 5.15 | 0 | 10.78 | 10.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195 | 75783 | 82199 | Electrical KMEP-BW 0934 | Level 2 | Birdcage | 1 | 15 | 5 | 2.5 | 1 | m3 | 187.5 | 2023-01-13 | 2023-03-02 | 100% | 100% | 100% | 7 | 7.08 | 0.49 | 929.25 | 643.13 | 398.25 | 1970.63 | 1506.75 | 463.88 |  | 1506.75 | 463.88 | 1970.63 | 0 | 929.25 | 929.25 | 0 | 643.13 | 577.5 | 65.63 | 398.25 | 0 | 398.25 | 463.88 | 463.88 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195a | 75784 | 82198 | Electrical KMEP-BW 0934 | Level 2 | Independent | 1 | 6.1 | 1.3 | 2.5 | 1 | m2-LxH | 15.25 | 2023-01-13 | 2023-03-02 | 100% | 100% | 100% | 7 | 12.01 | 0.49 | 128.21 | 52.31 | 54.95 | 235.47 | 175.18 | 60.29 |  | 175.18 | 60.29 | 235.47 | 0 | 128.21 | 128.21 | 0 | 52.31 | 46.97 | 5.34 | 54.95 | 0 | 54.95 | 60.29 | 60.29 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195b | 75785 | 82197 | Electrical KMEP-BW 0934 | Level 2 | Birdcage | 1 | 4.3 | 3.6 | 2.5 | 1 | m3 | 38.7 | 2023-01-13 | 2023-03-02 | 100% | 100% | 100% | 7 | 7.08 | 0.49 | 191.8 | 132.74 | 82.2 | 406.74 | 311 | 95.74 |  | 311 | 95.74 | 406.74 | 0 | 191.8 | 191.8 | 0 | 132.74 | 119.2 | 13.54 | 82.2 | 0 | 82.2 | 95.74 | 95.74 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195c | 75786 | 82196 | Electrical KMEP-BW 0934 | Level 2 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2023-01-13 | 2023-03-02 | 100% | 100% | 100% | 7 | 63.34 | 7.28 | 133.01 | 152.88 | 57.01 | 342.9 | 270.29 | 72.61 |  | 270.29 | 72.61 | 342.9 | 0 | 266.02 | 266.02 | 0 | 305.76 | 274.56 | 31.2 | 114.02 | 0 | 114.02 | 145.22 | 145.22 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195c | 75786 | 82196 | Electrical KMEP-BW 0934 | Level 2 | Tower | 1 | 2.5 | 2.5 | 3 | 1 | rm | 3 | 2023-01-13 | 2023-03-02 | 100% | 100% | 100% | 7 | 63.34 | 7.28 | 133.01 | 152.88 | 57.01 | 342.9 | 270.29 | 72.61 |  | 270.29 | 72.61 | 342.9 | 0 | 266.02 | 266.02 | 0 | 305.76 | 274.56 | 31.2 | 114.02 | 0 | 114.02 | 145.22 | 145.22 | 0
E11/K149/SK/SR/517 | RESIDENCE | 196&196a | 75787 |  | Balcony Ceiling Work | Level 10 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-14 |  | 100% | 100% | 0% | 10.1429 | 1772.5845 | 52.192 | 1240.81 | 529.38 | 0 | 1770.19 | 1561.42 | 208.77 | Tas Quote 2439-25-1 (item#5) | 1561.42 | 208.77 | 1770.19 | 0 | 1240.81 | 1240.81 | 0 | 529.38 | 320.61 | 208.77 | 0 | 0 | 0 | 208.77 | 208.77 | 0
E11/K149/SK/dm/213 | RESIDENCE | 197 | 75788 |  | Access Scaffold | Level 10 | Tower | 1 | 1.8 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-14 |  | 100% | 100% | 0% | 10.1429 | 63.34 | 7.28 | 155.18 | 258.44 | 0 | 413.62 | 311.7 | 101.92 |  | 311.7 | 101.92 | 413.62 | 0 | 524.43 | 524.43 | 0 | 528.36 | 317.35 | 211.01 | 0 | 0 | 0 | 211.01 | 211.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 197a | 75788 |  | Access Scaffold | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 1 |  | 1 | m2-LxW | 1.3 | 2023-01-14 |  | 100% | 100% | 0% | 10.1429 | 36.52 | 2.94 | 33.23 | 38.77 | 0 | 72 | 56.71 | 15.29 |  | 56.71 | 15.29 | 72 | 0 | 524.43 | 524.43 | 0 | 528.36 | 317.35 | 211.01 | 0 | 0 | 0 | 211.01 | 211.01 | 0
E11/K149/SK/SR/517 | RESIDENCE | 198&198a | 75789 | 79859 | Balcony Ceiling Work | Level 16 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-14 | 2023-03-04 | 100% | 100% | 100% | 7.1429 | 1772.5845 | 52.192 | 1240.81 | 372.8 | 531.78 | 2145.39 | 1561.42 | 583.97 | Tas Quote 2439-25-1 (item#5) | 1561.42 | 583.97 | 2145.39 | 0 | 1240.81 | 1240.81 | 0 | 372.8 | 320.61 | 52.19 | 531.78 | 0 | 531.78 | 583.97 | 583.97 | 0
E11/K149/SK/dm/213 | RESIDENCE | 199 | 75788 |  | EFIS Instalation Work | Level 10 | Independent | 1 | 10 | 0.9 | 3.5 | 1 | m2-LxH | 35 | 2023-01-16 |  | 100% | 100% | 0% | 9.8571 | 12.01 | 0.49 | 294.25 | 169.05 | 0 | 463.3 | 394.7 | 68.6 |  | 394.7 | 68.6 | 463.3 | 0 | 524.43 | 524.43 | 0 | 528.36 | 317.35 | 211.01 | 0 | 0 | 0 | 211.01 | 211.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 199 | 75788 |  | EFIS Instalation Work | Level 10 | Additional Boarding | 1 | 10 | 0.9 |  | 1 | m2-LxW | 9 | 2023-01-16 |  | 100% | 100% | 0% | 9.8571 | 6.63 | 0.7 | 41.77 | 62.1 | 0 | 103.87 | 78.67 | 25.2 |  | 78.67 | 25.2 | 103.87 | 0 | 524.43 | 524.43 | 0 | 528.36 | 317.35 | 211.01 | 0 | 0 | 0 | 211.01 | 211.01 | 0
E11/K149/SK/dm/213 | RESIDENCE | 199a | 75792 |  | EFIS Instalation Work | Level 10 | Independent | 1 | 8.8 | 0.9 | 1 | 1 | m2-LxH | 8.8 | 2023-01-16 |  | 100% | 100% | 0% | 9.8571 | 12.01 | 0.49 | 73.98 | 42.5 | 0 | 116.48 | 99.24 | 17.24 |  | 99.24 | 17.24 | 116.48 | 0 | 73.98 | 73.98 | 0 | 42.5 | 25.26 | 17.24 | 0 | 0 | 0 | 17.24 | 17.24 | 0
E11/K149/SK/dm/213 | RESIDENCE | 200 | 75791 | 78627 | Electrical KMEP-BW 1042 | Ground Level | Tower | 1 | 1.8 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-16 | 2023-02-02 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 287.21 | 0 |  | 287.21 | 0 | 287.21 | 0 | 166.04 | 166.04 | 0 | 69.73 | 69.73 | 0 | 71.16 | 71.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 200 | 75791 | 78627 | Electrical KMEP-BW 1042 | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-16 | 2023-02-02 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 10.86 | 4.21 | 4.65 | 19.72 | 19.72 | 0 |  | 19.72 | 0 | 19.72 | 0 | 166.04 | 166.04 | 0 | 69.73 | 69.73 | 0 | 71.16 | 71.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 150e | 75793 | 82149 | EFIS Instalation Work | Level 10 | Additional Boarding | 1 | 8.8 | 0.9 |  | 1 | m2-LxW | 7.92 | 2023-01-16 | 2023-02-14 | 100% | 100% | 100% | 4.2857 | 6.63 | 0.7 | 36.76 | 23.76 | 15.75 | 76.27 | 69.23 | 7.04 |  | 69.23 | 7.04 | 76.27 | 0 | 36.76 | 36.76 | 0 | 23.76 | 32.47 | -8.71 | 15.75 | 0 | 15.75 | 7.04 | 7.04 | -1.0658e-14
E11/K149/SK/dm/213 | RESIDENCE | 201 | 75794 | 78603 | Wall Finishing Work | Level 31 | Tower | 1 | 1.8 | 1.3 | 0.5 | 1 | rm | 0.5 | 2023-01-16 | 2023-01-24 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 22.17 | 4.68 | 9.5 | 36.35 | 36.35 | 0 |  | 36.35 | 0 | 36.35 | 0 | 22.17 | 22.17 | 0 | 4.68 | 4.68 | 0 | 9.5 | 9.5 | 0 | 0 | 0 | 0
E11/K149/MS/MV/564 | RESIDENCE | 202 | 75795 |  | GRC Instalation Work | Level 10 | 1399-34b | 1 |  |  |  | 1 | unit | 1 | 2023-01-16 |  | 100% | 100% | 0% | 9.8571 | 15779.64 | 1079.32 | 11045.75 | 10639.01 | 0 | 21684.76 | 17367.48 | 4317.28 | 2439-26-1(Item-6) | 17367.48 | 4317.28 | 21684.76 | 0 | 11045.75 | 11045.75 | 0 | 10639.01 | 6321.73 | 4317.28 | 0 | 0 | 0 | 4317.28 | 4317.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 203 | 75796 | 82151 | Electrical KMEP BW-1042 | Ground Level | Independent | 1 | 5 | 1.3 | 4 | 1 | m2-LxH | 20 | 2023-01-17 | 2023-02-09 | 100% | 100% | 100% | 3.4286 | 12.01 | 0.49 | 168.14 | 33.6 | 72.06 | 273.8 | 273.8 | 0 |  | 273.8 | 0 | 273.8 | 0 | 198.31 | 198.31 | 0 | 49.2 | 49.2 | 0 | 84.99 | 84.99 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 203 | 75796 | 82151 | Electrical KMEP BW-1042 | Ground Level | Additional Boarding | 1 | 5 | 1.3 |  | 1 | m2-LxW | 6.5 | 2023-01-17 | 2023-02-09 | 100% | 100% | 100% | 3.4286 | 6.63 | 0.7 | 30.17 | 15.6 | 12.93 | 58.7 | 58.7 | 0 |  | 58.7 | 0 | 58.7 | 0 | 198.31 | 198.31 | 0 | 49.2 | 49.2 | 0 | 84.99 | 84.99 | 0 | 0 | 0 | 0
E11/K149/NA/dm/612 | RESIDENCE | 204 | 75797 | 78606 | Wall Finishing Work | Ground Level | 1399-44 | 1 | 8 | 1.5 | 3 | 1 | m2-LxH | 24 | 2023-01-17 | 2023-01-27 | 100% | 100% | 100% | 1.5714 | 326.29 | 26.113 | 5481.67 | 984.83 | 2349.29 | 8815.79 | 8815.79 | 0 | Prorate 2439-32-1 (Item-12) | 8815.79 | 0 | 8815.79 | 0 | 5481.67 | 5481.67 | 0 | 984.83 | 984.83 | 0 | 2349.29 | 2349.29 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 205 | 75798 | 80898 | Electrical KMEP BW-0987 | Level 2 | Tower | 2.5 | 1.8 | 6 | 1 | 1 | rm | 2.5 | 2023-01-17 | 2023-01-23 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 110.85 | 18.2 | 47.51 | 176.56 | 176.56 | 0 |  | 176.56 | 0 | 176.56 | 0 | 160.39 | 160.39 | 0 | 22.66 | 22.66 | 0 | 68.74 | 68.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 205 | 75798 | 80898 | Electrical KMEP BW-0987 | Level 2 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-01-17 | 2023-01-23 | 100% | 100% | 100% | 1 | 6.63 | 0.7 | 20.88 | 3.15 | 8.95 | 32.98 | 32.98 | 0 |  | 32.98 | 0 | 32.98 | 0 | 160.39 | 160.39 | 0 | 22.66 | 22.66 | 0 | 68.74 | 68.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 205a | 75798 | 80898 | Electrical KMEP BW-0987 | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 |  | 1 | m2-LxW | 1.25 | 2023-01-17 | 2023-01-23 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 28.66 | 1.31 | 12.28 | 42.25 | 42.25 | 0 |  | 42.25 | 0 | 42.25 | 0 | 160.39 | 160.39 | 0 | 22.66 | 22.66 | 0 | 68.74 | 68.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 206 | 75799 | 80900 | Block Work | Level 2 | Tower | 2.5 | 1.3 | 3.8 | 1 | 1 | rm | 2.5 | 2023-01-18 | 2023-01-23 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 110.85 | 15.6 | 47.51 | 173.96 | 173.96 | 0 |  | 173.96 | 0 | 173.96 | 0 | 125.93 | 125.93 | 0 | 17.55 | 17.55 | 0 | 53.97 | 53.97 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 206 | 75799 | 80900 | Block Work | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-18 | 2023-01-23 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 15.08 | 1.95 | 6.46 | 23.49 | 23.49 | 0 |  | 23.49 | 0 | 23.49 | 0 | 125.93 | 125.93 | 0 | 17.55 | 17.55 | 0 | 53.97 | 53.97 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 207 | 75800 | 80899 | Block Work | Level 2 | Independent | 3.6 | 1.3 | 1.5 | 1 | 1 | m2-LxH | 4.68 | 2023-01-18 | 2023-01-23 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 39.34 | 1.97 | 16.86 | 58.17 | 58.17 | 0 |  | 58.17 | 0 | 58.17 | 0 | 39.34 | 39.34 | 0 | 1.97 | 1.97 | 0 | 16.86 | 16.86 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 208 | 75853 | 78607 | Loading Bay Work | Roof | Independent 1.8m wide | 1 | 4 | 2 | 0.5 | 1 | m2-LxH | 2 | 2023-01-18 | 2023-01-26 | 100% | 100% | 100% | 1.2857 | 16.76 | 0.77 | 23.46 | 1.98 | 10.06 | 35.5 | 35.5 | 0 |  | 35.5 | 0 | 35.5 | 0 | 23.46 | 23.46 | 0 | 1.98 | 1.98 | 0 | 10.06 | 10.06 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 209 | 75854 | 78608 | Canopy Frame Instalation Work | Roof | Independent | 1 | 10 | 1.5 | 1.5 | 1 | m2-LxH | 15 | 2023-01-18 | 2023-01-26 | 100% | 100% | 100% | 1.2857 | 12.01 | 0.49 | 126.11 | 9.45 | 54.05 | 189.61 | 189.61 | 0 |  | 189.61 | 0 | 189.61 | 0 | 126.11 | 126.11 | 0 | 9.45 | 9.45 | 0 | 54.05 | 54.05 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 181a | 75855 | 82162 | Electrical Work | Ground Level | Tower | 1 | 2 | 1 | 2 | 1 | rm | 2 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 63.34 | 7.28 | 88.68 | 64.48 | 38 | 191.16 | 191.16 | 0 |  | 191.16 | 0 | 191.16 | 0 | 100.14 | 100.14 | 0 | 66.81 | 66.81 | 0 | 42.91 | 42.91 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 181b | 75855 | 82162 | Electrical Work | Ground Level | Cantilever (0 < 0.5m width) | 1 | 2 | 0.25 |  | 1 | m2-LxW | 0.5 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 32.75 | 1.05 | 11.46 | 2.33 | 4.91 | 18.7 | 18.7 | 0 |  | 18.7 | 0 | 18.7 | 0 | 100.14 | 100.14 | 0 | 66.81 | 66.81 | 0 | 42.91 | 42.91 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195d | 75857 | 82195 | Electrical Work BW-0934 | Level 2 | Birdcage | 1 | 17 | 3 | 2.5 | 1 | m3 | 127.5 | 2023-01-19 | 2023-03-02 | 100% | 100% | 100% | 6.1429 | 7.08 | 0.49 | 631.89 | 383.78 | 270.81 | 1286.48 | 971.04 | 315.44 |  | 971.04 | 315.44 | 1286.48 | 0 | 631.89 | 631.89 | 0 | 383.78 | 339.15 | 44.63 | 270.81 | 0 | 270.81 | 315.44 | 315.44 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195e | 75858 | 82194 | Electrical Work BW-0934 | Level 2 | Independent | 1 | 8.8 | 1.3 | 2.5 | 1 | m2-LxH | 22 | 2023-01-19 | 2023-03-02 | 100% | 100% | 100% | 6.1429 | 12.01 | 0.49 | 184.95 | 66.22 | 79.27 | 330.44 | 243.47 | 86.97 |  | 243.47 | 86.97 | 330.44 | 0 | 184.95 | 184.95 | 0 | 66.22 | 58.52 | 7.7 | 79.27 | 0 | 79.27 | 86.97 | 86.97 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195f | 75859 | 82193 | Electrical Work BW-0934 | Level 2 | Independent | 1 | 6.3 | 2.5 | 2.5 | 1 | m2-LxH | 15.75 | 2023-01-19 | 2023-03-02 | 100% | 100% | 100% | 6.1429 | 12.01 | 0.49 | 132.41 | 47.41 | 56.75 | 236.57 | 174.31 | 62.26 |  | 174.31 | 62.26 | 236.57 | 0 | 132.41 | 132.41 | 0 | 47.41 | 41.9 | 5.51 | 56.75 | 0 | 56.75 | 62.26 | 62.26 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195g | 75860 | 82192 | Electrical Work BW-0934 | Level 2 | Independent | 1 | 3.8 | 1.3 | 2.5 | 1 | m2-LxH | 9.5 | 2023-01-19 | 2023-03-02 | 100% | 100% | 100% | 6.1429 | 12.01 | 0.49 | 79.87 | 28.6 | 34.23 | 142.7 | 105.14 | 37.56 |  | 105.14 | 37.56 | 142.7 | 0 | 79.87 | 79.87 | 0 | 28.6 | 25.27 | 3.33 | 34.23 | 0 | 34.23 | 37.56 | 37.56 | 0
E11/K149/SK/dm/213 | RESIDENCE | 207a | 75861 | 80899 | Block Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 |  | 1 | m2-LxW | 1.95 | 2023-01-19 | 2023-01-23 | 100% | 100% | 100% | 0.71429 | 36.52 | 2.94 | 49.85 | 4.1 | 21.36 | 75.31 | 75.31 | 0 |  | 75.31 | 0 | 75.31 | 0 | 49.85 | 49.85 | 0 | 4.1 | 4.1 | 0 | 21.36 | 21.36 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 211 | 75862 | 78637 | Wall Repair Work | Basement 1 | Tower | 1 | 2.5 | 1 | 1.5 | 1 | rm | 1.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 66.51 | 28.08 | 28.5 | 123.09 | 123.09 | 0 |  | 123.09 | 0 | 123.09 | 0 | 66.51 | 66.51 | 0 | 28.08 | 28.08 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 212 | 75863 | 78643 | Wall Repair Work | Basement 2 | Independent | 1 | 3.8 | 0.9 | 1 | 1 | m2-LxH | 3.8 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 31.95 | 4.79 | 13.69 | 50.43 | 50.43 | 0 |  | 50.43 | 0 | 50.43 | 0 | 31.95 | 31.95 | 0 | 4.79 | 4.79 | 0 | 13.69 | 13.69 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 213 | 75864 | 78632 | Edge Protection | Roof | Tripple Hnadrail | 1 | 20 |  | 1.5 |  | lm | 20 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 15 | 0.91 | 210 | 46.8 | 90 | 346.8 | 346.8 | 0 |  | 346.8 | 0 | 346.8 | 0 | 210 | 210 | 0 | 46.8 | 46.8 | 0 | 90 | 90 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 214 | 75865 | 78628 | Board Fixing Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 287.21 | 0 |  | 287.21 | 0 | 287.21 | 0 | 170.26 | 170.26 | 0 | 71.37 | 71.37 | 0 | 72.97 | 72.97 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 214 | 75865 | 78628 | Board Fixing Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 15.08 | 5.85 | 6.46 | 27.39 | 27.39 | 0 |  | 27.39 | 0 | 27.39 | 0 | 170.26 | 170.26 | 0 | 71.37 | 71.37 | 0 | 72.97 | 72.97 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 215 | 75866 | 78629 | Board Fixing Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 | 287.21 | 0 |  | 287.21 | 0 | 287.21 | 0 | 166.04 | 166.04 | 0 | 69.73 | 69.73 | 0 | 71.16 | 71.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 215 | 75866 | 78629 | Board Fixing Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 10.86 | 4.21 | 4.65 | 19.72 | 19.72 | 0 |  | 19.72 | 0 | 19.72 | 0 | 166.04 | 166.04 | 0 | 69.73 | 69.73 | 0 | 71.16 | 71.16 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216 | 75867 | 78630 | Wall Repair Work | Basement 2 | Independent | 1 | 3.8 | 0.9 | 1.5 | 1 | m2-LxH | 5.7 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 47.92 | 5.99 | 20.54 | 74.45 | 74.45 | 0 |  | 74.45 | 0 | 74.45 | 0 | 165.62 | 165.62 | 0 | 20.69 | 20.69 | 0 | 70.98 | 70.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216a | 75867 | 78630 | Wall Repair Work | Basement 2 | Independent | 1 | 7 | 0.9 | 2 | 1 | m2-LxH | 14 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 117.7 | 14.7 | 50.44 | 182.84 | 182.84 | 0 |  | 182.84 | 0 | 182.84 | 0 | 165.62 | 165.62 | 0 | 20.69 | 20.69 | 0 | 70.98 | 70.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216b | 75868 | 78631 | Wall Repair Work | Basement 1 | Independent | 1 | 7.5 | 0.9 | 2.5 | 1 | m2-LxH | 18.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 157.63 | 19.69 | 67.56 | 244.88 | 244.88 | 0 |  | 244.88 | 0 | 244.88 | 0 | 188.96 | 188.96 | 0 | 29.82 | 29.82 | 0 | 80.99 | 80.99 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216b | 75868 | 78631 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 7.5 | 0.9 |  | 1 | m2-LxW | 6.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 31.33 | 10.13 | 13.43 | 54.89 | 54.89 | 0 |  | 54.89 | 0 | 54.89 | 0 | 188.96 | 188.96 | 0 | 29.82 | 29.82 | 0 | 80.99 | 80.99 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216c | 75869 | 78631 | Wall Repair Work | Basement 1 | Independent | 1 | 7.5 | 0.9 | 2.5 | 1 | m2-LxH | 18.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 157.63 | 19.69 | 67.56 | 244.88 | 244.88 | 0 |  | 244.88 | 0 | 244.88 | 0 | 340.13 | 340.13 | 0 | 53.67 | 53.67 | 0 | 145.78 | 145.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216c | 75869 | 78631 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 7.5 | 0.9 |  | 1 | m2-LxW | 6.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 31.33 | 10.13 | 13.43 | 54.89 | 54.89 | 0 |  | 54.89 | 0 | 54.89 | 0 | 340.13 | 340.13 | 0 | 53.67 | 53.67 | 0 | 145.78 | 145.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216d | 75869 | 78633 | Wall Repair Work | Basement 1 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 126.11 | 15.75 | 54.05 | 195.91 | 195.91 | 0 |  | 195.91 | 0 | 195.91 | 0 | 340.13 | 340.13 | 0 | 53.67 | 53.67 | 0 | 145.78 | 145.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216d | 75869 | 78633 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 25.06 | 8.1 | 10.74 | 43.9 | 43.9 | 0 |  | 43.9 | 0 | 43.9 | 0 | 340.13 | 340.13 | 0 | 53.67 | 53.67 | 0 | 145.78 | 145.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216e | 75870 | 78633 | Wall Repair Work | Basement 1 | Independent | 1 | 6.3 | 0.9 | 2.5 | 1 | m2-LxH | 15.75 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 132.41 | 16.54 | 56.75 | 205.7 | 205.7 | 0 |  | 205.7 | 0 | 205.7 | 0 | 158.72 | 158.72 | 0 | 25.05 | 25.05 | 0 | 68.03 | 68.03 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 216e | 75870 | 78633 | Wall Repair Work | Basement 1 | Additional Boarding | 1 | 6.3 | 0.9 |  | 1 | m2-LxW | 5.67 | 2023-01-21 | 2023-02-04 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 26.31 | 8.51 | 11.28 | 46.1 | 46.1 | 0 |  | 46.1 | 0 | 46.1 | 0 | 158.72 | 158.72 | 0 | 25.05 | 25.05 | 0 | 68.03 | 68.03 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 217 | 75871 | 78639 | Access Scaffold | Ground Level | Independent | 1 | 5.1 | 1.3 | 1 | 1 | m2-LxH | 5.1 | 2023-01-21 | 2023-02-07 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 42.88 | 6.43 | 18.38 | 67.69 | 67.69 | 0 |  | 67.69 | 0 | 67.69 | 0 | 42.88 | 42.88 | 0 | 6.43 | 6.43 | 0 | 18.38 | 18.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 218 | 75872 | 78634 | Wall Finishing Work | Ground Level | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 | 193.81 | 0 |  | 193.81 | 0 | 193.81 | 0 | 151.17 | 151.17 | 0 | 20.67 | 20.67 | 0 | 64.79 | 64.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 218 | 75872 | 78634 | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 25.06 | 7.02 | 10.74 | 42.82 | 42.82 | 0 |  | 42.82 | 0 | 42.82 | 0 | 151.17 | 151.17 | 0 | 20.67 | 20.67 | 0 | 64.79 | 64.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 218a | 75873 | 78634 | Wall Finishing Work | Ground Level | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 142.92 | 15.47 | 61.25 | 219.64 | 219.64 | 0 |  | 219.64 | 0 | 219.64 | 0 | 171.32 | 171.32 | 0 | 23.43 | 23.43 | 0 | 73.42 | 73.42 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 218a | 75873 | 78634 | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 6.8 | 0.9 |  | 1 | m2-LxW | 6.12 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 28.4 | 7.96 | 12.17 | 48.53 | 48.53 | 0 |  | 48.53 | 0 | 48.53 | 0 | 171.32 | 171.32 | 0 | 23.43 | 23.43 | 0 | 73.42 | 73.42 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 218b | 75874 | 78635 | Wall Finishing Work | Level 1 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 84.07 | 9.1 | 36.03 | 129.2 | 129.2 | 0 |  | 129.2 | 0 | 129.2 | 0 | 84.07 | 84.07 | 0 | 9.1 | 9.1 | 0 | 36.03 | 36.03 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 219 | 75875 | 78636 | Wall Finishing Work | Level 3 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 | 193.81 | 0 |  | 193.81 | 0 | 193.81 | 0 | 151.17 | 151.17 | 0 | 20.67 | 20.67 | 0 | 64.79 | 64.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 219 | 75875 | 78636 | Wall Finishing Work | Level 3 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-23 | 2023-02-04 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 25.06 | 7.02 | 10.74 | 42.82 | 42.82 | 0 |  | 42.82 | 0 | 42.82 | 0 | 151.17 | 151.17 | 0 | 20.67 | 20.67 | 0 | 64.79 | 64.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 220 | 75876 | 79870 | Edge Protection | Ground Level | Tripple Hnadrail | 1 | 24 |  | 1.5 |  | lm | 24 | 2023-01-24 | 2023-03-06 | 100% | 100% | 100% | 6 | 15 | 0.91 | 252 | 131.04 | 108 | 491.04 | 354.96 | 136.08 |  | 354.96 | 136.08 | 491.04 | 0 | 252 | 252 | 0 | 131.04 | 102.96 | 28.08 | 108 | 0 | 108 | 136.08 | 136.08 | 0
E11/K149/SK/dm/213 | RESIDENCE | 221 | 75877 |  | Water Proofing Work | Level 31 | Independent | 1 | 3.6 | 1.3 | 4 | 1 | m2-LxH | 14.4 | 2023-01-25 |  | 100% | 100% | 0% | 8.5714 | 12.01 | 0.49 | 121.06 | 60.48 | 0 | 181.54 | 153.32 | 28.22 |  | 153.32 | 28.22 | 181.54 | 0 | 234.81 | 234.81 | 0 | 179.28 | 95.62 | 83.66 | 0 | 0 | 0 | 83.66 | 83.66 | 0
E11/K149/SK/dm/213 | RESIDENCE | 221 | 75877 |  | Water Proofing Work | Level 31 | Additional Boarding | 1 | 3.6 | 1.3 |  | 1 | m2-LxW | 4.68 | 2023-01-25 |  | 100% | 100% | 0% | 8.5714 | 6.63 | 0.7 | 21.72 | 28.08 | 0 | 49.8 | 36.7 | 13.1 |  | 36.7 | 13.1 | 49.8 | 0 | 234.81 | 234.81 | 0 | 179.28 | 95.62 | 83.66 | 0 | 0 | 0 | 83.66 | 83.66 | 0
E11/K149/SK/dm/213 | RESIDENCE | 221a | 75877 |  | Water Proofing Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 4.8 | 0.75 |  | 1 | m2-LxW | 3.6 | 2023-01-25 |  | 100% | 100% | 0% | 8.5714 | 36.52 | 2.94 | 92.03 | 90.72 | 0 | 182.75 | 140.41 | 42.34 |  | 140.41 | 42.34 | 182.75 | 0 | 234.81 | 234.81 | 0 | 179.28 | 95.62 | 83.66 | 0 | 0 | 0 | 83.66 | 83.66 | 0
E11/K149/SK/dm/213 | HOTEL | 79 | 79093 | 79910 | Electrical KMEP-BW 0917 | Ground Level | Independent | 1 | 5.3 | 1.3 | 3.8 | 1 | m2-LxH | 20.14 | 2022-12-26 | 2023-03-15 | 100% | 100% | 100% | 11.4286 | 12.01 | 0.49 | 169.32 | 112.78 | 72.56 | 354.66 | 256.73 | 97.93 |  | 256.73 | 97.93 | 354.66 | 0 | 201.3 | 201.3 | 0 | 167.9 | 130.13 | 37.77 | 86.26 | 0 | 86.26 | 124.03 | 124.03 | 0
E11/K149/SK/dm/213 | HOTEL | 79 | 79093 | 79910 | Electrical KMEP-BW 0917 | Ground Level | Additional Boarding | 1 | 5.3 | 1.3 |  | 1 | m2-LxW | 6.89 | 2022-12-26 | 2023-03-15 | 100% | 100% | 100% | 11.4286 | 6.63 | 0.7 | 31.98 | 55.12 | 13.7 | 100.8 | 74.7 | 26.1 |  | 74.7 | 26.1 | 100.8 | 0 | 201.3 | 201.3 | 0 | 167.9 | 130.13 | 37.77 | 86.26 | 0 | 86.26 | 124.03 | 124.03 | 0
E11/K149/SK/dm/213 | HOTEL | 80 | 79094 |  | Wall Concrete Work | Level 2 | Independent | 1 | 4.8 | 1.3 | 5 | 1 | m2-LxH | 24 | 2022-12-26 |  | 100% | 100% | 0% | 12.8571 | 12.01 | 0.49 | 201.77 | 151.2 | 0 | 352.97 | 305.93 | 47.04 |  | 305.93 | 47.04 | 352.97 | 0 | 230.73 | 230.73 | 0 | 207.36 | 142.85 | 64.51 | 0 | 0 | 0 | 64.51 | 64.51 | 0
E11/K149/SK/dm/213 | HOTEL | 80 | 79094 |  | Wall Concrete Work | Level 2 | Additional Boarding | 1 | 4.8 | 1.3 |  | 1 | m2-LxW | 6.24 | 2022-12-26 |  | 100% | 100% | 0% | 12.8571 | 6.63 | 0.7 | 28.96 | 56.16 | 0 | 85.12 | 67.65 | 17.47 |  | 67.65 | 17.47 | 85.12 | 0 | 230.73 | 230.73 | 0 | 207.36 | 142.85 | 64.51 | 0 | 0 | 0 | 64.51 | 64.51 | 0
E11/K149/SK/dm/213 | HOTEL | 80a | 79095 |  | Wall Concrete Work | Level 2 | Tower | 1 | 1.3 | 1 | 3.5 | 1 | rm | 3.5 | 2022-12-26 |  | 100% | 100% | 0% | 12.8571 | 63.34 | 7.28 | 155.18 | 327.6 | 0 | 482.78 | 380.86 | 101.92 |  | 380.86 | 101.92 | 482.78 | 0 | 159.82 | 159.82 | 0 | 336.6 | 231.88 | 104.72 | 0 | 0 | 0 | 104.72 | 104.72 | 0
E11/K149/SK/dm/213 | HOTEL | 80a | 79095 |  | Wall Concrete Work | Level 2 | Additional Boarding | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2022-12-26 |  | 100% | 100% | 0% | 12.8571 | 6.63 | 0.7 | 4.64 | 9 | 0 | 13.64 | 10.84 | 2.8 |  | 10.84 | 2.8 | 13.64 | 0 | 159.82 | 159.82 | 0 | 336.6 | 231.88 | 104.72 | 0 | 0 | 0 | 104.72 | 104.72 | 0
E11/K149/SK/dm/213 | HOTEL | 81 | 79096 | 78599 | Staircase 7 For (KMEP - BW 793) | Ground Level | Tower | 1 | 1.8 | 1 | 2.7 | 1 | rm | 2.7 | 2022-12-26 | 2023-02-22 | 100% | 100% | 100% | 8.4286 | 63.34 | 7.28 | 119.71 | 165.67 | 51.31 | 336.69 | 336.69 | 0 |  | 336.69 | 0 | 336.69 | 0 | 119.71 | 119.71 | 0 | 165.67 | 165.67 | 0 | 51.31 | 51.31 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 82 | 79097 | 79849 | Canopy EFIS Fixing Work | Level 29 | Independent 1.8m wide | 1 | 22.5 | 1.8 | 8 | 1 | m2-LxH | 180 | 2022-12-28 | 2023-03-08 | 100% | 100% | 100% | 10.1429 | 16.76 | 0.77 | 2111.76 | 1405.8 | 905.04 | 4422.6 | 3299.76 | 1122.84 |  | 3299.76 | 1122.84 | 4422.6 | 0 | 2369.67 | 2369.67 | 0 | 1459.8 | 1242 | 217.8 | 1015.57 | 110.53 | 905.04 | 1122.84 | 1122.84 | 0
E11/K149/SK/dm/213 | HOTEL | 82a | 79097 | 80935 | Canopy EFIS Fixing Work | Level 29 | Cantilever (0 < 0.5m width) | 1 | 22.5 | 0.5 | 1 | 1 | m2-LxW | 11.25 | 2022-12-28 | 2023-01-28 | 100% | 100% | 100% | 4.5714 | 32.75 | 1.05 | 257.91 | 54 | 110.53 | 422.44 | 422.44 | 0 |  | 422.44 | 0 | 422.44 | 0 | 2369.67 | 2369.67 | 0 | 1459.8 | 1242 | 217.8 | 1015.57 | 110.53 | 905.04 | 1122.84 | 1122.84 | 0
E11/K149/SK/dm/553 | HOTEL | 83 | 79098 | 80908 | Parapet FIFS Plaster Work | Level 2 | 1399-38 | 1 | 24 | 1.8 | 3 | 1 | m2-LxH | 72 | 2022-12-28 | 2023-01-12 | 100% | 100% | 100% | 2.2857 | 475.573 | 37.29 | 23968.88 | 6136.87 | 10272.38 | 40378.13 | 40378.13 | 0 |  | 40378.13 | 0 | 40378.13 | 0 | 23968.88 | 23968.88 | 0 | 6136.87 | 6136.87 | 0 | 10272.38 | 10272.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 84 | 79099 | 78593 | Canopy Instalation Work | Level 29 | Independent 1.8m wide | 1 | 12.5 | 1.8 | 3.5 | 1 | m2-LxH | 43.75 | 2022-12-30 | 2023-02-18 | 100% | 100% | 100% | 7.2857 | 16.76 | 0.77 | 513.28 | 245.44 | 219.98 | 978.7 | 978.7 | 0 |  | 978.7 | 0 | 978.7 | 0 | 604.98 | 604.98 | 0 | 276.04 | 276.04 | 0 | 259.28 | 259.28 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 84a | 79099 | 78593 | Canopy Instalation Work | Level 29 | Cantilever (0 < 0.5m width) | 1 | 8 | 0.5 | 1 | 1 | m2-LxW | 4 | 2022-12-30 | 2023-02-18 | 100% | 100% | 100% | 7.2857 | 32.75 | 1.05 | 91.7 | 30.6 | 39.3 | 161.6 | 161.6 | 0 |  | 161.6 | 0 | 161.6 | 0 | 604.98 | 604.98 | 0 | 276.04 | 276.04 | 0 | 259.28 | 259.28 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 85&85a | 79100 | 80920 | Balcony Ceiling Work | Level 19 | Design 1399-35b | 1 | 6.1 | 1 | 1 | 1 | unit | 1 | 2022-12-30 | 2023-01-26 | 100% | 100% | 100% | 4 | 2514.5966 | 74.0398 | 1760.22 | 296.16 | 754.38 | 2810.76 | 2810.76 | 0 | Tas Quote 2439-25-1 (item#5) | 2810.76 | 0 | 2810.76 | 0 | 1760.22 | 1760.22 | 0 | 296.16 | 296.16 | 0 | 754.38 | 754.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 150d | 79199 | 78613 | Access Scaffold | Level 17 | Tower | 1 | 2 | 1 | 2 | 1 | rm | 2 | 2023-01-02 | 2023-01-30 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 88.68 | 60.32 | 38 | 187 | 187 | 0 |  | 187 | 0 | 187 | 0 | 88.68 | 88.68 | 0 | 60.32 | 60.32 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 84b | 75801 | 79848 | Canopy Instalation Work | Level 29 | Independent 1.8m wide | 1 | 10 | 1.8 | 3.5 | 1 | m2-LxH | 35 | 2023-01-02 | 2023-03-08 | 100% | 100% | 100% | 9.4286 | 16.76 | 0.77 | 410.62 | 254.1 | 175.98 | 840.7 | 622.37 | 218.33 |  | 622.37 | 218.33 | 840.7 | 0 | 525.25 | 525.25 | 0 | 290.1 | 247.75 | 42.35 | 225.11 | 49.13 | 175.98 | 218.33 | 218.33 | 0
E11/K149/SK/dm/213 | HOTEL | 84c | 75801 | 78594 | Canopy Instalation Work | Level 29 | Cantilever (0 < 0.5m width) | 1 | 10 | 0.5 | 1 | 1 | m2-LxW | 5 | 2023-01-02 | 2023-02-18 | 100% | 100% | 100% | 6.8571 | 32.75 | 1.05 | 114.63 | 36 | 49.13 | 199.76 | 199.76 | 0 |  | 199.76 | 0 | 199.76 | 0 | 525.25 | 525.25 | 0 | 290.1 | 247.75 | 42.35 | 225.11 | 49.13 | 175.98 | 218.33 | 218.33 | 0
E11/K149/SK/dm/213 | HOTEL | 84d | 75802 | 80911 | EFIS Finshing Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 17 | 1.5 | 1 | 1 | m2-LxW | 25.5 | 2023-01-02 | 2023-01-16 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 651.88 | 160.65 | 279.38 | 1091.91 | 1091.91 | 0 |  | 1091.91 | 0 | 1091.91 | 0 | 651.88 | 651.88 | 0 | 160.65 | 160.65 | 0 | 279.38 | 279.38 | 0 | 0 | 0 | 0
E11/K149/PK/dm/378 | HOTEL | 43f&43g | 75803 | 80934 | GRC Panel Work | Ground Level | 1399-21 | 1 | 2.5 | 1.3 | 5 | 1 | m2-LxH | 12.5 | 2023-01-02 | 2023-01-30 | 100% | 100% | 100% | 4.1429 | 95.9 | 13.9 | 839.13 | 719.82 | 359.63 | 1918.58 | 1918.58 | 0 | Tas Quote - 2439-15-1 (item-1 Prorate) | 1918.58 | 0 | 1918.58 | 0 | 839.13 | 839.13 | 0 | 719.82 | 719.82 | 0 | 359.63 | 359.63 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 86&86a | 75804 | 80916 | Balcony Ceiling Work | Level 13 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-03 | 2023-01-20 | 100% | 100% | 100% | 2.5714 | 1772.5845 | 52.192 | 1240.81 | 134.21 | 531.78 | 1906.8 | 1906.8 | 0 | Tas Quote 2439-25-1 (item#5) | 1906.8 | 0 | 1906.8 | 0 | 1240.81 | 1240.81 | 0 | 134.21 | 134.21 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 87&87a | 75805 | 80917 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 6.1 | 1 | 1 | 1 | unit | 1 | 2023-01-04 | 2023-01-23 | 100% | 100% | 100% | 2.8571 | 2514.5966 | 74.0398 | 1760.22 | 211.54 | 754.38 | 2726.14 | 2726.14 | 0 | Tas Quote 2439-25-1 (item#5) | 2726.14 | 0 | 2726.14 | 0 | 1760.22 | 1760.22 | 0 | 211.54 | 211.54 | 0 | 754.38 | 754.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88 | 75806 | 78560 | Wall Painting Work | basement 2 | Independent | 1 | 4 | 1.3 | 2 | 1 | m2-LxH | 8 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 67.26 | 22.4 | 28.82 | 118.48 | 118.48 | 0 |  | 118.48 | 0 | 118.48 | 0 | 67.26 | 67.26 | 0 | 22.4 | 22.4 | 0 | 28.82 | 28.82 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88a | 75807 | 78560 | Wall Painting Work | basement 2 | Tower | 1 | 2.5 | 0.9 | 2 | 1 | rm | 2 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 63.34 | 7.28 | 88.68 | 83.2 | 38 | 209.88 | 209.88 | 0 |  | 209.88 | 0 | 209.88 | 0 | 88.68 | 88.68 | 0 | 83.2 | 83.2 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88b | 75808 | 78561 | Wall Painting Work | basement 2 | Independent | 1 | 3.1 | 1.3 | 1.5 | 1 | m2-LxH | 4.65 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 39.09 | 13.02 | 16.75 | 68.86 | 68.86 | 0 |  | 68.86 | 0 | 68.86 | 0 | 39.09 | 39.09 | 0 | 13.02 | 13.02 | 0 | 16.75 | 16.75 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88c | 75809 | 78561 | Wall Painting Work | basement 1 | Independent | 1 | 6.1 | 0.9 | 1.5 | 1 | m2-LxH | 9.15 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 76.92 | 25.62 | 32.97 | 135.51 | 135.51 | 0 |  | 135.51 | 0 | 135.51 | 0 | 76.92 | 76.92 | 0 | 25.62 | 25.62 | 0 | 32.97 | 32.97 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88d | 75810 | 78562 | Wall Painting Work | basement 1 | Independent | 1 | 6.8 | 0.9 | 1.5 | 1 | m2-LxH | 10.2 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 85.75 | 28.56 | 36.75 | 151.06 | 151.06 | 0 |  | 151.06 | 0 | 151.06 | 0 | 85.75 | 85.75 | 0 | 28.56 | 28.56 | 0 | 36.75 | 36.75 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88e | 75811 | 78562 | Wall Painting Work | basement 1 | Independent | 1 | 6.3 | 0.9 | 3 | 1 | m2-LxH | 18.9 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 158.89 | 52.92 | 68.1 | 279.91 | 279.91 | 0 |  | 279.91 | 0 | 279.91 | 0 | 413.69 | 413.69 | 0 | 166.72 | 166.72 | 0 | 177.3 | 177.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88e | 75811 | 78562 | Wall Painting Work | basement 1 | Additional Boarding | 1 | 6.3 | 0.9 |  | 1 | m2-LxW | 5.67 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 6.63 | 0.7 | 26.31 | 22.68 | 11.28 | 60.27 | 60.27 | 0 |  | 60.27 | 0 | 60.27 | 0 | 413.69 | 413.69 | 0 | 166.72 | 166.72 | 0 | 177.3 | 177.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88f | 75811 | 78563 | Wall Painting Work | basement 1 | Independent | 1 | 6.8 | 0.9 | 3.5 | 1 | m2-LxH | 23.8 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 12.01 | 0.49 | 200.09 | 66.64 | 85.75 | 352.48 | 352.48 | 0 |  | 352.48 | 0 | 352.48 | 0 | 413.69 | 413.69 | 0 | 166.72 | 166.72 | 0 | 177.3 | 177.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 88f | 75811 | 78563 | Wall Painting Work | basement 1 | Additional Boarding | 1 | 6.8 | 0.9 |  | 1 | m2-LxW | 6.12 | 2023-01-05 | 2023-02-13 | 100% | 100% | 100% | 5.7143 | 6.63 | 0.7 | 28.4 | 24.48 | 12.17 | 65.05 | 65.05 | 0 |  | 65.05 | 0 | 65.05 | 0 | 413.69 | 413.69 | 0 | 166.72 | 166.72 | 0 | 177.3 | 177.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 89 | 75813 | 79902 | Wall Painting Work | Ground Level | Tower | 1 | 1.3 | 1 | 2.5 | 1 | rm | 2.5 | 2023-01-05 | 2023-03-11 | 100% | 100% | 100% | 9.4286 | 63.34 | 7.28 | 110.85 | 171.6 | 47.51 | 329.96 | 246.05 | 83.91 |  | 246.05 | 83.91 | 329.96 | 0 | 110.85 | 110.85 | 0 | 171.6 | 135.2 | 36.4 | 47.51 | 0 | 47.51 | 83.91 | 83.91 | 0
E11/K149/SK/dm/213 | HOTEL | 90 | 75814 | 80921 | Road Side Access | Level 28 | Tower | 1 | 1.3 | 0.9 | 1.5 | 1 | rm | 1.5 | 2023-01-06 | 2023-01-26 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 66.51 | 32.76 | 28.5 | 127.77 | 127.77 | 0 |  | 127.77 | 0 | 127.77 | 0 | 66.51 | 66.51 | 0 | 32.76 | 32.76 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 91 | 75815 |  | Road Side Access | Roof | Independent | 1 | 3 | 1.3 | 1 | 1 | m2-LxH | 3 | 2023-01-06 |  | 100% | 100% | 0% | 11.2857 | 12.01 | 0.49 | 25.22 | 16.59 | 0 | 41.81 | 35.93 | 5.88 |  | 35.93 | 5.88 | 41.81 | 0 | 25.22 | 25.22 | 0 | 16.59 | 10.71 | 5.88 | 0 | 0 | 0 | 5.88 | 5.88 | 0
E11/K149/SK/dm/595 | HOTEL | 92&92a | 75816 | 78591 | View Deck Loading Platform | Level 29 | 1399-41A | 1 |  |  |  | 1 | unit | 1 | 2023-01-06 | 2023-02-18 | 100% | 100% | 100% | 6.2857 | 7493.729 | 639.6768 | 5245.61 | 4020.83 | 2248.12 | 11514.56 | 11514.56 | 0 | 2439-30-1 Item--10) | 11514.56 | 0 | 11514.56 | 0 | 5245.61 | 5245.61 | 0 | 4020.83 | 4020.83 | 0 | 2248.12 | 2248.12 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 93&93a | 75817 | 80922 | Balcony Ceiling Work | Level 15 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-07 | 2023-01-27 | 100% | 100% | 100% | 3 | 1772.5845 | 52.192 | 1240.81 | 156.58 | 531.78 | 1929.17 | 1929.17 | 0 | Tas Quote 2439-25-1 (item#5) | 1929.17 | 0 | 1929.17 | 0 | 1240.81 | 1240.81 | 0 | 156.58 | 156.58 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 94 | 75818 | 80906 | Electrical Work | basement 1 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-09 | 2023-01-10 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 110.85 | 5.2 | 47.51 | 163.56 | 163.56 | 0 |  | 163.56 | 0 | 163.56 | 0 | 110.85 | 110.85 | 0 | 5.2 | 5.2 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 95 | 75819 | 80943 | Electrical Work BW 0973 | basement 1 | Independent | 1 | 3.8 | 1.3 | 2 | 1 | m2-LxH | 7.6 | 2023-01-09 | 2023-01-28 | 100% | 100% | 100% | 2.8571 | 12.01 | 0.49 | 63.89 | 10.64 | 27.38 | 101.91 | 101.91 | 0 |  | 101.91 | 0 | 101.91 | 0 | 63.89 | 63.89 | 0 | 10.64 | 10.64 | 0 | 27.38 | 27.38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 96 | 75820 | 80912 | Electrical Work BW 0973 | basement 1 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-09 | 2023-01-16 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 88.68 | 16.64 | 38 | 143.32 | 143.32 | 0 |  | 143.32 | 0 | 143.32 | 0 | 88.68 | 88.68 | 0 | 16.64 | 16.64 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 97&97a | 75821 | 80923 | Balcony Ceiling Work | Level 26 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-09 | 2023-01-26 | 100% | 100% | 100% | 2.5714 | 1772.5845 | 52.192 | 1240.81 | 134.21 | 531.78 | 1906.8 | 1906.8 | 0 | Tas Quote 2439-25-1 (item#5) | 1906.8 | 0 | 1906.8 | 0 | 1240.81 | 1240.81 | 0 | 134.21 | 134.21 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 98 | 75822 | 80944 | Electrical Work BW 0973 | basement 1 | Independent 1.8m wide | 1 | 3.6 | 2.5 | 3 | 1 | m2-LxH | 10.8 | 2023-01-10 | 2023-02-01 | 100% | 100% | 100% | 3.2857 | 16.76 | 0.77 | 126.71 | 27.32 | 54.3 | 208.33 | 208.33 | 0 |  | 208.33 | 0 | 208.33 | 0 | 126.71 | 126.71 | 0 | 27.32 | 27.32 | 0 | 54.3 | 54.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 99 | 75823 | 80903 | Wall Concrete Work | Ground Level | Independent | 1 | 15.7 | 1 | 1 | 1 | m2-LxH | 15.7 | 2023-01-10 | 2023-01-10 | 100% | 100% | 100% | 0.14286 | 12.01 | 0.49 | 131.99 | 1.1 | 56.57 | 189.66 | 189.66 | 0 |  | 189.66 | 0 | 189.66 | 0 | 131.99 | 131.99 | 0 | 1.1 | 1.1 | 0 | 56.57 | 56.57 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 100&100a | 75824 | 80924 | Balcony Ceiling Work | Level 25 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-10 | 2023-01-27 | 100% | 100% | 100% | 2.5714 | 1772.5845 | 52.192 | 1240.81 | 134.21 | 531.78 | 1906.8 | 1906.8 | 0 | Tas Quote 2439-25-1 (item#5) | 1906.8 | 0 | 1906.8 | 0 | 1240.81 | 1240.81 | 0 | 134.21 | 134.21 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 101 | 75826 | 80907 | Electrical Work | basement 1 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-10 | 2023-01-12 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 | 166.16 | 0 |  | 166.16 | 0 | 166.16 | 0 | 110.85 | 110.85 | 0 | 7.8 | 7.8 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 102&102a | 75827 | 80925 | Balcony Ceiling Work | Level 26 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-11 | 2023-01-26 | 100% | 100% | 100% | 2.2857 | 1772.5845 | 52.192 | 1240.81 | 119.3 | 531.78 | 1891.89 | 1891.89 | 0 | Tas Quote 2439-25-1 (item#5) | 1891.89 | 0 | 1891.89 | 0 | 1240.81 | 1240.81 | 0 | 119.3 | 119.3 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 103 | 75828 | 80945 | Generator Room AC Chiller Work | basement 1 | Independent | 1 | 5 | 0.6 | 1.5 | 1 | m2-LxH | 7.5 | 2023-01-11 | 2023-01-31 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 63.05 | 11.03 | 27.02 | 101.1 | 101.1 | 0 |  | 101.1 | 0 | 101.1 | 0 | 63.05 | 63.05 | 0 | 11.03 | 11.03 | 0 | 27.02 | 27.02 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 104 | 75829 | 80913 | Electrical Work BW 0973 | basement 1 | Independent | 1 | 3.8 | 1.3 | 2.3 | 1 | m2-LxH | 8.74 | 2023-01-11 | 2023-01-16 | 100% | 100% | 100% | 0.85714 | 12.01 | 0.49 | 73.48 | 3.67 | 31.49 | 108.64 | 108.64 | 0 |  | 108.64 | 0 | 108.64 | 0 | 73.48 | 73.48 | 0 | 3.67 | 3.67 | 0 | 31.49 | 31.49 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 105&105a | 75830 | 80926 | Balcony Ceiling Work | Level 20 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-12 | 2023-01-26 | 100% | 100% | 100% | 2.1429 | 1772.5845 | 52.192 | 1240.81 | 111.84 | 531.78 | 1884.43 | 1884.43 | 0 | Tas Quote 2439-25-1 (item#5) | 1884.43 | 0 | 1884.43 | 0 | 1240.81 | 1240.81 | 0 | 111.84 | 111.84 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 82b | 75831 | 79847 | Balcony Ceiling Work | Level 29 | Independent 1.8m wide | 1 | 3.8 | 1.8 | 3.5 | 1 | m2-LxH | 13.3 | 2023-01-12 | 2023-03-08 | 100% | 100% | 100% | 8 | 16.76 | 0.77 | 156.04 | 81.93 | 66.87 | 304.84 | 221.88 | 82.96 |  | 221.88 | 82.96 | 304.84 | 0 | 184.93 | 184.93 | 0 | 104.71 | 87.2 | 17.51 | 79.25 | 0 | 79.25 | 96.76 | 96.76 | 0
E11/K149/SK/dm/213 | HOTEL | 82c | 75831 | 79818 | Balcony Ceiling Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 0.75 | 1 | 1 | m2-LxW | 1.13 | 2023-01-12 | 2023-02-28 | 100% | 100% | 100% | 6.8571 | 36.52 | 2.94 | 28.89 | 22.78 | 12.38 | 64.05 | 50.25 | 13.8 |  | 50.25 | 13.8 | 64.05 | 0 | 184.93 | 184.93 | 0 | 104.71 | 87.2 | 17.51 | 79.25 | 0 | 79.25 | 96.76 | 96.76 | 0
E11/K149/SK/dm/213 | HOTEL | 106 | 75832 | 78564 | Wall Corring Work | Level 29 | Tower | 1 | 2.5 | 1 | 3 | 1 | rm | 3 | 2023-01-12 | 2023-02-09 | 100% | 100% | 100% | 4.1429 | 63.34 | 7.28 | 133.01 | 90.48 | 57.01 | 280.5 | 280.5 | 0 |  | 280.5 | 0 | 280.5 | 0 | 133.01 | 133.01 | 0 | 90.48 | 90.48 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/595 | HOTEL | 107 | 75833 | 79808 | View Deck Loading Platform | Level 29 | 1399-42 | 1 |  |  |  | 1 | unit | 1 | 2023-01-12 | 2023-02-22 | 100% | 100% | 100% | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439-30-1 Item--10), Charged under Tag 92&92a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/640 | HOTEL | 108 To 108e | 75838 | 80929 | Steel Column Lifting Work (1399-45a) | Level 29 | Independent | 1 |  |  |  |  | unit | 1 | 2023-01-13 | 2023-01-28 | 75% | 75% | 75% | 2.2857 | 19801.4293 | 837.8213 | 10395.75 | 1436.27 | 4455.32 | 16287.34 | 16287.34 | 0 | Tas Quote 2439-34-1 | 16287.34 | 0 | 16287.34 | 0 | 10395.75 | 10395.75 | 0 | 1436.27 | 1436.27 | 0 | 4455.32 | 4455.32 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 109 | 75834 | 79827 | Electrical KMEP-BW 1012 | Level 5 | Independent | 1 | 4.3 | 1.3 | 4 | 1 | m2-LxH | 17.2 | 2023-01-13 | 2023-03-06 | 100% | 100% | 100% | 7.5714 | 12.01 | 0.49 | 144.6 | 63.81 | 61.97 | 270.38 | 197.58 | 72.8 |  | 197.58 | 72.8 | 270.38 | 0 | 144.6 | 144.6 | 0 | 63.81 | 52.98 | 10.83 | 61.97 | 0 | 61.97 | 72.8 | 72.8 | 0
E11/K149/SK/dm/213 | HOTEL | 110 | 75835 | 79828 | Electrical KMEP-BW 1012 | Level 5 | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2023-01-13 | 2023-03-06 | 100% | 100% | 100% | 7.5714 | 63.34 | 7.28 | 199.52 | 248.04 | 85.51 | 533.07 | 405.44 | 127.63 |  | 405.44 | 127.63 | 533.07 | 0 | 199.52 | 199.52 | 0 | 248.04 | 205.92 | 42.12 | 85.51 | 0 | 85.51 | 127.63 | 127.63 | 0
E11/K149/SK/dm/213 | HOTEL | 80b | 75839 |  | Ceiling Work KMEP-BW 1012 | Level 2 | Tower | 1 | 2.5 | 2.5 | 5.5 | 1 | rm | 5.5 | 2023-01-14 |  | 100% | 100% | 0% | 10.1429 | 63.34 | 7.28 | 243.86 | 406.12 | 0 | 649.98 | 489.82 | 160.16 |  | 489.82 | 160.16 | 649.98 | 0 | 243.86 | 243.86 | 0 | 406.12 | 245.96 | 160.16 | 0 | 0 | 0 | 160.16 | 160.16 | 0
E11/K149/SK/dm/213 | HOTEL | 111 | 75836 | 79829 | Ceiling Work KMEP-BW 1012 | Level 5 | Tower | 1 | 2.5 | 1.3 | 4.5 | 1 | rm | 4.5 | 2023-01-14 | 2023-03-06 | 100% | 100% | 100% | 7.4286 | 63.34 | 7.28 | 199.52 | 243.36 | 85.51 | 528.39 | 400.76 | 127.63 |  | 400.76 | 127.63 | 528.39 | 0 | 214.6 | 214.6 | 0 | 260.26 | 215.22 | 45.04 | 91.97 | 0 | 91.97 | 137.01 | 137.01 | 0
E11/K149/SK/dm/213 | HOTEL | 111 | 75836 | 79829 | Ceiling Work KMEP-BW 1012 | Level 5 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-14 | 2023-03-06 | 100% | 100% | 100% | 7.4286 | 6.63 | 0.7 | 15.08 | 16.9 | 6.46 | 38.44 | 29.06 | 9.38 |  | 29.06 | 9.38 | 38.44 | 0 | 214.6 | 214.6 | 0 | 260.26 | 215.22 | 45.04 | 91.97 | 0 | 91.97 | 137.01 | 137.01 | 0
E11/K149/SK/dm/213 | HOTEL | 43h | 75837 |  | Wall Plaster Work | Ground Level | Additional Boarding | 1 | 1.5 | 1.5 |  | 1 | m2-LxW | 2.25 | 2023-01-14 | 2023-01-30 | 100% | 100% | 100% | 2.4286 | 6.63 | 0.7 | 10.44 | 3.83 | 4.48 | 18.75 | 18.75 | 0 |  | 18.75 | 0 | 18.75 | 0 | 10.44 | 10.44 | 0 | 3.83 | 3.83 | 0 | 4.48 | 4.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 112 | 75840 | 79825 | Plant Room Kmep Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 3.2 | 1 | rm | 3.2 | 2023-01-16 | 2023-03-06 | 100% | 100% | 100% | 7.1429 | 63.34 | 7.28 | 141.88 | 166.4 | 60.81 | 369.09 | 278.33 | 90.76 |  | 278.33 | 90.76 | 369.09 | 0 | 197.27 | 197.27 | 0 | 217.25 | 178.15 | 39.1 | 84.55 | 0 | 84.55 | 123.65 | 123.65 | 0
E11/K149/SK/dm/213 | HOTEL | 112 | 75840 | 79825 | Plant Room Kmep Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-01-16 | 2023-03-06 | 100% | 100% | 100% | 7.1429 | 6.63 | 0.7 | 20.88 | 22.5 | 8.95 | 52.33 | 39.33 | 13 |  | 39.33 | 13 | 52.33 | 0 | 197.27 | 197.27 | 0 | 217.25 | 178.15 | 39.1 | 84.55 | 0 | 84.55 | 123.65 | 123.65 | 0
E11/K149/SK/dm/213 | HOTEL | 112a | 75840 | 79825 | Plant Room Kmep Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 0.75 |  | 1 | m2-LxW | 1.35 | 2023-01-16 | 2023-03-06 | 100% | 100% | 100% | 7.1429 | 36.52 | 2.94 | 34.51 | 28.35 | 14.79 | 77.65 | 57.76 | 19.89 |  | 57.76 | 19.89 | 77.65 | 0 | 197.27 | 197.27 | 0 | 217.25 | 178.15 | 39.1 | 84.55 | 0 | 84.55 | 123.65 | 123.65 | 0
E11/K149/SK/dm/213 | HOTEL | 113 | 75841 | 79826 | Plant Room Kmep Work | Level 5 | Independent | 1 | 4 | 1.5 | 2.3 | 1 | m2-LxH | 9.2 | 2023-01-16 | 2023-03-06 | 100% | 100% | 100% | 7.1429 | 12.01 | 0.49 | 77.34 | 32.2 | 33.15 | 142.69 | 103.74 | 38.95 |  | 103.74 | 38.95 | 142.69 | 0 | 77.34 | 77.34 | 0 | 32.2 | 26.4 | 5.8 | 33.15 | 0 | 33.15 | 38.95 | 38.95 | 0
E11/K149/SK/dm/213 | HOTEL | 114 | 75842 | 80915 | Road Side Access | Level 29 | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-01-16 | 2023-01-19 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 66.51 | 6.24 | 28.5 | 101.25 | 101.25 | 0 |  | 101.25 | 0 | 101.25 | 0 | 66.51 | 66.51 | 0 | 6.24 | 6.24 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 115 | 75843 |  | Road Side Access | Level 29 | Independent 1.8m wide | 1 | 11.8 | 2.5 | 3 | 1 | m2-LxH | 35.4 | 2023-01-16 |  | 100% | 100% | 0% | 9.8571 | 16.76 | 0.77 | 415.31 | 268.69 | 0 | 684 | 574.96 | 109.04 |  | 574.96 | 109.04 | 684 | 0 | 529.94 | 529.94 | 0 | 290.44 | 181.4 | 109.04 | 49.13 | 49.13 | 0 | 109.04 | 109.04 | 0
E11/K149/SK/dm/213 | HOTEL | 115a | 75843 | 78565 | Road Side Access | Level 29 | Cantilever (0 < 0.5m width) | 1 | 10 | 0.5 |  | 1 | m2-LxW | 5 | 2023-01-16 | 2023-02-13 | 100% | 100% | 100% | 4.1429 | 32.75 | 1.05 | 114.63 | 21.75 | 49.13 | 185.51 | 185.51 | 0 |  | 185.51 | 0 | 185.51 | 0 | 529.94 | 529.94 | 0 | 290.44 | 181.4 | 109.04 | 49.13 | 49.13 | 0 | 109.04 | 109.04 | 0
E11/K149/SK/dm/213 | HOTEL | 116 | 75844 | 80914 | Edge Protection | Level 29 | Tripple Hnadrail | 1 | 20 |  | 1.5 | 1 | lm | 20 | 2023-01-17 | 2023-01-18 | 100% | 100% | 100% | 0.28571 | 15 | 0.91 | 210 | 5.2 | 90 | 305.2 | 305.2 | 0 |  | 305.2 | 0 | 305.2 | 0 | 210 | 210 | 0 | 5.2 | 5.2 | 0 | 90 | 90 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 117 | 75845 |  | Canopy Instalation Work | Roof | Independent 1.8m wide | 1 | 8 | 2.5 | 1.5 | 1 | m2-LxH | 12 | 2023-01-18 |  | 100% | 100% | 0% | 9.5714 | 16.76 | 0.77 | 140.78 | 88.44 | 0 | 229.22 | 192.26 | 36.96 |  | 192.26 | 36.96 | 229.22 | 0 | 232.48 | 232.48 | 0 | 104.64 | 67.68 | 36.96 | 39.3 | 39.3 | 0 | 36.96 | 36.96 | 0
E11/K149/SK/dm/213 | HOTEL | 117a | 75845 | 78566 | Canopy Instalation Work | Roof | Cantilever (0 < 0.5m width) | 1 | 8 | 0.5 |  | 1 | m2-LxW | 4 | 2023-01-18 | 2023-02-13 | 100% | 100% | 100% | 3.8571 | 32.75 | 1.05 | 91.7 | 16.2 | 39.3 | 147.2 | 147.2 | 0 |  | 147.2 | 0 | 147.2 | 0 | 232.48 | 232.48 | 0 | 104.64 | 67.68 | 36.96 | 39.3 | 39.3 | 0 | 36.96 | 36.96 | 0
E11/K149/SK/dm/213 | HOTEL | 82d | 75846 | 79846 | Canopy Instalation Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 4 | 1 |  | 1 | m2-LxW | 4 | 2023-01-18 | 2023-03-08 | 100% | 100% | 100% | 7.1429 | 36.52 | 2.94 | 102.26 | 84 | 43.82 | 230.08 | 167.78 | 62.3 |  | 167.78 | 62.3 | 230.08 | 0 | 102.26 | 102.26 | 0 | 84 | 65.52 | 18.48 | 43.82 | 0 | 43.82 | 62.3 | 62.3 | 0
E11/K149/SK/dm/213 | HOTEL | 118 | 75847 |  | Edge Protection | Level 29 | Tripple Hnadrail | 1 | 20 |  | 1.5 | 1 | lm | 20 | 2023-01-18 |  | 100% | 100% | 0% | 9.5714 | 15 | 0.91 | 210 | 174.2 | 0 | 384.2 | 311.4 | 72.8 |  | 311.4 | 72.8 | 384.2 | 0 | 210 | 210 | 0 | 174.2 | 101.4 | 72.8 | 0 | 0 | 0 | 72.8 | 72.8 | 0
E11/K149/SK/dm/213 | HOTEL | 119 | 75848 | 80939 | Access Scaffold | Level 30 | Tower | 1 | 2.5 | 1.3 | 1.3 | 1 | rm | 1.3 | 2023-01-18 | 2023-01-31 | 100% | 100% | 100% | 2 | 63.34 | 7.28 | 57.64 | 18.93 | 24.7 | 101.27 | 101.27 | 0 |  | 101.27 | 0 | 101.27 | 0 | 95.99 | 95.99 | 0 | 27.75 | 27.75 | 0 | 41.13 | 41.13 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 119a | 75848 | 80939 | Access Scaffold | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 2 | 0.75 |  | 1 | m2-LxW | 1.5 | 2023-01-18 | 2023-01-31 | 100% | 100% | 100% | 2 | 36.52 | 2.94 | 38.35 | 8.82 | 16.43 | 63.6 | 63.6 | 0 |  | 63.6 | 0 | 63.6 | 0 | 95.99 | 95.99 | 0 | 27.75 | 27.75 | 0 | 41.13 | 41.13 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 82e | 75849 | 79845 | EFIS Instalation Work | Level 29 | Additional Boarding | 2 | 22.5 | 1.8 |  | 2 | m2-LxW | 81 | 2023-01-18 | 2023-03-08 | 100% | 100% | 100% | 7.1429 | 6.63 | 0.7 | 375.92 | 405 | 161.11 | 942.03 | 691.82 | 250.21 |  | 691.82 | 250.21 | 942.03 | 0 | 375.92 | 375.92 | 0 | 405 | 315.9 | 89.1 | 161.11 | 0 | 161.11 | 250.21 | 250.21 | 0
E11/K149/SK/dm/213 | HOTEL | 120 | 75850 | 79941 | Electrical BOND MEP Work | Level 28 | Birdcage | 1 | 19.3 | 6 | 3.5 | 1 | m3 | 405.3 | 2023-01-19 | 2023-03-23 | 100% | 100% | 100% | 9.1429 | 7.08 | 0.49 | 2008.67 | 1815.74 | 860.86 | 4685.27 | 3086.77 | 1598.5 |  | 3086.77 | 1598.5 | 4685.27 | 0 | 2008.67 | 2008.67 | 0 | 1815.74 | 1078.1 | 737.64 | 860.86 | 0 | 860.86 | 1598.5 | 1598.5 | 0
E11/K149/SK/SR/582 | HOTEL | 121&121a | 75901 | 78588 | Lift Shaft RC Slab Extention Work | Level 29 | Design 1399-39 | 1 | 2.5 | 1.3 | 5.5 | 1 | unit | 1 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 4805.88 | 212.24 | 3364.12 | 939.92 | 1441.76 | 5745.8 | 5745.8 | 0 | 2439-29-1 (Item-9) | 5745.8 | 0 | 5745.8 | 0 | 3364.12 | 3364.12 | 0 | 939.92 | 939.92 | 0 | 1441.76 | 1441.76 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 121b | 75902 | 78590 | Access Scaffold | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 |  | 1 | m2-LxW | 1.5 | 2023-01-19 | 2023-02-18 | 100% | 100% | 100% | 4.4286 | 36.52 | 2.94 | 38.35 | 19.53 | 16.43 | 74.31 | 74.31 | 0 |  | 74.31 | 0 | 74.31 | 0 | 38.35 | 38.35 | 0 | 19.53 | 19.53 | 0 | 16.43 | 16.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 210 | 75856 | 80893 | Column Finishing Work | Ground Level | Birdcage | 1 | 5 | 3.8 | 12.2 | 1 | m3 | 231.8 | 2023-01-19 | 2023-01-21 | 100% | 100% | 100% | 0.42857 | 7.08 | 0.49 | 1148.8 | 48.68 | 492.34 | 1689.82 | 1689.82 | 0 |  | 1689.82 | 0 | 1689.82 | 0 | 1589.7 | 1589.7 | 0 | 77.18 | 77.18 | 0 | 681.3 | 681.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 210 | 75856 | 80893 | Column Finishing Work | Ground Level | Additional Boarding | 5 | 5 | 3.8 |  | 5 | m2-LxW | 95 | 2023-01-19 | 2023-01-21 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 440.9 | 28.5 | 188.96 | 658.36 | 658.36 | 0 |  | 658.36 | 0 | 658.36 | 0 | 1589.7 | 1589.7 | 0 | 77.18 | 77.18 | 0 | 681.3 | 681.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 122 | 75905 | 80927 | KMEP Work BW-01036 | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-20 | 2023-01-26 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 110.85 | 18.2 | 47.51 | 176.56 | 176.56 | 0 |  | 176.56 | 0 | 176.56 | 0 | 110.85 | 110.85 | 0 | 18.2 | 18.2 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 123 | 75906 | 79835 | KMEP Work BW-01012 | Level 5 | Tower | 1 | 2.5 | 1.3 | 2.5 | 1 | rm | 2.5 | 2023-01-20 | 2023-03-06 | 100% | 100% | 100% | 6.5714 | 63.34 | 7.28 | 110.85 | 119.6 | 47.51 | 277.96 | 207.05 | 70.91 |  | 207.05 | 70.91 | 277.96 | 0 | 158.91 | 158.91 | 0 | 155.92 | 125.42 | 30.5 | 68.11 | 0 | 68.11 | 98.61 | 98.61 | 0
E11/K149/SK/dm/213 | HOTEL | 123a | 75906 | 79835 | KMEP Work BW-01012 | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 0.75 |  | 1 | m2-LxW | 1.88 | 2023-01-20 | 2023-03-06 | 100% | 100% | 100% | 6.5714 | 36.52 | 2.94 | 48.06 | 36.32 | 20.6 | 104.98 | 77.28 | 27.7 |  | 77.28 | 27.7 | 104.98 | 0 | 158.91 | 158.91 | 0 | 155.92 | 125.42 | 30.5 | 68.11 | 0 | 68.11 | 98.61 | 98.61 | 0
E11/K149/SK/dm/213 | HOTEL | 124 | 75907 | 80928 | KMEP Work | Level 5 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-20 | 2023-01-26 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 88.68 | 14.56 | 38 | 141.24 | 141.24 | 0 |  | 141.24 | 0 | 141.24 | 0 | 88.68 | 88.68 | 0 | 14.56 | 14.56 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 125 | 75908 | 78552 | Wall Repair Work | Basement 1 | Tower | 1 | 1.8 | 1 | 0.5 | 1 | rm | 0.5 | 2023-01-20 | 2023-02-06 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 22.17 | 9.36 | 9.5 | 41.03 | 41.03 | 0 |  | 41.03 | 0 | 41.03 | 0 | 22.17 | 22.17 | 0 | 9.36 | 9.36 | 0 | 9.5 | 9.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 126 | 75909 |  | Electrical BOND MEP Work | Level 28 | Tower | 1 | 2.5 | 1.3 | 3 | 1 | rm | 3 | 2023-01-20 |  | 100% | 100% | 0% | 9.2857 | 63.34 | 7.28 | 133.01 | 202.8 | 0 | 335.81 | 248.45 | 87.36 |  | 248.45 | 87.36 | 335.81 | 0 | 133.01 | 133.01 | 0 | 202.8 | 115.44 | 87.36 | 0 | 0 | 0 | 87.36 | 87.36 | 0
E11/K149/SK/dm/213 | HOTEL | 127 | 75910 |  | Edge Protection | Level 29 | Tripple Hnadrail | 1 | 20 |  | 1.5 |  | lm | 20 | 2023-01-20 |  | 100% | 100% | 0% | 9.2857 | 15 | 0.91 | 210 | 169 | 0 | 379 | 306.2 | 72.8 |  | 306.2 | 72.8 | 379 | 0 | 210 | 210 | 0 | 169 | 96.2 | 72.8 | 0 | 0 | 0 | 72.8 | 72.8 | 0
E11/K149/SK/SR/517 | HOTEL | 128&128a | 75911 | 80941 | Balcony Ceiling Work | Level 14 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-21 | 2023-01-31 | 100% | 100% | 100% | 1.5714 | 1772.5845 | 52.192 | 1240.81 | 82.02 | 531.78 | 1854.61 | 1854.61 | 0 | Tas Quote 2439-25-1 (item#5) | 1854.61 | 0 | 1854.61 | 0 | 1240.81 | 1240.81 | 0 | 82.02 | 82.02 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 129 | 75912 | 80936 | BW-0026 | Level 2 | Tower | 1 | 2.5 | 1.3 | 5 | 1 | rm | 5 | 2023-01-23 | 2023-01-30 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 221.69 | 41.6 | 95.01 | 358.3 | 358.3 | 0 |  | 358.3 | 0 | 358.3 | 0 | 286.62 | 286.62 | 0 | 50.75 | 50.75 | 0 | 122.83 | 122.83 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 129 | 75912 | 80936 | KMEP Work | Level 2 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-23 | 2023-01-30 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 15.08 | 2.6 | 6.46 | 24.14 | 24.14 | 0 |  | 24.14 | 0 | 24.14 | 0 | 286.62 | 286.62 | 0 | 50.75 | 50.75 | 0 | 122.83 | 122.83 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 129a | 75912 | 80936 | KMEP Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1.3 |  | 1 | m2-LxW | 1.95 | 2023-01-23 | 2023-01-30 | 100% | 100% | 100% | 1.1429 | 36.52 | 2.94 | 49.85 | 6.55 | 21.36 | 77.76 | 77.76 | 0 |  | 77.76 | 0 | 77.76 | 0 | 286.62 | 286.62 | 0 | 50.75 | 50.75 | 0 | 122.83 | 122.83 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 130 | 75915 | 79834 | Access Scaffold | Level 2 | Tower | 1 | 1.3 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-01-23 | 2023-03-06 | 100% | 100% | 100% | 6.1429 | 63.34 | 7.28 | 66.51 | 67.08 | 28.5 | 162.09 | 119.55 | 42.54 |  | 119.55 | 42.54 | 162.09 | 0 | 66.51 | 66.51 | 0 | 67.08 | 53.04 | 14.04 | 28.5 | 0 | 28.5 | 42.54 | 42.54 | 0
E11/K149/SK/dm/213 | HOTEL | 131 | 75913 | 78554 | Wall Finishing Work | Ground Level | Independent | 1 | 5.9 | 0.9 | 2 | 1 | m2-LxH | 11.8 | 2023-01-23 | 2023-02-08 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 99.2 | 14.04 | 42.52 | 155.76 | 155.76 | 0 |  | 155.76 | 0 | 155.76 | 0 | 99.2 | 99.2 | 0 | 14.04 | 14.04 | 0 | 42.52 | 42.52 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 131a | 75914 | 78554 | Wall Finishing Work | Level 1 | Independent | 1 | 6.8 | 0.9 | 2 | 1 | m2-LxH | 13.6 | 2023-01-23 | 2023-02-08 | 100% | 100% | 100% | 2.4286 | 12.01 | 0.49 | 114.34 | 16.18 | 49 | 179.52 | 179.52 | 0 |  | 179.52 | 0 | 179.52 | 0 | 114.34 | 114.34 | 0 | 16.18 | 16.18 | 0 | 49 | 49 | 0 | 0 | 0 | 0
E11/K149/SK/SR/517 | HOTEL | 132&132a | 75916 | 80942 | Balcony Ceiling Work | Level 19 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-24 | 2023-01-31 | 100% | 100% | 100% | 1.1429 | 1772.5845 | 52.192 | 1240.81 | 59.65 | 531.78 | 1832.24 | 1832.24 | 0 | Tas Quote 2439-25-1 (item#5) | 1832.24 | 0 | 1832.24 | 0 | 1240.81 | 1240.81 | 0 | 59.65 | 59.65 | 0 | 531.78 | 531.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 133 | 75917 | 80918 | Wall Concrete Work | Ground Level | Independent | 1 | 5 | 1.3 | 1.2 | 1 | m2-LxH | 6 | 2023-01-24 | 2023-01-25 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 50.44 | 0.84 | 21.62 | 72.9 | 72.9 | 0 |  | 72.9 | 0 | 72.9 | 0 | 50.44 | 50.44 | 0 | 0.84 | 0.84 | 0 | 21.62 | 21.62 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 134 | 75918 | 80919 | Wall Concrete Work | Ground Level | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2023-01-24 | 2023-01-25 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 66.51 | 3.12 | 28.5 | 98.13 | 98.13 | 0 |  | 98.13 | 0 | 98.13 | 0 | 66.51 | 66.51 | 0 | 3.12 | 3.12 | 0 | 28.5 | 28.5 | 0 | 0 | 0 | 0
E11/K149/SK/SR/585 | AL QUOZ METAL YARD | 1 | 75851 |  | KMEP Pipe Storage | Ground Level | Frame | 1 | 5.2 | 3.9 | 2 |  | unit | 0 | 2023-01-06 |  | 100% | 100% |  | 11.2857 | 1820.72 | 95.83 | 0 | 0 | 0 | 0 | 1972.69 | -1972.69 | Tas Quot 2671-1-1 (Item-1) | 0 | 0 | 0 | -1972.69 | 0 | 1274.5 | -1274.5 | 0 | 698.19 | -698.19 | 0 | 0 | 0 | -1972.69 | -1972.69 | 0
E11/K149/SK/SR/585 | AL QUOZ METAL YARD | 2 | 75852 |  | KMEP Pipe Storage | Ground Level | Frame | 1 | 5.2 | 3.9 | 2 |  | unit | 0 | 2023-01-06 |  | 100% | 100% |  | 11.2857 | 1820.72 | 95.83 | 0 | 0 | 0 | 0 | 1972.69 | -1972.69 | Tas Quot 2671-1-1 (Item-1) | 0 | 0 | 0 | -1972.69 | 0 | 1274.5 | -1274.5 | 0 | 698.19 | -698.19 | 0 | 0 | 0 | -1972.69 | -1972.69 | 0
E11/K149/SK/dm/213 | RESIDENCE | 215a | 75878 | 78629 | Wall Board Fixing Work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-01-26 | 2023-02-06 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 10.86 | 2.81 | 4.65 | 18.32 | 18.32 | 0 |  | 18.32 | 0 | 18.32 | 0 | 10.86 | 10.86 | 0 | 2.81 | 2.81 | 0 | 4.65 | 4.65 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 214a | 75879 | 78628 | Wall Board Fixing Work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-01-26 | 2023-02-06 | 100% | 100% | 100% | 1.7143 | 6.63 | 0.7 | 15.08 | 3.9 | 6.46 | 25.44 | 25.44 | 0 |  | 25.44 | 0 | 25.44 | 0 | 15.08 | 15.08 | 0 | 3.9 | 3.9 | 0 | 6.46 | 6.46 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 219a | 75880 | 78636 | Staircase - 3 Wall Finishing Work | Level 3 | Independent | 1 | 6.8 | 0.9 | 2 | 1 | m2-LxH | 13.6 | 2023-01-26 | 2023-02-04 | 100% | 100% | 100% | 1.4286 | 12.01 | 0.49 | 114.34 | 9.52 | 49 | 172.86 | 172.86 | 0 |  | 172.86 | 0 | 172.86 | 0 | 114.34 | 114.34 | 0 | 9.52 | 9.52 | 0 | 49 | 49 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 222 | 75881 |  | Concrete Cutting Work | Level 28 | Tower | 1 | 1.3 | 1 | 2.5 | 1 | rm | 2.5 | 2023-01-26 |  | 100% | 100% |  | 8.4286 | 63.34 | 7.28 | 110.85 | 153.4 | 0 | 264.25 | 191.45 | 72.8 |  | 191.45 | 72.8 | 264.25 | 0 | 145.24 | 145.24 | 0 | 166.23 | 87.58 | 78.65 | 14.74 | 0 | 14.74 | 93.39 | 93.39 | 0
E11/K149/SK/dm/213 | RESIDENCE | 222a | 75881 | 351 | Concrete Cutting Work | Level 28 | Cantilever (0 < 0.5m width) | 1 | 3 | 0.5 |  | 1 | m2-LxW | 1.5 | 2023-01-26 | 2023-03-23 | 100% | 100% | 100% | 8.1429 | 32.75 | 1.05 | 34.39 | 12.83 | 14.74 | 61.96 | 41.37 | 20.59 |  | 41.37 | 20.59 | 61.96 | 0 | 145.24 | 145.24 | 0 | 166.23 | 87.58 | 78.65 | 14.74 | 0 | 14.74 | 93.39 | 93.39 | 0
E11/K149/SK/dm/213 | RESIDENCE | 223 | 75882 | 82152 | Repairing Led Light | Ground Level | Independent 1.8m wide | 1 | 3.8 | 1.8 | 3 | 1 | m2-LxH | 11.4 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 133.74 | 18.81 | 57.32 | 209.87 | 209.87 | 0 |  | 209.87 | 0 | 209.87 | 0 | 162.4 | 162.4 | 0 | 21.62 | 21.62 | 0 | 69.6 | 69.6 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 223a | 75882 | 82152 | Repairing Led Light | Ground Level | Cantilever (0 < 0.5m width) | 1 | 5 | 0.25 |  | 1 | m2-LxW | 1.25 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 32.75 | 1.05 | 28.66 | 2.81 | 12.28 | 43.75 | 43.75 | 0 |  | 43.75 | 0 | 43.75 | 0 | 162.4 | 162.4 | 0 | 21.62 | 21.62 | 0 | 69.6 | 69.6 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 223b | 75883 | 82153 | Repairing Led Light | Ground Level | Independent | 1 | 5 | 1.3 | 3 | 1 | m2-LxH | 15 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 126.11 | 15.75 | 54.05 | 195.91 | 195.91 | 0 |  | 195.91 | 0 | 195.91 | 0 | 177.24 | 177.24 | 0 | 28.35 | 28.35 | 0 | 75.96 | 75.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 223c | 75883 | 82153 | Repairing Led Light | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 2 | 1 |  | 1 | m2-LxW | 2 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 51.13 | 12.6 | 21.91 | 85.64 | 85.64 | 0 |  | 85.64 | 0 | 85.64 | 0 | 177.24 | 177.24 | 0 | 28.35 | 28.35 | 0 | 75.96 | 75.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 224 | 75884 | 82154 | Repairing Led Light | Ground Level | Independent 1.8m wide | 1 | 10 | 1.8 | 3 | 1 | m2-LxH | 30 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 16.76 | 0.77 | 351.96 | 49.5 | 150.84 | 552.3 | 552.3 | 0 |  | 552.3 | 0 | 552.3 | 0 | 505.34 | 505.34 | 0 | 87.3 | 87.3 | 0 | 216.58 | 216.58 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 224a | 75884 | 82154 | Repairing Led Light | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 |  | 1 | m2-LxW | 6 | 2023-01-26 | 2023-02-09 | 100% | 100% | 100% | 2.1429 | 36.52 | 2.94 | 153.38 | 37.8 | 65.74 | 256.92 | 256.92 | 0 |  | 256.92 | 0 | 256.92 | 0 | 505.34 | 505.34 | 0 | 87.3 | 87.3 | 0 | 216.58 | 216.58 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 225 | 75885 | 78640 | BTU Meter Wire Pulling Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-01-27 | 2023-02-07 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 155.18 | 43.68 | 66.51 | 265.37 | 265.37 | 0 |  | 265.37 | 0 | 265.37 | 0 | 155.18 | 155.18 | 0 | 43.68 | 43.68 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 226 | 75886 | 78641 | BTU Meter Wire Pulling Work | Ground Level | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2023-01-27 | 2023-02-07 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 155.18 | 43.68 | 66.51 | 265.37 | 265.37 | 0 |  | 265.37 | 0 | 265.37 | 0 | 155.18 | 155.18 | 0 | 43.68 | 43.68 | 0 | 66.51 | 66.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 227 | 75887 | 79872 | Neae Lift Loby Shaft Wall Partition | Ground Level | Tower | 1 | 1.3 | 0.6 | 4 | 2 | rm | 4 | 2023-01-27 | 2023-03-09 | 100% | 100% | 100% | 6 | 63.34 | 7.28 | 177.35 | 174.72 | 76.01 | 428.08 | 302.15 | 125.93 |  | 302.15 | 125.93 | 428.08 | 0 | 177.35 | 177.35 | 0 | 174.72 | 124.8 | 49.92 | 76.01 | 0 | 76.01 | 125.93 | 125.93 | 0
E11/K149/SK/dm/213 | RESIDENCE | 228 | 75888 | 82179 | Balcony For Mast Climber Access | Level 23 | Independent | 1 | 3.2 | 1.3 | 2 | 1 | m2-LxH | 6.4 | 2023-01-28 | 2023-02-24 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 53.8 | 12.54 | 23.06 | 89.4 | 89.4 | 0 |  | 89.4 | 0 | 89.4 | 0 | 53.8 | 53.8 | 0 | 12.54 | 12.54 | 0 | 23.06 | 23.06 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a3 | 75889 | 79886 | Hotel Side Glass Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 17 | 0.75 |  | 1 | m2-LxW | 12.75 | 2023-01-28 | 2023-03-13 | 100% | 100% | 100% | 6.4286 | 36.52 | 2.94 | 325.94 | 240.98 | 139.69 | 706.61 | 481.24 | 225.37 |  | 481.24 | 225.37 | 706.61 | 0 | 325.94 | 325.94 | 0 | 240.98 | 155.3 | 85.68 | 139.69 | 0 | 139.69 | 225.37 | 225.37 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1x | 75890 | 79899 | Canal Side Glass Fixing Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 15 | 0.5 |  | 1 | m2-LxW | 7.5 | 2023-01-28 | 2023-03-15 | 100% | 100% | 100% | 6.7143 | 32.75 | 1.05 | 171.94 | 52.88 | 73.69 | 298.51 | 204.57 | 93.94 |  | 204.57 | 93.94 | 298.51 | 0 | 171.94 | 171.94 | 0 | 52.88 | 32.63 | 20.25 | 73.69 | 0 | 73.69 | 93.94 | 93.94 | 0
E11/K149/SK/dm/213 | RESIDENCE | 229 | 75891 | 82167 | EIFS Work | Level 23 | Independent | 1 | 6.3 | 1.3 | 3.5 | 1 | m2-LxH | 22.05 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 12.01 | 0.49 | 185.37 | 33.96 | 79.45 | 298.78 | 298.78 | 0 |  | 298.78 | 0 | 298.78 | 0 | 223.38 | 223.38 | 0 | 51.98 | 51.98 | 0 | 95.74 | 95.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 229 | 75891 | 82167 | EIFS Work | Level 23 | Additional Boarding | 1 | 6.3 | 1.3 |  | 1 | m2-LxW | 8.19 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 6.63 | 0.7 | 38.01 | 18.02 | 16.29 | 72.32 | 72.32 | 0 |  | 72.32 | 0 | 72.32 | 0 | 223.38 | 223.38 | 0 | 51.98 | 51.98 | 0 | 95.74 | 95.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 229a | 75892 | 82168 | EIFS Work | Level 23 | Independent | 1 | 7.5 | 1.3 | 2 | 1 | m2-LxH | 15 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 12.01 | 0.49 | 126.11 | 23.1 | 54.05 | 203.26 | 203.26 | 0 |  | 203.26 | 0 | 203.26 | 0 | 164.46 | 164.46 | 0 | 36.96 | 36.96 | 0 | 70.48 | 70.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 229b | 75892 | 82168 | EIFS Work | Level 23 | Cantilever (0.5 > 1.2m width) | 1 | 1.5 | 1 |  | 1 | m2-LxW | 1.5 | 2023-01-28 | 2023-02-18 | 100% | 100% | 100% | 3.1429 | 36.52 | 2.94 | 38.35 | 13.86 | 16.43 | 68.64 | 68.64 | 0 |  | 68.64 | 0 | 68.64 | 0 | 164.46 | 164.46 | 0 | 36.96 | 36.96 | 0 | 70.48 | 70.48 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 230 | 75893 | 79871 | Shaft For Wall Partition | Level 2 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 | 2023-03-09 | 100% | 100% | 100% | 5.5714 | 63.34 | 7.28 | 88.68 | 81.12 | 38 | 207.8 | 144.84 | 62.96 |  | 144.84 | 62.96 | 207.8 | 0 | 88.68 | 88.68 | 0 | 81.12 | 56.16 | 24.96 | 38 | 0 | 38 | 62.96 | 62.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 231 | 75894 | 82155 | Shaft For Wall Partition | Level 3 | Tower | 1 | 1.3 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 | 2023-02-09 | 100% | 100% | 100% | 1.5714 | 63.34 | 7.28 | 88.68 | 22.88 | 38 | 149.56 | 149.56 | 0 |  | 149.56 | 0 | 149.56 | 0 | 88.68 | 88.68 | 0 | 22.88 | 22.88 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 232 | 75895 | 79873 | Shaft For Wall Partition | Level 4 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 | 2023-03-09 | 100% | 100% | 100% | 5.5714 | 63.34 | 7.28 | 88.68 | 81.12 | 38 | 207.8 | 144.84 | 62.96 |  | 144.84 | 62.96 | 207.8 | 0 | 88.68 | 88.68 | 0 | 81.12 | 56.16 | 24.96 | 38 | 0 | 38 | 62.96 | 62.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 233 | 75896 | 82191 | Shaft For Wall Partition | Level 5 | Tower | 1 | 1 | 0.6 | 2 | 1 | rm | 2 | 2023-01-30 | 2023-03-02 | 100% | 100% | 100% | 4.5714 | 63.34 | 7.28 | 88.68 | 66.56 | 38 | 193.24 | 144.84 | 48.4 |  | 144.84 | 48.4 | 193.24 | 0 | 88.68 | 88.68 | 0 | 66.56 | 56.16 | 10.4 | 38 | 0 | 38 | 48.4 | 48.4 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1y | 75897 | 82144-82147 | GRC Panel Work | Level 31 | Single Handrail | 1 | 136 |  | 1 |  | lm | 136 | 2023-01-28 | 2023-03-06 | 100% | 100% | 100% | 5.4286 | 7 | 0.42 | 666.4 | 310.08 | 285.6 | 1262.08 | 903.04 | 359.04 |  | 903.04 | 359.04 | 1262.08 | 0 | 666.4 | 666.4 | 0 | 310.08 | 236.64 | 73.44 | 285.6 | 0 | 285.6 | 359.04 | 359.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 202e | 76901 |  | GRC Panel Work | Level 10 | Independent | 1 | 9 | 1.3 | 1 | 1 | m2-LxH | 9 | 2023-02-01 |  | 100% | 100% | 0% | 7.5714 | 12.01 | 0.49 | 75.66 | 33.39 | 0 | 109.05 | 91.41 | 17.64 |  | 91.41 | 17.64 | 109.05 | 0 | 75.66 | 75.66 | 0 | 33.39 | 15.75 | 17.64 | 0 | 0 | 0 | 17.64 | 17.64 | 0
E11/K149/SK/dm/213 | RESIDENCE | 178b | 76902 | 82156 | Shaft 9 For Kmep Work | Level 4 to 5 | Tower | 1 | 2 | 2 | 7.5 | 1 | rm | 7.5 | 2023-02-02 | 2023-02-09 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 332.54 | 62.4 | 142.52 | 537.46 | 537.46 | 0 |  | 537.46 | 0 | 537.46 | 0 | 369.67 | 369.67 | 0 | 68.8 | 68.8 | 0 | 158.43 | 158.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 178b | 76902 | 82156 | Shaft 9 For Kmep Work | Level 4 to 5 | Additional Boarding | 2 | 2 | 2 |  | 2 | m2-LxW | 8 | 2023-02-02 | 2023-02-09 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 37.13 | 6.4 | 15.91 | 59.44 | 59.44 | 0 |  | 59.44 | 0 | 59.44 | 0 | 369.67 | 369.67 | 0 | 68.8 | 68.8 | 0 | 158.43 | 158.43 | 0 | 0 | 0 | 0
E11/K149/MS/DM/647 | RESIDENCE | 234 | 76903 | 79879 | Glass Panel Fixing Work | Level 30 to 32 | Design 1399-37a | 1 |  |  |  |  | unit | 1 | 2023-02-02 | 2023-03-14 | 100% | 100% | 100% | 5.8571 | 7648.53 | 125.44 | 5353.97 | 734.72 | 2294.56 | 8383.25 | 5784.05 | 2599.2 | Tas Quote 2439-28-1 | 5784.05 | 2599.2 | 8383.25 | 0 | 5353.97 | 5353.97 | 0 | 734.72 | 430.08 | 304.64 | 2294.56 | 0 | 2294.56 | 2599.2 | 2599.2 | 0
E11/K149/SK/dm/213 | RESIDENCE | 235 | 76904 |  | KMEP Work | Level 2 | Independent | 1 | 3 | 0.75 | 2.3 | 1 | m2-LxH | 6.9 | 2023-02-02 |  | 100% | 100% | 0% | 7.4286 | 12.01 | 0.49 | 58.01 | 25.12 | 0 | 83.13 | 69.6 | 13.53 |  | 69.6 | 13.53 | 83.13 | 0 | 83.57 | 83.57 | 0 | 46.96 | 21.67 | 25.29 | 0 | 0 | 0 | 25.29 | 25.29 | 0
E11/K149/SK/dm/213 | RESIDENCE | 235a | 76904 |  | KMEP Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-02-02 |  | 100% | 100% | 0% | 7.4286 | 36.52 | 2.94 | 25.56 | 21.84 | 0 | 47.4 | 35.64 | 11.76 |  | 35.64 | 11.76 | 47.4 | 0 | 83.57 | 83.57 | 0 | 46.96 | 21.67 | 25.29 | 0 | 0 | 0 | 25.29 | 25.29 | 0
E11/K149/SK/dm/213 | RESIDENCE | 236 | 76905 | 82171 | Entrance Area Access | Ground Level | Independent | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxH | 5.4 | 2023-02-06 | 2023-02-21 | 100% | 100% | 100% | 2.2857 | 12.01 | 0.49 | 45.4 | 6.05 | 19.46 | 70.91 | 70.91 | 0 |  | 70.91 | 0 | 70.91 | 0 | 45.4 | 45.4 | 0 | 6.05 | 6.05 | 0 | 19.46 | 19.46 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 237 | 76906 | 78642 | Wall Concrete Work | Ground Level | Independent | 1 | 15.5 | 1 | 1.5 | 1 | m2-LxH | 23.25 | 2023-02-06 | 2023-02-07 | 100% | 100% | 100% | 0.28571 | 12.01 | 0.49 | 195.46 | 3.26 | 83.77 | 282.49 | 282.49 | 0 |  | 282.49 | 0 | 282.49 | 0 | 195.46 | 195.46 | 0 | 3.26 | 3.26 | 0 | 83.77 | 83.77 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 224b | 76908 | 82157 | Lift Lobby Led Light Repairing | Ground Level | Tower | 1 | 2.5 | 1.8 | 2.5 | 1 | rm | 2.5 | 2023-02-07 | 2023-02-09 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 | 166.16 | 0 |  | 166.16 | 0 | 166.16 | 0 | 110.85 | 110.85 | 0 | 7.8 | 7.8 | 0 | 47.51 | 47.51 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 238 | 76910 | 82158 | Wall Board Fixing Work | Ground Level | Independent | 1 | 5 | 1.3 | 3.5 | 1 | m2-LxH | 17.5 | 2023-02-07 | 2023-02-13 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 147.12 | 8.58 | 63.05 | 218.75 | 218.75 | 0 |  | 218.75 | 0 | 218.75 | 0 | 177.29 | 177.29 | 0 | 13.13 | 13.13 | 0 | 75.98 | 75.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 238 | 76910 | 82158 | Wall Board Fixing Work | Ground Level | Additional Boarding | 1 | 5 | 1.3 | 1 | 1 | m2-LxW | 6.5 | 2023-02-07 | 2023-02-13 | 100% | 100% | 100% | 1 | 6.63 | 0.7 | 30.17 | 4.55 | 12.93 | 47.65 | 47.65 | 0 |  | 47.65 | 0 | 47.65 | 0 | 177.29 | 177.29 | 0 | 13.13 | 13.13 | 0 | 75.98 | 75.98 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 3g | 76914 | 82128 | Canopy Instalation Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2.75 | 1 |  | 1 | m2-LxW | 2.75 | 2023-02-02 | 2023-03-18 | 100% | 100% | 100% | 6.4286 | 36.52 | 2.94 | 70.3 | 51.98 | 30.13 | 152.41 | 98.02 | 54.39 |  | 98.02 | 54.39 | 152.41 | 0 | 70.3 | 70.3 | 0 | 51.98 | 27.72 | 24.26 | 30.13 | 0 | 30.13 | 54.39 | 54.39 | 0
E11/K149/SK/dm/213 | RESIDENCE | 188b | 76911 | 82190 | KMEP | Level 2 | Birdcage | 1 | 4.5 | 3.6 | 2.5 | 1 | m3 | 40.5 | 2023-02-07 | 2023-03-02 | 100% | 100% | 100% | 3.4286 | 7.08 | 0.49 | 200.72 | 68.04 | 86.02 | 354.78 | 254.59 | 100.19 |  | 254.59 | 100.19 | 354.78 | 0 | 200.72 | 200.72 | 0 | 68.04 | 53.87 | 14.17 | 86.02 | 0 | 86.02 | 100.19 | 100.19 | 0
E11/K149/SK/dm/213 | RESIDENCE | 188c | 76912 | 82189 | KMEP | Level 2 | Birdcage | 1 | 5 | 3 | 2.5 | 1 | m3 | 37.5 | 2023-02-07 | 2023-03-02 | 100% | 100% | 100% | 3.4286 | 7.08 | 0.49 | 185.85 | 63 | 79.65 | 328.5 | 235.73 | 92.77 |  | 235.73 | 92.77 | 328.5 | 0 | 185.85 | 185.85 | 0 | 63 | 49.88 | 13.12 | 79.65 | 0 | 79.65 | 92.77 | 92.77 | 0
E11/K149/SK/dm/213 | RESIDENCE | 188d | 76913 | 82188 | KMEP | Level 2 | Birdcage | 1 | 6 | 3.1 | 2.5 | 1 | m3 | 46.5 | 2023-02-07 | 2023-03-02 | 100% | 100% | 100% | 3.4286 | 7.08 | 0.49 | 230.45 | 78.12 | 98.77 | 407.34 | 292.3 | 115.04 |  | 292.3 | 115.04 | 407.34 | 0 | 230.45 | 230.45 | 0 | 78.12 | 61.85 | 16.27 | 98.77 | 0 | 98.77 | 115.04 | 115.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 195h | 76915 | 82187 | KMEP | Level 2 | Independent 1.8m wide | 1 | 3 | 2 | 2.5 | 1 | m2-LxH | 7.5 | 2023-02-08 | 2023-03-02 | 100% | 100% | 100% | 3.2857 | 16.76 | 0.77 | 87.99 | 18.98 | 37.71 | 144.68 | 102.84 | 41.84 |  | 102.84 | 41.84 | 144.68 | 0 | 87.99 | 87.99 | 0 | 18.98 | 14.85 | 4.13 | 37.71 | 0 | 37.71 | 41.84 | 41.84 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a4 | 76916 |  | Glass Work |  | Additional Boarding | 6 | 10.8 | 1.8 |  | 1 | m2-LxW | 116.64 | 2023-02-08 |  | 100% | 100% | 0% | 6.5714 | 6.63 | 0.7 | 541.33 | 536.54 | 0 | 1077.87 | 751.28 | 326.59 |  | 751.28 | 326.59 | 1077.87 | 0 | 541.33 | 541.33 | 0 | 536.54 | 209.95 | 326.59 | 0 | 0 | 0 | 326.59 | 326.59 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a5 | 76917 |  | Glass Work | Level 28 to 29 | Cantilever (0 < 0.5m width) | 1 | 16.2 | 0.5 |  | 1 | m2-LxW | 8.1 | 2023-02-08 |  | 100% | 100% | 0% | 6.5714 | 32.75 | 1.05 | 185.69 | 55.89 | 0 | 241.58 | 207.56 | 34.02 |  | 207.56 | 34.02 | 241.58 | 0 | 185.69 | 185.69 | 0 | 55.89 | 21.87 | 34.02 | 0 | 0 | 0 | 34.02 | 34.02 | 0
E11/K149/SK/dm/213 | RESIDENCE | 239 | 76918 |  | KMEP Work | Ground Level | Tower | 1 | 1.3 | 0.9 | 3 | 1 | rm | 3 | 2023-02-09 |  | 100% | 100% | 0% | 6.4286 | 63.34 | 7.28 | 133.01 | 140.4 | 0 | 273.41 | 186.05 | 87.36 |  | 186.05 | 87.36 | 273.41 | 0 | 133.01 | 133.01 | 0 | 140.4 | 53.04 | 87.36 | 0 | 0 | 0 | 87.36 | 87.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 238a | 76919 | 82159 | Entrance Area Partition Board Fixing | Ground Level | Tower | 1 | 1.8 | 1.3 | 3 | 2 | rm | 3 | 2023-02-09 | 2023-02-13 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 133.01 | 15.6 | 57.01 | 205.62 | 205.62 | 0 |  | 205.62 | 0 | 205.62 | 0 | 133.01 | 133.01 | 0 | 15.6 | 15.6 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 240 | 76920 | 82173 | Wall Finishing Work | Level 4 to 5 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 84.07 | 9.1 | 36.03 | 129.2 | 129.2 | 0 |  | 129.2 | 0 | 129.2 | 0 | 184.95 | 184.95 | 0 | 20.02 | 20.02 | 0 | 79.27 | 79.27 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 240a | 76920 | 82174 | Wall Finishing Work | Level 4 to 5 | Independent | 1 | 6 | 0.9 | 2 | 1 | m2-LxH | 12 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 100.88 | 10.92 | 43.24 | 155.04 | 155.04 | 0 |  | 155.04 | 0 | 155.04 | 0 | 184.95 | 184.95 | 0 | 20.02 | 20.02 | 0 | 79.27 | 79.27 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 240b | 76921 | 82175 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6.8 | 0.9 | 1.5 | 1 | m2-LxH | 10.2 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 85.75 | 9.28 | 36.75 | 131.78 | 131.78 | 0 |  | 131.78 | 0 | 131.78 | 0 | 161.41 | 161.41 | 0 | 17.47 | 17.47 | 0 | 69.18 | 69.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 240c | 76921 | 82176 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6 | 0.9 | 1.5 | 1 | m2-LxH | 9 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 75.66 | 8.19 | 32.43 | 116.28 | 116.28 | 0 |  | 116.28 | 0 | 116.28 | 0 | 161.41 | 161.41 | 0 | 17.47 | 17.47 | 0 | 69.18 | 69.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 240d | 76922 | 82177 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6.8 | 0.9 | 1.5 | 1 | m2-LxH | 10.2 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 85.75 | 9.28 | 36.75 | 131.78 | 131.78 | 0 |  | 131.78 | 0 | 131.78 | 0 | 161.41 | 161.41 | 0 | 17.47 | 17.47 | 0 | 69.18 | 69.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 240e | 76922 | 82178 | Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6 | 0.9 | 1.5 | 1 | m2-LxH | 9 | 2023-02-10 | 2023-02-22 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 75.66 | 8.19 | 32.43 | 116.28 | 116.28 | 0 |  | 116.28 | 0 | 116.28 | 0 | 161.41 | 161.41 | 0 | 17.47 | 17.47 | 0 | 69.18 | 69.18 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 229c | 76923 | 82169 | Canal Side Wall Painting Work | Level 23 | Tower | 1 | 1.3 | 1.3 | 3.5 | 2 | rm | 3.5 | 2023-02-10 | 2023-02-18 | 100% | 100% | 100% | 1.2857 | 12.01 | 0.49 | 29.42 | 2.21 | 12.61 | 44.24 | 44.24 | 0 |  | 44.24 | 0 | 44.24 | 0 | 29.42 | 29.42 | 0 | 2.21 | 2.21 | 0 | 12.61 | 12.61 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 241 | 76924 | 79868 | Ceiling Work | Ground Level | Independent | 1 | 32.5 | 1.3 | 4.2 | 1 | m2-LxH | 136.5 | 2023-02-11 | 2023-03-07 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 1147.56 | 238.88 | 491.81 | 1878.25 | 1290.89 | 587.36 |  | 1290.89 | 587.36 | 1878.25 | 0 | 1245.1 | 1245.1 | 0 | 296.08 | 177.65 | 118.43 | 533.61 | 0 | 533.61 | 652.04 | 652.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 241a | 76924 | 79868 | Ceiling Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 1 | rm | 2.2 | 2023-02-11 | 2023-03-07 | 100% | 100% | 100% | 3.5714 | 63.34 | 7.28 | 97.54 | 57.2 | 41.8 | 196.54 | 131.86 | 64.68 |  | 131.86 | 64.68 | 196.54 | 0 | 1245.1 | 1245.1 | 0 | 296.08 | 177.65 | 118.43 | 533.61 | 0 | 533.61 | 652.04 | 652.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 180b | 76925 | 82134 | KMEP Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 1.5 |  | 1 | m2-LxW | 3.75 | 2023-02-11 | 2023-02-26 | 100% | 100% | 100% | 2.2857 | 36.52 | 2.94 | 95.87 | 25.2 | 41.09 | 162.16 | 119.5 | 42.66 |  | 119.5 | 42.66 | 162.16 | 0 | 95.87 | 95.87 | 0 | 25.2 | 23.63 | 1.57 | 41.09 | 0 | 41.09 | 42.66 | 42.66 | 0
E11/K149/SK/dm/213 | RESIDENCE | 242 | 76931 | 82160 | Lift Lobby For Block Work | Ground Level | Independent | 1 | 3.1 | 1.8 | 3 | 1 | m2-LxH | 9.3 | 2023-02-13 | 2023-02-15 | 100% | 100% | 100% | 0.42857 | 16.76 | 0.77 | 109.11 | 3.07 | 46.76 | 158.94 | 158.94 | 0 |  | 158.94 | 0 | 158.94 | 0 | 126 | 126 | 0 | 4.16 | 4.16 | 0 | 54 | 54 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 242a | 76931 | 82160 | Lift Lobby For Block Work | Ground Level | Additional Boarding | 1 | 2.8 | 1.3 |  | 1 | m2-LxW | 3.64 | 2023-02-13 | 2023-02-15 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 16.89 | 1.09 | 7.24 | 25.22 | 25.22 | 0 |  | 25.22 | 0 | 25.22 | 0 | 126 | 126 | 0 | 4.16 | 4.16 | 0 | 54 | 54 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 243 | 76927 | 82164 | Staircase 3 Wall Painting Work | Level 27 | Independent | 1 | 3.3 | 1 | 2 | 1 | m2-LxH | 6.6 | 2023-02-13 | 2023-02-16 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 55.49 | 1.85 | 23.78 | 81.12 | 81.12 | 0 |  | 81.12 | 0 | 81.12 | 0 | 55.49 | 55.49 | 0 | 1.85 | 1.85 | 0 | 23.78 | 23.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 244 | 76928 | 82165 | Staircase 3 Wall Painting Work | Level 26 | Independent | 1 | 3.5 | 1 | 2 | 2 | m2-LxH | 7 | 2023-02-13 | 2023-02-16 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 58.85 | 1.96 | 25.22 | 86.03 | 86.03 | 0 |  | 86.03 | 0 | 86.03 | 0 | 58.85 | 58.85 | 0 | 1.96 | 1.96 | 0 | 25.22 | 25.22 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 245 | 76929 | 82166 | Staircase 3 Wall Painting Work | Level 28 | Independent | 1 | 3.3 | 1 | 2 | 1 | m2-LxH | 6.6 | 2023-02-14 | 2023-02-16 | 100% | 100% | 100% | 0.42857 | 12.01 | 0.49 | 55.49 | 1.39 | 23.78 | 80.66 | 80.66 | 0 |  | 80.66 | 0 | 80.66 | 0 | 55.49 | 55.49 | 0 | 1.39 | 1.39 | 0 | 23.78 | 23.78 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 246 | 76930 | 82180 | Planter Area Shaft For MEP Work | Ground Level | Tower | 1 | 1.3 | 0.6 | 4 | 2 | rm | 4 | 2023-02-14 | 2023-02-28 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 177.35 | 62.4 | 76.01 | 315.76 | 227.27 | 88.49 |  | 227.27 | 88.49 | 315.76 | 0 | 177.35 | 177.35 | 0 | 62.4 | 49.92 | 12.48 | 76.01 | 0 | 76.01 | 88.49 | 88.49 | 0
E11/K149/SK/dm/213 | RESIDENCE | 247 | 76932 |  | Edge Protection | Level 7 to 31 | Double Handrail | 1 | 24 |  | 1 |  | lm | 24 | 2023-02-14 |  | 100% | 100% | 0% | 5.7143 | 15 | 0.91 | 252 | 124.8 | 0 | 376.8 | 289.44 | 87.36 |  | 289.44 | 87.36 | 376.8 | 0 | 252 | 252 | 0 | 124.8 | 37.44 | 87.36 | 0 | 0 | 0 | 87.36 | 87.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 221b | 76933 |  | EIFS Work | Level 31 | Additional Boarding | 2 | 1.3 | 1.2 | 2 | 1 | m2-LxW | 3.12 | 2023-02-14 |  | 100% | 100% | 0% | 5.7143 | 6.63 | 0.7 | 14.48 | 12.48 | 0 | 26.96 | 18.22 | 8.74 |  | 18.22 | 8.74 | 26.96 | 0 | 14.48 | 14.48 | 0 | 12.48 | 3.74 | 8.74 | 0 | 0 | 0 | 8.74 | 8.74 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145a | 76934 |  | EIFS Work | Level 31 | Additional Boarding | 1 | 2.5 | 1.5 |  | 1 | m2-LxW | 3.75 | 2023-02-14 |  | 100% | 100% | 0% | 5.7143 | 6.63 | 0.7 | 17.4 | 15 | 0 | 32.4 | 21.9 | 10.5 |  | 21.9 | 10.5 | 32.4 | 0 | 24.36 | 24.36 | 0 | 21 | 6.3 | 14.7 | 0 | 0 | 0 | 14.7 | 14.7 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145b | 76934 |  | EIFS Work | Level 31 | Additional Boarding | 1 | 1.5 | 1 |  | 1 | m2-LxW | 1.5 | 2023-02-14 |  | 100% | 100% | 0% | 5.7143 | 6.63 | 0.7 | 6.96 | 6 | 0 | 12.96 | 8.76 | 4.2 |  | 8.76 | 4.2 | 12.96 | 0 | 24.36 | 24.36 | 0 | 21 | 6.3 | 14.7 | 0 | 0 | 0 | 14.7 | 14.7 | 0
E11/K149/SK/dm/213 | RESIDENCE | 248 | 76935 | 82131 | Telicom Room KMEP Work | Level 2 | Tower | 1 | 1.8 | 1.8 | 2.2 | 1 | rm | 2.2 | 2023-02-14 | 2023-03-23 | 100% | 100% | 100% | 5.4286 | 63.34 | 7.28 | 97.54 | 86.94 | 41.8 | 226.28 | 125 | 101.28 |  | 125 | 101.28 | 226.28 | 0 | 118.17 | 118.17 | 0 | 92.07 | 29.08 | 62.99 | 50.64 | 0 | 50.64 | 113.63 | 113.63 | 0
E11/K149/SK/dm/213 | RESIDENCE | 248a | 76935 | 82131 | Telicom Room KMEP Work | Level 2 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 |  | 1 | m2-LxW | 0.9 | 2023-02-14 | 2023-03-23 | 100% | 100% | 100% | 5.4286 | 32.75 | 1.05 | 20.63 | 5.13 | 8.84 | 34.6 | 22.25 | 12.35 |  | 22.25 | 12.35 | 34.6 | 0 | 118.17 | 118.17 | 0 | 92.07 | 29.08 | 62.99 | 50.64 | 0 | 50.64 | 113.63 | 113.63 | 0
E11/K149/SK/dm/213 | RESIDENCE | 249 | 76936 |  | Telicom Room KMEP Work | Level 5 | Tower | 1 | 1.8 | 1.8 | 4.5 | 2 | rm | 4.5 | 2023-02-15 |  | 100% | 100% | 0% | 5.5714 | 63.34 | 7.28 | 199.52 | 182.52 | 0 | 382.04 | 251 | 131.04 |  | 251 | 131.04 | 382.04 | 0 | 240.79 | 240.79 | 0 | 193.05 | 54.45 | 138.6 | 0 | 0 | 0 | 138.6 | 138.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 249a | 76936 |  | Telicom Room KMEP Work | Level 5 | Cantilever (0 < 0.5m width) | 2 | 1.8 | 0.5 |  | 2 | m2-LxW | 1.8 | 2023-02-15 |  | 100% | 100% | 0% | 5.5714 | 32.75 | 1.05 | 41.27 | 10.53 | 0 | 51.8 | 44.24 | 7.56 |  | 44.24 | 7.56 | 51.8 | 0 | 240.79 | 240.79 | 0 | 193.05 | 54.45 | 138.6 | 0 | 0 | 0 | 138.6 | 138.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 250 | 76937 | 82163 | Telicom Room KMEP Work | Level 2 | Tower | 1 | 1 | 1 | 2 | 1 | rm | 2 | 2023-02-15 | 2023-02-17 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 88.68 | 6.24 | 38 | 132.92 | 132.92 | 0 |  | 132.92 | 0 | 132.92 | 0 | 88.68 | 88.68 | 0 | 6.24 | 6.24 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 251 | 76938 | 82170 | Block Work | Ground Level | Tower | 1 | 1.3 | 1.3 | 4 | 2 | rm | 4 | 2023-02-16 | 2023-02-20 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 177.35 | 20.8 | 76.01 | 274.16 | 274.16 | 0 |  | 274.16 | 0 | 274.16 | 0 | 177.35 | 177.35 | 0 | 20.8 | 20.8 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a6 | 76939 |  | Glass Work | Level 27 | Cantilever (0 < 0.5m width) | 2 | 9.5 | 0.5 |  | 2 | m2-LxW | 9.5 | 2023-02-16 |  | 100% | 100% | 0% | 5.4286 | 32.75 | 1.05 | 217.79 | 54.15 | 0 | 271.94 | 232.04 | 39.9 |  | 232.04 | 39.9 | 271.94 | 0 | 217.79 | 217.79 | 0 | 54.15 | 14.25 | 39.9 | 0 | 0 | 0 | 39.9 | 39.9 | 0
E11/K149/SK/dm/213 | RESIDENCE | 252 | 76940 | 79858 | Wall Finishing Work | Basement 1 | Independent | 1 | 6.3 | 0.9 | 4 | 1 | m2-LxH | 25.2 | 2023-02-17 | 2023-03-03 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 211.86 | 26.46 | 90.8 | 329.12 | 227.74 | 101.38 |  | 227.74 | 101.38 | 329.12 | 0 | 248.61 | 248.61 | 0 | 38.35 | 23.01 | 15.34 | 106.56 | 0 | 106.56 | 121.9 | 121.9 | 0
E11/K149/SK/dm/213 | RESIDENCE | 252 | 76940 | 79858 | Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 6.3 | 0.9 |  | 1 | m2-LxW | 5.67 | 2023-02-17 | 2023-03-03 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 26.31 | 8.51 | 11.28 | 46.1 | 31.41 | 14.69 |  | 31.41 | 14.69 | 46.1 | 0 | 248.61 | 248.61 | 0 | 38.35 | 23.01 | 15.34 | 106.56 | 0 | 106.56 | 121.9 | 121.9 | 0
E11/K149/SK/dm/213 | RESIDENCE | 252a | 76940 | 79858 | Wall Finishing Work | Basement 1 | Additional Boarding | 1 | 2.5 | 0.9 |  | 1 | m2-LxW | 2.25 | 2023-02-17 | 2023-03-03 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 10.44 | 3.38 | 4.48 | 18.3 | 12.47 | 5.83 |  | 12.47 | 5.83 | 18.3 | 0 | 248.61 | 248.61 | 0 | 38.35 | 23.01 | 15.34 | 106.56 | 0 | 106.56 | 121.9 | 121.9 | 0
E11/K149/SK/dm/213 | RESIDENCE | 253 | 76941 | 82185 | Ceiling Work (BW-1148) | Level 5 | Tower | 1 | 2.5 | 1.3 | 4 | 2 | rm | 4 | 2023-02-18 | 2023-03-02 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 177.35 | 54.08 | 76.01 | 307.44 | 210.63 | 96.81 |  | 210.63 | 96.81 | 307.44 | 0 | 177.35 | 177.35 | 0 | 54.08 | 33.28 | 20.8 | 76.01 | 0 | 76.01 | 96.81 | 96.81 | 0
E11/K149/SK/dm/213 | RESIDENCE | 253a | 76942 | 82186 | Ceiling Work (BW-1148) | Level 5 | Tower | 1 | 1.8 | 1.8 | 4 | 1 | rm | 4 | 2023-02-18 | 2023-03-02 | 100% | 100% | 100% | 1.8571 | 63.34 | 7.28 | 177.35 | 54.08 | 76.01 | 307.44 | 210.63 | 96.81 |  | 210.63 | 96.81 | 307.44 | 0 | 211.86 | 211.86 | 0 | 61.45 | 37.82 | 23.63 | 90.8 | 0 | 90.8 | 114.43 | 114.43 | 0
E11/K149/SK/dm/213 | RESIDENCE | 253b | 76942 | 82186 | Ceiling Work (BW-1148) | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 0.75 |  | 1 | m2-LxW | 1.35 | 2023-02-18 | 2023-03-02 | 100% | 100% | 100% | 1.8571 | 36.52 | 2.94 | 34.51 | 7.37 | 14.79 | 56.67 | 39.05 | 17.62 |  | 39.05 | 17.62 | 56.67 | 0 | 211.86 | 211.86 | 0 | 61.45 | 37.82 | 23.63 | 90.8 | 0 | 90.8 | 114.43 | 114.43 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a7 | 76943 |  | Glass Work | Level 26 | Additional Boarding | 2 | 4.6 | 0.75 |  | 2 | m2-LxW | 6.9 | 2023-02-18 |  | 100% | 100% | 0% | 5.1429 | 6.63 | 0.7 | 32.02 | 24.84 | 0 | 56.86 | 37.54 | 19.32 |  | 37.54 | 19.32 | 56.86 | 0 | 32.02 | 32.02 | 0 | 24.84 | 5.52 | 19.32 | 0 | 0 | 0 | 19.32 | 19.32 | 0
E11/K149/SK/dm/213 | RESIDENCE | 252b | 76944 | 79857 | Stair 1 For Wall Finishing Work | Basement 1 | Independent | 1 | 6.3 | 0.9 | 1.5 | 1 | m2-LxH | 9.45 | 2023-02-18 | 2023-03-03 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 79.45 | 9.26 | 34.05 | 122.76 | 84.74 | 38.02 |  | 84.74 | 38.02 | 122.76 | 0 | 95.32 | 95.32 | 0 | 14.05 | 8.03 | 6.02 | 40.85 | 0 | 40.85 | 46.87 | 46.87 | 0
E11/K149/SK/dm/213 | RESIDENCE | 252c | 76944 | 79857 | Stair 1 For Wall Finishing Work | Basement 2 | Additional Boarding | 1 | 3.8 | 0.9 |  | 1 | m2-LxW | 3.42 | 2023-02-18 | 2023-03-03 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 15.87 | 4.79 | 6.8 | 27.46 | 18.61 | 8.85 |  | 18.61 | 8.85 | 27.46 | 0 | 95.32 | 95.32 | 0 | 14.05 | 8.03 | 6.02 | 40.85 | 0 | 40.85 | 46.87 | 46.87 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a8 | 76945 | 79867 | Glass Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 7.2 | 0.75 |  | 1 | m2-LxW | 5.4 | 2023-02-18 | 2023-03-06 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 138.05 | 38.56 | 59.16 | 235.77 | 156.19 | 79.58 |  | 156.19 | 79.58 | 235.77 | 0 | 138.05 | 138.05 | 0 | 38.56 | 18.14 | 20.42 | 59.16 | 0 | 59.16 | 79.58 | 79.58 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a9 | 76946 | 79885 | Glass Work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 |  | 1 | m2-LxW | 4.05 | 2023-02-18 | 2023-03-18 | 100% | 100% | 100% | 4.1429 | 36.52 | 2.94 | 103.53 | 49.33 | 44.37 | 197.23 | 117.14 | 80.09 |  | 117.14 | 80.09 | 197.23 | 0 | 103.53 | 103.53 | 0 | 49.33 | 13.61 | 35.72 | 44.37 | 0 | 44.37 | 80.09 | 80.09 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8a10 | 76947 |  | Glass Work | Level 27 | Additional Boarding | 1 | 1.8 | 1.8 |  | 1 | m2-LxW | 3.24 | 2023-02-20 |  | 100% | 100% | 0% | 4.8571 | 6.63 | 0.7 | 15.04 | 11.02 | 0 | 26.06 | 16.98 | 9.08 |  | 16.98 | 9.08 | 26.06 | 0 | 15.04 | 15.04 | 0 | 11.02 | 1.94 | 9.08 | 0 | 0 | 0 | 9.08 | 9.08 | 0
E11/K149/SK/dm/213 | RESIDENCE | 254 | 76948 | 82148 | Glass Work | Level 26 | Independent | 1 | 8.5 | 1 | 2 | 1 | m2-LxH | 17 | 2023-02-21 | 2023-03-20 | 100% | 100% | 100% | 4 | 12.01 | 0.49 | 142.92 | 33.32 | 61.25 | 237.49 | 148.87 | 88.62 |  | 148.87 | 88.62 | 237.49 | 0 | 142.92 | 142.92 | 0 | 33.32 | 5.95 | 27.37 | 61.25 | 0 | 61.25 | 88.62 | 88.62 | 0
E11/K149/SK/dm/213 | RESIDENCE | 255 | 76949 |  |  | Ground Level | Independent | 1 | 5.4 | 1.3 | 1 | 1 | m2-LxH | 5.4 | 2023-02-22 |  | 100% | 100% | 0% | 4.5714 | 12.01 | 0.49 | 45.4 | 12.1 | 0 | 57.5 | 46.91 | 10.59 |  | 46.91 | 10.59 | 57.5 | 0 | 45.4 | 45.4 | 0 | 12.1 | 1.51 | 10.59 | 0 | 0 | 0 | 10.59 | 10.59 | 0
E11/K149/SK/dm/213 | RESIDENCE | 256 | 76950 | 82109 | Signage Removing Work | Level 23 | Independent | 1 | 18.8 | 1.3 | 2.2 | 1 | m2-LxH | 41.36 | 2023-02-22 | 2023-03-16 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 347.71 | 66.59 | 149.02 | 563.32 | 359.29 | 204.03 |  | 359.29 | 204.03 | 563.32 | 0 | 347.71 | 347.71 | 0 | 66.59 | 11.58 | 55.01 | 149.02 | 0 | 149.02 | 204.03 | 204.03 | 0
E11/K149/SK/dm/213 | RESIDENCE | 257 | 77401 | 79865 | Staircase 4 For Fire Line Work | Ground Level | Tower | 1 | 2.5 | 0.9 | 2 | 1 | rm | 2 | 2023-02-24 | 2023-03-07 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 88.68 | 24.96 | 38 | 151.64 | 92.84 | 58.8 |  | 92.84 | 58.8 | 151.64 | 0 | 88.68 | 88.68 | 0 | 24.96 | 4.16 | 20.8 | 38 | 0 | 38 | 58.8 | 58.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 257a | 77402 | 79866 | Staircase 4 For Fire Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-02-24 | 2023-03-07 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 88.68 | 24.96 | 38 | 151.64 | 92.84 | 58.8 |  | 92.84 | 58.8 | 151.64 | 0 | 88.68 | 88.68 | 0 | 24.96 | 4.16 | 20.8 | 38 | 0 | 38 | 58.8 | 58.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 258 | 77403 |  | Fire Line Work | Ground Level | Tower | 1 | 2.5 | 1.3 | 4 | 2 | rm | 4 | 2023-02-24 |  | 100% | 100% | 0% | 4.2857 | 63.34 | 7.28 | 177.35 | 124.8 | 0 | 302.15 | 185.67 | 116.48 |  | 185.67 | 116.48 | 302.15 | 0 | 177.35 | 177.35 | 0 | 124.8 | 8.32 | 116.48 | 0 | 0 | 0 | 116.48 | 116.48 | 0
E11/K149/SK/dm/213 | RESIDENCE | 258a | 77404 |  | Fire Line Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 1 |  | 1 | m2-LxW | 1.3 | 2023-02-25 |  | 100% | 100% | 0% | 4.1429 | 36.52 | 2.94 | 33.23 | 15.83 | 0 | 49.06 | 33.78 | 15.28 |  | 33.78 | 15.28 | 49.06 | 0 | 33.23 | 33.23 | 0 | 15.83 | 0.55 | 15.28 | 0 | 0 | 0 | 15.28 | 15.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 258b | 77405 |  | Fire Line Work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 1 |  | 1 | m2-LxW | 1.3 | 2023-02-25 |  | 100% | 100% | 0% | 4.1429 | 36.52 | 2.94 | 33.23 | 15.83 | 0 | 49.06 | 33.78 | 15.28 |  | 33.78 | 15.28 | 49.06 | 0 | 33.23 | 33.23 | 0 | 15.83 | 0.55 | 15.28 | 0 | 0 | 0 | 15.28 | 15.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 259 | 77406 | 82101 | Water Tank Access | Ground Level | Tower | 1 | 2.5 | 1.3 | 1.7 | 1 | rm | 1.7 | 2023-02-25 | 2023-03-18 | 100% | 100% | 100% | 3.1429 | 63.34 | 7.28 | 75.37 | 38.9 | 32.3 | 146.57 | 77.14 | 69.43 |  | 77.14 | 69.43 | 146.57 | 0 | 75.37 | 75.37 | 0 | 38.9 | 1.77 | 37.13 | 32.3 | 0 | 32.3 | 69.43 | 69.43 | 0
E11/K149/SK/dm/213 | HOTEL | 135 | 75919 | 78555 | Staircase 8 For Wall Finishing Work | Level 1 to 2 | Independent | 1 | 6 | 0.9 | 1.5 | 1 | m2-LxH | 9 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 75.66 | 8.82 | 32.43 | 116.91 | 116.91 | 0 |  | 116.91 | 0 | 116.91 | 0 | 190 | 190 | 0 | 22.15 | 22.15 | 0 | 81.43 | 81.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135a | 75919 | 78555 | Staircase 8 For Wall Finishing Work | Level 1 to 2 | Independent | 1 | 6.8 | 0.9 | 2 | 1 | m2-LxH | 13.6 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 114.34 | 13.33 | 49 | 176.67 | 176.67 | 0 |  | 176.67 | 0 | 176.67 | 0 | 190 | 190 | 0 | 22.15 | 22.15 | 0 | 81.43 | 81.43 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135b | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 126.11 | 14.7 | 54.05 | 194.86 | 194.86 | 0 |  | 194.86 | 0 | 194.86 | 0 | 322.49 | 322.49 | 0 | 47.49 | 47.49 | 0 | 138.21 | 138.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135b | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 25.06 | 7.56 | 10.74 | 43.36 | 43.36 | 0 |  | 43.36 | 0 | 43.36 | 0 | 322.49 | 322.49 | 0 | 47.49 | 47.49 | 0 | 138.21 | 138.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135c | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 142.92 | 16.66 | 61.25 | 220.83 | 220.83 | 0 |  | 220.83 | 0 | 220.83 | 0 | 322.49 | 322.49 | 0 | 47.49 | 47.49 | 0 | 138.21 | 138.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135c | 75920 | 78556 | Staircase 8 For Wall Finishing Work | Level 3 | Additional Boarding | 1 | 6.8 | 0.9 |  | 1 | m2-LxW | 6.12 | 2023-01-26 | 2023-02-08 | 100% | 100% | 100% | 2 | 6.63 | 0.7 | 28.4 | 8.57 | 12.17 | 49.14 | 49.14 | 0 |  | 49.14 | 0 | 49.14 | 0 | 322.49 | 322.49 | 0 | 47.49 | 47.49 | 0 | 138.21 | 138.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 136 | 75921 | 78587 | Glass Line ACP Fixing | Roof | Independent | 1 | 3 | 1.3 | 1.5 | 1 | m2-LxH | 4.5 | 2023-01-26 | 2023-02-18 | 100% | 100% | 100% | 3.4286 | 12.01 | 0.49 | 37.83 | 7.56 | 16.21 | 61.6 | 61.6 | 0 |  | 61.6 | 0 | 61.6 | 0 | 37.83 | 37.83 | 0 | 7.56 | 7.56 | 0 | 16.21 | 16.21 | 0 | 0 | 0 | 0
E11/K149/SK/dm/640 | HOTEL | 108g | 75922 | 79809 | Steel Column Lifting Work (1399-45a) | Level 29 | Design 1399-45a | 1 |  |  |  |  | unit | 1 | 2023-01-26 | 2023-02-22 | 25% | 25% | 25% | 4 | 19801.43 | 837.82 | 3465.25 | 837.82 | 1485.11 | 5788.18 | 5788.18 | 0 | Tas Quote 2439-34-1 | 5788.18 | 0 | 5788.18 | 0 | 3465.25 | 3465.25 | 0 | 837.82 | 837.82 | 0 | 1485.11 | 1485.11 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 137 | 75923 | 78567 | Plant Room Fire Seelent Work | Level 1 | Tower | 1 | 1.8 | 1.8 | 2 | 1 | rm | 2 | 2023-01-26 | 2023-02-13 | 100% | 100% | 100% | 2.7143 | 63.34 | 7.28 | 88.68 | 39.52 | 38 | 166.2 | 166.2 | 0 |  | 166.2 | 0 | 166.2 | 0 | 88.68 | 88.68 | 0 | 39.52 | 39.52 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 138 | 75924 | 79824 | Plant Room Fire Seelent Work | Level 1 | Tower | 1 | 1.8 | 1.8 | 1.5 | 1 | rm | 1.5 | 2023-01-26 | 2023-03-06 | 100% | 100% | 100% | 5.7143 | 63.34 | 7.28 | 66.51 | 62.4 | 28.5 | 157.41 | 114.87 | 42.54 |  | 114.87 | 42.54 | 157.41 | 0 | 66.51 | 66.51 | 0 | 62.4 | 48.36 | 14.04 | 28.5 | 0 | 28.5 | 42.54 | 42.54 | 0
E11/K149/SK/SR/517 | HOTEL | 139 | 75925 |  | Balcony Ceiling Work | Level 21 | Design 1399-35b | 1 | 4.3 | 1 | 1 | 1 | unit | 1 | 2023-01-26 |  | 100% | 100% | 0% | 8.4286 | 1772.5845 | 52.192 | 1240.81 | 439.9 | 0 | 1680.71 | 1471.95 | 208.76 | Tas Quote 2439-25-1 (item#5) | 1471.95 | 208.76 | 1680.71 | 0 | 1240.81 | 1240.81 | 0 | 439.9 | 231.14 | 208.76 | 0 | 0 | 0 | 208.76 | 208.76 | 0
E11/K149/SK/dm/213 | HOTEL | 135d | 75926 | 78557 | Staircase 8 For Wall Finishing Work | Level 3 to 4 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 | 193.81 | 0 |  | 193.81 | 0 | 193.81 | 0 | 151.17 | 151.17 | 0 | 20.67 | 20.67 | 0 | 64.79 | 64.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135d | 75926 | 78557 | Staircase 8 For Wall Finishing Work | Level 3 to 4 | Additional Boarding | 1 | 6 | 0.9 |  | 1 | m2-LxW | 5.4 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 6.63 | 0.7 | 25.06 | 7.02 | 10.74 | 42.82 | 42.82 | 0 |  | 42.82 | 0 | 42.82 | 0 | 151.17 | 151.17 | 0 | 20.67 | 20.67 | 0 | 64.79 | 64.79 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135e | 75927 | 78557 | Staircase 8 For Wall Finishing Work | Level 4 to 5 | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 142.92 | 15.47 | 61.25 | 219.64 | 219.64 | 0 |  | 219.64 | 0 | 219.64 | 0 | 269.03 | 269.03 | 0 | 29.12 | 29.12 | 0 | 115.3 | 115.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135f | 75927 | 78558 | Staircase 8 For Wall Finishing Work | Level 4 to 5 | Independent | 1 | 6 | 0.9 | 2.5 | 1 | m2-LxH | 15 | 2023-01-27 | 2023-02-08 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 126.11 | 13.65 | 54.05 | 193.81 | 193.81 | 0 |  | 193.81 | 0 | 193.81 | 0 | 269.03 | 269.03 | 0 | 29.12 | 29.12 | 0 | 115.3 | 115.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135g | 75928 | 78568 | Staircase 8 For Wall Finishing Work | Level 5 to 6 | Independent | 1 | 6.8 | 0.9 | 2.5 | 1 | m2-LxH | 17 | 2023-01-27 | 2023-02-14 | 100% | 100% | 100% | 2.7143 | 12.01 | 0.49 | 142.92 | 22.61 | 61.25 | 226.78 | 226.78 | 0 |  | 226.78 | 0 | 226.78 | 0 | 142.92 | 142.92 | 0 | 22.61 | 22.61 | 0 | 61.25 | 61.25 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 140 | 75929 | 78570 | Near Ramp For Concret Cutting | Basement 1 | Tower | 1 | 2.5 | 2.5 | 10 | 1 | rm | 10 | 2023-01-27 | 2023-02-14 | 100% | 100% | 100% | 2.7143 | 63.34 | 7.28 | 443.38 | 197.6 | 190.02 | 831 | 831 | 0 |  | 831 | 0 | 831 | 0 | 535.96 | 535.96 | 0 | 221.35 | 221.35 | 0 | 229.7 | 229.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 140a | 75929 | 78570 | Near Ramp For Concret Cutting | Basement 1 | Buttress | 1 | 2.5 | 2.5 | 4 |  | m3 | 25 | 2023-01-27 | 2023-02-14 | 100% | 100% | 100% | 2.7143 | 5.29 | 0.35 | 92.58 | 23.75 | 39.68 | 156.01 | 156.01 | 0 |  | 156.01 | 0 | 156.01 | 0 | 535.96 | 535.96 | 0 | 221.35 | 221.35 | 0 | 229.7 | 229.7 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135h | 75930 | 78568 | Staircase 8 For Wall Finishing Work | Level 5 to 6 | Independent | 1 | 5.3 | 0.9 | 2.5 | 1 | m2-LxH | 13.25 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 111.39 | 16.7 | 47.74 | 175.83 | 175.83 | 0 |  | 175.83 | 0 | 175.83 | 0 | 133.53 | 133.53 | 0 | 25.29 | 25.29 | 0 | 57.23 | 57.23 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135h | 75930 | 78568 | Staircase 8 For Wall Finishing Work | Level 5 to 6 | Additional Boarding | 1 | 5.3 | 0.9 |  | 1 | m2-LxW | 4.77 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 6.63 | 0.7 | 22.14 | 8.59 | 9.49 | 40.22 | 40.22 | 0 |  | 40.22 | 0 | 40.22 | 0 | 133.53 | 133.53 | 0 | 25.29 | 25.29 | 0 | 57.23 | 57.23 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135i | 75931 | 78569 | Staircase 8 For Wall Finishing Work | Level 6 to 7 | Independent | 1 | 6 | 0.9 | 2 | 1 | m2-LxH | 12 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 100.88 | 15.12 | 43.24 | 159.24 | 159.24 | 0 |  | 159.24 | 0 | 159.24 | 0 | 100.88 | 100.88 | 0 | 15.12 | 15.12 | 0 | 43.24 | 43.24 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 135j | 75932 | 78569 | Staircase 8 For Wall Finishing Work | Level 6 to 7 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-01-28 | 2023-02-14 | 100% | 100% | 100% | 2.5714 | 12.01 | 0.49 | 84.07 | 12.6 | 36.03 | 132.7 | 132.7 | 0 |  | 132.7 | 0 | 132.7 | 0 | 84.07 | 84.07 | 0 | 12.6 | 12.6 | 0 | 36.03 | 36.03 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 119b | 75933 | 80940 | Lift Machine Room Riser Wall Block Work | Level 30 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-01-28 | 2023-01-31 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 | 135 | 0 |  | 135 | 0 | 135 | 0 | 88.68 | 88.68 | 0 | 8.32 | 8.32 | 0 | 38 | 38 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 108h | 75934 | 79807 | Cabana Structure Work | Level 29 | Independent | 1 | 10.7 | 1.8 | 1.5 | 1 | m2-LxH | 16.05 | 2023-01-28 | 2023-02-22 | 100% | 100% | 100% | 3.7143 | 16.76 | 0.77 | 188.3 | 45.9 | 80.7 | 314.9 | 314.9 | 0 |  | 314.9 | 0 | 314.9 | 0 | 188.3 | 188.3 | 0 | 45.9 | 45.9 | 0 | 80.7 | 80.7 | 0 | 0 | 0 | 0
E11/K149/SMF/dm/641 | HOTEL | 141 to a,b | 75935 | 79903 | Canopy & EIFS Work | Level 28 to 30 | Design-1399-43 | 1 |  |  |  |  | unit | 1 | 2023-01-28 | 2023-03-11 | 100% | 100% | 100% | 6.1429 | 7845.02 | 212.35 | 5491.51 | 1304.44 | 2353.51 | 9149.46 | 6371.25 | 2778.21 | Tas Quote 2439-33-1 | 6371.25 | 2778.21 | 9149.46 | 0 | 5491.51 | 5491.51 | 0 | 1304.44 | 879.74 | 424.7 | 2353.51 | 0 | 2353.51 | 2778.21 | 2778.21 | 0
E11/K149/SK/dm/213 | HOTEL | 142 | 75936 |  | Mast Climber Access | Level 17 | Tower | 1 | 1.8 | 1 | 1 | 1 | rm | 1 | 2023-01-30 |  | 100% | 100% | 0% | 7.8571 | 63.34 | 7.28 | 44.34 | 57.2 | 0 | 101.54 | 72.42 | 29.12 |  | 72.42 | 29.12 | 101.54 | 0 | 44.34 | 44.34 | 0 | 57.2 | 28.08 | 29.12 | 0 | 0 | 0 | 29.12 | 29.12 | 0
E11/K149/SK/dm/213 | HOTEL | 150f | 75937 | 78572 | External EIFS Work | Level 17 | Tower | 1 | 1.8 | 0.75 | 0.5 | 1 | rm | 0.5 | 2023-01-30 | 2023-02-14 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 22.17 | 8.32 | 9.5 | 39.99 | 39.99 | 0 |  | 39.99 | 0 | 39.99 | 0 | 22.17 | 22.17 | 0 | 8.32 | 8.32 | 0 | 9.5 | 9.5 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 143 | 75938 |  | Planter Area edge protection | Level 4 | Double Handrail | 1 | 31 |  | 1 |  | lm | 31 | 2023-01-30 |  | 100% | 100% | 0% | 7.8571 | 15 | 0.91 | 325.5 | 221.65 | 0 | 547.15 | 434.31 | 112.84 |  | 434.31 | 112.84 | 547.15 | 0 | 325.5 | 325.5 | 0 | 221.65 | 108.81 | 112.84 | 0 | 0 | 0 | 112.84 | 112.84 | 0
E11/K149/SK/dm/213 | HOTEL | 144 | 75939 | 79810 | EIFS Work | Level 30 | Independent | 1 | 7 | 1 | 2 | 1 | m2-LxH | 14 | 2023-01-31 | 2023-02-24 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 117.7 | 24.5 | 50.44 | 192.64 | 192.64 | 0 |  | 192.64 | 0 | 192.64 | 0 | 302.65 | 302.65 | 0 | 63 | 63 | 0 | 129.71 | 129.71 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 144a | 75939 | 79811 | EIFS Work | Level 30 | Independent | 1 | 11 | 0.5 | 2 | 1 | m2-LxH | 22 | 2023-01-31 | 2023-02-24 | 100% | 100% | 100% | 3.5714 | 12.01 | 0.49 | 184.95 | 38.5 | 79.27 | 302.72 | 302.72 | 0 |  | 302.72 | 0 | 302.72 | 0 | 302.65 | 302.65 | 0 | 63 | 63 | 0 | 129.71 | 129.71 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 144b | 75940 | 79812 | EIFS Work | Level 30 | Tower | 1 | 2 | 1 | 1 | 1 | rm | 1 | 2023-01-31 | 2023-02-24 | 100% | 100% | 100% | 3.5714 | 63.34 | 7.28 | 44.34 | 26 | 19 | 89.34 | 89.34 | 0 |  | 89.34 | 0 | 89.34 | 0 | 44.34 | 44.34 | 0 | 26 | 26 | 0 | 19 | 19 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 145 | 75941 | 79806 | EIFS Work | Level 29 | Independent | 1 | 7 | 1.3 | 3 | 1 | m2-LxH | 21 | 2023-01-31 | 2023-02-22 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 176.55 | 33.81 | 75.66 | 286.02 | 286.02 | 0 |  | 286.02 | 0 | 286.02 | 0 | 264.82 | 264.82 | 0 | 50.72 | 50.72 | 0 | 113.49 | 113.49 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 145a | 75941 | 79805 | EIFS Work | Level 29 | Independent | 1 | 3.5 | 1 | 3 | 1 | m2-LxH | 10.5 | 2023-01-31 | 2023-02-22 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 88.27 | 16.91 | 37.83 | 143.01 | 143.01 | 0 |  | 143.01 | 0 | 143.01 | 0 | 264.82 | 264.82 | 0 | 50.72 | 50.72 | 0 | 113.49 | 113.49 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 115b | 75942 |  | EIFS Work | Upper Roof | Additional Boarding | 1 | 9.5 | 1 |  | 1 | m2-LxW | 9.5 | 2023-01-31 |  | 100% | 100% | 0% | 7.7143 | 6.63 | 0.7 | 44.09 | 51.3 | 0 | 95.39 | 68.79 | 26.6 |  | 68.79 | 26.6 | 95.39 | 0 | 44.09 | 44.09 | 0 | 51.3 | 24.7 | 26.6 | 0 | 0 | 0 | 26.6 | 26.6 | 0
E11/K149/SK/dm/213 | HOTEL | 115c | 75943 | 79844 | ACP Panel Work | Upper Roof | Independent | 1 | 4 | 0.75 | 4 | 1 | m2-LxH | 16 | 2023-01-31 | 2023-03-06 | 100% | 100% | 100% | 5 | 12.01 | 0.49 | 134.51 | 39.2 | 57.65 | 231.36 | 163.63 | 67.73 |  | 163.63 | 67.73 | 231.36 | 0 | 134.51 | 134.51 | 0 | 39.2 | 29.12 | 10.08 | 57.65 | 0 | 57.65 | 67.73 | 67.73 | 0
E11/K149/SK/dm/213 | HOTEL | 146 | 75944 |  | Lift Machine Room EIFS Work | Level 30 | Independent | 1 | 7.5 | 1.2 | 4 | 1 | m2-LxH | 30 | 2023-02-01 |  | 100% | 100% | 0% | 7.5714 | 12.01 | 0.49 | 252.21 | 111.3 | 0 | 363.51 | 304.71 | 58.8 |  | 304.71 | 58.8 | 363.51 | 0 | 554.86 | 554.86 | 0 | 244.86 | 115.5 | 129.36 | 0 | 0 | 0 | 129.36 | 129.36 | 0
E11/K149/SK/dm/213 | HOTEL | 146a | 75944 |  | Lift Machine Room EIFS Work | Level 30 | Independent | 1 | 9 | 1 | 4 | 1 | m2-LxH | 36 | 2023-02-01 |  | 100% | 100% | 0% | 7.5714 | 12.01 | 0.49 | 302.65 | 133.56 | 0 | 436.21 | 365.65 | 70.56 |  | 365.65 | 70.56 | 436.21 | 0 | 554.86 | 554.86 | 0 | 244.86 | 115.5 | 129.36 | 0 | 0 | 0 | 129.36 | 129.36 | 0
E11/K149/SK/dm/213 | HOTEL | 147 | 75945 | 78598 | Pool Side GRC Panel Work | Level 29 | Mobile Tower | 1 | 2.5 | 1.3 | 2.3 | 2 | rm | 2.3 | 2023-02-01 | 2023-02-22 | 100% | 100% | 100% | 3.1429 | 103.33 | 10.29 | 166.36 | 74.38 | 71.3 | 312.04 | 312.04 | 0 |  | 312.04 | 0 | 312.04 | 0 | 166.36 | 166.36 | 0 | 74.38 | 74.38 | 0 | 71.3 | 71.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 141d | 75946 | 79904 | EIFS Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 6 | 1 |  | 1 | m2-LxW | 6 | 2023-02-01 | 2023-03-11 | 100% | 100% | 100% | 5.5714 | 36.52 | 2.94 | 153.38 | 98.28 | 65.74 | 317.4 | 216.38 | 101.02 |  | 216.38 | 101.02 | 317.4 | 0 | 153.38 | 153.38 | 0 | 98.28 | 63 | 35.28 | 65.74 | 0 | 65.74 | 101.02 | 101.02 | 0
E11/K149/SK/dm/213 | HOTEL | 148 | 75947 |  | Wall Finishing Work | Ground Level | Independent | 1 | 8.8 | 1.3 | 3.5 | 1 | m2-LxH | 30.8 | 2023-02-02 |  | 100% | 100% | 0% | 7.4286 | 12.01 | 0.49 | 258.94 | 112.11 | 0 | 371.05 | 310.68 | 60.37 |  | 310.68 | 60.37 | 371.05 | 0 | 624.57 | 624.57 | 0 | 348.4 | 160.8 | 187.6 | 0 | 0 | 0 | 187.6 | 187.6 | 0
E11/K149/SK/dm/213 | HOTEL | 148 | 75947 |  | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 8.8 | 1.3 |  | 1 | m2-LxW | 11.44 | 2023-02-02 |  | 100% | 100% | 0% | 7.4286 | 6.63 | 0.7 | 53.09 | 59.49 | 0 | 112.58 | 80.55 | 32.03 |  | 80.55 | 32.03 | 112.58 | 0 | 624.57 | 624.57 | 0 | 348.4 | 160.8 | 187.6 | 0 | 0 | 0 | 187.6 | 187.6 | 0
E11/K149/SK/dm/213 | HOTEL | 148a | 75947 |  | Wall Finishing Work | Ground Level | Independent | 1 | 10 | 1.3 | 3 | 1 | m2-LxH | 30 | 2023-02-02 |  | 100% | 100% | 0% | 7.4286 | 12.01 | 0.49 | 252.21 | 109.2 | 0 | 361.41 | 302.61 | 58.8 |  | 302.61 | 58.8 | 361.41 | 0 | 624.57 | 624.57 | 0 | 348.4 | 160.8 | 187.6 | 0 | 0 | 0 | 187.6 | 187.6 | 0
E11/K149/SK/dm/213 | HOTEL | 148a | 75947 |  | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 10 | 1.3 |  | 1 | m2-LxW | 13 | 2023-02-02 |  | 100% | 100% | 0% | 7.4286 | 6.63 | 0.7 | 60.33 | 67.6 | 0 | 127.93 | 91.53 | 36.4 |  | 91.53 | 36.4 | 127.93 | 0 | 624.57 | 624.57 | 0 | 348.4 | 160.8 | 187.6 | 0 | 0 | 0 | 187.6 | 187.6 | 0
E11/K149/SK/dm/213 | HOTEL | 82f | 75948 | 79843 | Glass Line Frame Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 4 | 0.75 |  | 1 | m2-LxW | 3 | 2023-02-02 | 2023-03-08 | 100% | 100% | 100% | 5 | 36.52 | 2.94 | 76.69 | 44.1 | 32.87 | 153.66 | 106.93 | 46.73 |  | 106.93 | 46.73 | 153.66 | 0 | 76.69 | 76.69 | 0 | 44.1 | 30.24 | 13.86 | 32.87 | 0 | 32.87 | 46.73 | 46.73 | 0
E11/K149/SK/dm/213 | HOTEL | 149 | 75949 | 79911 | Wall Finishing Work | Ground Level | Independent | 1 | 14 | 1.3 | 3.5 | 1 | m2-LxH | 49 | 2023-02-03 | 2023-03-06 | 100% | 100% | 100% | 4.5714 | 12.01 | 0.49 | 411.94 | 109.76 | 176.55 | 698.25 | 490.83 | 207.42 |  | 490.83 | 207.42 | 698.25 | 0 | 496.41 | 496.41 | 0 | 168 | 120.75 | 47.25 | 212.75 | 0 | 212.75 | 260 | 260 | 0
E11/K149/SK/dm/213 | HOTEL | 149 | 75949 | 79911 | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 14 | 1.3 |  | 1 | m2-LxW | 18.2 | 2023-02-03 | 2023-03-06 | 100% | 100% | 100% | 4.5714 | 6.63 | 0.7 | 84.47 | 58.24 | 36.2 | 178.91 | 126.33 | 52.58 |  | 126.33 | 52.58 | 178.91 | 0 | 496.41 | 496.41 | 0 | 168 | 120.75 | 47.25 | 212.75 | 0 | 212.75 | 260 | 260 | 0
E11/K149/SK/dm/213 | HOTEL | 141c | 75950 | 79904 | EIFS Work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 1 |  | 1 | m2-LxW | 5.4 | 2023-01-28 | 2023-03-11 | 100% | 100% | 100% | 6.1429 | 36.52 | 2.94 | 138.05 | 97.52 | 59.16 | 294.73 | 203.82 | 90.91 |  | 203.82 | 90.91 | 294.73 | 0 | 138.05 | 138.05 | 0 | 97.52 | 65.77 | 31.75 | 59.16 | 0 | 59.16 | 90.91 | 90.91 | 0
E11/K149/SK/dm/213 | HOTEL | 150 | 76801 | 79814 | Wall Finishing Work | Ground Level | Independent | 1 | 18.5 | 1.3 | 2.2 | 1 | m2-LxH | 40.7 | 2023-02-03 | 2023-02-25 | 100% | 100% | 100% | 3.2857 | 12.01 | 0.49 | 342.16 | 65.53 | 146.64 | 554.33 | 554.33 | 0 |  | 554.33 | 0 | 554.33 | 0 | 342.16 | 342.16 | 0 | 65.53 | 65.53 | 0 | 146.64 | 146.64 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 107a | 76802 | 78586 | View Deck Loading Platform | Level 29 | Design-1399-42 | 1 |  |  |  | 1 | unit | 1 | 2023-02-03 | 2023-02-21 | 0% | 0% | 0% | 2.7143 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2439-30-1 Item--10), Charged under Tag 92&92a | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 151 | 76803 |  | Edge Protection | Level 29 | Double Handrail | 1 | 70 |  | 1.5 |  | lm | 70 | 2023-02-03 |  | 100% | 100% | 0% | 7.2857 | 15 | 0.91 | 735 | 464.1 | 0 | 1199.1 | 944.3 | 254.8 |  | 944.3 | 254.8 | 1199.1 | 0 | 735 | 735 | 0 | 464.1 | 209.3 | 254.8 | 0 | 0 | 0 | 254.8 | 254.8 | 0
E11/K149/SK/dm/213 | HOTEL | 115d | 76804 | 79842 | ACP Panel Work | Upper Roof | Cantilever (0.5 > 1.2m width) | 1 | 4 | 0.75 |  | 1 | m2-LxW | 3 | 2023-02-04 | 2023-03-08 | 100% | 100% | 100% | 4.7143 | 36.52 | 2.94 | 76.69 | 41.58 | 32.87 | 151.14 | 104.41 | 46.73 |  | 104.41 | 46.73 | 151.14 | 0 | 76.69 | 76.69 | 0 | 41.58 | 27.72 | 13.86 | 32.87 | 0 | 32.87 | 46.73 | 46.73 | 0
E11/K149/SK/dm/213 | HOTEL | 150g | 76805 | 78573 | Glass Cleaning & ceiling work | Level 17 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-02-06 | 2023-02-14 | 100% | 100% | 100% | 1.2857 | 36.52 | 2.94 | 25.56 | 3.78 | 10.96 | 40.3 | 40.3 | 0 |  | 40.3 | 0 | 40.3 | 0 | 25.56 | 25.56 | 0 | 3.78 | 3.78 | 0 | 10.96 | 10.96 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 152 | 76806 | 78559 | Decking Access | Level 29 | Tower | 1 | 1.5 | 1.3 | 4 | 2 | rm | 4 | 2023-02-07 | 2023-02-08 | 100% | 100% | 100% | 0.28571 | 63.34 | 7.28 | 177.35 | 8.32 | 76.01 | 261.68 | 261.68 | 0 |  | 261.68 | 0 | 261.68 | 0 | 177.35 | 177.35 | 0 | 8.32 | 8.32 | 0 | 76.01 | 76.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 153 | 76813 | 79803 | Decking Access | Level 29 | Independent | 1 | 6 | 1.3 | 4 | 1 | m2-LxH | 24 | 2023-02-08 | 2023-02-22 | 100% | 100% | 100% | 2.1429 | 12.01 | 0.49 | 201.77 | 25.2 | 86.47 | 313.44 | 313.44 | 0 |  | 313.44 | 0 | 313.44 | 0 | 201.77 | 201.77 | 0 | 25.2 | 25.2 | 0 | 86.47 | 86.47 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 148b | 76807 |  | Wall Finishing Work | Ground Level | Independent | 1 | 17.5 | 0.9 | 2.5 | 1 | m2-LxH | 43.75 | 2023-02-07 |  | 100% | 100% | 0% | 6.7143 | 12.01 | 0.49 | 367.81 | 143.94 | 0 | 511.75 | 426 | 85.75 |  | 426 | 85.75 | 511.75 | 0 | 367.81 | 367.81 | 0 | 143.94 | 58.19 | 85.75 | 0 | 0 | 0 | 85.75 | 85.75 | 0
E11/K149/SK/dm/213 | HOTEL | 145b | 76808 | 79804 | Corner Side ACP Panel | Level 29 | Independent | 1 | 4 | 2.3 | 2 | 1 | m2-LxH | 8 | 2023-02-07 | 2023-02-22 | 100% | 100% | 100% | 2.2857 | 16.76 | 0.77 | 93.86 | 14.08 | 40.22 | 148.16 | 148.16 | 0 |  | 148.16 | 0 | 148.16 | 0 | 93.86 | 93.86 | 0 | 14.08 | 14.08 | 0 | 40.22 | 40.22 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 113a | 76809 | 79830 | Plant Room For Painting Work | Level 5 | Cantilever (0.5 > 1.2m width) | 1 | 7 | 1 |  | 1 | m2-LxW | 7 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 36.52 | 2.94 | 178.95 | 79.38 | 76.69 | 335.02 | 231.87 | 103.15 |  | 231.87 | 103.15 | 335.02 | 0 | 178.95 | 178.95 | 0 | 79.38 | 52.92 | 26.46 | 76.69 | 0 | 76.69 | 103.15 | 103.15 | 0
E11/K149/SK/dm/213 | HOTEL | 2f | 76810 | 79831 | Plant Room For Painting Work | Level 5 | Independent | 1 | 2.6 | 1.8 | 4 | 2 | m2-LxH | 10.4 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 12.01 | 0.49 | 87.43 | 19.66 | 37.47 | 144.56 | 100.53 | 44.03 |  | 100.53 | 44.03 | 144.56 | 0 | 108.31 | 108.31 | 0 | 31.81 | 21.2 | 10.61 | 46.42 | 0 | 46.42 | 57.03 | 57.03 | 0
E11/K149/SK/dm/213 | HOTEL | 2g | 76810 | 79831 | Plant Room For Painting Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 6.63 | 0.7 | 20.88 | 12.15 | 8.95 | 41.98 | 28.98 | 13 |  | 28.98 | 13 | 41.98 | 0 | 108.31 | 108.31 | 0 | 31.81 | 21.2 | 10.61 | 46.42 | 0 | 46.42 | 57.03 | 57.03 | 0
E11/K149/SK/dm/213 | HOTEL | 2h | 76811 | 79832 | Plant Room For Painting Work | Level 5 | Tower | 1 | 2.5 | 1.8 | 4 | 1 | rm | 4 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 63.34 | 7.28 | 177.35 | 112.32 | 76.01 | 365.68 | 252.23 | 113.45 |  | 252.23 | 113.45 | 365.68 | 0 | 198.23 | 198.23 | 0 | 124.47 | 82.98 | 41.49 | 84.96 | 0 | 84.96 | 126.45 | 126.45 | 0
E11/K149/SK/dm/213 | HOTEL | 2h | 76811 | 79832 | Plant Room For Painting Work | Level 5 | Additional Boarding | 1 | 2.5 | 1.8 |  | 1 | m2-LxW | 4.5 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 6.63 | 0.7 | 20.88 | 12.15 | 8.95 | 41.98 | 28.98 | 13 |  | 28.98 | 13 | 41.98 | 0 | 198.23 | 198.23 | 0 | 124.47 | 82.98 | 41.49 | 84.96 | 0 | 84.96 | 126.45 | 126.45 | 0
E11/K149/SK/dm/213 | HOTEL | 109a | 76812 | 79833 | Plant Room For Painting Work | Level 5 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 |  | 1 | m2-LxW | 0.9 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 32.75 | 1.05 | 20.63 | 3.65 | 8.84 | 33.12 | 23.06 | 10.06 |  | 23.06 | 10.06 | 33.12 | 0 | 31.49 | 31.49 | 0 | 9.97 | 6.64 | 3.33 | 13.49 | 0 | 13.49 | 16.82 | 16.82 | 0
E11/K149/SK/dm/213 | HOTEL | 109b | 76812 | 79833 | Plant Room For Painting Work | Level 5 | Additional Boarding | 1 | 1.8 | 1.3 |  | 1 | m2-LxW | 2.34 | 2023-02-08 | 2023-03-06 | 100% | 100% | 100% | 3.8571 | 6.63 | 0.7 | 10.86 | 6.32 | 4.65 | 21.83 | 15.07 | 6.76 |  | 15.07 | 6.76 | 21.83 | 0 | 31.49 | 31.49 | 0 | 9.97 | 6.64 | 3.33 | 13.49 | 0 | 13.49 | 16.82 | 16.82 | 0
E11/K149/SK/dm/213 | HOTEL | 121c | 76814 | 78574 | KID Ceiling Work | Level 29 | Independent | 1 | 5.5 | 2.5 | 3.5 | 1 | m2-LxH | 19.25 | 2023-02-08 | 2023-02-11 | 100% | 100% | 100% | 0.57143 | 16.76 | 0.77 | 225.84 | 8.47 | 96.79 | 331.1 | 331.1 | 0 |  | 331.1 | 0 | 331.1 | 0 | 225.84 | 225.84 | 0 | 8.47 | 8.47 | 0 | 96.79 | 96.79 | 0 | 0 | 0 | 0
E11/K149/SK/SR/582 | HOTEL | 154 & a,b | 76815 | 78575 | Lift Shaft RC Slab Extention Work | Level 29 | Design 1399-39 | 1 |  |  |  |  | unit | 1 | 2023-02-09 | 2023-02-13 | 100% | 100% | 100% | 0.71429 | 4805.88 | 212.24 | 3364.12 | 151.6 | 1441.76 | 4957.48 | 4957.48 | 0 | 2439-29-1 (Item-9) | 4957.48 | 0 | 4957.48 | 0 | 3364.12 | 3364.12 | 0 | 151.6 | 151.6 | 0 | 1441.76 | 1441.76 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 80c | 76816 | 78578 | Entrance For Ceiling Work | Level 2 | Tower | 1 | 2.5 | 1.8 | 5 | 1 | rm | 5 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 221.69 | 36.4 | 95.01 | 353.1 | 353.1 | 0 |  | 353.1 | 0 | 353.1 | 0 | 242.32 | 242.32 | 0 | 37.35 | 37.35 | 0 | 103.85 | 103.85 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 80d | 76816 | 78578 | Entrance For Ceiling Work | Level 2 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 |  | 1 | m2-LxW | 0.9 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 20.63 | 0.95 | 8.84 | 30.42 | 30.42 | 0 |  | 30.42 | 0 | 30.42 | 0 | 242.32 | 242.32 | 0 | 37.35 | 37.35 | 0 | 103.85 | 103.85 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 80e | 76817 | 78579 | Entrance For Ceiling Work | Level 2 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.25 |  | 1 | m2-LxW | 0.63 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 32.75 | 1.05 | 14.44 | 0.66 | 6.19 | 21.29 | 21.29 | 0 |  | 21.29 | 0 | 21.29 | 0 | 40 | 40 | 0 | 3.6 | 3.6 | 0 | 17.15 | 17.15 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 80f | 76817 | 78579 | Entrance For Ceiling Work | Level 2 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-02-09 | 2023-02-15 | 100% | 100% | 100% | 1 | 36.52 | 2.94 | 25.56 | 2.94 | 10.96 | 39.46 | 39.46 | 0 |  | 39.46 | 0 | 39.46 | 0 | 40 | 40 | 0 | 3.6 | 3.6 | 0 | 17.15 | 17.15 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 151a | 76818 |  | Infinity Pool Edge Protection | Level 29 | Double Handrail | 1 | 45 |  | 1.5 |  | lm | 45 | 2023-02-09 |  | 100% | 100% | 0% | 6.4286 | 15 | 0.91 | 472.5 | 263.25 | 0 | 735.75 | 571.95 | 163.8 |  | 571.95 | 163.8 | 735.75 | 0 | 472.5 | 472.5 | 0 | 263.25 | 99.45 | 163.8 | 0 | 0 | 0 | 163.8 | 163.8 | 0
E11/K149/SK/dm/213 | HOTEL | 148c | 76819 |  | Over Head Protection | Ground Level | Independent | 1 | 18.8 | 0.9 | 2 | 1 | m2-LxH | 37.6 | 2023-02-10 |  | 100% | 100% | 0% | 6.2857 | 12.01 | 0.49 | 316.1 | 115.81 | 0 | 431.91 | 358.21 | 73.7 |  | 358.21 | 73.7 | 431.91 | 0 | 796.7 | 796.7 | 0 | 463.23 | 168.45 | 294.78 | 0 | 0 | 0 | 294.78 | 294.78 | 0
E11/K149/SK/dm/213 | HOTEL | 148d | 76819 |  | Over Head Protection | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 18.8 | 1 |  | 1 | m2-LxW | 18.8 | 2023-02-10 |  | 100% | 100% | 0% | 6.2857 | 36.52 | 2.94 | 480.6 | 347.42 | 0 | 828.02 | 606.94 | 221.08 |  | 606.94 | 221.08 | 828.02 | 0 | 796.7 | 796.7 | 0 | 463.23 | 168.45 | 294.78 | 0 | 0 | 0 | 294.78 | 294.78 | 0
E11/K149/SK/dm/213 | HOTEL | 155 | 76820 | 78576 | View Deck For Welding Work | Level 29 | Independent 1.8m wide | 1 | 5 | 2 | 0.5 | 1 | m2-LxH | 2.5 | 2023-02-10 | 2023-02-11 | 100% | 100% | 100% | 0.28571 | 16.76 | 0.77 | 29.33 | 0.55 | 12.57 | 42.45 | 42.45 | 0 |  | 42.45 | 0 | 42.45 | 0 | 29.33 | 29.33 | 0 | 0.55 | 0.55 | 0 | 12.57 | 12.57 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 156 | 76821 |  | View Deck Edge Protection | Level 29 | Double Handrail | 1 | 18 |  | 1 |  | lm | 18 | 2023-02-10 |  | 100% | 100% | 0% | 6.2857 | 15 | 0.91 | 189 | 102.96 | 0 | 291.96 | 226.44 | 65.52 |  | 226.44 | 65.52 | 291.96 | 0 | 189 | 189 | 0 | 102.96 | 37.44 | 65.52 | 0 | 0 | 0 | 65.52 | 65.52 | 0
E11/K149/SK/dm/213 | HOTEL | 141e | 76822 | 79904 | EIFS Work | Level 29 | Cantilever (0 < 0.5m width) | 2 | 1 | 0.5 |  | 2 | m2-LxW | 1 | 2023-02-10 | 2023-03-11 | 100% | 100% | 100% | 4.2857 | 32.75 | 1.05 | 22.93 | 4.5 | 9.83 | 37.26 | 25.33 | 11.93 |  | 25.33 | 11.93 | 37.26 | 0 | 22.93 | 22.93 | 0 | 4.5 | 2.4 | 2.1 | 9.83 | 0 | 9.83 | 11.93 | 11.93 | 0
E11/K149/SK/dm/213 | HOTEL | 67b | 76823 |  | Material Shifting Access | Level 27 | Tower | 1 | 1.5 | 1 | 1.5 | 1 | rm | 1.5 | 2023-02-10 |  | 100% | 100% | 0% | 6.2857 | 63.34 | 7.28 | 66.51 | 68.64 | 0 | 135.15 | 91.47 | 43.68 |  | 91.47 | 43.68 | 135.15 | 0 | 66.51 | 66.51 | 0 | 68.64 | 24.96 | 43.68 | 0 | 0 | 0 | 43.68 | 43.68 | 0
E11/K149/SK/dm/213 | HOTEL | 84e | 76824 | 78585 | Silicon Work Canopy | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 5.5 | 1.2 |  | 1 | m2-LxW | 6.6 | 2023-02-11 | 2023-02-18 | 100% | 100% | 100% | 1.1429 | 36.52 | 2.94 | 168.72 | 22.18 | 72.31 | 263.21 | 263.21 | 0 |  | 263.21 | 0 | 263.21 | 0 | 168.72 | 168.72 | 0 | 22.18 | 22.18 | 0 | 72.31 | 72.31 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 157 | 76825 |  | Corridor For Painting Work | Level 28 | Independent | 1 | 19 | 1.3 | 2 | 1 | m2-LxH | 38 | 2023-02-11 |  | 100% | 100% | 0% | 6.1429 | 12.01 | 0.49 | 319.47 | 114.38 | 0 | 433.85 | 359.37 | 74.48 |  | 359.37 | 74.48 | 433.85 | 0 | 319.47 | 319.47 | 0 | 114.38 | 39.9 | 74.48 | 0 | 0 | 0 | 74.48 | 74.48 | 0
E11/K149/SK/dm/213 | HOTEL | 158 | 76826 | 79934 | Column For Ceiling Work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4 | 2 | rm | 4 | 2023-02-11 | 2023-03-15 | 100% | 100% | 100% | 4.7143 | 63.34 | 7.28 | 177.35 | 137.28 | 76.01 | 390.64 | 239.75 | 150.89 |  | 239.75 | 150.89 | 390.64 | 0 | 177.35 | 177.35 | 0 | 137.28 | 62.4 | 74.88 | 76.01 | 0 | 76.01 | 150.89 | 150.89 | 0
E11/K149/SK/dm/213 | HOTEL | 159 | 76827 | 78580 | View Deck Access | Level 29 | Independent | 1 | 3.3 | 1.5 | 1 | 1 | m2-LxH | 3.3 | 2023-02-11 | 2023-02-15 | 100% | 100% | 100% | 0.71429 | 12.01 | 0.49 | 27.74 | 1.16 | 11.89 | 40.79 | 40.79 | 0 |  | 40.79 | 0 | 40.79 | 0 | 27.74 | 27.74 | 0 | 1.16 | 1.16 | 0 | 11.89 | 11.89 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 70d | 76828 | 79912 | Entrance For Ceiling Work | Ground Level | Independent 1.8m wide | 1 | 3.4 | 1.8 | 4 | 1 | m2-LxH | 13.6 | 2023-02-11 | 2023-03-15 | 100% | 100% | 100% | 4.7143 | 16.76 | 0.77 | 159.56 | 49.37 | 68.38 | 277.31 | 182 | 95.31 |  | 182 | 95.31 | 277.31 | 0 | 159.56 | 159.56 | 0 | 49.37 | 22.44 | 26.93 | 68.38 | 0 | 68.38 | 95.31 | 95.31 | 0
E11/K149/SK/dm/213 | HOTEL | 160 | 76829 | 79817 | Corridor For Painting Work | Level 28 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-02-13 | 2023-02-28 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 88.68 | 33.28 | 38 | 159.96 | 115.72 | 44.24 |  | 115.72 | 44.24 | 159.96 | 0 | 88.68 | 88.68 | 0 | 33.28 | 27.04 | 6.24 | 38 | 0 | 38 | 44.24 | 44.24 | 0
E11/K149/SK/SR/582 | HOTEL | 161 & a,b | 76830 | 78584 | Lift Shaft RC Slab Extention Work | Level 29 | Design 1399-39 | 1 |  |  |  |  | unit | 1 | 2023-02-14 | 2023-02-17 | 100% | 100% | 100% | 0.57143 | 4805.88 | 212.24 | 3364.12 | 121.28 | 1441.76 | 4927.16 | 4927.16 | 0 | 2439-29-1 (Item-9) | 4927.16 | 0 | 4927.16 | 0 | 3364.12 | 3364.12 | 0 | 121.28 | 121.28 | 0 | 1441.76 | 1441.76 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 162 | 76831 | 78597 | GRC Panel Work | Level 29 | Mobile Tower | 1 | 1.3 | 1.3 | 2.3 | 2 | rm | 2.3 | 2023-02-14 | 2023-02-22 | 100% | 100% | 100% | 1.2857 | 103.33 | 10.29 | 166.36 | 30.43 | 71.3 | 268.09 | 268.09 | 0 |  | 268.09 | 0 | 268.09 | 0 | 166.36 | 166.36 | 0 | 30.43 | 30.43 | 0 | 71.3 | 71.3 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 140b | 76832 | 78571 | Ramp Area For Concret Slab Cuttinhg | Basement 1 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 1.5 |  | 1 | m2-LxW | 3.75 | 2023-02-13 | 2023-02-14 | 100% | 100% | 100% | 0.28571 | 36.52 | 2.94 | 95.87 | 3.15 | 41.09 | 140.11 | 140.11 | 0 |  | 140.11 | 0 | 140.11 | 0 | 95.87 | 95.87 | 0 | 3.15 | 3.15 | 0 | 41.09 | 41.09 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 84f | 76833 | 78581 | Silicon Work Canopy (Damac Side) | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 10 | 1 |  | 1 | m2-LxW | 10 | 2023-02-14 | 2023-02-18 | 100% | 100% | 100% | 0.71429 | 36.52 | 2.94 | 255.64 | 21 | 109.56 | 386.2 | 386.2 | 0 |  | 386.2 | 0 | 386.2 | 0 | 255.64 | 255.64 | 0 | 21 | 21 | 0 | 109.56 | 109.56 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 163 | 76834 |  | Ceiling Work | Level 24 | Independent | 1 | 4.3 | 0.9 | 1 | 1 | m2-LxH | 4.3 | 2023-02-15 |  | 100% | 100% | 0% | 5.5714 | 12.01 | 0.49 | 36.15 | 11.74 | 0 | 47.89 | 39.46 | 8.43 |  | 39.46 | 8.43 | 47.89 | 0 | 36.15 | 36.15 | 0 | 11.74 | 3.31 | 8.43 | 0 | 0 | 0 | 8.43 | 8.43 | 0
E11/K149/SK/dm/213 | HOTEL | 164 | 76835 | 79942 | Balcony Access | Level 24 | Tower | 1 | 2.5 | 1.3 | 3.5 | 1 | rm | 3.5 | 2023-02-15 | 2023-03-24 | 100% | 100% | 100% | 5.4286 | 63.34 | 7.28 | 155.18 | 138.32 | 66.51 | 360.01 | 195.22 | 164.79 |  | 195.22 | 164.79 | 360.01 | 0 | 185.09 | 185.09 | 0 | 156.99 | 45.45 | 111.54 | 79.33 | 0 | 79.33 | 190.87 | 190.87 | 0
E11/K149/SK/dm/213 | HOTEL | 164a | 76835 | 79942 | Balcony Access | Level 24 | Cantilever (0.5 > 1.2m width) | 1 | 1.3 | 0.9 |  | 1 | m2-LxW | 1.17 | 2023-02-15 | 2023-03-24 | 100% | 100% | 100% | 5.4286 | 36.52 | 2.94 | 29.91 | 18.67 | 12.82 | 61.4 | 35.32 | 26.08 |  | 35.32 | 26.08 | 61.4 | 0 | 185.09 | 185.09 | 0 | 156.99 | 45.45 | 111.54 | 79.33 | 0 | 79.33 | 190.87 | 190.87 | 0
E11/K149/SK/dm/213 | HOTEL | 148e | 76837 | 79913 | Wall Finishing Work | Ground Level | Additional Boarding | 1 | 17.5 | 0.9 |  | 1 | m2-LxW | 15.75 | 2023-02-17 | 2023-03-07 | 100% | 100% | 100% | 2.7143 | 6.63 | 0.7 | 73.1 | 29.93 | 31.33 | 134.36 | 87.28 | 47.08 |  | 87.28 | 47.08 | 134.36 | 0 | 73.1 | 73.1 | 0 | 29.93 | 14.18 | 15.75 | 31.33 | 0 | 31.33 | 47.08 | 47.08 | 0
E11/K149/SK/dm/213 | HOTEL | 165 | 76838 | 79815 | Balcony Ceiling Work | Level 24 | Independent | 1 | 4.3 | 0.9 | 1 | 1 | m2-LxH | 4.3 | 2023-02-17 | 2023-02-24 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 36.15 | 2.41 | 15.49 | 54.05 | 38.86 | 15.19 |  | 38.86 | 15.19 | 54.05 | 0 | 36.15 | 36.15 | 0 | 2.41 | 2.71 | -0.3 | 15.49 | 0 | 15.49 | 15.19 | 15.19 | 0
E11/K149/SK/dm/213 | HOTEL | 147a | 76839 | 78596 | GRC Panel Work | Level 29 | Additional Boarding | 1 | 2.5 | 0.75 |  | 1 | m2-LxW | 1.88 | 2023-02-17 | 2023-02-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 8.73 | 1.13 | 3.74 | 13.6 | 13.6 | 0 |  | 13.6 | 0 | 13.6 | 0 | 8.73 | 8.73 | 0 | 1.13 | 1.13 | 0 | 3.74 | 3.74 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 162a | 76840 | 78595 | GRC Panel Work | Level 29 | Additional Boarding | 1 | 1.3 | 0.75 |  | 1 | m2-LxW | 0.98 | 2023-02-17 | 2023-02-22 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 4.55 | 0.59 | 1.95 | 7.09 | 7.09 | 0 |  | 7.09 | 0 | 7.09 | 0 | 4.55 | 4.55 | 0 | 0.59 | 0.59 | 0 | 1.95 | 1.95 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 84g | 76841 | 79840 | EIFS Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 4.5 | 0.75 |  | 1 | m2-LxW | 3.38 | 2023-02-18 | 2023-03-06 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 86.41 | 24.13 | 37.03 | 147.57 | 97.77 | 49.8 |  | 97.77 | 49.8 | 147.57 | 0 | 86.41 | 86.41 | 0 | 24.13 | 11.36 | 12.77 | 37.03 | 0 | 37.03 | 49.8 | 49.8 | 0
E11/K149/SK/dm/213 | HOTEL | 141f | 76842 | 79841 | EIFS Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 3 | 1 |  | 1 | m2-LxW | 3 | 2023-02-18 | 2023-03-06 | 100% | 100% | 100% | 2.4286 | 36.52 | 2.94 | 76.69 | 21.42 | 32.87 | 130.98 | 86.77 | 44.21 |  | 86.77 | 44.21 | 130.98 | 0 | 76.69 | 76.69 | 0 | 21.42 | 10.08 | 11.34 | 32.87 | 0 | 32.87 | 44.21 | 44.21 | 0
E11/K149/SK/dm/213 | HOTEL | 166 | 76843 | 79813 | KMEP Work | Level 28 | Tower | 1 | 1 | 0.9 | 3 | 2 | rm | 3 | 2023-02-20 | 2023-02-25 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 133.01 | 18.72 | 57.01 | 208.74 | 208.74 | 0 |  | 208.74 | 0 | 208.74 | 0 | 133.01 | 133.01 | 0 | 18.72 | 18.72 | 0 | 57.01 | 57.01 | 0 | 0 | 0 | 0
E11/K149/SK/dm/213 | HOTEL | 167 | 76844 | 79816 | KMEP Work | Level 28 | Tower | 1 | 0.9 | 0.6 | 3 | 1 | rm | 3 | 2023-02-21 | 2023-02-28 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 133.01 | 24.96 | 57.01 | 214.98 | 148.61 | 66.37 |  | 148.61 | 66.37 | 214.98 | 0 | 133.01 | 133.01 | 0 | 24.96 | 15.6 | 9.36 | 57.01 | 0 | 57.01 | 66.37 | 66.37 | 0
E11/K149/SK/dm/213 | HOTEL | 168 | 76845 |  | KMEP Work | Level 28 | Tower | 1 | 0.9 | 0.9 | 3 | 1 | rm | 3 | 2023-02-21 |  | 100% | 100% | 0% | 4.7143 | 63.34 | 7.28 | 133.01 | 102.96 | 0 | 235.97 | 148.61 | 87.36 |  | 148.61 | 87.36 | 235.97 | 0 | 133.01 | 133.01 | 0 | 102.96 | 15.6 | 87.36 | 0 | 0 | 0 | 87.36 | 87.36 | 0
E11/K149/SK/dm/213 | HOTEL | 169 | 76846 |  | Mast Climber | Level 27 | Independent | 1 | 5.3 | 0.9 | 1.3 | 1 | m2-LxH | 6.89 | 2023-02-22 |  | 100% | 100% | 0% | 4.5714 | 12.01 | 0.49 | 57.92 | 15.43 | 0 | 73.35 | 59.85 | 13.5 |  | 59.85 | 13.5 | 73.35 | 0 | 57.92 | 57.92 | 0 | 15.43 | 1.93 | 13.5 | 0 | 0 | 0 | 13.5 | 13.5 | 0
E11/K149/SK/dm/213 | HOTEL | 170 | 76847 | 79822 | KMEP Work | Level 28 | Tower | 1 | 1.3 | 1.3 | 3.3 | 2 | rm | 3.3 | 2023-02-23 | 2023-03-02 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 146.32 | 27.46 | 62.71 | 236.49 | 156.62 | 79.87 |  | 156.62 | 79.87 | 236.49 | 0 | 146.32 | 146.32 | 0 | 27.46 | 10.3 | 17.16 | 62.71 | 0 | 62.71 | 79.87 | 79.87 | 0
E11/K149/SK/dm/213 | HOTEL | 118a | 76848 |  | Edge Protection | Level 29 | Double Handrail | 1 | 14 |  | 1 |  | lm | 14 | 2023-02-23 |  | 100% | 100% | 0% | 4.4286 | 15 | 0.91 | 147 | 56.42 | 0 | 203.42 | 152.46 | 50.96 |  | 152.46 | 50.96 | 203.42 | 0 | 147 | 147 | 0 | 56.42 | 5.46 | 50.96 | 0 | 0 | 0 | 50.96 | 50.96 | 0
E11/K149/SK/dm/213 | HOTEL | 171 | 76849 | 79850 | GRC Panel Work | Level 22 | Independent | 1 | 6.1 | 1 | 1 | 1 | m2-LxH | 6.1 | 2023-02-24 | 2023-03-09 | 100% | 100% | 100% | 2 | 12.01 | 0.49 | 51.28 | 5.98 | 21.98 | 79.24 | 52.13 | 27.11 |  | 52.13 | 27.11 | 79.24 | 0 | 51.28 | 51.28 | 0 | 5.98 | 0.85 | 5.13 | 21.98 | 0 | 21.98 | 27.11 | 27.11 | 0
E11/K149/SK/dm/213 | HOTEL | 172 | 76850 | 79933 | GRC Panel Work | Level 25 | Independent | 1 | 6.1 | 1 | 1 | 1 | m2-LxH | 6.1 | 2023-02-24 | 2023-03-16 | 100% | 100% | 100% | 3 | 12.01 | 0.49 | 51.28 | 8.97 | 21.98 | 82.23 | 52.13 | 30.1 |  | 52.13 | 30.1 | 82.23 | 0 | 51.28 | 51.28 | 0 | 8.97 | 0.85 | 8.12 | 21.98 | 0 | 21.98 | 30.1 | 30.1 | 0
E11/K149/SMF/dm/756 | HOTEL | 173 | 77301 |  | GRC Panel Work | Level 26 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-02-24 |  | 100% | 100% | 0% | 4.2857 | 2022.88 | 17.43 | 1416.02 | 74.7 | 0 | 1490.72 | 1421 | 69.72 | Tas Quote 2439-35-1 | 1421 | 69.72 | 1490.72 | 0 | 1416.02 | 1416.02 | 0 | 74.7 | 4.98 | 69.72 | 0 | 0 | 0 | 69.72 | 69.72 | 0
E11/K149/SK/dm/213 | HOTEL | 174 | 77304 |  | KMEP Work | Level 28 | Tower | 1 | 1.3 | 1.3 | 2.8 | 1 | rm | 2.8 | 2023-02-25 |  | 100% | 100% | 0% | 4.1429 | 63.34 | 7.28 | 124.15 | 84.45 | 0 | 208.6 | 127.06 | 81.54 |  | 127.06 | 81.54 | 208.6 | 0 | 124.15 | 124.15 | 0 | 84.45 | 2.91 | 81.54 | 0 | 0 | 0 | 81.54 | 81.54 | 0
E11/K149/SK/dm/213 | HOTEL | 175 | 77305 | 79839 | KMEP Work | Level 28 | Tower | 1 | 0.9 | 0.6 | 2.8 | 1 | rm | 2.8 | 2023-02-25 | 2023-03-08 | 100% | 100% | 100% | 1.7143 | 63.34 | 7.28 | 124.15 | 34.94 | 53.21 | 212.3 | 127.06 | 85.24 |  | 127.06 | 85.24 | 212.3 | 0 | 124.15 | 124.15 | 0 | 34.94 | 2.91 | 32.03 | 53.21 | 0 | 53.21 | 85.24 | 85.24 | 0
E11/K149/SK/dm/213 | HOTEL | 176 | 77306 |  | KMEP Work | Level 28 | Tower | 1 | 1.8 | 1.3 | 3.5 | 2 | rm | 3.5 | 2023-02-25 |  | 100% | 100% | 0% | 4.1429 | 63.34 | 7.28 | 155.18 | 105.56 | 0 | 260.74 | 158.82 | 101.92 |  | 158.82 | 101.92 | 260.74 | 0 | 155.18 | 155.18 | 0 | 105.56 | 3.64 | 101.92 | 0 | 0 | 0 | 101.92 | 101.92 | 0
E11/K149/SK/dm/213 | HOTEL | 177 | 77307 | 79821 | KMEP Work | Level 28 | Tower | 1 | 1.3 | 1.3 | 3.5 | 2 | rm | 3.5 | 2023-02-25 | 2023-03-02 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 155.18 | 21.84 | 66.51 | 243.53 | 158.82 | 84.71 |  | 158.82 | 84.71 | 243.53 | 0 | 155.18 | 155.18 | 0 | 21.84 | 3.64 | 18.2 | 66.51 | 0 | 66.51 | 84.71 | 84.71 | 0
E11/K149/SK/dm/213 | RESIDENCE | 260 | 77407 | 82106 | Staircase 4 For Fire Line Work | Level 3 | Independent | 1 | 7.7 | 0.9 | 2 | 1 | m2-LxH | 15.4 | 2023-02-27 | 2023-03-18 | 100% | 100% | 100% | 2.8571 | 12.01 | 0.49 | 129.47 | 21.56 | 55.49 | 206.52 |  | 206.52 |  |  | 206.52 | 206.52 | 0 | [5 empty] | 80652.83 |  |  | 29698.69 | 110351.52
E11/K149/SK/dm/213 | RESIDENCE | 260a | 77408 | 82107 | Staircase 4 For Fire Line Work | Level 3 | Tower | 1 | 2.5 | 0.9 | 2 | 1 | rm | 2 | 2023-02-27 | 2023-03-18 | 100% | 100% | 100% | 2.8571 | 63.34 | 7.28 | 88.68 | 41.6 | 38 | 168.28 |  | 168.28 |  |  | 168.28 | 168.28 | 0
E11/K149/SK/dm/213 | RESIDENCE | 261 | 77409 |  | Glass Line work | Level 24 | Tower | 1 | 2.5 | 1.3 | 2 | 1 | rm | 2 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 63.34 | 7.28 | 88.68 | 54.08 | 0 | 142.76 |  | 142.76 |  |  | 142.76 | 142.76 | 0
E11/K149/SK/dm/213 | RESIDENCE | 262 | 77410 |  | Staircase - 5 Painting work | Ground Level | Independent | 1 | 7.5 | 0.9 | 1.7 | 1 | m2-LxH | 12.75 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 12.01 | 0.49 | 107.19 | 23.21 | 0 | 130.4 |  | 130.4 |  |  | 130.4 | 130.4 | 0
E11/K149/SK/dm/213 | RESIDENCE | 262a | 77410 |  | Staircase - 5 Painting work | Ground Level | Additional Boarding | 1 | 2.5 | 0.9 |  | 1 | m2-LxW | 2.25 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 6.63 | 0.7 | 10.44 | 5.85 | 0 | 16.29 |  | 16.29 |  |  | 16.29 | 16.29 | 0
E11/K149/SK/dm/213 | RESIDENCE | 263 | 77411 | 79862 | Marble work | Ground Level | Tower | 1 | 2.5 | 1.3 | 2.2 | 2 | rm | 2.2 | 2023-02-28 | 2023-03-07 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 97.54 | 18.3 | 41.8 | 157.64 |  | 157.64 |  |  | 157.64 | 157.64 | 0
E11/K149/SK/dm/213 | RESIDENCE | 264 | 77412 | 79863 | Marble work | Ground Level | Tower | 1 | 2.5 | 1 | 2.2 | 2 | rm | 2.2 | 2023-02-28 | 2023-03-07 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 97.54 | 18.3 | 41.8 | 157.64 |  | 157.64 |  |  | 157.64 | 157.64 | 0
E11/K149/SK/dm/213 | RESIDENCE | 257b | 77413 | 79864 | Staircase 4 For Fire Line Work | Ground Level | Independent | 1 | 7.7 | 0.9 | 2 | 1 | m2-LxH | 15.4 | 2023-02-28 | 2023-03-07 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 129.47 | 8.62 | 55.49 | 193.58 |  | 193.58 |  |  | 193.58 | 193.58 | 0
E11/K149/SK/dm/767 | RESIDENCE | 265 | 77414 |  | Loading Platform | Ground Level | Design 1399-47a | 1 |  |  |  |  | unit | 1 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 12211.06 | 812.7 | 8547.74 | 3018.6 | 0 | 11566.34 |  | 11566.34 | Tas Quote 2439-36-1 |  | 11566.34 | 11566.34 | 0
E11/K149/SK/dm/213 | RESIDENCE | 266 | 77415 | 82184 | Access Scaffold | Level 29 | Tower | 1 | 1.8 | 1 | 1 | 1 | rm | 1 | 2023-02-28 | 2023-03-02 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 44.34 | 3.12 | 19 | 66.46 |  | 66.46 |  |  | 66.46 | 66.46 | 0
E11/K149/SK/dm/213 | RESIDENCE | 267 | 77416 |  | Electrical Work | Ground Level | Independent 1.8m wide | 1 | 3.4 | 2.5 | 3.8 | 1 | m2-LxH | 12.92 | 2023-03-03 |  | 100% | 100% | 0% | 3.2857 | 16.76 | 0.77 | 151.58 | 32.69 | 0 | 184.27 |  | 184.27 |  |  | 184.27 | 184.27 | 0
E11/K149/SK/dm/213 | RESIDENCE | 268 | 77417 |  | Electrical Work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.7 | 1 | rm | 3.7 | 2023-03-03 |  | 100% | 100% | 0% | 3.2857 | 63.34 | 7.28 | 164.05 | 88.5 | 0 | 252.55 |  | 252.55 |  |  | 252.55 | 252.55 | 0
E11/K149/SK/dm/213 | RESIDENCE | 269 | 77418 | 79861 | Housekeeping Lobby Sealnt work | Ground Level | Tower | 1 | 1.8 | 1.8 | 2.5 | 1 | rm | 2.5 | 2023-03-04 | 2023-03-06 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 47.51 | 166.16 |  | 166.16 |  |  | 166.16 | 166.16 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a11 | 77419 | 79884 | Glass work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 7 | 0.9 | 1 | 1 | m2-LxW | 6.3 | 2023-03-06 | 2023-03-18 | 100% | 100% | 100% | 1.8571 | 36.52 | 2.94 | 161.05 | 34.4 | 69.02 | 264.47 |  | 264.47 |  |  | 264.47 | 264.47 | 0
E11/K149/SK/dm/213 | RESIDENCE | 270 | 77420 |  | Electrical work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2023-03-06 |  | 100% | 100% | 0% | 2.8571 | 63.34 | 7.28 | 155.18 | 72.8 | 0 | 227.98 |  | 227.98 |  |  | 227.98 | 227.98 | 0
E11/K149/SK/dm/213 | RESIDENCE | 271 | 77421 |  | Electrical work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2023-03-06 |  | 100% | 100% | 0% | 2.8571 | 63.34 | 7.28 | 155.18 | 72.8 | 0 | 227.98 |  | 227.98 |  |  | 227.98 | 227.98 | 0
E11/K149/SK/dm/213 | RESIDENCE | 272 | 77422 |  | Support tower for Edge Protection | Ground Level | Buttress | 1 | 2.5 | 1.3 | 5 | 1 | m3 | 16.25 | 2023-03-07 |  | 100% | 100% | 0% | 2.7143 | 5.29 | 0.35 | 60.17 | 15.44 | 0 | 75.61 |  | 75.61 |  |  | 75.61 | 75.61 | 0
E11/K149/SK/dm/213 | RESIDENCE | 272 | 77422 |  | Edge Protection | Ground Level | Double Handrail | 1 | 16 |  | 1 |  | lm | 16 | 2023-03-07 |  | 100% | 100% | 0% | 2.7143 | 15 | 0.91 | 168 | 39.52 | 0 | 207.52 |  | 207.52 |  |  | 207.52 | 207.52 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1z | 77423 | 82113 | Glass work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 20 | 0.5 | 1 | 1 | m2-LxW | 10 | 2023-03-08 | 2023-03-18 | 100% | 100% | 100% | 1.5714 | 32.75 | 1.05 | 229.25 | 16.5 | 98.25 | 344 |  | 344 |  |  | 344 | 344 | 0
E11/K149/SK/dm/213 | RESIDENCE | 273 | 77424 | 82135 | Staircase 4 For wall repairing work | Ground Level | Tower | 1 | 2.5 | 1.3 | 5.3 | 2 | rm | 5.3 | 2023-03-08 | 2023-03-24 | 100% | 100% | 100% | 2.4286 | 63.34 | 7.28 | 234.99 | 93.7 | 100.71 | 429.4 |  | 429.4 |  |  | 429.4 | 429.4 | 0
E11/K149/SK/dm/213 | RESIDENCE | 273 | 77424 | 82135 | Staircase 4 For wall repairing work | Ground Level | Additional Boarding | 1 | 2.5 | 1.3 | 1 | 1 | m2-LxW | 3.25 | 2023-03-08 | 2023-03-24 | 100% | 100% | 100% | 2.4286 | 6.63 | 0.7 | 15.08 | 5.53 | 6.46 | 27.07 |  | 27.07 |  |  | 27.07 | 27.07 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1a1 | 77425 | 79883 | Glass work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 20 | 0.5 | 1 | 1 | m2-LxW | 10 | 2023-03-09 | 2023-03-18 | 100% | 100% | 100% | 1.4286 | 32.75 | 1.05 | 229.25 | 15 | 98.25 | 342.5 |  | 342.5 |  |  | 342.5 | 342.5 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 c | 77426 |  | Ceiling work | Level 31 | Birdcage | 1 | 6.3 | 3.6 | 4.5 | 1 | m3 | 102.06 | 2023-03-10 |  | 100% | 100% | 0% | 2.2857 | 7.08 | 0.49 | 505.81 | 114.31 | 0 | 620.12 |  | 620.12 |  |  | 620.12 | 620.12 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 d | 77426 |  | Ceiling work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 6 | 0.5 |  | 1 | m2-LxW | 3 | 2023-03-10 |  | 100% | 100% | 0% | 2.2857 | 32.75 | 1.05 | 68.78 | 7.2 | 0 | 75.98 |  | 75.98 |  |  | 75.98 | 75.98 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145e | 77427 |  | Ceiling work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 4 | 0.75 |  | 1 | m2-LxW | 3 | 2023-03-10 |  | 100% | 100% | 0% | 2.2857 | 36.52 | 2.94 | 76.69 | 20.16 | 0 | 96.85 |  | 96.85 |  |  | 96.85 | 96.85 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 f | 77427 |  | Ceiling work | Level 31 | Additional Boarding | 1 | 4 | 1 |  | 1 | m2-LxW | 4 | 2023-03-10 |  | 100% | 100% | 0% | 2.2857 | 6.63 | 0.7 | 18.56 | 6.4 | 0 | 24.96 |  | 24.96 |  |  | 24.96 | 24.96 | 0
E11/K149/SK/dm/213 | RESIDENCE | 222 b | 77428 | 351 | Concrete Cutting Work | Level 28 | Cantilever (0.5 > 1.2m width) | 1 | 3 | 1 |  | 1 | m2-LxW | 3 | 2023-03-10 | 2023-03-23 | 100% | 100% | 100% | 2 | 36.52 | 2.94 | 76.69 | 17.64 | 32.87 | 127.2 |  | 127.2 |  |  | 127.2 | 127.2 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1a2 | 77429 |  | Ceiling work | Level 31 | Additional Boarding | 1 | 11.3 | 1.5 |  | 1 | m2-LxW | 16.95 | 2023-03-11 |  | 100% | 100% | 0% | 2.1429 | 6.63 | 0.7 | 78.66 | 25.43 | 0 | 104.09 |  | 104.09 |  |  | 104.09 | 104.09 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 g | 77430 |  | Ceiling work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 1.5 | 0.5 |  | 1 | m2-LxW | 0.75 | 2023-03-11 |  | 100% | 100% | 0% | 2.1429 | 32.75 | 1.05 | 17.19 | 1.69 | 0 | 18.88 |  | 18.88 |  |  | 18.88 | 18.88 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 | 77431 |  | EIFS Work | Level 31 | Independent | 1 | 7.5 | 0.9 | 5.5 | 1 | m2-LxH | 41.25 | 2023-03-13 |  | 100% | 100% | 0% | 1.8571 | 12.01 | 0.49 | 346.79 | 37.54 | 0 | 384.33 |  | 384.33 |  |  | 384.33 | 384.33 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 | 77431 |  | EIFS Work | Level 31 | Additional Boarding | 1 | 7.5 | 0.9 | 1 | 1 | m2-LxW | 6.75 | 2023-03-13 |  | 100% | 100% | 0% | 1.8571 | 6.63 | 0.7 | 31.33 | 8.78 | 0 | 40.11 |  | 40.11 |  |  | 40.11 | 40.11 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274a | 77432 |  | EIFS Work | Level 31 | Independent | 1 | 9.3 | 0.9 | 2 | 1 | m2-LxH | 18.6 | 2023-03-13 |  | 100% | 100% | 0% | 1.8571 | 12.01 | 0.49 | 156.37 | 16.93 | 0 | 173.3 |  | 173.3 |  |  | 173.3 | 173.3 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274b | 77433 |  | EIFS Work | Level 31 | Independent | 1 | 8 | 0.5 | 1.5 | 1 | m2-LxH | 12 | 2023-03-13 |  | 100% | 100% | 0% | 1.8571 | 12.01 | 0.49 | 100.88 | 10.92 | 0 | 111.8 |  | 111.8 |  |  | 111.8 | 111.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 202f | 77434 |  | GRC work | Level 10 | Cantilever (0.5 > 1.2m width) | 1 | 4.5 | 0.75 |  | 1 | m2-LxW | 3.38 | 2023-03-13 |  | 100% | 100% | 0% | 1.8571 | 36.52 | 2.94 | 86.41 | 18.45 | 0 | 104.86 |  | 104.86 |  |  | 104.86 | 104.86 | 0
E11/K149/SK/dm/213 | RESIDENCE | 273a | 77435 | 82108 | Staircase 4 wall repair work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1 | 1 |  | 1 | m2-LxW | 1 | 2023-03-13 | 2023-03-18 | 100% | 100% | 100% | 0.85714 | 36.52 | 2.94 | 25.56 | 2.52 | 10.96 | 39.04 |  | 39.04 |  |  | 39.04 | 39.04 | 0
E11/K149/SK/dm/213 | RESIDENCE | 172c | 77436 | 82102 | Support tower for Edge Protection | Ground Level | Buttress | 1 | 2.5 | 1.3 | 2 |  | m3 | 6.5 | 2023-03-13 | 2023-03-18 | 100% | 100% | 100% | 0.85714 | 5.29 | 0.35 | 24.07 | 1.95 | 10.32 | 36.34 |  | 36.34 |  |  | 36.34 | 36.34 | 0
E11/K149/SK/dm/213 | RESIDENCE | 172c | 77436 | 82102 | Edge Protection | Ground Level | Double Handrail | 1 | 24 |  | 1 |  | lm | 24 | 2023-03-13 | 2023-03-18 | 100% | 100% | 100% | 0.85714 | 15 | 0.91 | 252 | 18.72 | 108 | 378.72 |  | 378.72 |  |  | 378.72 | 378.72 | 0
E11/K149/SK/dm/213 | RESIDENCE | 173c | 77437 |  | Edge Protection | Ground Level | Double Handrail | 1 | 20 |  | 1 |  | lm | 20 | 2023-03-13 |  | 100% | 100% | 0% | 1.8571 | 15 | 0.91 | 210 | 33.8 | 0 | 243.8 |  | 243.8 |  |  | 243.8 | 243.8 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a12 | 77438 | 79882 | Glass work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 4 | 0.75 |  | 1 | m2-LxW | 3 | 2023-03-14 | 2023-03-16 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 76.69 | 3.78 | 32.87 | 113.34 |  | 113.34 |  |  | 113.34 | 113.34 | 0
E11/K149/SK/dm/213 | RESIDENCE | 275 | 77440 | 82110 | Marble work | Ground Level | Independent | 1 | 5 | 1.3 | 3 | 1 | m2-LxH | 15 | 2023-03-18 | 2023-03-21 | 100% | 100% | 100% | 0.57143 | 12.01 | 0.49 | 126.11 | 4.2 | 54.05 | 184.36 |  | 184.36 |  |  | 184.36 | 184.36 | 0
E11/K149/SK/dm/213 | RESIDENCE | 275 | 77440 | 82110 | Marble work | Ground Level | Additional Boarding | 1 | 5 | 1.3 |  | 1 | m2-LxW | 6.5 | 2023-03-18 | 2023-03-21 | 100% | 100% | 100% | 0.57143 | 6.63 | 0.7 | 30.17 | 2.6 | 12.93 | 45.7 |  | 45.7 |  |  | 45.7 | 45.7 | 0
E11/K149/SK/dm/213 | RESIDENCE | 273b | 77439 | 82135 | Stair 4 Ceiling work | Ground Level | Tower | 1 | 2.5 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-03-17 | 2023-03-24 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 66.51 | 12.48 | 28.5 | 107.49 |  | 107.49 |  |  | 107.49 | 107.49 | 0
E11/K149/SK/dm/213 | RESIDENCE | 276 | 77441 |  | KMEP Work | Basement 1 | Independent 1.8m wide | 1 | 7.4 | 1.8 | 4 | 1 | m2-LxH | 29.6 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 16.76 | 0.77 | 347.27 | 26.05 | 0 | 373.32 |  | 373.32 |  |  | 373.32 | 373.32 | 0
E11/K149/SK/dm/213 | RESIDENCE | 277 | 77442 |  | KMEP Work | Basement 1 | Independent 1.8m wide | 1 | 8.1 | 1.8 | 5 | 1 | m2-LxH | 40.5 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 16.76 | 0.77 | 475.15 | 35.64 | 0 | 510.79 |  | 510.79 |  |  | 510.79 | 510.79 | 0
E11/K149/SK/dm/213 | RESIDENCE | 278 | 77443 |  | GRC work | Ground Level | Tower | 1 | 1.8 | 1.3 | 4.5 | 1 | rm | 4.5 | 2023-03-20 |  | 100% | 100% | 0% | 0.85714 | 63.34 | 7.28 | 199.52 | 28.08 | 0 | 227.6 |  | 227.6 |  |  | 227.6 | 227.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 278 | 77443 |  | GRC work | Ground Level | Additional Boarding | 1 | 1.8 | 1.3 | 1 | 1 | m2-LxW | 2.34 | 2023-03-20 |  | 100% | 100% | 0% | 0.85714 | 6.63 | 0.7 | 10.86 | 1.4 | 0 | 12.26 |  | 12.26 |  |  | 12.26 | 12.26 | 0
E11/K149/SK/dm/213 | RESIDENCE | 279 | 77444 |  | KMEP Work | Basement 2 | Tower | 1 | 1.8 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 0 | 74.31 |  | 74.31 |  |  | 74.31 | 74.31 | 0
E11/K149/SK/dm/213 | RESIDENCE | 280 | 77445 |  | Mast climber Access | Level 29 | Tower | 1 | 1.8 | 1.3 | 1.5 | 1 | rm | 1.5 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 66.51 | 7.8 | 0 | 74.31 |  | 74.31 |  |  | 74.31 | 74.31 | 0
E11/K149/HW/DM/815 | RESIDENCE | 281 | 77446 |  | Loading Platform for Cherry picker | Level 4 | Design 1399-50 | 1 |  |  |  |  | unit | 1 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 15834.81 | 279.86 | 11084.37 | 199.9 | 0 | 11284.27 |  | 11284.27 | Tas Quote 2439-38-1 |  | 11284.27 | 11284.27 | 0
E11/K149/SK/dm/213 | RESIDENCE | 282 | 77447 |  | KMEP Work | Basement 1 | Independent | 1 | 4 | 1.3 | 3.5 | 1 | m2-LxH | 14 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 12.01 | 0.49 | 117.7 | 4.9 | 0 | 122.6 |  | 122.6 |  |  | 122.6 | 122.6 | 0
E11/K149/SK/dm/213 | RESIDENCE | 282a | 77448 |  | KMEP Work | Basement 1 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 63.34 | 7.28 | 155.18 | 18.2 | 0 | 173.38 |  | 173.38 |  |  | 173.38 | 173.38 | 0
E11/K149/SK/dm/213 | RESIDENCE | 282a | 77448 |  | KMEP Work | Basement 1 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 6.63 | 0.7 | 20.88 | 2.25 | 0 | 23.13 |  | 23.13 |  |  | 23.13 | 23.13 | 0
E11/K149/SK/dm/213 | RESIDENCE | 283 | 77449 |  | KMEP Work | Basement 2 | Birdcage | 1 | 6.8 | 3.5 | 1.6 | 1 | m3 | 38.08 | 2023-03-21 |  | 100% | 100% | 0% | 0.71429 | 7.08 | 0.49 | 188.72 | 13.33 | 0 | 202.05 |  | 202.05 |  |  | 202.05 | 202.05 | 0
E11/K149/SK/SR/517 | RESIDENCE | 284 | 77450 |  | Ceiling work | Level 27 | Design 1399-35b | 1 | 4.6 | 1.3 | 1.8 | 1 | unit | 1 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 1772.58 | 52.19 | 1240.81 | 29.82 | 0 | 1270.63 |  | 1270.63 | Tas Quote 2439-25-1 (item#5) |  | 1270.63 | 1270.63 | 0
E11/K149/SK/dm/213 | RESIDENCE | 285 | 77351 |  | KMEP Work | Basement 2 | Independent 1.8m wide | 1 | 6.8 | 1.8 | 1.8 | 1 | m2-LxH | 12.24 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 16.76 | 0.77 | 143.6 | 5.39 | 0 | 148.99 |  | 148.99 |  |  | 148.99 | 148.99 | 0
E11/K149/SK/dm/213 | RESIDENCE | 1a3 | 77352 | 82146 | Glass work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1.5 | 1 | 1 | m2-LxW | 2.7 | 2023-03-22 | 2023-03-24 | 100% | 100% | 100% | 0.42857 | 36.52 | 2.94 | 69.02 | 3.4 | 29.58 | 102 |  | 102 |  |  | 102 | 102 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a13 | 77353 | 82130 | Glass work | Level 30 | Cantilever (0.5 > 1.2m width) | 1 | 5.4 | 0.75 | 1 | 1 | m2-LxW | 4.05 | 2023-03-22 | 2023-03-23 | 100% | 100% | 100% | 0.28571 | 36.52 | 2.94 | 103.53 | 3.4 | 44.37 | 151.3 |  | 151.3 |  |  | 151.3 | 151.3 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a14 | 77354 | 82145 | Glass work | Level 30 | Cantilever (0 < 0.5m width) | 1 | 4 | 0.25 | 1 | 1 | m2-LxW | 1 | 2023-03-22 | 2023-03-24 | 100% | 100% | 100% | 0.42857 | 32.75 | 1.05 | 22.93 | 0.45 | 9.83 | 33.21 |  | 33.21 |  |  | 33.21 | 33.21 | 0
E11/K149/SK/dm/213 | RESIDENCE | 8 a15 | 77354 | 82145 | Glass work | Level 30 | Additional Boarding | 1 | 4 | 0.75 | 1 | 1 | m2-LxW | 3 | 2023-03-22 | 2023-03-24 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 13.92 | 0.9 | 5.97 | 20.79 |  | 20.79 |  |  | 20.79 | 20.79 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 g | 77355 |  | Glass work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 2.5 | 1 | 1 | 1 | m2-LxW | 2.5 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 36.52 | 2.94 | 63.91 | 4.2 | 0 | 68.11 |  | 68.11 |  |  | 68.11 | 68.11 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 h | 77355 |  | Glass work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.5 | 1 | 1 | m2-LxW | 0.9 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 32.75 | 1.05 | 20.63 | 0.54 | 0 | 21.17 |  | 21.17 |  |  | 21.17 | 21.17 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 c | 77356 |  | EIFS Work | Level 31 | Tower | 1 | 2.5 | 1.5 | 6 | 1 | rm | 6 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 266.03 | 24.96 | 0 | 290.99 |  | 290.99 |  |  | 290.99 | 290.99 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 c | 77356 |  | EIFS Work | Level 31 | Additional Boarding | 2 | 2.5 | 1.5 | 1 | 2 | m2-LxW | 7.5 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 6.63 | 0.7 | 34.81 | 3 | 0 | 37.81 |  | 37.81 |  |  | 37.81 | 37.81 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274d | 77356 |  | EIFS Work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 1 | 0.5 | 1 | 1 | m2-LxW | 0.5 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 32.75 | 1.05 | 11.46 | 0.3 | 0 | 11.76 |  | 11.76 |  |  | 11.76 | 11.76 | 0
E11/K149/SK/dm/213 | RESIDENCE | 145 i | 77357 |  | ceiling work | Level 31 | Cantilever (0 < 0.5m width) | 1 | 9.5 | 0.5 | 1 | 1 | m2-LxW | 4.75 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 32.75 | 1.05 | 108.89 | 2.85 | 0 | 111.74 |  | 111.74 |  |  | 111.74 | 111.74 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 e | 77358 |  | EIFS Work | Level 31 | Independent | 1 | 7 | 1.2 | 2 | 1 | m2-LxH | 14 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 12.01 | 0.49 | 117.7 | 3.92 | 0 | 121.62 |  | 121.62 |  |  | 121.62 | 121.62 | 0
E11/K149/SK/dm/213 | RESIDENCE | 278 a | 77359 |  | GRC work | Ground Level | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 0.75 | 1 | 1 | m2-LxW | 1.35 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 36.52 | 2.94 | 34.51 | 2.27 | 0 | 36.78 |  | 36.78 |  |  | 36.78 | 36.78 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 f | 77361 |  | EIFS Work | Level 31 | Tower | 1 | 1.3 | 1 | 4 | 1 | rm | 4 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 177.35 | 16.64 | 0 | 193.99 |  | 193.99 |  |  | 193.99 | 193.99 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 g | 77361 |  | EIFS Work | Level 31 | Cantilever (0.5 > 1.2m width) | 1 | 1 | 0.75 | 1 | 1 | m2-LxW | 0.75 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 36.52 | 2.94 | 19.17 | 1.26 | 0 | 20.43 |  | 20.43 |  |  | 20.43 | 20.43 | 0
E11/K149/SK/dm/213 | RESIDENCE | 274 h | 77362 |  | EIFS Work | Level 31 | Tower | 1 | 1.5 | 1 | 2 | 1 | rm | 2 | 2023-03-22 |  | 100% | 100% | 0% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 0 | 97 |  | 97 |  |  | 97 | 97 | 0
E11/K149/SK/dm/213 | RESIDENCE | 286 | 77363 |  | Ceiling work | Level 28 | Independent | 1 | 2.8 | 1.3 | 2 | 1 | m2-LxH | 5.6 | 2023-03-23 |  | 100% | 100% | 0% | 0.42857 | 12.01 | 0.49 | 47.08 | 1.18 | 0 | 48.26 |  | 48.26 |  |  | 48.26 | 48.26 | 0
E11/K149/SK/dm/213 | RESIDENCE | 286 a | 77364 |  | Ceiling work | Level 28 | Cantilever (0 < 0.5m width) | 1 | 1.8 | 0.25 | 1 | 1 | m2-LxW | 0.45 | 2023-03-23 |  | 100% | 100% | 0% | 0.42857 | 32.75 | 1.05 | 10.32 | 0.2 | 0 | 10.52 |  | 10.52 |  |  | 10.52 | 10.52 | 0
E11/K149/SK/dm/213 | RESIDENCE | 287 | 77365 |  | Staircase 2 For plaster work | Level 3 | Tower | 1 | 1.3 | 0.9 | 2.5 | 1 | rm | 2.5 | 2023-03-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 110.85 | 5.2 | 0 | 116.05 |  | 116.05 |  |  | 116.05 | 116.05 | 0
E11/K149/SK/dm/213 | RESIDENCE | 288 | 77360 |  | Electrical work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2023-03-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 155.18 | 7.28 | 0 | 162.46 |  | 162.46 |  |  | 162.46 | 162.46 | 0
E11/K149/SK/dm/213 | RESIDENCE | 289 | 77366 |  | Kmep work | Basement 1 | Tower | 1 | 2.5 | 1.8 | 4.5 | 1 | rm | 4.5 | 2023-03-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 199.52 | 9.36 | 0 | 208.88 |  | 208.88 |  |  | 208.88 | 208.88 | 0
E11/K149/SK/dm/213 | RESIDENCE | 290 | 77367 |  | Electrical work | Ground Level | Tower | 1 | 2.5 | 2.5 | 3.5 | 1 | rm | 3.5 | 2023-03-24 |  | 100% | 100% | 0% | 0.28571 | 63.34 | 7.28 | 155.18 | 7.28 | 0 | 162.46 |  | 162.46 |  |  | 162.46 | 162.46 | 0
E11/K149/SK/dm/213 | HOTEL | 178 | 77308 | 79917 | Balcony Ceiling work | Level 15 | Independent | 1 | 5.3 | 0.9 | 1 | 1 | m2-LxH | 5.3 | 2023-02-27 | 2023-03-09 | 100% | 100% | 100% | 1.5714 | 12.01 | 0.49 | 44.56 | 4.08 | 19.1 | 67.74 |  | 67.74 |  |  | 67.74 | 67.74 | 0
E11/K149/NA/DM/762 | HOTEL | 179 | 77309 | 79945 | Slab Concret work | Basement 1 | Design 1399-49 | 1 | 3.1 | 2.3 | 10.5 |  | unit | 1 | 2023-02-27 | 2023-03-25 | 100% | 100% | 100% | 3.8571 | 2503.64 | 190.87 | 1752.55 | 736.21 | 751.09 | 3239.85 |  | 3239.85 | Tas Quote 2439-37-1 |  | 3239.85 | 3239.85 | 0
E11/K149/SK/dm/213 | HOTEL | 180 | 77310 | 79932 | KID work | Level 29 | Tower | 1 | 1.8 | 0.9 | 2 | 1 | rm | 2 | 2023-02-28 | 2023-03-20 | 100% | 100% | 100% | 3 | 63.34 | 7.28 | 88.68 | 43.68 | 38 | 170.36 |  | 170.36 |  |  | 170.36 | 170.36 | 0
E11/K149/SMF/dm/756 | HOTEL | 181 | 77311 |  | GRC Panel Work | Level 23 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 2022.88 | 17.43 | 1416.02 | 64.74 | 0 | 1480.76 |  | 1480.76 | Tas Quote 2439-35-1 |  | 1480.76 | 1480.76 | 0
E11/K149/SK/dm/213 | HOTEL | 60b | 77312 |  | Access For Material Shifting | Level 22 | Tower | 1 | 1.5 | 1 | 1.5 | 1 | rm | 1.5 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 63.34 | 7.28 | 66.51 | 40.56 | 0 | 107.07 |  | 107.07 |  |  | 107.07 | 107.07 | 0
E11/K149/SK/dm/213 | HOTEL | 182 | 77313 | 79838 | Bathrooms Corridoor KMEP work | Level 28 | Tower | 1 | 2.5 | 1 | 4 | 1 | rm | 4 | 2023-02-28 | 2023-03-07 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 76.01 | 286.64 |  | 286.64 |  |  | 286.64 | 286.64 | 0
E11/K149/SK/dm/213 | HOTEL | 182 | 77313 | 79838 | Bathrooms Corridoor KMEP work | Level 28 | Additional Boarding | 1 | 2.5 | 1 |  | 1 | m2-LxW | 2.5 | 2023-02-28 | 2023-03-07 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 11.6 | 2 | 4.97 | 18.57 |  | 18.57 |  |  | 18.57 | 18.57 | 0
E11/K149/SK/dm/213 | HOTEL | 182a | 77313 | 79838 | Bathrooms Corridoor KMEP work | Level 28 | Cantilever (0 < 0.5m width) | 1 | 2.5 | 0.5 | 1 | 1 | m2-LxW | 1.25 | 2023-02-28 | 2023-03-07 | 100% | 100% | 100% | 1.1429 | 32.75 | 1.05 | 28.66 | 1.5 | 12.28 | 42.44 |  | 42.44 |  |  | 42.44 | 42.44 | 0
E11/K149/SK/dm/213 | HOTEL | 183 | 77314 | 79931 | KMEP work | Level 28 | Tower | 1 | 1.3 | 1 | 3 | 1 | rm | 3 | 2023-02-28 | 2023-03-17 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 133.01 | 56.16 | 57.01 | 246.18 |  | 246.18 |  |  | 246.18 | 246.18 | 0
E11/K149/SK/dm/213 | HOTEL | 151b | 77315 |  | Swimming pool area | Level 29 | Double Handrail (hilti) | 1 | 20 |  | 1 |  | lm | 20 | 2023-02-28 |  | 100% | 100% | 0% | 3.7143 | 24 | 0.7 | 336 | 52 | 0 | 388 |  | 388 |  |  | 388 | 388 | 0
E11/K149/SK/dm/213 | HOTEL | 184 | 77316 |  | Lagauge Room KMEP work | Level 2 | Independent | 1 | 6.3 | 1.3 | 5 | 1 | m2-LxH | 31.5 | 2023-03-01 |  | 100% | 100% | 0% | 3.5714 | 12.01 | 0.49 | 264.82 | 55.13 | 0 | 319.95 |  | 319.95 |  |  | 319.95 | 319.95 | 0
E11/K149/SMF/dm/756 | HOTEL | 185 | 77317 | 79916 | GRC Panel Work | Level 24 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-03-01 | 2023-03-14 | 100% | 100% | 100% | 2 | 2022.88 | 17.43 | 1416.02 | 34.86 | 606.86 | 2057.74 |  | 2057.74 | Tas Quote 2439-35-1 |  | 2057.74 | 2057.74 | 0
E11/K149/SMF/dm/756 | HOTEL | 186 | 77318 |  | GRC Panel Work | Level 21 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-03-01 |  | 100% | 100% | 0% | 3.5714 | 2022.88 | 17.43 | 1416.02 | 62.25 | 0 | 1478.27 |  | 1478.27 | Tas Quote 2439-35-1 |  | 1478.27 | 1478.27 | 0
E11/K149/SK/dm/213 | HOTEL | 80g | 77319 |  | Marble work | Level 2 | Additional Boarding | 1 | 4.8 | 1.3 | 1 | 1 | m2-LxW | 6.24 | 2023-03-01 |  | 100% | 100% | 0% | 3.5714 | 6.63 | 0.7 | 28.96 | 15.6 | 0 | 44.56 |  | 44.56 |  |  | 44.56 | 44.56 | 0
E11/K149/SK/dm/213 | HOTEL | 80h | 77320 |  | Marble work | Level 2 | Tower | 1 | 1 | 1 | 5.5 | 3 | rm | 5.5 | 2023-03-01 |  | 100% | 100% | 0% | 3.5714 | 63.34 | 7.28 | 243.86 | 143 | 0 | 386.86 |  | 386.86 |  |  | 386.86 | 386.86 | 0
E11/K149/SK/dm/213 | HOTEL | 187 | 77321 | 79930 | KMEP Work | Level 28 | Tower | 1 | 2.5 | 0.9 | 3.5 | 1 | rm | 3.5 | 2023-03-02 | 2023-03-17 | 100% | 100% | 100% | 2.2857 | 63.34 | 7.28 | 155.18 | 58.24 | 66.51 | 279.93 |  | 279.93 |  |  | 279.93 | 279.93 | 0
E11/K149/SK/dm/213 | HOTEL | 187 | 77321 | 79930 | KMEP Work | Level 28 | Additional Boarding | 1 | 2.5 | 0.9 | 1 | 1 | m2-LxW | 2.25 | 2023-03-02 | 2023-03-17 | 100% | 100% | 100% | 2.2857 | 6.63 | 0.7 | 10.44 | 3.6 | 4.48 | 18.52 |  | 18.52 |  |  | 18.52 | 18.52 | 0
E11/K149/SK/dm/213 | HOTEL | 188 | 77322 |  | Roof Access | Roof | Tower | 1 | 2.5 | 1 | 2 | 1 | rm | 2 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 63.34 | 7.28 | 88.68 | 49.92 | 0 | 138.6 |  | 138.6 |  |  | 138.6 | 138.6 | 0
E11/K149/SK/dm/213 | HOTEL | 189 | 77324 | 79915 | Ceiling work | Level 13 | Tower | 1 | 2.5 | 1 | 1 | 1 | rm | 1 | 2023-03-02 | 2023-03-09 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 44.34 | 8.32 | 19 | 71.66 |  | 71.66 |  |  | 71.66 | 71.66 | 0
E11/K149/SK/dm/213 | HOTEL | 190 | 77325 | 79836 | Lift Shaft Repairing work | Basement 1 | Tower | 1 | 1.8 | 1.8 | 9 | 1 | rm | 9 | 2023-03-02 | 2023-03-07 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 399.04 | 56.16 | 171.02 | 626.22 |  | 626.22 |  |  | 626.22 | 626.22 | 0
E11/K149/SK/dm/213 | HOTEL | 190 | 77325 | 79836 | Lift Shaft Repairing work | Basement 1 | Additional Boarding | 1 | 1.8 | 1.8 | 1 | 1 | m2-LxW | 3.24 | 2023-03-02 | 2023-03-07 | 100% | 100% | 100% | 0.85714 | 6.63 | 0.7 | 15.04 | 1.94 | 6.44 | 23.42 |  | 23.42 |  |  | 23.42 | 23.42 | 0
E11/K149/SK/dm/213 | HOTEL | 191 | 77331 |  | EIFS Work | Level 30 | Tower | 1 | 2.5 | 1.5 | 3 | 1 | rm | 3 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 63.34 | 7.28 | 133.01 | 74.88 | 0 | 207.89 |  | 207.89 |  |  | 207.89 | 207.89 | 0
E11/K149/SK/dm/213 | HOTEL | 192 | 77326 | 79837 | Toilet Area KMEP work | Level 28 | Tower | 1 | 0.9 | 0.9 | 2.5 | 1 | rm | 2.5 | 2023-03-02 | 2023-03-08 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 110.85 | 18.2 | 47.51 | 176.56 |  | 176.56 |  |  | 176.56 | 176.56 | 0
E11/K149/SK/dm/213 | HOTEL | 193 | 77328 | 79929 | Treatment Room KMEP work | Level 28 | Independent | 1 | 3.5 | 1 | 3 | 1 | m2-LxH | 10.5 | 2023-03-02 | 2023-03-20 | 100% | 100% | 100% | 2.7143 | 12.01 | 0.49 | 88.27 | 13.97 | 37.83 | 140.07 |  | 140.07 |  |  | 140.07 | 140.07 | 0
E11/K149/SK/dm/213 | HOTEL | 194 | 77329 |  | Ceiling Work | Level 17 | Independent | 1 | 5 | 0.9 | 2 | 1 | m2-LxH | 10 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 12.01 | 0.49 | 84.07 | 16.8 | 0 | 100.87 |  | 100.87 |  |  | 100.87 | 100.87 | 0
E11/K149/SK/dm/213 | HOTEL | 80i | 77330 |  | Marble work | Level 2 | Tower | 1 | 2.5 | 1.8 | 5.5 | 1 | rm | 5.5 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 63.34 | 7.28 | 243.86 | 137.28 | 0 | 381.14 |  | 381.14 |  |  | 381.14 | 381.14 | 0
E11/K149/SK/dm/213 | HOTEL | 80i | 77330 |  | Marble work | Level 2 | Additional Boarding | 1 | 2.5 | 1.8 | 1 | 1 | m2-LxW | 4.5 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 6.63 | 0.7 | 20.88 | 10.8 | 0 | 31.68 |  | 31.68 |  |  | 31.68 | 31.68 | 0
E11/K149/SK/dm/213 | HOTEL | 80j | 77330 |  | Marble work | Level 2 | Cantilever (0 < 0.5m width) | 3 | 4.8 | 0.5 | 1 | 3 | m2-LxW | 7.2 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 32.75 | 1.05 | 165.06 | 25.92 | 0 | 190.98 |  | 190.98 |  |  | 190.98 | 190.98 | 0
E11/K149/SK/dm/213 | HOTEL | 151c | 77332 |  | Edge Protection | Level 29 | Double Handrail | 1 | 27 |  | 1 |  | lm | 27 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 15 | 0.91 | 283.5 | 84.24 | 0 | 367.74 |  | 367.74 |  |  | 367.74 | 367.74 | 0
E11/K149/SK/dm/213 | HOTEL | 146b | 77333 |  | EIFS work | Level 30 | Tower | 1 | 2 | 1 | 2 | 1 | rm | 2 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 63.34 | 7.28 | 88.68 | 49.92 | 0 | 138.6 |  | 138.6 |  |  | 138.6 | 138.6 | 0
E11/K149/SK/dm/213 | HOTEL | 146b | 77333 |  | EIFS work | Level 30 | Additional Boarding | 1 | 2 | 1 |  | 1 | m2-LxW | 2 | 2023-03-02 |  | 100% | 100% | 0% | 3.4286 | 6.63 | 0.7 | 9.28 | 4.8 | 0 | 14.08 |  | 14.08 |  |  | 14.08 | 14.08 | 0
E11/K149/SK/dm/213 | HOTEL | 195 | 77334 | 79901 | Staircase 7 For Electrical Work | Ground Level | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2023-03-06 | 2023-03-11 | 100% | 100% | 100% | 0.85714 | 63.34 | 7.28 | 155.18 | 21.84 | 66.51 | 243.53 |  | 243.53 |  |  | 243.53 | 243.53 | 0
E11/K149/SK/dm/213 | HOTEL | 196 | 77335 | 79918 | Lift shaft -20 For Wall Reparing work | Basement 2 | Tower | 1 | 1.8 | 1.8 | 9 | 1 | rm | 9 | 2023-03-07 | 2023-03-11 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 399.04 | 46.8 | 171.02 | 616.86 |  | 616.86 |  |  | 616.86 | 616.86 | 0
E11/K149/SK/dm/213 | HOTEL | 196 | 77335 | 79918 | Lift shaft -20 For Wall Reparing work | Basement 2 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2023-03-07 | 2023-03-11 | 100% | 100% | 100% | 0.71429 | 6.63 | 0.7 | 30.07 | 3.24 | 12.89 | 46.2 |  | 46.2 |  |  | 46.2 | 46.2 | 0
E11/K149/SK/dm/213 | HOTEL | 197 | 77336 | 79943 | Pump Room For KMEP work | Level 28 | Tower | 1 | 2.5 | 1.8 | 3.5 | 1 | rm | 3.5 | 2023-03-07 | 2023-03-24 | 100% | 100% | 100% | 2.5714 | 63.34 | 7.28 | 155.18 | 65.52 | 66.51 | 287.21 |  | 287.21 |  |  | 287.21 | 287.21 | 0
E11/K149/SK/dm/213 | HOTEL | 198 | 77337 | 79928 | Lift shaft - 19 Wall Reparing work | Basement 2 | Tower | 1 | 1.8 | 1.8 | 9 | 1 | rm | 9 | 2023-03-07 | 2023-03-17 | 100% | 100% | 100% | 1.5714 | 63.34 | 7.28 | 399.04 | 102.96 | 171.02 | 673.02 |  | 673.02 |  |  | 673.02 | 673.02 | 0
E11/K149/SK/dm/213 | HOTEL | 198 | 77337 | 79928 | Lift shaft - 19 Wall Reparing work | Basement 2 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2023-03-07 | 2023-03-17 | 100% | 100% | 100% | 1.5714 | 6.63 | 0.7 | 30.07 | 7.13 | 12.89 | 50.09 |  | 50.09 |  |  | 50.09 | 50.09 | 0
E11/K149/SK/dm/213 | HOTEL | 79a | 77338 | 79914 | Ceiling work | Ground Level | Independent | 1 | 8 | 1.3 | 3.5 | 1 | m2-LxH | 28 | 2023-03-07 | 2023-03-15 | 100% | 100% | 100% | 1.2857 | 12.01 | 0.49 | 235.4 | 17.64 | 100.88 | 353.92 |  | 353.92 |  |  | 353.92 | 353.92 | 0
E11/K149/SK/dm/213 | HOTEL | 199 | 77339 |  | Electrical work | Ground Level | Tower | 1 | 2.5 | 2.5 | 4.5 | 1 | rm | 4.5 | 2023-03-08 |  | 100% | 100% | 0% | 2.5714 | 63.34 | 7.28 | 199.52 | 84.24 | 0 | 283.76 |  | 283.76 |  |  | 283.76 | 283.76 | 0
E11/K149/SK/dm/213 | HOTEL | 200 | 77340 | 79939 | Water meter room ceiling work | Level 1 | Tower | 1 | 2.5 | 1.5 | 2 | 1 | rm | 2 | 2023-03-08 | 2023-03-22 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 88.68 | 31.2 | 38 | 157.88 |  | 157.88 |  |  | 157.88 | 157.88 | 0
E11/K149/SMF/dm/756 | HOTEL | 201 | 77341 |  | GRC Panel Work | Level 18 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-03-08 |  | 100% | 100% | 0% | 2.5714 | 2022.88 | 17.43 | 1416.02 | 44.82 | 0 | 1460.84 |  | 1460.84 |  |  | 1460.84 | 1460.84 | 0
E11/K149/SK/dm/213 | HOTEL | 202 | 77342 | 79938 | Water meter room ceiling work | Level 2 | Tower | 1 | 1.5 | 0.9 | 8 | 1 | rm | 8 | 2023-03-08 | 2023-03-22 | 100% | 100% | 100% | 2.1429 | 63.34 | 7.28 | 354.7 | 124.8 | 152.02 | 631.52 |  | 631.52 |  |  | 631.52 | 631.52 | 0
E11/K149/SK/dm/213 | HOTEL | 202 | 77342 | 79938 | Water meter room ceiling work | Level 2 | Additional Boarding | 1 | 1.5 | 0.9 |  | 1 | m2-LxW | 1.35 | 2023-03-08 | 2023-03-22 | 100% | 100% | 100% | 2.1429 | 6.63 | 0.7 | 6.27 | 2.03 | 2.69 | 10.99 |  | 10.99 |  |  | 10.99 | 10.99 | 0
E11/K149/SK/dm/213 | HOTEL | 80k | 77343 |  | Marble work | Level 2 | Independent | 1 | 3.7 | 1.3 | 5.5 | 1 | m2-LxH | 20.35 | 2023-03-09 |  | 100% | 100% | 0% | 2.4286 | 12.01 | 0.49 | 171.08 | 24.22 | 0 | 195.3 |  | 195.3 |  |  | 195.3 | 195.3 | 0
E11/K149/SK/dm/213 | HOTEL | 80k | 77343 |  | Marble work | Level 2 | Additional Boarding | 2 | 3.7 | 1.3 |  | 2 | m2-LxW | 9.62 | 2023-03-09 |  | 100% | 100% | 0% | 2.4286 | 6.63 | 0.7 | 44.65 | 16.35 | 0 | 61 |  | 61 |  |  | 61 | 61 | 0
E11/K149/SK/dm/213 | HOTEL | 203 | 77344 | 79926 | Roof Side Block work | Level 29 | Independent | 1 | 15 | 0.9 | 2.5 | 1 | m2-LxH | 37.5 | 2023-03-09 | 2023-03-16 | 100% | 100% | 100% | 1.1429 | 12.01 | 0.49 | 315.26 | 21 | 135.11 | 471.37 |  | 471.37 |  |  | 471.37 | 471.37 | 0
E11/K149/SK/dm/213 | HOTEL | 203 | 77344 | 79926 | Roof Side Block work | Level 29 | Additional Boarding | 1 | 15 | 0.9 |  | 1 | m2-LxW | 13.5 | 2023-03-09 | 2023-03-16 | 100% | 100% | 100% | 1.1429 | 6.63 | 0.7 | 62.65 | 10.8 | 26.85 | 100.3 |  | 100.3 |  |  | 100.3 | 100.3 | 0
E11/K149/SK/dm/213 | HOTEL | 203a | 77345 | 79927 | Block Work | Level 29 | Tower | 1 | 1.3 | 0.9 | 0.5 | 1 | rm | 0.5 | 2023-03-09 | 2023-03-16 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 22.17 | 4.16 | 9.5 | 35.83 |  | 35.83 |  |  | 35.83 | 35.83 | 0
E11/K149/SK/dm/213 | HOTEL | 204 | 77346 | 79919 | Staircase - 8 For Fire line work | Level 5 | Independent | 1 | 6.1 | 0.9 | 2 | 1 | m2-LxH | 12.2 | 2023-03-09 | 2023-03-15 | 100% | 100% | 100% | 1 | 12.01 | 0.49 | 102.57 | 5.98 | 43.96 | 152.51 |  | 152.51 |  |  | 152.51 | 152.51 | 0
E11/K149/SK/dm/213 | HOTEL | 204a | 77347 | 79920 | Staircase - 8 For Fire line work | Level 5 | Tower | 1 | 2.2 | 1.3 | 2.3 | 1 | rm | 2.3 | 2023-03-09 | 2023-03-15 | 100% | 100% | 100% | 1 | 63.34 | 7.28 | 101.98 | 16.74 | 43.7 | 162.42 |  | 162.42 |  |  | 162.42 | 162.42 | 0
E11/K149/SK/dm/213 | HOTEL | 203b | 77348 | 79925 | Block Work | Level 29 | Independent | 1 | 10 | 0.9 | 2.5 | 1 | m2-LxH | 25 | 2023-03-10 | 2023-03-20 | 100% | 100% | 100% | 1.5714 | 12.01 | 0.49 | 210.18 | 19.25 | 90.08 | 319.51 |  | 319.51 |  |  | 319.51 | 319.51 | 0
E11/K149/SK/dm/213 | HOTEL | 203b | 77348 | 79925 | Block Work | Level 29 | Additional Boarding | 1 | 10 | 0.9 |  | 1 | m2-LxW | 9 | 2023-03-10 | 2023-03-20 | 100% | 100% | 100% | 1.5714 | 6.63 | 0.7 | 41.77 | 9.9 | 17.9 | 69.57 |  | 69.57 |  |  | 69.57 | 69.57 | 0
E11/K149/SK/dm/213 | HOTEL | 203c | 77349 | 79924 | Block Work | Level 29 | Tower | 1 | 1.5 | 0.9 | 0.9 | 1 | rm | 0.9 | 2023-03-10 | 2023-03-18 | 100% | 100% | 100% | 1.2857 | 63.34 | 7.28 | 39.9 | 8.42 | 17.1 | 65.42 |  | 65.42 |  |  | 65.42 | 65.42 | 0
E11/K149/SK/dm/213 | HOTEL | 205 | 77350 |  | Lift shaft wall repairng work | Basement 2 | Tower | 1 | 1.8 | 1.8 | 9 | 1 | rm | 9 | 2023-03-11 |  | 100% | 100% | 0% | 2.1429 | 63.34 | 7.28 | 399.04 | 140.4 | 0 | 539.44 |  | 539.44 |  |  | 539.44 | 539.44 | 0
E11/K149/SK/dm/213 | HOTEL | 205 | 77350 |  | Lift shaft wall repairng work | Basement 2 | Additional Boarding | 2 | 1.8 | 1.8 |  | 2 | m2-LxW | 6.48 | 2023-03-11 |  | 100% | 100% | 0% | 2.1429 | 6.63 | 0.7 | 30.07 | 9.72 | 0 | 39.79 |  | 39.79 |  |  | 39.79 | 39.79 | 0
E11/K149/SK/dm/213 | HOTEL | 206 | 77201 | 79944 | Ballroom For reducing grill height | Basement 1 | Independent | 1 | 9.3 | 1.3 | 5.8 | 1 | m2-LxH | 53.94 | 2023-03-13 | 2023-03-25 | 100% | 100% | 100% | 1.8571 | 12.01 | 0.49 | 453.47 | 49.09 | 194.35 | 696.91 |  | 696.91 |  |  | 696.91 | 696.91 | 0
E11/K149/SK/dm/213 | HOTEL | 206a | 77201 | 79944 | Ballroom For reducing grill height | Basement 1 | Cantilever (0 < 0.5m width) | 1 | 20.6 | 0.5 |  | 1 | m2-LxW | 10.3 | 2023-03-13 | 2023-03-25 | 100% | 100% | 100% | 1.8571 | 32.75 | 1.05 | 236.13 | 20.09 | 101.2 | 357.42 |  | 357.42 |  |  | 357.42 | 357.42 | 0
E11/K149/SK/dm/213 | HOTEL | 1e | 77203 | 79937 | ACP Panel Work | Level 29 | Tower | 1 | 1.8 | 1.3 | 4 | 1 | rm | 4 | 2023-03-13 | 2023-03-22 | 100% | 100% | 100% | 1.4286 | 63.34 | 7.28 | 177.35 | 41.6 | 76.01 | 294.96 |  | 294.96 |  |  | 294.96 | 294.96 | 0
E11/K149/SK/dm/213 | HOTEL | 1f | 77203 | 79937 | ACP Panel Work | Level 29 | Cantilever (0.5 > 1.2m width) | 1 | 1.8 | 1.2 |  | 1 | m2-LxW | 2.16 | 2023-03-13 | 2023-03-22 | 100% | 100% | 100% | 1.4286 | 36.52 | 2.94 | 55.22 | 9.07 | 23.66 | 87.95 |  | 87.95 |  |  | 87.95 | 87.95 | 0
E11/K149/SK/dm/213 | HOTEL | 207 | 77204 |  | Staircase 10 For Wall repairing work | Ground Level | Tower | 1 | 2.5 | 1 | 2 | 1 | rm | 2 | 2023-03-15 |  | 100% | 100% | 0% | 1.5714 | 63.34 | 7.28 | 88.68 | 22.88 | 0 | 111.56 |  | 111.56 |  |  | 111.56 | 111.56 | 0
E11/K149/SK/dm/213 | HOTEL | 207a | 77205 | 79923 | Staircase 10 For Wall repairing work | Ground Level | Tower | 1 | 2.5 | 1 | 2 | 1 | rm | 2 | 2023-03-15 | 2023-03-18 | 100% | 100% | 100% | 0.57143 | 63.34 | 7.28 | 88.68 | 8.32 | 38 | 135 |  | 135 |  |  | 135 | 135 | 0
E11/K149/SK/dm/213 | HOTEL | 208 | 77206 | 79940 | EIFS Work | Level 29 | Tower | 1 | 2.5 | 1.3 | 4 | 1 | rm | 4 | 2023-03-15 | 2023-03-22 | 100% | 100% | 100% | 1.1429 | 63.34 | 7.28 | 177.35 | 33.28 | 76.01 | 286.64 |  | 286.64 |  |  | 286.64 | 286.64 | 0
E11/K149/SK/dm/213 | HOTEL | 208 | 77206 |  | EIFS Work | Level 29 | Additional Boarding | 1 | 2.5 | 1.3 |  | 1 | m2-LxW | 3.25 | 2023-03-15 |  | 100% | 100% | 0% | 1.5714 | 6.63 | 0.7 | 15.08 | 3.58 | 0 | 18.66 |  | 18.66 |  |  | 18.66 | 18.66 | 0
E11/K149/SK/dm/213 | HOTEL | 209 | 77207 | 79936 | Fire Fighting leak work | Level 28 | Tower | 1 | 1.8 | 0.9 | 2.2 | 1 | rm | 2.2 | 2023-03-18 | 2023-03-22 | 100% | 100% | 100% | 0.71429 | 63.34 | 7.28 | 97.54 | 11.44 | 41.8 | 150.78 |  | 150.78 |  |  | 150.78 | 150.78 | 0
E11/K149/SK/dm/213 | HOTEL | 210 | 77208 |  | Lift shaft -23 For wall repairing work | Basement 2 | Tower | 1 | 1.8 | 1.8 | 9 | 1 | rm | 9 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 63.34 | 7.28 | 399.04 | 74.88 | 0 | 473.92 |  | 473.92 |  |  | 473.92 | 473.92 | 0
E11/K149/SK/dm/213 | HOTEL | 210 | 77208 |  | Lift shaft -23 For wall repairing work | Basement 2 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 6.63 | 0.7 | 30.07 | 5.18 | 0 | 35.25 |  | 35.25 |  |  | 35.25 | 35.25 | 0
E11/K149/SK/dm/213 | HOTEL | 211 | 77209 |  | Edge Protection | Level 24 | Tripple Handrail | 1 | 19.5 |  | 1.5 |  | lm | 19.5 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 24 | 0.7 | 327.6 | 15.6 | 0 | 343.2 |  | 343.2 |  |  | 343.2 | 343.2 | 0
E11/K149/SK/dm/213 | HOTEL | 203d | 77210 | 79922 | Block Work | Level 29 | Tower | 1 | 1.5 | 1.5 | 3 | 1 | rm | 3 | 2023-03-18 | 2023-03-20 | 100% | 100% | 100% | 0.42857 | 63.34 | 7.28 | 133.01 | 9.36 | 57.01 | 199.38 |  | 199.38 |  |  | 199.38 | 199.38 | 0
E11/K149/SK/dm/213 | HOTEL | 203d | 77210 | 79922 | Block Work | Level 29 | Additional Boarding | 1 | 1.5 | 1.5 |  | 1 | m2-LxW | 2.25 | 2023-03-18 | 2023-03-20 | 100% | 100% | 100% | 0.42857 | 6.63 | 0.7 | 10.44 | 0.68 | 4.48 | 15.6 |  | 15.6 |  |  | 15.6 | 15.6 | 0
E11/K149/SMF/dm/756 | HOTEL | 212 | 77211 |  | GRC Panel Work | Level 7 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 2022.88 | 17.43 | 1416.02 | 19.92 | 0 | 1435.94 |  | 1435.94 |  |  | 1435.94 | 1435.94 | 0
E11/K149/SMF/dm/756 | HOTEL | 213 | 77212 |  | GRC Panel Work | Level 13 | Design 1399-48 | 1 |  |  |  |  | unit | 1 | 2023-03-18 |  | 100% | 100% | 0% | 1.1429 | 2022.88 | 17.43 | 1416.02 | 19.92 | 0 | 1435.94 |  | 1435.94 |  |  | 1435.94 | 1435.94 | 0
E11/K149/SK/dm/213 | HOTEL | 214 | 77213 |  | Block Work | Level 29 | Tower | 1 | 2.5 | 0.9 | 2.5 | 1 | rm | 2.5 | 2023-03-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 110.85 | 7.8 | 0 | 118.65 |  | 118.65 |  |  | 118.65 | 118.65 | 0
E11/K149/SK/dm/213 | HOTEL | 214a | 77213 |  | Block Work | Level 29 | Tower | 1 | 1.3 | 0.9 | 1 | 1 | rm | 1 | 2023-03-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 44.34 | 3.12 | 0 | 47.46 |  | 47.46 |  |  | 47.46 | 47.46 | 0
E11/K149/SK/dm/213 | HOTEL | 215 | 77214 |  | Shaft 24 wall repairing work | Basement 2 | Tower | 1 | 1.8 | 1.8 | 9 | 1 | rm | 9 | 2023-03-23 |  | 100% | 100% | 0% | 0.42857 | 63.34 | 7.28 | 399.04 | 28.08 | 0 | 427.12 |  | 427.12 |  |  | 427.12 | 427.12 | 0
E11/K149/SK/dm/213 | HOTEL | 215 | 77214 |  | Shaft 24 wall repairing work | Basement 2 | Additional Boarding | 2 | 1.8 | 1.8 | 1 | 2 | m2-LxW | 6.48 | 2023-03-23 |  | 100% | 100% | 0% | 0.42857 | 6.63 | 0.7 | 30.07 | 1.94 | 0 | 32.01 |  | 32.01 |  |  | 32.01 | 32.01 | 0
Total |  |  | 1066 | 826 | [18 empty] | 811148.84 | 858454.8 | 194431.92 | 1864035.56 | 1685134.4 | 178901.16 |  | 1681188.62 | 182846.94 | 1864035.56
[30 empty] | Contract | 50491.82 | 603199.84
[30 empty] | Variation | 132355.12 | 1260835.72
[30 empty] | Modification | 2788 | 16318
Note on D29: Himal Kosala: This is not in the HOC
Note on D33: Himal Kosala: Not in the HOC
Note on D731: Himal Kosala: No approval from OME
Note on D732: Himal Kosala: No approval from OME
Note on Q1078: Himal Kosala: Not added
Note on Q1079: Himal Kosala: Not added

## Modification
Khansaheb Civil Engineering LLC
Application No.: | 7
Project Name: | Dorchester Hotel & Residences (Completion Works)
Order Reference: | 201A22002/49
As On Date: | 2023-03-25
Dayworks
DTS | Date | Hrs | Total | Previous | Net Amount
62652 | 2022-09-18 | 26 | 533 | 533 | 0
62653 | 2022-09-30 | 6 | 123 | 123 | 0
62654 | 2022-10-10 | 30 | 615 | 615 | 0
62655 | 2022-11-16 | 8 | 164 | 164 | 0
62657 | 2022-11-21 | 54 | 1107 | 1107 | 0
62658 | 2022-11-21 | 16 | 328 | 328 | 0
62661 | 2022-12-22 | 5 | 102.5 | 102.5 | 0
62662 | 2022-12-23 | 10 | 205 | 205 | 0
62663 | 2022-12-26 | 30 | 615 | 615 | 0
62664 | 2022-12-26 | 24 | 492 | 492 | 0
62665 | 2023-01-09 | 20 | 410 | 410 | 0
62667 | 2023-01-10 | 6 | 123 | 123 | 0
62668 | 2023-01-21 | 47.5 | 973.75 | 973.75 | 0
62670 | 2023-01-21 | 12 | 246 | 246 | 0
62671 | 2023-01-21 | 32.5 | 666.25 | 666.25 | 0
62669 | 2023-01-23 | 47.5 | 973.75 | 973.75 | 0
62673 | 2023-01-23 | 25 | 512.5 | 512.5 | 0
62672 | 2023-01-24 | 47.5 | 973.75 | 973.75 | 0
62674 | 2023-01-26 | 16 | 328 | 328 | 0
62675 | 2023-01-28 | 8 | 164 | 164 | 0
62676 | 2023-01-28 | 8 | 164 | 164 | 0
62677 | 2023-02-01 | 76 | 1558 | 1558 | 0
62678 | 2023-02-02 | 24 | 492 | 492 | 0
62679 | 2023-02-04 | 5 | 102.5 | 102.5 | 0
62680 | 2023-02-09 | 16 | 328 | 328 | 0
62693 | 2023-02-11 | 8 | 164 | 164 | 0
62694 | 2023-02-13 | 3 | 61.5 | 61.5 | 0
62681 | 2023-02-14 | 6 | 123 | 123 | 0
62682 | 2023-02-15 | 9 | 184.5 | 184.5 | 0
62683 | 2023-02-20 | 16 | 328 | 328 | 0
62684 | 2023-02-20 | 6 | 123 | 123 | 0
62685 | 2023-02-21 | 12 | 246 | 246 | 0
62686 | 2023-03-01 | 12 | 246 | 0 | 246
62687 | 2023-03-02 | 4 | 82 | 0 | 82
62688 | 2023-03-06 | 12 | 246 | 0 | 246
62690 | 2023-03-07 | 8 | 164 | 0 | 164
62691 | 2023-03-08 | 16 | 328 | 0 | 328
62692 | 2023-03-09 | 16 | 328 | 0 | 328
62695 | 2023-03-09 | 16 | 328 | 0 | 328
62696 | 2023-03-13 | 12 | 246 | 0 | 246
62697 | 2023-03-11 | 8 | 164 | 0 | 164
62698 | 2023-03-15 | 8 | 164 | 0 | 164
62699 | 2023-03-16 | 8 | 164 | 0 | 164
62700 | 2023-03-18 | 16 | 328 | 0 | 328
Total |  | 796 | 16318 | 13530 | 2788

## Order References
Rate Card Ref | Order Reference | Scaffolding Type | Fixed Duration | Item | Unit | Rate IN AED
1 | E11/K149/SK/dm/213 | Static tower | 0 | Erect & Dismantle | Rising Meter | 63.34
2 | E11/K149/SK/dm/213 | Static tower | 0 | Hire per Week | Rising Meter | 7.28
3 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Erect & Dismantle | Rising Meter | 103.33
4 | E11/K149/SK/dm/213 | Mobile Tower | 0 | Hire per Week | Rising Meter | 10.29
5 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Erect & Dismantle | Rising Meter | 148
6 | E11/K149/SK/dm/213 | Heavy duty tower | 0 | Hire per Week | Rising Meter | 12.88
7 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Erect & Dismantle | M2 (LxH) | 12.01
8 | E11/K149/SK/dm/213 | Independent 1.2m wide | 0 | Hire per Week | M2 (LxH) | 0.49
9 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Erect & Dismantle | M2 (LxH) | 16.76
10 | E11/K149/SK/dm/213 | Independent 1.8m wide | 0 | Hire per Week | M2 (LxH) | 0.77
11 | E11/K149/SK/dm/213 | Birdcage | 0 | Erect & Dismantle | M3 | 7.08
12 | E11/K149/SK/dm/213 | Birdcage | 0 | Hire per Week | M3/Day | 0.49
13 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Erect & Dismantle | M3 | 10
14 | E11/K149/SK/dm/213 | Heavy duty birdcage | 0 | Hire per Week | M3/Day | 0.91
15 | E11/K149/SK/dm/213 | Buttress | 0 | Erect & Dismantle | M3 | 5.29
16 | E11/K149/SK/dm/213 | Buttress | 0 | Hire per Week | M3/Day | 0.35
17 | E11/K149/SK/dm/213 | Boarded lift | 0 | Erect & Dismantle | M2 (LxW) | 6.63
18 | E11/K149/SK/dm/213 | Boarded lift | 0 | Hire per Week | M2 (LxW) | 0.7
19 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Erect & Dismantle | M2 (LxW) | 32.75
20 | E11/K149/SK/dm/213 | Cantilever (0 < 0.5m width) | 0 | Hire per Week | M2 (LxW) | 1.05
21 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Erect & Dismantle | M2 (LxW) | 36.52
22 | E11/K149/SK/dm/213 | Cantilever (0.5 > 1.2m width) | 0 | Hire per Week | M2 (LxW) | 2.94
23 | E11/K149/SK/dm/213 | Bridge | 0 | Erect & Dismantle | Linear Meter | 37.43
24 | E11/K149/SK/dm/213 | Bridge | 0 | Hire per Week | Linear Meter | 1.4
25 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Erect & Dismantle | Linear Meter | 0.3
26 | E11/K149/SK/dm/213 | Counterweight (Scaffold Tubes) | 0 | Hire per Week | Linear Meter | 0.14
27 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Erect & Dismantle | Linear Meter | 7
28 | E11/K149/SK/dm/213 | Edge protection - A Frame Single | 0 | Hire per Week | Linear Meter | 0.42
29 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Erect & Dismantle | Linear Meter | 12
30 | E11/K149/SK/dm/213 | Edge protection - A Frame double | 0 | Hire per Week | Linear Meter | 0.7
31 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Erect & Dismantle | Linear Meter | 15
32 | E11/K149/SK/dm/213 | Edge Protection - Double | 0 | Hire per Week | Linear Meter | 0.91
33 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Erect & Dismantle | Linear Meter | 24
34 | E11/K149/SK/dm/213 | Edge Protection - Double (Hilti) | 0 | Hire per Week | Linear Meter | 0.7
35 | E11/K149/SK/dm/213 | Netting supply - Beige Colour | 0 | Supply only | M2 (LxH) | 4.52
36 | E11/K149/SK/dm/213 | Netting install | 0 | Supply only | M2 (LxH) | 4
37 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Erect & Dismantle | Rising Meter | 250
38 | E11/K149/SK/dm/213 | Staircase Supported by structure | 0 | Hire per Week | Rising Meter | 14.35
39 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Erect & Dismantle | Rising Meter | 376.2
40 | E11/K149/SK/dm/213 | Staircase supported by Buttress | 0 | Hire per Week | Rising Meter | 40.11
41 | E11/K149/SK/dm/213 | Manpower - Scaffolder | 0 | Dayworks | Hour | 20.5
42 | E11/K149/SK/dm/213 | Manpower - Foreman | 0 | Dayworks | Hour | 24
43 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Erect & Dismantle | Set | 0
44 | E11/K149/SK/dm/216 | Aluminium Tower | 0 | Hire per Week | Set | 28.5714
45 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Erect & Dismantle | Lumpsum | 6044.84
46 | E11/K149/SK/dm/238 | Design - TAS-1399-10A | 1 | Hire per Week | Hire per Week | 45.3871
47 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Erect & Dismantle | Lumpsum | 16252.45
48 | E11/K149/SK/dm/239 | Design - TAS-1399-7 | 1 | Hire per Week | Hire per Week | 89.4243
49 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Erect & Dismantle | Lumpsum | 4844.83
50 | E11/K149/SK/dm/256 | Balcony Scaffold - Type1 | 1 | Hire per Week | Hire per Week | 15.99
51 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Erect & Dismantle | Lumpsum | 4990.83
52 | E11/K149/SK/dm/256 | Balcony Scaffold - Type2 | 1 | Hire per Week | Hire per Week | 17.4214
53 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Erect & Dismantle | Lumpsum | 5095.97
54 | E11/K149/SK/dm/256 | Balcony Scaffold - Type3 | 1 | Hire per Week | Hire per Week | 18.45
55 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Erect & Dismantle | Lumpsum | 4127.36
56 | E11/K149/SK/dm/256 | Balcony Scaffold - Type4 | 1 | Hire per Week | Hire per Week | 8.4371
57 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Erect & Dismantle | Lumpsum | 8714.14
58 | E11/K149/SK/dm/256 | Balcony Scaffold - Type5 | 1 | Hire per Week | Hire per Week | 38.73
59 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Erect & Dismantle | Lumpsum | 5210.58
60 | E11/K149/SK/dm/256 | Balcony Scaffold - Type6 | 1 | Hire per Week | Hire per Week | 19.3229
61 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Erect & Dismantle | Lumpsum | 5900.72
62 | E11/K149/SK/dm/256 | Balcony Scaffold - Type7 | 1 | Hire per Week | Hire per Week | 26.07
63 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Erect & Dismantle | Lumpsum | 53510.26
64 | E11/K149/SK/dm/257 | Design - TAS-1399-02D | 1 | Hire per Week | Hire per Week | 401
65 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Erect & Dismantle | Lumpsum | 158449.11
66 | E11/K149/SK/dm/259 | Design - TAS-1399-06B | 1 | Hire per Week | Hire per Week | 2018.4243
67 | CONTRACT - 201A22002/49
68 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Erect & Dismantle | Lumpsum | 5083.25
69 | E11/K149/HN/dm/285 | Design-TAS-1399-12 | 1 | Hire per Week | Hire per Week | 123.48
70 | E11/K149/SK/dm/365 |  | 1 | Erect & Dismantle | Lumpsum | 5979.17
71 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Erect & Dismantle | Lumpsum | 14003.16
72 | E11/K149/SK/dm/350 | Design-TAS-1399-14 | 1 | Hire per Week | Hire per Week | 660.1
73 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Erect & Dismantle | Lumpsum | 4082.38
74 | E11/K149/SK/dm/300 | Design-Tas-1399-13A | 1 | Hire per Week | Hire per Week | 49.28
75 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 5325.76
76 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 48.26
77 | E11/K149/SK/dm/341 |  | 1 | Erect & Dismantle | Lumpsum | 1375.16
78 | E11/K149/SK/dm/341 |  | 1 | Hire per Week | Hire per Week | 6.17
79 | E11/K149/MS/dm/396 |  | 1 | Erect & Dismantle | Lumpsum | 2448.62
80 | E11/K149/MS/dm/396 |  | 1 | Hire per Week | Hire per Week | 57.19
81 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Erect & Dismantle | Lumpsum | 15415.16
82 | E11/K149/PK/dm/400 | Design-Tas-1399-22 | 1 | Hire per Week | Hire per Week | 297.83
83 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Erect & Dismantle | Lumpsum | 11289.34
84 | E11/K149/PK/dm/378 | Design -Tas-1399-21 | 1 | Hire per Week | Hire per Week | 1429.84
85 | E11/K149/JA/dm/429 |  | 1 | Erect & Dismantle | Lumpsum | 13590.73
86 | E11/K149/JA/dm/429 |  | 1 | Hire per Week | Hire per Week | 302.12
87 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Erect & Dismantle | Lumpsum | 32825.12
88 | E11/K149/JJ/dm/377 | Design -Tas-1399-20a | 1 | Hire per Week | Hire per Week | 2044.24
89 | E11/K149/SK/dm/468 |  | 1 | Erect & Dismantle | Lumpsum | 4760.74
90 | E11/K149/SK/dm/468 |  | 1 | Hire per Week | Hire per Week | 414.05
91 | E11/K149/MS/dm/497 | Design -Tas-1399-30&31 | 1 | Erect & Dismantle | Lumpsum | 13067.86
92 | E11/K149/MS/dm/497 | Design -Tas-1399-30&31 | 1 | Hire per Week | Hire per Week | 788.67
93 | E11/K149/SK/SR/517 | Design - Tas-1399-35b | 1 | Erect & Dismantle | Lumpsum | 3675.3
94 | E11/K149/SK/SR/517 | Design - Tas-1399-35b | 1 | Hire per Week | Hire per Week | 54.93
95 | E11/K149/SK/dm/480 | Design - Tas- 1399-25a | 1 | Erect & Dismantle | Lumpsum | 3562.04
96 | E11/K149/SK/dm/480 | Design - Tas- 1399-25a | 1 | Hire per Week | Hire per Week | 181.02
97 | E11/K149/SK/SR/503 | Design - Tas - 1399-29 | 1 | Erect & Dismantle | Lumpsum | 36307.15
98 | E11/K149/SK/SR/503 | Design - Tas - 1399-29 | 1 | Hire per Week | Hire per Week | 1384.55
99 | E11/K149/SK/SR/550 | Aluminium Tower |  | Erect & Dismantle | Set | 0
100 | E11/K149/SK/SR/550 | Aluminium Tower |  | Hire per Week | Set | 275
101 | E11/K149/SK/SR/560 | Aluminium Tower |  | Erect & Dismantle | Set | 0
102 | E11/K149/SK/SR/560 | Aluminium Tower |  | Hire per Week | Set | 275
103 | E11/K149/SK/SR/582 | Design - TAS-1399-39 |  | Erect & Dismantle | Lumpsum | 5018.12
104 | E11/K149/SK/SR/582 | Design - TAS-1399-39 |  | Hire per Week | Hire per Week | 212.24
105 | E11/K149/SK/SR/585 | Temp. Rack |  | Erect & Dismantle | Lumpsum | 3833.1
106 | E11/K149/SK/SR/585 | Temp. Rack |  | Hire per Week | Hire per Week | 95.83
107 | E11/K149/MS/DM/647 | Design -Tas-1399-37a |  | Erect & Dismantle | Lumpsum | 7773.97
108 | E11/K149/MS/DM/647 | Design -Tas-1399-37a |  | Hire per Week | Hire per Week | 125.44
109 | E11/K149/SMF/DM/641 | Design-Tas-1399-43 |  | Erect & Dismantle | Lumpsum | 8057.37
110 | E11/K149/SMF/DM/641 | Design-Tas-1399-43 |  | Hire per Week | Hire per Week | 212.35
111 | E11/K149/SMF/DM/756 | Design-Tas-1399-48 |  | Erect & Dismantle | Lumpsum | 2040.31
112 | E11/K149/SMF/DM/756 | Design-Tas-1399-48 |  | Hire per Week | Hire per Week | 17.43
113 | E11/K149/SK/DM/767 | Design-Tas-1399-47a |  | Erect & Dismantle | Lumpsum | 13026.76
114 | E11/K149/SK/DM/767 | Design-Tas-1399-47a |  | Hire per Week | Hire per Week | 812.7
115 | E11/K149/NA/DM/762 | Design-Tas-1399-49 |  | Erect & Dismantle | Lumpsum | 2694.51
116 | E11/K149/NA/DM/762 | Design-Tas-1399-49 |  | Hire per Week | Hire per Week | 190.87
117 | E11/K149/HW/DM/815 | Design-Tas-1399-50 |  | Erect & Dismantle | Lumpsum | 16114.67
118 | E11/K149/HW/DM/815 | Design-Tas-1399-50 |  | Hire per Week | Hire per Week | 279.86
119
120
121
122
123
124
125
126
127
128
129
130
131
132
133
134
135
136
137
138
139
140
141
142
143
144
145
146
147
148
149
150
151
152
153
154
155
156
157
158
159
160
161
162
163
164
165
166
167
168
169
170
171
172
173
174

## Manpower (hidden)
Client: | Khansaheb Civil Engineering LLC
Application No.: | 7
Project Name: | Dorchester Hotel & Residences (Completion Works)
Site: | #REF!
As Of: | 2023-03-25
Modification Hours
DTS | Date | Scaffolder | Foreman | Cumulative | Previous | Net
Total |  |  |  | 0 | 0 | 0

## SCOPE (hidden)
SCOPE OF WORKS & ADDITIONAL WORKS RATES
Reference | Description | Number | L | W | H | BL | Item Price | Period (Wks) | Extra Hire per Week

## PASummary (hidden)
Client: | Khansaheb Civil Engineering LLC
Project Name: | Dorchester Hotel & Residences (Completion Works)
Contract Ref: | 201A22002/49
PAYMENT APPLICATION SUMMARY
Application No. | Application Date | Works Carried Out | Day Works | Total | Remarks
1 | 2022-09-30 | 125287.35 | 0 | 125287.35
2 | 2022-10-31 | 221656.79 | 1,271.00 | 222927.79
3 | 2022-11-25 | 254058.2 | 1599 | 255657.2
0
0
0
0
0
Total |  | 601002.34 | 1599 | 603872.34 | 0