## BOQ
AL SHIRAWI CONTRACTING CO. LLC
M/s, KHANSAHEB CIVIL ENGINEERING LLC | [8 empty] | PROJECT: DORCHESTER HOTEL & RESIDENCES
JOB NO: C5710 | [5 empty] | Cumulative Claim |  |  | Last Month Claim |  |  | This Month Claim |  |  | Remark
2022-12-01
S.N | Description | Quantity | Unit | Rate | Amount UAE Dirhams | Quantity | Progress in % | Total Amount | Quantity | Progress in % | Total Amount | Quantity | Progress in % | Total Amount
WATERPROOFING WORKS
A | Supply and apply Masterseal 588 two component acrylic modified Cementitious coating to the horizontal and vertical areas of water tank to the thickness of 1.5mm along with Masterseal 940 ICJ 250 Internal water Stopper.
| To floor | 1981.61 | m2 | 47.21 | 93551.8081 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0 |  |  | 563691734
B | Combo Roof system which complies to Dubai Green Building Regulations. Price includes Upstand areas.
| - Supply and apply spray applied polyurethane foam 45 to 50Kg/m3 density and up to 68 - 70mm thick ( To achieve U value 0.30w/m2k) - Supply & brush apply acrylic UV resistance protective coating above the entire PU foam coating. - Supply and lay of geotextile separation layer 150grm/m2 with an overlap of 20cm. - Supply and fix ridges in the panel. - Supply and lay protection Screed concrete, average 80mm thick. - Supply and apply backing rod and heavy duty PU sealant to all expansion joints. - Supply and apply angle fillets (with cement sand mortar) along the parapet, duct openings and pre built utility upstands. - Supply and fix geotextile mesh 80grm/m2 reinforcement all over the angle fillet and pre-built utility up stands with polyurethane top coat - Supply and apply polyurethane UV protective final coat above screed, angle fillet and other up stands. | 1358.45 | m2 | 157.68 | 214200.396 | 950.915 | 70% | 149940.2772 | 611.3 | 45% | 96390.18 | 339.615 | 25% | 53550.4932
C | WET AREAS
Supply and apply Masterseal 588 two component acrylic modified Cementitious coating to the horizontal and vertical areas of to the thickness of 1.5mm and water test.
Waterproofing to wet areas (floor/wall) in White Box areas all in accordance with drawings and specifications
| Bathrooms and toilets in Hotel tower suites, Apartment tower suites and penthouses. Ground, 2nd and 4th level public toilets and verticals | 1178.28 | m2 | 37.01 | 43608.1428 | 1178.28 | 100% | 43608.1428 | 895 | 75.95% | 33122.21 | 283.28 | 24.04% | 10484.1928
D | BALCONIES/TERRACES
Supply and apply Masterseal 588 two component acrylic modified Cementitious coating to the horizontal and vertical areas of to the thickness of 1.5mm and water test.
| To Horizontal | 2135.74 | m2 | 37.17 | 79385.4558 | 873.23 | 40.89% | 32457.9591 | 873 | 40.89% | 32457.96 | 0.23 | 0.01077% | 8.5491 |  | 854.296
E | Supply and apply two coats of Polycoat RBE rubberized emulsion coating to the façade areas
| Damp proof course behind external cladding | 14738 | m2 | 8 | 117904 | 0 | 0% | 0 | 0 | 0% | 0 | 0 | 0% | 0
F | Hard Landscape Waterproofing - Walkways
Supply and apply one coat of Primer and lay one layer of Sopralene Flam 180 4P 4mm Black finish SBS modified non woven polyester reinforcement torch on membrane with 75 mm side and end laps fully bonded to the primed surface of the Substructures, including 3.2mm thick protection board for vertical areas, sealant for termination and water test.
| To Horizontal | 11992.6467 | m2 | 32.39 | 388441.8266 | 10543.933 | 87.92% | 341517.9899 | 9360.39 | 78.05% | 303183 | 1183.543 | 9.869% | 38334.9578
G | Hard Landscape Waterproofing - Driveways
Supply and apply one coat of Primer and lay one layer of Sopralene Flam 180 4P 5mm Black finish SBS modified non woven polyester reinforcement torch on membrane with 75 mm side and end laps fully bonded to the primed surface of the Substructures, including 3.2mm thick protection board for horizontal & vertical areas and sealant for termination at drive way areas and water test
| To Horizontal | 3759.9 | m2 | 50.127 | 188472.5073 | 1664.66 | 44.27% | 83444.4118 | 1516.05 | 40.32% | 75995.04 | 148.61 | 3.952% | 7449.3735
H | Supply and apply 3.2mm thick protection board for horizontal & vertical areas and sealant for termination at drive way areas and water test
| Hard landscape protection works | 14989 | m2 | 17.74 | 265904.86 | 10543.933 | 70.34% | 187049.3714 | 9360.39 | 62.45% | 166053.3 | 1183.543 | 7.896% | 20996.0528
ADDITIONAL WORKS
LPG TANK WATERPROOFING
1 | Supply and apply primer and membrane | 196.34 | m2 | 59 | 11584.06 | 196.3355 | 100% | 11583.7945 | 196.34 | 100% | 11583.79 | -0.0045 | -0.002292% | -0.2655
2 | Supply and fix protection board | 196.34 | m2 | 17.74 | 3483.0716 | 110 | 56.03% | 1951.4 | 110 | 56.03% | 1951.4 | 0 | 0% | 0
E11/K110/AS/dm/495
3 | Fill void in cored concrete segment | 1 | LS | 50000 | 50000 | 1 | 90% | 45000 | 1 | 50% | 25000 | 0 | 50% | 25000 | 90% until VO approval
E11/K110/HN/MV/700
4 | Supply and apply primer and membrane |  |  | 32.39 |  | 208.43 | 90% | 6075.9429 | 0 | 0% | 0 | 208.43 | 90% | 6075.9429 | 90% until VO approval
5 | Supply and fix protection board |  |  | 17.74 |  | 208.43 | 90% | 3327.7934 | 0 | 0% | 0 | 208.43 | 90% | 3327.7934 | 90% until VO approval
Grand Total - UAE Dirhams |  |  |  | 100% | 1456536.1282 |  | 62.2% | 905957.083 |  | 51.2% | 745736.88 |  | 11.34% | 165227.09
[7 empty] | KCE Claim | 820138 |  |  | 130693 |  |  | 950831
[7 empty] | Difference | -74401.12 |  |  | 34534.09 |  |  | -44873.917

## Balcony
AL-SHIRAWI CONTRACTING CO.LLC
PROJECT-PLOT18 BUSINESS BAY Dorchester Hotel
MEASUREMENTS FOR SOFT LANDSCAPE WATERPROOFING WORK
S.NO | Month | Location | DESCRIPTION | NOS | LENGTH | HEIGHT | AREA (M2) | VERT. A (M2) | Dwg Ref
1 | 2022-07-21 | LVL-20 | Hotel-Balcony |  |  |  | 14.27 |  | ALS-WF-SD-L20-00037
2 | 2022-07-21 | LVL-8 | Hotel-Balcony |  |  |  | 11.1 |  | ALS-WF-SD-L8-00026
3 | 2022-07-21 | LVL-25 | Hotel-Balcony |  |  |  | 6.52 |  | ALS-WF-SD-L25-00042
4 | 2022-07-21 | LVL-23 | Hotel-Balcony |  |  |  | 53.45 |  | ALS-WF-SD-L23-00040
5 | 2022-07-21 | LVL-26 | Hotel-Balcony |  |  |  | 6.53 |  | ALS-WF-SD-L26-00043
6 | 2022-07-21 | LVL-28 | Hotel-Balcony |  |  |  | 74.27 |  | ALS-WF-SD-L28-00045
7 | 2022-07-21 | LVL-6 | RESIDNETIAL-Balcony |  |  |  | 91.28 |  | ALS-WF-SD-L6-00021
8 | 2022-10-01 | LVL-6 | RESIDNETIAL-Balcony |  |  |  | 14.52
9 | 2022-10-01 | LVL-6 | RESIDNETIAL-Balcony |  |  |  | 16.05
10 | 2022-10-01 | LVL-6 | RESIDNETIAL-Balcony |  |  |  | 16.26
11 | 2022-10-01 | LVL-6 | RESIDNETIAL-Balcony |  |  |  | 32.52
12 | 2022-10-01 | LVL-28 | RESIDNETIAL-Balcony |  |  |  | 16.1
13 | 2022-10-01 | LVL-26 | Hotel-Balcony |  |  |  | 13.31
14 | 2022-10-01 | LVL-18 | Hotel-Balcony |  |  |  | 162.76
15 | 2022-11-01 | LVL-23 | RESIDNETIAL-Balcony |  |  |  | 178.32
16 | 2022-11-01 | LVL-23 | RESIDNETIAL-Balcony |  |  |  | 51.25
17 | 2022-11-01 | LVL-27 | Hotel-Balcony |  |  |  | 22.32
18 | 2022-12-01 | LVL-28 | Hotel-Balcony |  |  |  | 19.9
19 | 2022-12-01 | LVL-25 | RESIDNETIAL-Balcony |  |  |  | 17.59
20 | 2023-01-01 | LVL-23 | RESIDNETIAL-Balcony |  |  |  | 27.47
21 | 2023-01-01 | LVL-23 | RESIDNETIAL-Balcony |  |  |  | 27.44
|  | Total Qty |  | SQM |  |  | 873.23 | 0

## Wet Area
AL-SHIRAWI CONTRACTING CO.LLC
PROJECT-PLOT18 BUSINESS BAY Dorchester Hotel
MEASUREMENTS FOR SOFT LANDSCAPE WATERPROOFING WORK
S.NO | Month | Location |  | DESCRIPTION | NOS | LENGTH | HEIGHT | AREA (M2) | VERT. A (M2) | Dwg Ref
1 | 2022-07-21 | LVL-23 |  | Hotel-Floor |  |  |  | 1.92
| 2022-07-21 | LVL-23 |  | Hotel-Vertfical | 1 | 5.56 | 0.3 |  | 1.668
2 | 2022-07-21 | LVL-24 |  | Hotel-Floor |  |  |  | 1.92 |  | ALS-WF-SD-L24-00041
| 2022-07-21 | LVL-24 |  | Hotel-Vertfical | 1 | 5.56 | 0.3 |  | 1.668 | ALS-WF-SD-L24-00041
| 2022-07-21 | LVL-25 |  | Hotel-Floor |  |  |  | 1.92
| 2022-07-21 | LVL-25 |  | Hotel-Vertfical | 1 | 5.56 | 0.3 |  | 1.668
| 2022-07-21 | LVL-26 |  | Hotel-Floor |  |  |  | 1.92
| 2022-07-21 | LVL-26 |  | Hotel-Vertfical | 1 | 5.56 | 0.3 |  | 1.668
| 2022-10-01 | LVL-23 |  | Residential Pump room | 1 |  |  | 30.72
| 2022-10-01 | LVL-23 |  | Pump room vertical | 1 | 22.07 | 0.3 |  | 6.621
| 2022-10-01 | GF |  | Female toilet floor | 1 |  |  | 57.21
| 2022-10-01 | GF |  | Female toilet vertical | 1 | 37.95 | 0.3 |  | 11.385
| 2022-12-01 | LVL-23 | RESI | PUMP ROOM | 1 |  |  | 314.33
| 2022-12-01 | LVL-23 | RESI | Pump room vertical | 1 | 71.31 | 0.3 |  | 21.393
| 2022-12-01 | LVL-23 | RESI | PUMP ROOM 2 | 1 |  |  | 139.21
| 2022-12-01 | LVL-23 | RESI | Pump room vertical | 1 | 55.11 | 0.3 |  | 16.533
| 2022-12-01 | LVL-4 |  | BOH ROOM | 1 |  |  | 95.42
| 2022-12-01 | LVL-4 |  | BOH ROOM VERTICAL | 1 | 42.32 | 0.3 |  | 12.696
| 2022-12-01 | LVL-2 |  | AREA-1 | 1 |  |  | 7.46
| 2022-12-01 | LVL-2 |  | VERTICAL | 1 | 11.46 | 0.3 |  | 3.438
| 2022-12-01 | LVL-2 |  | AREA-2 | 1 |  |  | 5.45
| 2022-12-01 | LVL-2 |  | VERTICAL | 1 | 18.15 | 0.3 |  | 5.445
| 2023-01-01 | GF |  | BALL ROOM MALE TOILET | 1 |  |  | 13.58
| 2023-01-01 | GF |  | VERTICAL | 1 | 27.1 | 0.3 |  | 8.13
| 2023-01-01 | LVL-29 | HOTEL | HORIZONTAL | 1 |  |  | 32.66
| 2023-01-01 | LVL-29 |  | VERTICAL | 1 | 25.64 | 0.3 |  | 7.692
| 2023-01-01 | LVL-18 | HOTEL | HORIZONTAL | 1 |  |  | 79.81
| 2023-01-01 | LVL-18 |  | VERTICAL | 1 | 38.06 | 0.3 |  | 11.418
| 2023-02-01 | LVL-18 | HOTEL | FIRE PUMP ROOM HOR | 1 |  |  |  |  | Old waterproofing area
| 2023-02-01 | LVL-18 | HOTEL | VERTICAL | 1 | 37.33 | 0.3 |  |  | Old waterproofing area
| 2023-02-01 | LVL-18 | HOTEL | FIRE PUMP TANK HOR | 1 |  |  |  |  | Old waterproofing area
| 2023-02-01 | LVL-18 | HOTEL | VERTICAL | 1 | 33.2 | 0.3 |  |  | Old waterproofing area
| 2023-02-01 | LVL-18 | HOTEL | FIRE PUMP ROOM HOR | 1 |  |  |  |  | Old waterproofing area
| 2023-02-01 | LVL-18 | HOTEL | VERTICAL | 1 | 33.2 | 0.3 |  |  | Old waterproofing area
| 2023-02-01 | LVL-18 | HOTEL | AHU FOR F&B HX ROOM | 1 |  |  | 215.28
| 2023-02-01 | LVL-18 | HOTEL |  | 1 | 71.71 | 0.3 |  | 21.513
| 2023-02-01 | LVL-1 |  | PLANT ROOM HOR | 1 |  |  | 30.89
| 2023-02-01 | LVL-1 |  | VERTICAL | 1 | 92.52 | 0.3 |  | 27.756
|  | Total Qty |  |  | SQM |  |  | 1029.7 | 160.692

## Landscape Areas
AL-SHIRAWI CONTRACTING CO.LLC
PROJECT-PLOT18 BUSINESS BAY Dorchester Hotel
MEASUREMENTS FOR SOFT LANDSCAPE WATERPROOFING WORK
S.NO | Month | Location |  | DESCRIPTION | NOS | LENGTH | HEIGHT | AREA (M2) | VERT. A (M2) | Dwg Ref
| 2022-07-21 | LVL-25 |  | Residential-Floor |  |  |  | 212.06 |  | ALS-WF-SD-L25-00063
| 2022-07-21 | LVL-25 |  | Residential-Vertfical | 1 | 65.71 | 0.3 |  | 19.713 | ALS-WF-SD-L25-00063
| 2022-07-21 | LVL-25 |  | Residential-Pool area Vertfical | 1 | 37.8 | 0.3 |  | 11.34 | ALS-WF-SD-L25-00063
| 2022-07-21 | LVL-26 |  | Residential-Floor |  |  |  | 214.67 |  | ALS-WF-SD-L26-00064
| 2022-07-21 | LVL-26 |  | Residential-Vertfical | 1 | 67.72 | 0.3 |  | 20.316 | ALS-WF-SD-L26-00064
| 2022-07-21 | LVL-26 |  | Residential-Pool area Vertfical | 1 | 28.79 | 0.3 |  | 8.637 | ALS-WF-SD-L26-00064
| 2022-07-21 | LVL-27 |  | Residential-Floor |  |  |  | 102.84 |  | ALS-WF-SD-L27-00065
| 2022-07-21 | LVL-27 |  | Residential-Vertfical | 1 | 43.31 | 0.3 |  | 12.993 | ALS-WF-SD-L27-00065
| 2022-07-21 | LVL-27 |  | Residential-Pool area Vertfical | 1 | 15.8 | 0.3 |  | 4.74 | ALS-WF-SD-L27-00065
| 2022-07-21 | LVL-10 |  | Residential-Floor |  |  |  | 372.58 |  | ALS-WF-SD-L10-00090
| 2022-07-21 | LVL-10 |  | Vertical | 1 | 144.34 | 0.3 |  | 43.302 | ALS-WF-SD-L10-00090
| 2022-07-21 | LVL-2 |  | LVL2-PART 4 & 5 LANDSCAPE SECONDARY GA |  |  |  | 576.08 |  | RP-LX-SD-L2-1739
| 2022-10-01 | GF |  | AREA-1 | 1 |  |  | 371.14
| 2022-10-01 | GF |  | AREA-2 | 1 |  |  | 232.59
| 2022-10-01 | GF |  | AREA-3 | 1 |  |  | 231.29
| 2022-10-01 | GF |  | AREA-4 | 1 |  |  | 85.75
| 2022-10-01 | LVL-24 |  | Residential - Pool | 1 |  |  | 21.313
| 2022-10-01 | LVL-27 |  | Residential-Floor | 1 |  |  | 15.72
| 2022-11-01 |  |  | LANDSCAPE AREA GF,L2,L4,L29 |  |  |  | 3693
| 2022-12-01 | LVL-4 |  | AREA 1 |  |  |  | 298.91
| 2022-12-01 | LVL-4 |  | L | 1 | 205.82 | 0.3 |  | 61.746
| 2022-12-01 | LVL-4 |  | AREA 2 |  |  |  | 103.11
| 2022-12-01 | LVL-4 |  | L | 1 | 151.44 | 0.3 |  | 45.432
| 2022-12-01 | LVL-4 |  | AREA 3 |  |  |  | 1006.7 |  |  | 866.76
| 2022-12-01 | LVL-4 |  | deduction of planters |  |  |  | -29.83
| 2022-12-01 | LVL-4 | [5 empty] | -12.16
| 2022-12-01 | LVL-4 | [5 empty] | -2.59
| 2022-12-01 | LVL-4 | [5 empty] | -2.92
| 2022-12-01 | LVL-4 | [5 empty] | -3.5
| 2022-12-01 | LVL-4 | [5 empty] | -3.5
| 2022-12-01 | LVL-4 | [5 empty] | -2.87
| 2022-12-01 | LVL-4 | [5 empty] | -9.71
| 2022-12-01 | LVL-4 | [5 empty] | -73.83
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 308.33 | 0.3 |  | 92.499
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 52.05 | 0.3 |  | 15.615
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 14.31 | 0.3 |  | 4.293
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 11.39 | 0.3 |  | 3.417
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 12.71 | 0.3 |  | 3.813
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 15 | 0.3 |  | 4.5
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 15 | 0.3 |  | 4.5
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 9.61 | 0.3 |  | 2.883
| 2022-12-01 | LVL-4 |  | VERTICAL | 1 | 35.96 | 0.3 |  | 10.788
| 2022-12-01 | LVL-2 |  | AREA 1 | 1 |  |  | 302.22
| 2022-12-01 | LVL-2 |  | AREA 2 | 1 |  |  | 107.99
| 2022-12-01 | GF |  | AREA 1 | 1 |  |  | 107.31
| 2022-12-01 | GF |  | VERTICAL | 1 | 33.29 | 1 |  | 33.29
| 2022-12-01 | LVL-29 |  | AREA A | 1 |  |  | 345.85
| 2022-12-01 | LVL-23 | RESI | AREA | 1 |  |  | 123.81
| 2022-12-01 | LVL-17 | HOTEL | AREA 1 | 1 |  |  | 37.32
| 2022-12-01 | LVL-17 | HOTEL | AREA 2 | 1 |  |  | 16.78
| 2022-12-01 | LVL-17 | HOTEL | VERTICAL | 1 | 23.82 | 0.45 |  | 10.719
| 2022-12-01 | LVL-17 | HOTEL | AREA 3 | 1 |  |  | 53.64
| 2022-12-01 | LVL-17 | HOTEL | VERTICAL | 1 | 48.61 | 0.2 |  | 9.722
| 2023-01-01 | GF |  | AREA 1 | 1 |  |  | 101.034 |  | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-01-01 | GF |  | L | 1 | 57.04 | 0.3 |  | 10.2672 | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-01-01 | GF |  | A2 | 1 |  |  | 85.662 |  | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-01-01 | GF |  | L | 1 | 20.26 | 0.3 |  | 3.6468 | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-01-01 | GF |  | A3 | 1 |  |  | 249.39 |  | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-01-01 | GF |  | VERTICAL | 1 | 72.75 | 0.3 |  | 13.095 | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-01-01 | LVL-2 |  | AREA | 1 |  |  | 206.65
| 2023-01-01 | LVL-2 |  | DEDUCTION | 1 |  |  | -78.53
| 2023-01-01 | LVL-2 |  | L | 1 | 31.41 | 0.3 |  | 9.423
| 2023-01-01 | LVL-2 |  | L | 1 | 11.32 | 0.3 |  | 3.396
| 2023-01-01 | LVL-4 |  | AREA | 1 |  |  | 182.45
| 2023-01-01 | LVL-4 |  | L | 1 | 113.5 | 0.3 |  | 34.05
| 2023-01-01 | LVL-23 | RESI | AREA | 1 |  |  | 72.58
| 2023-01-01 | LVL-23 |  | L | 1 | 47.83 | 0.3 |  | 14.349
| 2023-02-01 | GF |  | AREA1 | 1 |  |  | 97.79
| 2023-02-01 | GF |  | L | 1 | 70.2 | 0.3 |  | 21.06
| 2023-02-01 | LVL-4 |  | A1 | 1 |  |  | 15.6
| 2023-02-01 | LVL-4 |  | L | 1 | 12.04 | 0.3 |  | 3.612
| 2023-02-01 | LVL-4 |  | A2 | 1 |  |  | 18.94
| 2023-02-01 | LVL-4 |  | L | 1 | 18.15 | 0.3 |  | 5.445
| 2023-02-01 | LVL-4 |  | A3 | 1 |  |  | 18.94
| 2023-02-01 | LVL-4 |  | L | 1 | 18.15 | 0.3 |  | 5.445
| 2023-02-01 | LVL-4 |  | A4 | 1 |  |  | 18.94
| 2023-02-01 | LVL-4 |  | L | 1 | 18.15 | 0.3 |  | 5.445
| 2023-02-01 | LVL-4 |  | A5 | 1 |  |  | 18.94
| 2023-02-01 | LVL-4 |  | L | 1 | 18.15 | 0.3 |  | 5.445
| 2023-02-01 | LVL-4 |  | A6 | 1 |  |  | 35.21
| 2023-02-01 | LVL-4 |  | L | 1 | 35.2 | 0.3 |  | 10.56
| 2023-02-01 | LVL-4 |  | A7 | 1 |  |  | 31.05
| 2023-02-01 | LVL-4 |  | L | 1 | 29.83 | 0.3 |  | 8.949
| 2023-02-01 | LVL-2 |  | A1 | 1 |  |  | 116.1 |  | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-02-01 | LVL-2 |  | L | 1 | 62.92 | 0.3 |  | 11.3256 | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-02-01 | LVL-2 |  | DEDUCTION | 1 |  |  | -2.496 |  | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-02-01 | LVL-2 |  | L | 1 | 8.04 | 0.3 |  | 1.4472 | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-02-01 | LVL-2 |  | DEDUCTION | 1 |  |  | -2.946 |  | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-02-01 | LVL-2 |  | L | 1 | 9.04 | 0.3 |  | 1.6272 | Variation- Pleasae include this under Variation (Until 60% only)
| 2023-02-01 | GF |  | A1 | 1 |  |  | 274.02 |  | Variation- Pleasae include this under Variation (Until 60% only)
|  | Total Qty |  |  | SQM |  |  | 9951.087 | 592.846
|  | Total Qty |  |  | SQM |  |  | 10543.933

## LPG Tank
AL-SHIRAWI CONTRACTING CO.LLC
PROJECT-PLOT18 BUSINESS BAY Dorchester Hotel
MEASUREMENTS FOR SOFT LANDSCAPE WATERPROOFING WORK
S.NO | Month | Location | DESCRIPTION | NOS | LENGTH | HEIGHT | AREA (M2) | VERT. A (M2) | Dwg Ref
GROUND FLOOR
1 | 2022-10-01 | GF | LPG Tank area | 1 |  |  | 92.39
2 | 2022-10-01 | GF | vertical | 1 | 39.95 | 2.43 |  | 97.0785
3 | 2022-10-01 | GF | vertical | 1 | 22.89 | 0.3 |  | 6.867
|  | Total Qty |  | SQM |  |  | 92.39 | 103.9455
|  | TOTAL |  | SQM |  |  | 196.3355

## Driver Ways
AL-SHIRAWI CONTRACTING CO.LLC
PROJECT-PLOT18 BUSINESS BAY Dorchester Hotel
MEASUREMENTS FOR SOFT LANDSCAPE WATERPROOFING WORK
S.NO | Month | Location | DESCRIPTION | NOS | LENGTH | HEIGHT | AREA (M2) | VERT. A (M2) | Dwg Ref
| 2022-11-01 | GF | DRIVE WAY |  |  |  | 613
| 2022-12-01 | GF | DRIVE WAY |  |  |  | 54.26
| 2023-01-01 | GF | DRIVE WAY |  |  |  | 848.79
| 2023-02-01 | GF | DRIVE WAY |  |  |  | 148.61
|  | Total Qty |  | SQM |  |  | 1664.66 | 0
|  | Total Qty |  | SQM |  |  | 1664.66