## Value of Workdone
|  | Period Ending: |  | 2023-01-30
Bill Ref | Description of Works | Application
|  | Previous (Nov assessment) | This Month (Dec+ Jan) | To Date
| Cumulative | 477692.45 | 70324 | 548016.45
| KCE Claim | 542776.45 | 52304 | 595080.45
| Difference | -65084 | 18020 | -47064

## Summary of Measured Work Done
[7 empty] | Period Ending; |  | 2023-01-30
Measured works
Item | DESCRIPTION | UNIT | Sub-Contract BQ |  |  | Application
|  |  | QTY | RATE | AMOUNT | Last Qty | This Qty | Total Qty | Rate | Amount
A | RCC Walls and Slabs
upto 52mm dia
A.1 | 150mm - 200mm thick | No | 5 | 40 | 200 | 74 | 38 | 112 | 40 | 4480 | 1520
A.2 | 201mm - 250mm thick | No | 5 | 44 | 220 | 734 | 0 | 734 | 44 | 32296 | 0
A.3 | 251mm - 350mm thick | No | 5 | 47 | 235 | 176 | 16 | 192 | 47 | 9024 | 752
A.4 | 351mm - 400mm thick | No | 5 | 52 | 260 | 26 | 0 | 26 | 52 | 1352 | 0
A.4 | 401mm - 500mm thick | No | 5 | 60 | 300 | 410 | 63 | 473 | 60 | 28380 | 3780
0
| 53mm dia 102mm dia | [9 empty] | 0
A.6 | 150mm - 200mm thick | No | 25 | 50 | 1250 | 255 | 0 | 255 | 50 | 12750 | 0
A.7 | 201mm - 250mm thick | No | 25 | 55 | 1375 | 6 | 0 | 6 | 55 | 330 | 0
A.8 | 251mm - 350mm thick | No | 5 | 64 | 320 | 96 | 4 | 100 | 64 | 6400 | 256
A.9 | 351mm - 400mm thick | No | 5 | 67 | 335 | 58 | 19 | 77 | 67 | 5159 | 1273
A.10 | 401mm - 500mm thick | No | 5 | 75 | 375 | 55 | 0 | 55 | 75 | 4125 | 0
0
| 103mm dia 152mm dia | [9 empty] | 0
A.11 | 150mm - 200mm thick | No | 25 | 60 | 1500 | 69 | 2 | 71 | 60 | 4260 | 120
A.12 | 201mm - 250mm thick | No | 25 | 65 | 1625 | 29 | 2 | 31 | 65 | 2015 | 130
A.13 | 251mm - 350mm thick | No | 5 | 78 | 390 | 157 | 128 | 285 | 78 | 22230 | 9984
A.14 | 351mm - 400mm thick | No | 5 | 84 | 420 | 54 | 36 | 90 | 84 | 7560 | 3024
A.15 | 401mm - 500mm thick | No | 5 | 90 | 450 | 53 | 1 | 54 | 90 | 4860 | 90
0
| 153mm dia 202mm dia | [9 empty] | 0
A.16 | 150mm - 200mm thick | No | 25 | 70 | 1750 | 113 | 0 | 113 | 70 | 7910 | 0
A.17 | 201mm - 250mm thick | No | 25 | 74 | 1850 | 132 | 0 | 132 | 74 | 9768 | 0
A.18 | 251mm - 350mm thick | No | 5 | 88 | 440 | 335 | 0 | 335 | 88 | 29480 | 0
A.19 | 351mm - 400mm thick | No | 5 | 95 | 475 | 177 | 1 | 178 | 95 | 16910 | 95
A.20 | 401mm - 500mm thick | No | 5 | 110 | 550 | 206 | 1 | 207 | 110 | 22770 | 110
0
| 203mm dia 302mm dia | [9 empty] | 0
A.21 | 150mm - 200mm thick | No | 25 | 112 | 2800 | 7 | 0 | 7 | 112 | 784 | 0
A.22 | 201mm - 250mm thick | No | 25 | 125 | 3125 | 14 | 0 | 14 | 125 | 1750 | 0
A.23 | 251mm - 350mm thick | No | 5 | 150 | 750 | 46 | 0 | 46 | 150 | 6900 | 0
A.24 | 351mm - 400mm thick | No | 5 | 158 | 790 | 8 | 0 | 8 | 158 | 1264 | 0
A.25 | 401mm - 500mm thick | No | 5 | 175 | 875 | 17 | 0 | 17 | 175 | 2975 | 0
0
B | Scanning | [9 empty] | 0
B.1 | Concrete Scanning to locate Rebar / PT strands with reports | No | 25 | 150 | 3750 | 86 | 23 | 109 | 150 | 16350 | 3450
0
C | Mobilization | [9 empty] | 0
C.1 | Mobilization & demobilization charge for markings less than 5 Nos | No | 20 | 250 | 5000 | 43 | 0 | 43 | 250 | 10750 | 0
C.2 | Mobilization & demobilization charge for markings less than 10 Nos | No | 20 | 200 | 4000 | 44 | 0 | 44 | 200 | 8800 | 0
|  |  |  | Total | 35410 |  |  |  | Total | 281632 | 24584
Prepared by: Manoj Haridas Mob : +971 50 626 6342 ¦ E: manoj@corecut.ae For Corecut Engineering LLC

## VO
|  |  |  | Period ending; |  | 2023-01-30
Variation
Item | Description | unit | Application
|  |  | Last Qty | This Qty | Total Qty | Rate | Amount
A | Variations - recoverable
1 | 53mm dia - 102mm dia - 501mm thick to 700mm thick | No | 7 | 0 | 7 | 105 | 735 | 0
2 | 103mm dia - 152mm dia - 500mm - 700 mm thick | No | 7 | 0 | 7 | 148 | 1036 | 0
3 | 153mm dia - 202mm dia- 500mm thick to 700mm thick | No | 14 | 0 | 14 | 154 | 2156 | 0
4 | 203mm dia - 302mm dia- 700mm thick to 800mm thick | No | 2 | 0 | 2 | 560 | 1120 | 0
5 | 350mm dia - 201mm thixk - 250mm thixk | No | 3 | 0 | 3 | 245 | 735 | 0
| 350mm dia - 251mm thixk - 350mm thixk | No | 1 | 0 | 1 | 260 | 260 | 0
6 | 350mm dia - 350mm thixk - 400mm thixk | No | 1 | 0 | 1 | 280 | 280 | 0
7 | 450mm dia - 201mm thixk - 250mm thixk | No | 3 | 0 | 3 | 740 | 2220 | 0
8 | Cutting of jumpform columns - 3m x 1.6m x 0.5m | No | 2 | 0 | 2 | 6600 | 13200 | 0
9 | Cutting of jumpform columns - 3m x 1.2m x 0.5m | No | 2 | 0 | 2 | 4900 | 9800 | 0
10 | Wall openings 0.6m x 0.6m x .5m | No | 4 | 0 | 4 | 2450 | 9800 | 0
11 | Opening 1.1m x 1.4m x 0.5m | No | 1 | 0 | 1 | 3700 | 3700 | 0
| Container interior demolition and removal | No | 1 | 0 | 1 | 46082.45 | 46082.45 | 0
12 | Cutting of columns - 3.2m x 0.5m x 0.4m | No | 2 | 0 | 2 | 5200 | 10400 | 0
13 | Cutting of wall 7in Hotel GF LV Room: 1250mm x 930mm x 500mm | No | 2 | 0 | 2 | 2900 | 5800 | 0
14 | Wire sawing / wall sawing of plinth: 0.5m x 0.5m x 0.2 | No | 2 | 0 | 2 | 950 | 1900 | 0
15 | Cutting of corewall - 1.2mx0.6mx0.5m | No | 1 | 0 | 1 | 3300 | 3300 | 0
16 | Plinth cutting - 2.3mx1.14mx0.33m | No | 1 | 0 | 1 | 6600 | 6600 | 0
17 | Cutting of beams - 3.6mx0.8mx0.5m | No | 1 | 0 | 1 | 6700 | 6700 | 0
18 | Parapet cutting | LM | 144.4 | 0 | 144.4 | 710 | 102524 | 0
19 | Wet cutting of slab - 1.3mx0.55mx0.2m | No | 2 | 0 | 2 | 3200 | 6400 | 0
20 | Wall Cutting level-29 | No | 1 | 0 | 1 | 7300 | 7300 | 0
21 | Planther box-Level-17 (E11/510) | No | 1 | 0 | 1 | 40600 | 40600 | 16240 | 20300 | 20300 | 36540 | 16240
22 | Slab cutting level-24,25,29 (E11/637) | No | 4 | 7 | 11 | 2800 | 30800 | 22120 | 5600 | 3080 | 27720 | 22120
23 | 21.42M Length x 1.15-0.85-0.00M H x 0.2M T- (QT-2023-0017) | No | 0 | 1 | 1 | 8200 | 8200 | 7380
| Total Variations | [5 empty] | 321648.45 | 45740
24584
Note on J42: Himal Kosala: Only approved 90% from the total variation, until rate approval
Note on K42: Himal Kosala: Previous certified
Note on L42: Himal Kosala: Balance to Certified
Note on J43: Himal Kosala: Only approved 90% from the total variation, until rate approval
Note on K43: Himal Kosala: Previous Certified
Note on L43: Himal Kosala: Balance to certifed
Note on J44: Himal Kosala: 90% until Variation approval