## Value of Workdone
|  | Period Ending: |  | 2023-01-30
Bill Ref | Description of Works | Application
|  | Previous (Nov assessment) | This Month (Dec+ Jan) | To Date
| Cumulative | 398708.45 | 78984 | 477692.45

## Summary of Measured Work Done
[7 empty] | Period Ending; |  | 2023-01-30
Measured works
Item | DESCRIPTION | UNIT | Sub-Contract BQ |  |  | Application
|  |  | QTY | RATE | AMOUNT | Last Qty | This Qty | Total Qty | Rate | Amount
A | RCC Walls and Slabs
upto 52mm dia
A.1 | 150mm - 200mm thick | No | 5 | 40 | 200 | 30 | 44 | 74 | 40 | 2960 | 1200
A.2 | 201mm - 250mm thick | No | 5 | 44 | 220 | 367 | 367 | 734 | 44 | 32296 | 16148
A.3 | 251mm - 350mm thick | No | 5 | 47 | 235 | 3 | 173 | 176 | 47 | 8272 | 141
A.4 | 351mm - 400mm thick | No | 5 | 52 | 260 | 0 | 26 | 26 | 52 | 1352 | 0
A.4 | 401mm - 500mm thick | No | 5 | 60 | 300 | 18 | 392 | 410 | 60 | 24600 | 1080
0
| 53mm dia 102mm dia | [9 empty] | 0
A.6 | 150mm - 200mm thick | No | 25 | 50 | 1250 | 12 | 243 | 255 | 50 | 12750 | 600
A.7 | 201mm - 250mm thick | No | 25 | 55 | 1375 | 0 | 6 | 6 | 55 | 330 | 0
A.8 | 251mm - 350mm thick | No | 5 | 64 | 320 | 11 | 85 | 96 | 64 | 6144 | 704
A.9 | 351mm - 400mm thick | No | 5 | 67 | 335 | 5 | 53 | 58 | 67 | 3886 | 335
A.10 | 401mm - 500mm thick | No | 5 | 75 | 375 | 4 | 51 | 55 | 75 | 4125 | 300
0
| 103mm dia 152mm dia | [9 empty] | 0
A.11 | 150mm - 200mm thick | No | 25 | 60 | 1500 | 4 | 65 | 69 | 60 | 4140 | 240
A.12 | 201mm - 250mm thick | No | 25 | 65 | 1625 | 0 | 29 | 29 | 65 | 1885 | 0
A.13 | 251mm - 350mm thick | No | 5 | 78 | 390 | 9 | 148 | 157 | 78 | 12246 | 702
A.14 | 351mm - 400mm thick | No | 5 | 84 | 420 | 3 | 51 | 54 | 84 | 4536 | 252
A.15 | 401mm - 500mm thick | No | 5 | 90 | 450 | 1 | 52 | 53 | 90 | 4770 | 90
0
| 153mm dia 202mm dia | [9 empty] | 0
A.16 | 150mm - 200mm thick | No | 25 | 70 | 1750 | 0 | 113 | 113 | 70 | 7910 | 0
A.17 | 201mm - 250mm thick | No | 25 | 74 | 1850 | 4 | 128 | 132 | 74 | 9768 | 296
A.18 | 251mm - 350mm thick | No | 5 | 88 | 440 | 94 | 241 | 335 | 88 | 29480 | 8272
A.19 | 351mm - 400mm thick | No | 5 | 95 | 475 | 83 | 94 | 177 | 95 | 16815 | 7885
A.20 | 401mm - 500mm thick | No | 5 | 110 | 550 | 2 | 204 | 206 | 110 | 22660 | 220
0
| 203mm dia 302mm dia | [9 empty] | 0
A.21 | 150mm - 200mm thick | No | 25 | 112 | 2800 | 0 | 7 | 7 | 112 | 784 | 0
A.22 | 201mm - 250mm thick | No | 25 | 125 | 3125 | 0 | 14 | 14 | 125 | 1750 | 0
A.23 | 251mm - 350mm thick | No | 5 | 150 | 750 | 7 | 39 | 46 | 150 | 6900 | 1050
A.24 | 351mm - 400mm thick | No | 5 | 158 | 790 | 0 | 8 | 8 | 158 | 1264 | 0
A.25 | 401mm - 500mm thick | No | 5 | 175 | 875 | 0 | 17 | 17 | 175 | 2975 | 0
0
B | Scanning | [9 empty] | 0
B.1 | Concrete Scanning to locate Rebar / PT strands with reports | No | 25 | 150 | 3750 | 30 | 56 | 86 | 150 | 12900 | 4500
0
C | Mobilization | [9 empty] | 0
C.1 | Mobilization & demobilization charge for markings less than 5 Nos | No | 20 | 250 | 5000 | 2 | 41 | 43 | 250 | 10750 | 500
C.2 | Mobilization & demobilization charge for markings less than 10 Nos | No | 20 | 200 | 4000 | 2 | 42 | 44 | 200 | 8800 | 400
|  |  |  | Total | 35410 |  |  |  | Total | 257048 | 44915
Prepared by: Manoj Haridas Mob : +971 50 626 6342 ¦ E: manoj@corecut.ae For Corecut Engineering LLC

## VO
|  |  |  | Period ending; |  | 2023-01-30
Variation
Item | Description | unit | Application
|  |  | Last Qty | This Qty | Total Qty | Rate | Amount
A | Variations - recoverable
1 | 53mm dia - 102mm dia - 501mm thick to 700mm thick | No | 1 | 6 | 7 | 105 | 735 | 105
2 | 103mm dia - 152mm dia - 500mm - 700 mm thick | No | 1 | 6 | 7 | 148 | 1036 | 148
3 | 153mm dia - 202mm dia- 500mm thick to 700mm thick | No | 4 | 10 | 14 | 154 | 2156 | 616
4 | 203mm dia - 302mm dia- 700mm thick to 800mm thick | No |  | 2 | 2 | 560 | 1120 | 0
5 | 350mm dia - 201mm thixk - 250mm thixk | No |  | 3 | 3 | 245 | 735 | 0
| 350mm dia - 251mm thixk - 350mm thixk | No |  | 1 | 1 | 260 | 260 | 0
6 | 350mm dia - 350mm thixk - 400mm thixk | No |  | 1 | 1 | 280 | 280 | 0
7 | 450mm dia - 201mm thixk - 250mm thixk | No |  | 3 | 3 | 740 | 2220 | 0
8 | Cutting of jumpform columns - 3m x 1.6m x 0.5m | No |  | 2 | 2 | 6600 | 13200 | 0
9 | Cutting of jumpform columns - 3m x 1.2m x 0.5m | No |  | 2 | 2 | 4900 | 9800 | 0
10 | Wall openings 0.6m x 0.6m x .5m | No |  | 4 | 4 | 2450 | 9800 | 0
11 | Opening 1.1m x 1.4m x 0.5m | No |  | 1 | 1 | 3700 | 3700 | 0
| Container interior demolition and removal | No |  | 1 | 1 | 46082.45 | 46082.45 | 0
12 | Cutting of columns - 3.2m x 0.5m x 0.4m | No |  | 2 | 2 | 5200 | 10400 | 0
13 | Cutting of wall 7in Hotel GF LV Room: 1250mm x 930mm x 500mm | No |  | 2 | 2 | 2900 | 5800 | 0
14 | Wire sawing / wall sawing of plinth: 0.5m x 0.5m x 0.2 | No |  | 2 | 2 | 950 | 1900 | 0
15 | Cutting of corewall - 1.2mx0.6mx0.5m | No |  | 1 | 1 | 3300 | 3300 | 0
16 | Plinth cutting - 2.3mx1.14mx0.33m | No |  | 1 | 1 | 6600 | 6600 | 0
17 | Cutting of beams - 3.6mx0.8mx0.5m | No |  | 1 | 1 | 6700 | 6700 | 0
18 | Parapet cutting | LM |  | 144.4 | 144.4 | 710 | 102524 | 0
19 | Wet cutting of slab - 1.3mx0.55mx0.2m | No | 0 | 0 | 2 | 3200 | 6400 | 0
20 | Wall Cutting level-29 | No | 1 | 0 | 1 | 7300 | 7300 | 7300
21 | Planther box-Level-17 (E11/510) (80% work completed) | No | 1 | 0 | 1 | 40600 | 32480 | 20300
22 | Slab cutting level-24,25,29 (E11/637) | No | 4 | 0 | 4 | 2800 | 11200 | 5600
| Total Variations | [5 empty] | 285728.45 | 34069
44915
Note on J42: Himal Kosala: 50% only, site instruction, and WIR or supportings
Note on J43: Himal Kosala: 50% only, site instruction, and WIR or supportings