## Sheet1
No | Descrition | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous Amount | Current Amount | Cumulative Amount
Supply and Installation of Stair Nosing
1 | Stair nosing- Stair 1 Residence ; B2 to GF level | 75 | m | 29 | 2175 | 75 | 0 | 75 | 2175 | 0 | 2175
2 | Stair nosing- Stair 2-Residence; B2 to 4th Floor level | 208 | m | 29 | 6032 | 208 | 0 | 208 | 6032 | 0 | 6032
3 | Stair nosing- Stair 3 Residence; B2 to level 31 | 1144 | m | 29 | 33176 | 1144 | 0 | 1144 | 33176 | 0 | 33176
4 | Stair nosing- Stair 4 Residence; B2 to level 31 | 1144 | m | 29 | 33176 | 1144 | 0 | 1144 | 33176 | 0 | 33176
5 | Stair nosing- Stair 5 Residence; B2 to GF level | 89 | m | 29 | 2581 | 89 | 0 | 89 | 2581 | 0 | 2581
6 | Stair nosing- Stair 6- Residence; B2 to level 29 | 1036 | m | 29 | 30044 | 1036 | 0 | 1036 | 30044 | 0 | 30044
7 | Stair nosing- Stair 7; Hotel B2 to roof | 1074 | m | 29 | 31146 | 1074 | 0 | 1074 | 31146 | 0 | 31146
8 | Stair nosing- Stair 8; Hotel 82 to roof | 1074 | m | 29 | 31146 | 1074 | 0 | 1074 | 31146 | 0 | 31146
9 | Stair nosing- Stair 9; Hotel B2 to GF level | 80 | m | 29 | 2320 | 80 | 0 | 80 | 2320 | 0 | 2320
10 | Stair nosing- Stair 10; Hotel B2 to Ballroom level | 73 | m | 29 | 2117 | 73 | 0 | 73 | 2117 | 0 | 2117
11 | Installation of stair nosing | 5997 | m | 8 | 47976 | 0 | 4761.32 | 4761.32 | 0 | 25520.6752 | 25520.6752 | Balance 10% will realesed after full work completion and TOC
[5 empty] | 221889 |  |  |  | 173913 | 25520.6752 | 199433.6752 | 89.88%