## AR template
APPROVAL REQUEST
Approval Type: | Award of Works / Services: |  | Variation Order: | Provisional Sum Expenditure: |  | Tender List: | Other: …..................................
Description of Budget: BOH EQUIPMENT-Commercial Kitchen and Laundry
Vendor's Name: Elenco Trading Establishment
Description of Works: Food Service, Waste Management and Laundry Equipment
Approval Request Number: |  | AR 370 |  | Date: |  | 2023-02-20
Project Name: |  | Dorchester, Business Bay |  | Master Developer: |  | Business Bay LLC
Project Description: |  | Plot-18 |  | Employer: |  | Sky Palace Real Estate Development LLC
Location: |  | Plot 18, Business Bay, Dubai |  | Development Manager: |  | Omniyat Concept Investment LLC
Request:
The revised staff dining counter of the B1 staff resturent was issued by Omniyat (on the request of Dochester Technical Team), revising numarous kitchen equipment. Please refer to the attached e-mail approvals, the negotiated additional cost of the equipment with the revised specification is AED 415,750.00. Accordingly, we seek approval to expend the final negotiated lump sum amount of AED 415,750.00 to proceed with the procurement of revised kitchen equipment.
DESCRIPTION OF WORKS | [6 empty] | VALUE
Expected Expenditure: Food Service, Waste Management and Laundry Equipment | [6 empty] | 415750
Contract Value for Approval (excl. VAT) | [6 empty] | 415750
BUDGET | [6 empty] | VALUE
Budget | [6 empty] | 6751750
Expected Expenditure | [6 empty] | 415750
Previously Approved | [6 empty] | 6336000
Remaining Budget | [6 empty] | 0
Gain / (Loss) | [6 empty] | 0
We certify that the above to be true and correct for and on behalf of Omniyat Concept Investments LLC.
DEVELOPMENT MANAGER CERTIFICATION | [6 empty] | COMMERCIAL REVIEW
Name: | TIAGO MARQUES DA GAMA |  |  |  | MUHAMMED KOCAK |  | CHRISTOPHER THOMAS
Designation: | Senior Project Manager |  |  |  | Senior Project Manager |  | Commercial Director
Signature: | …………………………….. |  |  |  | …………………………….. |  | …………………………..
Date: | …………………………….. |  |  |  | …………………………….. |  | …………………………..
APPROVAL
Omniyat Concept Investments LLC approval to proceed as detailed herein.
Name: | PETER STEPHENSON |  |  |  |  | ISHAN GARGA
Designation: | Managing Director |  |  |  |  | Managing Director
| Development |  |  |  |  | Corporate Finance & Investments
Signature: | ………………………….. |  |  |  |  | …………………………..
Date: | ………………………….. |  |  |  |  | …………………………..