## Adjustments
Sky Palaces Real Estate Development LLC
Adjustments
Project: Plot - 18 |  |  |  | Certificate Date:
Contractor:Khansaheb Civil Engineering LLC |  |  |  | Certificate No:
Contract :Base Build Works |  |  |  | Currency: | AED
SN | Description | Bill Category | IPA Ref | Amount | Remarks
01 | Visa Cost of labours | Labour cost | IPA 08 | 2797.41 | Visa cost is already included in the hiring rate | Category | Amount
02 | Visa Cost of labours | Labour cost | IPA 09 | 1259.8 | Visa cost is already included in the hiring rate | Material Cost | 77124.49
03 | Included VAT | Overheads | IPA 10 | 521.189 | Telecommunication, Chris McCann (Petty Cash) | Labour cost | 4057.21
04 | TXM Manpower cost adjustment from material transaction- August 22 | Material Cost | IPA 10 | 9071.54 |  | Plant Cost | 0
05 | TXM Manpower cost adjustment from material transaction- September 22 | Material Cost | IPA 10 | 9384.76 |  | Overheads | 48681.189
06 | TXM Manpower cost adjustment from material transaction- October 22 | Material Cost | IPA 10 | 9051.18 |  | TOTAL | 129862.889
07 | TXM Manpower cost adjustment from material transaction- November 22 | Material Cost | IPA 10 | 9951.73
08 | TXM Manpower cost adjustment from material transaction- November 22 | Material Cost | IPA 10 | 1583.52
| TXM Manpower cost adjustment from material transaction- December 22 | Material Cost | IPA 11 | 19197
| TXM Manpower cost adjustment from material transaction- January 23 | Material Cost | IPA 12 | 18884.76
09 | IT costs adjustment from Overhead transaction for June 22 | Overheads | IPA 10 | 8370.53
10 | IT costs adjustment from Overhead transaction July 22 | Overheads | IPA 10 | 11789.47
11 | IT costs adjustment from Overhead transaction August 22 | Overheads | IPA 10 | 14000
12 | IT costs adjustment from Overhead transaction September 22 | Overheads | IPA 10 | 14000
129862.889