## Annexure 7-Overhead Summary
Sky Palaces Real Estate Development LLC
Annexure 07 - Overhead Cost Breakdown
Project: | Plot - 18 |  | Certificate Date:
Contractor: | Khansaheb Civil Engineering LLC |  | Certificate No:
Contract : | Base Build Works |  | Currency: | AED
Sn | KCE IPA Section Description | Previous | This Month | Cumulative
1 | General Preliminaries | 1121275.85 | 164904.35 | 1286180.2
2 | Adjustments | -48681.189 | 0 | -48681.189
TOTAL |  | 1072594.661 | 164904.35 | 1237499.011

## Data
OH Monthly Transactions - January 2023
Cost Code | Description | Fin Date | Cat | Src | Tran Type | Key | Int Ref | Ext Ref | Tran Date | Effective Date | Description | Composite Description | Amount | WA Ref. | Ramarks
XXX900060621 | Def Fees and charges Other fee - charges | 2023-01-31 | O | GL | JNL |  | 158661 |  | 2023-01-31 | 2023-01-31 | Credit card transactions_9134-RTA - Fees to obtain access NOC-1432191555-04/01/2023-201A22002 (JAN-2023) | 158661,O,Credit card transactions_9134-RTA - Fees to obtain access NOC-1432191555-04/01/2023-201A22002 (JAN-2023) | 120 |  | Invoice attached
XXX900060621 | Def Fees and charges Other fee - charges | 2023-01-31 | O | GL | JNL |  | 158661 |  | 2023-01-31 | 2023-01-31 | Credit card transactions_9134-DDA - fees to renew BCC-1434134628-06/01/2023-201A22002 (JAN-2023) | 158661,O,Credit card transactions_9134-DDA - fees to renew BCC-1434134628-06/01/2023-201A22002 (JAN-2023) | 5020 |  | Invoice attached
XXX900060621 | Def Fees and charges Other fee - charges | 2023-01-31 | O | GL | JNL |  | 158661 |  | 2023-01-31 | 2023-01-31 | Credit card transactions_9134-DM - Fees to obtain a sand disposal permit-202300048472-26/01/2023-201A22002 (JAN-2023) | 158661,O,Credit card transactions_9134-DM - Fees to obtain a sand disposal permit-202300048472-26/01/2023-201A22002 (JAN-2023) | 230 |  | Invoice attached
XXX900060621 | Def Fees and charges Other fee - charges | 2023-01-31 | O | GL | JNL |  | 158661 |  | 2023-01-31 | 2023-01-31 | Credit card transactions_9134-RTA - Fees to obtain diversion NOC-1449951882-27/01/2023-201A22002 (JAN-2023) | 158661,O,Credit card transactions_9134-RTA - Fees to obtain diversion NOC-1449951882-27/01/2023-201A22002 (JAN-2023) | 220 |  | Invoice attached
XXXD00160621 | Def Direct Costs at Site Other fee - charges | 2023-01-31 | O | CB | PCP | 1721 | JAN/11817/10 |  | 2023-01-03 | 2023-01-03 | 04193-MURALI N-201A22002-NOC CHARGES | 158195,O,04193-MURALI N-201A22002-NOC CHARGES | 5250 |  | Invoice attached
XXXD00160621 | Def Direct Costs at Site Other fee - charges | 2023-01-31 | O | GL | JNL |  | 158624 |  | 2023-01-31 | 2023-01-31 | Replacement Of Lost No Plate | 158624,O,Replacement Of Lost No Plate | 70 |  | Details attached
XXXD00160701 | Def Direct Costs at Site Communication expense - landline and fax usage | 2023-01-31 | O | PL | PINN | EMIR032 | 2301PL000425 | 0129762458 | 2023-01-12 | 2022-12-31 | DU-DEC 2022 (Internet broad band-1) | 31/12/22,0129762458,EMIR032,Emirates Integrated Telecommunication Corporation | 3020 |  | Invoice attached
XXXD00160701 | Def Direct Costs at Site Communication expense - landline and fax usage | 2023-01-31 | O | PL | PINN | EMIR032 | 2301PL000425 | 0129762458 | 2023-01-12 | 2022-12-31 | DU-DEC 2022 (Internet broad band-2) | 31/12/22,0129762458,EMIR032,Emirates Integrated Telecommunication Corporation | 1580 |  | Invoice attached
XXXD00160701 | Def Direct Costs at Site Communication expense - landline and fax usage | 2023-01-31 | O | PL | PINN | ETIS001 | 2301PL000776 | DEC-2022 (C1) | 2023-01-18 | 2023-01-01 | Tel Cost-0565456086-201A22002-DORCHESTER HOTEL-HIRED--SANEESH MOHAN (DEC-2022) | 31/12/22,DEC-2022 (C1),ETIS001,Emirates Telecommunications Group Company (ETISALAT Group) PJSC | 105.35 |  | Invoice attached
XXXD00160701 | Def Direct Costs at Site Communication expense - landline and fax usage | 2023-01-31 | O | PL | PINN | ETIS001 | 2301PL000776 | DEC-2022 (C1) | 2023-01-18 | 2023-01-01 | Tel Cost-0509394368-201A22002-DORCHESTER HOTEL-DORCHESTER FACE STATION (DEC-2022) | 31/12/22,DEC-2022 (C1),ETIS001,Emirates Telecommunications Group Company (ETISALAT Group) PJSC | 100 |  | Invoice attached
XXXD00160701 | Def Direct Costs at Site Communication expense - landline and fax usage | 2023-01-31 | O | PL | PINN | ETIS001 | 2301PL000776 | DEC-2022 (C1) | 2023-01-18 | 2023-01-01 | Tel Cost-0501894373-201A22002-DORCHESTER HOTEL-DORCHESTER FACE STATION (DEC-2022) | 31/12/22,DEC-2022 (C1),ETIS001,Emirates Telecommunications Group Company (ETISALAT Group) PJSC | 63.2 |  | Invoice attached
XXXD00160803 | Def Direct Costs at Site Utilities - water external supply | 2023-01-31 | O | PL | PINN | DUBA003 | 2301PL000199 | 1800046239 | 2023-01-09 | 2023-01-06 | SWEET WATER CHGS - DEC'2022 | 01/01/23,1800046239,DUBA003,Dubai Aluminium PJSC | 2475 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 156782 | 1750731 | 2023-01-03 | 2023-01-03 | Mouse Logitec Wireless Black - New | 156782,O,Mouse Logitec Wireless Black - New | 50 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 157743 | 1755247 | 2023-01-11 | 2023-01-11 | EVOLIS-YMCKO Color Ribbon - New | 157743,O,EVOLIS-YMCKO Color Ribbon - New | 440 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 157749 | 1760481 | 2023-01-19 | 2023-01-19 | Laptop Bag HP - New | 157749,O,Laptop Bag HP - New | 90 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 157749 | 1760482 | 2023-01-19 | 2023-01-19 | Mouse Logitec Wireless Black - New | 157749,O,Mouse Logitec Wireless Black - New | 50 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 157749 | 1760485 | 2023-01-19 | 2023-01-19 | Mouse Logitec Wireless Black - New | 157749,O,Mouse Logitec Wireless Black - New | 50 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 157749 | 1760486 | 2023-01-19 | 2023-01-19 | Mouse Logitec Wireless Black - New | 157749,O,Mouse Logitec Wireless Black - New | 50 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 158492 | 1762337 | 2023-01-25 | 2023-01-25 | Laptop Bag HP - New | 158492,O,Laptop Bag HP - New | 90 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | ST | ISS |  | 158492 | 1762339 | 2023-01-25 | 2023-01-25 | Mouse Logitec Wireless Black - New | 158492,O,Mouse Logitec Wireless Black - New | 50 |  | Invoice attached
XXXD00160905 | Def Direct Costs at Site Computers & Accessories | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 22130.5
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | PL | PINV | ALJA007 | 2212PL001701 | T-19660 | 2023-01-10 | 2022-12-24 | Fire Extinguisher Refilling & Servicing | 24/12/22,T-19660,ALJA007,Al Jas Technical Services LLC | 3936 |  | Invoice attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750789 | 2023-01-02 | 2023-01-02 | Fire Extinguisher Inspection Tag | 156807,O,Fire Extinguisher Inspection Tag | 85 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750793 | 2023-01-02 | 2023-01-02 | Safety Shoe for workers Saudi 59102 SIZE 40 | 156809,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750794 | 2023-01-02 | 2023-01-02 | Safety Shoe for workers Saudi 59102 SIZE 42 | 156809,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750795 | 2023-01-02 | 2023-01-02 | Safety Shoe for workers Saudi 59102 SIZE 43 | 156809,O,Safety Shoe for workers Saudi 59102 SIZE 43 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750853 | 2023-01-02 | 2023-01-02 | Safety Shoe for workers Saudi 59102 SIZE 45 | 156809,O,Safety Shoe for workers Saudi 59102 SIZE 45 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750854 | 2023-01-02 | 2023-01-02 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 156809,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750855 | 2023-01-02 | 2023-01-02 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 156809,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 210.36 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750866 | 2023-01-02 | 2023-01-02 | Safety Shoe for workers Saudi 59102 SIZE 40 | 156811,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750867 | 2023-01-02 | 2023-01-02 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 156811,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 207 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750890 | 2023-01-03 | 2023-01-03 | Safety Shoe for workers Saudi 59102 SIZE 42 | 156819,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750891 | 2023-01-03 | 2023-01-03 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 156819,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750892 | 2023-01-03 | 2023-01-03 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 156819,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 70.12 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750936 | 2023-01-04 | 2023-01-04 | Safety Shoe for workers Saudi 59102 SIZE 42 | 156859,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 195 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1750937 | 2023-01-04 | 2023-01-04 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 156859,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 210.58 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751225 | 2023-01-06 | 2023-01-06 | Safety Shoe for workers Saudi 59102 SIZE 42 | 156981,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751226 | 2023-01-06 | 2023-01-06 | Safety Shoe for workers Saudi 59102 SIZE 44 | 156981,O,Safety Shoe for workers Saudi 59102 SIZE 44 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751227 | 2023-01-06 | 2023-01-06 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 156981,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751228 | 2023-01-06 | 2023-01-06 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 156981,O,Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751663 | 2023-01-07 | 2023-01-07 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | 157003,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | 750 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751664 | 2023-01-07 | 2023-01-07 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | 157003,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | 1500 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751665 | 2023-01-07 | 2023-01-07 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 | 157003,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 | 750 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751669 | 2023-01-07 | 2023-01-07 | Disposable Face Mask Blue 3 Ply (1x50) Local | 157004,O,Disposable Face Mask Blue 3 Ply (1x50) Local | 326.56 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1751671 | 2023-01-07 | 2023-01-07 | Safety Goggles - Clear - Globus - Riley - Bm08 | 157005,O,Safety Goggles - Clear - Globus - Riley - Bm08 | 660 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755228 | 2023-01-11 | 2023-01-11 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157204,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755229 | 2023-01-11 | 2023-01-11 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157204,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755230 | 2023-01-11 | 2023-01-11 | Safety Shoe for workers Saudi 59102 SIZE 43 | 157204,O,Safety Shoe for workers Saudi 59102 SIZE 43 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755231 | 2023-01-11 | 2023-01-11 | Safety Shoe for workers Saudi 59102 SIZE 44 | 157204,O,Safety Shoe for workers Saudi 59102 SIZE 44 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755232 | 2023-01-11 | 2023-01-11 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157204,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755233 | 2023-01-11 | 2023-01-11 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 157204,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 210.58 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755234 | 2023-01-11 | 2023-01-11 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157204,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 70.12 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755235 | 2023-01-11 | 2023-01-11 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 157204,O,Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 140.39 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755509 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157240,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 195 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755510 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 41 | 157240,O,Safety Shoe for workers Saudi 59102 SIZE 41 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755511 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157240,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 195 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755512 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 43 | 157240,O,Safety Shoe for workers Saudi 59102 SIZE 43 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755513 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157240,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 725.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755514 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 157240,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 140.39 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755515 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157240,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 140.24 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755525 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157242,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755527 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157242,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 260 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755528 | 2023-01-12 | 2023-01-12 | Safety Shoe for workers Saudi 59102 SIZE 44 | 157242,O,Safety Shoe for workers Saudi 59102 SIZE 44 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755529 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 157242,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 207 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755530 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157242,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755531 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 157242,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 210.58 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1755533 | 2023-01-12 | 2023-01-12 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 157242,O,Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756079 | 2023-01-13 | 2023-01-13 | Safety Shoe For Staff 59351 Size 42 | 157313,O,Safety Shoe For Staff 59351 Size 42 | 80 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756345 | 2023-01-14 | 2023-01-14 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157371,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756346 | 2023-01-14 | 2023-01-14 | Safety Shoe for workers Saudi 59102 SIZE 44 | 157371,O,Safety Shoe for workers Saudi 59102 SIZE 44 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756347 | 2023-01-14 | 2023-01-14 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157371,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756348 | 2023-01-14 | 2023-01-14 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157371,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 70.12 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756475 | 2023-01-16 | 2023-01-16 | Safety Shoe for workers Saudi 59102 SIZE 41 | 157430,O,Safety Shoe for workers Saudi 59102 SIZE 41 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756476 | 2023-01-16 | 2023-01-16 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157430,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756477 | 2023-01-16 | 2023-01-16 | Safety Shoe for workers Saudi 59102 SIZE 43 | 157430,O,Safety Shoe for workers Saudi 59102 SIZE 43 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756478 | 2023-01-16 | 2023-01-16 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 157430,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 207 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756479 | 2023-01-16 | 2023-01-16 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157430,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 140.24 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756744 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 39 | 157491,O,Safety Shoe for workers Saudi 59102 SIZE 39 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756746 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157491,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756748 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 41 | 157491,O,Safety Shoe for workers Saudi 59102 SIZE 41 | 325 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756762 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157491,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 260 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756763 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 43 | 157491,O,Safety Shoe for workers Saudi 59102 SIZE 43 | 260 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756764 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 157491,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 1656 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756766 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157491,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 3444.66 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756768 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 157491,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 701.93 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756769 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157491,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 420.71 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756772 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 157491,O,Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 280.77 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756773 | 2023-01-17 | 2023-01-17 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Large | 157491,O,Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Large | 342 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756801 | 2023-01-17 | 2023-01-17 | Safety Shoe For Staff 59351 Size 43 | 157493,O,Safety Shoe For Staff 59351 Size 43 | 80 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756817 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157495,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756818 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157495,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756872 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157505,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756873 | 2023-01-17 | 2023-01-17 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157505,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756874 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157505,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1756875 | 2023-01-17 | 2023-01-17 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157505,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 70.12 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1757469 | 2023-01-18 | 2023-01-18 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157588,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1757470 | 2023-01-18 | 2023-01-18 | Safety Shoe for workers Saudi 59102 SIZE 41 | 157588,O,Safety Shoe for workers Saudi 59102 SIZE 41 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1757471 | 2023-01-18 | 2023-01-18 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157588,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1757472 | 2023-01-18 | 2023-01-18 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157588,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 725.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760347 | 2023-01-19 | 2023-01-19 | Safety Shoe for workers Saudi 59102 SIZE 41 | 157711,O,Safety Shoe for workers Saudi 59102 SIZE 41 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760350 | 2023-01-19 | 2023-01-19 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157711,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760351 | 2023-01-19 | 2023-01-19 | Safety Shoe for workers Saudi 59102 SIZE 45 | 157711,O,Safety Shoe for workers Saudi 59102 SIZE 45 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760353 | 2023-01-19 | 2023-01-19 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157711,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760354 | 2023-01-19 | 2023-01-19 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 157711,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760356 | 2023-01-19 | 2023-01-19 | Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 157711,O,Blue Pant/Shirt 180 Gsm Full Sleeve -XL | 70.12 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1760357 | 2023-01-19 | 2023-01-19 | Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | 157711,O,Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | 70.56 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | PL | PINV | SALE001 | 2301PL001779 | 109471 | 2023-01-31 | 2023-01-19 | Safety induction Sticker | 19/01/23,109471,SALE001,Saleem Jacobson Trading | 3000 |  | Invoice attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761287 | 2023-01-21 | 2023-01-21 | Safety Shoe for workers Saudi 59102 SIZE 40 | 157885,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 130 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761288 | 2023-01-21 | 2023-01-21 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 157885,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 414 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761293 | 2023-01-21 | 2023-01-21 | Safety Shoe for workers Saudi 59102 SIZE 42 | 157886,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761294 | 2023-01-21 | 2023-01-21 | Safety Shoe for workers Saudi 59102 SIZE 44 | 157886,O,Safety Shoe for workers Saudi 59102 SIZE 44 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761295 | 2023-01-21 | 2023-01-21 | Safety Shoe for workers Saudi 59102 SIZE 45 | 157886,O,Safety Shoe for workers Saudi 59102 SIZE 45 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761296 | 2023-01-21 | 2023-01-21 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 157886,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761297 | 2023-01-21 | 2023-01-21 | Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 157886,O,Blue Pant/Shirt 180 Gsm Full Sleeve -2XL | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1761298 | 2023-01-21 | 2023-01-21 | Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | 157886,O,Blue Pant/Shirt 180 Gsm Full Sleeve -3XL | 70.56 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1762964 | 2023-01-25 | 2023-01-25 | Safety Shoe for workers Saudi 59102 SIZE 40 | 158094,O,Safety Shoe for workers Saudi 59102 SIZE 40 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1762970 | 2023-01-25 | 2023-01-25 | Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Medium | 158094,O,Beige Pant/Shirt 180 Gsm Full Sleeve for Chargehand - Medium | 114 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763009 | 2023-01-25 | 2023-01-25 | Safety Shoe For Staff 59351 Size 43 | 158112,O,Safety Shoe For Staff 59351 Size 43 | 80 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763048 | 2023-01-25 | 2023-01-25 | Safety Shoe for workers Saudi 59102 SIZE 39 | 158117,O,Safety Shoe for workers Saudi 59102 SIZE 39 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763050 | 2023-01-25 | 2023-01-25 | Safety Shoe for workers Saudi 59102 SIZE 42 | 158117,O,Safety Shoe for workers Saudi 59102 SIZE 42 | 195 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763052 | 2023-01-25 | 2023-01-25 | Safety Shoe for workers Saudi 59102 SIZE 44 | 158117,O,Safety Shoe for workers Saudi 59102 SIZE 44 | 65 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763054 | 2023-01-25 | 2023-01-25 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 158117,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 414 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763056 | 2023-01-25 | 2023-01-25 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 158117,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 362.6 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763058 | 2023-01-25 | 2023-01-25 | Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 158117,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Large | 70.19 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | RTN |  |  | 1763574 | 2023-01-25 | 2023-01-25 | Blue Pant/Shirt 180 Gsm Full Sleeve - Small | 158248,O,Blue Pant/Shirt 180 Gsm Full Sleeve - Small | -207 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1763576 | 2023-01-25 | 2023-01-25 | Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 158249,O,Blue Pant/Shirt 180 Gsm Full Sleeve -Medium | 181.3 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1768323 | 2023-01-30 | 2023-01-30 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | 158387,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 8 | 375 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1768324 | 2023-01-30 | 2023-01-30 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | 158387,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 9 | 2250 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1768325 | 2023-01-30 | 2023-01-30 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 | 158387,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 10 | 750 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | ST | ISS |  |  | 1768326 | 2023-01-30 | 2023-01-30 | Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 11 | 158387,O,Hand Gloves 15g Nylon + Spandex with Washed Micro Foam Size 11 | 375 |  | LPO and details attached
XXXD00161001 | Def Direct Costs at Site Health and safety - material items | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 15
XXXD00161003 | Def Direct Costs at Site First-aid and medical expenses | 2023-01-31 | O | PL | PINV | DANA002 | 2301PL000667 | INV-003172 | 2023-01-18 | 2022-12-01 | Third Party for Cradle Operatives | 15/09/22,INV-003172,DANA002,Danat Alkhaleej for Safety Consultancy | 600 |  | Invoice attached
XXXD00161003 | Def Direct Costs at Site First-aid and medical expenses | 2023-01-31 | O | PL | PINN | YORK004 | 2301PL000478 | 2222154 | 2023-01-12 | 2023-01-12 | PCR COVID TESTS (81 SAMPLES @ AED 85) (SEPT'2022 TO NOV'2022) | 31/12/22,2222154,YORK004,York Diagnostic Laboratories DMCC | 1445 |  | Invoice attached
XXXD00161111 | Def Direct Costs at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | CB | PCP | 1766 | JAN/11832/16 |  | 2023-01-13 | 2023-01-13 | 27743-CHRIS McCANN-201A22002 | 158390,O,27743-CHRIS McCANN-201A22002 | 7063.76 |  | Accounts to provide details
XXXD00161111 | Def Direct Costs at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | CB | PCP | 1796 | JAN/11836/21 |  | 2023-01-23 | 2023-01-23 | 27743-CHRIS McCANN-201A22002 | 158467,O,27743-CHRIS McCANN-201A22002 | 2258.75 |  | Accounts to provide details
XXXD00161111 | Def Direct Costs at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | GL | JNL |  | 158556 |  | 2023-01-31 | 2023-01-31 | Unclaimed VAT Dec'22 W/Off | 158556,O,Unclaimed VAT Dec'22 W/Off | 21.75 |  | Invoice attached
XXXD00161111 | Def Direct Costs at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | GL | JNL |  | 158556 |  | 2023-01-31 | 2023-01-31 | Unclaimed VAT Dec'22 W/Off | 158556,O,Unclaimed VAT Dec'22 W/Off | 84.66 |  | Invoice attached
XXXD00161111 | Def Direct Costs at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | GL | JNL |  | 158556 |  | 2023-01-31 | 2023-01-31 | Unclaimed VAT Dec'22 W/Off | 158556,O,Unclaimed VAT Dec'22 W/Off | 190.67 |  | Invoice attached
XXXD00161131 | Def Direct Costs at Site Miscellaneous staff welfare expense | 2023-01-31 | O | CB | PCP | 1766 | JAN/11832/16 |  | 2023-01-13 | 2023-01-13 | 27743-CHRIS McCANN-201A22002 | 158390,O,27743-CHRIS McCANN-201A22002 | 1100 |  | Accounts to provide details
XXXD00161441 | Def Direct Costs at Site Office - consumables - material and services | 2023-01-31 | O | PL | PINV | ALAB003 | 2301PL000116 | 202113113 | 2023-01-09 | 2022-12-10 | Polythene sheet 500 gauge | 10/12/22,202113113,ALAB003,Al Abbasi Fasteners and Hardware | 4300 |  | Invoice attached
XXXD00161441 | Def Direct Costs at Site Office - consumables - material and services | 2023-01-31 | O | PL | PINV | ALAB003 | 2301PL000117 | 202113114 | 2023-01-09 | 2022-12-10 | Polythene Sheet 1000 Gauge | 10/12/22,202113114,ALAB003,Al Abbasi Fasteners and Hardware | 2580 |  | Invoice attached
XXXD00161441 | Def Direct Costs at Site Office - consumables - material and services | 2023-01-31 | O | PL | PINV | ALAB003 | 2301PL000361 | 202113151 | 2023-01-12 | 2022-12-27 | Polythene sheet 500 gauge | 27/12/22,202113151,ALAB003,Al Abbasi Fasteners and Hardware | 4300 |  | Invoice attached
XXXD00161441 | Def Direct Costs at Site Office - consumables - material and services | 2023-01-31 | O | PL | PINV | ALAB003 | 2301PL000362 | 202113152 | 2023-01-12 | 2022-12-27 | Polythene Sheet 1000 Gauge | 27/12/22,202113152,ALAB003,Al Abbasi Fasteners and Hardware | 2580 |  | Invoice attached
XXXD00161441 | Def Direct Costs at Site Office - consumables - material and services | 2023-01-31 | O | GL | REV |  | 156787 |  | 2023-01-03 | 2023-01-01 | M/E Accrual | M/E Accrual | -6880
XXXD00161521 | Def Direct Costs at Site Waste and sewage disposal | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 38000
XXXD00161531 | Def Direct Costs at Site Mobilization expenses - site | 2023-01-31 | O | PL | PINV | ALNA007 | 2301PL001111 | 58249 | 2023-01-25 | 2023-01-17 | Supply of Revolving chair | 17/01/23,58249,ALNA007,Al Najah Furnishings LLC | 5500 |  | Invoice attached
XXXD00162001 | Def Direct Costs at Site Miscellaneous expenses | 2023-01-31 | O | CB | PCP | 1796 | JAN/11836/21 |  | 2023-01-23 | 2023-01-23 | 27743-CHRIS McCANN-201A22002 | 158467,O,27743-CHRIS McCANN-201A22002 | 350 |  | Accounts to provide details
XXXD00167001 | Def Direct Costs at Site Remedial Works Provision | 2023-01-31 | O | CV | JCV | 201A22002 | 0009 | JOBREMWKSM/CONTRACT/201A22002//// | 2023-01-13 | 2023-01-01 | CVR Item 3.08 Remedial Works | 157356,O,CVR Item 3.08 Remedial Works
XXXP00125512 | Def Prelims at Site Signage and accessories | 2023-01-31 | O | GL | REV |  | 156787 |  | 2023-01-03 | 2023-01-01 | M/E Accrual | M/E Accrual | -890
XXXP00125512 | Def Prelims at Site Signage and accessories | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 890
XXXP00129955 | Def Prelims at Site Profit Abatement CVR | 2023-01-31 | O | CV | JCV | 201A22002 | 0009 | JOBPABATE/CONTRACT/201A22002//// | 2023-01-13 | 2023-01-01 | CVR Item Contract Profit Abatement | 157356,O,CVR Item Contract Profit Abatement | -2587002
XXXP00129955 | Def Prelims at Site Profit Abatement CVR | 2023-01-31 | O | GL | REV | 201A22002 | 157375 | JOBPABATE/CONTRACT/201A22002//// | 2022-12-31 | 2023-01-01 | CVR Item Contract Profit Abatement | 157375,O,CVR Item Contract Profit Abatement | 2587002
XXXP00160905 | Def Prelims at Site Computers & Accessories | 2023-01-31 | O | PC | PCHG | ITA0003005 | 1 4 5010685 | COST/196 | 2023-01-31 | 2023-01-31 | ITA0003005 Face Station 2 - Identification Device | 158333,O,ITA0003005 Face Station 2 - Identification Device | 217 |  | Invoice attached
XXXP00160905 | Def Prelims at Site Computers & Accessories | 2023-01-31 | O | PC | PCHG | ITA0003060 | 1 4 5010685 | COST/197 | 2023-01-31 | 2023-01-31 | ITA0003060 Face Station 2 - Identification Device | 158333,O,ITA0003060 Face Station 2 - Identification Device | 217 |  | Invoice attached
XXXP00160905 | Def Prelims at Site Computers & Accessories | 2023-01-31 | O | PC | PCHG | ITA0003084 | 1 4 5010685 | COST/198 | 2023-01-31 | 2023-01-31 | ITA0003084 Face Station 2 - Identification Device | 158333,O,ITA0003084 Face Station 2 - Identification Device | 217 |  | Invoice attached
XXXP00160905 | Def Prelims at Site Computers & Accessories | 2023-01-31 | O | PC | PCHG | ITA0003075 | 1 4 5010685 | COST/199 | 2023-01-31 | 2023-01-31 | ITA0003075 Face Station 2 - Identification Device | 158333,O,ITA0003075 Face Station 2 - Identification Device | 217 |  | Invoice attached
XXXP00160905 | Def Prelims at Site Computers & Accessories | 2023-01-31 | O | PC | PCHG | ITA0003063 | 1 4 5010685 | COST/200 | 2023-01-31 | 2023-01-31 | ITA0003063 Face Station 2 - Identification Device | 158333,O,ITA0003063 Face Station 2 - Identification Device | 217 |  | Invoice attached
XXXP00160905 | Def Prelims at Site Computers & Accessories | 2023-01-31 | O | PC | PCHG | ITA0002123 | 1 4 5010685 | COST/201 | 2023-01-31 | 2023-01-31 | ITA0002123 Samsung Galaxy Tab Active Pro | 158333,O,ITA0002123 Samsung Galaxy Tab Active Pro | 0
XXXP00161001 | Def Prelims at Site Health and safety - material items | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 3003
XXXP00161003 | Def Prelims at Site First-aid and medical expenses | 2023-01-31 | O | PL | PINV | ALAM004 | 2301PL001795 | 389703 | 2023-01-31 | 2023-01-19 | First Aid & Medical Supplies | 19/01/23,389703,ALAM004,Al Ameen Pharmacy LLC | 826.11 |  | Invoice attached
XXXP00161003 | Def Prelims at Site First-aid and medical expenses | 2023-01-31 | O | PL | PINV | ALAM004 | 2301PL001795 | 389703 | 2023-01-31 | 2023-01-19 | First Aid & Medical Supplies | 19/01/23,389703,ALAM004,Al Ameen Pharmacy LLC | 494.9 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL000501 | 9506170543 | 2023-01-16 | 2022-12-24 | Tea Room Items | 24/12/22,9506170543,CHOI001,T Choithram and Sons LLC | 710 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL000501 | 9506170543 | 2023-01-16 | 2022-12-24 | Tea Room Items | 24/12/22,9506170543,CHOI001,T Choithram and Sons LLC | 337.5 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL000501 | 9506170543 | 2023-01-16 | 2022-12-24 | Tea Room Items | 24/12/22,9506170543,CHOI001,T Choithram and Sons LLC | 221.7 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | GL | REV |  | 156787 |  | 2023-01-03 | 2023-01-01 | M/E Accrual | M/E Accrual | -5895.4
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001315 | 9506171097 | 2023-01-31 | 2023-01-02 | Tea Room Items | 02/01/23,9506171097,CHOI001,T Choithram and Sons LLC | 1796 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001315 | 9506171097 | 2023-01-31 | 2023-01-02 | Tea Room Items | 02/01/23,9506171097,CHOI001,T Choithram and Sons LLC | 832.5 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001315 | 9506171097 | 2023-01-31 | 2023-01-02 | Tea Room Items | 02/01/23,9506171097,CHOI001,T Choithram and Sons LLC | 738.7 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001315 | 9506171097 | 2023-01-31 | 2023-01-02 | Tea Room Items | 02/01/23,9506171097,CHOI001,T Choithram and Sons LLC | 319 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 80 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 128 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 112 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 156 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 124 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 160 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 180 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 124 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 288 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | ALSH022 | 2301PL000725 | 11077/84 | 2023-01-18 | 2023-01-12 | Drinking Water 5USG/bottle | 12/01/23,11077/84,ALSH022,Al Shalal Pure Drinking Water LLC | 164 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001314 | 9506172203 | 2023-01-31 | 2023-01-16 | Tea Room Items | 16/01/23,9506172203,CHOI001,T Choithram and Sons LLC | 2535 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001314 | 9506172203 | 2023-01-31 | 2023-01-16 | Tea Room Items | 16/01/23,9506172203,CHOI001,T Choithram and Sons LLC | 433 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001314 | 9506172203 | 2023-01-31 | 2023-01-16 | Tea Room Items | 16/01/23,9506172203,CHOI001,T Choithram and Sons LLC | 206.5 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | PL | PINV | CHOI001 | 2301PL001314 | 9506172203 | 2023-01-31 | 2023-01-16 | Tea Room Items | 16/01/23,9506172203,CHOI001,T Choithram and Sons LLC | 390 |  | Invoice attached
XXXP00161111 | Def Prelims at Site Refreshments (snacks, tea, coffee etc.) | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 3169
XXXP00161441 | Def Prelims at Site Office - consumables - material and services | 2023-01-31 | O | GL | REV |  | 156787 |  | 2023-01-03 | 2023-01-01 | M/E Accrual | M/E Accrual | -3832
XXXP00161441 | Def Prelims at Site Office - consumables - material and services | 2023-01-31 | O | PL | PINV | MANG001 | 2301PL001003 | 2023/0059 | 2023-01-25 | 2023-01-17 | Garbage bag | 17/01/23,2023/0059,MANG001,Mangal Trading Co LLC | 2250 |  | Invoice attached
XXXP00161441 | Def Prelims at Site Office - consumables - material and services | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 3832
XXXP00161511 | Def Prelims at Site Testing and certification charges | 2023-01-31 | O | PL | PINV | DANA002 | 2301PL001181 | INV-003359 | 2023-01-23 | 2022-12-01 | Cradle Operator Training | 01/10/22,INV-003359,DANA002,Danat Alkhaleej for Safety Consultancy | 4200 |  | Invoice attached
XXXP00161521 | Def Prelims at Site Waste and sewage disposal | 2023-01-31 | O | PL | PINV | GREE044 | 2301PL000496 | INV-008184 | 2023-01-16 | 2022-12-31 | Skips Disposal | 31/12/22,INV-008184,GREE044,Green Earth Waste Collection & Transportation Services | 1800 |  | Invoice attached
XXXP00161521 | Def Prelims at Site Waste and sewage disposal | 2023-01-31 | O | PL | PINV | GREE044 | 2301PL000496 | INV-008184 | 2023-01-16 | 2022-12-31 | Skips Disposal | 31/12/22,INV-008184,GREE044,Green Earth Waste Collection & Transportation Services | 2268.72 |  | Invoice attached
XXXP00161701 | Def Prelims at Site Stationary | 2023-01-31 | O | PL | PINV | ASTD001 | 2301PL000150 | I1A13825 | 2023-01-12 | 2022-12-31 | Hire extension of Plotter | 31/12/22,I1A13825,ASTD001,AST Digital Print Centre | 2500 |  | Invoice attached
XXXP00161701 | Def Prelims at Site Stationary | 2023-01-31 | O | GL | ACC |  | 158656 |  | 2023-02-01 | 2023-01-31 | M/E Accrual | M/E Accrual | 614.06
| OH Cost ( AED ) | [11 empty] | 164904.35
[12 empty] | M/E Accrual ( Positive ) | 71653.56
[12 empty] | M/E Accrual ( Negative ) | -17497.4

## Accruals
Report: | Accruals Report |  | Accruals Report
Record Type | Batch | Order Type | Contract | ttOrder.tSort | ttOrder.tCostCode | ttOrder.tgla_acct | Ph | Cost Code | tOurRef | Ct | Supplier A/C No | Supplier Name | Del/Due /Sheet Date | tunwound | Ticket No | PO Number | Cur | Itm | Description | Quantity | UN | AED Value
ttOrder | ACC | Contract | 201A22002 | 426 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 2 | IT Equipment Printer Cameras etc | 2 | EA | 1050
ttOrder | ACC | Contract | 201A22002 | 427 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 3 | IT Equipment Printer Cameras etc | 12 | EA | 264
ttOrder | ACC | Contract | 201A22002 | 428 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 4 | IT Equipment Printer Cameras etc | 1 | EA | 1320
ttOrder | ACC | Contract | 201A22002 | 429 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 5 | IT Equipment Printer Cameras etc | 1 | EA | 725
ttOrder | ACC | Contract | 201A22002 | 430 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 6 | IT Equipment Printer Cameras etc | 1 | EA | 1800
ttOrder | ACC | Contract | 201A22002 | 431 | XXXD00160905 |  |  | XXXD00160905 |  | O | ZENE003 | Zener Marine Services LLC | 2023-01-30 |  | 230250 | HM-201A22002/0298 | AED | 4 | IT Equipment Printer Cameras etc | 1 | EA | 700
ttOrder | ACC | Contract | 201A22002 | 432 | XXXD00160905 |  |  | XXXD00160905 |  | O | ZENE003 | Zener Marine Services LLC | 2023-01-30 |  | 230250 | HM-201A22002/0298 | AED | 3 | IT Equipment Printer Cameras etc | 1 | EA | 5100
ttOrder | ACC | Contract | 201A22002 | 433 | XXXD00160905 |  |  | XXXD00160905 |  | O | ZENE003 | Zener Marine Services LLC | 2023-01-30 |  | 230250 | HM-201A22002/0298 | AED | 2 | IT Equipment Printer Cameras etc | 10 | EA | 1500
ttOrder | ACC | Contract | 201A22002 | 434 | XXXD00160905 |  |  | XXXD00160905 |  | O | ZENE003 | Zener Marine Services LLC | 2023-01-30 |  | 230250 | HM-201A22002/0298 | AED | 1 | IT Equipment Printer Cameras etc | 10 | EA | 5000
ttOrder | ACC | Contract | 201A22002 | 435 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15722 | HM-201A22002/0285 | AED | 1 | IT Equipment Printer Cameras etc | 150 | EA | 1087.5
ttOrder | ACC | Contract | 201A22002 | 436 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15722 | HM-201A22002/0285 | AED | 2 | IT Equipment Printer Cameras etc | 2 | EA | 1050
ttOrder | ACC | Contract | 201A22002 | 437 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15722 | HM-201A22002/0285 | AED | 3 | IT Equipment Printer Cameras etc | 12 | EA | 264
ttOrder | ACC | Contract | 201A22002 | 438 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 8 | IT Equipment Printer Cameras etc | 1 | EA | 225
ttOrder | ACC | Contract | 201A22002 | 439 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15722 | HM-201A22002/0285 | AED | 4 | IT Equipment Printer Cameras etc | 1 | EA | 1320
ttOrder | ACC | Contract | 201A22002 | 440 | XXXD00160905 |  |  | XXXD00160905 |  | O | NEOT001 | Neo Tech Engineering LLC | 2023-01-27 |  | 15726 | HM-201A22002/0305 | AED | 1 | IT Equipment Printer Cameras etc | 100 | EA | 725
ttOrder | ACC | Contract | 201A22002 | 440 |  | 01.701020 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 441 | XXXD00161001 |  |  | XXXD00161001 |  | O | ALJA007 | Al Jas Technical Services LLC | 2023-01-30 |  | 14155/14154 | HM-201A22002/0317 | AED | 5 | Safety Clothing and Equipment / PPE | 1 | NR | 15
ttOrder | ACC | Contract | 201A22002 | 441 |  | 01.701020 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 442 | XXXD00161521 |  |  | XXXD00161521 |  | O | STUR001 | Sturdy Products UAE Limited | 2023-01-20 |  | 106517 | HM-201A22002/0299 | AED | 1 | Rubbish Removal | 20 | NR | 38000
ttOrder | ACC | Contract | 201A22002 | 442 |  | 01.701020 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 443 | XXXP00125512 |  |  | XXXP00125512 |  | O | ABDU011 | Abdulrahman Al Abdooli Advertising LLC | 2022-05-06 |  | 41490 | HM-201A22002/0021 | AED | 1 | Project Sign Boards | 1 | EA | 445
ttOrder | ACC | Contract | 201A22002 | 444 | XXXP00125512 |  |  | XXXP00125512 |  | O | ABDU011 | Abdulrahman Al Abdooli Advertising LLC | 2022-05-06 |  | 41490 | HM-201A22002/0021 | AED | 2 | Project Sign Boards | 1 | EA | 445
ttOrder | ACC | Contract | 201A22002 | 444 |  | 01.701010 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 445 |  | 01.701015 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 446 | XXXP00161001 |  |  | XXXP00161001 |  | O | ALJA007 | Al Jas Technical Services LLC | 2023-01-30 |  | 14155/14154 | HM-201A22002/0317 | AED | 2 | Safety Clothing and Equipment / PPE | 40 | NR | 1400
ttOrder | ACC | Contract | 201A22002 | 447 | XXXP00161001 |  |  | XXXP00161001 |  | O | ALJA007 | Al Jas Technical Services LLC | 2023-01-30 |  | 14155/14154 | HM-201A22002/0317 | AED | 3 | Safety Clothing and Equipment / PPE | 10 | NR | 270
ttOrder | ACC | Contract | 201A22002 | 448 | XXXP00161001 |  |  | XXXP00161001 |  | O | ALJA007 | Al Jas Technical Services LLC | 2023-01-30 |  | 14155/14154 | HM-201A22002/0317 | AED | 4 | Safety Clothing and Equipment / PPE | 1 | NR | 183
ttOrder | ACC | Contract | 201A22002 | 449 | XXXP00161001 |  |  | XXXP00161001 |  | O | ALJA007 | Al Jas Technical Services LLC | 2023-01-30 |  | 14155/14154 | HM-201A22002/0317 | AED | 1 | Safety Clothing and Equipment / PPE | 50 | NR | 1150
ttOrder | ACC | Contract | 201A22002 | 449 |  | 01.701020 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 450 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-06 |  | 1226916/1226920/1209992 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 72 | NR | 288
ttOrder | ACC | Contract | 201A22002 | 451 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-10 |  | 1226934 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 42 | NR | 168
ttOrder | ACC | Contract | 201A22002 | 452 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-13 |  | 1226949 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 19 | NR | 76
ttOrder | ACC | Contract | 201A22002 | 453 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-13 |  | 1226947 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 25 | NR | 100
ttOrder | ACC | Contract | 201A22002 | 454 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-17 |  | 1221656/1221673 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 52 | NR | 208
ttOrder | ACC | Contract | 201A22002 | 455 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 31 | Refreshments (snacks tea coffee etc.) | 6 | BOX | 252
ttOrder | ACC | Contract | 201A22002 | 456 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 34 | Refreshments (snacks tea coffee etc.) | 1 | BOX | 168
ttOrder | ACC | Contract | 201A22002 | 457 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 36 | Refreshments (snacks tea coffee etc.) | 1 | NR | 30
ttOrder | ACC | Contract | 201A22002 | 458 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 38 | Refreshments (snacks tea coffee etc.) | 30 | BOX | 435
ttOrder | ACC | Contract | 201A22002 | 459 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 40 | Refreshments (snacks tea coffee etc.) | 6 | NR | 84
ttOrder | ACC | Contract | 201A22002 | 460 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 42 | Refreshments (snacks tea coffee etc.) | 8 | NR | 204
ttOrder | ACC | Contract | 201A22002 | 461 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 55 | Refreshments (snacks tea coffee etc.) | 5 | EA | 27.5
ttOrder | ACC | Contract | 201A22002 | 462 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 60 | Refreshments (snacks tea coffee etc.) | 25 | EA | 250
ttOrder | ACC | Contract | 201A22002 | 463 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 70 | Refreshments (snacks tea coffee etc.) | 4 | NR | 25
ttOrder | ACC | Contract | 201A22002 | 464 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-24 |  | 1221685/1224819 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 62 | NR | 248
ttOrder | ACC | Contract | 201A22002 | 465 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-30 |  | 1224843/1224831/1221695 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 86 | NR | 344
ttOrder | ACC | Contract | 201A22002 | 466 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 23 | Refreshments (snacks tea coffee etc.) | 8 | NR | 96
ttOrder | ACC | Contract | 201A22002 | 467 | XXXP00161111 |  |  | XXXP00161111 |  | O | CHOI001 | T Choithram and Sons LLC | 2023-01-20 |  | 804513939 | HM-201A22002/0196 | AED | 1 | Refreshments (snacks tea coffee etc.) | 10 | NR | 29.5
ttOrder | ACC | Contract | 201A22002 | 468 | XXXP00161111 |  |  | XXXP00161111 |  | O | ALSH022 | Al Shalal Pure Drinking Water LLC | 2023-01-20 |  | 1228406 | HM-201A22002/0254 | AED | 1 | Refreshments (snacks tea coffee etc.) | 34 | NR | 136
ttOrder | ACC | Contract | 201A22002 | 468 |  | 01.701020 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 469 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 3 | Site Office Consumables | 10 | NR | 850
ttOrder | ACC | Contract | 201A22002 | 470 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 4 | Site Office Consumables | 10 | NR | 250
ttOrder | ACC | Contract | 201A22002 | 471 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 5 | Site Office Consumables | 6 | NR | 72
ttOrder | ACC | Contract | 201A22002 | 472 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 6 | Site Office Consumables | 10 | NR | 300
ttOrder | ACC | Contract | 201A22002 | 473 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 7 | Site Office Consumables | 15 | NR | 600
ttOrder | ACC | Contract | 201A22002 | 474 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 2 | Site Office Consumables | 20 | NR | 700
ttOrder | ACC | Contract | 201A22002 | 475 | XXXP00161441 |  |  | XXXP00161441 |  | O | ALBA009 | Al Bariq Equipment LLC | 2022-07-07 |  | 22/7968 | HM-201A22002/0101 | AED | 1 | Site Office Consumables | 4 | NR | 1060
ttOrder | ACC | Contract | 201A22002 | 475 |  | 01.701020 | [13 empty] | 0 |  | 0
ttOrder | ACC | Contract | 201A22002 | 476 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 14 | Printing and Stationery | 20 | EA | 58
ttOrder | ACC | Contract | 201A22002 | 477 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 16 | Printing and Stationery | 50 | EA | 12.5
ttOrder | ACC | Contract | 201A22002 | 478 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 18 | Printing and Stationery | 50 | EA | 3
ttOrder | ACC | Contract | 201A22002 | 479 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 19 | Printing and Stationery | 50 | EA | 3.5
ttOrder | ACC | Contract | 201A22002 | 480 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 22 | Printing and Stationery | 100 | EA | 16
ttOrder | ACC | Contract | 201A22002 | 481 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 30 | Printing and Stationery | 15 | EA | 65.25
ttOrder | ACC | Contract | 201A22002 | 482 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 41 | Printing and Stationery | 20 | EA | 75
ttOrder | ACC | Contract | 201A22002 | 483 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 42 | Printing and Stationery | 30 | EA | 112.5
ttOrder | ACC | Contract | 201A22002 | 484 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 43 | Printing and Stationery | 10 | EA | 8.5
ttOrder | ACC | Contract | 201A22002 | 485 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 56 | Printing and Stationery | 24 | EA | 43.2
ttOrder | ACC | Contract | 201A22002 | 486 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 95 | Printing and Stationery | 4 | EA | 78
ttOrder | ACC | Contract | 201A22002 | 487 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 98 | Printing and Stationery | 1 | EA | 37.5
ttOrder | ACC | Contract | 201A22002 | 488 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 205 | Printing and Stationery | 3 | EA | 9.45
ttOrder | ACC | Contract | 201A22002 | 489 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 164 | Printing and Stationery | 15 | EA | 81
ttOrder | ACC | Contract | 201A22002 | 490 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 167 | Printing and Stationery | 6 | EA | 5.4
ttOrder | ACC | Contract | 201A22002 | 491 | XXXP00161701 |  |  | XXXP00161701 |  | O | AGSO001 | AGS Office Supplies and Trading LLC | 2023-01-17 |  | 00041 | HM-201A22002/0015 | AED | 159 | Printing and Stationery | 2 | EA | 5.26
ttOrder | ACC | Contract | 201A22002 | 491 |  | 01.701020 | [13 empty] | 0 |  | 0
[10 empty] | Total Amount (AED ) | [11 empty] | 71653.56