## PC FOR ISSUANCE
INTERIM PAYMENT CERTIFICATE
PROJECT: |  | Plot 18, BUSINESS BAY DUBAI, UAE |  | Certificate No: | 03
|  |  |  | Date of Certificate : | 2023-04-11
| Issued By : | Employer's Representative |  | Invoice No. | Application No 03
|  | Omniyat Concept Investments LLC |  | Cost Code: | D171
Dubai, UAE
| Company : | Sky Palaces Real Estate Development LLC |  | Contract Start Date : | 2022-02-02
|  | PO Box 12501 |  | Date of Application: | 2023-03-29
|  | Dubai, UAE |  | Period for Works Certified: | N/A
|  |  |  | Payment Due Date : Prior to | 2023-05-13
|  |  |  | Certificate Currency: | AED
| Contractor : | Elenco Trading Establishment
|  | PO Box 2137 |  | VALUE COMPLETE | 20.21%
|  | Dubai, UAE |  | CERTIFIED FOR PAYMENT | 38.64%
|  |  |  | Currency | AED
|  |  |  | Original Contract Sum | 6336000
|  |  |  | Variation | 834750
|  |  |  | Current Final Value | 7170750
| (A) Contract Advance Payment in this certificate |  |  |  | 1465982.46
| Advance Payment |  | 1900800
LESS:
| Advance Payment Recovery 30% - Works Completed |  | 434817.54
| Advance Payment in this certificate |  | 1465982.46
| (B) Value of Works Completed To Date (Valuation of Work In Place) |  |  |  | 1449391.8
| (C=A+B) Certified Value - Cumulative |  |  |  | 2915374.26
| (D) LESS Retention (10%) |  |  |  | -144939.18
| (E) ADD: Release of Retention (50%) |  |  |  | 0
| (F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 2770435.08
| (G) LESS Previous Certified Value |  |  |  | -2320500.6
| (H=F-G) Net Certified for payment |  |  |  | 449934.48
| (I) 5% VAT |  |  |  | 22496.72
| (H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 472431.2
| RESIDUAL ADVANCE VALUE |  |  |  | 0
| LESS Recovery form this Certificate |  |  |  | 0
| RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
| Notes: | This payment certificate is for Material at Site
| Payment Terms: | Payment to be made within 45 days upon the receipt of the IPA
EMPLOYER'S REPRESENTATIVE CERTIFICATION
We certify that the above to be true and correct.
| For on behalf of OMNIYAT CONCEPT INVESTMENTS LLC |  |  |  | Date
APPROVAL BY EMPLOYER
Employer's approval of the net amount certified.
| For on behalf of SKY PALACES REAL ESTATE DEVELOPMENT LLC |  |  |  | Date

## Plot 18
INTERIM PAYMENT CERTIFICATE
PROJECT: |  | Plot 18, BUSINESS BAY DUBAI, UAE |  | Certificate No: | 03
|  |  |  | Date of Certificate : | 2023-04-11
| Issued By : | Employer's Representative |  | Invoice No. | Application No 03
|  | Omniyat Concept Investments LLC |  | Cost Code: | D171
Dubai, UAE
| Company : | Sky Palaces Real Estate Development LLC |  | Contract Start Date : | 2022-02-02
|  | PO Box 12501 |  | Date of Application: | 2023-03-29
|  | Dubai, UAE |  | Period for Works Certified: | N/A
|  |  |  | Payment Due Date : Prior to | 2023-05-13
|  |  |  | Certificate Currency: | AED
| Contractor : | Elenco Trading Establishment
|  | PO Box 2137 |  | VALUE COMPLETE | 20.21%
|  | Dubai, UAE |  | CERTIFIED FOR PAYMENT | 38.64%
|  |  |  | Currency | AED
|  |  |  | Original Contract Sum | 6336000
|  |  |  | Variation | 834750
|  |  |  | Current Final Value | 7170750
| (A) Contract Advance Payment in this certificate |  |  |  | 1465982.46
| Advance Payment |  | 1900800
LESS:
| Advance Payment Recovery 5% - Works Completed |  | 434817.54
| Advance Payment in this certificate |  | 1465982.46
| (B) Value of Works Completed To Date (Valuation of Work In Place) |  |  |  | 1449391.8
| (C=A+B) Certified Value - Cumulative |  |  |  | 2915374.26
| (D) LESS Retention (10%) |  |  |  | -144939.18
| (E) ADD: Release of Retention (50%) |  |  |  | 0
| (F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 2770435.08
| (G) LESS Previous Certified Value |  |  |  | -2320500.6
| (H=F-G) Net Certified for payment |  |  |  | 449934.48
| (I) 5% VAT |  |  |  | 22496.72
| (H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 472431.2
| RESIDUAL ADVANCE VALUE |  |  |  | 0
| LESS Recovery form this Certificate |  |  |  | 0
| RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
| Notes: | This payment certificate is for Material at Site
| Payment Terms: | Payment to be made within 45 days upon the receipt of the IPA
INTERNAL CERTIFICATION ONLY
We certify that the above to be true and correct for and on behalf of OMNIYAT CONCEPT INVESTMENTS LLC
| Christopher Thomas |  |  | Peter Stephenson
| Commercial Director |  |  | Managing Director - Development
SKY PALACES REAL ESTATE DEVELOPMENT LLC approval to proceed the net amount certified for approval
Ishan Garga
Managing Director - Corporate Finance & Investments

## BOQ
Item No. | Make | Model | Description | Qty | Rate | Amount | Previous Qty | Previous Amount | This Month Qty | This Month Amount | Cumulative Qty | Cumulative % | Cumulative Amount | Remark
BQ.01a | Sofinor | LMDESS1 | Paper Towel Dispenser | 1 | 114 | 114 | 1 | 68.4 | 0 | 0 | 1 | 60% | 68.4
BQ.03 | Moduline | HHT281E | Low Temperature Hot Holding Cabinets | 2 | 9111 | 18222 | 2 | 10933.2 | 0 | 0 | 2 | 60% | 10933.2
BQ.07 | Electrolux (900XP) | 900 XP LINE | 1 Piece Top Comprising; (MODULAR UNIT - NOT 1 PIECE TOP) | 1 | 0 | Pirce included in the individual units | 1 | 0 | 0 | 0 | 1 | 60% | 0
a | Electrolux (900XP) | 391006 | 4 Burner Gas Range with gas Ovens Under | 1 | 11887 | 11887 | 1 | 7132.2 | 0 | 0 | 1 | 60% | 7132.2
b | Electrolux (900XP) | 391158+391153+206350 | Open Storage | 2 | 3462 | 6924 | 2 | 4154.4 | 0 | 0 | 2 | 60% | 4154.4
BQ.10 | Rational+Everpure | I Combi Classic 201G +Kleen Steam CT | 20 GN1/1 Gas Combination Ovens | 2 | 58507 | 117014 | 2 | 70208.4 | 0 | 0 | 2 | 60% | 70208.4
BQ.12 | Rational+Everpure | I Vario pro 2-S+60.31.319+60.74.666+60.74.663(2)+60.74.986+60.75.330+60.75.359(2)+60.71.643 | 2x25L Vario Cooking Center - Multifunctional | 2 | 52464 | 104928 | 2 | 62956.8 | 0 | 0 | 2 | 60% | 62956.8
BQ.16 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelvings | 4 | 1159 | 4636 | 4 | 2781.6 | 0 | 0 | 4 | 60% | 2781.6
BQ.17 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Units | 4 | 608 | 2432 | 4 | 1459.2 | 0 | 0 | 4 | 60% | 1459.2
BQ.18 | Metro | DH2020N | Rack Dollies | 3 | 620 | 1860 | 3 | 1116 | 0 | 0 | 3 | 60% | 1116
BQ.24 | Rubbermaid | 1883459 | Mobile Waste Bins | 5 | 1211 | 6055 | 5 | 3633 | 0 | 0 | 5 | 60% | 3633
BQ.25 | Rubbermaid | SLIM JIM 1971258+FG269288+1980602 | Bottle Bins | 3 | 889 | 2667 | 3 | 1600.2 | 0 | 0 | 3 | 60% | 1600.2
BQ.27 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 | 1 | 1612.8 | 0 | 0 | 1 | 60% | 1612.8
BQ.28 | Sofinor | CNETC/1P+4550CNET04S | Wall Mounted Hose Reel | 1 | 3349 | 3349 | 1 | 2009.4 | 0 | 0 | 1 | 60% | 2009.4
BQ.30 | Rubbermaid | FG199300 | Mop/Broom Rack | 1 | 243 | 243 | 1 | 145.8 | 0 | 0 | 1 | 60% | 145.8
BQ.31 | IMC | 726 (F60/221) | Food Waste Disposer | 1 | 14804 | 14804 | 1 | 8882.4 | 0 | 0 | 1 | 60% | 8882.4
BQ.35 | Waring | MX1500XTXSEK | Blenders with Silencer | 2 | 2558 | 5116 | 2 | 3069.6 | 0 | 0 | 2 | 60% | 3069.6
BQ.40 | Scotsman+Everpure | NW308AS OX +Insurice i2000 Twin System | Ice Machines- Medium (160kg/24 hours) | 2 | 8918 | 17836 | 2 | 10701.6 | 0 | 0 | 2 | 60% | 10701.6
BQ.41 | Scotsman | SB322 (2nos) | Ice Storage Bin - 46 | 1 | 6792 | 6792 | 1 | 4075.2 | 0 | 0 | 1 | 60% | 4075.2
BQ.43 | Animo + Everpure | CB5W (1005397)+1006095+Claris M | Wall Mounted Bulk Brewers (30 litre/hr) | 2 | 9359 | 18718 | 2 | 11230.8 | 0 | 0 | 2 | 60% | 11230.8
BQ.44 | Animo | CN5E (1005364) | Insulated Beverage Containers (20 litres) | 4 | 2434 | 9736 | 4 | 5841.6 | 0 | 0 | 4 | 60% | 5841.6
BQ.45 | Animo | JR (60002) + 63001 | Mobile Hot Beverage Serving Trolleys | 4 | 3020 | 12080 | 4 | 7248 | 0 | 0 | 4 | 60% | 7248
BQ.46 | Metro | PCD11A | Poker Chip Dish Dolley | 1 | 3217 | 3217 | 1 | 1930.2 | 0 | 0 | 1 | 60% | 1930.2
UD.05 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 | 1 | 364.8 | 0 | 0 | 1 | 60% | 364.8
UD.07 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelving | 3 | 1298 | 3894 | 3 | 2336.4 | 0 | 0 | 3 | 60% | 2336.4
GV.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Hand Wash Station | 1 | 1046 | 1046 | 1 | 627.6 | 0 | 0 | 1 | 60% | 627.6
GV.04 | Eagle | PLT 150 S | Floor Mounted Weighing Scale -150KG | 1 | 889 | 889 | 1 | 533.4 | 0 | 0 | 1 | 60% | 533.4
GV.05 | Rubbermaid | 1883459 | Mobile Waste Bin | 1 | 1211 | 1211 | 1 | 726.6 | 0 | 0 | 1 | 60% | 726.6
GV.09 | Electrolux- Laundry | WH6-20-LAC (Lagoon)+JETSAVE | 20kg Washer Extractor | 1 | 59818 | 59818 | 1 | 35890.8 | 0 | 0 | 1 | 60% | 35890.8
GV.10 | Electrolux- Laundry | WH6-6LAC (Lagoon)+ED | 6kg Washer Extractor (As per layout 1 no) | 1 | 19498 | 19498 | 1 | 11698.8 | 0 | 0 | 1 | 60% | 11698.8
GV.21 | Renzacci | ML | Wall Mounted Automatic Bagger | 1 | 5094 | 5094 | 1 | 3056.4 | 0 | 0 | 1 | 60% | 3056.4
GV.24 | Metro | Super Erecta Pro | Runs of 5 Tier Static Storage Shelving (Spec Ref # GV.23) | 15 | 1296 | 19440 | 15 | 11664 | 0 | 0 | 15 | 60% | 11664
GV.25 | Metro | Super Erecta ProTop Rack | Run of High Density Shelving (Spec Ref # GV.24) | 1 | 13982 | 13982 | 1 | 8389.2 | 0 | 0 | 1 | 60% | 8389.2
GV.27 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Units (Spec Ref # GV.26) | 2 | 608 | 1216 | 2 | 729.6 | 0 | 0 | 2 | 60% | 729.6
FL.04 | Custom | Custom | U' Shaped Support Bench with Double Sink Bowl | 1 | 23000 | 23000 | 1 | 13800 | 0 | 0 | 1 | 60% | 13800
FL.05 | Custom | Custom | Wall Cupboards | 2 | 2444 | 4888 | 2 | 2932.8 | 0 | 0 | 2 | 60% | 2932.8
FL.06 | Custom | Custom | Wall Cupboards | 2 | 2833 | 5666 | 2 | 3399.6 | 0 | 0 | 2 | 60% | 3399.6
RD.02 | Custom | Custom | Support Bench with Sink Bowl | 1 | 8778 | 8778 | 1 | 5266.8 | 0 | 0 | 1 | 60% | 5266.8
RD.03 | Custom | Custom | Runs of 2 Tier Wall Shelvings | 2 | 1347 | 2694 | 2 | 1616.4 | 0 | 0 | 2 | 60% | 1616.4
RW.02 | Custom | Custom | Support Bench with Double Sink Bowls | 1 | 9306 | 9306 | 1 | 5583.6 | 0 | 0 | 1 | 60% | 5583.6
RW.07 | Custom | Custom | Support Bench with Sink Bowl | 1 | 9111 | 9111 | 1 | 5466.6 | 0 | 0 | 1 | 60% | 5466.6
RW.11 | Custom | Custom | Runs of 2 Tier Wall Mounted Storage Shelvings | 2 | 1639 | 3278 | 2 | 1966.8 | 0 | 0 | 2 | 60% | 1966.8
SDP.01 | Custom | Custom | Preparation Table with Sink Bowl | 1 | 14750 | 14750 | 1 | 8850 | 0 | 0 | 1 | 60% | 8850
SDP.04 | Custom | Custom | Wall Shelf | 1 | 1861 | 1861 | 1 | 1116.6 | 0 | 0 | 1 | 60% | 1116.6
BQ.01 | Custom | Custom | Worktop c/w Lowered Handwash Station | 1 | 11278 | 11278 | 1 | 6766.8 | 0 | 0 | 1 | 60% | 6766.8
BQ.04 | Custom | Custom | Mobile Set-up Tables (Cold) | 4 | 8806 | 35224 | 4 | 21134.4 | 0 | 0 | 4 | 60% | 21134.4
a | Custom | Custom | Island Gantries c/w Task Light | 4 | 3333 | 13332 | 4 | 7999.2 | 0 | 0 | 4 | 60% | 7999.2
BQ.05 | Custom | Custom | Mobile Set-up Tables (Hot) | 5 | 11000 | 55000 | 5 | 33000 | 0 | 0 | 5 | 60% | 33000
a | Custom | Custom | Hot Cupboards with Sliding Door | 5 | 0 | Included in BQ.05 | 5 | 0 | 0 | 0 | 5 | 60% | 0
c | Custom | Custom | Island Gantries c/w Heat Lamps | 5 | 3333 | 16665 | 5 | 9999 | 0 | 0 | 5 | 60% | 9999
BQ.11 | Custom | Custom | Ambient Base Unit c/w Tray Runners | 1 | 10528 | 10528 | 1 | 6316.8 | 0 | 0 | 1 | 60% | 6316.8
BQ.20 | Custom | Custom | Outlet Table | 1 | 3111 | 3111 | 1 | 1866.6 | 0 | 0 | 1 | 60% | 1866.6
BQ.21 | Custom | Custom | Dishwash Deposit / Inlet Table c/w Pre- rinse Spray | 1 | 12889 | 12889 | 1 | 7733.4 | 0 | 0 | 1 | 60% | 7733.4
a | Custom | Custom | Roll-over Rack Shelf | 1 | 1778 | 1778 | 1 | 1066.8 | 0 | 0 | 1 | 60% | 1066.8
BQ.29 | Custom | Custom | Cleaner's Sink | 1 | 2583 | 2583 | 1 | 1549.8 | 0 | 0 | 1 | 60% | 1549.8
BQ.32 | Custom | Custom | Rack Shelf | 1 | 1389 | 1389 | 1 | 833.4 | 0 | 0 | 1 | 60% | 833.4
BQ.33 | Custom | Custom | Wall Cupboards | 3 | 2509 | 7527 | 3 | 4516.2 | 0 | 0 | 3 | 60% | 4516.2
BQ.34 | Custom | Custom | Beverage Dispense Counter | 1 | 32722 | 32722 | 1 | 19633.2 | 0 | 0 | 1 | 60% | 19633.2
a | Custom | Custom | Lowered Handwash Station | 1 | 0 | Included in BQ.34 | 1 | 0 | 0 | 0 | 1 | 60% | 0
b | Custom | Custom | Lowered Blender Stations | 2 | 0 | Included in BQ.34 | 2 | 0 | 0 | 0 | 2 | 60% | 0
c | Custom | Custom | Insulated Ice Well | 1 | 0 | Included in BQ.34 | 1 | 0 | 0 | 0 | 1 | 60% | 0
d | Custom | Custom | Speedrail | 1 | 0 | Included in BQ.34 | 1 | 0 | 0 | 0 | 1 | 60% | 0
e | Custom | Custom | Underslung Sink Unit | 1 | 0 | Included in BQ.34 | 1 | 0 | 0 | 0 | 1 | 60% | 0
f | Custom | Custom | Stainless Steel Understructure and Storage/Drawers | 1 | 0 | Included in BQ.34 | 1 | 0 | 0 | 0 | 1 | 60% | 0
g | Custom | Custom | Storage Overshelf | 1 | 4028 | 4028 | 1 | 2416.8 | 0 | 0 | 1 | 60% | 2416.8
BQ.36 | Custom | Custom | Rear Beverage Counter | 1 | 23333 | 23333 | 1 | 13999.8 | 0 | 0 | 1 | 60% | 13999.8
BQ.38 | Custom | Custom | Wine Racks | 3 | 0 | Included in BQ.36 | 3 | 0 | 0 | 0 | 3 | 60% | 0
BQ.42 | Custom | Custom | Worktop c/w Sink Unit | 1 | 13667 | 13667 | 1 | 8200.2 | 0 | 0 | 1 | 60% | 8200.2
BQ.47 | Custom | Custom | Movable Table - Dishwash Deposit | 1 | 3028 | 3028 | 1 | 1816.8 | 0 | 0 | 1 | 60% | 1816.8
UD.04 | Newmatic | Alumtrolley/Mini | Soiled Uniform Carts | 5 | 1018 | 5090 | 5 | 3054 | 0 | 0 | 5 | 60% | 3054
UD.08 | Newmatic | SGRT | Uniform Hanging Rail | 1 | 1111 | 1111 | 1 | 666.6 | 0 | 0 | 1 | 60% | 666.6
GV.06 | Thermopatch | Y-151 | Bench Mounted Temporary Marking Machine | 1 | 26333 | 26333 | 1 | 15799.8 | 0 | 0 | 1 | 60% | 15799.8
GV.08 | Ghidini | GB S 88 F | Spotting Table | 1 | 15570 | 15570 | 1 | 9342 | 0 | 0 | 1 | 60% | 9342
GV.11 | Ghidini | P 88 U3 ABL | Utility Press | 1 | 42424 | 42424 | 1 | 25454.4 | 0 | 0 | 1 | 60% | 25454.4
GV.12 | Ghidini | TORNADO/A MAXI | Steam Ironing Table (As per layout and specification 2 nos) | 2 | 18834 | 37668 | 2 | 22600.8 | 0 | 0 | 2 | 60% | 22600.8
GV.13 | Ghidini | PM 98 U3L | Utility Press | 1 | 41044 | 41044 | 1 | 24626.4 | 0 | 0 | 1 | 60% | 24626.4
GV.14 | Ghidini | P 88 V1 AB | Fast Back Press | 1 | 38261 | 38261 | 1 | 22956.6 | 0 | 0 | 1 | 60% | 22956.6
GV.15 | Ghidini | MC 100/S+MAXI 16+ AMICO/25/(2HP)/1PH | Universal Finisher | 1 | 67622 | 67622 | 1 | 40573.2 | 0 | 0 | 1 | 60% | 40573.2
GV.16 | Forenta | 5CFL | Forming Post | 1 | 6479 | 6479 | 1 | 3887.4 | 0 | 0 | 1 | 60% | 3887.4
GV.17 | Ghidini | P 88 CP AB | Collar and Cuff Press | 1 | 37600 | 37600 | 1 | 22560 | 0 | 0 | 1 | 60% | 22560
GV.18 | Girbau | MBT Mini | Sprung Bottom Trolleys | 2 | 3193 | 6386 | 2 | 3831.6 | 0 | 0 | 2 | 60% | 3831.6
GV.19 | Newmatic | SGRT | Mobile Garment Rail | 1 | 1111 | 1111 | 1 | 666.6 | 0 | 0 | 1 | 60% | 666.6
GV.22 | SINGER | 20U105C | Bench Mounted Sewing Machine | 1 | 3322 | 3322 | 1 | 1993.2 | 0 | 0 | 1 | 60% | 1993.2
GV.26 | Newmatic | CONTROLY/2 | Wire Linen Trolleys (Spec Ref # GV.25) | 2 | 3193 | 6386 | 2 | 3831.6 | 0 | 0 | 2 | 60% | 3831.6
FL.02 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelving | 4 | 1351 | 5404 |  |  | 4 | 3242.4 | 4 | 60% | 3242.4 | DC-123
FL.03 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
FL.07 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity | 3 | 1211 | 3633 |  |  | 3 | 2179.8 | 3 | 60% | 2179.8 | DC-123
FL.08 | Sofinor | MZC10S | Knife Disinfection Cabinet | 1 | 990 | 990 |  |  | 1 | 594 | 1 | 60% | 594 | DC-123
FL.09 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
FL.10 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-123
LD.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
LD.03 | Palletco | Pullre 25 | Manual Pallet Trucks | 2 | 944 | 1888 |  |  | 2 | 1132.8 | 2 | 60% | 1132.8 | DC-123
LD.05 | Haws | 7360BT | Automatic Eye Wash Station | 1 | 2159 | 2159 |  |  | 1 | 1295.4 | 1 | 60% | 1295.4 | DC-123
RD.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
RD.04 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity | 1 | 1211 | 1211 |  |  | 1 | 726.6 | 1 | 60% | 726.6 | DC-123
RD.05 | Eagle | PLT 12M T7+RAMP | Floor Mounted Weighing Scale (As Per Layout 2 qty) | 2 | 3611 | 7222 |  |  | 2 | 4333.2 | 2 | 60% | 4333.2 | DC-123
a | Eagle | Ramp | Ramp (Checkered Deck) (As Per Layout 2 qty) | 2 | Included in RD.05 | [8 empty] | DC-123
RD.06 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
RW.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
RW.04 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit (Not Shwon in the Spec) | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
RW.05 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelvings (Spec Ref # RW.004) | 2 | 1158 | 2316 |  |  | 2 | 1389.6 | 2 | 60% | 1389.6 | DC-123
RW.06 | IMC | MF.15 | Floor Standing Peeler with Stand | 1 | 14836 | 14836 |  |  | 1 | 8901.6 | 1 | 60% | 8901.6 | DC-124
RW.09 | Sofinor | MZC10S | Knife Disinfection Cabinet | 1 | 990 | 990 |  |  | 1 | 594 | 1 | 60% | 594 | DC-123
RW.10 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity | 2 | 1211 | 2422 |  |  | 2 | 1453.2 | 2 | 60% | 1453.2 | DC-123
RW.12 | Electrolux (Dito) | LV301R (660034) | Automatic Vegetable Washer (Tilting) | 1 | 52799 | 52799 |  |  | 1 | 31679.4 | 1 | 60% | 31679.4 | DC-124
P.03 | Sofinor | MZC10S | Knife Disinfection Cabinets | 2 | 990 | 1980 |  |  | 2 | 1188 | 2 | 60% | 1188 | DC-123
P.04 | Robot Coupe | R23+57069+57072 | Vertical Cutter Mixer with Stand | 1 | 35904 | 35904 |  |  | 1 | 21542.4 | 1 | 60% | 21542.4 | DC-123
P.06 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
P.07 | Thermomix | TM6 | Multifunctional Processors | 2 | 6333 | 12666 |  |  | 2 | 7599.6 | 2 | 60% | 7599.6 | DC-123
P.08 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity | 2 | 1211 | 2422 |  |  | 2 | 1453.2 | 2 | 60% | 1453.2 | DC-123
P.11 | Robot Coupe | J80U | Multi-fruit Juicers (As per Spec 1 qty) | 2 | 4144 | 8288 |  |  | 2 | 4972.8 | 2 | 60% | 4972.8 | DC-123
P.13 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Stations (As per Spec 1 qty) | 2 | 1046 | 2092 |  |  | 2 | 1255.2 | 2 | 60% | 1255.2 | DC-123
P.17 | Thermomix | TM6 | Multifunctional Processors | 2 | 6333 | 12666 |  |  | 2 | 7599.6 | 2 | 60% | 7599.6 | DC-123
P.18 | La Minerva | DERBY 460+Stand | Vacuum Packer on mobile stand | 1 | 8129 | 8129 |  |  | 1 | 4877.4 | 1 | 60% | 4877.4 | DC-124
P.20 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity | 2 | 1211 | 2422 |  |  | 2 | 1453.2 | 2 | 60% | 1453.2 | DC-123
P.24 | Sofinor | MZC10S | Knife Disinfection Cabinets | 2 | 990 | 1980 |  |  | 2 | 1188 | 2 | 60% | 1188 | DC-123
P.25 | Sirman | SO 1550 F3 | Meat and Bone Saw | 1 | 5698 | 5698 |  |  | 1 | 3418.8 | 1 | 60% | 3418.8 | DC-123
P.26 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Stations | 2 | 1046 | 2092 |  |  | 2 | 1255.2 | 2 | 60% | 1255.2 | DC-123
P.28 | Sammic | PS-32 | Mincing Machine (As per the layout & Specification 2 nos) | 2 | 8360 | 16720 |  |  | 2 | 10032 | 2 | 60% | 10032 | DC-123
P.29 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit (As per the layout & Specification 2 nos) | 2 | 608 | 1216 |  |  | 2 | 729.6 | 2 | 60% | 729.6 | DC-123
P.31 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity (As per the layout & Specification 1 no) | 1 | 1211 | 1211 |  |  | 1 | 726.6 | 1 | 60% | 726.6 | DC-123
P.33 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
P.34 | KTS | KTS 200 | Fish Scaler (As per the layout & Specification 1 no) | 1 | 4456 | 4456 |  |  | 1 | 2673.6 | 1 | 60% | 2673.6 | DC-123
P.35 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerinator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-123
P.37 | Sofinor | MZC10S | Knife Disinfection Cabinet | 1 | 990 | 990 |  |  | 1 | 594 | 1 | 60% | 594 | DC-123
P.40 | Eagle | DM253-5 | Digital Bench Scale - 5kg (As per the layout & Specification 2 no) | 2 | 556 | 1112 |  |  | 2 | 667.2 | 2 | 60% | 667.2 | DC-123
P.42 | La Minerva | DERBY 460 | Vacuum Packer | 1 | 7303 | 7303 |  |  | 1 | 4381.8 | 1 | 60% | 4381.8 | DC-124
P.43 | Scotsman+Everpure | MW458AS OX +Insurice i2000 Twin System | Cube Ice Makers c/w Water Filtration Unit 230kg | 2 | 9764 | 19528 |  |  | 2 | 11716.8 | 2 | 60% | 11716.8 | DC-124
P.44 | Scotsman | SB948+CBT48EAMCD+KSC450 | Ice Storage Bin - 406 | 1 | 6578 | 6578 |  |  | 1 | 3946.8 | 1 | 60% | 3946.8 | DC-124
P.46 | Scotsman | SB530+CBT30EFSD | 243kg - Ice Storage Bin | 1 | 5710 | 5710 |  |  | 1 | 3426 | 1 | 60% | 3426 | DC-124
BP.03 | Rubbermaid | FG360088 | Ingredient Bins | 8 | 1278 | 10224 |  |  | 6 | 4600.8 | 6 | 60% | 4600.8 | DC-120
BP.04 | Rubbermaid | 1883459 | Mobile Waste Bin - 50L Capacity | 5 | 1211 | 6055 |  |  | 5 | 3633 | 5 | 60% | 3633 | DC-120
BP.05 | Kolb | K31-0601AB4 | 60 litre Planetary Mixer | 1 | 30060 | 30060 |  |  | 1 | 18036 | 1 | 60% | 18036 | DC-119
BP.06 | Kolb | K31-0071AG9 | 5 Litre Bench Mixer | 1 | 3443 | 3443 |  |  | 1 | 2065.8 | 1 | 60% | 2065.8 | DC-119
BP.07 | Kolb | K32-0801AB4 | 80 Litre Spiral Mixer | 1 | 30507 | 30507 |  |  | 1 | 18304.2 | 1 | 60% | 18304.2 | DC-119
BP.08 | Salva | CL-1 | Water Meters | 2 | 4343 | 8686 |  |  | 2 | 5211.6 | 2 | 60% | 5211.6 | DC-119
BP.09 | Salva | EA-175 | Water Coolers | 2 | 10621 | 21242 |  |  | 2 | 12745.2 | 2 | 60% | 12745.2 | DC-119
BP.10 | Kolb | K43-6301AF8 | Floor Mounted Roller Sheeter | 1 | 20710 | 20710 |  |  | 1 | 12426 | 1 | 60% | 12426 | DC-119
BP.12 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelvings | 9 | 1266 | 11394 |  |  | 9 | 6836.4 | 9 | 60% | 6836.4 | DC-120
BP.14 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Stations (As per layout 3 qty) | 3 | 1046 | 3138 |  |  | 3 | 1882.8 | 3 | 60% | 1882.8 | DC-120
BP.18 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Units (As per layout 3 qty) | 3 | 608 | 1824 |  |  | 3 | 1094.4 | 3 | 60% | 1094.4 | DC-120
BP.19 | Sulo | 240 with Pedal | Refuse Bins -50Gal | 2 | 306 | 612 |  |  | 2 | 367.2 | 2 | 60% | 367.2 | DC-120
BP.22 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-120
BP.23a | IMC | Pot Boy | Pot Boy (Cookware Scrubber) | 1 | 17537 | 17537 |  |  | 1 | 10522.2 | 1 | 60% | 10522.2 | DC-119
BP.23a | IMC | S64/103+U07/012 | Accessories for Pot Boy | 1 | Included in BP.23a | [8 empty] | DC-121
BP.25 | Eagle | DM253-5 | Digital Bench Scale - 5kg | 2 | 556 | 1112 |  |  | 2 | 667.2 | 2 | 60% | 667.2 | DC-120
BP.28 | Salva | DB-30 | Dough Divider | 1 | 30057 | 30057 |  |  | 1 | 18034.2 | 1 | 60% | 18034.2 | DC-121
BP.40 | Thermomix | TM6 | Multifunctional Processors | 2 | 6333 | 12666 |  |  | 2 | 7599.6 | 2 | 60% | 7599.6 | DC-120
BP.41 | Kolb | K31-0401AB4 | 40 Qt Spiral MIxer | 1 | 11691 | 11691 |  |  | 1 | 7014.6 | 1 | 60% | 7014.6 | DC-119
BP.43 | Salva | TC-5 | Chocolate Tempering Unit | 1 | 3136 | 3136 |  |  | 1 | 1881.6 | 1 | 60% | 1881.6 | DC-119
BP.44 | Pacojet | Pacojet 2 | Sorbet Machine | 1 | 20882 | 20882 |  |  | 1 | 12529.2 | 1 | 60% | 12529.2 | DC-120
BP.49 | Sofinor | CNETC/1P+4550CNET04S | Wall Mounted Hose Reel | 1 | 3349 | 3349 |  |  | 1 | 2009.4 | 1 | 60% | 2009.4 | DC-120
BP.51 | Rubbermaid | FG199300 | Mop/Broom Rack | 1 | 243 | 243 |  |  | 1 | 145.8 | 1 | 60% | 145.8 | DC-120
GM.02 | Rubbermaid | 1883459 | Mobile Waste Bins - 50L Capacity (As per layout & Specification 3qty) | 3 | 1211 | 3633 |  |  | 3 | 2179.8 | 3 | 60% | 2179.8 | DC-120
GM.03 | Pacojet | Pacojet 2 | Sorbet Machine | 1 | 20882 | 20882 |  |  | 1 | 12529.2 | 1 | 60% | 12529.2 | DC-120
GM.06 | Thermomix | TM6 | Multifunctional Processors (As per layout & specification 1no) | 1 | 6333 | 6333 |  |  | 1 | 3799.8 | 1 | 60% | 3799.8 | DC-120
GM.08 | Sirman | PALLADIO 350 VV AUTO | Bench Mounted Automatic Slicer | 1 | 10726 | 10726 |  |  | 1 | 6435.6 | 1 | 60% | 6435.6 | DC-122
GM.09 | Kolb | K31-0071AG9 | Bench Mounted Mixer | 1 | 3443 | 3443 |  |  | 1 | 2065.8 | 1 | 60% | 2065.8 | DC-119
GM.12 | Clifton | FL28D | Water Bath | 1 | 5042 | 5042 |  |  | 1 | 3025.2 | 1 | 60% | 3025.2 | DC-120
GM.13 | La Minerva | DERBY 460+Stand | Vacuum Packer on Mobile Table | 1 | 8192 | 8192 |  |  | 1 | 4915.2 | 1 | 60% | 4915.2 | DC-119
GM.14 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-120
GM.17 | Sofinor | MZC10S | Knife Disinfection Cabinet | 2 | 990 | 1980 |  |  | 2 | 1188 | 2 | 60% | 1188 | DC-120
GM.21 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-120
GM.22 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelvings | 3 | 1351 | 4053 |  |  | 3 | 2431.8 | 3 | 60% | 2431.8 | DC-120
GM.24 | Scotsman+Everpure | NW458AS OX +SB530+Insurice i2000 Twin System | 230kg -Cube Ice Makers c/w Water Filtration Unit , Bin 243kg | 1 | 13892 | 13892 |  |  | 1 | 8335.2 | 1 | 60% | 8335.2 | DC-119
HK.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-120
HK.05 | Clayoven | Custom | Charcoal Tandoor Ovens | 2 | 14880 | 29760 |  |  | 2 | 17856 | 2 | 60% | 17856 | DC-119 & DC-121
HK.06 | Rational+Everpure | I Combi Classic 201G +Kleen Steam CT | 20 GN1/1 Gas Combination Ovens | 2 | 58507 | 117014 |  |  | 2 | 70208.4 | 2 | 60% | 70208.4 | DC-120 & DC-121 & DC-122
HK.06A | Everpure | Kleensteam CT | Water Filters | 1 | Included in HK.06 | [8 empty] | DC-120
HK.08 | Electrolux (900XP) | 391101 | 100L Gas Quick Boiling Kettle | 1 | 23900 | 23900 |  |  | 1 | 14340 | 1 | 60% | 14340 | DC-124
HK.13 | Electrolux (900XP) | 900 XP LINE | Modular Cookline Comprising | 1 |  | 0 |  |  | 1 | 0 | 1 | 60% | 0 | DC-121
HK.13 a | Electrolux (900XP) | 391158+391153+206350*(2)+391160+391154+206350+206350 | Spreader Benches (As per layout 3nos) | 3 | 3912 | 11736 |  |  | 3 | 7041.6 | 3 | 60% | 7041.6 | DC-121
HK.13 b | Electrolux (900XP) | 391006 | Gas Range with 4 Burner & Gas Oven 2/1GN | 2 | 11887 | 23774 |  |  | 2 | 14264.4 | 2 | 60% | 14264.4 | DC-121
HK.13 c | Electrolux (900XP) | 391054+391154+206350+206350 | Plancha - Gas | 1 | 13577 | 13577 |  |  | 1 | 8146.2 | 1 | 60% | 8146.2 | DC-121
HK.13 d | Clifton | FL28D | Water Bath | 1 | 5042 | 5042 |  |  | 1 | 3025.2 | 1 | 60% | 3025.2 | DC-120
HK.17 | Rubbermaid | 1883459 | Mobile Waste Bins - 50L Capacity | 4 | 1211 | 4844 |  |  | 4 | 2906.4 | 4 | 60% | 2906.4 | DC-120
HK.22 | NU-VU | Smoke6 | Mobile Hot Smoking Oven | 1 | 20033 | 20033 |  |  | 1 | 12019.8 | 1 | 60% | 12019.8 | DC-121
HK.25 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelvings | 8 | 1351 | 10808 |  |  | 8 | 6484.8 | 8 | 60% | 6484.8 | DC-120
HK.28 | Thermomix | TM6 | Multifunctional Processors | 2 | 6333 | 12666 |  |  | 2 | 7599.6 | 2 | 60% | 7599.6 | DC-120
HK.29 | Sofinor | MZC10S | Knife Disinfection Cabinets | 2 | 990 | 1980 |  |  | 2 | 1188 | 2 | 60% | 1188 | DC-120
HK.31 | Hobart+Everpure | Ecomax702-11A+Basket+Claris XL | Potwash Machine | 1 | 23617 | 23617 |  |  | 1 | 14170.2 | 1 | 60% | 14170.2 | DC-119
HK.36 | Rubbermaid | FG199300 | Mop/Broom Rack | 1 | 243 | 243 |  |  | 1 | 145.8 | 1 | 60% | 145.8 | DC-120
HK.37 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-120
HK.38 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Units | 2 | 608 | 1216 |  |  | 2 | 729.6 | 2 | 60% | 729.6 | DC-120
SDP.02 | Rubbermaid | 1883459 | Mobile Waste Bins - 50L Capacity | 1 | 1211 | 1211 |  |  | 1 | 726.6 | 1 | 60% | 726.6 | DC-123
SDP.03 | Kolb (Atoll Speed) | Atollspeed 400H (K02-4003T1S) | Microwave Oven | 1 | 18859 | 18859 |  |  | 1 | 11315.4 | 1 | 60% | 11315.4 | DC-124
SDP.08 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
WW.03 | Rubbermaid | SLIM JIM 1971258+FG269288+1980602 | Bottle Bins | 2 | 889 | 1778 |  |  | 2 | 1066.8 | 2 | 60% | 1066.8 | DC-123
WW.04 | Rubbermaid | 1883459 | Mobile Waste Bins | 6 | 1211 | 7266 |  |  | 6 | 4359.6 | 6 | 60% | 4359.6 | DC-123
WW.06 | Hobart+Everpure | Eco-H604S-12B+Claris XL | Hood Type Dishwasher | 1 | 14824 | 14824 |  |  | 1 | 8894.4 | 1 | 60% | 8894.4 | DC-124
WW.09 | Metro | DH2020N | Rack Dollies | 4 | 620 | 2480 |  |  | 4 | 1488 | 4 | 60% | 1488 | DC-123
WW.11 | Rubbermaid | FG199300 | Mop/Broom Rack | 1 | 243 | 243 |  |  | 1 | 145.8 | 1 | 60% | 145.8 | DC-123
WW.14 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
WW.15 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-123
WW.16 | Metro | Super Erecta Pro | Run of 5 Tier Storage Shelvings | 2 | 1052 | 2104 |  |  | 2 | 1262.4 | 2 | 60% | 1262.4 | DC-123
WW.17 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
WW.19 | Metro | PCD11A | Crockery Carts | 2 | 3217 | 6434 |  |  | 2 | 3860.4 | 2 | 60% | 3860.4 | DC-123
SBP.02 | Scotsman+Everpure | ECM106AS OX+Insurice i2000 Single System | Undercounter Ice Machine (50 kg/24 hours) + Filter | 1 | 5264 | 5264 |  |  | 1 | 3158.4 | 1 | 60% | 3158.4 | DC-114
SBP.05 | Rubbermaid | 1883459 | Mobile Waste Bins - 50L Capacity | 1 | 1211 | 1211 |  |  | 1 | 726.6 | 1 | 60% | 726.6 | DC-114
SBP.06 | Hobart+Everpure | Eco-G404S-10B+Claris L | Undercounter Glasswasher 30 baskets/hour | 1 | 6531 | 6531 |  |  | 1 | 3918.6 | 1 | 60% | 3918.6 | DC-114
SBP.07 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-114
LL.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Stations | 2 | 1046 | 2092 |  |  | 2 | 1255.2 | 2 | 60% | 1255.2 | DC-117
LL.03 | Scotsman+Everpure | MFNS56AS+Insurice i2000 Twin System | 570Kg -Cube Ice Makers c/w Water Filtration Unit | 1 | 19833 | 19833 |  |  | 1 | 11899.8 | 1 | 60% | 11899.8 | DC-115
LL.07 | Waring | MX1500XTXSEK | Blender with Silencer | 1 | 2558 | 2558 |  |  | 1 | 1534.8 | 1 | 60% | 1534.8 | DC-117
LL.08 | Rubbermaid | 1883459 | Mobile Waste Bins - 50L Capacity | 7 | 1211 | 8477 |  |  | 7 | 5086.2 | 7 | 60% | 5086.2 | DC-117
LL.09 | Robot Coupe | J80U | Bench Mounted Juicer | 1 | 4144 | 4144 |  |  | 1 | 2486.4 | 1 | 60% | 2486.4 | DC-117
LL.11 | Micromatic | 25" Americano (MDD23) | Nitro Cold Brew Dispenser With Filter | 1 | 18952 | 18952 |  |  | 1 | 11371.2 | 1 | 60% | 11371.2 | DC-117
LL.12 | Animo | M22 (10597) | Arabic Coffee Hotplate | 1 | 617 | 617 |  |  | 1 | 370.2 | 1 | 60% | 370.2 | DC-117
LL.15 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Units | 2 | 608 | 1216 |  |  | 2 | 729.6 | 2 | 60% | 729.6 | DC-117
LL.17 | Metro | Super Erecta Pro | Runs of 5 Tier Storage Shelving (As per the layout 4 nos) | 4 | 1159 | 4636 |  |  | 4 | 2781.6 | 4 | 60% | 2781.6 | DC-117
LL.18 | Metro | PCD11A | Poker Chip Trolleys | 2 | 3217 | 6434 |  |  | 2 | 3860.4 | 2 | 60% | 3860.4 | DC-117
LL.19 | Metro | DH2020N | Rack Dollies | 3 | 620 | 1860 |  |  | 3 | 1116 | 3 | 60% | 1116 | DC-117
LL.21 | Hobart+Everpure | Eco-H604S-12B+Claris XL | Hood Type Dishwasher | 1 | 14824 | 14824 |  |  | 1 | 8894.4 | 1 | 60% | 8894.4 | DC-115
LL.27 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-117
LL.28 | Gamko | KFK/1+KFKHC/MUCS | Refrigerated Waste Cabinet | 1 | 10973 | 10973 |  |  | 1 | 6583.8 | 1 | 60% | 6583.8 | DC-115
LL.42 | Electrolux (Panini) | 603885 HSG3RPRSE3 | Sandwich Grill- High speed | 1 | 28646 | 28646 |  |  | 1 | 17187.6 | 1 | 60% | 17187.6 | DC-115
LL.44 | Rational+Everpure | I Combi Classic XS Mod. 6 ⅔ E+Kleen Steam CT | 6 x 2/3 GN Electric Combination Oven with Softener | 1 | 17617 | 17617 |  |  | 1 | 10570.2 | 1 | 60% | 10570.2 | DC-117
LL.45 | Sofinor | MZC10S | Knife Disinfection Cabinet | 1 | 990 | 990 |  |  | 1 | 594 | 1 | 60% | 594 | DC-117
LL.47 | Electrolux (XP) | 283014+283035 | Electric Salamander Grill | 1 | 6096 | 6096 |  |  | 1 | 3657.6 | 1 | 60% | 3657.6 | DC-115
LL.48 | Electrolux (700XP) | 700 XP LINE | Modular Cooking suite comprising: | 1 |  | 0 |  |  | 1 | 0 | 1 | 60% | 0 | DC-115
48a | Electrolux (700XP) | 371116+371112+206350 | Joining/Infill Table | 1 | 2876 | 2876 |  |  | 1 | 1725.6 | 1 | 60% | 1725.6 | DC-115
48b | Electrolux (700XP) | 371002 | 4 Gas Burner with Gas Oven Range (As per the specification gas oven) | 1 | 8687 | 8687 |  |  | 1 | 5212.2 | 1 | 60% | 5212.2 | DC-115
48c | Electrolux (700XP) | 371323+371112+206350 | Ribbed Griddle - Gas (As per the specification gas oven) | 1 | 7048 | 7048 |  |  | 1 | 4228.8 | 1 | 60% | 4228.8 | DC-115
48d | Electrolux (700XP) | 371340+371113+206350+206350 | Plancha - Electric | 1 | 9446 | 9446 |  |  | 1 | 5667.6 | 1 | 60% | 5667.6 | DC-115
48e | Electrolux (700XP) | 371109+206350 | Aqua Cooker - Electric | 1 | 9221 | 9221 |  |  | 1 | 5532.6 | 1 | 60% | 5532.6 | DC-115
48f | Electrolux (700XP) | 371116+371112+206350 | Joining/Infill Table | 1 | 2876 | 2876 |  |  | 1 | 1725.6 | 1 | 60% | 1725.6 | DC-115
48g | Electrolux (700XP) | 371081+921692 | Twin Pan Electric Deep Fat Fryer (2x5lt) | 1 | 8473 | 8473 |  |  | 1 | 5083.8 | 1 | 60% | 5083.8 | DC-115
48h | Electrolux (700XP) | 371116+371112+206350 | Joining/Infill Table | 1 | 2876 | 2876 |  |  | 1 | 1725.6 | 1 | 60% | 1725.6 | DC-115
UD.01 | WHITE | W340 WITH automatic keyboard control | Uniform Conveyors equipped with a 601 had switch and 600 automatic keyboard control | 2 | 28906 | 57812 |  |  | 2 | 34687.2 | 2 | 60% | 34687.2 | DC-112
R01.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
R01.05 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Unit | 1 | 608 | 608 |  |  | 1 | 364.8 | 1 | 60% | 364.8 | DC-123
R01.06 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminator | 1 | 2688 | 2688 |  |  | 1 | 1612.8 | 1 | 60% | 1612.8 | DC-123
R02.01 | Sofinor | LMASW+LMDSAVX+LMPBP | Knee Operated Wash Hand Station | 1 | 1046 | 1046 |  |  | 1 | 627.6 | 1 | 60% | 627.6 | DC-123
R02.05 | Sofinor | TMX40+TMXG40 | Wall Mounted Insect Control Units | 2 | 608 | 1216 |  |  | 2 | 729.6 | 2 | 60% | 729.6 | DC-123
R02.06 | Mechline -Hygenikx (MGK) | HGX-T-30-S | Air Degerminators | 2 | 2688 | 5376 |  |  | 2 | 3225.6 | 2 | 60% | 3225.6 | DC-123
[8 empty] | 699501 |  | 749890.8 |  |  | 1449391.8
699501

## CERTIFIED TO DATE
PREVIOUS PAYMENTS -ANNEXURE 2
Project Name : |  | Plot 18, Business Bay Dubai, UAE |  |  |  | 03
Company : |  | Sky Palaces Real Estate Development LLC
Contractor : |  | Elenco Trading Establishment
Payment Cert. No. |  | 03 | Budget |  | 7170750 | D171 | 2023-04-11
Contract Title: |  | Hotel Kitchen, Laundry and Waste Equipment for Levels B2, B1, GF, 02, 04 and Typical Guestroom Floors
SN | PC No. | INVOICE NO. |  | PHASE |  | PREVIOUSLY CERTIFIED | CERTIFIED TO DATE
1 | 1 | Application No 01 |  | Advance Payment |  | 1900800 | 1900800
2 | 2 | Application No 02 |  | Material at Site |  | 419700.6 | 419700.6
3 | 3 | Application No 03 |  | Material at Site |  | 0 | 449934.48
TOTAL | [5 empty] | 2320500.6 | 2770435.08
PC No (Please don’t delete this) |  |  |  | 3
Invoice No (Please don’t delete this) |  |  |  | Application No 03
Work Done (Please don’t delete this) |  |  |  | Material at Site
Type |  |  |  | Contractor :
Name |  |  |  | Elenco Trading Establishment
Address 01 |  |  |  | PO Box 2137
Address 02 |  |  |  | Dubai, UAE
Cost Code |  |  |  | D171
Contract Start Date |  |  |  | 2022-02-02
Date of Application |  |  |  | 2023-03-29
Period for Works Certified |  |  |  | N/A
Payment Due Date |  |  |  | 2023-05-13
Certificate Currency |  |  |  | AED
Payment Terms |  |  |  | Payment to be made within 45 days upon the receipt of the IPA

## PS (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Client Provisional Sums
SUMMARY - Bill 2
|  | Accepted Contract Amount | PROGRESS VALUATION
Item | Package |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
2 | Provisional Sum Packages
2.1 | Structure - Steel | 10600000
2.2 | Roof Coverings | 1100000
2.3 | External Walls - Gartners | 154500000
2.4 | External Walls - Remaining Provisional Sum | 11700000
2.5 | BMU | 7000000
2.6 | External Doors | 300000
2.7 | Internal Walls & Partitions | 2600000
2.8 | Contractor Floor Finishes | 1000000
2.9 | Contractor Wall Finishes | 1300000
2.1 | Contractor Ceiling Finishes | 900000
2.11 | Sanitary Appliances | 1900000
2.12 | Electrical Installations | 57800000
2.13 | Mechanical Installations | 63200000
2.14 | Vertical Transportation - KONE | 30000000
2.15 | BWIC | 2800000
2.16 | Drainage | 9600000
2.17 | External Works | 12750000
2.18 | External Lighting | 8000000
2.19 | Client Finishes, Incl Doors, Ironmongery, Fixtures & Fittings & Oyster Fit Out | 28700000
15000000
2.2 | IT Building Automation
| Totals | 420750000 | 0% | 0 | 0% | 0 | 0% | 0

## Contractor's Application (hidden)
NASA MULTIPLEX L.L.C.
THE OPUS, BUSINESS BAY
CONTRACTOR'S APPLICATION FOR INTERIM CERTIFICATE
Contract Title: |  | The Opus, Business Bay |  | Application No: | 11
Date of Contract: |  | 9th March 2008 (Letter of Acceptance) |  | Date of Application: | 2009-03-01
Contractor: |  | Nasa Multiplex L.L.C.
Contract Sum: |  | UAE Dirhams 794,057,000
Contractor's Application for Interim Certificate No: |  |  | 11
We hereby apply for an Interim Certificate in accordance with Clause 14.2 (Advance Payment) and 14.3 (Application for Interim Payment
Certificates ) the amount of such Interim Certificate being as set out below.
| Advance Payment (In Accordance with Item 41 of the LOA dated 9th March 08) |  |  |  | 54196050
| Estimate of the Contract Value of the Works carried out on Site |  |  |  | #N/A
up to Date of Application
| 90% of the Invoice Value delivered to Site of all Plant on Site |  |  |  | 0
| Any other amounts to which we consider ourselves to be |  |  |  | 0
entitled
| GROSS AMOUNT OF INTERIM CERTIFICATE APPLICATION |  |  |  | #N/A
| Deduct Recovery of Advance Payment |  |  |  | 0
(Subject to Receipt of Advanced Payment)
| Amount owed by Omniyat for NMX portion of Certificate No 1 |  |  |  | -2654754.4
| Amount owed by Omniyat for NMX against Certificate No 5 |  |  |  | -999607
| Amount owed by Omniyat for NMX against Certificate No 6 |  |  |  | -806223.4
| Advance Abatement uopto and Including Certificate No 6 |  |  |  | -1143169
| Amount owed by Omniyat for NMX against Certificate No7 |  |  |  | -1880835
| Amount owed by Omniyat for NMX against Certificate No 8 |  |  |  | -1427250
| Amount Owed by Omniyat for NMx against Certificate No 9 |  |  |  | -800000
| Amount Owed by Omniyat for NMx against Certificate No 10 |  |  |  | -800000
| Amount Owed by Omniyat for NMx against Certificate No 11 |  |  |  | -800000
| NET AMOUNT TO DATE |  |  |  | #N/A
| Deduct: Retention |  |  |  | #N/A
| Add: Retention Bond |  |  |  | #N/A
| Deduct: Previous Employer's Representatives Certificate |  |  |  | -61288954
| NETT AMOUNT OF INTERIM CERTIFICATE APPLICATION |  |  |  | #N/A
For and on behalf of
NASA MULTIPLEX L.L.C.
Mr. Andrew Phillips
Contractor's Representative
Distribution (By the Engineer): |  | Original: Employer's Representative
Copies: (1) Employer (2) Quantity Surveyor
Note on H7: lizae:
Note on H8: lizae:
Note on H53: ashleyw: Gross Certified Less Advance Payment Payback

## Payment Application (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
[5 empty] | Accepted Contract Amount | Application Value |  | Total Application Value
1 | Structural Concrete : |  |  |  | 204300000 | 0
(Refer to the Breakdown Appended)
2 | Provisional Sum Packages : |  |  |  | 420750000 | 0
(Refer to the Breakdown Appended)
3 | Design Fees :
| 3.1 | Structural Engineer : |  |  | 10439000 | 6119850
(Refer to the Breakdown Appended)
| 3.2 | MEP : |  |  | 1561000 | 528000
(Refer to the Breakdown Appended)
4 | Preliminaries : |  |  |  | 80000000 | 0
(Refer to the Breakdown Appended)
5 | Attendances for Enabling Works : |  |  |  | 2820000 | 1794548
(Refer to the Breakdown Appended)
6 | Professional Indemnity Insurance : |  |  |  | 2000000 | 437500
(Refer to the Breakdown Appended)
7 | Variation Works : |  |  |  | 0 | #N/A
(Refer to the Breakdown Appended)
8 | Remeasurements : |  |  |  | 0 | 0
(Refer to the Breakdown Appended)
|  |  |  | Sub Total | 721870000 |  |  | #N/A
9 | Margin |  |  | 10% | 72187000 |  |  | #N/A
[5 empty] | 794057000 |  |  | #N/A
10 | Materials On Site:
| 11.1 | NMX Works : | [5 empty] | 0
11 | Additional Expenditure for Preliminaries, EOT : | [6 empty] | 3200000
(Refer to the Breakdown Appended)
(Subject to Receipt of Advanced Payment)
|  |  |  | GROSS AMOUNT DUE |  |  |  | #N/A
|  |  | LESS RETENTION |  |  |  | 5% | #N/A
|  |  |  | GROSS AMOUNT DUE |  |  |  | #N/A
Note on I11: lizae: Linked Structural Concrete Temporary Sheet
Note on I19: lizae: linked to LEC
Note on I22: lizae: linked to LEC
Note on I25: lizae: Linked Prelim Temporary Sheet
Note on I28: lizae: linked to LEC
Note on I31: lizae: linked to LEC
Note on I34: lizae: linked to LEC
Note on I53: lizae: Linked EOT Temporary Sheet

## Advance Payment (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Advance Payment
|  |  | Advance Payment Claim |  |  | Advance Payment Abatement
Item |  | Description | Accepted Contract Amount | % | Value | Works Complete | % | Value
1 | Bill No. 1 | Structural Concrete Frame | 204300000 | 15% | 30645000 | 0 | 15% | 0
2 | Bill No. 2 | Provisional Sum Packages :
|  | Structure - Steel | 10600000
|  | Roof Coverings | 1100000
|  | External Walls - Gartners | 154500000 | 15% |  | 0
|  | External Walls - Remaining PS Allowance | 11700000
|  | BMU | 7000000
|  | External Doors | 300000
|  | Internal Walls & Partitions | 2600000
|  | Contractor Floor Finishes | 1000000
|  | Contractor Wall Finishes | 1300000
|  | Contractor Ceiling Finishes | 900000
|  | Sanitary Appliances | 1900000
|  | Electrical Installations | 57800000
|  | Mechanical Installations | 63200000
|  | Vertical Transportation - KONE | 30000000 | 15% | 0 | 0
|  | BWIC | 2800000
|  | Drainage | 9600000
|  | External Works | 12750000
|  | External Lighting | 8000000
|  | Client Finishes, Incl Doors, Ironmongery, Fixtures & Fittings & Oyster Fit Out | 28700000
|  | IT Building Automation | 15000000
3 | Bill No. 3 | Provisional Sum for Completion of Mechanical, Electrical and Plumbing (MEP) Design and Structural Design Supervision and Inspections :
|  | Structural - BG&E | 10439000 | 15% | 0 | 6119850 | 0% | 0
|  | MEP - Whitby & Bird LOI | 960000 | 15% | 0 | 528000 | 0% | 0
|  | Remaining Design Provisional Sum | 601000
4 |  | Preliminaries (Fixed) | 80000000 | 15% | 12000000 | 0 | 15% | 0
5 | Bill No. 4(a) | Attendances for Piling, Shoring and Enabling Works (Fixed) | 2820000 | 15% | 423000 | 1794548 | 0% | 0
6 | Bill No. 4(b) | Professional Indemnity Insurance (Fixed) | 2000000 | 15% | 300000 | 437500 | 0% | 0
|  | Sub Totals | 721870000 |  | 43368000 | 8879898 |  | 0
7 |  | Add Contractor's Profit Margin at 10% | 72187000 | 15% | 10828050 | 887990 | 0% | 0
|  | TOTAL | 794057000 |  | 54196050 | 9767888 |  | 0
Note on H15: lizae: Linked Structural Concrete Temporary Sheet
Note on H49: lizae: Linked Prelim Temporary Sheet

## Structure-Temp (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: |  |  |  |  | 2009-03-01
Application No: |  |  |  |  | 11
Structural Concrete
|  | Accepted Contract Amount | Percentage Complete | Application Amount | Remarks
Item | Package
1 | Structural Concrete
1.1 | System Formwork |  |  | 0 | Included within Advance Payment
1.2 | Jumpform |  |  | 0 | Included within Advance Payment
1.3 | Substructure Waterproofing |  |  | 0 | Included within Advance Payment
| Totals | 204300000 | 0% | 0

## Structural Sum (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Structural Concrete
SUMMARY - Bill 1
|  | Accepted Contract Amount | PROGRESS VALUATION
Item | Package |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
1 | Structural Concrete
1.1 | Dewatering | Excluded
1.2 | Earthworks | 110228.24 |  |  | 0% | 0
1.3 | Termite Treatment | 64071.44 |  |  | 0% | 0
1.4 | Pile Head Cut Off | 509200 |  |  | 0% | 0
1.5 | Road Markings | Excluded
1.6 | Road Markings | Excluded
1.7 | Formwork | 51071506.79 | 26% | 13354958 | 0% | 0 | 26% | 13354958 | 22191310 | 80% | 17753048
-4398090
1.8 | Expansion / Construction Joints | 32144.5 |  |  | 0% | 0
1.9 | Reinforcement | 81596753.79 |  |  | 0% | 0
1.1 | Concrete | 57422108.31 |  |  | 0% | 0
1.11 | Post Tensioning Works | 10311307.2 |  |  | 0% | 0
1.12 | Waterproofing Works | 3182679.73 |  |  | 0% | 0
| Totals | 204300000 | 7% | 13354958 | 0% | 0 | 7% | 13354958

## ◄Formwork (hidden)
Omniyat Properties
The Opus, Business Bay | [13 empty] | 2009-03-01
Application No: |  | 11
Contract : | The Opus At Business Bay, Dubai, U.A.E.
Item : | Formwork
Ref: | Description | Qty | Unit | Rate | Amount | PROGRESS VALUATION | [8 empty] | Remeasured Surplus/ Deficit
[6 empty] | Last Month |  |  | This Month |  |  | To Date |  |  | Estimated Qty Tower | Diff from Orig Qty | Rate | Value At Risk
[6 empty] | % | Qty | Value | % | Qty | Value | % | Qty | Value
Formwork
A | To Pile Caps | 560.68 | m2 | 280.73 | 157399.7 | 25% |  | 39349.93 | 0% |  | 0 | 25% |  | 39349.93 | 560.68 | 0 | 280.73 | 0
B | To Raft slab | 2488.93 | m2 | 380.7 | 947535.65 | 25% |  | 236883.91 | 0% |  | 0 | 25% |  | 236883.91 | 2488.93 | 0 | 380.7 | 0
C | To Retaining Walls | 19343.32 | m2 | 155.6 | 3009820.59 | 25% |  | 752455.15 | 0% |  | 0 | 25% |  | 752455.15 | 19343.32 | 0 | 155.6 | 0
D | To Staircases | 3600.64 | m2 | 144.6 | 520652.54 | 25% |  | 130163.14 | 0% |  | 0 | 25% |  | 130163.14 | 3600.64 | 0 | 144.6 | 0
E | To Walls | 90092.55 | m2 | 206.1 | 18568074.56 | 25% |  | 4642018.64 | 0% |  | 0 | 25% |  | 4642018.64 | 90092.55 | 0 | 206.1 | 0
F | To Columns | 17844.87 | m2 | 114.3 | 2039668.64 | 25% |  | 509917.16 | 0% |  | 0 | 25% |  | 509917.16 | 17844.87 | 0 | 114.3 | 0
G | To Columns (inclined) | 3702.86 | m2 | 247 | 914606.42 | 25% |  | 228651.61 | 0% |  | 0 | 25% |  | 228651.61 | 3702.86 | 0 | 247 | 0
H | To Post Tensioned Beams & Slabs | 46418.66 | m2 | 138.4 | 6424342.54 | 25% |  | 1606085.64 | 0% |  | 0 | 25% |  | 1606085.64 | 46418.66 | 0 | 138.4 | 0
I | To Suspended Slabs | 125250.76 | m2 | 153.5 | 19225991.66 | 25% |  | 4806497.92 | 0% |  | 0 | 25% |  | 4806497.92 | 125250.76 | 0 | 153.5 | 0
J | To Suspended Beams | 3964.92 | m2 | 128.4 | 509095.73 | 25% |  | 127273.93 | 0% |  | 0 | 25% |  | 127273.93 | 3964.92 | 0 | 128.4 | 0
K | To Civil Works concrete | 2000 | m2 | 171.2 | 342400 | 25% |  | 85600 | 0% |  | 0 | 25% |  | 85600 | 2000 | 0 | 171.2 | 0
L | To Miscellaneous Concrete | 800 | m2 | 171.2 | 136960 | 25% |  | 34240 | 0% |  | 0 | 25% |  | 34240 | 800 | 0 | 171.2 | 0
|  | 316068.19 | m2 |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 316068.19 | 0
M | To edges of slab: 600mm thick | 960 | m | 43.4 | 41664 | 25% |  | 10416 | 0% |  | 0 | 25% |  | 10416 | 960 | 0 | 43.4 | 0
N | To edges of slab: 500mm thick |  | m | [5 empty] | 0% |  | 0 |  |  |  |  | 0 | 0 | 0
O | To edges of slab: 350mm thick | 1321.74 | m | 27.4 | 36215.68 | 25% |  | 9053.92 | 0% |  | 0 | 25% |  | 9053.92 | 1321.74 | 0 | 27.4 | 0
P | To edges of slab: 350mm thick (curved) | 445 | m | 27.4 | 12193 | 25% |  | 3048.25 | 0% |  | 0 | 25% |  | 3048.25 | 445 | 0 | 27.4 | 0
Q | To edges of slab: 300mm thick | 248.88 | m | 24.2 | 6022.9 | 25% |  | 1505.73 | 0% |  | 0 | 25% |  | 1505.73 | 248.88 | 0 | 24.2 | 0
R | To edges of slab: 400mm thick | 467.23 | m | 30.6 | 14297.24 | 25% |  | 3574.31 | 0% |  | 0 | 25% |  | 3574.31 | 467.23 | 0 | 30.6 | 0
S | To edges of slab: 300mm thick (curved) |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
T | To edges of slab: 275mm thick | 8708.3 | m | 22.6 | 196807.58 | 25% |  | 49201.9 | 0% |  | 0 | 25% |  | 49201.9 | 8708.3 | 0 | 22.6 | 0
U | To edges of slab: 275mm thick (curved) | 4609.78 | m | 22.6 | 104181.03 | 25% |  | 26045.26 | 0% |  | 0 | 25% |  | 26045.26 | 4609.78 | 0 | 22.6 | 0
Formwork Continued
A | To edges of slab: 250mm thick |  | m | 20.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 20.2 | 0
B | To edges of slab: 300mm thick |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
C | To edges of slab: 280mm thick |  | m | 22.9 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 22.9 | 0
D | To edges of slab: 280mm thick (curved) |  | m | 22.9 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 22.9 | 0
E | To edges of slab: 250mm thick |  | m | 20.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 20.2 | 0
F | To edges of slab: 250mm thick (curved) | 355.58 | m | 20.2 | 7182.72 | 25% |  | 1795.68 | 0% |  | 0 | 25% |  | 1795.68 | 355.58 | 0 | 20.2 | 0
G | To edges of slab: 300mm thick |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
H | To edges of slab: 300mm thick (curved) |  | m | 24.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 24.2 | 0
I | To edges of slab: 225mm thick |  | m | 18.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 18.2 | 0
J | To edges of slab: 150mm thick | 605.48 | m | 12.2 | 7386.86 | 25% |  | 1846.72 | 0% |  | 0 | 25% |  | 1846.72 | 605.48 | 0 | 12.2 | 0
K | To edges of slab: 150mm thick (curved) | 52.86 | m | 12.2 | 644.89 | 25% |  | 161.22 | 0% |  | 0 | 25% |  | 161.22 | 52.86 | 0 | 12.2 | 0
L | To edges of slab: 225mm thick (curved) |  | m | 18.2 |  |  |  |  | 0% |  | 0 |  |  |  |  | 0 | 18.2 | 0
M | Formwork to edges to form Construction Joints | 12528 | m | 15 | 187920 | 25% |  | 46980 | 0% |  | 0 | 25% |  | 46980 | 12528 | 0 | 15 | 0
N | Formwork to edges to form Expansion Joints | 292.3 | m | 30 | 8769 | 25% |  | 2192.25 | 0% |  | 0 | 25% |  | 2192.25 | 292.3 | 0 | 30 | 0
|  | 30595.15 | m |  |  |  | 0 |  |  | 0 |  |  | 0 |  | 30595.15 | 0
| TOTAL |  |  |  | 53419832.93 | 25% |  | 13354958.27 | 0% |  | 0 | 25% |  | 13354958.27 |  |  |  | 0
Note on M15: lizae:

## Design (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Provisional Sums - Design
|  | Accepted Contract Amount | PROGRESS VALUATION
Item | Description |  | Total Claim |  | Previous Claims |  | This Claim
|  |  | % | Value | % | Value | % | Value
3 | Provisional Sums - Design
Provisional Sum for Completion of Mechanical, Electrical and Plumbing (MEP) Design and Structural Design Supervision and Inspections :
| Structure | 10439000 | 59% | 6119850 | 59% | 6119850 | 0% | 0
3.1 | Structure - BG&E Engineers | 6900000 | 89% | 6119850 | -89% | 6119850 | 0% | 0
| Supervision | 3539000 |  | 0 |  | 0 |  | 0
| MEP | 1561000 | 34% | 528000 | 34% | 528000 | 0% | 0
3.2 | MEP - Whitby & Bird | 960000 | 55% | 528000 | 55% | 528000 | 0% | 0
| MEP Design - Outstanding Provisional Sum Value | 601000 |  | 0 |  | 0 |  | 0
| Totals | 12000000 | 55% | 6647850 | 55% | 6647850 | 0% | 0

## Prelim-Temp (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: |  |  |  |  | 2009-03-01
Application No: |  |  |  |  | 11
Preliminaries
|  | Accepted Contract Amount | Percentage Complete | Application Amount | Remarks
Item | Package
1 | Preliminaries | 80000000
1.1 | Site Administration and Supervision(Pre & Post Construction,Staff - Management & Supervision) |  |  | 0 | Included within Advance Payment
1.2 | Miscellaneous Labour (Labour for site) |  |  | 0 | Included within Advance Payment
1.3 | Crane Operator, Alimak, Drivers and Banksman |  |  | 0 | Included within Advance Payment
1.4 | Transport of People |  |  | 0 | Included within Advance Payment
1.5 | Health and Safety Programme(Safety Training, First Aid, Safety Signage, Extinguishers) |  |  | 0 | Included within Advance Payment
1.6 | Site Accomodation (Temporary Buildings, Office Furniture , IT & Software Set Up, Consumables, Plotter, Photocopy machines) |  |  | 0 | Included within Advance Payment
1.7 | Site Signage |  |  | 0 | Included within Advance Payment
1.8 | Temporary Utilities ( Site Power, Water, Drainage, Genset, Fuel) |  |  | 0 | Included within Advance Payment
1.9 | Telecommunications (Telephone, & Telephone Set up, Fax & Mobile Phones) |  |  | 0 | Included within Advance Payment
1.1 | Plant and Cranage ( Crane, Hoist, Other Plant & Equipment, FOL) |  |  | 0 | Included within Advance Payment
1.11 | Scaffolding-Access / Edge Protection |  |  | 0 | Included within Advance Payment
1.12 | Site Clean Up( Rubbish Removal ) |  |  | 0 | Included within Advance Payment
1.13 | Final Cleaning |  |  | 0 | Included within Advance Payment
1.14 | Site Security (Security Guards, Protection of Permanent Works) |  |  | 0 | Included within Advance Payment
1.15 | Surveys ( Survey and Surveying Equipment ) |  |  | 0 | Included within Advance Payment
1.16 | Photographs and Records |  |  | 0 | Included within Advance Payment
1.17 | Facilities for Employer |  |  | 0 | Included within Advance Payment
1.18 | Insurance and Bonds |  |  | 0 | Included within Advance Payment
| Totals | 80000000 | 0% | 0

## ◄Cranes (hidden)
MPXPE / HOA / OPUS - 001
OPUS - Business Bay
Appendix A
Multiplex Plant & Equipment LLC
| TC1 | TC2 | TC3 | TC4
Tower Crane Specification
Make | HKTC | HKTC | HKTC | HKTC
Model | 290-HC 12 | 290-HC 12 | 290-HC 12 | 290-HC 12
Y.O.M | 2008 | 2008 | 2008 | 2008
Jib Length | 60m | 55m | 55m | 55m
Maximum Capacity Freestand | 12T | 12T | 12T | 12T
Tip Load | 4.1T@60m | 4.8T@55m | 4.8T@55m | 4.8T@55m
Freestand Height | 69.9m | 57.3m | 69.9m | 57.3m
Final Height | 119.58m | 131.82m | 119.58m | 131.82m
Additional Tower Sections Required | 12 | 18 | 12 | 18
No Collars Required | 2 | 3 | 2 | 3
Mast Dimension | 2.3 x 2.3 x 4.14 | 2.3 x 2.3 x 4.14 | 2.3 x 2.3 x 4.14 | 2.3 x 2.3 x 4.14
Rental (Incl. Maintenance)
Minimum Hire Duration (Months) | 20 | 18 | 19 | 17
Rental / Month | 95000 | 95000 | 95000 | 95000
Total Rent Payable | 1900000 | 1710000 | 1805000 | 1615000
Extras
Fixing Angles | 40000 | 35000 | 40000 | 35000
Transport to Site | 40000 | 40000 | 40000 | 40000
First Erection | 20000 | 20000 | 20000 | 20000
Tie Installation (Dhs 4000 / Set) | 8000 | 12000 | 8000 | 12000
Jacking Up or Down (Dhs 1400 / Section) | 16800 | 25200 | 16800 | 25200
Third party Inspections (Dhs 1,500 / Test) | 4500 | 6000 | 4500 | 6000
Dismantling | 45000 | 45000 | 45000 | 45000
Transport from Site | 40000 | 40000 | 40000 | 40000
Total Extras | 214300 | 223200 | 214300 | 223200
Minimum Payable to Multiplex Plant & Equipment LLC | 2114300 | 1933200 | 2019300 | 1838200
Totals | 7905000

## Enabling Works Attendances (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Enabling Work Attendances
SUMMARY - Bill 4(b)
Month No |  | Accepted Contract Amount | PROGRESS VALUATION
| Month |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
Enabling Works Attendances
-6 | May 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-5 | June 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-4 | July 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-3 | Áugust 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-2 | September 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
-1 | Óctober 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
1 | November 2008 | 256364 | 100% | 256364 | 0% | 0 | 100% | 256364
2 | December 2008 | 256364
3 | Januray 2009 | 256364
4 | February 2009 | 256364
5 | March 2009 | 256360
| Totals | 2820000 | 64% | 1794549 | 0% | 0 | 64% | 1794548

## PI Insurance (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: | [7 empty] | 2009-03-01
Application No: | [7 empty] | 11
Professional Indemnity Insurance
Month No |  | Accepted Contract Amount | PROGRESS VALUATION
| Month |  | Last Month |  | This Month |  | To Date
|  |  | % | Value | % | Value | % | Value
Professional Indemnity Insurance
2008
-7 | Ápril 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-6 | May 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-5 | June 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-4 | July 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-3 | Áugust 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-2 | September 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
-1 | Óctober 2008 | 62500 | 100% | 62500 | 0% | 0 | 100% | 62500
1 | November 2009 | 62500 |  |  |  |  | 0% | 0
2 | December 2008 | 62500 |  |  | 0% | 0 |  | 0
2009
3 | January 2009 | 62500 |  |  | 0% | 0 |  | 0
4 | February 2009 | 62500 |  |  | 0% | 0 |  | 0
5 | March 2009 | 62500 |  |  | 0% | 0 |  | 0
6 | Ápril 2009 | 62500 |  |  | 0% | 0 |  | 0
7 | May 2009 | 62500 |  |  | 0% | 0 |  | 0
8 | June 2009 | 62500 |  |  | 0% | 0 |  | 0
9 | July 2009 | 62500 |  |  | 0% | 0 |  | 0
10 | Áugust 2009 | 62500 |  |  | 0% | 0 |  | 0
11 | September 2009 | 62500 |  |  | 0% | 0 |  | 0
12 | Óctober 2009 | 62500 |  |  | 0% | 0 |  | 0
13 | November 2009 | 62500 |  |  | 0% | 0 |  | 0
14 | December 2009 | 62500 |  |  | 0% | 0 |  | 0
2010
15 | January 2010 | 62500 |  |  | 0% | 0 |  | 0
16 | February 2010 | 62500 |  |  | 0% | 0 |  | 0
17 | March 2010 | 62500 |  |  | 0% | 0 |  | 0
18 | Ápril 2010 | 62500 |  |  | 0% | 0 |  | 0
19 | May 2010 | 62500 |  |  | 0% | 0 |  | 0
20 | June 2010 | 62500 |  |  | 0% | 0 |  | 0
21 | July 2010 | 62500 |  |  | 0% | 0 |  | 0
22 | Áugust 2010 | 62500 |  |  | 0% | 0 |  | 0
23 | September 2010 | 62500 |  |  | 0% | 0 |  | 0
24 | Óctober 2010 | 62500 |  |  | 0% | 0 |  | 0
25 | November 2010 | 62500 |  |  | 0% | 0 |  | 0
| Totals | 2000000 | 22% | 437500 | 0% | 0 | 22% | 437500

## EOT-Temp (hidden)
NASA MULTIPLEX L.L.C
The Opus, Business Bay
Date of Application: |  |  |  |  | 2009-03-01
Application No: |  |  |  |  | 11
Additional Expenditure for Preliminaries Extension of Time
|  | Accepted Contract Amount | Percentage Complete | Application Amount | Remarks
Item | Package
1 | Additional Expenditure for Preliminaries Extension of Time
1.1 | Month 1 - Nov 08 | 800000 | 100% | 800000
1.2 | Month 2 - Dec 08 | 800000 | 100% | 800000
1.3 | Month 3 - Jan 09 | 800000 | 100% | 800000
1.4 | Month 4 - Feb 09 | 800000 | 100% | 800000
1.5 | Month 5 - Mar 09 | 800000 |  | 0
1.5 | Month 6 - Apr 09 | 800000 |  | 0
1.5 | Month 7 - May 09 | 361290.32 |  | 0
Note : Month 7 May 09 based on proposed
start date on site 15/05/09
| Totals | 5161290 | 62% | 3200000

## Anwa (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | ANWA, DUBAI MARITIME CITY |  | Certificate No: | 014
|  |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Asset Management LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Manamgement LLC |  | Contract Start Date :
Date of Application:
Employer : | ANWA Real Estate Developments LLC |  | Payment Due Date :
| PO Box 709298 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMNIYAT ASSET MANAGEMENT LLC
Oliver Keegan |  | Tore Zeidler |  | Dean Lander
Project Manager |  | Development Manager |  | Development Director
ANWA REAL ESTATE DEVELOPMENT LLC approval to proceed the net amount certified for approval
Mohammad Ali Al Rahma |  |  |  | Date
Manager
ALMASA MARITIME ONE LIMITED approval to proceed the net amount certified for approval
Ishan Garga |  | Mark Phoenix |  | Date
Authorized Signatory |  | Authorized Signatory
Note: MA is POA of M. Ali Al Rahma

## The Sterling East (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Sterling East House |  | Certificate No: | 014
| Business Bay Dubai UAE |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Middle East Real Estate Developments LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Management LLC |  | Contract Start Date :
Date of Application:
Employer : | OP 17 Limited |  | Payment Due Date :
| PO Box 48926 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMINIYAT MIDDLE EAST REAL ESTATE DEVELOPMENTS LLC
Oliver Keegan |  | Tore Zeidler |  | Dean Lander
Project Manager |  | Development Manager |  | Development Director
Ishan Garga |  | Mark Phoenix |  | Date
Director - Corporate Finance |  | Managing Director
OP 17 LIMITED approval to proceed the net amount certified for approval
Anthony Manning
Authorized Signatory

## The Sterling West (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Sterling West House |  | Certificate No: | 014
| Business Bay Dubai UAE |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Middle East Real Estate Developments LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Management LLC |  | Contract Start Date :
Date of Application:
Employer : | Omniyat Properties Seventeen Ltd. |  | Payment Due Date :
| PO Box 48926 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMINIYAT MIDDLE EAST REAL ESTATE DEVELOPMENTS LLC
Oliver Keegan |  | Tore Zeidler |  | Dean Lander
Project Manager |  | Development Manager |  | Development Director
Ishan Garga |  | Mark Phoenix |  | Date
Director - Corporate Finance |  | Managing Director
OMNIYAT PROPERTIES SEVENTEEN LTD. approval to proceed the net amount certified for approval
Zainab T A M Ali
Authorized Signatory

## The Gemini (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Gemini, Business Bay Dubai UAE |  | Certificate No: | 014
|  |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Middle East Real Estate Developments LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Middle East Real Estate Developments LLC |  | Contract Start Date :
Date of Application:
Employer : | Omniyat Properties Ten Limited |  | Payment Due Date :
| PO Box 48926 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMNIYAT MIDDLE EAST REAL ESTATE DEVELOPMENTS LLC
Colin James |  | Joel Shearer |  | John Airey
Project Manager |  | Senior Development Manager |  | Development Director
Ishan Garga
Director - Corporate Finance
OMNIYAT PROPERTIES TEN LIMITED approval to proceed the net amount certified
Anthony Manning |  | Mark Phoenix |  | Date
Authorized Signatory |  | Authorized Signatory

## Opus Hotel (hidden)
INTERIM PAYMENT CERTIFICATE
PROJECT: | The Opus Boutique Hotel |  | Certificate No: | 014
| Business Bay Dubai UAE |  | Date of Certificate : | 2014-08-15
Issued By : | Employer's Representative |  | Invoice No. | (invoice submitted by the supplier)
| Omniyat Asset Management LLC |  | Cost Code: | (cost codes supplied by Omniyat accounts)
Dubai, UAE
Development Management | Omniyat Asset Management LLC |  | Contract Start Date :
Date of Application:
Employer : | Opus HM Limited |  | Payment Due Date :
| PO Box 506503 |  | Certificate Currency:
Dubai, UAE
|  |  | VALUE COMPLETE | %
Contractor/Consultant : |  |  | CERTIFIED FOR PAYMENT | %
(Address)
Dubai, UAE
Currency
Original Contract Value
Variations Approved to Date
AdjustedContract Value
(A) Contract Residual Advance Payment Balance After This certificate |  |  |  | 0
Advance Payment |  | 0
LESS:
Advance Payment Recovery - Works Completed |  | 0
Residual Advance Carried from Last Certificate |  | 0
Residual Advance After this certificate |  | 0
(B) Value of Works Completed To Date (Valuation of Work In Place)-AED |  |  |  | 0
Contract Works |  | 0
Variations |  | 0
(C=A+B) Certified Value - Cumulative |  |  |  | 0
(D) LESS Retention (%) | Refer to calculation
(E) LESS: Deferred (%) | Refer to calculation
(F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 0
(G) LESS Previous Certified Value
(H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  |  | 0
RESIDUAL ADVANCE VALUE |  |  |  | 0
LESS Recovery form this Certificate |  |  |  | 0
RESIDUAL ADVANCE VALUE OF THIS CERTIFICATE |  |  |  | 0
Notes:
Payment Terms:
APPROVALS
We certify that the above to be true and correct for and on behalf of OMNIYAT ASSET MANAGEMENT LLC
Joel Shearer
Senior Development Manager |  |  |  | Date
John Airey
Development Director |  |  |  | Date
OPUS HM LIMITED approval to proceed the net amount certified
Ishan Garga |  | Mark Phoenix
Authorized Signatory |  | Authorized Signatory |  | Date