## IPC
PROJECT |  |  | DORCHESTER HOTEL AND RESIDENCES | [8 empty] | IPC-11
EMPLOYER |  |  | SKY PALACES REAL ESTATE DEVELOPMENT LLC
EMPLOYER'S REP |  |  | OMNIYAT CONCEPT INVESTMENTS LLC
ENGINEER |  |  | BREWER SMITH BREWER GULG ( BSBG )
CONTRACTOR |  |  | KHANSAHEB CIVIL ENGINEERING - MEP DIVISION
FOR THE PERIOD ENDING |  |  | 2022-12-31
Item | Description | Contractor | F015/15.710.57/33803/CDCT/0322 |  | Current Anticipated Contract |  |  |  | Work Done |  |  | Remarks
|  |  | Contract Amount (AED) | % | Amount (AED) | Previous Progress (%) | This Month Progress (%) | Cumulative Progress (%) | Previous Amount (AED) | This Month Amount (AED) | Cumulative Amount (AED)
| PRELIMINARIES |  | 11059900 | 104.4% | 11547237.94 |  |  |  | 8828756.6855 | 1246859.4316 | 10075616.1172
A | MEP Staff | KMEP | 10059900 | 100% | 10059900 | 74.3% | 11.07% | 85.37% | 7474618.4055 | 1113659.7716 | 8588278.1772
B | MEP Preliminaries | KMEP | 1000000 | 148.7% | 1487337.94 | 91.04% | 8.956% | 100% | 1354138.28 | 133199.66 | 1487337.94
| DIRECT WORKS |  | 22000000 | 147.1% | 32351673.7929 |  |  |  | 21193196.0133 | 3785644.9194 | 24978840.9327
C | MEP Labour Supply | KMEP | 9700189.2421 | 155.9% | 15122050.735 | 85% | 15% | 100% | 12853596.905 | 2268453.83 | 15122050.735
D | MEP Work Approvals | KMEP | 6850000 | 144.7% | 9911100.37 | 59.44% | 12.79% | 72.24% | 5765745.09 | 1365433.36 | 7131178.45
E | MEP Material Purchases | KMEP | [6 empty] | 125828.59 | -97397.42 | 28431.17
F | Historical Cost under W.A | KMEP |  |  | 892511.93 | 90.99% | -1.381% | 89.61% | 812072.34 | -12324.05 | 799748.29
G | Fire Protection | FIREX | 1848858 | 108.9% | 2012658 | 56.76% | 4.607% | 61.37% | 1142381.4423 | 92719.2482 | 1235100.6905
H | BMS works | JCI | 400386 | 103.3% | 413786 | 15.94% | 0% | 15.94% | 65964.5899 | 0 | 65964.5899
I | Gas works | UGAZ | 374640 | 100% | 374640 | 45.07% | 5.501% | 50.57% | 168840 | 20608 | 189448
J | HWS Equipments | FJT | 359100 | 322.5% | 1158100 | 0% | 0% | 0% | 0 | 0 | 0
K | ELV works | SIS | 2274721.7579 | 100% | 2274721.7579 | 5.226% | 5.026% | 10.25% | 118886.8361 | 114330.5336 | 233217.3697
L | Fire Stop - Sealant Works | FSME | 192105 | 100% | 192105 | 72.81% | 17.61% | 90.42% | 139880.22 | 33821.4176 | 173701.6376
| PS WORKS |  | 9400000 | 103% | 9686412.1578 |  |  |  | 1791197.2249 | 552474.7865 | 2343672.0114
M | Lifts | KONE | 1800000 | 51.02% | 918410.634 | 6.615% | 0% | 6.615% | 60750 | 0 | 60750
N | GRMS and Access control system | Creation Gulf | 2300000 | 113.2% | 730824 | 14.47% | 0% | 14.47% | 105770.5869 | 0 | 105770.5869
O | FOH ELV Works | SIS (FOH) |  |  | 1873397.3838 | 11.51% | 3.836% | 15.35% | 215654.418 | 71859.2065 | 287513.6245
P | Sanitarywares | SANIPEX, AF and Others | 1000000 | 174.6% | 1746063.96 | 11.2% | 2.173% | 13.38% | 195616.76 | 37946.1 | 233562.86 | Purchased under work approvals
Q | Lighting fixtures | P&S, HSE and Others | 4300000 | 102.7% | 4417716.18 | 27.47% | 10.02% | 37.49% | 1213405.46 | 442669.48 | 1656074.94
| Total MEP Amount |  | 42459900 | 126.2% | 53585323.8907 |  |  |  | 31813149.9237 | 5584979.1375 | 37398129.0612
| MEP OHP (12.5%) |  | 5307487.5 |  | 6698165.4863 |  |  |  | 3976643.7405 | 698122.3922 | 4674766.1327
| Overall KMEP Amount |  | 47767387.5 | 126.2% | 60283489.377 |  |  |  | 35789793.6642 | 6283101.5297 | 42072895.1939
[5 empty] | -12516101.877 |  |  | Dec' 2022 | 31813149.9237 | 0
[8 empty] | Nov' 2022 | 31813149.9237 | 6948777.268
[8 empty] | Oct' 2022 | 24864372.6557 | 5429139.06
[8 empty] | Sep' 2022 | 19435233.5958 | 5173658.1427
[8 empty] | Aug' 2022 | 14261575.453 | 2992453.6061
[8 empty] | Jul' 2022 | 11269121.8469 | 3790588.8902
[8 empty] | Jun' 2022 | 7478532.9567 | 4393908.9631
[8 empty] | May' 2022 | 3084623.9936 | 2277051.0336
[8 empty] | Apr' 2022 | 807572.96 | 807572.96

## A. Staff
IPC-11 | MEP STAFF COST | [6 empty] | PRELIMINARIES
S.Nr | Description | Designation | Company | Claim/ Invoice Ref. | Previous Amount (AED) | Current Amount (AED) | Cumulative Amount (AED) | Remarks | Dec'22 | Nov'22 | Oct'22 | Sep'22 | Aug'22 | July'22 | June'22 | May'22 | Apr'22
| KMEP |  |  |  | 5666850.052 | 802072.73 | 6468922.782
1 | KMEP Direct Staffs | All | KMEP | Statff schedule | 5666850.052 | 802072.73 | 6468922.782 | KMEP Schedule | 802072.73 | 807009.09 | 779414.29 | 776959.09 | 752213.04 | 788080.95 | 736518.182 | 682136.36 | 344519.05
| TXM Labour Supply |  |  |  | 725469.8835 | 139339.6706 | 864809.5542
1 | Mohammad Azhar | Mech Engineer | TXM Labour Supply | Invoice-4463 | 118799.7 | 21458.5 | 140258.2 | 31 days of Dec'22
2 | Ibrahim Sultan | Mech Engineer | TXM Labour Supply | Invoice-4463 | 88258.2 | 19383.24 | 107641.44 | 30 days of Dec'22
3 | Pradeep C Yadav | Mech Engineer | TXM Labour Supply | Invoice-4466 | 32354.19 | 9555 | 41909.19 | 31 days of Dec'22
4 | Dinesh Dhondiyal | QA/QC Engineer | TXM Labour Supply | Invoice-4463 | 69058.74 | 12551.8 | 81610.54 | 31 days of Dec'22
5 | Mohamed Hakkim | QA/QC Engineer | TXM Labour Supply | Invoice-4463 | 50203.52 | 8163 | 58366.52 | 31 days of Dec'22
6 | Rafael Sangueza | QA/QC Engineer | TXM Labour Supply | Invoice-4463 | 56553.5835 | 9254.9806 | 65808.5642 | 28 days of Dec'22
7 | Cesar Sta Ana | Mech Supervisor | TXM Labour Supply | Invoice-4463 | 35805.64 | 6922.7 | 42728.34 | 29 days of Dec'22
8 | Reyazuddin Anasari | Mech Supervisor | TXM Labour Supply | Invoice-4463 | 41657.97 | 9246.37 | 50904.34 | 30 days of Dec'22
9 | Santhosh | Electrical Supervisor | TXM Labour Supply | Invoice-4463 | 58790 | 8630.08 | 67420.08 | 28 days of Dec'22
10 | Kamrul Islam | Elec Supervisor | TXM Labour Supply | Invoice-4465 | 32214.48 | 7343 | 39557.48 | 31 days of Dec'22
11 | Emad Abdel Halim | Elec Supervisor | TXM Labour Supply | Invoice-4463 | 63839.74 | 9555 | 73394.74 | 31 days of Dec'22
12 | Syed Nusrath | Design Manager | TXM Labour Supply | Invoice-3473 | 56958.92 | 0 | 56958.92 | 31 days of July'22
13 | Mithun Mathew | Elec Engineer | TXM Labour Supply | Invoice-4464 | 20975.2 | 7343 | 28318.2 | 31 days of Dec'22
14 | Aslam Alam |  | TXM Labour Supply | Invoice-4467 |  | 9933 | 9933 | 31 days of Dec'22
| T&C Technology |  |  |  | 27300 | 0 | 27300
15 | T&C Engineer | Mech Engineer | T&C Technology | Invoice-TC/10657 | 21000 | 0 | 21000 | 30 days of July'22
16 | T&C Engineer | Elec Engineer | T&C Technology | Invoice-TC/10657 | 6300 | 0 | 6300 | 30 days of July'22 | 0
| Smooth International |  |  |  | 99614 | 11863.5 | 111477.5
17 | Saju Alex Antony | Piping Supervisor | Smooth International | INV/2023/01/0002 | 38306.5 | 5865 | 44171.5 | 26 days of Dec'22
18 | Ahmad Ali Abdul | Piping Supervisor | Smooth International | INV/2023/01/0002 | 36098.5 | 5278.5 | 41377 | 23 days of Dec'22
19 | Islam Hossain Miah | Duct Supervisor | Smooth International | INV/2023/01/0002 | 24795 | 720 | 25515 | 4 days of Dec'22
20 | Ali Raza Wazir Ahmad | Duct Supervisor | Smooth International | SM-KNB-DR-001 | 414 | 0 | 414 | 2 days of May'22
| Capston Engineering |  |  |  | 281331.73 | 40306.4516 | 321638.1816
21 | Udaya Kumar | Draftsman | Capston Engineering | CST/22/MEP/00250-09 | 61483.33 | 8500 | 69983.33 | 31 days of Dec'22
22 | Yassar Moidins | Draftsman | Capston Engineering | CST/22/MEP/00250-09 | 54253.76 | 8500 | 62753.76 | 31 days of Dec'22
23 | Swish Gupta | Draftsman | Capston Engineering | CST/22/MEP/00250-09 | 57534.93 | 8225.8065 | 65760.7365 | 31 days of Dec'22
24 | Saleem Khan | Draftsman | Capston Engineering | CST/22/MEP/00250-09 | 48477.44 | 8500 | 56977.44 | 31 days of Dec'22
25 | Sneha | Draftsman | Capston Engineering | CST/22/MEP/00250-09 | 47682.26 | 6580.6452 | 54262.9052 | 24 days of Dec'22
26 | Seiyadu ali | Draftsman | Capston Engineering | CST/22/MEP/00250-01,02 | 566.68 | 0 | 566.68 | 2 days of April'22
27 | Maria Cecilia | Draftsman | Capston Engineering | CST/22/MEP/00250-01,02 | 11333.33 | 0 | 11333.33 | 10 days of April'22
| PKP Engineering |  |  |  | 73191.4 | 7951.6129 | 81143.0129
28 | O.I Abdulla | MEP Draftsman | PKP Engineering | KS-MEP-DES-40457-02-22 | 9870.97 | 0 | 9870.97 | 5 days of July'22
29 | S.E.A. Mohammad Sahib | MEP Draftsman | PKP Engineering | KS-MEP-DES-40457-02-22 | 24129.03 | 0 | 24129.03 | 26 days of Aug'22
30 | Parthipan | MEP Draftsman | PKP Engineering | KS-MEP-DES-40457-07-23 | 39191.4 | 7951.6129 | 47143.0129 | 29 days of Dec'22
| RamTech |  |  |  | 144819.92 | 24951.6129 | 169771.5329
31 | Girish Chandra | Mech Draftsman | RamTech | RSS-2022-12-8954 | 47600.01 | 7951.6129 | 55551.6229 | 29 days of Dec'22
32 | Mandeep Kumar | Elec Draftsman | RamTech | RSS-2022-11-8892 | 47919.91 | 8500 | 56419.91 | 31 days of Dec'22
33 | Syed Muzaffaruddin | Mech Draftsman | RamTech | RSS-2022-11-8892 | 49300 | 8500 | 57800 | 31 days of Dec'22
| Pace Arabia |  |  |  | 291641.42 | 59774.1935 | 351415.6135
34 | Prabhakaran Murugan | Elec Foreman | Pace Arabia | IPA-06 | 33908.6 | 8500 | 42408.6 | 31 days of Dec'22
35 | Muhammed Siddique | Elec Foreman | Pace Arabia | IPA-06 | 41677.43 | 8500 | 50177.43 | 31 days of Dec'22
36 | Sathish Guna | Elec Foreman | Pace Arabia | IPA-06 | 35617.74 | 7677.4194 | 43295.1594 | 28 days of Dec'22
37 | Arun Sadasivam | Elec Foreman | Pace Arabia | IPA-06 | 20564.52 | 6854.8387 | 27419.3587 | 25 days of Dec'22
38 | Bhutto Ansari | Plumbing Supervisor | Pace Arabia | IPA-06 | 42225.81 | 7951.6129 | 50177.4229 | 29 days of Dec'22
39 | Dinuhass | Plumbing Supervisor | Pace Arabia | IPA-06 | 24339.24 | 7403.2258 | 31742.4658 | 27 days of Dec'22
40 | Amjad Ali | Plumbing Supervisor | Pace Arabia | IPA-06 | 27693.55 | 8500 | 36193.55 | 31 days of Dec'22
41 | Subramaniam Jaishankar | Elec Foreman | Pace Arabia | IPA-03 | 6233.33 | 0 | 6233.33 | 22 days of Sep'22
42 | Siva kumar | Elec Foreman | Pace Arabia | IPA-06 | 14760.76 | 0 | 14760.76 | 23 days of Nov'22
43 | Mahesh kumar | Plumbing Supervisor | Pace Arabia | IPA-06 | 21377.96 | 3290.3226 | 24668.2826 | 16 days of Dec'22
44 | Ali Sher | HVAC Supervisor | Pace Arabia | IPA-06 | 23242.48 | 1096.7742 | 24339.2542 | 4 days of Dec'22
| Total Amount |  |  |  | 7310218.4055 | 1086259.7716 | 8396478.1772
|  |  |  | WA-M037 & 047 Sutton HVAC TAB works | 164400 | 27400 | 191800
| Staff Total Amount |  |  |  | 7474618.4055 | 1113659.7716 | 8588278.1772

## B. Prelims
IPC-11 | PRELIMS AND GENERAL ITEMS |  |  |  | PRELIMINARIES
S.Nr | Description | Previous IPC Amount (AED) | Current Month Amount (AED) | Cumulative Amount (AED) | Remarks
1 | Site Office Establish and Running Cost | 232742.31 | 19556.05 | 252298.36
| Site Office Consumables | 39539.15 | 3173.25 | 42712.4 | Drinking Water, Tea Coffee powders, milk, Disposable cups, Hand wash, Washing liquid, Carton box, Fire Extingisher, Micro wave, Fridge
| Office & Site Furniture - Including A/C | 2625 | 0 | 2625
| Floor Protection sheet | 360 | 0 | 360
| Initial Office Set-up Stationary - Mr. Yatheesh | 10000 | 0 | 10000 | PO-0001 dt 19.04.22
| Printing and Stationery items | 57824.92 | 12852.25 | 70677.17 | Office Stationeries and Photocopies
| Refreshments (snacks, tea, coffee etc.) | 5797.59 | 0 | 5797.59 | Aqualyte Solutions
| Computers & Accessories | 30790.57 | 2627.09 | 33417.66 | Mouse, Cat6 Cable, Laptop & Desktop - Rental
| Telecommunication Services | 8197.46 | 0 | 8197.46 | Wi-fi adapter, Mobile Handset
| Mobile Phones | 8111.62 | 903.46 | 9015.08 | Samsung Mobile phones, post paid
| Business cards | 540 | 0 | 540 | 600 Business cards
| Project IT Infrastructure & Softwares | 68956 | 0 | 68956 | 10Nr Autocad Software, Windows OS License
2 | Site Transportation | 392291.95 | 33290.79 | 425582.74
| Fuels | 172207.51 | 0 | 172207.51 | Fuel charges of Bus-4, 3 Ton-1, 13 seat-1, Yaris-1
| I-Passenger motor vehicles | 196391.76 | 29618 | 226009.76 | Rental charges of Bus-5, 3 Ton-1, 13 seat-1, Yaris-1
| ENOC VIP fuel card | 2201.85 | 0 | 2201.85 | Fuel using ENOC VIP fuel card
| E-Passenger motor vehicles | 21490.83 | 3672.79 | 25163.62 | Salik cost
3 | Plant & Equipment | 80876.85 | 4569.48 | 85446.33
| Electrical equipment, components and supplies | 11764.45 | 0 | 11764.45 | Task lighting
| I-lifting equipment and accessories | 41219.65 | 4569.48 | 45789.13 | Peco lift 3.5m, 8m - Rental charges
| Stillage with side cover (Mesh type) | 8385 | 0 | 8385 | Stillage - Rental Charges
| Pedestrian Barrier steel and tripod | 17000 | 0 | 17000 | Pedestrian Barrier steel (2.5mx1.2m) - Rent
| EHD Gas Monitor | 2507.75 | 0 | 2507.75 | Gas Monitor, Plant works
4 | Site Power Consumption | 0 | 0 | 0
5 | Water Charges | 0 | 0 | 0
6 | Sewage Disposal | 0 | 0 | 0
7 | Labour Committed Costs | 88491.27 | 2904.61 | 91395.88
| Safety Clothing and Equipment / PPE | 32844.65 | 0 | 32844.65 | Safety Vest & Helmet
| White Clothes | 4889.35 | 250 | 5139.35 | White and Red Clothes
| Health and safety - material items | 48447.27 | 1464.61 | 49911.88 | Blue dress, Hand gloves, Safety shoes and goggles
| Face Mask | 2310 | 1190 | 3500 | Face Mask
8 | Access Scaffolding, Safety, Tools and Equipments | 21175.09 | 3945.5 | 25120.59
| Safety tools | 11975 | 3945.5 | 15920.5 | Welding gloves, Fire blanket, Ear plug, Rubber gloves, First aid kit, Repairs etc.,
| Fiber Glass Type A Ladder - 8 Step and 12 Step | 9200.09 | 0 | 9200.09 | Ascend Inv-1119, Hopup Stand Inv-CSI-CRINV-2022-721
9 | Insurances and Certificates | 0 | 0 | 0
10 | Others | 75363.81 | 3575.88 | 78939.69
| MEP Approved Drawing Printing Works - PV Jophy | 23700 | 0 | 23700 | PO-0002 dt 21.04.22
| Petty Cash purchase of fittings and accessories | 42671.91 | 0 | 42671.91 | Petty Cash purchase
| Bank LC Charges for Project Supplies Advance Payment | 5931.9 | 3575.88 | 9507.78 | Bank LC Charges
| RTA fines "for stopping on the road for no reason" in Plot-18 | 3060 | 0 | 3060 | RTA Fines for 3 bus
11 | Employer & Engineer Facilities | 0 | 0 | 0
| Total Amount | 890941.28 | 67842.31 | 958783.59
| WA-M012, 025, 046, 058, 069, 089, 092, 097, 117, 160, 188, 204, 249, 391, 420 | 463197 | 65357.35 | 528554.35 | Scaffolding, Power tools, Consumables, Walkie Talkie and Safety full body harness cost from WA-M
| Prelims Total Amount | 1354138.28 | 133199.66 | 1487337.94

## C. Labor
IPC-11 | MEP LABOUR COST | [8 empty] | DIRECT WORKS
S.Nr | Description | Company | Claim/ Invoice Ref. | Man-hours |  |  | Amount AED |  |  | Remarks
|  |  |  | Previous | Current | Cumulative | Previous | Current | Cumulative
| KMEP | [5 empty] | 4840198.53 | 845418.83 | 5685617.36
1 | Unskilled labour | KMEP | IPA Attendance Report | 40800.5 | 6821 | 47621.5 | 433658.96 | 67101.68 | 500760.64
2 | Skilled labour | KMEP | IPA Attendance Report | 310741.5 | 55794 | 366535.5 | 3823344.31 | 641421.9 | 4464766.21
3 | Operator Costs | KMEP | IPA Attendance Report | 17098.5 | 2917 | 20015.5 | 219175.12 | 36559.86 | 255734.98
4 | Charge hand labour | KMEP | IPA Attendance Report | 27179.5 | 8155.5 | 35335 | 364020.14 | 100335.39 | 464355.53
| Smooth International | [5 empty] | 3805078.5 | 491477.5 | 4296556
5 | Electrical Charge hand | Smooth International | INV/2023/01/0001 | 17325.5 | 2377.5 | 19703 | 294533.5 | 40417.5 | 334951 | 17 / HR
6 | Electrician | Smooth International | INV/2023/01/0001 | 143696 | 16076.5 | 159772.5 | 2011744 | 225071 | 2236815 | 14 / HR
7 | Plumbing Charge hand | Smooth International | INV/2023/01/0001 | 2643 | 446.5 | 3089.5 | 44931 | 7590.5 | 52521.5 | 17 / HR
8 | Plumber | Smooth International | INV/2023/01/0001 | 28615 | 4360 | 32975 | 400610 | 61040 | 461650 | 14 / HR
9 | Pipe fitter | Smooth International | INV/2023/01/0001 | 22084.5 | 4010.5 | 26095 | 353352 | 64168 | 417520 | 16 / HR
10 | Duct foreman | Smooth International | SM-KNB-DR-003 & 004 | 234 | 0 | 234 | 4212 | 0 | 4212 | 18 / HR
11 | Ducting Charge hand | Smooth International | INV/2023/01/0001 | 4940 | 662.5 | 5602.5 | 83980 | 11262.5 | 95242.5 | 17 / HR
12 | Ductman | Smooth International | INV/2023/01/0001 | 35520 | 4863 | 40383 | 497280 | 68082 | 565362 | 14 / HR
13 | Insulator | Smooth International | INV/2023/01/0001 | 8174 | 989 | 9163 | 114436 | 13846 | 128282 | 14 / HR
| Madinat Jalfar | [5 empty] | 1634733 | 320249.25 | 1954982.25
14 | Electrical Charge hand | Madinat Jalfar | MJ/KCE_DR-007 | 6750.5 | 1430.5 | 8181 | 101257.5 | 21457.5 | 122715 | 15 / HR
15 | Electrician | Madinat Jalfar | MJ/KCE_DR-007 | 85648.5 | 16770 | 102418.5 | 1156254.75 | 226395 | 1382649.75 | 13.5 / HR
16 | Plumbing Charge hand | Madinat Jalfar | MJ/KCE_DR-007 | 538.5 | 0 | 538.5 | 8077.5 | 0 | 8077.5 | 15 / HR
17 | Plumber | Madinat Jalfar | MJ/KCE_DR-007 | 15047 | 3325.5 | 18372.5 | 203134.5 | 44894.25 | 248028.75 | 13.5 / HR
18 | Ducting Charge hand | Madinat Jalfar | MJ/KCE_DR-007 | 1327 | 231.5 | 1558.5 | 19905 | 3472.5 | 23377.5 | 15 / HR
19 | Ductman | Madinat Jalfar | MJ/KCE_DR-007 | 10822.5 | 1780 | 12602.5 | 146103.75 | 24030 | 170133.75 | 13.5 / HR
| Golden Effect | [5 empty] | 117768 | 0 | 117768
20 | Plumber | Golden Effect | Invoice No.228 | 8412 | 0 | 8412 | 117768 | 0 | 117768 | 14 / HR
| Main Star | [5 empty] | 528890.5 | 98125 | 627015.5
21 | Electrical Charge hand | Main Star | MST/KHB/2548-2022 | 3786.5 | 632 | 4418.5 | 64370.5 | 10744 | 75114.5 | 17 / HR
22 | Electrician | Main Star | MST/KHB/2548-2022 | 33180 | 6241.5 | 39421.5 | 464520 | 87381 | 551901 | 14 / HR
| Pace Arabia | [5 empty] | 1922644.375 | 513183.25 | 2435827.625
23 | Electrical Charge hand | Pace Arabia | DH-2022-KCE-IPA-06 | 2500.5 | 674.5 | 3175 | 42508.5 | 11466.5 | 53975 | 17 / HR
24 | Electrician | Pace Arabia | DH-2022-KCE-IPA-06 | 51964 | 17453.5 | 69417.5 | 805442 | 270529.25 | 1075971.25 | 15.5 / HR
25 | Electrician OT | Pace Arabia | DH-2022-KCE-IPA-06 |  | 206 | 206 |  | 3991.25 | 3991.25 | 19.375 / HR
26 | HVAC Charge hand | Pace Arabia | DH-2022-KCE-IPA-06 | 1592.5 | 228 | 1820.5 | 27072.5 | 3876 | 30948.5 | 17 / HR
27 | Ductman/Insulator | Pace Arabia | DH-2022-KCE-IPA-06 | 13612 | 2455.5 | 16067.5 | 210986 | 38060.25 | 249046.25 | 15.5 / HR
28 | Plumbing Charge hand | Pace Arabia | DH-2022-KCE-IPA-06 | 4115 | 874 | 4989 | 69955 | 14858 | 84813 | 17 / HR
29 | Plumbing Charge hand OT | Pace Arabia | DH-2022-KCE-IPA-06 |  | 18 | 18 |  | 382.5 | 382.5 | 21.25 / HR
30 | Plumber | Pace Arabia | DH-2022-KCE-IPA-06 | 40724 | 8578.5 | 49302.5 | 631222 | 132966.75 | 764188.75 | 15.5 / HR
31 | Pipe fitter | Pace Arabia | DH-2022-KCE-IPA-06 | 8518 | 1878 | 10396 | 132029 | 29109 | 161138 | 15.5 / HR
32 | Plumber & Pipe Fitter OT | Pace Arabia | DH-2022-KCE-IPA-06 | 177 | 410 | 587 | 3429.375 | 7943.75 | 11373.125 | 19.375 / HR
0
| Amigo Electro Mechanical | [5 empty] | 4284 | 0 | 4284
33 | Electrician | Amigo | HG/AM/270922 | 306 | 0 | 306 | 4284 | 0 | 4284 | 14 / HR
| Total Amount | [5 empty] | 12853596.905 | 2268453.83 | 15122050.735
[6 empty] | Direct Labour | 4840198.53 | 845418.83 | 5685617.36 | 37.6%
[6 empty] | Labour Supply | 8013398.375 | 1423035 | 9436433.375 | 62.4%

## D. WA-M
IPC-11 | WORK APPROVALS (MEP) | [16 empty] | DIRECT WORKS
[7 empty] | DATE | [5 empty] | PROGRESS % |  |  | AMOUNT (AED)
REF NO. | REV | COST CATEGORY | TOWER | FLOOR/ AREA | DESCRIPTION OF WORKS/GOODS | APPROVED SUBCONTRACTOR/SUPPLIER | KCE SUBMITTED | AGREED AND ISSUED | BUDGET/ SUBMITTED AMOUNT | APPROVED AMOUNT | HISTORICAL COST AMOUNT | PREVIOUS | CURRENT | CUMULAT | PREVIOUS | CURRENT | CUMULAT | REMARKS | RATE BACK-UP DONE
WA-M001 | 1 | HVAC | General | General | Supply, Install, T&C of Pressurization Unit | Metallic Building Materials | 2022-05-25 | 2022-05-25 |  | 49875.12 | 49875.12 | 100% | 0% | 100% | 49875.12 | 0 | 49875.12 |  | RBD
WA-M002 | - | PL & DR | General | General | Supply, T&C of Sump Pumps | Aquagas | 2022-05-17 | 2022-05-20 |  | 47085.5 | 47085.5 | 100% | 0% | 100% | 47085.5 | 0 | 47085.5 |  | RBD
WA-M003 | 1 | PL & DR | General | General | Booster & Circulation Pumps T&C | Aquagas | 2022-05-24 | 2022-05-24 |  | 76400 | 76400 | 0% | 0% | 0% | 0 | 0 | 0
WA-M004 | - | PL & DR | General | General | Supply, Install, T&C of GRP Water Tanks | Translink | 2022-05-17 | 2022-05-23 |  | 190000 | 190000 | 91.39% | 0% | 91.39% | 173636.36 | 0 | 173636.36
WA-M005 | - | ELEC | General | Various | Light Fixtures | Projects & Supplies |  |  |  | 0 | [5 empty] | 0 |  | Rejected
WA-M006 | 1 | ELEC | Hot & Res | Various | Supply of Light Fixtures | Projects & Supplies | 2022-06-21 | 2022-06-23 |  | 2920312.44 |  | 32.55% | 8.537% | 41.08% | 950458.46 | 249310.64 | 1199769.1 | PS - Light fittings | Refer WA-M254 for further update | 1,031,744.7 (35% of AED 2,947,842)
WA-M007 | - | ELEC | General | General | Supply, Install, T&C of Switchgear | Arabian Gulf Switchgear | 2022-05-17 | 2022-05-23 |  | 81254.44 | 81254.44 | 100% | 0% | 100% | 81254.44 | 0 | 81254.44
WA-M008 | - | ELEC | General | L8 | Supply, Install, T&C of Dali System @ Level 8 | Ikonhouse | 2022-05-18 | 2022-05-23 |  | 10965 |  | 80% | 0% | 80% | 8772 | 0 | 8772 | PS - Light fittings
WA-M008 | - | ELEC | Res | L8 | Supply of Light Fixtures @ Level 8 | Gulf Line | 2022-05-18 | 2022-05-23 |  | 4094 | 4094 | 100% | 0% | 100% | 4094 | 0 | 4094 | PS - Light fittings | RBD
WA-M008 |  | ELEC | Res | L8 | Supply of Light Fixtures @ Level 8 | Extra Ordinary | 2022-05-18 | 2022-05-23 |  | 2750 |  | 100% | 0% | 100% | 2750 | 0 | 2750 | PS - Light fittings | RBD
WA-M009 | - | ELEC | General | General | Modification, T&C of Busbar & Tap-Offs | PBB Group FZE | 2022-05-20 | 2022-05-20 |  | 133043.42 | 9068.43 | 100% | 0% | 100% | 133043.42 | 0 | 133043.42 | WA-M amount has been updated based on Invoices as per KMEP email on 21 Nov 2022
WA-M010 | 1 | PL & DR | General | Various | Supply of Plumbing Valves | Fluid Control Trading | 2022-05-30 | 2022-05-30 |  | 8047.2 |  | 100% | 0% | 100% | 8047.2 | 0 | 8047.2 | WA-M amount has been updated based on Invoices as per KMEP email on 21 Nov 2022
WA-M011 | - | HVAC | General | Various | CHW Flushing + Final Chemicals + Circ Pump | Culligan International Emirates | 2022-05-25 | 2022-05-25 |  | 29500 |  | 100% | 0% | 100% | 29500 | 0 | 29500 |  | RBD
WA-M012 | - | GENERAL | General | Various | Supply of ALU Scaffolding 1.5m & 3.5m | Crescent Scaffolding Industries | 2022-05-23 | 2022-05-24 |  | 139560 |  | 92.77% | 0% | 92.77% | 129470 | 0 | 129470 | Prelims - Scaffolding
WA-M013 | - | ELEC | Hot & Res | Various | Supply of Single Core Wires | Clevland Cable Trading FZCO | 2022-05-25 | 2022-05-26 |  | 113670 |  | 100% | 0% | 100% | 113670 | 0 | 113670 |  | RBD
WA-M014 | - | ELEC | Hot & Res | Various | Supply, T&C of Emergency System | ODS Global | 2022-05-31 | 2022-06-02 |  | 148656 | 46443.81 | 31.24% | 0% | 31.24% | 46443.81 | 0 | 46443.81
WA-M015 | 1 | HVAC | Hot & Res | Various | Supply of HVAC Duct works | Seagull HVAC Industry | 2022-05-27 | 2022-05-30 |  | 211879.46 | 211879.46 | 100% | 0% | 100% | 211879.46 | 0 | 211879.46 |  | RBD
WA-M016 | - | ELEC | Hot & Res | Various | Supply of Control Cable for Type XL3 Lights | Huda Lighting | 2022-05-30 | 2022-05-30 |  | 7800 |  | 95% | 0% | 95% | 7410 | 0 | 7410 | PS - Light fittings
WA-M017 | - | ELEC | General | Various | Switchgear Modifications | Arabian Gulf Switchgear | 2022-05-27 | 2022-05-30 |  | 30577.31 |  | 100% | 0% | 100% | 30577.31 | 0 | 30577.31
WA-M018 | - | ELEC | Hot & Res | Various | Supply of Cables and Wires | Clevland Cable Trading FZCO | 2022-05-27 | 2022-05-30 |  | 72392.92 |  | 96.63% | 0% | 96.63% | 69952.07 | 0 | 69952.07
WA-M019 | - | GENERAL | Hot & Res | Various | Stress Analysis | Kinetics Middle East LLC | 2022-05-27 | 2022-05-30 |  | 14850 | 14850 | 100% | 0% | 100% | 14850 | 0 | 14850
WA-M020 | - | ELEC | Hot & Res | Various | Supply of Fire rated Cables | Ali Haji Abdulla Awazi Gargash | 2022-05-27 | 2022-05-30 |  | 43830 |  | 100% | 0% | 100% | 43830 | 0 | 43830 |  | RBD
WA-M021 | - | GENERAL | General | CHWP | Supply and replacement of Mechanical Seal | Aquagas | 2022-05-30 | 2022-05-30 |  | 6000 |  | 100% | 0% | 100% | 6000 | 0 | 6000 |  | RBD
WA-M022 | - | GENERAL | Hot & Res | Various | Supply of Consumables & other urgent materials | Various Suppliers | 2022-06-01 | 2022-06-02 |  | 247881.01 |  | 99.2% | 0% | 99.2% | 245888.41 | 0 | 245888.41
WA-M023 | - | HVAC | Hot & Res | Various | Supply of GI & Fire Rated Ducts | Seagull HVAC Industry | 2022-06-01 | 2022-06-02 |  | 363540 |  | 79.12% | 3.813% | 82.93% | 287630.86 | 13860.86 | 301491.72
WA-M024 | - | ELEC | Hot | Various | Supply of Wiring Accessories | SMKA Electric | 2022-06-02 | 2022-06-02 |  | 41695.42 |  | 89.59% | 0% | 89.59% | 37356.72 | 0 | 37356.72
WA-M025 | - | GENERAL | General | Various | Supply of ALU Scaffolding 1.5m & 3.5m | Crescent Scaffolding Industries | 2022-06-06 | 2022-06-07 |  | 17610 |  | 87.9% | 0% | 87.9% | 15480 | 0 | 15480 | Prelims - Scaffolding
WA-M026 | - | PL & DR | General | General | Supply of Sump Pumps | Aquagas | 2022-06-06 | 2022-06-07 |  | 144700 |  | 100% | 0% | 100% | 144700 | 0 | 144700 |  | RBD
WA-M027 | - | ELEC | Hot | Various | Supply of Royal & Presidential Suites Light Fittings | HS Energy Solutions FZCO | 2022-06-16 | 2022-06-17 |  | 120000 |  | 0% | 94.09% | 94.09% | 0 | 112903.84 | 112903.84 | PS - Light fittings |  | 62,500 (52.0833% of 120,000)
WA-M028 | - | ELEC | General | Various | Supply and Installation of remaining Generator works | Sun Star Electro-Mechanical | 2022-06-06 | 2022-06-07 |  | 612870.48 | 98886.48 | 53.67% | 21.96% | 75.63% | 328902.48 | 134616 | 463518.48 | KMEP Domestic SC paid based on their progress completion |  | 278,780.88 (35% of AED 513,984)
WA-M029 | - | FP | General | Various | Supply of Temperature Transmitters | Abdulla Bin Hamid Trading | 2022-06-07 | 2022-06-10 |  | 11600 |  | 100% | 0% | 100% | 11600 | 0 | 11600 |  | RBD
WA-M030 | - | ELEC | General | General | Installation of Busbar | Al Qubtan Al Mutamayez Tech. Cont. | 2022-06-09 | 2022-06-10 |  | 41081.25 | 32435.54 | 100% | 0% | 100% | 41081.25 | 0 | 41081.25 |  | RBD
WA-M031 | - | PL & DR | General | General | Supply of Water supply pipe insulation (KIMMCO) | Leminar Air Conditioning | 2022-06-15 | 2022-06-15 |  | 38950.91 |  | 100% | 0% | 100% | 38950.77 | 0 | 38950.77 |  | RBD
WA-M032 | - | ELEC | General | Various | SMDB, DB Modification works | Arabian Gulf Switchgear | 2022-06-13 | 2022-06-14 |  | 24127 |  | 69.1% | 0% | 69.1% | 16672.17 | 0 | 16672.17
WA-M033 | 1 | HVAC | General | General | Supply (rental) of bagfilters for CHW flushing | Culligan International Emirates | 2022-06-17 | 2022-06-21 |  | 28773.4 |  | 0% | 0% | 0% |  | 0
WA-M034 | - | HVAC | General | Various | Ecology units - Dismantling & Assembly + 6nr CP | Trosten Industries | 2022-06-17 | 2022-06-21 |  | 90980 |  | 0% | 0% | 0% |  | 0
WA-M035 | - | HVAC | General | Various | Supply, Install, T&C of BTU & Smart valve system for Empower | ISTA Middle East FZE | 2022-06-13 | 2022-06-13 |  | 350000 |  | 70% | 0% | 70% | 245000 | 0 | 245000 | KMEP Domestic SC paid based on their progress completion |  | 122,500 (35% of AED 350,000)
WA-M036 | - | PL & DR | Hot & Res | General | Supply of Acoustic lagging for drainage pipes | Kinetics Middle East LLC | 2022-06-15 | 2022-06-15 |  | 21250 |  | 100% | 0% | 100% | 21249 | 0 | 21249 |  | RBD
WA-M037 | - | HVAC | Hot & Res | Various | Supply of Commissioning Manager and Engineer | Sutton | 2022-08-01 | 2022-08-12 |  | 685000 |  | 24% | 4% | 28% | 164400 | 27400 | 191800 | Staff Cost | 14% | 14%
WA-M038 | - | PL & DR | General | Water tank | Supply of Float control valve for water tank | Hydro point | 2022-06-16 | 2022-06-17 |  | 15000 |  | 100% | 0% | 100% | 15000 | 0 | 15000 |  | RBD
WA-M039 | - | HVAC | Bas | B1 UPS room | Supply of DX unit for UPS room | Daikin | 2022-06-16 | 2022-06-17 |  | 11000 |  | 0% | 0% | 0% |  | 0
WA-M040 | - | HVAC | Hot, Res & Pod | Various | Supply of Bronze GV and FODRV manual balancing valves | Maunsell | 2022-07-01 | 2022-07-12 |  | 18061.18 |  | 100% | 0% | 100% | 18061.18 | 0 | 18061.18 |  | RBD
WA-M041 | - | HVAC | Hot & Res | Various | Supply of MI fittings | Bisan building | 2022-06-21 | 2022-06-22 |  | 16577.99 |  | 100% | 0% | 100% | 16577.94 | 0 | 16577.94 |  | RBD
WA-M042 | - | [14 empty] | 0
WA-M043 | - | HVAC | General | All Fan & AHU | Supply of Flexible duct | Focus AC | 2022-06-21 | 2022-06-22 |  | 5105 |  | 100% | 0% | 100% | 5105 | 0 | 5105 |  | RBD
WA-M044 | - | HVAC | General | ETS room | Supply of CHW Flexible connectors | Kinetics Middle East LLC | 2022-06-21 | 2022-06-22 |  | 5809.44 |  | 100% | 0% | 100% | 5809.44 | 0 | 5809.44 |  | RBD
WA-M045 | - | HVAC | Hot | B1, L1 Plant room | Supply of flexible duct connector | Focus AC | 2022-06-24 | 2022-06-24 |  | 4400 |  | 100% | 0% | 100% | 4400 | 0 | 4400 |  | RBD
WA-M046 | - | GENERAL | General | Various | Supply of ALU Scaffolding 0.8m & 1.8m | Crescent Scaffolding Industries | 2022-06-22 | 2022-06-22 |  | 14750 |  | 0% | 0% | 0% |  | 0 |  | Prelims - Scaffolding
WA-M047 | - | HVAC | Hot & Res | Various | TAB of HVAC Commissioning Works | Sutton | 2022-08-01 | 2022-08-12 |  | 352386 |  | 0% | 0% | 0% | 0 | 0 | 0 | Staff Cost
WA-M048 | - | HVAC | General | Plant room | Supply of Pressure gauge, thermometer and accessories | Technova | 2022-06-24 | 2022-06-24 |  | 31764.5 |  | 100% | 0% | 100% | 31764.5 | 0 | 31764.5 |  | RBD
WA-M049 | - | HVAC | Res | L7-L9 BTU Meter room | Installation of BTU meters, snag works and back flushing | Rukn Alkanz | 2022-06-24 | 2022-06-24 |  | 10000 |  | 71.35% | 0% | 71.35% | 7135 | 0 | 7135
WA-M050 | - | ELEC | Hot & Res | Various | Suppy, T&C of lighting control system | Gama Engineering | 2022-06-24 | 2022-06-30 |  | 108000 |  | 86.8% | 8.203% | 95% | 93741 | 8859 | 102600 | PS - Light fittings
WA-M051 | - | HVAC | Hot, Res & Pod | Various | Supply of FD and VCD | Prime A/C | 2022-06-24 | 2022-06-30 |  | 21292.65 | 21292.65 | 100% | 0% | 100% | 21292.65 | 0 | 21292.65 |  | RBD
WA-M052 | - | HVAC | Hot | L29 | Chilled water pipe freezing work | Unique Wellube | 2022-06-27 | 2022-06-30 |  | 7600 |  | 0% | 0% | 0% |  | 0
WA-M053 | - | HVAC | Hot, Res & Pod | Various | Supply of duct acoustic insulation | Kepco | 2022-06-28 | 2022-06-30 |  | 5497.8 |  | 100% | 0% | 100% | 5497.8 | 0 | 5497.8 |  | RBD
WA-M054 | - | HVAC | Hot & Res | Various | Supply of duct XLPE insulation | Ramesh hira | 2022-06-28 | 2022-06-30 |  | 21715.2 |  | 100% | 0% | 100% | 21715.2 | 0 | 21715.2 |  | RBD
WA-M055 | - | ELV works | General | General | Supply of media power panel | Hospitality Solutions | 2022-06-28 | 2022-06-30 |  | 4064 | 4064 | 100% | 0% | 100% | 4064 | 0 | 4064 |  | RBD
WA-M056 | - | HVAC | Hot & Res | Various | Supply of ATS 2 way control valve | ATS Advanced Technical Solutions | 2022-06-28 | 2022-06-30 |  | 5110 |  | 100% | 0% | 100% | 5110 | 0 | 5110 |  | RBD
WA-M057 | - | [14 empty] | 0
WA-M058 | - | GENERAL | Hot | Various | Supply of ALU Scaffolding 0.8m & 1.2m, 0.8m & 1.8m | Crescent Scaffolding Industries | 2022-06-30 | 2022-06-30 |  | 47890 |  | 90.21% | 0% | 90.21% | 43200 | 0 | 43200 | Prelims - Scaffolding
WA-M059 | - | [14 empty] | 0
WA-M060 | - | HVAC | Hot | GF, L2,3,5 | Supply of Rockwool blanket for KED | Abdulla Al Zaabi | 2022-06-30 | 2022-06-30 |  | 5705.28 |  | 100% | 0% | 100% | 5705.28 | 0 | 5705.28 |  | RBD
WA-M061 | - | PL & DR | Bas | B1 Entrance | Supply of ductile iron channel grating | Green fields | 2022-06-30 | 2022-06-30 |  | 4300 |  | 100% | 0% | 100% | 4300 | 0 | 4300 |  | RBD
WA-M062 | - | GENERAL | General | Various | Supply of channels and angles | Al Adil | 2022-06-30 | 2022-06-30 |  | 18725 |  | 100% | 0% | 100% | 18725 | 0 | 18725 |  | RBD
WA-M063 | - | PL & DR | Pod & Landscape | Podium & Landscape | UPVC pipes and fittings | Polyfab Plastic | 2022-07-15 | 2022-07-25 |  | 47396.2 |  | 83.36% | 0% | 83.36% | 39507.48 | 0 | 39507.48
WA-M064 | - | PL & DR | Hot & Res | HL28 & RL31 | Supply of Float control valve for water tank | Hydro point | 2022-10-04 | 2022-10-24 |  | 15000 |  | 100% | 0% | 100% | 15000 | 0 | 15000
WA-M065 | - | GENERAL | Hot & Res | Various | Supply of HDG Angle | Avadh Metal | 2022-07-01 | 2022-07-12 |  | 9400 |  | 100% | 0% | 100% | 9400 | 0 | 9400 |  | RBD
WA-M066 | - | HVAC | Hot & Pod | CHW line | Supply of MS Pipes | MM Steel | 2022-07-01 | 2022-07-12 |  | 10538 |  | 100% | 0% | 100% | 10538 | 0 | 10538 |  | RBD
WA-M067 | - | GENERAL | Hot & Res | Various | MEP 1st and 2nd fix units | Various Suppliers | 2022-06-30 | 2022-07-28 |  | 144221.67 |  | 95.96% | 0% | 95.96% | 138388.13 | 0 | 138388.13
WA-M068 | 1 | PL & DR | Hot & Res | Both Plant room areas | Supply of PPR Pipes and Fittings | Al Muhaideb | 2022-07-29 | 2022-08-08 |  | 30091.8 |  | 95.02% | 0% | 95.02% | 28594.26 | 0 | 28594.26
WA-M069 | - | ELEC | Hot & Res | Various | Supply of Power tools | Various Suppliers | 2022-07-07 | 2022-07-07 |  | 133789.83 |  | 100% | 0% | 100% | 133789.83 | 0 | 133789.83 | Prelims - Power tools | RBD | WA-M069 Claimed under July & Aug IPA - Stock issues.
WA-M070 | - | ELEC | Hot & Res | HL17-18, 28-29 & RL23 | Supply of Wires and Cables | Clevland Cable Trading FZCO | 2022-07-12 | 2022-07-25 |  | 272738 |  | 98.89% | 0% | 98.89% | 269715.81 | 0 | 269715.81
WA-M071 | - | ELEC | Hot | Staircase no.6-8 | Supply of GI conduits and accessories | Various Suppliers | 2022-07-12 | 2022-07-25 |  | 40591.91 |  | 98.48% | 0% | 98.48% | 39975.02 | 0 | 39975.02
WA-M072 | - | ELEC | Hot & Res | HL17-18, 28 & RL23 | Cable trunking, tray and accessories | Power Solution | 2022-07-12 | 2022-07-25 |  | 28235.9 |  | 100% | 0% | 100% | 28235.9 | 0 | 28235.9 |  | RBD
WA-M073 | - | PL & DR | Pod | L1-3 & 5 | Supply of Valves and Strainer | Technical Parts | 2022-07-12 | 2022-07-25 |  | 10726.2 |  | 93.38% | 0% | 93.38% | 10015.8 | 0 | 10015.8
WA-M074 | - | ELEC | Hot | FOH Guest Rooms | Supply of Driver for Light Fixtures | HS Energy Solutions FZCO | 2022-08-18 | 2022-08-26 |  | 41165 |  | 100% | 0% | 100% | 41165 | 0 | 41165 | PS - Light fittings
WA-M075 | 1 | ELEC | Hot | GR & Corridor | Wiring Accessories | SMKA Electric | 2022-08-25 | 2022-09-21 |  | 98583.34 |  | 57.16% | 8.391% | 65.55% | 56349.3 | 8272 | 64621.3
WA-M076 | 2 | ELEC | Hot & Res | Hot & Res Plant room | Supply of TPN isolator | Sentor Electrical | 2022-10-18 | 2022-10-26 |  | 13064.15 |  | 80.32% | 0% | 80.32% | 10493.03 | 0 | 10493.03
WA-M077 | - | HVAC | Hot & Res | Various | Chilled water flushing works | Culligan International Emirates | 2022-07-13 | 2022-07-28 |  | 107500 |  | 78.87% | 0% | 78.87% | 84787.5 | 0 | 84787.5 | Apr'22 Material Purchase + Oct'22 Progress
WA-M078 | - | PL & DR | Hot & B1 | BoH | Supply of Sanitary wares and accessories | Sanipex | 2022-07-18 | 2022-07-28 | [9 empty] | This amount AED 39,744.99 was Superded by WA-M155
WA-M079 | - | HVAC | Hot & Res | Various | Stress analysis and support design for CHW risers | Kinetics Middle East LLC | 2022-07-19 | 2022-07-26 |  | 39450 |  | 100% | 0% | 100% | 39450 | 0 | 39450 |  | RBD
WA-M080 | - | PL & DR | Hot | L28 | GRP Tank Alteration works | Translink | 2022-07-19 | 2022-08-03 |  | 18000 |  | 100% | 0% | 100% | 18000 | 0 | 18000
WA-M081 | - | HVAC | Hot & Res | L30 & 31 | Supply of FCU valve package with actuator & insulation | ATS Advanced Technical Solutions | 2022-07-19 | 2022-08-08 |  | 10000 |  | 47% | 47% | 94% | 4700 | 4700 | 9400
WA-M082 | - | [14 empty] | 0
WA-M083 | - | GENERAL | Hot & Res | Various | Supply of Aluminium Tape | Focus AC | 2022-07-19 | 2022-07-28 |  | 10200 |  | 100% | 0% | 100% | 10200 | 0 | 10200 |  | RBD
WA-M084 | - | PL & DR | Hot | L29 Landscape | Supply of FD, PD and PLD | Hydro point | 2022-07-20 | 2022-07-28 |  | 5920 |  | 98.65% | 0% | 98.65% | 5840 | 0 | 5840
WA-M085 | - | HVAC | Hot & Res | Various | ID Stickers for Ducts | Silver line | 2022-07-20 | 2022-07-28 |  | 1152.5 |  | 100% | 0% | 100% | 1152.5 | 0 | 1152.5 |  | RBD
WA-M086 | - | ELEC | Hot | Guest Room | Earthing Backbox | Hospitality Solutions | 2022-07-27 | 2022-08-08 |  | 6300 |  | 100% | 0% | 100% | 6300 | 0 | 6300 |  | RBD
WA-M087 | - | PL & DR | Hot & Res | GF-L4 both landscape | Supply of Planter drains | Hydro point | 2022-07-20 | 2022-07-28 |  | 30000 |  | 100% | 0% | 100% | 30000 | 0 | 30000 |  | RBD
WA-M088 | - | PL & DR | Pod | L5 | Rubber pads | Kinetics Middle East LLC | 2022-07-20 | 2022-07-28 |  | 5640 |  | 99.65% | 0% | 99.65% | 5620 | 0 | 5620 |  | RBD
WA-M089 | - | GENERAL | Hot & Res | Various | Supply of Walkie-Talkie | Micro net | 2022-07-20 | 2022-07-28 |  | 12920 |  | 100% | 0% | 100% | 12920 | 0 | 12920
WA-M090 | - | ELEC | Res | Various | Supply of ATS Actuator for pending FCU link | Advanced Technical | 2022-08-19 | 2022-08-26 |  | 14910 |  | 100% | 0% | 100% | 14910 | 0 | 14910 |  | RBD
WA-M091 | - | PL & DR | Hot & Pod | GF, L2-L4 | HDPE pipe and its accessories | Fikree pipe | 2022-07-21 | 2022-07-28 |  | 24166.63 |  | 86.81% | 0% | 86.81% | 20979.29 | 0 | 20979.29
WA-M092 | - | GENERAL | Hot & Res | Various | Safety full body harness | Al Abbasi Fastners & hardware | 2022-07-21 | 2022-07-28 |  | 6150 |  | 0% | 0% | 0% |  | 0
WA-M093 | 1 | ELEC | Hot & Pod | Various | Supply of FP200 gold Fire rated cables | Ali Haji Abdulla Awazi Gargash | 2022-11-10 |  |  | 67460 |  | 75.52% | 24.48% | 100% | 50942.5 | 16517.5 | 67460 | Not yet approved by OCI but invoices received | RBD
WA-M094 | - | HVAC | Hot & Res | Various | Supply of Aluminium Tape with flange and accessories | Victor Tech. Cont | 2022-07-29 | 2022-08-08 |  | 42400 |  | 41.54% | 0% | 41.54% | 17614.19 | 0 | 17614.19
WA-M095 | - | HVAC | Hot | L29 Toilets | Supply of CW BCU's | Daikin AC | 2022-07-29 | 2022-08-08 |  | 18000 |  | 100% | 0% | 100% | 18000 | 0 | 18000 |  | RBD
WA-M096 | - | [14 empty] | 0 |  | PS Item to be submitted
WA-M097 | - | GENERAL | Hot & Pod | BoH & Plant rooms | Supply of ALU Scaffolding 0.8m & 1.2m, 0.8m & 1.8m | Crescent Scaffolding Industries | 2022-07-28 | 2022-08-02 |  | 13360 |  | 100% | 0% | 100% | 13360 | 0 | 13360 | Prelims - Scaffolding | RBD
WA-M098 | - | [14 empty] | 0
WA-M099 | - | PL & DR | Hot & Res | HL28 & RL30 Plant rooms | Supply of PP-RCT Electrofusion Coupler 200mm | Wassermech | 2022-07-29 | 2022-08-08 |  | 46500 |  | 99.14% | 0% | 99.14% | 46100 | 0 | 46100
WA-M100 | - | PL & DR | Hot | L7-L27 | Supply of Sanitary wares and accessories | Ultimate Trading | 2022-07-29 | 2022-08-08 |  | 10237.5 |  | 100% | 0% | 100% | 10237.5 | 0 | 10237.5 | PS - Sanitarywares
WA-M101 | - | [14 empty] | 0
WA-M102 | - | HVAC | Hot & Res | Various | Supply of Fire rated GI Access Doors | Seagull HVAC Industry | 2022-08-01 | 2022-08-08 |  | 76560 |  | 40.79% | 7.669% | 48.45% | 31225.64 | 5871.46 | 37097.1
WA-M103 | - | ELEC | Pod | GF, L2, L4 | Supply of PVC Conduits and accessories | BMTC | 2022-08-01 | 2022-08-08 |  | 37135.25 |  | 99.52% | 0% | 99.52% | 36955.4 | 0 | 36955.4 |  | RBD
WA-M104 | - | PL & DR | Landscape | Kitchens, Public toilets | Supply of Pipe fittings | Polyfab Plastic | 2022-08-22 | 2022-08-26 |  | 53206.14 |  | 99.52% | 0% | 99.52% | 52952.19 | 0 | 52952.19 |  | RBD
WA-M105 | - | [14 empty] | 0
WA-M106 | - | PL & DR | Res | L22 | Supply of Acoustic lagging for drainage pipes | Kinetics Middle East LLC | 2022-08-10 | 2022-08-12 |  | 3569.83 |  | 100% | 0% | 100% | 3569.83 | 0 | 3569.83 |  | RBD
WA-M107 | - | PL & DR | Hot & Bas | L29, L26, L19, BF and Podium | Supply of PEX Pipe amd Fittings | ATAD Internation | 2022-08-10 | 2022-08-12 |  | 4570 |  | 100% | 0% | 100% | 4570 | 0 | 4570 |  | RBD
WA-M108 | - | [14 empty] | 0
WA-M109 | - | [14 empty] | 0
WA-M110 | - | HVAC | Hot, Res & Pod | Various | Supply of CHW Valves, ERW pipes and accessories | Maunsell | 2022-08-10 | 2022-08-18 |  | 10800 |  | 100% | 0% | 100% | 10800 | 0 | 10800 |  | RBD
WA-M110 | - | HVAC | Hot, Res & Pod | Various | Supply of CHW Valves, ERW pipes and accessories | Mega Star | 2022-08-10 | 2022-08-18 |  | 34875 |  | 100% | 0% | 100% | 34875 | 0 | 34875
WA-M110 | - | HVAC | Hot, Res & Pod | Various | Supply of CHW Valves, ERW pipes and accessories | Bisan building | 2022-08-10 | 2022-08-18 |  | 15414.5 |  | 100% | 0% | 100% | 15414.5 | 0 | 15414.5 |  | RBD
WA-M111 | - | ELEC | Res | L23,31 & 32 | Supply of Cable Tray and Trunking | Power Solution | 2022-09-29 | 2022-10-24 |  | 3628.32 |  | 100% | 0% | 100% | 3628.32 | 0 | 3628.32
WA-M112 | - | GENERAL | Hot, Res & Pod | Various | Supply of Fiber Ladder & Fan for electrical room | Artline Trading | 2022-08-11 | 2022-08-18 |  | 17810 |  | 100% | 0% | 100% | 17810 | 0 | 17810 |  | RBD
WA-M113 | - | PL & DR | Landscape | LG, 2 & 4 | Supply of SS Flood Drain | Hydro point | 2022-08-09 | 2022-08-12 |  | 5520 |  | 98.55% | 0% | 98.55% | 5440 | 0 | 5440
WA-M114 | - | ELEC | Landscape | Main feeder | Supply of 1C PVC Cable | Clevland Cable Trading FZCO | 2022-08-10 | 2022-08-12 |  | 3820.75 |  | 96.62% | 0% | 96.62% | 3691.55 | 0 | 3691.55
WA-M115 | - | HVAC | Hot | L28 - Gym & Spa, L18-PR, L-29 Toilet & L-30 Rf | Supply of XLPE duct insulation | Hira Industries | 2022-08-10 | 2022-08-12 |  | 26726.4 |  | 100% | 0% | 100% | 26726.4 | 0 | 26726.4 |  | RBD
WA-M116 | - | ELEC | Landscape | LV to L2&4 | Supply of Cable Tray and Trunking | Power Solution | 2022-08-10 | 2022-08-12 |  | 22746 |  | 100% | 0% | 100% | 22746 | 0 | 22746 |  | RBD
WA-M117 | - | GENERAL | Hot, Res & Pod | Various | Pipe Threading Machine Tester, Calibration | AAB Tools | 2022-08-10 | 2022-08-12 |  | 46175 |  | 91.17% | 0% | 91.17% | 42099.17 | 0 | 42099.17 | Prelims - Power tools |  | WA-M117 Claimed under Aug IPA - Stock issues.
WA-M118 | 1 | HVAC | Hot, Res & Pod | Various | Chilled Water Pipe insulation | Korea & ME | 2022-10-18 | 2022-10-26 |  | 16699.9 |  | 100% | 0% | 100% | 16699.9 | 0 | 16699.9 |  | RBD
WA-M119 | - | FP | Res | L26 and L28 | Removal and Reinstallation of Fire Fighting and Fire Alarm Works | Emirates Firefighting Equipment Factory (FIREX) | 2022-08-15 | 2022-10-24 |  | 15000 |  | 0% | 50% | 50% |  | 7500 | 7500 | Direct works - FIREX
WA-M120 | - | PL & DR | Res | Small buildings | UPVC Drainage Materials | Polyfab Plastic | 2022-08-18 | 2022-08-26 |  | 3968.04 |  | 89.26% | 0% | 89.26% | 3541.76 | 0 | 3541.76
WA-M121 | - | ELEC | Landscape | Various | Supply of Single Core Wires | Clevland Cable Trading FZCO | 2022-08-19 | 2022-08-26 |  | 397900.62 |  | 98.51% | 0% | 98.51% | 391959.76 | 0 | 391959.76
WA-M122 | - | PL & DR | Hot | BoH L7-29 | Supply of Brass Double Check Valve | Hydro point | 2022-08-18 | 2022-08-18 |  | 1750 |  | 100% | 0% | 100% | 1750 | 0 | 1750 |  | RBD
WA-M123 | - | [14 empty] | 0
WA-M124 | - | ELEC | Hot | Guest Room | Supply of HDMI Cables for Media Hub | Hospitality Solutions | 2022-08-19 | 2022-08-25 |  | 2511 |  | 100% | 0% | 100% | 2511 | 0 | 2511 |  | RBD
WA-M125 | - | ELEC | Hot | Guest Room | Supply of DB's, ELCB and Isolators | Arabian Gulf Switchgear | 2022-08-22 | 2022-08-26 |  | 18598 |  | 21.28% | 0% | 21.28% | 3958 | 0 | 3958
WA-M126 | - | ELEC | Bas | B1 UPS room | Supply of 150AH Batteries | Site Technology | 2022-08-19 | 2022-09-21 |  | 30360 |  | 0% | 100% | 100% |  | 30360 | 30360
WA-M127 | - | HVAC | Hot, Res & Pod | Various | Supply of Duct Insulation (25mm Thickness) | Hira Industries | 2022-08-20 | 2022-08-26 |  | 38001.6 |  | 99.34% | 0% | 99.34% | 37751.04 | 0 | 37751.04
WA-M128 | 2 | PL & DR | Landscape | Various | Supply of Slot Drain | Hydro point | 2022-10-19 | 2022-10-24 |  | 402167.15 |  | 0% | 62.17% | 62.17% |  | 250036.47 | 250036.47
WA-M129 | - | ELEC | Hot | IDF Rooms | Supply of 1C 16 sqmm yellow/ green cable | Clevland Cable Trading FZCO | 2022-08-20 | 2022-08-26 |  | 27405 |  | 98.52% | 0% | 98.52% | 27000 | 0 | 27000
WA-M130 | - | PL & DR | Hot | B1 | Heavy Duty Park Drains | Green fields | 2022-08-22 | 2022-08-26 |  | 1410 |  | 100% | 0% | 100% | 1410 | 0 | 1410 |  | RBD
WA-M131 | - | ELV works | General | Various | Supply of Structure Cabling Works | SIS | 2022-08-23 | 2022-09-21 |  | 131894.2 |  | 27.83% | 25.7% | 53.53% | 36704.25 | 33896.67 | 70600.92 | PS - SIS
WA-M132 | - | HVAC | Hot & Res | RL5-HB1 | AHU chilled water header line modification works | Daikin AC | 2022-08-23 | 2022-08-26 |  | 8400 |  | 100% | 0% | 100% | 8400 | 0 | 8400
WA-M133 | - | HVAC | Pod | Podium | Supply of FCU Model: DCMP | SKM AC | 2022-08-23 | 2022-08-26 |  | 13675.16 |  | 0% | 100% | 100% |  | 13675.08 | 13675.08
WA-M134 | - | [14 empty] | 0
WA-M135 | 1 | PL & DR | Res | B2-L5 | Supply of PPR Pipes and Fittings | Al Muhaideb | 2022-09-28 | 2022-10-24 |  | 85865.4 |  | 0% | 25.53% | 25.53% |  | 21920.3 | 21920.3
WA-M136 | - | HVAC | Hot | Staircase no.6 | Supply of Air registers | Tecnalco | 2022-08-24 | 2022-08-26 |  | 2607 |  | 100% | 0% | 100% | 2607 | 0 | 2607 |  | RBD
WA-M137 | - | PL & DR | Hot | Ballroom | Supply of Cistern tanks for the Ballroom toilets | Sanipex | 2022-08-24 | 2022-08-26 |  | 17581.46 |  | 100% | 0% | 100% | 17581.46 | 0 | 17581.46 | PS - Sanitarywares | RBD
WA-M138 | - | ELEC | Hot | L18-24 | Supply of XLPE fire rated cables | Clevland Cable Trading FZCO | 2022-08-25 | 2022-09-07 |  | 8479.93 |  | 99.99% | 0% | 99.99% | 8479 | 0 | 8479 |  | RBD
WA-M139 | - | ELV works | Hot | Ballroom & Meeting Room | Supply of ELV System works | SIS | 2022-08-26 | 2022-09-21 |  | 833824 |  | 0% | 3.326% | 3.326% | 0 | 27733.305 | 27733.305 | PS - SIS
WA-M140 | - | [14 empty] | 0
WA-M141 | - | GENERAL | Hot | Ball room | Ball room lift works | KONE | 2022-08-29 | 2022-10-26 |  | 101250 |  | 60% | 0% | 60% | 60750 | 0 | 60750 | PS - Kone
WA-M142 | - | PL & DR | Hot | KDP 29 & Riser upto L6 | Supply of HDPE Pipe | Fikree pipe | 2022-08-29 | 2022-09-07 |  | 29959.65 |  | 98.91% | 0% | 98.91% | 29633.97 | 0 | 29633.97
WA-M143 | - | PL & DR | Res | L31 Water tank | UPVC puddle flange and GI backing ring | Fikree pipe | 2022-08-29 | 2022-09-07 |  | 3044 |  | 100% | 0% | 100% | 3044 | 0 | 3044 |  | RBD
WA-M144 | - | ELEC | Res | B2-L5 Elec Room | Supply of Electrical items and accessories | Various Suppliers | 2022-09-13 |  |  | 31476.5 |  | 0% | 0% | 0% |  | 0
WA-M145 | - | HVAC | General | Various | Supply of Aluminium tapes | Focus AC | 2022-08-30 | 2022-09-07 |  | 10200 |  | 100% | 0% | 100% | 10200 | 0 | 10200 |  | RBD
WA-M146 | 1 | PL & DR | General | Various | Supply of Channel gratings | Tanseeq | 2022-09-23 | 2022-09-29 |  | 39600 |  | 0% | 0% | 0% |  | 0
WA-M147 | 2 | PL & DR | Hot & Res | Various | Supply of PPR Pipes and Fittings | Al Muhaideb | 2022-09-28 | 2022-10-24 |  | 317197.2 |  | 77.14% | 7.28% | 84.42% | 244691.1 | 23093.45 | 267784.55
WA-M148 | 1 | HVAC | Hot & Res | Various | Chilled water fittings and valves | Maunsell | 2022-11-02 | 2022-11-13 |  | 75000 |  | 100% | 0% | 100% | 75000 | 0 | 75000 |  | RBD
WA-M148 | 1 | HVAC | Hot & Res | Various | Chilled water fittings and valves | Bisan building | 2022-11-02 | 2022-11-13 |  | 15916.86 |  | 100% | 0% | 100% | 15916.86 | 0 | 15916.86 |  | RBD
WA-M148 | 1 | HVAC | Hot & Res | Various | Chilled water fittings and valves | Technopro ME | 2022-11-02 | 2022-11-13 |  | 7837.42 |  | 100% | 0% | 100% | 7837.42 | 0 | 7837.42 |  | RBD
WA-M149 | - | HVAC | Hot & Res | B2 | Chilled water flushing works | Cool line AC | 2022-09-01 | 2022-09-07 |  | 58000 |  | 100% | 0% | 100% | 58000 | 0 | 58000 | KMEP Domestic SC paid based on their progress completion
WA-M150 | - | ELEC | Hot | L28 & LV Room | Repariing works on damaged cables | Cable Cure EMW | 2022-08-31 | 2022-09-07 |  | 9990 |  | 100% | 0% | 100% | 9990 | 0 | 9990 |  | RBD
WA-M151 | - | ELEC | General | PR, Staircase, Shaft & B1 | Supply of GI conduits and accessories | Al Hathboor | 2022-08-31 | 2022-09-07 |  | 42997.5 |  | 100% | 0% | 100% | 42997.45 | 0 | 42997.45 |  | RBD
WA-M152 | - | PL & DR | Hot | L29 Roof | Supply of Sanitary wares and accessories | Sanipex | 2022-09-01 |  |  | 247809.81 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M153 | 1 | PL & DR | Hot | L26 Royal Suite | Supply of Sanitary wares and accessories | Sanipex | 2022-10-26 | 2022-10-31 |  | 102763.81 |  | 15.51% | 0% | 15.51% | 15943.64 | 0 | 15943.64 | PS - Sanitarywares
WA-M153 | 1 | PL & DR | Hot | L26 Royal Suite | Supply of Sanitary wares and accessories | Al Futtaim | 2022-10-26 | 2022-10-31 |  | 15195 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M153 | 1 | PL & DR | Hot | L26 Royal Suite | Supply of Sanitary wares and accessories | Taps & More Marketing | 2022-10-26 | 2022-10-31 |  | 5000 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M154 | 1 | PL & DR | Hot | L19 Presidential Suite | Supply of Sanitary wares and accessories | Sanipex | 2022-10-31 | 2022-10-31 |  | 110319.43 |  | 22.83% | 0% | 22.83% | 25190.6 | 0 | 25190.6 | PS - Sanitarywares
WA-M154 | 1 | PL & DR | Hot | L19 Presidential Suite | Supply of Sanitary wares and accessories | Al Futtaim | 2022-10-31 | 2022-10-31 |  | 15195 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M155 | - | PL & DR | Hot | BoH | Supply of Sanitary wares and accessories | Sanipex | 2022-09-01 | 2022-09-21 |  | 98675.48 |  | 51.89% | 0% | 51.89% | 51199.18 | 0 | 51199.18 | PS - Sanitarywares | This one supersedes WA-M78
WA-M156 | 1 | PL & DR | Hot | L7-L27 | Supply of Sanitary wares and accessories | Various Suppliers | 2022-09-13 | 2022-09-21 |  | 575449.27 |  | 7.337% | 6.594% | 13.93% | 42222.95 | 37946.1 | 80169.05 | PS - Sanitarywares | 9603.23 - Get Back-up from KMEP
WA-M157 | - | ELEC | Hot | L9 | Supply of missing GRMS materials | Creation Gulf | 2022-09-02 | 2022-09-16 |  | 4193 |  | 0% | 0% | 0% |  | 0 |  | PS - Creation Gulf
WA-M158 | - | ELEC | Bas | Carpark | Supply of CO2 Sensors | Johnson Controls | 2022-09-02 | 2022-09-21 |  | 13400 | [5 empty] | 0 |  | Direct works - JCI
WA-M159 | - | ELEC | Res & Landscape | Corridor, Gym | Supply of light fittings | Projects & Supplies | 2022-09-03 | 2022-09-21 |  | 171555.84 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M160 | 1 | ELEC | Hot & Res | Various | Supply of pending power tools | Various Suppliers | 2022-09-12 | 2022-09-16 |  | 80005 |  | 91.09% | 0% | 91.09% | 72878 | 0 | 72878 | Prelims - Power tools |  | (270+20300+36800+2500+7608) claimed in Oct'22 IPA Stock issues
WA-M161 | - | ELEC | Pod | Landscape | Supply of IP65 waterproof connector | Misterlight | 2022-09-05 | 2022-09-21 |  | 5137.5 |  | 100% | 0% | 100% | 5137.5 | 0 | 5137.5 |  | RBD
WA-M162 | - | ELEC | Pod | Landscape | Supply of IP67 Junction box | Al Ghandi | 2022-09-05 | 2022-09-21 |  | 5800 |  | 100% | 0% | 100% | 5800 | 0 | 5800 |  | RBD
WA-M163 | - | ELEC | Hot & Res | Landscape | Supply of 8 way Copper earth bar | TECON | 2022-09-05 | 2022-09-21 |  | 12750 |  | 100% | 0% | 100% | 12750 | 0 | 12750 |  | RBD
WA-M164 | - | HVAC | Hot, Res & Pod | Various | Supply of Flexible duct | AW Rostamani Lumina | 2022-09-05 | 2022-09-29 |  | 4640.9 |  | 100% | 0% | 100% | 4640.9 | 0 | 4640.9
WA-M164 | - | ELEC | Hot, Res & Pod | Various | Supply of Flexible conduit | BMTC | 2022-09-05 | 2022-09-29 |  | 2378.25 |  | 100% | 0% | 100% | 2378.25 | 0 | 2378.25 |  | RBD
WA-M165 | 1 | GENERAL | General | Various | Supply of consumables | Fine Tools | 2022-10-18 | 2022-10-26 |  | 5192 |  | 100% | 0% | 100% | 5192 | 0 | 5192 |  | RBD
WA-M166 | - | HVAC | Hot & Res | Various | Supply of flexible duct & duct connector | Focus AC | 2022-09-06 | 2022-09-21 |  | 11680 |  | 100% | 0% | 100% | 11680 | 0 | 11680 |  | RBD
WA-M167 | - | HVAC | Hot & Res | Various | Supply of 50mm thickness Rockwool insulation | Abdulla Al Zaabi | 2022-09-06 | 2022-09-21 |  | 5705.28 |  | 100% | 0% | 100% | 5705.28 | 0 | 5705.28 |  | RBD
WA-M168 | - | HVAC | Hot & Res | Various | Supply of Acoustic insulation for Duct | Kepco | 2022-09-06 | 2022-09-21 |  | 3050.04 |  | 99.43% | 0% | 99.43% | 3032.52 | 0 | 3032.52
WA-M169 | - | HVAC | General | Various | Flushing consumable - Mist fan & torch | Pioneers Electricals | 2022-09-06 | 2022-09-21 |  | 2220 |  | 100% | 0% | 100% | 2220 | 0 | 2220 |  | RBD
WA-M169 | - | HVAC | General | Various | Flushing consumable - Flex chute & welding screen | Fine Tools | 2022-09-06 | 2022-09-21 |  | 5480 |  | 0% | 0% | 0% |  | 0
WA-M170 | 1 | GENERAL | General | Various | Supply of consumable items | Various Suppliers | 2022-09-15 | 2022-09-16 |  | 85168.55 |  | 94.64% | 0% | 94.64% | 80602.89 | 0 | 80602.89
WA-M171 | 1 | PL & DR | Bas | B2 Sump pump | Supply of sump pump items | Fikree pipe | 2022-10-22 | 2022-10-26 |  | 3712.22 |  | 100% | 0% | 100% | 3712.16 | 0 | 3712.16
WA-M171 | 1 | PL & DR | Bas | B2 Sump pump | Supply of sump pump items | Fluid Control Trading | 2022-10-22 | 2022-10-26 |  | 12167 |  | 0% | 0% | 0% |  | 0
WA-M172 | - | PL & DR | Pod & Bas | Risers | Supply of rubber lined clamp | Kepco | 2022-09-07 | 2022-09-21 |  | 2102.26 |  | 100% | 0% | 100% | 2102.21 | 0 | 2102.21 |  | RBD
WA-M173 | - | HVAC | Hot & Res | Stress Analysis | Supply of SS Expansion joints | Kinetics Middle East LLC | 2022-09-08 | 2022-09-21 |  | 61244.8 |  | 100% | 0% | 100% | 61244.8 | 0 | 61244.8 |  | RBD
WA-M174 | 1 | HVAC | Pod | GF Corridor | Supply of linear slot diffusers | Tecnalco | 2022-09-08 | 2022-09-21 |  | 1790.8 |  | 100% | 0% | 100% | 1790.8 | 0 | 1790.8 |  | RBD
WA-M174 | 1 | HVAC | Pod | GF Corridor | GI Duct ring | Seagull HVAC Industry | 2022-09-08 | 2022-09-21 |  | 600 |  | 0% | 0% | 0% |  | 0
WA-M175 | - | HVAC | General | Various | Chilled water flushing materials | Various Suppliers | 2022-09-08 | 2022-09-16 |  | 25302 |  | 100% | 0% | 100% | 25302 | 0 | 25302 |  | RBD
WA-M176 | - | ELEC | Hot | Various | Supply of FOH light fittings | Projects & Supplies | 2022-09-08 | 2022-09-21 |  | 112536 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M177 | - | [14 empty] | 0
WA-M178 | - | GENERAL | General | Various | MEP 1st and 2nd fix items | Various Suppliers | 2022-09-08 | 2022-09-21 |  | 175051.33 |  | 95.49% | 0.1542% | 95.65% | 167163.73 | 270 | 167433.73
WA-M179 | - | ELEC | Res | Various | Supply of power socket outlets | Ali Haji Abdulla Awazi Gargash | 2022-09-09 | 2022-09-16 |  | 2290 |  | 68.21% | 0% | 68.21% | 1562 | 0 | 1562
WA-M180 | - | ELEC | Res | L23 | Supply of PVC Conduits and accessories | BMTC | 2022-09-09 | 2022-09-16 |  | 4946.25 |  | 100% | 0% | 100% | 4946.25 | 0 | 4946.25 |  | RBD
WA-M181 | - | ELEC | Hot | Stair L7-28 and 7-26 FTR rooms | Supply of light fixtures (BoH) | Genfocus | 2022-09-09 | 2022-09-21 |  | 40070 |  | 52.41% | 42.55% | 94.96% | 21000 | 17050 | 38050 | PS - Light fittings
WA-M182 | - | HVAC | All | Various | Installation of chilled water valves and testing | Cool line AC | 2022-09-10 | 2022-09-16 |  | 60000 |  | 100% | 0% | 100% | 60000 | 0 | 60000 | KMEP Domestic SC paid based on their progress completion
WA-M183 | - | HVAC | All | Various | Supply of Consumable items | Various Suppliers | 2022-09-10 | 2022-09-16 |  | 7260 |  | 75.55% | 0% | 75.55% | 5485 | 0 | 5485
WA-M184 | - | PL & DR | Res | L3 Kitchen | Supply of HDPE Pipes and fittings | Various Suppliers | 2022-09-10 | 2022-09-22 |  | 21981.7 |  | 99.93% | 0% | 99.93% | 21966.1 | 0 | 21966.1 |  | RBD
WA-M185 | - | PL & DR | Bas | B2 Sump pump | Supply of Gate valve and NRV | Technical Parts | 2022-09-10 | 2022-09-16 |  | 2610 |  | 100% | 0% | 100% | 2610 | 0 | 2610 |  | RBD
WA-M186 | - | PL & DR | Res | B2-L5 WM Room | Supply of Valves and accessories | Technical Parts | 2022-09-10 | 2022-09-16 |  | 19803.6 |  | 97.53% | 0% | 97.53% | 19314.6 | 0 | 19314.6
WA-M187 | - | HVAC | GF & B2 | B2 & ETS | Supply of Chilled water line vibration isolator for HEX and Pumps | Kinetics Middle East LLC | 2022-09-12 | 2022-09-16 |  | 8124.6 |  | 100% | 0% | 100% | 8124.6 | 0 | 8124.6 |  | RBD
WA-M188 | 1 | GENERAL | Pod & Bas | Podium & Basement | Supply of Aluminium Mobile Scaffolding | Crescent Scaffolding Industries | 2022-09-15 | 2022-09-16 |  | 10020 |  | 0% | 0% | 0% |  | 0 |  | Prelims - Scaffolding
WA-M189 | - | HVAC | All | Staircase | Supply of Dampers | Prime A/C | 2022-09-12 | 2022-09-16 |  | 17582.08 |  | 92.3% | 0% | 92.3% | 16229.12 | 0 | 16229.12
WA-M190 | - | PL & DR | Hot & Res | Various | Supply of PRV's for Water supply system | Hydro point | 2022-09-12 | 2022-09-22 |  | 62924.31 |  | 74.25% | 0% | 74.25% | 46723.25 | 0 | 46723.25
WA-M191 | - | ELEC | Hot | GF, L2 & L4 Landscape | Supply of Trunking | Various Suppliers | 2022-09-13 |  |  | 38977.5 |  | 0% | 0% | 0% |  | 0
WA-M192 | - | ELEC | Pod | L2 | Supply of Fire cables and accessories | Various Suppliers | 2022-09-13 |  |  | 41795.25 |  | 0% | 0% | 0% |  | 0
WA-M193 | - | ELEC | Pod | B1-L5 | Supply of electrical items and accessories | Various Suppliers | 2022-09-13 |  |  | 176044.22 |  | 0% | 0% | 0% |  | 0
WA-M194 | - | ELEC | Pod | B1-L5 | Supply of electrical items and accessories | Various Suppliers | 2022-09-13 |  |  | 57044.5 |  | 0% | 0% | 0% |  | 0
WA-M195 | 2 | HVAC | Pod | Various | Chilled water flushing consumable items | Bin Shakir | 2022-11-09 | 2022-11-13 |  | 3475 |  | 100% | 0% | 100% | 3475 | 0 | 3475
WA-M195 | 2 | HVAC | Pod | Various | Chilled water flushing consumable items | We Serve | 2022-11-09 | 2022-11-13 |  | 4950 |  | 0% | 0% | 0% | 0 | 0 | 0 | Previous Gmark changed as We Serve
WA-M196 | 1 | HVAC | Hot & Res | L18 and L23 | Supply of chilled water pipes | Mega meter | 2022-09-15 | 2022-09-16 |  | 7054 |  | 100% | 0% | 100% | 7054 | 0 | 7054 |  | RBD
WA-M197 | - | ELEC | Pod | Various | Supply of PVC Conduits and accessories | Various Suppliers | 2022-11-09 | 2022-11-13 |  | 56704.6 |  | 95.83% | 1.757% | 97.59% | 54342.64 | 996.2 | 55338.84
WA-M198 | - | HVAC | Hot & Pod | Various | FCU repair works | MRI Technical | 2022-09-21 | 2022-09-22 |  | 7800 |  | 100% | 0% | 100% | 7800 | 0 | 7800 |  | RBD
WA-M199 | - | ELEC | Pod | GF & Retail | Supply of meter cabinets, MCCB and MDB modification works | Arabian Gulf Switchgear | 2022-09-17 | 2022-09-21 |  | 102083 |  | 0% | 100% | 100% |  | 102083 | 102083 |  | 9976
WA-M200 | - | ELEC | Res | PR, Staircase, WM, Lobby, FTR & GSM room | Supply of BOH light fittings | Genfocus | 2022-09-20 | 2022-09-22 |  | 22030 |  | 63.8% | 0% | 63.8% | 14055 | 0 | 14055 | PS - Light fittings
WA-M201 | - | HVAC | Hot | Various | Supply of chilled water glue and acoustic glue | Hira Industries | 2022-09-20 | 2022-09-22 |  | 5750 |  | 100% | 0% | 100% | 5750 | 0 | 5750 |  | RBD
WA-M201 | - | HVAC | Hot | Various | Supply of chilled water glue and acoustic glue | Kepco | 2022-09-20 | 2022-09-22 |  | 993.6 |  | 100% | 0% | 100% | 993.6 | 0 | 993.6 |  | RBD
WA-M202 | - | GENERAL | General | Various | Supply of access doors | Victor Tech. Cont | 2022-09-20 | 2022-09-22 |  | 2774 |  | 100% | 0% | 100% | 2774 | 0 | 2774 |  | RBD
WA-M203 | - | ELEC | Pod | Various | FP200 Gold fire rated cables | Ali Haji Abdulla Awazi Gargash | 2022-09-21 | 2022-10-24 |  | 9705 |  | 100% | 0% | 100% | 9705 | 0 | 9705 |  | RBD
WA-M204 | - | GENERAL | General | Various | Supply of Aluminium Hop up stand | Crescent Scaffolding Industries | 2022-09-21 | 2022-09-22 |  | 900 |  | 0% | 0% | 0% |  | 0 |  | Prelims - Scaffolding
WA-M205 | - | ELEC | Hot & Res | Electrical rooms | Supply of PVC insulated wires | Misterlight | 2022-09-21 | 2022-09-22 |  | 337.5 |  | 0% | 0% | 0% |  | 0
WA-M206 | - | ELEC | Hot & Res | Plant room | Supply of HDGI cable tray covers | Power Solution | 2022-09-29 | 2022-10-24 |  | 1129.07 |  | 100% | 0% | 100% | 1129.07 | 0 | 1129.07 |  | RBD
WA-M207 | - | ELEC | Pod | Various | Supply of GI Conduits and Accessories | Al Hathboor | 2022-09-21 | 2022-09-22 |  | 66495.5 |  | 97.09% | 0% | 97.09% | 64560.5 | 0 | 64560.5
WA-M208 | - | ELEC | Pod | Various | Supply of switchgear components and cable glands | Various Suppliers | 2022-09-23 | 2022-09-29 |  | 4915.5 |  | 85.35% | 9.155% | 94.51% | 4195.5 | 450 | 4645.5
WA-M209 | 1 | PL & DR | Pod | L1-3 | Supply of MS Pipes, Valves and Accessories for BTU meter relocation | Various Suppliers | 2022-10-12 | 2022-10-24 |  | 57356.19 |  | 88.06% | 0% | 88.06% | 50508.07 | 0 | 50508.07
WA-M210 | - | PL & DR | Bas | B1 | Supply of B1 Toilet accessories | Sanipex | 2022-09-23 | 2022-09-29 |  | 17644.06 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M211 | - | ELEC | Bas | B2 | Supply of electrical materials for sump pump modification | Prakash Trading | 2022-09-23 | 2022-10-24 |  | 6480 |  | 100% | 0% | 100% | 6480 | 0 | 6480
WA-M211 | - | ELEC | Bas | B2 | Supply of electrical materials for sump pump modification | Nysa Electrical Trading | 2022-09-23 | 2022-10-24 |  | 2795 |  | 93.02% | 0% | 93.02% | 2600 | 0 | 2600
WA-M212 | - | HVAC | All | Various | Supply of ventilation fans | Energy International | 2022-09-26 | 2022-09-29 |  | 123500 |  | 0% | 28.35% | 28.35% |  | 35012.01 | 35012.01
WA-M213 | 1 | ELEC | Hot & Res | Various | Supply of floor boxes | Nysa Electrical Trading | 2022-11-25 |  |  | 104650 |  | 0% | 75.6% | 75.6% |  | 79120 | 79120
WA-M214 | - | HVAC | Res | Various | Supply of chilled water valves and accessories | Various Suppliers | 2022-10-14 | 2022-10-24 |  | 10131.21 |  | 13.95% | 50.47% | 64.43% | 1413.8 | 5113.68 | 6527.48
WA-M215 | - | ELEC | Hot | Ballroom | Supply of Cables | Cleveland Cable Trading FZCO | 2022-09-27 | 2022-10-24 |  | 63052.85 |  | 33.53% | 0% | 33.53% | 21141.9 | 0 | 21141.9
WA-M216 | - | ELEC | Hot | Guest Room | Supply of Light Fittings (Guestrooms) | Projects & Supplies | 2022-09-27 | 2022-09-30 |  | 200000 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M217 | - | [14 empty] | 0
WA-M218 | - | HVAC | Res | L3 | Supply of blower coil units | Daikin AC | 2022-09-28 | 2022-09-29 |  | 10500 |  | 0% | 0% | 0% |  | 0
WA-M219 | - | GENERAL | General | Various | Supply of PVC glue | BMTC | 2022-09-28 | 2022-09-29 |  | 4644 |  | 41.67% | 0% | 41.67% | 1935 | 0 | 1935
WA-M220 | - | PL & DR | Pod & Bas | Various | Supply of Plumbing Valves | Fluid Control Trading | 2022-09-28 | 2022-09-29 |  | 46715.13 |  | 100% | 0% | 100% | 46715.13 | 0 | 46715.13
WA-M221 | 1 | GENERAL | General | Various | Supply of Aluminium glass tape | Delta duct AC | 2022-11-09 | 2022-11-13 |  | 19600 |  | 42.5% | 0% | 42.5% | 8330 | 0 | 8330
WA-M221 | 1 | GENERAL | General | Various | Supply of teflon tapes | Fine Tools | 2022-11-09 | 2022-11-13 |  | 1350 |  | 100% | 0% | 100% | 1350 | 0 | 1350
WA-M222 | - | ELEC | General | Various | Supply of LED driver | Projects & Supplies | 2022-09-28 | 2022-09-29 |  | 5818 |  | 88.14% | 0% | 88.14% | 5128 | 0 | 5128
WA-M223 | 1 | ELEC | Hot | Various | Supply of Guest rooms Strip light fittings | HS Energy Solutions FZCO | 2022-09-29 | 2022-10-26 |  | 243451.4 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M224 | - | PL & DR | GF | Kitchen | Supply of Ecology unit with ESP | Trosten Industries | 2022-09-28 | 2022-09-29 |  | 47800 |  | 0% | 94.14% | 94.14% |  | 45000 | 45000
WA-M225 | - | HVAC | General | Various | Installation of riser flexible connectors and supports | Cool line AC | 2022-09-28 | 2022-10-24 |  | 20000 |  | 100% | 0% | 100% | 20000 | 0 | 20000 | KMEP Domestic SC paid based on their progress completion | RBD
WA-M226 | - | ELEC | General | Various | Supply of electrical consumable items and accessories | Various Suppliers | 2022-09-29 | 2022-10-24 |  | 13711.37 |  | 100% | 0% | 100% | 13711.37 | 0 | 13711.37
WA-M227 | - | PL & DR | General | Various | Transport cost for bath tub delivery | Taps & More Marketing | 2022-09-29 | 2022-10-24 |  | 5857.5 |  | 69.95% | 0% | 69.95% | 4097.5 | 0 | 4097.5 | PS - Sanitarywares
WA-M228 | 1 | GENERAL | Hot | Ball room | Ball room consumable items | Various Suppliers | 2022-10-13 | 2022-10-24 |  | 12211.15 |  | 100% | 0% | 100% | 12211.15 | 0 | 12211.15
WA-M229 | - | ELEC | Hot, Res & Pod | Various | Supply of modules and accessories for lighting control system | Gama Engineering | 2022-10-03 | 2022-10-24 |  | 28000 |  | 0% | 1.446% | 1.446% |  | 405 | 405 | PS - Light fittings
WA-M230 | - | HVAC | Hot & Res | Various | Supply of duct insulations 25mm & 50mm | Hira Industries | 2022-10-03 | 2022-10-24 |  | 33408 |  | 100% | 0% | 100% | 33408 | 0 | 33408 |  | RBD
WA-M231 | - | ELEC | Pod & Bas | Various | Supply of BOH light fittings | Genfocus | 2022-10-04 |  |  | 77557.5 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M232 | - | [14 empty] | 0
WA-M233 | - | HVAC | Hot, Res & Pod | Various | Supply of Lap up chemicals and services | Culligan International Emirates | 2022-10-04 |  |  | 24500 |  | 0% | 0% | 0% |  | 0
WA-M234 | - | PL & DR | Hot, Res & Bas | Various | Supply of Drainage UPVC and WS PPR pipes with accessories | Various Suppliers | 2022-10-28 | 2022-10-31 |  | 104458.64 |  | 50.8% | 13.77% | 64.57% | 53069.35 | 14380.3 | 67449.65
WA-M235 | 1 | HVAC | Hot, Res & Pod | Various | Chilled water riser supports | Various Suppliers | 2022-10-11 | 2022-10-24 |  | 9025 |  | 59.83% | 0% | 59.83% | 5400 | 0 | 5400
WA-M236 | - | HVAC | Hot, Res & Pod | Various | Tube insulation for Chilled water system | Korea & ME | 2022-10-05 | 2022-10-24 |  | 9594.4 |  | 100% | 0% | 100% | 9594.4 | 0 | 9594.4 |  | RBD
WA-M237 | - | HVAC | Hot & Res | Various | Supply of slip on flanges for CHWP expansions | Technopro ME | 2022-10-05 | 2022-10-24 |  | 3014.08 |  | 76.01% | 0% | 76.01% | 2290.98 | 0 | 2290.98
WA-M238 | - | HVAC | Res | L23 | Supply of Chilled water fittings for L23 modification works | Technopro ME | 2022-10-05 | 2022-10-24 |  | 1676.42 |  | 100% | 0% | 100% | 1676.42 | 0 | 1676.42 |  | RBD
WA-M239 | - | HVAC | General | Various | Valves pending payment release | Maunsell | 2022-10-06 | 2022-10-24 |  | 4882.5 | 4882.5 | 100% | 0% | 100% | 4882.5 | 0 | 4882.5
WA-M240 | - | PL & DR | General | Various | Supply of bathtub anf accessories | Taps & More Marketing | 2022-10-06 | 2022-10-24 |  | 5000 |  | 100% | 0% | 100% | 5000 | 0 | 5000 | PS - Sanitarywares
WA-M241 | - | HVAC | General | Various | Supply of Consumable Items | Fine Tools | 2022-10-07 | 2022-10-24 |  | 5340.6 |  | 100% | 0% | 100% | 5340.6 | 0 | 5340.6 |  | RBD
WA-M242 | - | HVAC | Hot & Res | L5 & L23 | Chilled water pipe valves and fittings | Various Suppliers | 2022-10-13 | 2022-10-24 |  | 5562.9 |  | 75.25% | 0% | 75.25% | 4185.99 | 0 | 4185.99
WA-M243 | - | ELEC | General | Various | Supply of Earthing protection materials | Various Suppliers | 2022-10-10 | 2022-10-24 |  | 19839.38 |  | 99.74% | 0% | 99.74% | 19788.24 | 0 | 19788.24
WA-M244 | - | HVAC | Hot & Res | Risers | Supply of chilled water riser supports | Al Adil | 2022-10-11 | 2022-10-24 |  | 3390 |  | 100% | 0% | 100% | 3390 | 0 | 3390
WA-M245 | - | ELEC | Hot | Guest Room | Supply of light fitting for guest rooms | HS Energy Solutions FZCO | 2022-10-11 | 2022-10-26 |  | 65080 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M246 | - | ELEC | Hot | Various | Supply of stickers for Electrical services | Various Suppliers | 2022-10-11 | 2022-10-24 |  | 5300 |  | 0% | 100% | 100% |  | 5300 | 5300
WA-M247 | - | FP | Hot & Res | Various | Re-rouing of 6" wet riser interconnection | Emirates Firefighting Equipment Factory (FIREX) | 2022-10-18 | 2022-10-31 |  | 11550 |  | 0% | 100% | 100% |  | 11550 | 11550 | Direct works - FIREX
WA-M248 | - | PL & DR | Bas | B1 Ablution room | Supply of ablution taps for ablution rooms | Sanipex | 2022-10-11 | 2022-10-24 |  | 3982.86 |  | 100% | 0% | 100% | 3982.86 | 0 | 3982.86 | PS - Sanitarywares | RBD
WA-M249 | - | GENERAL | General | Generator room | Charges for checking and approval of Generator room drawings | Jengan LLC | 2022-10-12 | 2022-10-24 |  | 5000 |  | 0% | 0% | 0% |  | 0 |  | Prelims - Drawing review and approval
WA-M250 | 1 | HVAC | Hot | GF & L29 | Supply of Air Curtains | Hira Industries | 2022-11-18 | 2022-12-06 |  | 11500 |  | 0% | 0% | 0% |  | 0
WA-M251 | - | HVAC | General | Various | Chilled water - Anchor for stress analysis supports - Riser supports | Hilti Emirates | 2022-10-13 | 2022-10-24 |  | 8400.6 |  | 0% | 0% | 0% |  | 0
WA-M252 | - | PL & DR | Hot & Res | Various | Supply of PPR electro fusion sockets | Aquagas | 2022-10-13 | 2022-10-24 |  | 37940 |  | 0% | 100% | 100% |  | 37940 | 37940
WA-M253 | - | PL & DR | Hot & Res | Various | Supply of PRV and valve connection to FAHU's | Faisal Jassim Trading |  |  |  | 366000 |  | 0% | 0% | 0% |  | 0 |  | Direct works - FJT
WA-M254 | - | ELEC | GF | Staircase | Supply of additional stair light fittings | Projects & Supplies | 2022-10-18 | 2022-10-26 |  | 35323 |  | 0% | 100% | 100% |  | 35323 | 35323 | PS - Light fittings
WA-M255 | - | HVAC | Hot & Res | Risers | Supply of chilled water riser supports | Bin Shakir | 2022-10-14 | 2022-10-24 |  | 1752.84 |  | 100% | 0% | 100% | 1752.84 | 0 | 1752.84 |  | RBD
WA-M256 | - | PL & DR | Res | Landscape | Supply of planter drain/ bespoke/ spot drains | Hydro point | 2022-10-14 | 2022-10-24 |  | 8200 |  | 0% | 90.12% | 90.12% |  | 7390 | 7390
WA-M257 | - | ELEC | Hot | RF - B2 | High voltage Shielded cable for lightning protection | SMKA Electric | 2022-10-18 | 2022-10-26 |  | 69960 |  | 100% | 0% | 100% | 69960 | 0 | 69960 | PS - Light fittings | RBD
WA-M258 | - | ELEC | Res | BoH | Supply of BoH wiring accessories | Ali Haji Abdulla Awazi Gargash | 2022-10-18 | 2022-10-26 |  | 3657 |  | 92.18% | 0% | 92.18% | 3371 | 0 | 3371
WA-M259 | - | ELEC | Res | L23, L30 and L31 | Supply of DB breakers | Arabian Gulf Switchgear | 2022-10-17 | 2022-10-24 |  | 1882 |  | 0% | 100% | 100% |  | 1882 | 1882
WA-M260 | - | PL & DR | Hot | L17 | Supply of Planter drains | Hydro point | 2022-10-17 | 2022-10-26 |  | 4600 |  | 100% | 0% | 100% | 4600 | 0 | 4600
WA-M261 | 1 | ELEC | Hot | Ball room | Supply of DB, Cables and accessories for Ball Room | Various Suppliers | 2022-10-22 | 2022-10-31 |  | 21366.57 |  | 42.99% | 56.37% | 99.36% | 9184.9 | 12044 | 21228.9
WA-M262 | - | ELEC | Res | Various | Supply of Single Core Wires | Cleveland Cable Trading FZCO | 2022-10-25 | 2022-10-31 |  | 17189.72 |  | 94.22% | 0% | 94.22% | 16195.52 | 0 | 16195.52
WA-M263 | - | ELEC | Pod | GF and L2 | MCCB changes in SMDB as per DEWA comments | Arabian Gulf Switchgear | 2022-10-18 | 2022-10-24 |  | 12676 |  | 0% | 100% | 100% |  | 12676 | 12676
WA-M264 | - | HVAC | All | Various | Fire blanket for chilled water works | Leminar Air Conditioning | 2022-10-25 | 2022-10-31 |  | 5833.75 |  | 99.42% | 0% | 99.42% | 5800.18 | 0 | 5800.18
WA-M265 | - | HVAC | Hot | L18, L28 toL 30 | Supply of duct acoustic insulation | Kepco | 2022-10-18 | 2022-10-24 |  | 1401.6 |  | 100% | 0% | 100% | 1401.6 | 0 | 1401.6 |  | RBD
WA-M266 | - | [14 empty] | 0
WA-M267 | - | PL & DR | GF | GF-B1 | DEWA line modification works | Various Suppliers | 2022-10-20 | 2022-10-26 |  | 8328.87 |  | 94.21% | 0% | 94.21% | 7846.37 | 0 | 7846.37
WA-M268 | - | HVAC | Hot | Podium | Supply of duct insulation works | Various Suppliers | 2022-10-20 | 2022-10-26 |  | 15778.56 |  | 100% | 0% | 100% | 15778.56 | 0 | 15778.56
WA-M269 | - | PL & DR | Hot | FOH | Supply of floor drain and linear shower drain | Hydro point | 2022-10-20 | 2022-10-26 |  | 9300 |  | 100% | 0% | 100% | 9300 | 0 | 9300 |  | RBD
WA-M270 | - | PL & DR | Hot & Res | Roof | Supply of Roof drains | Green fields | 2022-10-20 | 2022-10-26 |  | 3520 |  | 76.14% | 0% | 76.14% | 2680 | 0 | 2680
WA-M271 | - | PL & DR | Hot & Pod | Various | Supply of 8" UPVC gray socket | Modern Plastic | 2022-10-21 | 2022-10-26 |  | 2113.2 |  | 0% | 100% | 100% |  | 2113.2 | 2113.2
WA-M272 | - | [14 empty] | 0
WA-M273 | - | ELEC | Pod | Various | Supply of Wiring Accessories, Isolaors and Swithes | Various Suppliers | 2022-11-03 | 2022-11-13 |  | 76010.13 |  | 0% | 71.7% | 71.7% |  | 54498.65 | 54498.65
WA-M274 | - | ELEC | All | Various | Supply and installation of cable and containment for BTU meter | ISTA Middle East FZE | 2022-10-25 | 2022-10-31 |  | 45240 |  | 0% | 0% | 0% |  | 0 |  | KMEP Domestic SC paid based on their progress completion
WA-M275 | - | ELEC | Pod | Various | Supply of Fire rated cable | Ali Haji Abdulla Awazi Gargash | 2022-10-31 | 2022-10-31 |  | 32000 |  | 93.12% | 0% | 93.12% | 29800 | 0 | 29800
WA-M276 | - | PL & DR | Pod | Ground Floor | Landscape MEP works | Various Suppliers | 2022-10-26 | 2022-10-31 |  | 45370.13 |  | 79.8% | 10.72% | 90.51% | 36203.39 | 4862.49 | 41065.88
WA-M277 | 1 | ELEC | Hot & Res | Various | Bus bar tap-off modification works | PPB Group FZE | 2022-11-10 | 2022-11-13 |  | 24362.14 |  | 0% | 0% | 0% |  | 0
WA-M278 | - | ELEC | Pod | Various | Identification labels for electrical services | Silver line | 2022-10-31 | 2022-10-31 |  | 5472 |  | 0% | 100% | 100% |  | 5472 | 5472
WA-M279 | - | PL & DR | Hot | L28 | Supply of GRP drip tray | Extra Co | 2022-10-31 | 2022-10-31 |  | 1245 |  | 0% | 0% | 0% |  | 0
WA-M280 | - | ELEC | Hot & Res | Various | Supply and installation of universal sockets and removal of exising sockets | Hospitality Solutions | 2022-10-31 | 2022-10-31 |  | 24200 |  | 0% | 0% | 0% |  | 0
WA-M281 | - | GENERAL | General | Various | Supply of consumable items | Various Suppliers | 2022-10-31 | 2022-10-31 |  | 35589.5 |  | 95.21% | 0% | 95.21% | 33885 | 0 | 33885
WA-M282 | - | ELEC | Pod | Landscape | Air freight charges for supply of light fixtures | Projects & Supplies | 2022-10-31 | 2022-10-31 |  | 34745 |  | 0% | 0% | 0% |  | 0 |  | PS - Light fittings
WA-M283 | - | PL & DR | Hot | Ball room | Supply of sanitarywares for ball room and disable toilets | Sanipex | 2022-10-31 | 2022-10-31 |  | 273529.24 |  | 3.95% | 0% | 3.95% | 10803.26 | 0 | 10803.26 | PS - Sanitarywares
WA-M284 | - | HVAC | Hot | Various | Chilled water pipe insulation | Korea & ME | 2022-10-31 | 2022-10-31 |  | 6883.4 |  | 100% | 0% | 100% | 6883.4 | 0 | 6883.4 |  | RBD
WA-M285 | - | [14 empty] | 0
WA-M286 | - | PL & DR | Hot | L1 Prayer room | Supply of ablution tapes and floor drains | Sanipex | 2022-11-01 | 2022-11-13 |  | 5640.81 |  | 100% | 0% | 100% | 5640.81 | 0 | 5640.81 | PS - Sanitarywares | RBD
WA-M287 | - | ELV works | Res | L23 | Disable Toilet Alarm System | SIS | 2022-11-01 |  |  | 8249 |  | 0% | 0% | 0% |  | 0 |  | PS - SIS
WA-M288 | - | PL & DR | Res | L4 | Supply of sanitarywares for changing room | Sanipex | 2022-11-01 | 2022-11-13 |  | 45018.32 |  | 1.886% | 0% | 1.886% | 849.13 | 0 | 849.13 | PS - Sanitarywares
WA-M289 | - | ELEC | Hot, Res, Pod & Bas | Various | Missing Emergency lights and components on site | ODS Global | 2022-11-08 | 2022-11-13 |  | 240000 |  | 59.1% | 0% | 59.1% | 141841.05 | 0 | 141841.05
WA-M290 | - | HVAC | General | General | Supply of welding rods for Chilled water works | Fine Tools | 2022-11-02 | 2022-11-13 |  | 2862 |  | 100% | 0% | 100% | 2862 | 0 | 2862 |  | RBD
WA-M291 | - | HVAC | General | General | Chilled water draining works for temporary pipe connection | Culligan International Emirates | 2022-11-02 | 2022-11-13 |  | 5750 |  | 0% | 0% | 0% |  | 0
WA-M292 | 1 | HVAC | Res | L23 | Supply of FAHU | Trosten Industries | 2023-01-04 |  |  | 63000 |  | 0% | 0% | 0% |  | 0
WA-M292 | - | HVAC | Res | L23 | Dismantling of exisitng FAHU | Mars Metal | 2022-11-03 |  |  | 9500 |  | 0% | 0% | 0% |  | 0
WA-M293 | - | HVAC | All | Various | Supply of nut and bolt | Bin Shakir | 2022-11-03 | 2022-11-13 |  | 1156.4 |  | 0% | 100% | 100% |  | 1156.4 | 1156.4
WA-M294 | - | ELV works | Hot | GF Ball room | Additional CCTV Cameras | SIS | 2022-11-03 | 2022-11-13 |  | 8427 |  | 0% | 0% | 0% |  | 0 |  | PS - SIS
WA-M295 | - | ELEC | General | Various | LV Switchgear modification as per DEWA | Arabian Gulf Switchgear | 2022-11-04 | 2022-11-13 |  | 116171 |  | 0% | 99.13% | 99.13% |  | 115159 | 115159
WA-M296 | 1 | HVAC | Hot | Presidential & Royal suites | Supply of Grilles and Diffusers | Tecnalco | 2022-12-13 |  |  | 6244.5 |  | 0% | 0.5765% | 0.5765% |  | 36 | 36
WA-M297 | - | HVAC | Res | Various | Supply of fire dampers | Prime A/C | 2022-11-07 | 2022-11-13 |  | 2837 |  | 85.9% | 0% | 85.9% | 2437 | 0 | 2437
WA-M298 | - | HVAC | Hot | Various | Supply of SS flexible and connector for FCU valve package | Advanced Technical | 2022-11-07 | 2022-11-13 |  | 1780 |  | 100% | 0% | 100% | 1780 | 0 | 1780 |  | RBD
WA-M299 | - | HVAC | Hot & Res | Various | Supply of BW & MI Fittings | Bisan building | 2022-11-07 | 2022-11-13 |  | 2848.72 |  | 0% | 0% | 0% |  | 0
WA-M300 | - | HVAC | Hot & Res | Various | Supply of D.I butterfly valve | Maunsell | 2022-11-07 | 2022-11-13 |  | 6510 |  | 68.75% | 0% | 68.75% | 4475.51 | 0 | 4475.51
WA-M301 | - | PL & DR | General | Various | Supply of UPVC pipes and fittings | Various Suppliers | 2022-11-14 |  |  | 52763.23 |  | 17.75% | 74.9% | 92.65% | 9367.5 | 39518.75 | 48886.25
WA-M302 | - | FP | General | Various | Additional cost for usage of existing FP system as temporary fire protection | Emirates Firefighting Equipment Factory (FIREX) | 2022-11-08 |  |  | 128250 |  | 0% | 0% | 0% |  | 0 |  | Direct works - FIREX
WA-M303 | - | ELEC | Hot | Retail areas | Cable pulling and Re-pulling | Muhammad Naeem | 2022-11-08 | 2022-11-13 |  | 18995 |  | 0% | 79.78% | 79.78% |  | 15155 | 15155
WA-M304 | - | ELEC | Hot | Retail areas | Supply of new cables | Cleveland Cable Trading FZCO | 2022-11-08 | 2022-11-13 |  | 114777.5 |  | 96.38% | 0% | 96.38% | 110627.3 | 0 | 110627.3
WA-M305 | - | ELEC | Hot | Retail areas | Supply of cable glands | Misterlight | 2022-11-09 | 2022-11-13 |  | 1330 |  | 100% | 0% | 100% | 1330 | 0 | 1330 |  | RBD
WA-M306 | - | ELEC | General | Various | LV Switchgear modification as per DEWA | Arabian Gulf Switchgear | 2022-11-09 | 2022-11-13 |  | 17788 |  | 0% | 78.01% | 78.01% |  | 13877 | 13877
WA-M307 | - | ELEC | B1 | Kitchen | Supply of Cables, Conduits and accessories | Various Suppliers | 2022-11-11 |  |  | 61281.53 |  | 7.378% | 7.876% | 15.25% | 4521.58 | 4826.35 | 9347.93
WA-M308 | - | PL & DR | General | Various | Supply, installation, testing and commissioning of circulation pumps | Faisal Jassim Trading |  |  |  | 33000 |  | 0% | 0% | 0% |  | 0 |  | Direct works - FJT
WA-M309 | - | ELEC | L2 | Landscape | Supply of Cables and accessories | Various Suppliers | 2022-11-11 |  |  | 48158.78 |  | 72.65% | 16.21% | 88.86% | 34985.2 | 7808.28 | 42793.48
WA-M310 | 1 | HVAC | General | Pod | Supply of GI Angle for chilled water support | Avadh Metal | 2022-11-10 |  |  | 21156 |  | 75.27% | 13.74% | 89.01% | 15924 | 2907 | 18831
WA-M311 | - | PL & DR | Res | L28 | Supply of flanges for water tank connection | Fikree pipe | 2022-11-11 | 2022-12-06 |  | 1140 |  | 0% | 100% | 100% |  | 1140 | 1140
WA-M312 | - | HVAC | Hot & Res | Various | Supply of split clamps | Kepco | 2022-11-11 | 2022-12-06 |  | 948.9 |  | 100% | 0% | 100% | 948.9 | 0 | 948.9 |  | RBD
WA-M313 | - | [11 empty] | 0% |  |  | 0
WA-M314 | - | ELEC | GF | LV Room | Supply of Rubber mat for LV Room | Misterlight | 2022-11-14 | 2022-12-06 |  | 5800 |  | 0% | 100% | 100% |  | 5800 | 5800
WA-M315 | - | LIFT | Pod | L1 & L2 | Dismantling and reinstallation works due to landing doors changes | KONE | 2022-11-14 |  |  | 5300 |  | 0% | 0% | 0% |  | 0 |  | PS - Kone
WA-M316 | - | ELEC | Pod | GF | Supply of electrical cables and accessories for GF Kitchen changes | Various Suppliers | 2022-11-14 |  |  | 4741.44 |  | 0% | 84.52% | 84.52% |  | 4007.7 | 4007.7
WA-M317 | - | HVAC | Res | L2, L4 | Supply of linear grills and diffusers | Tecnalco | 2022-11-14 | 2022-12-06 |  | 6148.5 |  | 0% | 0% | 0% |  | 0
WA-M318 | - | PL & DR | Res | L28 | Supply of UPVC materials for water tank and CDP works | Fikree pipe | 2022-11-15 | 2022-12-06 |  | 2785.64 |  | 100% | 0% | 100% | 2785.64 | 0 | 2785.64 |  | RBD
WA-M319 | 1 | HVAC | Hot | Guest Room | Supply of actuator for FCU link | ATS Advanced Technical Solutions | 2022-11-26 |  |  | 46612 |  | 0% | 0% | 0% |  | 0
WA-M320 | - | ELEC | B1 | Kitchen | Supply of Switch socket outlets | Ali Haji Abdulla Awazi Gargash | 2022-11-17 | 2022-12-06 |  | 1017 |  | 0% | 100% | 100% |  | 1017 | 1017
WA-M320 | - | ELEC | B1 | Kitchen | Supply of isolators | Sentor Electrical | 2022-11-17 | 2022-12-06 |  | 98.32 |  | 0% | 0% | 0% |  | 0
WA-M321 | - | HVAC | Hot & Res | Various | Supply of FAHU flexible connectors | Kinetics Middle East LLC | 2022-11-16 | 2022-12-06 |  | 2043.2 |  | 96.5% | 0% | 96.5% | 1971.68 | 0 | 1971.68
WA-M322 | - | PL & DR | Hot & Res | Various | Supply of Sanitary wares and accessories | Al Futtaim | 2022-11-16 |  |  | 13580 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M323 | - | PL & DR | Pod | L3 | Supply of sanitarywares for BoH and pantry areas | Sanipex | 2022-11-16 |  |  | 8681.66 |  | 33.03% | 0% | 33.03% | 2867.87 | 0 | 2867.87 | PS - Sanitarywares
WA-M324 | - | PL & DR | Hot, Res, Pod & Bas | Various | Supply of flexible connectors for domestic pump | Bisan building | 2022-11-17 |  |  | 6283.56 |  | 0% | 0% | 0% |  | 0
WA-M325 | - | PL & DR | Pod | Landscape | Supply of floor drain (Bespoke drain) | Hydro point | 2022-11-18 |  |  | 12330 |  | 0% | 88.89% | 88.89% |  | 10960 | 10960
WA-M326 | - | PL & DR | Hot | L18 FF Tank | Supply of Motorized valve for domestic system | Hydro point | 2022-11-17 | 2022-12-06 |  | 2705.6 |  | 0% | 100% | 100% |  | 2705.6 | 2705.6
WA-M327 | - | HVAC | Pod | Various | Supply of Chilled water supports | Kepco | 2022-11-17 |  |  | 757.26 |  | 0% | 0% | 0% |  | 0
WA-M328 | - | HVAC | General | Various | Supply of Glue for chilled water works | Hira Industries | 2022-11-18 |  |  | 5750 |  | 0% | 0% | 0% |  | 0
WA-M329 | - | ELEC | B1 | Kitchen area | Supply of Light Fittings | Genfocus | 2022-11-22 | 2022-12-06 |  | 13750 |  | 0% | 100% | 100% |  | 13750 | 13750 | PS - Light fittings
WA-M330 | - | ELEC | Pod | L4 Landscape | Supply of Conduits, Cables and accessories | Various Suppliers | 2022-11-23 |  |  | 64886.35 |  | 0% | 27.17% | 27.17% |  | 17630 | 17630
WA-M331 | - | HVAC | Pod & Bas | GF, B1, B2 | Supply of Grills and Diffusers | Tecnalco | 2022-11-22 | 2022-12-06 |  | 2483.5 |  | 0% | 0% | 0% |  | 0
WA-M332 | - | PL & DR | Pod | L3 | Supply of Sanitary wares | Sanipex | 2022-11-23 |  |  | 4056.19 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M333 | - | PL & DR | Res | L23 | Supply of Sanitary wares | Sanipex | 2022-11-23 | 2022-12-20 |  | 133444.86 |  | 0% | 0% | 0% |  | 0 |  | PS - Sanitarywares
WA-M334 | - | PL & DR | Res | Various | Supply of UPVC Drainage fittings | Corys Piping | 2022-11-23 |  |  | 18130.12 |  | 0% | 0% | 0% |  | 0
WA-M335 | - | ELEC | Pod | L3 | Supply of Wiring accessories | Ali Haji Abdulla Awazi Gargash | 2022-11-23 | 2022-12-06 |  | 291.5 |  | 0% | 0% | 0% |  | 0
WA-M335 | - | ELEC | Pod | L3 | Supply of Wiring accessories | SMKA Electric | 2022-11-23 | 2022-12-06 |  | 2997.72 |  | 0% | 88.21% | 88.21% |  | 2644.32 | 2644.32
WA-M336 | - | ELEC | Hot | L26 and L27 | Supply of MCB and ELCB | Arabian Gulf Switchgear | 2022-11-23 | 2022-12-06 |  | 1103 |  | 0% | 0% | 0% |  | 0
WA-M337 | - | HVAC | Pod & Bas | B1, L2, L3 | FCU repair works | MRI Technical | 2022-11-23 | 2022-12-06 |  | 1530 |  | 0% | 0% | 0% |  | 0
WA-M338 | - | HVAC | Hot | L2 & L4 | Supply of Grills and Diffusers | Tecnalco | 2022-11-22 |  |  | 15529 |  | 0% | 0% | 0% |  | 0
WA-M339 | - | HVAC | General | Various | Supply of Automatic Air Vents | Metallic Building Materials | 2022-12-12 |  |  | 5392.5 |  | 0% | 0% | 0% |  | 0
WA-M340 | - | [11 empty] | 0% |  |  | 0
WA-M341 | - | ELEC | General | Various | Switchgear modification works as per DEWA | Arabian Gulf Switchgear | 2022-11-25 | 2022-12-06 |  | 8006 |  | 0% | 100% | 100% |  | 8006 | 8006
WA-M342 | - | GENERAL | General | Various | Supply of PVC Engraved Labels for Cable identification | Al Manar Advertising | 2022-11-25 | 2022-12-06 |  | 1732.5 |  | 0% | 0% | 0% |  | 0
WA-M343 | - | ELEC | General | Various | Supply of Cables for LV & Boiler Room changes as per DEWA | Various Suppliers | 2022-11-29 |  |  | 16761.95 |  | 0% | 5.504% | 5.504% |  | 922.5 | 922.5
WA-M344 | - | ELEC | B1 | Pump room | MCC modification works | Arabian Gulf Switchgear | 2022-11-25 |  |  | 10120 |  | 0% | 100% | 100% |  | 10120 | 10120
WA-M345 | - | ELEC | Pod | Landscape | Supply of Interface unit for LCP | Gama Engineering | 2022-11-28 |  |  | 26810 |  | 0% | 0% | 0% |  | 0
WA-M346 | - | HVAC | Hot & Res | L28, 29 and 31 | Supply of KIMMCO pipe insulations | Leminar Air Conditioning | 2022-11-28 |  |  | 24507.2 |  | 0% | 0% | 0% |  | 0
WA-M347 | - | ELEC | Hot & Res | Various | Supply of 20A Flex outlet | SMKA Electric | 2022-11-28 | 2022-12-06 |  | 16362.8 |  | 0% | 62.79% | 62.79% |  | 10275 | 10275
WA-M348 | - | PL & DR | Hot | Various | Supply of UPVC Drainage fittings | Corys Piping | 2022-11-28 |  |  | 19938.32 |  | 0% | 0% | 0% |  | 0
WA-M349 | - | [11 empty] | 0% |  |  | 0
WA-M350 | - | [11 empty] | 0% |  |  | 0
WA-M351 | - | PL & DR | Hot & Res | WM & Plant Room | Supply of Gate valves | Fluid Control Trading | 2022-11-29 |  |  | 19144.51 |  | 0% | 76.95% | 76.95% |  | 14732.4 | 14732.4
WA-M352 | - | PL & DR | Res | L6, 29-31 | Supply of Acoustic insulation for Drain Pipe | Kinetics Middle East LLC | 2022-11-29 | 2022-12-06 |  | 8650 |  | 0% | 98.26% | 98.26% |  | 8499.5 | 8499.5
WA-M353 | - | ELEC | General | LV Room | Supply of Cable Lugs | Misterlight | 2022-11-29 | 2022-12-06 |  | 966 |  | 0% | 100% | 100% |  | 966 | 966
WA-M354 | - | ELEC | Res | L29-30 | Supply of Cable trunking with accessories | Isam Kabbani | 2022-11-29 | 2022-12-06 |  | 1481.3 |  | 0% | 100% | 100% |  | 1481.3 | 1481.3
WA-M355 | - | HVAC | Pod & Bas | Various | Supply of XLPE, Rock wool insulation | Various Suppliers | 2022-11-29 |  |  | 37424.58 |  | 0% | 86.89% | 86.89% |  | 32518.08 | 32518.08
WA-M356 | - | GENERAL | General | Various | Supply of Consumables | Leminar Air Conditioning | 2022-11-29 | 2022-12-13 |  | 9112.4 |  | 0% | 46.11% | 46.11% |  | 4202 | 4202
WA-M357 | - | GENERAL | General | Various | Supply of Consumables | Various Suppliers | 2022-12-05 |  |  | 25014.33 |  | 0% | 75.63% | 75.63% |  | 18919.33 | 18919.33
WA-M358 | - | PL & DR | Hot & Res | Various | Supply, installation, testing and commissioning of Mixing valve | Faisal Jassim Trading | 2022-12-06 |  |  | 400000 |  | 0% | 0% | 0% |  | 0 |  | Direct works - FJT
WA-M359 | - | GENERAL | General | Various | Supply of Site Consumable items for HSE team | Fine Tools | 2022-12-06 |  |  | 1462.71 |  | 0% | 92.24% | 92.24% |  | 1349.25 | 1349.25
WA-M360 | - | FP | Bas | Pump room | Supply and installation of Exhaust pipe and Thermal Insulation | Emirates Firefighting Equipment Factory (FIREX) | 2022-12-07 |  |  | 9000 |  | 0% | 0% | 0% |  | 0 |  | Direct works - FIREX
WA-M361 | - | GENERAL | Hot | Bond Electrical room | Supply and fixing of GRP drip tray | Al Majd Fiber Glass | 2022-12-10 |  |  | 4065 |  |  | 0%
WA-M362 | - | HVAC | Hot | Various | Supply of Rock wool insulation | Abdulla Al Zaabi | 2022-12-08 |  |  | 5604.48 |  |  | 0%
WA-M363 | - | ELEC | General | Various | Supply of Back boxes for Scokets | BMTC | 2022-12-08 |  |  | 6787.5 |  |  | 0%
WA-M364 | - | PL & DR | General | Various | Supply of Plumbing and Drainage materials | Various Suppliers | 2022-12-13 |  |  | 35860.84 |  |  | 0%
WA-M365 | - | HVAC | Hot | Various | Supply of Kitchen duct accessories and glue | Various Suppliers | 2022-12-08 |  |  | 10797 |  | 0% | 57.29% | 57.29% |  | 6185.5 | 6185.5
WA-M366 | - | ELEC | Pod | Various | Supply of Eletcrical accessories | Various Suppliers | 2022-12-16 |  |  | 4866 |  |  | 0%
WA-M367 | - | ELEC | Pod | Various | Supply of FOH and BOH face plates | Ali Haji Abdulla Awazi Gargash | 2022-12-13 |  |  | 7347.6 |  | 0% | 32.66% | 32.66% |  | 2400 | 2400
WA-M368 | - | HVAC | Pod | L1 Ablution rooms | Supply of 2no. of FCU | SMKA Electric | 2022-12-10 |  |  | 3600 |  |  | 0%
WA-M369 | - | PL & DR | Res & Pod | Various | Supply of MS Galvanized Backing Ring | Fikree pipe | 2022-12-08 |  |  | 3492 |  | 0% | 100% | 100% |  | 3492 | 3492
WA-M370 | 1 | ELEC | Res | Various | Supply of lights (FOH) | Projects & Supplies | 2022-12-13 |  |  | 77155 |  |  | 0% |  |  |  |  | PS - Light fittings
WA-M371 | - | ELEC | Res | Various | Supply of Single core wires and lugs | Safeline | 2022-12-10 |  |  | 23712.39 |  |  | 0%
WA-M372 | - | ELEC | Hot | FOH Guest Room | Supply of landscape lighting filling connectors | Nysa Electrical Trading | 2022-12-09 |  |  | 11760 |  | 0% | 43.1% | 43.1% |  | 5068 | 5068 | PS - Light fittings
WA-M373 | - | PL & DR | Res | WM Room | Supply of plumbing fixtures | Obaid Masood | 2022-12-09 |  |  | 1020 |  | 0% | 100% | 100% |  | 1020 | 1020
WA-M374 | - | HVAC | Pod | GF ETS Room | Supply of motorized butterfly valves | Maunsell | 2022-12-10 |  |  | 26600 |  |  | 0%
WA-M375 | - | [11 empty] | 0%
WA-M376 | - | ELEC | General | Various | MDB Modification works as per DEWA comments | Arabian Gulf Switchgear | 2022-12-10 |  |  | 54013 |  |  | 0%
WA-M377 | - | ELEC | General | Various | Supply of Electrical items as per DEWA comment | Various Suppliers | 2022-12-16 |  |  | 16443.75 |  | 0% | 24.79% | 24.79% |  | 4076.75 | 4076.75
WA-M378 | - | PL & DR | GF | Kitchen | Installation of Ecology unit | Trosten Industries | 2022-12-13 |  |  | 3500 |  |  | 0%
WA-M379 | - | ELEC | Hot | Ball room | Supply of LED strips | Projects & Supplies | 2022-12-13 |  |  | 3750 |  |  | 0% |  |  |  |  | PS - Light fittings
WA-M380 | - | [11 empty] | 0%
WA-M381 | - | HVAC | Pod | L3 & L4 | Supply of Grills and Diffusers | Tecnalco | 2022-12-17 |  |  | 5743 |  |  | 0%
WA-M382 | - | ELEC | Res | Various | Supply of identification labels for electrical panels | Silver line | 2022-12-15 |  |  | 264 |  |  | 0%
WA-M383 | - | ELEC | Res | Landscape at L10,23, 26 | Supply of rubber flexible cables | Electric Way | 2022-12-17 |  |  | 3734.1 |  |  | 0%
WA-M384 | - | [11 empty] | 0%
WA-M385 | - | [11 empty] | 0%
WA-M386 | - | [11 empty] | 0%
WA-M387 | - | ELEC | Bas | Various | Supply of slotted channels, Size-41mm | Power Max | 2022-12-15 |  |  | 1036.8 |  |  | 0%
WA-M388 | - | ELEC | Hot | L3 Management Office | Supply of 4 compartments floor box accessories | SMKA Electric | 2022-12-15 |  |  | 922.64 |  |  | 0%
WA-M389 | - | HVAC | B2, GF | ETS room - B2 | Supply of stud anchor bolt for Chilled water stress analysis system | Hilti Emirates | 2022-12-15 |  |  | 7503.1 |  |  | 0%
WA-M390 | - | ELEC | B1, GF | Kitchen area | Supply of Junction boxes | Al Ghandi | 2022-12-16 |  |  | 615 |  |  | 0%
WA-M391 | - | GENERAL | General | Various | Supply of Hand tools | Al Abbasi Fastners & hardware | 2022-12-15 |  |  | 65357.35 |  | 0% | 100% | 100% |  | 65357.35 | 65357.35 | Prelims - Measuring Tape, Spanner, Screw Driver and etc.,
WA-M392 | - | ELEC | L1 | Various | Supply of trunking covers and slotted channels | Various Suppliers | 2022-12-16 |  |  | 1991.23 |  |  | 0%
WA-M393 | - | HVAC | Pod & Bas | B1 & L5 | Supply of Aluminium Rectangular Ductwork | Seagull HVAC Industry | 2022-12-16 |  |  | 1360 |  |  | 0%
WA-M394 | - | HVAC | Hot & Res | B1, B2 & GF | Supply of Grills and Diffusers | Tecnalco | 2022-12-17 |  |  | 11521.5 |  |  | 0%
WA-M395 | - | GENERAL | General | B1 | Supply of GI Channel for ecology unit installation | Al Adil | 2022-12-17 |  |  | 3900 |  |  | 0%
WA-M396 | - | ELEC | Res | Various | Supply of cable cleats and lugs | Misterlight | 2022-12-17 |  |  | 976.5 |  |  | 0%
WA-M397 | - | ELV works |  | L3 | Additional outlets for time and attendance biometric data points | SIS | 2022-12-17 |  |  | 4307 |  | 0% | 0% | 0% |  | 0 |  | PS - SIS
WA-M398 | - | GENERAL | General | Various | Additional material murchase from IPC-Nov'22 | Various Suppliers | 2022-12-19 |  |  | 26540.65 |  | 0% | 100% | 100% |  | 26540.65 | 26540.65
WA-M399 | - | PL & DR | Bas | B2 & B1 | Pump room missing materials | Various Suppliers | 2022-12-22 |  |  | 6576.16 |  | 0% | 23.24% | 23.24% |  | 1528 | 1528
WA-M400 | - | GENERAL | General | Various | Supply of Aluminium Tape | Focus AC | 2022-12-19 |  |  | 10200 |  |  | 0%
WA-M401 | - | WA-M401 | - | WA-M401 | [8 empty] | 0%
WA-M402 | - | FP | GF | Retail areas | Supply and installation of monitor modules | Emirates Firefighting Equipment Factory (FIREX) | 2022-12-20 |  |  | 9200 |  |  | 0%
WA-M403 | - | ELEC | Hot | Various | Supply of additional materials for curtain motor power outlet modification works | Various Suppliers | 2022-12-22 |  |  | 10969.1 |  |  | 0%
WA-M404 | - | PL & DR | GF | SPA | Supply of CDP pipe works | Fikree pipe | 2022-12-21 |  |  | 1609.3 |  |  | 0%
WA-M405 | - | ELEC | Pod | L3 | Supply of floor boxes | SMKA Electric | 2022-12-23 |  |  | 8387.29 |  |  | 0%
WA-M406 | - | HVAC | General | Various | Supply of valves for BMS in chilled water system | Maunsell | 2022-12-20 |  |  | 2535 |  |  | 0%
WA-M407 | - | GENERAL | General | Various | Supply of PVC Engraved Labels | Al Manar Advertising | 2022-12-23 |  |  | 1100 |  |  | 0%
WA-M408 | - | GENERAL | General | Various | Supply of welding rods | Fine Tools | 2022-12-23 |  |  | 8100 |  |  | 0%
WA-M409 | - | HVAC | General | Various | Supply of HW valves and flexible connectors for AHU/ FAHU | Various Suppliers | 2022-12-23 |  |  | 13385.99 |  |  | 0%
WA-M410 | - | [11 empty] | 0% |  |  |  |  | Cancelled / Rejected
WA-M411 | - | PL & DR | Hot | L28 Gym | Supply of Sanitary wares and accessories for Disable Toilet | Sanipex | 2022-12-24 |  |  | 31401.7 |  |  | 0% |  |  |  |  | PS - Sanitarywares
WA-M412 | 1 | HVAC | Pod & Bas | Various | Supply of HVAC materials | Various Suppliers | 2022-12-30 |  |  | 20502.42 |  |  | 0%
WA-M413 | - | PL & DR | Pod | GF & L29 | Supply of Channel gratings | Tanseeq | 2022-12-24 |  |  | 7700 |  |  | 0%
WA-M414 | - | HVAC | General | Various | Supply of Vibration Isolators for Fans | Hira Industries | 2022-12-27 |  |  | 4603.08 |  |  | 0%
WA-M415 | - | ELEC | Hot | Guest Room Balcony | Supply of light filling connectors | Nysa Electrical Trading | 2022-12-27 |  |  | 2700 |  |  | 0%
WA-M416 | - | HVAC | Hot | L18 | Supply of VCD for L18 FAHU | Prime A/C | 2022-12-27 |  |  | 335 |  |  | 0%
WA-M417 | - | ELEC | Res | Balcony | Supply of power sockets | Bass Middle East | 2022-12-28 |  |  | 1680 |  |  | 0%
WA-M418 | - | [11 empty] | 0%
WA-M419 | - | ELEC | Bas | B1 & B2 | Supply of Cable tray cover | Isam Kabbani | 2022-12-29 |  |  | 2512.5 |  |  | 0%
WA-M419 | - | ELEC | Bas | B1 & B2 | Supply of Cable tray cover | Leminar Air Conditioning | 2022-12-29 |  |  | 595 |  |  | 0%
WA-M420 | - | GENERAL | General | Various | Supply of Site Consumable items | Various Suppliers | 2022-12-31 |  |  | 20199.9 |  |  | 0% |  |  | 0 |  | Prelims - Drill pit, Holesaw cutter, Garbage bag and etc.,
[5 empty] | TOTAL AMOUNT |  |  |  | 6850000 | 20663678.55 | 892511.93 |  |  |  | 8711890.9 | 2007162.215 | 10719053.115 |  | 51.87%
[9 empty] | MEP W.A BUDGET (A) | 6850000 | 144.3% |  |  | ITEMS | PROGRESS AMOUNT (AED) |  |  | WORK APPROVAL REF.
[9 empty] | CURRENT AGREED AMOUNT (B) | 20663678.55 |  |  |  |  | PREVIOUS | CURRENT | CUMULATIVE
[9 empty] | STAFF AMOUNT (C) | -1037386 |  |  |  | STAFF | -164400 | -27400 | -191800 | WA-M037, 047 | 18.49%
[9 empty] | PREMILS AMOUNT (D) | -613687.08 |  |  |  | PRELIMS | -463197 | -65357.35 | -528554.35 | WA-M012, 025, 046, 058, 069, 089, 092, 097, 117, 160, 188, 204, 249, 391, 420 | 86.13%
[9 empty] | HISTORICAL COST (E) | -892511.93 |  |  |  | HISTORICAL | -812072.34 | 12324.05 | -799748.29 | Historical Cost | 89.61%
[9 empty] | FIRE PROTECTION AMOUNT (F) | -163800 |  |  |  | FIREX | 0 | -19050 | -19050 | WA-M119, 247, 302, 360 | 11.63%
[9 empty] | BMS AMOUNT (G) | -13400 |  |  |  | JCI | 0 | 0 | 0 | WA-M158 | 0%
[9 empty] | HWS AMOUNT (H) | -799000 |  |  |  | FJT | 0 | 0 | 0 | WA-M253, 308, 358 | 0%
[9 empty] | PS LIFTS AMOUNT (H) | -106550 |  |  |  | KONE | -60750 | 0 | -60750 | WA-M141, 315 | 57.02%
[9 empty] | PS GRMS AMOUNT (I) | -4193 |  |  |  | CGT | 0 | 0 | 0 | WA-M157 | 0%
[9 empty] | PS ELV AMOUNT (J) | -986701.2 |  |  |  | SIS | -36704.25 | -61629.975 | -98334.225 | WA-M131, 139, 287, 294, 397 | 9.966%
[9 empty] | PS SANITARY (K) | -1746063.96 |  |  |  | SANITARYWARES | -195616.76 | -37946.1 | -233562.86 | WA-M078, 100, 137, 152, 153, 154, 155, 156, 210, 227, 240, 248, 283, 286, 288, 322, 323, 332, 333, 411 | 13.38%
[9 empty] | PS LIGHTING (L) | -4417716.18 |  |  |  | LIGHTS | -1213405.46 | -442669.48 | -1656074.94 | WA-M006, 008, 016, 027, 050, 074, 159, 176, 181, 200, 216, 223, 229, 231, 245, 254, 257, 282, 329, 370, 372, 379 | 37.49%
[9 empty] | WORK APPROVAL AMOUNT (M) = Sum(B to L) | 9882669.2 |  |  |  | WA-M Progress Amount | 5765745.09 | 1365433.36 | 7131178.45 | 72.16%
Note on U44: Agreed % for Work Completion upto RPJV Termination
Note on S218: Nazeer Ahamed: Actual Invpoce Value was 95,214 but 82,538 was agreed to pay under this work approval. Balance amount 12,676 will move to WA-M263
Note on S241: Nazeer Ahamed: Amount omitted to reach agreed W.A value
Note on S249: Nazeer Ahamed: AED 1,080 Custom Clearance taken from Prelims Petty cash

## E. Material
IPC-11 | MEP MATERIAL PURCHASES | [6 empty] | DIRECT WORKS
S.Nr | Description | Suppplier/ Subcontractor | Source | Category | Previous IPC Amount (AED) | Current Month Amount (AED) | Cumulative Amount (AED) | Remarks
1 | Heavy duty racks | Al Dhabi Al Sarea | June'22 IPA | MEP | 12333.4 | 0 | 12333.4
2 | XLPE sheet + printfoil | Ramesh Hira | July'22 IPA | MEP | 1252.8 | 0 | 1252.8
3 | Circuit breaker and double hook | Fine Tools | Aug'22 IPA | MEP | 7550 | 0 | 7550
4 | MEP consumable tools & accessories | Al Abbasi | Aug'22 IPA | MEP | 66000.85 | -65357.35 | 643.5 | Included under WA-M391
5 | Scaffolding | Crescent Scaffolding Industries | Sep'22 IPA | MEP | 1750 | 0 | 1750
6 | Padlock and enclosures | Sentor Electrical | Sep'22 IPA | MEP | 2521.91 | 0 | 2521.91
7 | Pipe insulation - 1-1/2" x 25mm | Korea ME | Oct'22 IPA | MEP | 353.7 | 0 | 353.7 | It may include under WA-M118 - Check
8 | FCU link | ATS Advanced Technical Solutions | Nov'22 IPA | MEP | 4700 | -4700 | 0 | Included under WA-M081
9 | Kitchen extract duct work | Seagull | Nov'22 IPA | MEP | 2533.28 | -2533.28 | 0 | Included under WA-M023
10 | GI nut, Bolt, washer and accessories | Leminar | Nov'22 IPA | MEP | 4416.5 | -4416.5 | 0 | Included under WA-M398
11 | GRP Drip Tray | Extra Co | Nov'22 IPA | MEP | 850 | 0 | 850 | It may include under WA-M279 - Check
12 | GI nut, Bolt, washer and accessories | Al Abbasi | Nov'22 IPA | MEP | 2648.5 | -2648.5 | 0 | Included under WA-M398
13 | Electrical Consumables Cables | Pioneers Electricals | Nov'22 IPA | MEP | 6805 | -6805 | 0 | Included under WA-M398
14 | Electrical Consumables PVC wires | Pioneers Electricals | Nov'22 IPA | MEP | 1927.5 | -1927.5 | 0 | Included under WA-M398
15 | Electrical Consumables PVC Conduits | BMTC | Nov'22 IPA | MEP | 1736.5 | -1736.5 | 0 | Included under WA-M398
16 | Electrical Consumables MCB | Riyal Electrical | Nov'22 IPA | MEP | 1575 | -1575 | 0 | Included under WA-M398
17 | Electrical Consumables Pull Spring | Fine Tools | Nov'22 IPA | MEP | 5733.65 | -5733.65 | 0 | Included under WA-M398
18 | Electrical Consumable accessories | Al Hathboor | Nov'22 IPA | MEP | 1140 | -1140 | 0 | Included under WA-M398
19 | MS and MI Pipe accessories | Ultimate Trading | Dec'22 IPA | MEP |  | 1175.86 | 1175.86
| Total Amount |  |  |  | 125828.59 | -97397.42 | 28431.17

## G. FP
Plot 18 - Dorchester | [8 empty] | DIRECT WORKS
IPC Ref | IPC-11
Package | Fire Protection
Subcontractor | FIREX
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
SUBCONTRACT WORKS
A | Fire protection pipe work | 1889158 | 1513467 | 80.11% | 375691 | 330757.8693 | 9242.9638 | 340000.8332 | 90.5% | 1853467.8332 | 98.11%
B | Valves and accessories | 251053 | 173544 | 69.13% | 77509 | 54273.6668 | 4423.2994 | 58696.9662 | 75.73% | 232240.9662 | 92.51%
C | Fire hose cabinets | 512583 | 415185 | 81% | 97398 | 73048.1493 | 0 | 73048.1493 | 75% | 488233.1493 | 95.25%
D | Sprinklers | 263633 | 196633 | 74.59% | 67000 | 34840.7187 | 17924.6869 | 52765.4055 | 78.75% | 249398.4055 | 94.6%
E | Breeching inlet | 15458 | 6956 | 45% | 8502 | 765.1413 | 2295.4239 | 3060.5652 | 36% | 10016.5652 | 64.8%
F | Fire extinguishers | 206069 | 0 | 0% | 206069 | 0 | 0 | 0 | 0% | 0 | 0%
G | Fire pumps | 58708 | 0 | 0% | 58708 | 48448.3134 | 4682.7925 | 53131.1059 | 90.5% | 53131.1059 | 90.5%
H | FM200 system | 432954 | 218589 | 50.49% | 214365 | 160361.4802 | 0 | 160361.4802 | 74.81% | 378950.4802 | 87.53%
I | Foam system | 66579 | 11984 | 18% | 54595 | 34394.9657 | 0 | 34394.9657 | 63% | 46378.9657 | 69.66%
J | Fire Alarm System | 1170993 | 750431 | 64.09% | 420562 | 240733.9585 | 27804.9133 | 268538.8718 | 63.85% | 1018969.8718 | 87.02%
K | Voice evacuation system | 397335 | 233876 | 58.86% | 163459 | 79757.1791 | 2295.1685 | 82052.3476 | 50.2% | 315928.3476 | 79.51%
Sub-Total (A) |  | 5264523 | 3520665 | 66.88% | 1743858 | 1057381.4423 | 68669.2482 | 1126050.6905 | 64.57% | 4646715.6905 | 88.26%
VARIATIONS
Addendum-1 | Variations approved by RPJV | 150000 | 45000 | 30% | 105000 | 85000 | 5000 | 90000 | 85.71% | 135000 | 90%
Sub-Total (B) |  | 150000 | 45000 | 30% | 105000 | 85000 | 5000 | 90000 |  | 135000 | 90%
SUBCONTRACT AMOUNT (C) = (A+B) |  | 5414523 | 3565665 | 65.85% | 1848858 | 1142381.4423 | 73669.2482 | 1216050.6905 | 65.77% | 4781715.6905 | 88.31%
WORK APPROVALS
WA-M119 | Removal and Reinstallation of Fire Fighting and Fire Alarm Works |  |  |  | 15000 | 0 | 7500 | 7500 | 50% | 7500
WA-M247 | Re-rouing of 6" wet riser interconnection |  |  |  | 11550 | 0 | 11550 | 11550 | 100%
WA-M302 | Additional cost for usage of existing FP system as temporary fire protection |  |  |  | 128250 | 0 | 0 | 0 | 0%
WA-M350 | Not Yet Submitted |  |  |  | 9000 |  |  |  | 0%
Sub-Total (D) |  | 0 | 0 |  | 163800 | 0 | 19050 | 19050 |  | 7500
ANTICIPATED SUBCONTRACT AMOUNT (E) = (C+D) |  | 5414523 | 3565665 | 65.85% | 2012658 | 1142381.4423 | 92719.2482 | 1235100.6905 | 61.37% | 4789215.6905 | 88.45%

## FF
FIRE FIGHTING WORKS | [26 empty] | FIREX
DORCHESTER PROJECT | [7 empty] | Breakdown | [10 empty] | Breakdown
S.N. | Description | Unit | Qty | Material Unit Price (AED) | Installation Unit Price (AED) | Unit Price (AED) | Total Price (AED) | Certified Under FM Subcontract |  |  | Certified Under RPJV Subcontract |  |  | Amount Under KHANSAHEB Subcontract |  |  | Amount Under KHANSAHEB Subcontract |  | Previous Months |  |  | Current Month |  |  | Cumulative
[8 empty] | S & I | T & C | Total | S & I | T & C | Total | S & I | T & C | Total | S&I | T & C | S & I | T & C | Total | S & I | T & C | Total | S & I | T & C | Total
[8 empty] | 90% | 10% | Amount | 90% | 10% | Amount | 90% | 10% | Amount | 90% | 10% | 90% | 10% | Amount | 90% | 10% | Amount | 90% | 10% | Amount
A | Fire Fighting Pipes | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 375691.5284; Previous Months Total: 330757.8693; Current Month Total: 9242.9638; Cumulative Total: 340000.8332
A1 | GI Pipe - 25mm | m | 7410 | 22 | Included | 22 | 163020 | 42.78% | 0% | 62762.7 | 47.73% | 0% | 77813.1685 | 9.49% | 100% | 22444.1315 | 20199.7184 | 2244.4132 | 90% | 40% | 19077.5118 | 5% | 10% | 1234.4272 | 95% | 50% | 20311.939
A2 | GI Pipe - 32mm | m | 5580 | 27 | Included | 27 | 150660 | 42.78% | 0% | 58004.1 | 49.28% | 0% | 74241.1552 | 7.945% | 100% | 18414.7448 | 16573.2703 | 1841.4745 | 90% | 40% | 15652.533 | 5% | 10% | 1012.811 | 95% | 50% | 16665.344
A3 | GI Pipe - 40mm | m | 6930 | 34 | Included | 34 | 235620 | 42.78% | 0% | 90713.7 | 49.79% | 0% | 117320.5783 | 7.43% | 100% | 27585.7217 | 24827.1496 | 2758.5722 | 90% | 40% | 23447.8635 | 5% | 10% | 1517.2147 | 95% | 50% | 24965.0782
A4 | GI Pipe - 50mm | m | 3860 | 40 | Included | 40 | 154400 | 42.78% | 0% | 59444 | 49.53% | 0% | 76481.7056 | 7.687% | 100% | 18474.2944 | 16626.8649 | 1847.4294 | 90% | 40% | 15703.1502 | 5% | 10% | 1016.0862 | 95% | 50% | 16719.2364
A5 | GI Pipe - 65mm | m | 4230 | 61 | Included | 61 | 258030 | 42.78% | 0% | 99341.55 | 47.94% | 0% | 123695.1528 | 9.284% | 100% | 34993.2972 | 31493.9675 | 3499.3297 | 90% | 40% | 29744.3026 | 5% | 10% | 1924.6313 | 95% | 50% | 31668.934
A6 | GI Pipe - 80mm | m | 2771 | 82 | Included | 82 | 227222 | 42.78% | 0% | 87480.47 | 49.28% | 0% | 111968.829 | 7.945% | 100% | 27772.701 | 24995.4309 | 2777.2701 | 95% | 40% | 24856.5674 | 0% | 10% | 277.727 | 95% | 50% | 25134.2944
A7 | GI Pipe - 100mm | m | 4415 | 110 | Included | 110 | 485650 | 42.78% | 0% | 186975.25 | 49.53% | 0% | 240565.6758 | 7.687% | 100% | 58109.0742 | 52298.1668 | 5810.9074 | 95% | 40% | 52007.6214 | 0% | 10% | 581.0907 | 95% | 50% | 52588.7121
A8 | GI Pipe - 150mm | m | 6986 | 200 | Included | 200 | 1397200 | 42.78% | 0% | 537922 | 49.48% | 0% | 691380.4364 | 7.739% | 100% | 167897.5636 | 151107.8073 | 16789.7564 | 95% | 40% | 150268.3194 | 0% | 10% | 1678.9756 | 95% | 50% | 151947.2951
B | Valves and Accessories | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 77508.4554; Previous Months Total: 54273.6668; Current Month Total: 4423.2994; Cumulative Total: 58696.9662
B1 | 6" Alarm Check Valve Assembly complete with Wet Alarm Valve (1 no.), Wet Alarm Valve Trim Kit (1 no.), Alarm Gong & Retard Chamber (UL) | Nr | 5 | 12861.8713 | Included | 12861.8713 | 64309.3563 | 80% | 0% | 46302.7365 | 14.94% | 0% | 9607.8178 | 5.06% | 100% | 8398.8019 | 7558.9217 | 839.8802 | 95% | 10% | 7264.9637 | 0% | 0% | 0 | 95% | 10% | 7264.9637
B2 | 8" OS & Y Gate Valve Flanged - 300 psi (UL/FM) | Nr | 1 | 1854.2531 | Included | 1854.2531 | 1854.2531 | 100% | 0% | 1668.8278 | 0% | 0% | 0 | 0% | 100% | 185.4253 | 166.8828 | 18.5425 | 95% | 10% | 160.3929 | 0% | 0% | 0 | 95% | 10% | 160.3929
B3 | 6" OS & Y Gate Valve Flanged - 300 psi (UL/FM) | Nr | 21 | 1127.5574 | Included | 1127.5574 | 23678.705 | 100% | 0% | 21310.8345 | 0% | 0% | 0 | 0% | 100% | 2367.8705 | 2131.0834 | 236.787 | 90% | 10% | 1941.6538 | 0% | 0% | 0 | 90% | 10% | 1941.6538
B4 | Tamper Switch (UL) | Nr | 22 | 482.3202 | Included | 482.3202 | 10611.0438 | 0% | 0% | 0 | 18% | 0% | 1909.9879 | 82% | 100% | 8701.0559 | 7830.9503 | 870.1056 | 90% | 10% | 7134.8658 | 0% | 0% | 0 | 90% | 10% | 7134.8658
B5 | 6" Butterfly Valve, Grooved Type - 300 psi (UL/FM) | Nr | 48 | 969.9995 | Included | 969.9995 | 46559.974 | 34.58% | 0% | 14491.7919 | 56.11% | 0% | 26123.6374 | 9.309% | 100% | 5944.5447 | 5350.0902 | 594.4545 | 90% | 10% | 4874.5266 | 0% | 0% | 0 | 90% | 10% | 4874.5266
B6 | 6" Water Flow Detector (UL) | Nr | 48 | 341.9114 | Included | 341.9114 | 16411.7477 | 34.58% | 0% | 5108.1565 | 56.11% | 0% | 9208.2214 | 9.309% | 100% | 2095.3699 | 1885.8329 | 209.537 | 90% | 10% | 1718.2033 | 0% | 0% | 0 | 90% | 10% | 1718.2033
B7 | 4" Butterfly Valve, Grooved Type - 300 psi (UL/FM) | Nr | 70 | 657.0273 | Included | 657.0273 | 45991.908 | 20.71% | 0% | 8574.2057 | 64.94% | 0% | 29864.8454 | 14.35% | 100% | 7552.8568 | 6797.5711 | 755.2857 | 90% | 10% | 6193.3426 | 0% | 0% | 0 | 90% | 10% | 6193.3426
B8 | 4" Water Flow Detector (UL) | Nr | 22 | 341.9114 | Included | 341.9114 | 7522.051 | 65.91% | 0% | 4461.9439 | 29.35% | 0% | 2207.8929 | 4.739% | 100% | 852.2142 | 766.9928 | 85.2214 | 90% | 10% | 698.8156 | 0% | 0% | 0 | 90% | 10% | 698.8156
B9 | 3" Butterfly Valve, Grooved Type - 300 psi (UL/FM) | Nr | 11 | 599.1488 | Included | 599.1488 | 6590.6372 | 0% | 0% | 0 | 81.9% | 0% | 5397.7319 | 18.1% | 100% | 1192.9053 | 1073.6148 | 119.2905 | 90% | 10% | 978.1824 | 0% | 0% | 0 | 90% | 10% | 978.1824
B10 | 3" Water Flow Detector (UL) | Nr | 1 | 341.9114 | Included | 341.9114 | 341.9114 | 0% | 0% | 0 | 90% | 0% | 307.7203 | 10% | 100% | 34.1911 | 30.772 | 3.4191 | 90% | 10% | 28.0367 | 0% | 0% | 0 | 90% | 10% | 28.0367
B11 | 2-½" Butterfly Valve, Grooved Type - 300 psi (UL/FM) | Nr | 9 | 542.3422 | Included | 542.3422 | 4881.0801 | 0% | 0% | 0 | 82.8% | 0% | 4041.5344 | 17.2% | 100% | 839.5458 | 755.5912 | 83.9546 | 90% | 10% | 688.4275 | 0% | 0% | 0 | 90% | 10% | 688.4275
B12 | 2-½" Water Flow Detector (UL) | Nr | 5 | 341.9114 | Included | 341.9114 | 1709.5571 | 0% | 0% | 0 | 82.8% | 0% | 1415.5132 | 17.2% | 100% | 294.0438 | 264.6394 | 29.4044 | 90% | 10% | 241.1159 | 0% | 0% | 0 | 90% | 10% | 241.1159
B13 | 1" Test and Drain Valve (UL/FM) | Nr | 72 | 188.6408 | Included | 188.6408 | 13582.1361 | 37.64% | 0% | 4600.9486 | 42.09% | 0% | 5717.2304 | 20.27% | 100% | 3263.9571 | 2937.5614 | 326.3957 | 90% | 10% | 2676.4448 | 0% | 0% | 0 | 90% | 10% | 2676.4448
B14 | Pressure Gauge (UL) | Nr | 97 | 232.5855 | Included | 232.5855 | 22560.794 | 0% | 0% | 0 | 68.4% | 0% | 15431.5831 | 31.6% | 100% | 7129.2109 | 6416.2898 | 712.9211 | 90% | 10% | 5845.9529 | 0% | 0% | 0 | 90% | 10% | 5845.9529
B15 | Spare Sprinkler full mild steel Cabinet with 24 nos. Sprinklers c/w Wrench | Nr | 2 | 1957.5378 | Included | 1957.5378 | 3915.0757 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 3915.0757 | 3523.5681 | 391.5076 | 0% | 10% | 39.1508 | 0% | 0% | 0 | 0% | 10% | 39.1508
B16 | Spare Sprinkler full mild steel Cabinet with 12 nos. Sprinklers c/w Wrench | Nr | 1 | 1080.5921 | Included | 1080.5921 | 1080.5921 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 1080.5921 | 972.5329 | 108.0592 | 0% | 10% | 10.8059 | 0% | 0% | 0 | 0% | 10% | 10.8059
B17 | Spare Sprinkler full mild steel Cabinet with 6 nos. Sprinklers c/w Wrench | Nr | 3 | 642.1192 | Included | 642.1192 | 1926.3575 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 1926.3575 | 1733.7218 | 192.6358 | 0% | 10% | 19.2636 | 0% | 0% | 0 | 0% | 10% | 19.2636
B18 | 6" Pressure Reducing Valve Station consists of (4 nos.) 6" OS & Y Valve, (4 nos.) pressure gauge, (2 nos.) 1" Pressure Relief Valve (UL) | Nr | 4 | 16976.5982 | Included | 16976.5982 | 67906.393 | 0% | 0% | 0 | 88.2% | 0% | 59893.4386 | 11.8% | 100% | 8012.9544 | 7211.6589 | 801.2954 | 95% | 10% | 6931.2055 | 0% | 0% | 0 | 95% | 10% | 6931.2055
B19 | 1" Air Release Valve | Nr | 25 | 40.8251 | Included | 40.8251 | 1020.6275 | 71.2% | 0% | 654.0181 | 18.63% | 0% | 190.1796 | 10.17% | 100% | 176.4298 | 158.7868 | 17.643 | 90% | 10% | 144.6724 | 0% | 0% | 0 | 90% | 10% | 144.6724
B20 | 1" Drain Valve | Nr | 10 | 348.507 | Included | 348.507 | 3485.0695 | 0% | 0% | 0 | 63.9% | 0% | 2226.9594 | 36.1% | 100% | 1258.1101 | 1132.2991 | 125.811 | 90% | 10% | 1031.6503 | 0% | 0% | 0 | 90% | 10% | 1031.6503
B21 | 3- Way Roof Manifold | Nr | 2 | 5725.4713 | Included | 5725.4713 | 11450.9427 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 11450.9427 | 10305.8484 | 1145.0943 | 50% | 10% | 5267.4336 | 40% | 0% | 4122.3394 | 90% | 10% | 9389.773
B22 | Extra Material: Automatic Fire Hose Reel 1" dia x 30 meter mild steel drum, swing type with plastic nozzle (LPCB/BSI) | Nr | 2 | 418 | Included | 418 | 836 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 836 | 752.4 | 83.6 | 50% | 10% | 384.56 | 40% | 0% | 300.96 | 90% | 10% | 685.52
C | Fire Hose Cabinets | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 97397.5324; Previous Months Total: 73048.1493; Current Month Total: 0; Cumulative Total: 73048.1493
C1 | Automatic Fire Hose Reel 1" dia x 30 meter mild steel drum, swing type with plastic nozzle (LPCB/BSI) | Nr | 240 | 418.2083 | 200 | 2508.2351 | 601976.4209 | 16.5% |  | 89393.4985 | 68.97% | 0% | 415185.39 | 14.53% | 100% | 97397.5324 | 87657.7791 | 9739.7532 | 80% | 30% | 73048.1493 | 0% | 0% | 0 | 80% | 30% | 73048.1493
C2 | 1" Pressure Reducing Valve | Nr |  | 79.6587 |  | 86.5609 | 0 | Cumulative Total: 0
C3 | 1" Lockshield Valve | Nr |  | 46.7995 |  | 50.8545 | 0 | Cumulative Total: 0
C4 | 2-½" Pressure Reducing Angle Valve with 2-½" Female NPT x 2-½" Female NST - chrome finish with adaptor, 175 PSI (UL/FM) | Nr |  | 527.7391 |  | 573.4657 | 0 | Cumulative Total: 0
C5 | 2-½" x 30 meter Fire Hose (UL/FM) | Nr |  | 438.123 |  | 476.0848 | 0 | Cumulative Total: 0
C6 | 2-½" Plastic Nozzle with Adoptor (BSI) - FX07-131B | Nr |  | 73.6843 |  | 80.0688 | 0 | Cumulative Total: 0
C7 | 2-½" Pin Rack, chrome finish | Nr |  | 321.6221 |  | 349.4895 | 0 | Cumulative Total: 0
C8 | Double Cabinet (empty), full mild steel, red powder coated, (Recessed type/Surface mounted), Size: 160 x 80 x 30 cm (Standard) | Nr |  | 402.3999 |  | 437.2664 | 0 | Cumulative Total: 0
D | Sprinklers | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 66999.8108; Previous Months Total: 34840.7187; Current Month Total: 17924.6869; Cumulative Total: 52765.4055
D1 | Standard Response Upright Sprinkler, glass bulb, 79 deg C, 1/2" orifice, 1/2" NPT, K-5.6, chrome finish (UL) | Nr | 4468 | 10.1823 | 10 | 20.1823 | 90174.5823 | 13.2% |  | 10712.7404 | 71.87% | 0% | 64805.5867 | 14.93% | 100% | 14656.2552 | 13190.6297 | 1465.6255 | 85% | 50% | 11944.848 | 0% | 0% | 0 | 85% | 50% | 11944.848
D2 | Quick Response Ordinary Recessed Pendent Sprinkler, with chrome finish double Escutcheon plate, glass bulb, 68 deg C, 1/2" orifice, 1/2" NPT, 5.6 K, chr finish (UL) | Nr | 4962 | 18.221 | 10 | 28.221 | 140032.524 | 13.2% |  | 16635.8639 | 68.35% | 0% | 95714.1906 | 18.45% | 100% | 27682.4695 | 24914.2226 | 2768.247 | 85% | 50% | 22561.2127 | 0% | 0% | 0 | 85% | 50% | 22561.2127
D3 | Standard Response Sidewall Sprinkler, glass bulb, 79 deg C, 1/2" orifice, 1/2" NPT, 5.6 K, chrome finish (UL) | Nr | 86 | 12.326 | 10 | 22.326 | 1920.0326 | 13.2% |  | 228.0999 | 61.71% | 0% | 1184.8751 | 25.09% | 100% | 507.0576 | 456.3518 | 50.7058 | 70% | 30% | 334.658 | 10% | 10% | 50.7058 | 80% | 40% | 385.3637
D4 | Quick Response Sidewall Sprinkler with chrome finish double Escutcheon plate, glass bulb, 68 deg C, 1/2" orifice, 1/2" NPT, 5.6 K, chrome finish (UL) | Nr | 252 | 24.6519 | 10 | 34.6519 | 8732.2838 | 13.2% |  | 1037.3953 | 60.15% | 0% | 5252.3639 | 26.65% | 100% | 2442.5246 | 2198.2721 | 244.2525 |  |  | 0 | 80% | 20% | 1807.4682 | 80% | 20% | 1807.4682
D5 | Quick Response Extended Coverage Sidewall Sprinkler head, glass bulb, 1/2", 68 deg C, with chrome finish double Escutcheon plate, K-5.6 (UL) | Nr | 425 | 72.8839 | 10 | 82.8839 | 35225.6733 | 13.2% |  | 4184.81 | 60.15% | 0% | 21187.8198 | 26.65% | 100% | 9853.0435 | 8867.7392 | 985.3044 |  |  | 0 | 80% | 20% | 7291.2522 | 80% | 20% | 7291.2522
D6 | Garbage Chute Sprinkler (UL) | Nr | 55 | 24.6519 | 10 | 34.6519 | 1905.8556 | 13.2% |  | 226.4156 | 54.68% | 0% | 1042.1295 | 32.12% | 100% | 637.3105 | 573.5794 | 63.731 |  |  | 0 | 80% | 20% | 471.6098 | 80% | 20% | 471.6098
D7 | Dry Pendent Sprinkler (UL) | Nr | 23 | 911.0492 | 10 | 921.0492 | 21184.1319 | 13.2% |  | 2516.6749 | 35.15% | 0% | 7446.3071 | 51.65% | 100% | 11221.1499 | 10099.035 | 1122.115 |  |  | 0 | 80% | 20% | 8303.651 | 80% | 20% | 8303.651
E | Breeching Inlet | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 8501.57; Previous Months Total: 765.1413; Current Month Total: 2295.4239; Cumulative Total: 3060.5652
E1 | 4 Way Breeching Inlet 6" (LPCB) | Nr | 4 | 908.615 | 250 | 3864.515 | 15458.06 | 0% | 0% | 0 | 45% | 0% | 6956.49 | 55% | 100% | 8501.57 | 7651.413 | 850.157 | 10% | 0% | 765.1413 | 30% | 0% | 2295.4239 | 40% | 0% | 3060.5652
E2 | 6" Swing Check Valve - 300 psi (UL/FM) | Nr | 4 | 1822.19 |  |  |  | Certified Under RPJV Subcontract Total: 0; Current Month S & I: 0%; Current Month T & C: 0%; Current Month Total: 0; Cumulative Total: 0
E3 | 4-Way Breeching Inlet Cabinet, recessed type, back box mild steel, Door and Frame stainless steel (SS316), brush finish with wired glass, Size: 60 x 60 x 30 cm | Nr | 4 | 883.71 |  |  |  | Certified Under RPJV Subcontract Total: 0; Current Month S & I: 0%; Current Month T & C: 0%; Current Month Total: 0; Cumulative Total: 0
F | Fire Extinguishers | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 206069.1729; Previous Months Total: 0; Current Month Total: 0; Cumulative Total: 0
F1 | 5 Kg CO2 Fire Extinguisher (BSI/Kitemark) | Nr | 366 | 159.3175 | Included | 159.3175 | 58310.1916 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 58310.1916 | 52479.1724 | 5831.0192 |  |  | 0 |  |  | 0 |  |  | 0
F2 | 6 Kg Dry Chemical Powder Fire Extinguisher (BSI/Kitemark) | Nr | 286 | 70.6971 | Included | 70.6971 | 20219.3776 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 20219.3776 | 18197.4398 | 2021.9378 |  |  | 0 |  |  | 0 |  |  | 0
F3 | 2 Kg CO2 Fire Extinguisher (BSI/Kitemark) | Nr | 279 | 81.6502 | Included | 81.6502 | 22780.4058 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 22780.4058 | 20502.3652 | 2278.0406 |  |  | 0 |  |  | 0 |  |  | 0
F4 | 9 Liters Water Fire Extinguisher (BSI/Kitemark) | Nr | 192 | 104.5521 | Included | 104.5521 | 20074.0004 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 20074.0004 | 18066.6003 | 2007.4 |  |  | 0 |  |  | 0 |  |  | 0
F5 | 25 Kg Dry Chemical Powder Trolley type Fire Extinguisher (BSI/Kitemark) | Nr | 5 | 649.2187 | Included | 649.2187 | 3246.0933 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 3246.0933 | 2921.484 | 324.6093 |  |  | 0 |  |  | 0 |  |  | 0
F6 | 6 Kg Dry Chemical Powder ABC9 Fire Extinguisher (Standard) | Nr | 124 | 74.6801 | Included | 74.6801 | 9260.3276 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 9260.3276 | 8334.2948 | 926.0328 |  |  | 0 |  |  | 0 |  |  | 0
F7 | 100 Liters Foam Trolley type Fire Extinguisher (LPCB) | Nr | 52 | 1169.9876 | Included | 1169.9876 | 60839.3563 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 60839.3563 | 54755.4207 | 6083.9356 |  |  | 0 |  |  | 0 |  |  | 0
F8 | 4' x 4' (1.2 x 1.2 mtr.) Fire Blanket (LPCB/BSI) | Nr | 219 | 51.7782 | Included | 51.7782 | 11339.4204 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 11339.4204 | 10205.4784 | 1133.942 |  |  | 0 |  |  | 0 |  |  | 0
G | Fire Fighting Pumps | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 58708.4043; Previous Months Total: 48448.3134; Current Month Total: 4682.7925; Cumulative Total: 53131.1059
G1 | Fire Pump Set (UL) 1,000 USGPM @ 16 Bars, 1 no. Electrical + 1 no. Diesel + 1 no. Jockey, with Control Panel @ B2 | Set | 1 | 271829.7291 | 26338.9047 | 298168.6338 | 298168.6338 | 100% | 0% | 268351.7704 | 0% | 0% | 0 | 0% | 100% | 29816.8634 | 26835.177 | 2981.6863 | 90% | 30% | 25046.1652 | 5% | 20% | 1938.0961 | 95% | 50% | 26984.2614
G3 | Fire Pump Set (UL) 1,000 USGPM @ 14 Bars, 1 no. Electrical + 1 no. Diesel + 1 no. Jockey, with Control Panel @ Lv18 H | Set | 1 | 262576.5044 | 26338.9047 | 288915.409 | 288915.409 | 100% | 0% | 260023.8681 | 0% | 0% | 0 | 0% | 100% | 28891.5409 | 26002.3868 | 2889.1541 | 90% | 0% | 23402.1481 | 5% | 50% | 2744.6964 | 95% | 50% | 26146.8445
H | FM 200 System | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 214365.4791; Previous Months Total: 160361.4802; Current Month Total: 0; Cumulative Total: 160361.4802
H1 | Main Tel. Room @ B1 Volume (196.91 m³ ) | Lot | 1 | 27021.5598 | 14401.6818 | 41423.2416 | 41423.2416 | 0% | 0% | 0 | 82.6% | 0% | 34215.5976 | 17.4% | 100% | 7207.644 | 6486.8796 | 720.7644 | 80% | 20% | 5333.6566 | 0% | 0% | 0 | 80% | 20% | 5333.6566
H2 | Main Server Room @ B1 Volume (309.02 m³) | Lot | 1 | 35600.9574 | 15710.9256 | 51311.883 | 51311.883 | 22.22% | 0% | 10262.3766 | 59.7% | 0% | 30633.1945 | 18.08% | 100% | 10416.3119 | 9374.6807 | 1041.6312 | 80% | 20% | 7708.0708 | 0% | 0% | 0 | 80% | 20% | 7708.0708
H3 | LV Room Apartment @ G/F Volume (828.78 m³ ) | Lot | 1 | 99521.7054 | 18984.0351 | 118505.7405 | 118505.7405 | 22.22% | 0% | 23701.1481 | 64.25% | 0% | 76139.9379 | 13.53% | 100% | 18664.6545 | 16798.1891 | 1866.4655 | 80% | 20% | 13811.8443 | 0% | 0% | 0 | 80% | 20% | 13811.8443
H4 | LV Room Hotel @ G/F Volume (848.58 m³ ) - | Lot | 1 | 102058.2497 | 18984.0351 | 121042.2848 | 121042.2848 | 22.22% | 0% | 24208.457 | 64.11% | 0% | 77600.2092 | 13.67% | 100% | 19233.6187 | 17310.2568 | 1923.3619 | 90% | 20% | 15963.9035 | 0% | 0% | 0 | 90% | 20% | 15963.9035
I1 | Security and Equipment Room @ B1 Volume (247.77m³) | Lot | 1 | 17649.25 | 8824.625 | 26473.875 | 26473.875 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 26473.875 | 23826.4875 | 2647.3875 | 90% | 20% | 21973.3162 | 0% | 0% | 0 | 90% | 20% | 21973.3162
I2 | FTR Room @ B2 Volume (69.34m³) | Lot | 1 | 17649.25 | 8824.625 | 26473.875 | 26473.875 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 26473.875 | 23826.4875 | 2647.3875 | 80% | 20% | 19590.6675 | 0% | 0% | 0 | 80% | 20% | 19590.6675
I3 | UPS Room @ B1 Volume (125.27m³) | Lot | 1 | 17649.25 | 8824.625 | 26473.875 | 26473.875 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 26473.875 | 23826.4875 | 2647.3875 | 80% | 20% | 19590.6675 | 0% | 0% | 0 | 80% | 20% | 19590.6675
I4 | GSM Room @ B1 Volume (78.975 m³) | Lot | 1 | 17649.25 | 8824.625 | 26473.875 | 26473.875 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 26473.875 | 23826.4875 | 2647.3875 | 80% | 20% | 19590.6675 | 0% | 0% | 0 | 80% | 20% | 19590.6675
I5 | FTR Room @ B1 Volume (124.135m³) | Lot | 1 | 17649.25 | 8824.625 | 26473.875 | 26473.875 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 26473.875 | 23826.4875 | 2647.3875 | 80% | 20% | 19590.6675 | 0% | 0% | 0 | 80% | 20% | 19590.6675
I6 | AV Suite & AV Equipment Control Room @ Level 1 Volume (69.06m³) | Lot | 1 | 17649.25 | 8824.625 | 26473.875 | 26473.875 | 0% | 0% | 0 | 0% | 0% | 0 | 100% | 100% | 26473.875 | 23826.4875 | 2647.3875 | 70% | 20% | 17208.0187 | 0% | 0% | 0 | 70% | 20% | 17208.0187
I | Foam System | [6 empty] | Amount Under KHANSAHEB Subcontract Total: 54595.1837; Previous Months Total: 34394.9657; Current Month Total: 0; Cumulative Total: 34394.9657
I1 | GENERATOR ROOM @ BASEMENT FLOOR AREA: 8.12 m x 7 m = 56.84 m² | Lot | 1 | 55400.5925 | 11178.9012 | 66579.4937 | 66579.4937 | 0% | 0% | 0 | 18% | 0% | 11984.31 | 82% | 100% | 54595.1837 | 49135.6653 | 5459.5184 | 70% |  | 34394.9657 | 0% | 0% | 0 | 70% |  | 34394.9657
|  | Total (AED) |  |  |  |  | 5697496.8864 | Certified Under FM Subcontract Total: 2001300.3522; Certified Under RPJV Subcontract Total: 2536359.3973; Amount Under KHANSAHEB Subcontract Total: 1159837.137; Previous Months Total: 736890.3047; Current Month Total: 38569.1665; Cumulative Total: 775459.4712
350591.2194

## FA
FIRE ALARM AND VOICE EVACUATION | [35 empty] | FIREX
DORCHESTER PROJECT | [9 empty] | Breakdown | [14 empty] | Breakdown
S.N. | Description | Unit | Qty | Material Unit Price (AED) | Cabling Unit Price (AED) | Device Installation Unit Price (AED) | T&C Unit Price (AED) | Unit Price (AED) | Total Price (AED) | Certified Under FM Subcontract |  |  |  | Certifiedt Under RPJV Subcontract |  |  |  | Progress % under KHANSAHEB Subcontract |  |  |  | Amount Under KHANSAHEB Subcontract |  |  | Previous |  |  |  | Current |  |  |  | Cumulative
[10 empty] | Supply & Installation of Device | Cabling | T & C | Total | Supply & Installation of Device | Cabling | T & C | Total | Supply & Installation of Device | Cabling | T & C | Total | Supply & Installation of Device | Cabling | T & C | Supply & Installation of Device | Cabling | T & C | Total | Supply & Installation of Device | Cabling | T & C | Total | Supply & Installation of Device | Cabling | T & C | Total
[10 empty] | % | % | % | Amount | % | % | % | Amount | % | % | % | [7 empty] | Amount |  |  |  | Amount |  |  |  | Amount
J | Fire Alarm System | [26 empty] | 240733.9585 |  |  |  | 27804.9133 |  |  |  | 268538.8718
J1 | Addressable Fire Alarm Repeater Panel (NRP) | Nr | 2 | 1248.5358 | 0 | 0 | 138.727 | 1387.2628 | 2774.5256 | 0% | 0% | 0% | 0 | 62% | 0% | 0% | 1548.18 | 38% | 0% | 100% | 1226.3456 | 948.9 | 0 | 277.454 | 65% | 65% | 0% | 616.785 | 0% | 0% | 0% | 0 | 65% | 90% | 0% | 616.785
J2 | Addressable Fire Alarm Control Panel 8 Loops with Battery | Nr | 4 | 11684.2036 | 0 | 0 | 1298.244 | 12982.4476 | 51929.7902 | 0% | 0% | 0% | 0 | 82% | 0% | 0% | 38324.19 | 18% | 0% | 100% | 13605.6002 | 8412.6266 | 0 | 5192.976 | 90% | 90% | 30% | 9129.2567 | 0% | 0% | 0% | 0 | 90% | 90% | 30% | 9129.2567
J3 | Network Card | Nr | 4 | 1209.042 | 0 | 0 | 134.338 | 1343.38 | 5373.52 | 0% | 0% | 0% | 0 | 67% | 0% | 0% | 3240.23 | 33% | 0% | 100% | 2133.29 | 1595.9354 | 0 | 537.352 | 70% | 70% | 0% | 1117.1548 | 0% | 0% | 0% | 0 | 70% | 90% | 0% | 1117.1548
J4 | Addressable Optical Smoke Detector with base | Nr | 2261 | 87.7676 | 100 | 30 | 27.3 | 245.0676 | 554097.8965 | 5% | 44.1% | 0% | 113023.7298 | 73.91% | 49.19% | 0% | 308024.03 | 21.09% | 6.71% | 100% | 133050.1367 | 56156.8906 | 15171.31 | 61721.94 | 85% | 90% | 40% | 86076.312 | 0% | 0% | 0% | 0 | 85% | 90% | 40% | 86076.312
J5 | Addressable Heat Detector-rate of rise with base | Nr | 468 | 85.0809 | 100 | 30 | 27.3 | 242.3809 | 113434.2422 | 5% | 44.1% | 0% | 23331.6921 | 69.33% | 44.16% | 0% | 58004.74 | 25.67% | 11.74% | 100% | 32097.8101 | 13825.3081 | 5496.1 | 12776.4 | 70% | 90% | 40% | 19734.7657 | 0% | 0% | 0% | 0 | 70% | 90% | 40% | 19734.7657
J6 | Addressable Smoke Detector with Sounder base | Nr | 492 | 168.3705 | 100 | 30 | 27.3 | 325.6705 | 160229.9071 | 5% | 44.1% | 0% | 26577.1154 | 66.62% | 49.47% | 0% | 89364.75 | 28.38% | 6.43% | 100% | 44288.0417 | 27698.3996 | 3163.56 | 13426.08 | 55% | 90% | 40% | 23451.7558 | 15% | 0% | 0% | 4154.7599 | 70% | 90% | 40% | 27606.5157
J7 | Addressable Combined Smoke & Heat Detector with base | Nr | 219 | 115.5309 | 100 | 30 | 27.3 | 272.8309 | 59749.9564 | 5% | 44.1% | 0% | 11251.4628 | 57.51% | 46.68% | 0% | 28553.17 | 37.49% | 9.224% | 100% | 19945.3236 | 11946.56 | 2020.056 | 5978.7 | 50% | 90% | 40% | 10182.8104 | 10% | 0% | 0% | 1194.656 | 60% | 90% | 40% | 11377.4664
J8 | Addressable Combined Smoke & Heat Detector with Sounder base | Nr | 30 | 196.1338 | 100 | 30 | 27.3 | 353.4338 | 10603.0131 | 5% | 44.1% | 0% | 1662.2007 | 23.5% | 26.55% | 0% | 2390.8 | 71.5% | 29.35% | 100% | 6550.0125 | 4850.51 | 880.5 | 819 | 55% | 80% | 40% | 3699.7805 | 15% | 10% | 0% | 815.6265 | 70% | 90% | 40% | 4515.407
J9 | Addressable Manual Break Glass | Nr | 199 | 97.6191 | 100 | 30 | 27.3 | 254.9191 | 50728.8992 | 5% | 44.1% | 0% | 10045.71 | 70.63% | 42.76% | 0% | 26448.11 | 24.37% | 13.14% | 100% | 14235.0792 | 6187.52 | 2614.86 | 5432.7 | 75% | 80% | 40% | 8905.608 | 0% | 10% | 0% | 261.486 | 75% | 90% | 40% | 9167.094
J10 | Addressable Manual Break Glass W/P | Nr | 35 | 343.9058 | 100 | 30 | 27.3 | 501.2058 | 17542.2026 | 5% | 44.1% | 0% | 2197.8351 | 42.5% | 29.91% | 0% | 6608.56 | 52.5% | 25.99% | 100% | 8735.8075 | 6870.5189 | 909.79 | 955.5 | 50% | 85% | 40% | 4590.7809 | 20% | 5% | 0% | 1419.5933 | 70% | 90% | 40% | 6010.3742
J11 | Addressable Sounder with Strobe | Nr | 11 | 145.0853 | 100 | 30 | 27.3 | 302.3853 | 3326.2378 | 5% | 44.1% | 0% | 581.3969 | 33.95% | 40.53% | 0% | 1099.65 | 61.05% | 15.37% | 100% | 1645.1909 | 1175.79 | 169.0975 | 300.3 | 55% | 85% | 40% | 910.5374 | 10% | 5% | 0% | 126.0339 | 65% | 90% | 40% | 1036.5712
J12 | Addressable Sounder with Strobe W/P | Nr | 51 | 391.372 | 100 | 30 | 27.3 | 548.672 | 27982.2696 | 5% | 44.1% | 0% | 3323.5985 | 43.45% | 34.94% | 0% | 11119.18 | 51.55% | 20.96% | 100% | 13539.4911 | 11078.0793 | 1069.0875 | 1392.32 | 30% | 90% | 40% | 4842.5306 | 30% | 0% | 0% | 3323.4238 | 60% | 90% | 40% | 8165.9544
J13 | Addressable Control Module - OUTPUT | Nr | 350 | 205.9852 | 100 | 30 | 27.3 | 363.2852 | 127149.8335 | 5% | 44.1% | 0% | 19564.7417 | 66.28% | 45.56% | 0% | 70694.11 | 28.72% | 10.34% | 100% | 36890.9818 | 23716.45 | 3619.525 | 9555 | 60% | 90% | 40% | 21309.4425 | 20% | 0% | 0% | 4743.29 | 80% | 90% | 40% | 26052.7325
J14 | Addressable Monitor Module (Dual Priority Switch) - INPUT | Nr | 160 | 131.6514 | 100 | 30 | 27.3 | 288.9514 | 46232.2296 | 5% | 44.1% | 0% | 8349.2115 | 64.9% | 45.56% | 0% | 24075.15 | 30.1% | 10.34% | 100% | 13807.8681 | 7785.23 | 1654.64 | 4368 | 60% | 90% | 40% | 7907.514 | 10% | 0% | 0% | 778.523 | 70% | 90% | 40% | 8686.037
J15 | Isolator | Nr | 350 | 44.7794 | 100 | 30 | 27.3 | 202.0794 | 70727.7899 | 5% | 44.1% | 0% | 16743.6395 | 66.26% | 39.41% | 0% | 31136.37 | 28.74% | 16.49% | 100% | 22847.7804 | 7522.0598 | 5770.72 | 9555 | 60% | 90% | 40% | 13528.8839 | 10% | 0% | 0% | 752.206 | 70% | 90% | 40% | 14281.0899
J16 | Remote Indicator | Nr | 573 | 18.8073 | 100 | 30 | 27.3 | 176.1073 | 100909.5103 | 5% | 44.1% | 0% | 26667.6305 | 59.6% | 40.53% | 0% | 39890.07 | 35.4% | 15.37% | 100% | 34351.8098 | 9900.47 | 8808.4425 | 15642.9 | 60% | 90% | 40% | 20125.0402 | 10% | 0% | 0% | 990.047 | 70% | 90% | 40% | 21115.0872
J17 | Linear Heat Detector Cable (120 mtrs.) | Nr | 1 | 18135.6599 | 0 | 0 | 2015.073 | 20150.7329 | 20150.7329 | 0% | 0% | 0% | 0 | 49% | 0% | 0% | 8886.47 | 51% | 0% | 100% | 11264.2629 | 9249.1865 | 0 | 2015.073 | 0% | 0% | 0% | 0 | 90% | 90% | 0% | 8324.2679 | 90% | 90% | 0% | 8324.2679
J18 | PC Graphic | Nr | 1 | 8621.2892 | 0 | 0 | 957.921 | 9579.2102 | 9579.2102 | 0% | 0% | 0% | 0 | 10% | 0% | 0% | 862.13 | 90% | 0% | 100% | 8717.0802 | 7759.1603 | 0 | 957.921 | 50% | 50% | 0% | 3879.5801 | 10% | 10% | 0% | 775.916 | 60% | 90% | 0% | 4655.4962
J19 | Printer | Nr | 1 | 1612.056 | 0 | 0 | 179.118 | 1791.174 | 1791.174 | 0% | 0% | 0% | 0 | 10% | 0% | 0% | 161.21 | 90% | 0% | 100% | 1629.964 | 1450.84 | 0 | 179.118 | 50% | 50% |  | 725.42 | 10% | 10% | 0% | 145.084 | 60% | 90% |  | 870.504
K | Voice Evacuation System | [26 empty] | 79757.1791 |  |  |  | 2295.1685 |  |  |  | 82052.3476
Paging Control Modules
K1 | 24 zone Paging selector modules, 2 switches per zone | Nr | 2 | 567.8131 | 0 | 0 | 63.0903 | 630.9034 | 1261.8069 | 0% | 0% | 0% | 0 | 28% | 0% | 0% | 317.98 | 72% | 0% | 100% | 943.8269 | 817.6509 | 0 | 126.1807 | 80% | 80% |  | 654.1207 | 0% | 0% | 0% | 0 | 80% | 80% |  | 654.1207
K2 | Mic and Master paging panel with microphone | Nr | 1 | 1616.8497 | 0 | 0 | 179.65 | 1796.4997 | 1796.4997 | 0% | 0% | 0% | 0 | 33% | 0% | 0% | 533.56 | 67% | 0% | 100% | 1262.9397 | 1083.2893 | 0 | 179.65 | 80% | 80% |  | 866.6314 | 0% | 0% | 0% | 0 | 80% | 80% |  | 866.6314
K3 | Backbox to the above with accessories | Nr | 1 | 810.7237 | 0 | 0 | 90.0804 | 900.8041 | 900.8041 | 0% | 0% | 0% | 0 | 33% | 0% | 0% | 267.54 | 67% | 0% | 100% | 633.2641 | 543.1849 | 0 | 90.08 | 80% | 80% |  | 434.5479 | 0% | 0% | 0% | 0 | 80% | 80% |  | 434.5479
K4 | Door for BB-5008 | Nr | 1 | 1084.2855 | 0 | 0 | 120.4762 | 1204.7616 | 1204.7616 | 0% | 0% | 0% | 0 | 33% | 0% | 0% | 357.81 | 67% | 0% | 100% | 846.9516 | 726.4713 | 0 | 120.4762 | 80% | 80% |  | 581.177 | 0% | 0% | 0% | 0 | 80% | 80% |  | 581.177
K5 | Mounting Kit Expander Chassis | Nr | 1 | 983.9029 | 0 | 0 | 109.3225 | 1093.2254 | 1093.2254 | 0% | 0% | 0% | 0 | 33% | 0% | 0% | 324.69 | 67% | 0% | 100% | 768.5354 | 659.2149 | 0 | 109.3225 | 80% | 80% |  | 527.3719 | 0% | 0% | 0% | 0 | 80% | 80% |  | 527.3719
K6 | 24 zone Paging selector modules, 2 switches per zone | Nr | 3 | 567.81 | 0 | 0 | 63.0903 | 630.9003 | 1892.701 | 0% | 0% | 0% | 0 | 33% | 0% | 0% | 562.13 | 67% | 0% | 100% | 1330.571 | 1141.2981 | 0 | 189.271 | 80% | 80% |  | 913.0385 | 0% | 0% | 0% | 0 | 80% | 80% |  | 913.0385
Audio Panels
K7 | Digitalized voice chip module (Evacuation message channel) |  | 1 | 1324.1309 | 0 | 0 | 147.1257 | 1471.2566 | 1471.2566 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 582.62 | 56% | 0% | 100% | 888.6366 | 741.5133 | 0 | 147.1257 | 80% | 80% |  | 593.2107 | 0% | 0% | 0% | 0 | 80% | 80% |  | 593.2107
K8 | Alert Message or manual voice chip(Max.4 minutes per chips record) |  | 1 | 763.2144 | 0 | 0 | 84.8016 | 848.016 | 848.016 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 335.81 | 56% | 0% | 100% | 512.206 | 427.4 | 0 | 84.8016 | 80% | 80% |  | 341.92 | 0% | 0% | 0% | 0 | 80% | 80% |  | 341.92
K9 | Audio /Fire Alarm System Interface Card c/w Fire Alarm Input & Audio Trouble Output, Paging MIC Input, Zone Paging Multiplex Input, One Interface Card per System Mounts in QMB-5101B Slot #1 (one for each 16 floors and one building) |  | 1 | 1583.1334 | 0 | 0 | 175.9037 | 1759.0371 | 1759.0371 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 696.58 | 56% | 0% | 100% | 1062.4571 | 886.5547 | 0 | 175.9037 | 80% | 80% |  | 709.2438 | 0% | 0% | 0% | 0 | 80% | 80% |  | 709.2438
K10 | Main Mother board and card cage (two each 16 floors and one building) |  | 5 | 1385.4333 | 0 | 0 | 153.937 | 1539.3703 | 7696.8517 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 3047.95 | 56% | 0% | 100% | 4648.9017 | 3879.2133 | 0 | 769.6852 | 80% | 80% |  | 3103.3706 | 0% | 0% | 0% | 0 | 80% | 80% |  | 3103.3706
K11 | Audio power supply (one for each QMP5000B) |  | 5 | 1168.5762 | 0 | 0 | 129.8418 | 1298.418 | 6492.0901 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 2570.87 | 56% | 0% | 100% | 3921.2201 | 3272.0134 | 0 | 649.209 | 80% | 80% |  | 2617.6107 | 0% | 0% | 0% | 0 | 80% | 80% |  | 2617.6107
K12 | External power supply |  | 5 | 1480.452 | 0 | 0 | 164.4947 | 1644.9466 | 8224.7331 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 3256.99 | 56% | 0% | 100% | 4967.7431 | 4145.2655 | 0 | 822.4733 | 80% | 80% |  | 3316.2124 | 0% | 0% | 0% | 0 | 80% | 80% |  | 3316.2124
K13 | battery charger up to 40AH (two for each QMB-5000B) |  | 5 | 629.8817 | 0 | 0 | 69.9869 | 699.8686 | 3499.343 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 1385.74 | 56% | 0% | 100% | 2113.603 | 1763.6689 | 0 | 349.9343 | 80% | 80% |  | 1410.9351 | 0% | 0% | 0% | 0 | 80% | 80% |  | 1410.9351
K14 | Audio Back box enclosure(Off White Door & Black Back Box) (two for each 16 floors use one) |  | 5 | 807.6586 | 0 | 0 | 89.7398 | 897.3984 | 4486.9921 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 1776.85 | 56% | 0% | 100% | 2710.1421 | 2261.444 | 0 | 448.6992 | 80% | 80% |  | 1809.1552 | 0% | 0% | 0% | 0 | 80% | 80% |  | 1809.1552
K15 | interlink cable (one for each QMB-5000B) |  | 5 | 81.9919 | 0 | 0 | 9.1102 | 91.1021 | 455.5106 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 180.38 | 56% | 0% | 100% | 275.1306 | 229.5773 | 0 | 45.5511 | 80% | 80% |  | 183.6619 | 0% | 0% | 0% | 0 | 80% | 80% |  | 183.6619
K16 | Audio Interconnection module (QIF to QIF) (No. as per QBB5001) |  | 5 | 935.6272 | 0 | 0 | 103.9586 | 1039.5858 | 5197.9292 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 2058.38 | 56% | 0% | 100% | 3139.5492 | 2619.7563 | 0 | 519.7929 | 80% | 80% |  | 2095.805 | 0% | 0% | 0% | 0 | 80% | 80% |  | 2095.805
K17 | 16 input interface board for floor above/below (each floor needs one input) |  | 5 | 379.3083 | 0 | 0 | 42.1454 | 421.4537 | 2107.2686 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 834.48 | 56% | 0% | 100% | 1272.7886 | 1062.0634 | 0 | 210.7269 | 80% | 80% |  | 849.6507 | 0% | 0% | 0% | 0 | 80% | 80% |  | 849.6507
K18 | Connection of Fire Alarm to Voice Panel (1 no. each QIF-5000B) |  | 1 | 1059.7645 | 0 | 0 | 117.7516 | 1177.5161 | 1177.5161 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 466.3 | 56% | 0% | 100% | 711.2161 | 593.4681 | 0 | 117.7516 | 80% | 80% |  | 474.7745 | 0% | 0% | 0% | 0 | 80% | 80% |  | 474.7745
K19 | Batteries for Voice Evacuation Panel |  | 1 | 7662.7948 | 0 | 0 | 851.4216 | 8514.2165 | 8514.2165 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 3371.63 | 56% | 0% | 100% | 5142.5865 | 4291.1651 | 0 | 851.4216 | 80% | 80% |  | 3432.9321 | 0% | 0% | 0% | 0 | 80% | 80% |  | 3432.9321
K20 | Transformer 200/110V (1 no. each QDV-1000) |  | 5 | 919.5354 | 0 | 0 | 102.1706 | 1021.706 | 5108.5299 | 0% | 0% | 0% | 0 | 44% | 0% | 0% | 2022.98 | 56% | 0% | 100% | 3085.5499 | 2574.6991 | 0 | 510.853 | 80% | 80% |  | 2059.7593 | 0% | 0% | 0% | 0 | 80% | 80% |  | 2059.7593
Amplifiers
K21 | 4 x 15W Amplifier | Nr | 16 | 1409.9542 | 0 | 0 | 156.6616 | 1566.6158 | 25065.8533 | 0% | 0% | 0% | 0 | 59% | 0% | 0% | 13309.77 | 41% | 0% | 100% | 11756.0833 | 9249.49 | 0 | 2506.5853 | 90% | 90% |  | 8324.541 | 0% | 0% | 0% | 0 | 90% | 90% |  | 8324.541
K22 | 2 x 30W Amplifier | Nr | 3 | 1322.5984 | 0 | 0 | 146.9554 | 1469.5538 | 4408.6613 | 0% | 0% | 0% | 0 | 59% | 0% | 0% | 2341 | 41% | 0% | 100% | 2067.6613 | 1626.796 | 0 | 440.8661 | 90% | 90% |  | 1464.1164 | 0% | 0% | 0% | 0 | 90% | 90% |  | 1464.1164
K23 | 1 x 60W Amplifier | Nr | 11 | 1259.7635 | 0 | 0 | 139.9737 | 1399.7372 | 15397.1091 | 0% | 0% | 0% | 0 | 59% | 0% | 0% | 8175.86 | 41% | 0% | 100% | 7221.2491 | 5681.54 | 0 | 1539.7109 | 90% | 90% |  | 5113.386 | 0% | 0% | 0% | 0 | 90% | 90% |  | 5113.386
Speakers
K24 | 1W Ceiling Speaker with back box | Nr | 743 | 127.7132 | 115 | 40 | 39.15 | 321.8632 | 239144.3927 | 6% | 45.2% | 0% | 46097.7966 | 72.96% | 49.25% | 0% | 133002.93 | 21.04% | 5.55% | 100% | 60043.6661 | 26214.6532 | 4742.1975 | 29086.82 | 80% | 50% | 0% | 23342.8213 | 0% | 20% | 0 | 948.4395 | 80% | 70% | 0 | 24291.2608
K25 | 1W Wall Speaker with back box | Nr | 173 | 127.7132 | 115 | 40 | 39.15 | 321.8632 | 55682.3418 | 6% | 45.2% | 0% | 10733.4035 | 47.58% | 43.77% | 0% | 22514.28 | 46.42% | 11.03% | 100% | 22434.6583 | 13467.29 | 2194.4185 | 6772.95 | 60% | 80% | 0% | 9835.9088 | 10% | 0% | 0 | 1346.729 | 70% | 80% | 0 | 11182.6378
Telephone Jack
K26 | Master fire fighter telephone | Nr | 1 | 1385.4333 | 0 | 0 | 153.937 | 1539.3703 | 1539.3703 | 0% | 0% | 0% | 0 | 2% | 0% | 0% | 27.71 | 98% | 0% | 100% | 1511.6603 | 1357.7246 | 0 | 153.937 | 60% | 60% | 0% | 814.6348 | 0% | 0% | 0% | 0 | 60% | 60% | 0 | 814.6348
K27 | 12 Zone fire fighter selector panel | Nr | 2 | 567.8131 | 0 | 0 | 63.0903 | 630.9034 | 1261.8069 | 0% | 0% | 0% | 0 | 2% | 0% | 0% | 22.71 | 98% | 0% | 100% | 1239.0969 | 1112.92 | 0 | 126.1807 | 60% | 60% | 0% | 667.752 | 0% | 0% | 0% | 0 | 60% | 60% | 0 | 667.752
K28 | Fire Telephone Jack | Nr | 245 | 47.6796 | 115 | 40 | 39.15 | 241.8296 | 59248.255 | 6% | 45.2% | 0% | 14023.9903 | 75.78% | 44.87% | 0% | 28921.37 | 18.22% | 9.93% | 100% | 16302.8947 | 3913.36 | 2797.7775 | 9591.75 | 60% | 20% | 0% | 2907.5715 | 0% | 0% | 0 | 0 | 60% | 20% | 0 | 2907.5715
K29 | Portable Handset (for each 16 floors use one) | Nr | 4 | 281.9908 | 0 | 0 | 31.3323 | 313.3232 | 1253.2927 | 0% | 0% | 0% | 0 | 54% | 0% | 0% | 609.1 | 46% | 0% | 100% | 644.1927 | 518.8632 | 0 | 125.3293 | 60% | 60% | 0% | 311.3179 | 0% | 0% | 0% | 0 | 60% | 60% | 0 | 311.3179
| FIRE ALARM | Total (AED) | [6 empty] | 1902503.113 |  |  |  | 334175.1548 |  |  |  | 984307.1 |  |  |  | 584020.8582 | [6 empty] | 320491.1376 |  |  |  | 30100.0818 |  |  |  | 350591.2194
775459.4712
3.61

## H. BMS
Plot 18 - Dorchester | [8 empty] | DIRECT WORKS
IPC Ref | IPC-11
Package | BMS Works
Subcontractor | Johnson Controls International
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
SUBCONTRACT WORKS
A | Field devices | 145777 | 93187 | 63.92% | 52590 | 921 | 0 | 921 | 1.751% | 94108 | 64.56%
B | Controllers | 223015 | 199419 | 89.42% | 23596 | 0 | 0 | 0 | 0% | 199419 | 89.42%
C | FCU communication with thermostat | 150329 | 74823 | 49.77% | 75506 | 35672 | 0 | 35672 | 47.24% | 110495 | 73.5%
D | FCU communication with return air temp. sensor | 19879 | 8145 | 40.97% | 11734 | 8800.5 | 0 | 8800.5 | 75% | 16945.5 | 85.24%
E | VAV | 7156 | 0 | 0% | 7156 | 5367 | 0 | 5367 | 75% | 5367 | 75%
F | Workstation with software and PC | 42714 | 0 | 0% | 42714 | 0 | 0 | 0 | 0% | 0 | 0%
G | Control cables | 452519 | 426293 | 94.2% | 26226 | 2079.0899 | 0 | 2079.0899 | 7.928% | 428372.0899 | 94.66%
H | Sundry design changes and VE included in RPJV subcontract | 104079 | 52040 | 50% | 52039 | 0 | 0 | 0 | 0% | 52040 | 50%
Sub-Total (A) |  | 1145468 | 853907 | 74.55% | 291561 | 52839.5899 | 0 | 52839.5899 | 18.12% | 906746.5899 | 79.16%
VARIATIONS
J | Variations instructed by RPJV under JCI-001 | 40000 | 10000 | 25% | 30000 | 0 | 0 | 0 | 0% | 10000 | 25%
K | BACnet MSTP communication loop to hotel spa at L28 | 36500 | 9125 | 25% | 27375 | 0 | 0 | 0 | 0%
L | Reversal of VE no. 2 including new panels / controllers | 33600 | 8400 | 25% | 25200 | 0 | 0 | 0 | 0%
M | Remobilization charge (incl. allowance for price increases) | 75000 | 48750 | 65% | 26250 | 13125 | 0 | 13125 | 50%
Sub-Total (B) |  | 185100 | 76275 | 41.21% | 108825 | 13125 | 0 | 13125 |  | 10000 | 5.402%
SUBCONTRACT AMOUNT (C) = (A+B) |  | 1330568 | 930182 | 69.91% | 400386 | 65964.5899 | 0 | 65964.5899 | 16.48% | 916746.5899 | 68.9%
WORK APPROVALS
WA-M158 | Supply of CO2 Sensors |  |  |  | 13400 | 0 | 0 | 0 | 0% | 0 | #DIV/0!
Sub-Total (D) |  | 0 | 0 |  | 13400 | 0 | 0 | 0 |  | 0 | #DIV/0!
ANTICIPATED SUBCONTRACT AMOUNT (E) = (C+D) |  | 1330568 | 930182 | 69.91% | 413786 | 65964.5899 | 0 | 65964.5899 | 15.94% | #REF! | #REF!
* LS Contract and claim break-up may change as per email from JCI on 07 Dec 2022

## JCI
BMS works | [16 empty] | Johnson Controls International
S.Nr | Description | Contract Scope |  |  |  | Certified amount under FM subcontract | Amount under RPJV subcontract | Progress completion at RPJV termination |  | Amount under KCE subcontract | Progress % |  |  | Progress Amount (AED) |  |  | Remarks
|  | Qty | Unit | Rate | Amount | [5 empty] | Previous | Current | Cumulative | Previous | Current | Cumulative
A | Field devices |  |  |  | 284306 | 138528.75 | 145777.25 | 63.92% | 93187.253 | 52589.997 |  |  |  | 921 | 0 | 921
A1 | Differential pressure transmitter - water | 2 | Nr | 1895 | 3790 | 3221.5 | 568.5 | 5% | 28.425 | 540.075 | 95% | 0% | 95% | 513.0712 | 0 | 513.0712 | D.N-630637
A2 | Flow meter | 2 | Nr | 17586 | 35172 |  | 35172 | 90% | 31654.8 | 3517.2 |  | 0% |  | 0 | 0 | 0
A3 | Wall mounted T/H sensor | 24 | Nr | 236 | 5664 | 1805.4 | 3858.6 | 58% | 2237.988 | 1620.612 |  | 0% |  | 0 | 0 | 0
A4 | Outside air T/H sensor | 1 | Nr | 2095 | 2095 | 1780.75 | 314.25 | 5% | 15.7125 | 298.5375 |  | 0% |  | 0 | 0 | 0
A5 | Duct T/RH sensor | 113 | Nr | 642 | 72546 | 50750.1 | 21795.9 | 20% | 4358.99 | 17436.91 |  | 0% |  | 0 | 0 | 0
A6 | Damper actuator - On/Off | 36 | Nr | 403 | 14508 | 12331.8 | 2176.2 | 5% | 108.81 | 2067.39 |  | 0% |  | 0 | 0 | 0
A7 | Network thermostat - temperature | 4 | Nr | 128 | 512 | 0 | 512 | 90% | 460.8 | 51.2 |  | 0% |  | 0 | 0 | 0
A8 | Differential pressure switch - water | 20 | Nr | 439 | 8780 | 5597.25 | 3182.75 | 26% | 827.515 | 2355.235 |  | 0% |  | 0 | 0 | 0
A9 | Level sensor | 4 | Nr | 1433 | 5732 | 4872.2 | 859.8 | 5% | 42.99 | 816.81 | 50% | 0% | 50% | 408.405 | 0 | 408.405
A10 | Immersion temperature sensor + thermowell | 222 | Nr | 133 | 29526 | 19670.7 | 9855.3 | 23% | 2266.719 | 7588.581 |  | 0% |  | 0 | 0 | 0
A11 | Duct temperature sensor | 7 | Nr | 57 | 399 | 242.25 | 156.75 | 29% | 45.4575 | 111.2925 |  | 0% |  | 0 | 0 | 0
A12 | CO sensor | 72 | Nr | 336 | 24192 | 15708 | 8484 | 25% | 2121 | 6363 |  | 0% |  | 0 | 0 | 0
A13 | Ambient CO2 sensor | 1 | Nr | 2003 | 2003 | 0 | 2003 | 90% | 1802.7 | 200.3 |  | 0% |  | 0 | 0 | 0
A14 | Differential pressure transmitter - air | 33 | Nr | 545 | 17985 | 0 | 17985 | 90% | 16186.5 | 1798.5 |  | 0% |  | 0 | 0 | 0
A15 | Air flow sensor | 36 | Nr | 879 | 31644 | 0 | 31644 | 90% | 28479.6 | 3164.4 |  | 0% |  | 0 | 0 | 0
A16 | Differential pressure switch - air | 205 | Nr | 117 | 23985 | 20387.25 | 3597.75 | 5% | 179.8875 | 3417.8625 |  | 0% |  | 0 | 0 | 0
A17 | Pressure transmitter | 11 | Nr | 178 | 1958 | 1513 | 445 | 13% | 57.85 | 387.15 |  | 0% |  | 0 | 0 | 0
A18 | Pressure sensor | 5 | Nr | 763 | 3815 | 648.55 | 3166.45 | 73% | 2311.5085 | 854.9415 |  | 0% |  | 0 | 0 | 0
B | Controllers |  |  |  | 235954.02 | 12939.41 | 223014.59 | 89.42% | 199418.59 | 23596 |  |  |  | 0 | 0 | 0
B1 | DDC panels & supervisory panels | 31 | Nr | 7611.42 | 235954.02 | 12939.41 | 223014.59 | 89.42% | 199418.59 | 23596 |  | 0 |  | 0 | 0 | 0
C | FCU Communication |  |  |  | 177125 | 26796.25 | 150328.75 | 49.77% | 74822.75 | 75506 |  |  |  | 35672 | 0 | 35672
C1 | BACnet/ MSTP Thermostat with display | 325 | Nr | 448 | 145600 | 0 | 145600 | 51% | 74256 | 71344 | 50% | 0% | 50% | 35672 | 0 | 35672 | D.N-630368
C2 | Transformer with PVC enclosure - enclosure box | 325 | Nr | 97 | 31525 | 26796.25 | 4728.75 | 12% | 566.75 | 4162 |  | 0% |  | 0 | 0 | 0 | D.N-630368
D | FCU Communication - with return air |  |  |  | 20474 | 595 | 19879 | 40.97% | 8145 | 11734 |  |  |  | 8800.5 | 0 | 8800.5
D1 | BACnet/ MSTP Controller | 58 | Nr | 266 | 15428 | 0 | 15428 | 51% | 7868.28 | 7559.72 | 75% | 0% | 75% | 5669.79 | 0 | 5669.79
D2 | Return air temperature sensor | 58 | Nr | 37 | 2146 | 0 | 2146 | 0% | 0 | 2146 | 75% | 0% | 75% | 1609.5 | 0 | 1609.5
D3 | PVC enclosure - enclosure box | 58 | Nr | 50 | 2900 | 595 | 2305 | 12% | 276.72 | 2028.28 | 75% | 0% | 75% | 1521.21 | 0 | 1521.21
E | VAV |  |  |  | 8992 | 1836 | 7156 | 0% | 0 | 7156 |  |  |  | 5367 | 0 | 5367
E1 | BACnet/ MSTP VAV controller | 16 | Nr | 418 | 6688 | 0 | 6688 | 0% | 0 | 6688 | 75% | 0% | 75% | 5016 | 0 | 5016
E2 | Network thermostat temperature | 16 | Nr | 106 | 1696 | 1351.5 | 344.5 | 0% | 0 | 344.5 | 75% | 0% | 75% | 258.375 | 0 | 258.375
E3 | Transformer | 16 | Nr | 38 | 608 | 484.5 | 123.5 | 0% | 0 | 123.5 | 75% | 0% | 75% | 92.625 | 0 | 92.625
F | Workstation with software and PC |  |  |  | 42714 | 0 | 42714 | 0% | 0 | 42714 |  |  |  | 0 | 0 | 0
F1 | BMS workstation with software | 1 | Nr | 33609 | 33609 | 0 | 33609 | 0% | 0 | 33609 |  | 0% |  | 0 | 0 | 0
F2 | Alarm printer | 1 | Nr | 1095 | 1095 | 0 | 1095 | 0% | 0 | 1095 |  | 0% |  | 0 | 0 | 0
F3 | Report printer | 1 | Nr | 1095 | 1095 | 0 | 1095 | 0% | 0 | 1095 |  | 0% |  | 0 | 0 | 0
F4 | Laptop | 1 | Nr | 5475 | 5475 | 0 | 5475 | 0% | 0 | 5475 |  | 0% |  | 0 | 0 | 0
F5 | Touch display | 2 | Nr | 720 | 1440 | 0 | 1440 | 0% | 0 | 1440 |  | 0% |  | 0 | 0 | 0
G | Control cables |  |  |  | 515435.8 | 62915.86 | 452519.39 | 94.2% | 426293.3888 | 26226.0012 |  |  |  | 2079.0899 | 0 | 2079.0899
G1 | BMS cables 3C-22AWG (rolls) | 50 | Nr | 363.96 | 18198 | 9899.71 | 8298.22 | 92% | 7634.3624 | 663.8576 |  | 0% |  | 0 | 0 | 0
G2 | BMS cables 2C-18AWG (rolls) | 325 | Nr | 397.94 | 129330.5 | 25368.68 | 103961.37 | 92% | 95645.0104 | 8316.3596 | 25% | 0% | 25% | 2079.0899 | 0 | 2079.0899
G3 | BMS cables 4C-18AWG (rolls) | 30 | Nr | 596.91 | 17907.3 | 10147.47 | 7759.8 | 92% | 7139.016 | 620.784 |  | 0% |  | 0 | 0 | 0
G4 | Installation including cable pulling and termination | 1 | Ls | 350000 | 350000 | 17500 | 332500 | 95% | 315875 | 16625 |  | 0% |  | 0 | 0 | 0
H | Sundry design changes and VE |  |  |  | 104079.2 | 0 | 104079.2 | 50% | 52040.2 | 52039 |  |  |  | 0 | 0 | 0
H1 | Sundry design changes and VE included in RPJV subcontract | 1 | Item | 104079.2 | 104079.2 | 0 | 104079.2 | 50% | 52040.2 | 52039 |  | 0 |  | 0 | 0 | 0
| Total amount |  |  |  | 1389080.02 | 243611.27 | 1145468.18 | 74.55% | 853907.1818 | 291560.9982 |  |  |  | 52839.5899 | 0 | 52839.5899
I | Variations |  |  |  | 185100 | 0 | 185100 |  | 76275 | 108825 |  |  |  | 13125 | 0 | 13125
J | Variations instructed by RPJV under JCI-001 | 1 | Item | 40000 | [12 empty] | RPJVPlot18Letter:LOI17052020_0006 (SI-001)
| Residence FCU thermostats and controllers including programming, graphis and database generation | 60 | Nr | 226 | 13560 | 0 | 13560 | 25% | 3390 | 10170 |  | 0% |  | 0 | 0 | 0
| Modification of FCU controllers cables | 1 | Ls | 7500 | 7500 | 0 | 7500 | 25% | 1875 | 5625 |  | 0% |  | 0 | 0 | 0
| Additional flow meter for Level 17 chilled water line | 1 | Ls | 15570 | 15570 | 0 | 15570 | 25% | 3892.5 | 11677.5 |  | 0% |  | 0 | 0 | 0
| DX Units controls | 1 | Ls | 3370 | 3370 | 0 | 3370 | 25% | 842.5 | 2527.5 |  | 0% |  | 0 | 0 | 0
K | BACnet MSTP communication loop to hotel spa at L28 | 1 | Item | 36500 | 36500 | 0 | 36500 | 25% | 9125 | 27375 |  | 0% |  | 0 | 0 | 0 | JCI quote ref. JCI/CON/DS/17102021-R0
L | Reversal of VE no. 2 including new panels / controllers | 1 | Item | 33600 | 33600 | 0 | 33600 | 25% | 8400 | 25200 |  | 0% |  | 0 | 0 | 0 | Email agreement
M | Remobilization charge (incl. allowance for price increases) | 1 | Item | 75000 | 75000 | 0 | 75000 | 65% | 48750 | 26250 | 50% | 0% | 50% | 13125 | 0 | 13125
-0.04
| Overall Amount |  |  |  | 1574180.02 | 243611.27 | 1330568.18 |  | 930182.1818 | 400385.9982 |  |  |  | 65964.5899 | 0 | 65964.5899

## I. Gas
Plot 18 - Dorchester | [8 empty] | DIRECT WORKS
IPC Ref | IPC-11
Package | LPG Works
Subcontractor | UGAZ Specialized Piping and Related Fitting Contracting LLC
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
SUBCONTRACT WORKS
A | LPG tank 500 gallons and accessories | 44800 | 22400 | 50% | 22400 | 21280 | 0 | 21280 | 95% | 43680 | 97.5%
B | Vaporizer and accessories | 28000 | 0 |  | 28000 | 0 | 0 | 0 | 0% | 0 | 0%
C | Filling line and accessories | 28000 | 0 |  | 28000 | 22400 | 2800 | 25200 | 90% | 25200 | 90%
D | Main PRDP and basement piping works | 33600 | 31920 | 95% | 1680 | 1512 | 0 | 1512 | 90% | 33432 | 99.5%
E | Risers for kitchen (Residential & Commercial) | 100800 | 90720 | 90% | 10080 | 8064 | 1008 | 9072 | 90% | 99792 | 99%
F | Kitchen upstream and downstream piping | 44800 | 40320 | 90% | 4480 | 3584 | 0 | 3584 | 80% | 43904 | 98%
G | Kitchen valve and accessories (Residential) | 56000 |  |  | 56000 | 28000 | 11200 | 39200 | 70% | 39200 | 70%
H | Domestic gas detector (Residential) | 28000 |  |  | 28000 | 14000 | 5600 | 19600 | 70% | 19600 | 70%
I | Gas meter accessories (commercial) | 56000 |  |  | 56000 | 28000 | 8400 | 36400 | 65% | 36400 | 65%
J | Gas leak detection system | 56000 |  |  | 56000 | 28000 | 5600 | 33600 | 60% | 33600 | 60%
K | Testing and commissioning | 56000 |  |  | 56000 | 0 | 0 | 0 | 0% | 0 | 0%
L | Civil defence inspection | 28000 |  |  | 28000 | 14000 | -14000 | 0 | 0% | 0 | 0%
Sub-Total (A) |  | 560000 | 185360 | 33.1% | 374640 | 168840 | 20608 | 189448 | 50.57% | 374808 | 66.93%
VARIATIONS
[5 empty] | 0 | 0 | 0 |  |  | 0 | #DIV/0!
Sub-Total (B) |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | #DIV/0!
SUBCONTRACT AMOUNT (C) = (A+B) |  | 560000 | 185360 | 33.1% | 374640 | 168840 | 20608 | 189448 | 50.57% | 374808 | 66.93%

## J. HWS
Plot 18 - Dorchester | [8 empty] | DIRECT WORKS
IPC Ref | IPC-11
Package | Hot Water System
Subcontractor | Faisal Jassim Trading Co. (L.L.C.)
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
SUBCONTRACT WORKS
A | Supply, testing and commissioning of hot water equipment | 2040000 | 2040000 | 100% | 0 |  | 0 | 0 | 0% | 2040000 | 100%
B | Supply, installation, testing and commissioning of hot water network | 1710000 | 1350900 | 79% | 359100 |  | 0 | 0 | 0% | 1350900 | 79%
Sub-Total (A) |  | 3750000 | 3390900 | 90.42% | 359100 | 0 | 0 | 0 | 0% | 3390900 | 90.42%
VARIATIONS
WA-M253 | Supply of PRV and valve connection to FAHU's |  |  |  | 366000 | 0 | 0 | 0 |  | 0 | #DIV/0!
WA-M308 | Supply, installation, testing and commissioning of circulation pumps |  |  |  | 33000 | 0 | 0 | 0
WA-M358 | Supply, installation, testing and commissioning of Mixing valve |  |  |  | 400000 | 0 | 0 | 0
Sub-Total (B) |  | 0 | 0 |  | 799000 | 0 | 0 | 0 |  | 0 | #DIV/0!
SUBCONTRACT AMOUNT (C) = (A+B) |  | 3750000 | 3390900 | 90.42% | 1158100 | 0 | 0 | 0 | 0% | 3390900 | 90.42%

## K. ELV
Plot 18 - Dorchester | [8 empty] | DIRECT WORKS
IPC Ref | IPC-11
Package | ELV Works
Subcontractor | SIS
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
SUBCONTRACT WORKS
A | Structured cabling system | 1289358 | 1133965 | 87.95% | 155393 | 0 | 20881 | 20881 | 13.44% | 1154846 | 89.57%
B | IPTV system | 615325 | 509890 | 82.87% | 105435 | 0 | 0 | 0 | 0% | 509890 | 82.87%
C | Active components for ICT N/W | 3120592 | 2611675 | 83.69% | 508917 | 0 | 46465 | 46465 | 9.13% | 2658140 | 85.18%
D | CCTV system | 1265148 | 921254 | 72.82% | 343894 | 3249 | 24182 | 27431 | 7.977% | 948685 | 74.99%
E | Access control system | 177143 | 130479 | 73.66% | 46664 | 0 | 0 | 0 | 0% | 130479 | 73.66%
F | Digital signage | 116386 | 54367 | 46.71% | 62019 | 0 | 0 | 0 | 0% | 54367 | 46.71%
G | Background music system | 863286 | 448335 | 51.93% | 414951 | 47178 | 24381 | 71559 | 17.25% | 519894 | 60.22%
H | Audio visual system | 694200 | 197534 | 28.45% | 496666 | 32202 | 0 | 32202 | 6.484% | 229736 | 33.09%
I | Gate barrier and intercom system | 18091 | 0 | 0% | 18091 | 0 | 0 | 0 | 0% | 0 | 0%
J | PABX system | 525800 | 408761 | 77.74% | 117039 | 0 | 0 | 0 | 0% | 408761 | 77.74%
K | UPS system | 150902 | 132053 | 87.51% | 18849 | 0 | 0 | 0 | 0% | 132053 | 87.51%
L | CCTV recording | 80000 | 70800 | 88.5% | 9200 | 0 | 0 | 0 | 0% | 70800 | 88.5%
Sub-Total (A) |  | 8916231 | 6619113 | 74.24% | 2297118 | 82629 | 115909 | 198538 | 8.643% | 6817651 | 76.46%
VARIATIONS
VO-7 | Additional Data Outlets for LCPs | 2531.3 | 1898.475 | 75% | 632.825 | 0 | 0 | 0 |  | 1898.475 | 75%
VO-8 | Additional BOH Offices and Basement 1 Kitchen Points | 77832.1 | 23349.63 | 30% | 54482.47 | 31133.25 | 1453.9354 | 32587.1854 |  | 55936.8154 | 71.87%
VO-9 | Additional Outlets for Engineering Office | 17614.24 | 3522.848 | 20% | 14091.392 | 7101.75 | 1318.134 | 8419.884 |  | 11942.732 | 67.8%
VO-10 | Additional Points in Level 3 | 11164.58 | 3349.3691 | 30% | 7815.2109 | 3680.25 | 1090.0594 | 4770.3094 |  | 8119.6785 | 72.73%
VO-16 | AV Cost Saving | -137198 | 0 | 0% | -137198 | -7197.2263 | -6921.3947 | -14118.621 |  | -14118.621 | 10.29%
VO-17 | Digital Signage Saving | -49878.18 | 0 | 0% | -49878.18 | -2616.5436 | -2516.2653 | -5132.8089 |  | -5132.8089 | 10.29%
VO-18 | Negotiations Adjustment | 79231.04 | 0 | 0% | 79231.04 | 4156.3559 | 3997.0648 | 8153.4208 |  | 8153.4208 | 10.29%
Sub-Total (B) |  | 1297.08 | 32120.3221 |  | -30823.2421 | 36257.8361 | -1578.4664 | 34679.3697 |  | 66799.6918 | 5150%
WORK APPROVALS
WA-M294 | Additional CCTV Cameras |  |  |  | 8427 | 0 | 0 | 0 | 0% | 0 | #DIV/0!
Sub-Total (C) |  | 0 | 0 |  | 8427 | 0 | 0 | 0 |  | 0 | #DIV/0!
SUBCONTRACT AMOUNT (D) = (A+B+C) |  | 8917528.08 | 6651233.3221 | 74.59% | 2274721.7579 | 118886.8361 | 114330.5336 | 233217.3697 | 10.25% | 6884450.6918 | 77.2%

## SIS
ELV Works | [19 empty] | SIS
S.Nr | Description | Qty | Unit | Rate | Amount | Certified amount under FM subcontract | Amount under RPJV subcontract | Progress completion at RPJV termination |  |  |  | Amount under KCE subcontract | Progress continuation after RPJV termination |  |  |  | Progress Amount (AED) |  |  | Remarks
[8 empty] | 75% | 15% | 10% | TOTAL |  | 75% | 15% | 10% | TOTAL | Previous | Current | Cumulative
A | Structured Cabling System |  |  |  | 1695631.0009 | 406272.959 | 1289358.0418 | 87.95% |  |  | 1133964.5709 | 155393 | 13.44% |  |  | 20881 | 0 | 20881 | 20881
Horizontal Cabling
1 | Single faceplate | 185 | Nr | 4 | 740 | 0 | 740 | 0% | 0% | 0% | 0 | 740 | 0% | 0% | 0% | 0 | 0 | 0 | 0
2 | Dual faceplate | 149 | Nr | 5 | 745 | 0 | 745 | 0% | 0% | 0% | 0 | 745 | 0% | 0% | 0% | 0 | 0 | 0 | 0
3 | RJ45 Modular Plug, 8P8C for Round Cable (C6A) with Boot | 1225 | Nr | 5.8824 | 7205.8824 | 0 | 7205.8824 | 100% | 50% | 0% | 5944.8529 | 1261.0294 | 100% | 60% | 0% | 108.0882 | 0 | 108.0882 | 108.0882
4 | 180° Cat6A Unshielded Modular Jack of RIDC | 609 | Nr | 23.5294 | 14329.4118 | 0 | 14329.4118 | 100% | 50% | 0% | 11821.7647 | 2507.6471 | 100% | 60% | 0% | 214.9412 | 0 | 214.9412 | 214.9412
5 | 180° Cat6A Unshielded Modular Jack of RIDC | 1786 | Nr | 23.5294 | 42023.5294 | 0 | 42023.5294 | 100% | 50% | 0% | 34669.4118 | 7354.1176 | 100% | 60% | 0% | 630.3529 | 0 | 630.3529 | 630.3529
6 | Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 1M, LSZH, Blue | 78 | Nr | 18 | 1404 | 0 | 1404 | 100% | 10% | 0% | 1074.06 | 329.94 | 100% | 50% | 0% | 84.24 | 0 | 84.24 | 84.24
7 | Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 412 | Nr | 25.8824 | 10663.5488 | 0 | 10663.5488 | 100% | 10% | 0% | 8157.6148 | 2505.934 | 100% | 50% | 0% | 639.8129 | 0 | 639.8129 | 639.8129
8 | Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 3M, LSZH, Blue | 1786 | Nr | 36 | 64296 | 0 | 64296 | 100% | 10% | 0% | 49186.44 | 15109.56 | 100% | 50% | 10% | 4500.72 | 0 | 4500.72 | 4500.72
9 | Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 10M, LSZH, Blue | 30 | Nr | 104 | 3120 | 0 | 3120 | 100% | 10% | 0% | 2386.8 | 733.2 | 100% | 50% | 10% | 218.4 | 0 | 218.4 | 218.4
10 | 1U, 24Port Cat 6A Patch Panel , unloaded | 130 | Nr | 66 | 8580 | 6435 | 2145 | 100% | 90% | 0% | 1898.325 | 246.675 | 100% | 90% | 13% | 27.885 | 0 | 27.885 | 27.885
11 | 1U, Cable Manager | 130 | Nr | 63 | 8190 | 4725 | 3465 | 100% | 90% | 0% | 3066.525 | 398.475 | 100% | 90% | 10% | 34.65 | 0 | 34.65 | 34.65
12 | Cat6A F/UTP 23 AWG LSZH cable | 400 | Nr | 683 | 273200 | 179287.5 | 93912.5 | 100% | 90% | 0% | 83112.5625 | 10799.9375 | 100% | 90% | 10% | 939.125 | 0 | 939.125 | 939.125
Backbone Cabling
13 | Multi Mode, OM3, 50/125um, 12 Core, Single LSZH | 21000 | Nr | 11.199 | 235179 | 20158.2 | 215020.8 | 100% | 90% | 50% | 201044.448 | 13976.352 | 100% | 90% | 50% | 0 | 0 | 0 | 0
14 | F/O Patch Cord, LC/LC Type, Duplex, OM3, 2m, LSZH | 116 | Nr | 49 | 5684 | 0 | 5684 | 100% | 70% | 5% | 4888.24 | 795.76 | 100% | 80% | 50% | 341.04 | 0 | 341.04 | 341.04
15 | F/O Patch Cord, LC/LC Type, Duplex, OM3, 3m, LSZH | 348 | Nr | 55 | 19140 | 0 | 19140 | 100% | 70% | 50% | 17321.7 | 1818.3 | 100% | 80% | 50% | 287.1 | 0 | 287.1 | 287.1
16 | F/O Patch Cord, LC/LC Type, Duplex, OM3, 10m, LSZH | 20 | Nr | 96.13 | 1922.6 | 0 | 1922.6 | 100% | 70% | 50% | 1739.953 | 182.647 | 100% | 80% | 50% | 28.839 | 0 | 28.839 | 28.839
17 | LC/APC, MM Duplex adapter | 1392 | Nr | 12.8676 | 17911.7013 | 0 | 17911.7013 | 100% | 90% | 50% | 16747.4407 | 1164.2606 | 100% | 90% | 50% | 0 | 0 | 0 | 0
18 | F/O Pig Tail, LC Type, Simplex, OM3, 1m, LSZH | 2784 | Nr | 15 | 41760 | 0 | 41760 | 100% | 90% | 50% | 39045.6 | 2714.4 | 100% | 90% | 50% | 0 | 0 | 0 | 0
19 | Heat shrink sleeve (Pack of 50) | 56 | Nr | 21.446 | 1200.9761 | 546.8731 | 654.1031 | 100% | 90% | 50% | 611.5864 | 42.5167 | 100% | 90% | 50% | 0 | 0 | 0 | 0
20 | 24 Port Fiber patch Panel | 58 | Nr | 210 | 12180 | 9135 | 3045 | 100% | 90% | 50% | 2847.075 | 197.925 | 100% | 90% | 50% | 0 | 0 | 0 | 0
21 | 48 Port Fiber patch Panel | 16 | Nr | 210 | 3360 | 0 | 3360 | 100% | 90% | 50% | 3141.6 | 218.4 | 100% | 90% | 50% | 0 | 0 | 0 | 0
22 | Patch panel accessories (Splice tray, cassette etc.) | 74 | Nr | 69 | 5106 | 3415.5 | 1690.5 | 100% | 90% | 50% | 1580.6175 | 109.8825 | 100% | 90% | 50% | 0 | 0 | 0 | 0
23 | 1U, Cable Manager | 74 | Nr | 63 | 4662 | 0 | 4662 | 100% | 90% | 50% | 4358.97 | 303.03 | 100% | 90% | 50% | 0 | 0 | 0 | 0
Voice backbone Cabling
24 | 50 Pair Cat 3 Cable in Meters | 5000 | Nr | 14.4933 | 72466.7128 | 0 | 72466.7128 | 100% | 90% | 0% | 64133.0408 | 8333.672 | 100% | 90% | 50% | 3623.3356 | 0 | 3623.3356 | 3623.3356
25 | 50‐Port Cat3 Voice Patch Panel | 29 | Nr | 300 | 8700 | 0 | 8700 | 100% | 90% | 0% | 7699.5 | 1000.5 | 100% | 90% | 50% | 435 | 0 | 435 | 435
26 | Cat-3 MDF Frame-1450 Pair | 1 | Nr | 1177 | 1177 | 0 | 1177 | 100% | 90% | 0% | 1041.645 | 135.355 | 100% | 90% | 50% | 58.85 | 0 | 58.85 | 58.85
2x2C OM4 from IDF to guest room
27 | Indoor, Multi Mode, OM3, 2 Core fiber cable | 35000 | m | 2.5882 | 90588.4 | 72778.7206 | 17809.6794 | 100% | 90% | 50% | 16652.0503 | 1157.6292 | 100% | 90% | 50% | 0 | 0 | 0 | 0
28 | F/O Patch Cord, LC/LC Type, Duplex, OM3, 1m, LSZH | 272 | Nr | 43.4451 | 11817.07 | 0 | 11817.07 | 100% | 0% | 0% | 8862.8025 | 2954.2675 | 100% | 50% | 45% | 1418.0484 | 0 | 1418.0484 | 1418.0484
29 | F/O Patch Cord, LC/LC Type, Duplex, OM3, 3m, LSZH | 272 | Nr | 55 | 14960 | 0 | 14960 | 100% | 0% | 0% | 11220 | 3740 | 100% | 50% | 45% | 1795.2 | 0 | 1795.2 | 1795.2
30 | LC/APC, MM Duplex adapter | 1088 | Nr | 12.8676 | 13999.9505 | 1273.8926 | 12726.0579 | 100% | 90% | 50% | 11898.8641 | 827.1938 | 100% | 90% | 50% | 0 | 0 | 0 | 0
31 | F/O Pig Tail, LC Type, Simplex, OM3, 1m, LSZH | 2176 | Nr | 14.4761 | 31499.9936 | 0 | 31499.9936 | 100% | 90% | 50% | 29452.494 | 2047.4996 | 100% | 90% | 50% | 0 | 0 | 0 | 0
32 | Heat Shrink sleeve (Pack of 50) | 44 | Pairs | 22 | 968 | 0 | 968 | 100% | 90% | 50% | 905.08 | 62.92 | 100% | 90% | 50% | 0 | 0 | 0 | 0
33 | Micro ODF | 272 | Nr | 65 | 17680 | 0 | 17680 | 100% | 90% | 50% | 16530.8 | 1149.2 | 100% | 90% | 50% | 0 | 0 | 0 | 0
34 | 48 Port Fiber patch Panel | 49 | Nr | 210 | 10290 | 0 | 10290 | 100% | 90% | 50% | 9621.15 | 668.85 | 100% | 90% | 50% | 0 | 0 | 0 | 0
35 | Patch panel accessories (Splice tray, cassette etc.) | 49 | Nr | 69 | 3381 | 0 | 3381 | 100% | 90% | 50% | 3161.235 | 219.765 | 100% | 90% | 50% | 0 | 0 | 0 | 0
36 | 1U, Cable Manager | 49 | Nr | 63 | 3087 | 0 | 3087 | 100% | 90% | 50% | 2886.345 | 200.655 | 100% | 90% | 50% | 0 | 0 | 0 | 0
ISP Network
37 | Micro ODF | 54 | Nr | 65 | 3510 | 0 | 3510 | 100% | 90% | 50% | 3281.85 | 228.15 | 100% | 90% | 50% | 0 | 0 | 0 | 0
38 | Single Mode, 9/125um, 24 Core, Single LSZH Jacket | 2000 | m | 5.2353 | 10470.6 | 7852.95 | 2617.65 | 100% | 90% | 0% | 2316.6202 | 301.0297 | 100% | 90% | 0% | 0 | 0 | 0 | 0
39 | Single Mode, 9/125um, 6 Core, Single LSZH Jacket | 1000 | m | 3 | 3000 | 2250 | 750 | 100% | 90% | 0% | 663.75 | 86.25 | 100% | 90% | 0% | 0 | 0 | 0 | 0
40 | Single Mode, 9/125um, 4 Core, Single LSZH Jacket | 3000 | m | 3 | 9000 | 7515 | 1485 | 100% | 90% | 0% | 1314.225 | 170.775 | 100% | 90% | 0% | 0 | 0 | 0 | 0
41 | 1U, 24Port Cat 6A Patch Panel , unloaded | 39 | m | 77.74 | 3031.8595 | 991.1848 | 2040.6747 | 100% | 90% | 50% | 1908.0308 | 132.6439 | 100% | 90% | 50% | 0 | 0 | 0 | 0
42 | 1U, Cable Manager | 39 | Nr | 62.3529 | 2431.7647 | 0 | 2431.7647 | 100% | 90% | 50% | 2273.7 | 158.0647 | 100% | 90% | 50% | 0 | 0 | 0 | 0
43 | F/O Patch Cord, SCAPC to SCAPC, Duplex,SM, 1m,LSZH | 54 | Nr | 43 | 2322 | 0 | 2322 | 100% | 90% | 50% | 2171.07 | 150.93 | 100% | 90% | 50% | 0 | 0 | 0 | 0
44 | F/O Patch Cord, SCAPC to SCAPC, Duplex,SM, 5m,LSZH | 68 | Nr | 62 | 4216 | 0 | 4216 | 100% | 90% | 50% | 3941.96 | 274.04 | 100% | 90% | 50% | 0 | 0 | 0 | 0
45 | F/O Patch Cord, LCAPC to SCAPC, Duplex,SM, 1m,LSZH | 54 | Nr | 46 | 2484 | 0 | 2484 | 100% | 90% | 50% | 2322.54 | 161.46 | 100% | 90% | 50% | 0 | 0 | 0 | 0
46 | F/O Patch Cord, LCAPC to SCAPC, Duplex,SM, 5m,LSZH | 68 | Nr | 67 | 4556 | 0 | 4556 | 100% | 90% | 50% | 4259.86 | 296.14 | 100% | 90% | 50% | 0 | 0 | 0 | 0
47 | SCAPC SM Simplex Adapter- Ziconia, SM | 108 | Nr | 5 | 540 | 0 | 540 | 100% | 90% | 50% | 504.9 | 35.1 | 100% | 90% | 50% | 0 | 0 | 0 | 0
48 | LCAPC SM Duplex Adapter- Ziconia, SM | 303 | Nr | 10 | 3030 | 0 | 3030 | 100% | 90% | 50% | 2833.05 | 196.95 | 100% | 90% | 50% | 0 | 0 | 0 | 0
49 | LCAPC SM Duplex Adapter | 60 | Nr | 14 | 840 | 0 | 840 | 100% | 90% | 50% | 785.4 | 54.6 | 100% | 90% | 50% | 0 | 0 | 0 | 0
50 | SC/APC, SM Pigtail 1M | 714 | Nr | 9 | 6426 | 1782 | 4644 | 100% | 90% | 50% | 4342.14 | 301.86 | 100% | 90% | 50% | 0 | 0 | 0 | 0
51 | LC/APC, SM Pigtail 1M | 120 | Nr | 10 | 1200 | 0 | 1200 | 100% | 90% | 50% | 1122 | 78 | 100% | 90% | 50% | 0 | 0 | 0 | 0
52 | Heat shrink sleeve (Pack of 50) | 17 | Nr | 22 | 374 | 0 | 374 | 100% | 90% | 50% | 349.69 | 24.31 | 100% | 90% | 50% | 0 | 0 | 0 | 0
53 | 48 Core Fiber patch Panel, SC Duplex | 7 | Nr | 210 | 1470 | 0 | 1470 | 100% | 90% | 50% | 1374.45 | 95.55 | 100% | 90% | 50% | 0 | 0 | 0 | 0
54 | 24 port Fiber patch Panel | 8 | Nr | 210 | 1680 | 1260 | 420 | 100% | 90% | 50% | 392.7 | 27.3 | 100% | 90% | 50% | 0 | 0 | 0 | 0
55 | 25 port Fiber patch Panel | 2 | Nr | 210 | 420 | 0 | 420 | 100% | 90% | 50% | 392.7 | 27.3 | 100% | 90% | 50% | 0 | 0 | 0 | 0
56 | Patch panel accessories (Splice tray, cassette etc.) | 17 | Nr | 69 | 1173 | 0 | 1173 | 100% | 90% | 50% | 1096.755 | 76.245 | 100% | 90% | 50% | 0 | 0 | 0 | 0
57 | 1U, Cable Manager | 17 | Nr | 63 | 1071 | 0 | 1071 | 100% | 90% | 50% | 1001.385 | 69.615 | 100% | 90% | 50% | 0 | 0 | 0 | 0
58 | SCAPC Splitter_2 x 2 way -Etisalat | 2 | Nr | 1341 | 2682 | 0 | 2682 | 100% | 90% | 50% | 2507.67 | 174.33 | 100% | 90% | 50% | 0 | 0 | 0 | 0
59 | LCAPC Splitter_2 x 2 way -Du | 2 | Nr | 1609 | 3218 | 0 | 3218 | 100% | 90% | 50% | 3008.83 | 209.17 | 100% | 90% | 50% | 0 | 0 | 0 | 0
60 | MINI ODF Splice Cabinet | 8 | Nr | 306 | 2448 | 0 | 2448 | 100% | 90% | 50% | 2288.88 | 159.12 | 100% | 90% | 50% | 0 | 0 | 0 | 0
Cabinets
61 | 12U x 600 x 300 Depth _Commercial & Residential | 287 | Nr | 295 | 84665 | 61861.5 | 22803.5 | 100% | 90% | 50% | 21321.2725 | 1482.2275 | 100% | 90% | 50% | 0 | 0 | 0 | 0
62 | 12U x 600 x 150 Depth _Commercial & Residential | 6 | Nr | 200 | 1200 | 0 | 1200 | 100% | 90% | 50% | 1122 | 78 | 100% | 90% | 50% | 0 | 0 | 0 | 0
63 | 15u X 600 X 600 Depth_IDF Cabinet | 29 | Nr | 924 | 26796 | 0 | 26796 | 100% | 90% | 50% | 25054.26 | 1741.74 | 100% | 90% | 50% | 0 | 0 | 0 | 0
64 | 45u X 800 X 1000 Depth_IDF Cabinet | 29 | Nr | 3236 | 93844 | 0 | 93844 | 100% | 90% | 50% | 87744.14 | 6099.86 | 100% | 90% | 50% | 0 | 0 | 0 | 0
65 | 47u X 950 X 450 Depth_ ISP Rack | 2 | Nr | 3353 | 6706 | 0 | 6706 | 100% | 90% | 50% | 6270.11 | 435.89 | 100% | 90% | 50% | 0 | 0 | 0 | 0
66 | 45u X 800 X 1000 Depth _MDF | 14 | Nr | 3236 | 45304 | 0 | 45304 | 100% | 90% | 50% | 42359.24 | 2944.76 | 100% | 90% | 50% | 0 | 0 | 0 | 0
67 | Earthing Kit | 43 | Nr | 59 | 2537 | 0 | 2537 | 100% | 90% | 50% | 2372.095 | 164.905 | 100% | 90% | 50% | 0 | 0 | 0 | 0
Installation
68 | Installation, Termination, Testing & Commissioning | 1 | lot | 299766 | 299766 | 25004.638 | 274761.362 |  | 90% |  | 222556.7032 | 52204.6588 | 100% | 90% | 20% | 5495.2272 | 0 | 5495.2272 | 5495.2272
B | IPTV System |  |  |  | 671380 | 56055 | 615325 | 82.87% |  |  | 509890.11 | 105435 | 0% |  |  | 0 | 0 | 0 | 0
Server & IPTV services
1 | TV MDW - 101 TO 499 USERS | 1 | Nr | 64906 | 64906 | 0 | 64906 | 100% | 80% | 0% | 56468.22 | 8437.78 | 100% | 80% | 0% | 0 | 0 | 0 | 0
2 | ARANTIA TV STB LICENSE SW* | 225 | Nr | 220 | 49500 | 0 | 49500 | 100% | 80% | 0% | 43065 | 6435 | 100% | 80% | 0% | 0 | 0 | 0 | 0
3 | ARANTIA TV PMS INTERFACE SW* | 1 | Nr | 23344 | 23344 | 0 | 23344 | 100% | 80% | 0% | 20309.28 | 3034.72 | 100% | 80% | 0% | 0 | 0 | 0 | 0
Project management
4 | UPS | 1 | Nr | 4487 | 4487 | 0 | 4487 | 0% | 80% | 0% | 538.44 | 3948.56 | 0% | 80% | 0% | 0 | 0 | 0 | 0
5 | 19" RACK 27U (MOUNTED ADJUSTED) | 1 | Nr | 23344 | 23344 | 0 | 23344 | 100% | 80% | 0% | 20309.28 | 3034.72 | 100% | 80% | 0% | 0 | 0 | 0 | 0
6 | L2 SWITCH 24P100TX +4SFP | 1 | Nr | 3052 | 3052 | 0 | 3052 | 100% | 80% | 0% | 2655.24 | 396.76 | 100% | 80% | 0% | 0 | 0 | 0 | 0
IPTV headend
7 | T.0X ENCODER IP HD TWIN COFDM/ QAM | 10 | Nr | 6833 | 68330 | 0 | 68330 | 100% | 80% | 0% | 59447.1 | 8882.9 | 100% | 80% | 0% | 0 | 0 | 0 | 0
8 | 19" RACK FRAME 5RU | 2 | Nr | 277 | 554 | 0 | 554 | 100% | 80% | 0% | 481.98 | 72.02 | 100% | 80% | 0% | 0 | 0 | 0 | 0
9 | T.0X SM PSU 120W 24V-5A | 2 | Nr | 766 | 1532 | 0 | 1532 | 100% | 80% | 0% | 1332.84 | 199.16 | 100% | 80% | 0% | 0 | 0 | 0 | 0
10 | UNIVERSAL PROGRAMMER | 1 | Nr | 377 | 377 | 0 | 377 | 100% | 80% | 0% | 327.99 | 49.01 | 100% | 80% | 0% | 0 | 0 | 0 | 0
11 | IPTV HEAD END(28 FTA + 14 PAY) TRANSPONDER | 2 | Nr | 93245 | 186490 | 0 | 186490 | 100% | 80% | 0% | 162246.3 | 24243.7 | 100% | 80% | 0% | 0 | 0 | 0 | 0
3 Satellite reception system
12 | OFFSET DISH 1300 AL G42dBi WHI.10U | 3 | Nr | 1431 | 4293 | 0 | 4293 | 100% | 0% | 0% | 3219.75 | 1073.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
13 | "T" BRACKET RCP GROUND 750x200/ Ø60x2.9mm | 3 | Nr | 126 | 378 | 0 | 378 | 100% | 0% | 0% | 283.5 | 94.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
14 | OFFSET OPTICAL LNB G72dB Po7dBm 32x GR. | 3 | Nr | 845 | 2535 | 0 | 2535 | 100% | 0% | 0% | 1901.25 | 633.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
15 | F.O. ATTENUATOR 1310/1550nm "FC/ PC" 10dB | 3 | Nr | 62 | 186 | 0 | 186 | 100% | 0% | 0% | 139.5 | 46.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
16 | OP./ RF CONVERTER QUATTRO FM/ DAB/ UHF- SAT | 3 | Nr | 704 | 2112 | 0 | 2112 | 100% | 0% | 0% | 1584 | 528 | 100% | 0% | 0% | 0 | 0 | 0 | 0
17 | PSU 20V-1.2A (OPTICAL CONV.) | 3 | Nr | 97 | 291 | 0 | 291 | 100% | 0% | 0% | 218.25 | 72.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
18 | COAX.CAB.T100 PVC Eca/ A 16VAtC BL.250m | 250 | Nr | 14 | 3500 | 0 | 3500 | 100% | 0% | 0% | 2625 | 875 | 100% | 0% | 0% | 0 | 0 | 0 | 0
19 | Fiber Cable | 200 | Nr | 14 | 2800 | 0 | 2800 | 100% | 80% | 0% | 2436 | 364 | 100% | 80% | 0% | 0 | 0 | 0 | 0
IDF Distribution
20 | MINIKOM AMP.SAT 2/1 "F" G35..45dB +MATV MIX | 16 | Nr | 365 | 5840 | 0 | 5840 | 100% | 0% | 0% | 4380 | 1460 | 100% | 0% | 0% | 0 | 0 | 0 | 0
21 | TAP 5...2400MHz "F" 2W 12dB TA | 16 | Nr | 23 | 368 | 0 | 368 | 100% | 0% | 0% | 276 | 92 | 100% | 0% | 0% | 0 | 0 | 0 | 0
22 | SPLITTER 5...2400MHz "F" 2W 4/5dB | 16 | Nr | 20 | 320 | 0 | 320 | 100% | 0% | 0% | 240 | 80 | 100% | 0% | 0% | 0 | 0 | 0 | 0
23 | NEVOSWITCH 17x17x8 "F" TERMINAL/ CASCADE | 13 | Nr | 950 | 12350 | 0 | 12350 | 100% | 0% | 0% | 9262.5 | 3087.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
24 | NEVOSWITCH 17x17x12 "F" TERMINAL/ CASCADE | 5 | Nr | 1622 | 8110 | 0 | 8110 | 100% | 0% | 0% | 6082.5 | 2027.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
25 | NEVOSWITCH 17x17x16 "F" TERMINAL/ CASCADE | 5 | Nr | 1893 | 9465 | 0 | 9465 | 100% | 0% | 0% | 7098.75 | 2366.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
26 | NEVOSWITCH AMPLIF.17x17 "F" G-/27/25dB Vo110 | 7 | Nr | 947 | 6629 | 0 | 6629 | 100% | 0% | 0% | 4971.75 | 1657.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
27 | PSU 12V-1.5A UK | 11 | Nr | 80 | 880 | 0 | 880 | 100% | 0% | 0% | 660 | 220 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Cables and sockets
28 | END OUTLET.DIPLEX. TV/ FM- SAT 0.6-1.5dB +DC | 225 | Nr | 22.6222 | 5090 | 0 | 5090 | 0% | 0% | 0% | 0 | 5090 | 0% | 0% | 0% | 0 | 0 | 0 | 0
29 | FACE PLATE WHITE TV/ R- SAT OUTLET | 225 | pc | 3.04 | 684 | 0 | 684 | 0% | 0% | 0% | 0 | 684 | 0% | 0% | 0% | 0 | 0 | 0 | 0
30 | COAX.CAB.T100 PE Fca/ A 16PAtC BL.250m | 500 | m | 1.91 | 955 | 716.25 | 238.75 | 100% | 0% | 0% | 179.0625 | 59.6875 | 100% | 0% | 0% | 0 | 0 | 0 | 0
31 | COAX.CAB.T100 PVC Eca/ A 16VAtC BL.250m | 8500 | m | 1.55 | 13175 | 9881.25 | 3293.75 | 100% | 80% | 0% | 2865.5625 | 428.1875 | 100% | 80% | 0% | 0 | 0 | 0 | 0
32 | COAX.CAB.TR165 PE Fca/ A 11PRtC BL.250m | 11000 | m | 5.51 | 60610 | 45457.5 | 15152.5 | 100% | 80% | 0% | 13182.675 | 1969.825 | 100% | 80% | 0% | 0 | 0 | 0 | 0
VOD Server
33 | ARANTIA VOD SERVER 95 STREAMS 500GB | 1 | Nr | 51241 | 51241 | 0 | 51241 | 100% | 80% | 0% | 44579.67 | 6661.33 | 100% | 80% | 0% | 0 | 0 | 0 | 0
| Fire alarm service (single zone) | [7 empty] | 9% |  |  |  |  | 9%
34 | ARANTIA ALARM MONITOR DEVICE | 1 | Nr | 2699 | 2699 | 0 | 2699 | 100% | 0% | 0% | 2024.25 | 674.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
35 | ARANTIA TV ALARM SYSTEM INTEGRATION SW* | 1 | Nr | 19939 | 19939 | 0 | 19939 | 100% | 0% | 0% | 14954.25 | 4984.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
36 | STB PSU - UK PLUG | 1 | Nr | 45 | 45 | 0 | 45 | 100% | 0% | 0% | 33.75 | 11.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Installation
37 | installation, testing and commissioning | 1 | Nr | 30969 | 30969 | 0 | 30969 |  | 70% |  | 19510.47 | 11458.53 |  | 70% |  | 0 | 0 | 0 | 0
C | Active components for ICT N/W |  |  |  | 3120592 | 0 | 3120592 | 83.69% |  |  | 2611674.54 | 508917 | 9.13% |  |  | 46465 | 0 | 46465 | 46465
Core SW
1 | Aruba 5412R zl2 Switch | 2 | Nr | 5807 | 11614 | 0 | 11614 | 100% | 90% | 0% | 10278.39 | 1335.61 | 100% | 90% | 0% | 0 | 0 | 0 | 0
2 | Aruba 5400R 700W PoE+ zl2 PSU | 8 | Nr | 1013 | 8104 | 0 | 8104 | 100% | 90% | 0% | 7172.04 | 931.96 | 100% | 90% | 0% | 0 | 0 | 0 | 0
3 | Aruba 5400R zl2 Management Module | 2 | Nr | 3156 | 6312 | 0 | 6312 | 100% | 90% | 0% | 5586.12 | 725.88 | 100% | 90% | 0% | 0 | 0 | 0 | 0
4 | Aruba 8p 1G/10Gbe SFP+ v3 zl2 module | 18 | Nr | 6046 | 108828 | 0 | 108828 | 100% | 90% | 0% | 96312.78 | 12515.22 | 100% | 90% | 0% | 0 | 0 | 0 | 0
5 | Aruba 20p PoE+ / 4p SFP+ v3 zl2 Mod | 2 | Nr | 5043 | 10086 | 0 | 10086 | 100% | 90% | 0% | 8926.11 | 1159.89 | 100% | 90% | 0% | 0 | 0 | 0 | 0
6 | Aruba 10G SFP+ to SFP+ 7m DAC Cable | 2 | Nr | 337 | 674 | 0 | 674 | 100% | 90% | 0% | 596.49 | 77.51 | 100% | 90% | 0% | 0 | 0 | 0 | 0
7 | Aruba 10G SFP+ LC SR 300m MMF Transceiver | 136 | Nr | 1221 | 166056 | 0 | 166056 | 100% | 90% | 0% | 146959.56 | 19096.44 | 100% | 90% | 0% | 0 | 0 | 0 | 0
8 | HPE 1Y FC NBD Aruba 5412R zl2 Switc SVC [for J9822A] | 2 | Nr | 3895 | 7790 | 0 | 7790 | 100% | 90% | 0% | 6894.15 | 895.85 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Aggregation SW
9 | Aruba 5406R zl2 Switch | 14 | Nr | 3041 | 42574 | 0 | 42574 | 100% | 90% | 0% | 37677.99 | 4896.01 | 100% | 90% | 0% | 0 | 0 | 0 | 0
10 | Aruba 5400R 700W PoE+ zl2 PSU | 28 | Nr | 1013 | 28364 | 0 | 28364 | 100% | 90% | 0% | 25102.14 | 3261.86 | 100% | 90% | 0% | 0 | 0 | 0 | 0
11 | Aruba 8p 1G/10Gbe SFP+ v3 zl2 module | 14 | Nr | 6046 | 84644 | 0 | 84644 | 100% | 90% | 0% | 74909.94 | 9734.06 | 100% | 90% | 0% | 0 | 0 | 0 | 0
12 | Aruba 24p 1GbE SFP v3 zl2 Mod | 28 | Nr | 4916 | 137648 | 0 | 137648 | 100% | 90% | 0% | 121818.48 | 15829.52 | 100% | 90% | 0% | 0 | 0 | 0 | 0
13 | Aruba 20p PoE+ / 4p SFP+ v3 zl2 Mod | 7 | Nr | 5043 | 35301 | 0 | 35301 | 100% | 90% | 0% | 31241.385 | 4059.615 | 100% | 90% | 0% | 0 | 0 | 0 | 0
14 | Aruba 10G SFP+ LC SR 300m MMF Transceiver | 28 | Nr | 1221 | 34188 | 0 | 34188 | 100% | 90% | 0% | 30256.38 | 3931.62 | 100% | 90% | 0% | 0 | 0 | 0 | 0
15 | Aruba 1G SFP LC SX 500m MMF Transceiver | 446 | Nr | 294 | 131124 | 0 | 131124 | 100% | 90% | 0% | 116044.74 | 15079.26 | 100% | 90% | 0% | 0 | 0 | 0 | 0
IDF-SW-H&SA (ONU)
16 | Aruba 2530 8G PoE+ Switch | 172 | Nr | 927 | 159444 | 0 | 159444 | 100% | 90% | 0% | 141107.94 | 18336.06 | 100% | 90% | 0% | 0 | 0 | 0 | 0
17 | Aruba 2530 24G PoE+ Switch | 39 | Nr | 2194 | 85566 | 0 | 85566 | 100% | 90% | 0% | 75725.91 | 9840.09 | 100% | 90% | 0% | 0 | 0 | 0 | 0
18 | Aruba 2530 48G PoE+ Switch | 12 | Nr | 4079 | 48948 | 0 | 48948 | 100% | 90% | 0% | 43318.98 | 5629.02 | 100% | 90% | 0% | 0 | 0 | 0 | 0
19 | Aruba 1G SFP LC SX 500m MMF Transceiver | 446 | Nr | 294 | 131124 | 0 | 131124 | 100% | 90% | 0% | 116044.74 | 15079.26 | 100% | 90% | 0% | 0 | 0 | 0 | 0
IDF-SW-H&SA (Common areas)
20 | Aruba 2930F 24G PoE+ 4SFP+ Switch | 14 | Nr | 4303 | 60242 | 0 | 60242 | 100% | 90% | 0% | 53314.17 | 6927.83 | 100% | 90% | 0% | 0 | 0 | 0 | 0
21 | Aruba 2930F 48G PoE+ 4SFP+ Switch | 28 | Nr | 6541 | 183148 | 0 | 183148 | 100% | 90% | 0% | 162085.98 | 21062.02 | 100% | 90% | 0% | 0 | 0 | 0 | 0
22 | Aruba 10G SFP+ LC SR 300m MMF Transceiver | 84 | Nr | 1221 | 102564 | 0 | 102564 | 100% | 90% | 0% | 90769.14 | 11794.86 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Server SW (H&SA)
23 | Aruba 2930M 48G 1-slot Switch | 2 | Nr | 7918 | 15836 | 0 | 15836 | 100% | 90% | 0% | 14014.86 | 1821.14 | 100% | 90% | 0% | 0 | 0 | 0 | 0
24 | Aruba X371 12VDC 250W Power Supply | 4 | Nr | 552 | 2208 | 0 | 2208 | 100% | 90% | 0% | 1954.08 | 253.92 | 100% | 90% | 0% | 0 | 0 | 0 | 0
25 | Aruba 3810M/2930M 4SFP+ MACsec Module | 2 | Nr | 1591 | 3182 | 0 | 3182 | 100% | 90% | 0% | 2816.07 | 365.93 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Firewall
26 | FortiGate firewall Hardware plus 24x7 Forticare, 1 year | 1 | Nr | 33773 | 33773 | 0 | 33773 | 100% | 90% | 0% | 29889.105 | 3883.895 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Cisco router
27 | Cisco ISR 4331 (3GE.2NIM.1SM.4G FLASH.4G DRAM.IPB) | 1 | Nr | 26036 | 26036 | 0 | 26036 | 100% | 90% | 0% | 23041.86 | 2994.14 | 100% | 90% | 0% | 0 | 0 | 0 | 0
NMS
28 | Aruba IMC Ent SW Plat w/50-node E-LTU | 1 | Nr | 8889 | 8889 | 0 | 8889 | 100% | 90% | 0% | 7866.765 | 1022.235 | 100% | 90% | 0% | 0 | 0 | 0 | 0
29 | Aruba 1Y FC NBD IMC Ent SW PlfmE-LTU SVC | 1 | Nr | 8289 | 8289 | 0 | 8289 | 100% | 90% | 0% | 7335.765 | 953.235 | 100% | 90% | 0% | 0 | 0 | 0 | 0
30 | Aruba IMC Std and Ent Add 50-node E-LTU | 5 | Nr | 3780 | 18900 | 0 | 18900 | 100% | 90% | 0% | 16726.5 | 2173.5 | 100% | 90% | 0% | 0 | 0 | 0 | 0
31 | Aruba 1Y FC NBD IMC Std Ent AddE-LTU SVC | 5 | Nr | 986 | 4930 | 0 | 4930 | 100% | 90% | 0% | 4363.05 | 566.95 | 100% | 90% | 0% | 0 | 0 | 0 | 0
32 | PC based Server for NMS | 1 | Nr | 9476 | 9476 | 0 | 9476 | 100% | 90% | 0% | 8386.26 | 1089.74 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Installation
33 | Testing, Commisioning & Implementation | 1 | Nr | 55556 | 55556 | 0 | 55556 |  | 60% | 0% | 30000.24 | 25555.76 |  | 70% | 0% | 5000.04 | 0 | 5000.04 | 5000.04
Core SW
34 | Aruba 5412R zl2 Switch | 2 | Nr | 5751 | 11502 | 0 | 11502 | 100% | 90% | 0% | 10179.27 | 1322.73 | 100% | 90% | 0% | 0 | 0 | 0 | 0
35 | Aruba 5400R 700W PoE+ zl2 PSU | 8 | Nr | 1003 | 8024 | 0 | 8024 | 100% | 90% | 0% | 7101.24 | 922.76 | 100% | 90% | 0% | 0 | 0 | 0 | 0
36 | Aruba 5400R zl2 Management Module | 2 | Nr | 3125 | 6250 | 0 | 6250 | 100% | 90% | 0% | 5531.25 | 718.75 | 100% | 90% | 0% | 0 | 0 | 0 | 0
37 | Aruba 24p 1GbE SFP v3 zl2 Mod | 4 | Nr | 4868 | 19472 | 0 | 19472 | 100% | 90% | 0% | 17232.72 | 2239.28 | 100% | 90% | 0% | 0 | 0 | 0 | 0
38 | Aruba 20p PoE+ / 4p SFP+ v3 zl2 Mod | 2 | Nr | 4994 | 9988 | 0 | 9988 | 100% | 90% | 0% | 8839.38 | 1148.62 | 100% | 90% | 0% | 0 | 0 | 0 | 0
39 | Aruba 10G SFP+ to SFP+ 7m DAC Cable | 2 | Nr | 334 | 668 | 0 | 668 | 100% | 90% | 0% | 591.18 | 76.82 | 100% | 90% | 0% | 0 | 0 | 0 | 0
40 | 1G SFP LC SX 500m MMF Transceiver | 88 | Nr | 291 | 25608 | 0 | 25608 | 100% | 90% | 0% | 22663.08 | 2944.92 | 100% | 90% | 0% | 0 | 0 | 0 | 0
41 | HPE 1Y FC NBD Aruba 5412R zl2 Switc SVC [for J9822A] | 2 | Nr | 3857 | 7714 | 0 | 7714 | 100% | 90% | 0% | 6826.89 | 887.11 | 100% | 90% | 0% | 0 | 0 | 0 | 0
IDF-SW
42 | Aruba 2930F 24G PoE+ 4SFP Switch | 18 | Nr | 4261 | 76698 | 0 | 76698 | 100% | 90% | 0% | 67877.73 | 8820.27 | 100% | 90% | 0% | 0 | 0 | 0 | 0
43 | Aruba 2930F 48G PoE+ 4SFP 740W Switch | 22 | Nr | 6478 | 142516 | 0 | 142516 | 100% | 90% | 0% | 126126.66 | 16389.34 | 100% | 90% | 0% | 0 | 0 | 0 | 0
44 | 1G SFP LC SX 500m MMF Transceiver | 80 | Nr | 291 | 23280 | 0 | 23280 | 100% | 90% | 0% | 20602.8 | 2677.2 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Server SW
45 | Aruba 2930M 48G 1-slot Switch | 2 | Nr | 7841 | 15682 | 0 | 15682 | 100% | 90% | 0% | 13878.57 | 1803.43 | 100% | 90% | 0% | 0 | 0 | 0 | 0
46 | Aruba X371 12VDC 250W Power Supply | 4 | Nr | 547 | 2188 | 0 | 2188 | 100% | 90% | 0% | 1936.38 | 251.62 | 100% | 90% | 0% | 0 | 0 | 0 | 0
47 | Aruba 3810M/2930M 4SFP+ MACsec Module | 2 | Nr | 5357 | 10714 | 0 | 10714 | 100% | 90% | 0% | 9481.89 | 1232.11 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Installation
48 | Testing, Commisioning & Implementation | 1 | Nr | 23530 | 23530 | 0 | 23530 |  | 60% | 0% | 12706.2 | 10823.8 |  | 70% | 0% | 2117.7 | 0 | 2117.7 | 2117.7
WLAN - Mobility controller
49 | 7240 Mobility Controller with 4x 10GBase-x (SFP/SFP+) and 2x dual media (10/100/1000BASE-T or SFP) ports. Includes one 350W AC power supply | 2 | Nr | 44569 | 89138 | 0 | 89138 | 100% | 80% | 0% | 77550.06 | 11587.94 | 100% | 80% | 0% | 0 | 0 | 0 | 0
50 | 350W AC Power Supply. May be used as a redundant power supply or field-replaceable spare for 7200 Series, S3500-24T, S3500-48T and S3500-24F. Power cord not included- order country-specific (PC-AC-xx) power cord below. | 2 | Nr | 581 | 1162 | 0 | 1162 | 100% | 80% | 0% | 1010.94 | 151.06 | 100% | 80% | 0% | 0 | 0 | 0 | 0
51 | AC Power Cord (UK Version) | 4 | Nr | 6 | 24 | 0 | 24 | 100% | 80% | 0% | 20.88 | 3.12 | 100% | 80% | 0% | 0 | 0 | 0 | 0
52 | 10GBASE-SR SFP+; 850nm pluggable 10GbE optic; LC connector; up to 300 meters over multi-mode fiber (Type OM3) or 400 meters with OM4 | 2 | Nr | 1461 | 2922 | 0 | 2922 | 100% | 80% | 0% | 2542.14 | 379.86 | 100% | 80% | 0% | 0 | 0 | 0 | 0
53 | Capacity license to enable support for one Access Point on a Mobility Controller. Order in multiples of this license SKU based on the desired AP capacity per controller or across the network of controllers with centralized licensing enabled. The supported controllers include 6xx, 3xxx, M3, 70xx and 72xx running Aruba OS 6.0.x and beyond. | 673 | Nr | 90 | 60570 | 0 | 60570 | 100% | 80% | 0% | 52695.9 | 7874.1 | 100% | 80% | 0% | 0 | 0 | 0 | 0
54 | Aruba 1Y FC 24x7 7240 controller SVC | 2 | Nr | 46758 | 93516 | 0 | 93516 | 100% | 80% | 0% | 81358.92 | 12157.08 | 100% | 80% | 0% | 0 | 0 | 0 | 0
55 | Aruba 1Y FC 24x7 license SVC | 673 | Nr | 48 | 32304 | 0 | 32304 | 100% | 80% | 0% | 28104.48 | 4199.52 | 100% | 80% | 0% | 0 | 0 | 0 | 0
Access points
56 | Aruba AP-303H Wireless Access Point, 802.11n/ac, 2x2:2 / dual radio, integrated antennas | 245 | Nr | 464 | 113680 | 0 | 113680 | 100% | 0% | 0% | 85260 | 28420 | 100% | 50% | 0% | 8526 | 0 | 8526 | 8526
57 | Aruba AP-305 Wireless Access Point, 802.11n/ac, 4x4:4, dual radio, integrated antennas | 361 | Nr | 816 | 294576 | 0 | 294576 | 100% | 0% | 0% | 220932 | 73644 | 100% | 50% | 0% | 22093.2 | 0 | 22093.2 | 22093.2
58 | Aruba 320 Series Access points ceiling tile mount kit | 361 | Nr | 31 | 11191 | 0 | 11191 | 100% | 0% | 0% | 8393.25 | 2797.75 | 100% | 50% | 0% | 839.325 | 0 | 839.325 | 839.325
59 | AP-315 Wireless AP, 802.11n/ac, 4x4:4 MU-MIMO, dual radio, integrated antennas | 21 | Nr | 1168 | 24528 | 0 | 24528 | 100% | 0% | 0% | 18396 | 6132 | 100% | 50% | 0% | 1839.6 | 0 | 1839.6 | 1839.6
60 | Aruba 320 Series Access points ceiling tile mount kit | 21 | Nr | 31 | 651 | 0 | 651 | 100% | 0% | 0% | 488.25 | 162.75 | 100% | 50% | 0% | 48.825 | 0 | 48.825 | 48.825
Outdoor AP
61 | AP-365 Outdoor Wireless AP, 802.11ac, dual radio, integrated omni antennas | 40 | Nr | 1520 | 60800 | 0 | 60800 | 100% | 0% | 0% | 45600 | 15200 | 100% | 0% | 0% | 0 | 0 | 0 | 0
62 | Aruba 365 Series Outdoor AP Short Mount Kit. Pole/Wall Mount for AP-270. Positions AP 75 mm from vertical mounting asset | 40 | Nr | 147 | 5880 | 0 | 5880 | 100% | 0% | 0% | 4410 | 1470 | 100% | 0% | 0% | 0 | 0 | 0 | 0
HSIA
63 | HSIA solution | 1 | Nr | 107731 | 107731 | 0 | 107731 | 100% | 0% | 0% | 80798.25 | 26932.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Installation
64 | Tesing, Commissioning & Implementaion | 1 | Nr | 66667 | 66667 | 0 | 66667 |  | 40% |  | 24000.12 | 42666.88 |  | 50% |  | 6000.03 | 0 | 6000.03 | 6000.03
D | CCTV system |  |  |  | 1265148 | 0 | 1265148 | 72.82% |  |  | 921253.74 | 343894 | 7.977% |  |  | 27431 | 3249 | 24182 | 27431
Residential Apartments
1 | 1/2.5" Progressive Scan CMOS; H.265+/H.265/ H.264+/ H.264/ MJPEG; Powered by Darkfighter technology,Color: 0.007 lux @(F1.4, AGC ON), 0 lux with IR; 50fps/60fps(1920×1080); VCA functions; 3 streams; 3D DNR; BLC; ICR; EXIR; DC12V&PoE; Built-in micro SD/SDHC/SDXC slot; Built-in Audio/Alarm I/O, HIK-Connect cloud service; Audio/Alarm I/O, 2.7-13.5MM,Auto-Iris, IK10,IP67, IR 60M, 120DB WDR, Full Metal, 3streams | 548 | Nr | 585 | 320580 | 0 | 320580 | 100% | 40% | 0% | 259669.8 | 60910.2 | 100% | 50% | 0% | 4808.7 | 0 | 4808.7 | 4808.7
2 | Hik white Steel and Plastic Ø 225 mm × 98.2 mm (8.86" × 3.87") 700 g (1.54 lb.) | 548 | Nr | 71 | 38908 | 0 | 38908 | 100% | 40% | 0% | 31515.48 | 7392.52 | 100% | 50% | 0% | 583.62 | 0 | 583.62 | 583.62
3 | Darkfighter Ultra-low light technology, H.265+/H.265/H.264+/ H.264/ MJPEG, Color:0.002Lux/F1.2, BW:0.0002Lux/F1.2; 1/1.8"CMOS; 1080P , up to 50fps/60fps;150dB WDR, P-iris; 1*AudioOut,1*AudioIn; 1*AlarmIn, 1*AlarmOut; RS485;DC12Vout;5streams+5 custom streams;IK10; | 10 | Nr | 1251 | 12510 | 0 | 12510 | 100% | 0% | 0% | 9382.5 | 3127.5 | 100% | 50% | 0% | 938.25 | 0 | 938.25 | 938.25
4 | 1/2.8" Progressive Scan CMOS; H.265+/H.265/ H.264+/ H.264/ MJPEG; Powered by Darkfighter technology,Color: 0.005 lux @(F1.2, AGC ON), 0 lux with IR; 50fps/60fps(1920×1080); VCA functions; 3 streams; 3D DNR; BLC; ICR; EXIR; DC12V&PoE; Built-in micro SD/SDHC/SDXC slot; Built-in Audio/Alarm I/O, HIK-Connect cloud service; Audio/Alarm I/O, auto-iris | 346 | Nr | 585 | 202410 | 0 | 202410 | 100% | 20% | 0% | 157879.8 | 44530.2 | 100% | 50% | 0% | 9108.45 | 0 | 9108.45 | 9108.45
5 | Hik White | 4 | Nr | 73 | 292 | 0 | 292 | 100% | 0% | 0% | 219 | 73 | 100% | 50% | 0% | 21.9 | 0 | 21.9 | 21.9
6 | 2MP, 1/2.8" CMOS,H.265+/H.265/H.264+/H.264 codec, 3D DNR, True WDR, Ultra-low light Powerde By DarkFighter Color: 0.005lux/F1.6, B/W:0.001lux/F1.6, Optical Zoom:32x, Digital Zoom:16X 1920*1080:60fps, Pan Speed: 0.1° -250°/s, Tilt Speed: 0.1° -150°/s, PoE+&24VAC Smart Tracking Smart Detection | 2 | Nr | 1400 | 2800 | 0 | 2800 | 100% | 0% | 0% | 2100 | 700 | 100% | 0% | 0% | 0 | 0 | 0 | 0
7 | Hik white Aluminum alloy 281.2×170.7×395.5mm | 2 | Nr | 121 | 242 | 0 | 242 | 100% | 0% | 0% | 181.5 | 60.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
8 | 1/2.8" Progressive Scan CMOS; H.265+/H.265/H.264+/H.264/MJPEG; Powered by Darkfighter technology,Color: 0.009 lux @(F1.6, AGC ON), 0 lux with IR; 50fps/60fps(1920×1080); VCA functions; 3 streams; 3D DNR; BLC; ICR; EXIR; DC12V&PoE; Built-in micro SD/SDHC/SDXC slot; HIK-Connect cloud service, built-in mic, Audio/Alarm I/O | 2 | Nr | 483 | 966 | 0 | 966 | 100% | 0% | 0% | 724.5 | 241.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
9 | 4U, Double controller,256 Ch(2Mbps)Record+playback with IPSAN mode, 448 Ch(2Mbps)Record+playback with Direct steaming mode,24 HDD(SAS), Redundant power supply, SAS expansion ark support with MiniSas Interface,24*14TB SAS Seagate Enterprise Level HDD included | 2 | Nr | 77816 | 155632 | 0 | 155632 | 100% | 90% | 0% | 137734.32 | 17897.68 | 100% | 90% | 0% | 0 | 0 | 0 | 0
10 | 300 cameras manageable. Dell server with E3 CPU, Supported: Cloud Storage Server, Auxiliary Storage, Alarm Management (Alarm Cofiguration, Alarm Logs, Alarm Search), Email notification, Active Directory, Running on Virtual Machine, 100 Users Logged In Simultaneously, Client Operation (Auto-Switch, Private View, Adding Tag, Locking Video, Instant Playback, Custom Window Division) | 1 | Nr | 36000 | 36000 | 0 | 36000 | 100% | 90% | 0% | 31860 | 4140 | 100% | 90% | 0% | 0 | 0 | 0 | 0
11 | 1 camera connection. | 606 | Nr | 149 | 90294 | 0 | 90294 | 100% | 0% | 0% | 67720.5 | 22573.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
12 | E3-1220V5×1/16GB UDIMM, 2400MT/s, ECC×1 /1TB SATA 3.5 enterprise level x2 hot-plug hard drives,/1GbE×2/Single Power/Sliding Rails/1U/H330/Raid 1 default/Pre-Actived Windows Server 2012 R2 Standard Multi-languages/3 Years Dell Pro Support Plus Service | 1 | Nr | 14054 | 14054 | 0 | 14054 | 100% | 90% | 0% | 12437.79 | 1616.21 | 100% | 90% | 0% | 0 | 0 | 0 | 0
13 | Rose used for 1+1 VMS server backup,Only used for local back up of servers, USB Key license mode | 1 | Nr | 9955 | 9955 | 0 | 9955 | 100% | 90% | 0% | 8810.175 | 1144.825 | 100% | 90% | 0% | 0 | 0 | 0 | 0
| Dropdown pole for drive way areas cameras | [17 empty] | 0
14 | Drop down pipe for Driveway areas Cameras | 33 | Nr | 123 | 4059 | 0 | 4059 | 100% | 90% | 0% | 3592.215 | 466.785 | 100% | 90% | 0% | 0 | 0 | 0 | 0
| ANPR Camera | [17 empty] | 0
15 | Specific approved ANPR camera, color CCD sensor 1280x960 @30fps. Range up to 8m. Speed up to 250km/h* White LED illumination , housing and wall bracket, Remote configuration and monitoring with Cables & Connectors- | 2 | Nr | 18043 | 36086 | 0 | 36086 | 100% | 0% | 0% | 27064.5 | 9021.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
16 | ANPR loop detector and Loop cable | 2 | Nr |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
17 | ANPR workstation with Monitor | 1 | Nr |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
18 | Pole 2.5 Meter Galvanized powder coated | 2 | Nr | 722 | 1444 | 0 | 1444 | 0% | 0% | 0% | 0 | 1444 | 100% | 0% | 0% | 1083 | 1083 | 0 | 1083 | DN-12986
Dropdown pipe for drive way areas cameras
19 | Drop Down Pipe for Driveway areas Cameras | 29 | Nr | 104 | 3016 | 0 | 3016 | 0% | 0% | 0% | 0 | 3016 | 0% | 0% | 0% | 0 | 0 | 0 | 0
ANPR Camera
20 | Specific approved ANPR camera, color CCD sensor 1280x960 @30fps. Range up to 8m. Speed up to 250km/h* White LED illumination , housing and wall bracket, Remote configuration and monitoring with Cables & Connectors- | 4 | Nr | 17606 | 70424 | 0 | 70424 | 100% | 0% | 0% | 52818 | 17606 | 100% | 0% | 0% | 0 | 0 | 0 | 0
21 | ANPR loop detector and Loop cable | 4 | Nr |  | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
22 | Pole 2.5 Meter Galvanized powder coated | 4 | Nr | 722 | 2888 | 0 | 2888 | 0% | 0% | 0% | 0 | 2888 | 100% | 0% | 0% | 2166 | 2166 | 0 | 2166 | DN-12986
Video management software
23 | PTZ Keyboard | 2 | Nr | 4139 | 8278 | 0 | 8278 | 100% | 0% | 0% | 6208.5 | 2069.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Cotrol room monitoring
24 | Workstation with dual graphic card for operator | 6 | Nr | 6471 | 38826 | 0 | 38826 | 100% | 0% | 0% | 29119.5 | 9706.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
25 | 22" LCD CCTV monitor | 12 | Nr | 624 | 7488 | 0 | 7488 | 100% | 0% | 0% | 5616 | 1872 | 100% | 0% | 0% | 0 | 0 | 0 | 0
26 | Workstation with dual graphic card for critical cameras | 2 | Nr | 6471 | 12942 | 0 | 12942 | 100% | 0% | 0% | 9706.5 | 3235.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
27 | 43" 1080P, HDMI/VGA/DVI/BNC input, build-in speaker, view angle: 178°/178°, plastic casing for critical cameras | 4 | Nr | 3128 | 12512 | 0 | 12512 | 100% | 90% | 0% | 11073.12 | 1438.88 | 100% | 90% | 0% | 0 | 0 | 0 | 0
28 | Workstation with dual graphic card for important Camera | 3 | Nr | 6471 | 19413 | 0 | 19413 | 100% | 0% | 0% | 14559.75 | 4853.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
29 | 32'",monitor for important cameras | 6 | Nr | 2353 | 14118 | 0 | 14118 | 100% | 90% | 0% | 12494.43 | 1623.57 | 100% | 90% | 0% | 0 | 0 | 0 | 0
30 | Wall mount Brackets and HDMI cable | 1 | Nr | 2942 | 2942 | 0 | 2942 | 100% | 90% | 0% | 2603.67 | 338.33 | 100% | 90% | 0% | 0 | 0 | 0 | 0
31 | DPS approval charges | 1 | Nr | 35054 | 35054 | 0 | 35054 | 0% | 0% | 0% | 0 | 35054 | 0% | 0% | 0% | 0 | 0 | 0 | 0
32 | Video guard system | 1 | Nr | 14118 | 14118 | 0 | 14118 | 0% | 0% | 0% | 0 | 14118 | 0% | 0% | 0% | 0 | 0 | 0 | 0
33 | Accessories | 1 | Ls | 0 | 0 | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0% | 0% | 0% | 0 | 0 | 0 | 0
34 | Installation ,Testing and commissioning | 1 | Ls | 96897 | 96897 | 0 | 96897 |  | 30% | 0% | 26162.19 | 70734.81 |  | 40% | 0% | 8720.73 | 0 | 8720.73 | 8720.73
E | Access control system |  |  |  | 344535 | 167391.75 | 177143.25 | 73.66% |  |  | 130478.61 | 46664 | 0% |  |  | 0 | 0 | 0 | 0
Access control software for doors
1 | Net2 software - Pro | 1 | Nr | 1714 | 1714 | 1285.5 | 428.5 | 0% | 0% | 0% | 0 | 428.5 | 0% | 0% | 0% | 0 | 0 | 0 | 0
2 | Net2 desktop reader, USB | 1 | Nr | 247 | 247 | 185.25 | 61.75 | 0% | 0% | 0% | 0 | 61.75 | 0% | 0% | 0% | 0 | 0 | 0 | 0
3 | Net2 plus 1 door controller - 12V 2A PSU, Plastic cabinet | 85 | Nr | 1316 | 111860 | 83895 | 27965 | 100% | 50% | 0% | 23071.125 | 4893.875 | 100% | 50% | 0% | 0 | 0 | 0 | 0
4 | Net2 I/O board - 12V 2A PSU, Plastic cabinet | 33 | Nr | 1190 | 39270 | 15172.5 | 24097.5 | 100% | 50% | 0% | 19880.4375 | 4217.0625 | 100% | 50% | 0% | 0 | 0 | 0 | 0
5 | Battery Backup | 120 | Nr | 59 | 7080 | 0 | 7080 | 100% | 0% | 0% | 5310 | 1770 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Reader & credentials
6 | NET2 PROXIMITY MIFARE READER:P50 | 96 | Nr | 372 | 35712 | 25668 | 10044 | 100% | 50% | 0% | 8286.3 | 1757.7 | 100% | 50% | 0% | 0 | 0 | 0 | 0
7 | MIFARE CLASSIC 1K ISO CARD:WITHOUT MAGSTRIPE 500PK | 2 | Nr | 6375 | 12750 | 9562.5 | 3187.5 | 100% | 50% | 0% | 2629.6875 | 557.8125 | 100% | 50% | 0% | 0 | 0 | 0 | 0
Door hardware accessories
8 | Door Position Switch | 238 | Nr | 10 | 2380 | 22.5 | 2357.5 | 100% | 0% | 0% | 1768.125 | 589.375 | 100% | 0% | 0% | 0 | 0 | 0 | 0
9 | Shear Lock with bracket | 10 | Nr | 553 | 5530 | 0 | 5530 | 0% | 0% | 0% | 0 | 5530 | 0% | 0% | 0% | 0 | 0 | 0 | 0
10 | 2 X 600 lbs EM Lock with LED ( Monitored ) | 23 | Nr | 231 | 5313 | 173.25 | 5139.75 | 100% | 0% | 0% | 3854.8125 | 1284.9375 | 100% | 0% | 0% | 0 | 0 | 0 | 0
11 | ZL Bracket Adjustable for elock-600 series | 23 | Nr | 84 | 1932 | 63 | 1869 | 100% | 0% | 0% | 1401.75 | 467.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
12 | Exit Button, Flush Stainless Steel, Square Style, Single Pole | 22 | Nr | 52 | 1144 | 39 | 1105 | 100% | 0% | 0% | 828.75 | 276.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
13 | Emergency Break Glass | 11 | Nr | 53 | 583 | 0 | 583 | 100% | 0% | 0% | 437.25 | 145.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
14 | Intrusion alarm -Panic Button | 2 | Nr | 118 | 236 | 0 | 236 | 100% | 0% | 0% | 177 | 59 | 100% | 0% | 0% | 0 | 0 | 0 | 0
15 | 230V | 85 | Nr | 106 | 9010 | 0 | 9010 | 100% | 0% | 0% | 6757.5 | 2252.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
16 | Backup Battery | 85 | Nr | 59 | 5015 | 0 | 5015 | 100% | 0% | 0% | 3761.25 | 1253.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Cables (PVC cables-Unshidled cable)
17 | 2 Core,18 AWG, 7x26 stranding, bare copper for Power Cables for Lock (305m/roll) | 1 | Nr | 10589 | 10589 | 7941.75 | 2647.25 | 100% | 80% | 0% | 2303.1075 | 344.1425 | 100% | 80% | 0% | 0 | 0 | 0 | 0
18 | 8Core, 22 AWG, 7x30 stranding, bare copper for Card Reader (305m/roll) | 1 | Nr | 17942 | 17942 | 13456.5 | 4485.5 | 100% | 80% | 0% | 3902.385 | 583.115 | 100% | 80% | 0% | 0 | 0 | 0 | 0
19 | 2 Core, 18 AWG, 7x30 stranding, bare copper Cables for Door status input(305m/roll) | 1 | Nr | 13236 | 13236 | 9927 | 3309 | 100% | 80% | 0% | 2878.83 | 430.17 | 100% | 80% | 0% | 0 | 0 | 0 | 0
20 | PC Server + LCD Monitor | 1 | Nr | 10589 | 10589 | 0 | 10589 | 100% | 0% | 0% | 7941.75 | 2647.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
21 | RS485 Cable | 1 | Nr | 22353 | 22353 | 0 | 22353 | 100% | 0% | 0% | 16764.75 | 5588.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
22 | Laser Printer | 1 | Nr | 1177 | 1177 | 0 | 1177 | 100% | 0% | 0% | 882.75 | 294.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
23 | PC station with Monitor and anit virus software | 1 | Nr | 6471 | 6471 | 0 | 6471 | 100% | 0% | 0% | 4853.25 | 1617.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
24 | Badging Printer | 1 | Nr | 8236 | 8236 | 0 | 8236 | 100% | 0% | 0% | 6177 | 2059 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Installation
25 | Accessories | 1 | Ls | 787 | 787 | 0 | 787 | 100% | 0% | 0% | 590.25 | 196.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
26 | Installation, Testing and Commissioning | 1 | Ls | 13379 | 13379 | 0 | 13379 | 0% | 50% |  | 6020.55 | 7358.45 | 0% | 50% |  | 0 | 0 | 0 | 0
F | Digital Signage |  |  |  | 119000 | 2614.5 | 116385.5 | 46.71% |  |  | 54366.57 | 62019 | 0% |  |  | 0 | 0 | 0 | 0
Frontend
1 | 49" Digital Signage Display FullHD 1980x1080, 450cd/m2, 24/7 Proof | 4 | Nr | 5752 | 23008 | 0 | 23008 | 0% | 0% | 0% | 0 | 23008 | 0% | 0% | 0% | 0 | 0 | 0 | 0
2 | 49" Wall Mount Bracket Dual Swing Arm, 18" Extension | 4 | Nr | 889 | 3556 | 0 | 3556 | 0% | 0% | 0% | 0 | 3556 | 0% | 0% | 0% | 0 | 0 | 0 | 0
3 | Digital signage Player 1 Zone | 4 | Nr | 2783 | 11132 | 0 | 11132 | 0% | 0% | 0% | 0 | 11132 | 0% | 0% | 0% | 0 | 0 | 0 | 0
4 | 22" Digital Signage AIO Display FullHD 1920x1080, 250cd/m2, 24/7 Proof | 7 | Nr | 2485 | 17395 | 0 | 17395 | 100% | 0% | 0% | 13046.25 | 4348.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
5 | Digital signage Player 4 Zone | 7 | Nr | 3846 | 26922 | 0 | 26922 | 100% | 0% | 0% | 20191.5 | 6730.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
6 | 22" Wall Mount Bracket Dual Swing Arm, 18" Extension | 7 | Nr | 498 | 3486 | 2614.5 | 871.5 | 0% | 0% | 0% | 0 | 871.5 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Headend
7 | Content Management Server | 1 | Nr | 3258 | 3258 | 0 | 3258 | 100% | 90% | 0% | 2883.33 | 374.67 | 100% | 90% | 0% | 0 | 0 | 0 | 0
8 | 1 Year Support License Software updates and Maintenance support from Onelan | 1 | Lot | 771 | 771 | 0 | 771 | 100% | 90% | 0% | 682.335 | 88.665 | 100% | 90% | 0% | 0 | 0 | 0 | 0
9 | Interface with Property Management System | 1 | Lot | 10423 | 10423 | 0 | 10423 | 100% | 90% | 0% | 9224.355 | 1198.645 | 100% | 90% | 0% | 0 | 0 | 0 | 0
10 | Operator Workstation | 1 | Nr | 5528 | 5528 | 0 | 5528 | 100% | 0% | 0% | 4146 | 1382 | 100% | 0% | 0% | 0 | 0 | 0 | 0
11 | Cables, Connectors & Accessories | 1 | Lot | 3086 | 3086 | 0 | 3086 | 100% | 0% | 0% | 2314.5 | 771.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Services
12 | Installation, Testing & Commissioning | 1 | Lot | 10435 | 10435 | 0 | 10435 |  | 20% | 0% | 1878.3 | 8556.7 |  | 20% | 0% | 0 | 0 | 0 | 0
G | Background Music System |  |  |  | 863286 | 0 | 863286 | 51.93% |  |  | 448335.225 | 414951 | 17.25% |  |  | 71559 | 47178 | 24381 | 71559
Hotel
1 | Networked Digital signal processor | 1 | Nr | 22277 | 22277 | 0 | 22277 | 100% | 0% | 0% | 16707.75 | 5569.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
2 | Input Card | 4 | Nr | 1179 | 4716 | 0 | 4716 | 100% | 0% | 0% | 3537 | 1179 | 100% | 0% | 0% | 0 | 0 | 0 | 0
3 | Output Card | 4 | Nr | 1048 | 4192 | 0 | 4192 | 100% | 0% | 0% | 3144 | 1048 | 100% | 0% | 0% | 0 | 0 | 0 | 0
4 | Dante Card | 1 | Nr | 4848 | 4848 | 0 | 4848 | 100% | 0% | 0% | 3636 | 1212 | 100% | 0% | 0% | 0 | 0 | 0 | 0
5 | DSP card | 1 | Nr | 2621 | 2621 | 0 | 2621 | 100% | 0% | 0% | 1965.75 | 655.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
6 | Networked Digital Singal Processor I/O expander | 2 | Nr | 10483 | 20966 | 0 | 20966 | 100% | 0% | 0% | 15724.5 | 5241.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
7 | Volume Controller and Source Selector | 16 | Nr | 2913 | 46608 | 0 | 46608 | 62.5% | 0% | 0% | 21847.5 | 24760.5 | 62.5% | 0% | 0% | 0 | 0 | 0 | 0
8 | Loudspeaker Type (CM & CF) | 137 | Nr | 525 | 71925 | 0 | 71925 | 100% | 0% | 0% | 53943.75 | 17981.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
9 | Loudspeaker Type (BS) | 19 | Nr | 280 | 5320 | 0 | 5320 | 100% | 0% | 0% | 3990 | 1330 | 100% | 0% | 0% | 0 | 0 | 0 | 0
10 | Ceiling Subwoofer (Type CS) | 13 | Nr | 910 | 11830 | 0 | 11830 | 100% | 0% | 0% | 8872.5 | 2957.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
11 | Landscape Speaker ( Type E) | 7 | Nr | 895 | 6265 | 0 | 6265 | 100% | 0% | 0% | 4698.75 | 1566.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
12 | Wall Mounted Speaker (Type EFR) | 45 | Nr | 1050 | 47250 | 0 | 47250 | 0% | 0% | 0% | 0 | 47250 | 0% | 0% | 0% | 0 | 0 | 0 | 0
13 | Dual USB Charger with Auxillary input (AI 1) | 18 | Nr | 5242 | 94356 | 0 | 94356 | 0% | 0% | 0% | 0 | 94356 | 66.67% | 0% | 0% | 47178 | 47178 | 0 | 47178 | DN-13067
14 | Head Phone Distribution Processor | 1 | Nr | 3931 | 3931 | 0 | 3931 | 0% | 0% | 0% | 0 | 3931 | 0% | 0% | 0% | 0 | 0 | 0 | 0
15 | Source selection Panel with Headphone out (VSH) | 4 | Nr | 1572 | 6288 | 0 | 6288 | 0% | 0% | 0% | 0 | 6288 | 0% | 0% | 0% | 0 | 0 | 0 | 0
16 | Auxillary input (AI) | 8 | Nr | 3276 | 26208 | 0 | 26208 | 0% | 0% | 0% | 0 | 26208 | 0% | 0% | 0% | 0 | 0 | 0 | 0
17 | Dante 2 Channel Expander | 7 | Nr | 3276 | 22932 | 0 | 22932 | 100% | 0% | 0% | 17199 | 5733 | 100% | 0% | 0% | 0 | 0 | 0 | 0
18 | Dante 4 Channel Expander | 3 | Nr | 3276 | 9828 | 0 | 9828 | 100% | 0% | 0% | 7371 | 2457 | 100% | 0% | 0% | 0 | 0 | 0 | 0
19 | Wireless Touchpanel | 8 | Lot | 3276 | 26208 | 0 | 26208 | 100% | 0% | 0% | 19656 | 6552 | 100% | 0% | 0% | 0 | 0 | 0 | 0
20 | Wireless Touchpanel Docking Station | 8 | Lot | 3604 | 28832 | 0 | 28832 | 100% | 0% | 0% | 21624 | 7208 | 100% | 0% | 0% | 0 | 0 | 0 | 0
21 | Processor | 1 | Nr | 5291 | 5291 | 0 | 5291 | 100% | 0% | 0% | 3968.25 | 1322.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
22 | Amplifier (Type 1) | 13 | Nr | 8989 | 116857 | 0 | 116857 | 100% | 0% | 0% | 87642.75 | 29214.25 | 100% | 30% | 0% | 5258.565 | 0 | 5258.565 | 5258.565
23 | Amplifier (Type 2) | 5 | Nr | 8072 | 40360 | 0 | 40360 | 100% | 0% | 0% | 30270 | 10090 | 100% | 30% | 0% | 1816.2 | 0 | 1816.2 | 1816.2
24 | Cables and Connectors | 1 | Lot | 78614 | 78614 | 0 | 78614 | 100% | 20% | 0% | 61318.92 | 17295.08 | 100% | 30% | 0% | 1179.21 | 0 | 1179.21 | 1179.21
25 | Installation,Testing and Commisioning | 1 | Lot | 49111 | 49111 | 0 | 49111 | 0% | 0% | 0% | 0 | 49111 | 0% | 30% | 0% | 2209.995 | 0 | 2209.995 | 2209.995
Apartment
26 | Dante 2 Channel Expander | 3 | Nr | 3276 | 9828 | 0 | 9828 | 100% | 0% | 0% | 7371 | 2457 | 100% | 0% | 0% | 0 | 0 | 0 | 0
27 | Volume Controller and Source Selector | 3 | Nr | 2913 | 8739 | 0 | 8739 | 100% | 0% | 0% | 6554.25 | 2184.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
28 | Loudspeaker (CF) | 36 | Nr | 525 | 18900 | 0 | 18900 | 100% | 0% | 0% | 14175 | 4725 | 100% | 50% | 0% | 1417.5 | 0 | 1417.5 | 1417.5
29 | Loudspeaker (BS) | 3 | Nr | 280 | 840 | 0 | 840 | 100% | 0% | 0% | 630 | 210 | 100% | 0% | 0% | 0 | 0 | 0 | 0
30 | Amplifier | 4 | Nr | 8989 | 35956 | 0 | 35956 | 100% | 0% | 0% | 26967 | 8989 | 100% | 0% | 0% | 0 | 0 | 0 | 0
31 | Dual USB Charger with Auxillary input (AI 1) | 3 | Nr | 5242 | 15726 | 0 | 15726 | 0% | 0% | 0% | 0 | 15726 | 100% | 0% | 0% | 11794.5 | 0 | 11794.5 | 11794.5 | DN-13067
32 | Cables and Connectors | 1 | Lot | 6552 | 6552 | 0 | 6552 | 100% | 20% | 0% | 5110.56 | 1441.44 | 100% | 50% | 0% | 294.84 | 0 | 294.84 | 294.84
33 | Installation,Testing and Commisioning | 1 | Lot | 9111 | 9111 | 0 | 9111 |  | 5% | 0% | 409.995 | 8701.005 |  | 10% | 0% | 409.995 | 0 | 409.995 | 409.995
H | Audio Visual System |  |  |  | 694200 | 0 | 694200 | 28.45% |  |  | 197534.25 | 496666 | 6.484% |  |  | 32202 | 32202 | 0 | 32202
Control room
1 | 24" Monitor Display FullHD, Supports PIP, PBP | 3 | Nr | 1512 | 4536 | 0 | 4536 | 100% | 0% | 0% | 3402 | 1134 | 100% | 0% | 0% | 0 | 0 | 0 | 0
2 | Wall Mount Video & IR Receiver | 3 | Nr | 2632 | 7896 | 0 | 7896 | 0% | 0% | 0% | 0 | 7896 | 0% | 0% | 0% | 0 | 0 | 0 | 0
3 | Camera Feed Reveiver | 3 | Nr | 2632 | 7896 | 0 | 7896 | 0% | 0% | 0% | 0 | 7896 | 0% | 0% | 0% | 0 | 0 | 0 | 0
4 | IR Emitter | 3 | Nr | 132 | 396 | 0 | 396 | 0% | 0% | 0% | 0 | 396 | 0% | 0% | 0% | 0 | 0 | 0 | 0
5 | Technicians Operations Workstation | 1 | Nr | 5814 | 5814 | 0 | 5814 | 100% | 0% | 0% | 4360.5 | 1453.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
6 | Digital Audio Mixer 16 Mono 8 Stereo, 32x32 Dante | 2 | Nr | 32634 | 65268 | 0 | 65268 | 0% | 0% | 0% | 0 | 65268 | 0% | 0% | 0% | 0 | 0 | 0 | 0
7 | Studio Reference Monitor 8" Bi-Amped, Tuned Front-Firing Bass Port | 2 | Nr | 2907 | 5814 | 0 | 5814 | 100% | 0% | 0% | 4360.5 | 1453.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
8 | Lighting Desk Console 48 Channel Faders, 2048 Control Channels | 1 | Nr | 20461 | 20461 | 0 | 20461 | 0% | 0% | 0% | 0 | 20461 | 100% | 0% | 0% | 15345.75 | 15345.75 | 0 | 15345.75 | DN-12942
9 | 9.7" Wireless Touch Control Panel | 1 | Nr | 1925 | 1925 | 0 | 1925 | 100% | 0% | 0% | 1443.75 | 481.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
10 | Table Top Charging Locakable Dock | 1 | Nr | 3387 | 3387 | 0 | 3387 | 100% | 0% | 0% | 2540.25 | 846.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
AV Equipment room
11 | AV Equipment Rack 42U, Floor Mount, 800x800mm | 3 | Nr | 2942 | 8826 |  | 8826 | 100% | 0% | 0% | 6619.5 | 2206.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
12 | 24 Port Patch Panel | 3 | Nr | 618 | 1854 | 0 | 1854 | 100% | 0% | 0% | 1390.5 | 463.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
13 | Wireless Presentation Gateway Collaboration, HDMI In, Airplay Support | 5 | Nr | 5898 | 29490 | 0 | 29490 | 0% | 0% | 0% | 0 | 29490 | 0% | 0% | 0% | 0 | 0 | 0 | 0
14 | BluRay Player | 5 | Nr | 2255 | 11275 | 0 | 11275 | 100% | 0% | 0% | 8456.25 | 2818.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
15 | IPTV Set Top Box | 5 | Nr | 1463 | 7315 | 0 | 7315 | 100% | 0% | 0% | 5486.25 | 1828.75 | 100% | 0% | 0% | 0 | 0 | 0 | 0
16 | 4K Video Decoder | 22 | Nr | 2632 | 57904 | 0 | 57904 | 100% | 0% | 0% | 43428 | 14476 | 100% | 0% | 0% | 0 | 0 | 0 | 0
17 | 4K Video Encoder | 22 | Nr | 2632 | 57904 | 0 | 57904 | 100% | 0% | 0% | 43428 | 14476 | 100% | 0% | 0% | 0 | 0 | 0 | 0
18 | 52 Port Stackable Gigabit POE+ Switch | 2 | Nr | 9205 | 18410 | 0 | 18410 | 0% | 0% | 0% | 0 | 18410 | 0% | 0% | 0% | 0 | 0 | 0 | 0
19 | Network Controller | 1 | Nr | 1662 | 1662 | 0 | 1662 | 0% | 0% | 0% | 0 | 1662 | 0% | 0% | 0% | 0 | 0 | 0 | 0
20 | Rackmount for NHD | 2 | Nr | 1035 | 2070 | 0 | 2070 | 0% | 0% | 0% | 0 | 2070 | 0% | 0% | 0% | 0 | 0 | 0 | 0
21 | Antenna Distribution Amplifier | 4 | Nr | 2434 | 9736 | 0 | 9736 | 0% | 0% | 0% | 0 | 9736 | 0% | 0% | 0% | 0 | 0 | 0 | 0
22 | Wireless Microphone Receiver | 14 | Nr | 1344 | 18816 | 0 | 18816 | 0% | 0% | 0% | 0 | 18816 | 0% | 0% | 0% | 0 | 0 | 0 | 0
23 | Digital Audio Server 4 Channels, 500GB HDD | 1 | Nr | 17442 | 17442 | 0 | 17442 | 100% | 0% | 0% | 13081.5 | 4360.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
24 | Digital Signal Processor | 2 | Nr | 9157 | 18314 | 0 | 18314 | 100% | 0% | 0% | 13735.5 | 4578.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
25 | Feedback Eliminator 2Ch, 24 Filters/Ch, AFS™ technology | 2 | Nr | 1261 | 2522 | 0 | 2522 | 0% | 0% | 0% | 0 | 2522 | 0% | 0% | 0% | 0 | 0 | 0 | 0
26 | 4Ch Power Amplifier 1000W/Ch 100V | 2 | Nr | 12617 | 25234 | 0 | 25234 | 100% | 0% | 0% | 18925.5 | 6308.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
27 | 4Ch Power Amplifier 500W/Ch 100V | 2 | Nr | 9840 | 19680 | 0 | 19680 | 100% | 0% | 0% | 14760 | 4920 | 100% | 0% | 0% | 0 | 0 | 0 | 0
28 | Central Control Processor | 1 | Nr | 10597 | 10597 | 0 | 10597 | 100% | 0% | 0% | 7947.75 | 2649.25 | 100% | 0% | 0% | 0 | 0 | 0 | 0
29 | 2 COM Control Expander | 2 | Nr | 959 | 1918 | 0 | 1918 | 100% | 0% | 0% | 1438.5 | 479.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
30 | IR Emitter | 5 | Nr | 132 | 660 | 0 | 660 | 100% | 0% | 0% | 495 | 165 | 100% | 0% | 0% | 0 | 0 | 0 | 0
31 | AV Network Switch 24 Port, 1G, PoE+, 4SFP+ | 3 | Nr | 3918 | 11754 | 0 | 11754 | 0% | 0% | 0% | 0 | 11754 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Dimmer room
32 | Dimming Equipment Rack 26U, Floor Mount, 800x800mm | 1 | Nr | 2362 | 2362 | 0 | 2362 | 100% | 0% | 0% | 1771.5 | 590.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
33 | 24 Port Patch Panel | 1 | Nr | 618 | 618 | 0 | 618 | 100% | 0% | 0% | 463.5 | 154.5 | 100% | 0% | 0% | 0 | 0 | 0 | 0
34 | 4 Way 19 Pin Patch Bay | 1 | Nr | 6163 | 6163 | 0 | 6163 | 0% | 0% | 0% | 0 | 6163 | 0% | 0% | 0% | 0 | 0 | 0 | 0
35 | 19 Pin Socapex Patch Cord | 4 | Nr | 602 | 2408 | 0 | 2408 | 0% | 0% | 0% | 0 | 2408 | 0% | 0% | 0% | 0 | 0 | 0 | 0
36 | 18 Core Rubber Cabling with Socapex Termination | 1 | Lot | 10019 | 10019 | 0 | 10019 | 0% | 0% | 0% | 0 | 10019 | 0% | 0% | 0% | 0 | 0 | 0 | 0
37 | 24 Channel Dimmer Rack Single Bottom Feed w/ Amp Traps | 1 | Nr | 17091 | 17091 | 0 | 17091 | 0% | 0% | 0% | 0 | 17091 | 100% | 0% | 0% | 12818.25 | 12818.25 | 0 | 12818.25 | DN-12942
38 | DMX Patch Panel | 2 | Nr | 539 | 1078 | 0 | 1078 | 0% | 0% | 0% | 0 | 1078 | 0% | 0% | 0% | 0 | 0 | 0 | 0
39 | 8Ch DMX Combiner | 2 | Nr | 2692 | 5384 | 0 | 5384 | 0% | 0% | 0% | 0 | 5384 | 100% | 0% | 0% | 4038 | 4038 | 0 | 4038 | DN-12942
40 | Network Switch 24 Port, 1G, PoE+, 4SFP+ | 1 | Nr | 3918 | 3918 | 0 | 3918 | 0% | 0% | 0% | 0 | 3918 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Horizontal cable and misc. materials
41 | Cables, Connectors & Accessories Includes all materials required for system finishing, labeling and making good. | 1 | Lot | 11556 | 11556 | 0 | 11556 | 0% | 0% | 0% | 0 | 11556 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Services
42 | Installation | 1 | Lot | 34675 | 34675 | 0 | 34675 |  | 0% | 0% | 0 | 34675 |  | 0% | 0% |  | 0 | 0 | 0
43 | Testing & Commissioning | 1 | Lot | 4954 | 4954 | 0 | 4954 |  | 0% | 0% | 0 | 4954 |  | 0% | 0% | 0 | 0 | 0 | 0
| Indoor broadcast panels (OB1) | [9 empty] | 0 |  |  |  |  | 0
44 | Fabricated Face Plate and Backbox Custom Made 350 x 450 x 250 mm (HxWxD) | 5 | Nr | 1628 | 8140 | 0 | 8140 | 0% | 0% | 0% | 0 | 8140 | 0% | 0% | 0% | 0 | 0 | 0 | 0
45 | Fiber Optic Chassis Connectors | 10 | Nr | 310 | 3100 | 0 | 3100 | 0% | 0% | 0% | 0 | 3100 | 0% | 0% | 0% | 0 | 0 | 0 | 0
46 | Triax Chassis Connectors | 10 | Nr | 1256 | 12560 | 0 | 12560 | 0% | 0% | 0% | 0 | 12560 | 0% | 0% | 0% | 0 | 0 | 0 | 0
47 | RJ45 CAT6 Chassis Connectors | 10 | Nr | 79 | 790 | 0 | 790 | 0% | 0% | 0% | 0 | 790 | 0% | 0% | 0% | 0 | 0 | 0 | 0
48 | HD/SDI Chassis Connectors | 10 | Nr | 59 | 590 | 0 | 590 | 0% | 0% | 0% | 0 | 590 | 0% | 0% | 0% | 0 | 0 | 0 | 0
49 | Audio 3-P XLR Chassis Connectors | 10 | Nr | 16 | 160 | 0 | 160 | 0% | 0% | 0% | 0 | 160 | 0% | 0% | 0% | 0 | 0 | 0 | 0
50 | 24 Pole Multi Audio Connector | 5 | Nr | 313 | 1565 | 0 | 1565 | 0% | 0% | 0% | 0 | 1565 | 0% | 0% | 0% | 0 | 0 | 0 | 0
51 | Twin 13A UK power socket switched | 5 | Nr | 59 | 295 | 0 | 295 | 0% | 0% | 0% | 0 | 295 | 0% | 0% | 0% | 0 | 0 | 0 | 0
52 | Dual Data RJ45 face Plate | 4 | Nr | 70 | 280 | 0 | 280 | 0% | 0% | 0% | 0 | 280 | 0% | 0% | 0% | 0 | 0 | 0 | 0
53 | 125A Power Socket 3-Phase, 230V, PCE Socket | 4 | Nr | 5117 | 20468 | 0 | 20468 | 0% | 0% | 0% | 0 | 20468 | 0% | 0% | 0% | 0 | 0 | 0 | 0
54 | 32A Power Socket 3-Phase, 230V, PCE Socket | 1 | Nr | 311 | 311 | 0 | 311 | 0% | 0% | 0% | 0 | 311 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Outdoor broadcast panels (OB1)
55 | IP65 Rated Face Plate and Backbox Custom Made 650 x 1100 x 300 mm (HxWxD) | 1 | Nr | 4070 | 4070 | 0 | 4070 | 0% | 0% | 0% | 0 | 4070 | 0% | 0% | 0% | 0 | 0 | 0 | 0
56 | Fiber Optic Chassis Connectors | 10 | Nr | 302 | 3020 | 0 | 3020 | 0% | 0% | 0% | 0 | 3020 | 0% | 0% | 0% | 0 | 0 | 0 | 0
57 | Triax Chassis Connectors | 10 | Nr | 1047 | 10470 | 0 | 10470 | 0% | 0% | 0% | 0 | 10470 | 0% | 0% | 0% | 0 | 0 | 0 | 0
58 | RJ45 CAT6 Chassis Connectors | 10 | Nr | 79 | 790 | 0 | 790 | 0% | 0% | 0% | 0 | 790 | 0% | 0% | 0% | 0 | 0 | 0 | 0
59 | HD/SDI Chassis Connectors | 10 | Nr | 45 | 450 | 0 | 450 | 0% | 0% | 0% | 0 | 450 | 0% | 0% | 0% | 0 | 0 | 0 | 0
60 | Audio 3-P XLR Chassis Connectors | 10 | Nr | 17 | 170 | 0 | 170 | 0% | 0% | 0% | 0 | 170 | 0% | 0% | 0% | 0 | 0 | 0 | 0
61 | 24 Pole Multi Audio Connector | 5 | Nr | 313 | 1565 | 0 | 1565 | 0% | 0% | 0% | 0 | 1565 | 0% | 0% | 0% | 0 | 0 | 0 | 0
62 | Twin 13A UK power socket switched | 2 | Nr | 59 | 118 | 0 | 118 | 0% | 0% | 0% | 0 | 118 | 0% | 0% | 0% | 0 | 0 | 0 | 0
63 | Dual Data RJ45 face Plate | 1 | Nr | 70 | 70 | 0 | 70 | 0% | 0% | 0% | 0 | 70 | 0% | 0% | 0% | 0 | 0 | 0 | 0
64 | 125A Power Socket 3-Phase, 230V, PCE Socket | 1 | Nr | 5117 | 5117 | 0 | 5117 | 0% | 0% | 0% | 0 | 5117 | 0% | 0% | 0% | 0 | 0 | 0 | 0
65 | 32A Power Socket 3-Phase, 230V, PCE Socket | 1 | Nr | 311 | 311 | 0 | 311 | 0% | 0% | 0% | 0 | 311 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Interconnect cabling
66 | Fiber Optic Cable 4 Core, SM, LSZH | 1 | Lot | 2035 | 2035 | 0 | 2035 | 0% | 0% | 0% | 0 | 2035 | 0% | 0% | 0% | 0 | 0 | 0 | 0
67 | CAT6 Cable 4 Pair, UTP, PVC | 1 | Lot | 1861 | 1861 | 0 | 1861 | 0% | 0% | 0% | 0 | 1861 | 0% | 0% | 0% | 0 | 0 | 0 | 0
68 | HD-SDI Cable 75ohm, 1.0/4.7, LSZH | 1 | Lot | 4605 | 4605 | 0 | 4605 | 0% | 0% | 0% | 0 | 4605 | 0% | 0% | 0% | 0 | 0 | 0 | 0
69 | Audio Cable 2 Pair, Foil Shield, LSZH | 1 | Lot | 4605 | 4605 | 0 | 4605 | 0% | 0% | 0% | 0 | 4605 | 0% | 0% | 0% | 0 | 0 | 0 | 0
70 | Traix Cable 8mm, LSZH | 1 | Lot | 12035 | 12035 | 0 | 12035 | 0% | 0% | 0% | 0 | 12035 | 0% | 0% | 0% | 0 | 0 | 0 | 0
71 | Multi Audio Cable 8 Pair, Foil Shield | 1 | Lot | 6716 | 6716 | 0 | 6716 | 0% | 0% | 0% | 0 | 6716 | 0% | 0% | 0% | 0 | 0 | 0 | 0
72 | Mounts, Patches cords & Accessories | 1 | Lot | 6512 | 6512 | 0 | 6512 | 0% | 0% | 0% | 0 | 6512 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Services
73 | Installation, Testing & Commissioning | 1 | Lot | 24419 | 24419 | 0 | 24419 |  | 0% | 0% | 0 | 24419 |  | 0% | 0% | 0 | 0 | 0 | 0
I | Gate barrier and Intercom system |  |  |  | 32564 | 14473.38 | 18090.62 | 0% |  |  | 0 | 18091 | 0% |  |  | 0 | 0 | 0 | 0
Frontend
1 | Gard 3 3000 Barrier | 1 | Nr | 6230.11 | 6230.11 | 4672.5825 | 1557.5275 | 0% | 0% | 0% | 0 | 1557.5275 | 0% | 0% | 0% | 0 | 0 | 0 | 0
2 | Gard 3 3000 Barrier | 1 | Nr | 6230.11 | 6230.11 | 4672.5825 | 1557.5275 | 0% | 0% | 0% | 0 | 1557.5275 | 0% | 0% | 0% | 0 | 0 | 0 | 0
3 | Semi Oval boom | 2 | Nr | 606.17 | 1212.34 | 909.255 | 303.085 | 0% | 0% | 0% | 0 | 303.085 | 0% | 0% | 0% | 0 | 0 | 0 | 0
4 | Break Away boom | 2 | Nr | 1497.23 | 2994.46 | 2245.845 | 748.615 | 0% | 0% | 0% | 0 | 748.615 | 0% | 0% | 0% | 0 | 0 | 0 | 0
5 | Balancing Soring | 2 | Nr | 187.92 | 375.84 | 281.88 | 93.96 | 0% | 0% | 0% | 0 | 93.96 | 0% | 0% | 0% | 0 | 0 | 0 | 0
6 | Dome Shaped Flash Light | 2 | Nr | 133.36 | 266.72 | 200.04 | 66.68 | 0% | 0% | 0% | 0 | 66.68 | 0% | 0% | 0% | 0 | 0 | 0 | 0
7 | Support For DIR Photocell | 2 | Nr | 48.5 | 97 | 72.75 | 24.25 | 0% | 0% | 0% | 0 | 24.25 | 0% | 0% | 0% | 0 | 0 | 0 | 0
8 | Pair of Photocell | 2 | Nr | 187.5 | 375 | 281.88 | 93.12 | 0% | 0% | 0% | 0 | 93.12 | 0% | 0% | 0% | 0 | 0 | 0 | 0
9 | Black Anodized post | 2 | Nr | 103.05 | 206.1 | 154.575 | 51.525 | 0% | 0% | 0% | 0 | 51.525 | 0% | 0% | 0% | 0 | 0 | 0 | 0
10 | 24 V AC-DC Magnetic Sensor | 2 | Nr | 654.66 | 1309.32 | 981.99 | 327.33 | 0% | 0% | 0% | 0 | 327.33 | 0% | 0% | 0% | 0 | 0 | 0 | 0
11 | Intercom | 1 | Nr | 10208.16 | 10208.16 | 0 | 10208.16 | 0% | 0% | 0% | 0 | 10208.16 | 0% | 0% | 0% | 0 | 0 | 0 | 0
Services
12 | Accessories | 1 | Nr | 705.89 | 705.89 | 0 | 705.89 | 0% | 0% | 0% | 0 | 705.89 | 0% | 0% | 0% | 0 | 0 | 0 | 0
13 | Installation, Testing & Commissioning | 1 | Nr | 2352.95 | 2352.95 | 0 | 2352.95 |  | 0% | 0% | 0 | 2352.95 |  | 0% | 0% | 0 | 0 | 0 | 0
J | PABX |  |  |  | 525799.91 | 0 | 525799.91 | 77.74% |  |  | 408760.6077 | 117039 | 0% |  |  | 0 | 0 | 0 | 0
Voice boards
1 | Pack including one GA3 board aquipped with one additional ARMADA board | 1 | Nr | 6843.17 | 6843.17 | 0 | 6843.17 | 100% | 70% | 0% | 5850.9104 | 992.2596 | 100% | 70% | 0% | 0 | 0 | 0 | 0
2 | APA8 Analog trunk access board for 8 trunk lines | 1 | Nr | 908.81 | 908.81 | 0 | 908.81 | 100% | 70% | 0% | 777.0326 | 131.7774 | 100% | 70% | 0% | 0 | 0 | 0 | 0
3 | APA4 Analog trunk access board for 4 trunk lines | 1 | Nr | 463.25 | 463.25 | 0 | 463.25 | 100% | 70% | 0% | 396.0788 | 67.1712 | 100% | 70% | 0% | 0 | 0 | 0 | 0
4 | CLIDSP APA daughtercard for local management of CLI signals | 2 | Nr | 137.92 | 275.84 | 0 | 275.84 | 100% | 70% | 0% | 235.8432 | 39.9968 | 100% | 70% | 0% | 0 | 0 | 0 | 0
5 | Digital Public Access Board - 1 Primary Rate E1 T2 Access | 2 | Nr | 2058.09 | 4116.18 | 0 | 4116.18 | 100% | 70% | 0% | 3519.3339 | 596.8461 | 100% | 70% | 0% | 0 | 0 | 0 | 0
Data infrastructure
6 | Generic power cord | 4 | Nr | 26.53 | 106.12 | 0 | 106.12 | 100% | 70% | 0% | 90.7326 | 15.3874 | 100% | 70% | 0% | 0 | 0 | 0 | 0
7 | Mounting kit for Rack 3 | 2 | Nr | 102.56 | 205.12 | 0 | 205.12 | 100% | 70% | 0% | 175.3776 | 29.7424 | 100% | 70% | 0% | 0 | 0 | 0 | 0
8 | Blind slot stiffner (x1) | 11 | Nr | 21.22 | 233.42 | 0 | 233.42 | 100% | 70% | 0% | 199.5741 | 33.8459 | 100% | 70% | 0% | 0 | 0 | 0 | 0
9 | Up to 4xV24 accesses over IP (230V) | 1 | Nr | 1769.89 | 1769.89 | 0 | 1769.89 | 100% | 70% | 0% | 1513.2559 | 256.6341 | 100% | 70% | 0% | 0 | 0 | 0 | 0
Basic packages
10 | Alcatel-Lucent IP Media Gateway cabinets (2xMR3), with 230V power supply (must be used with external battery and rack) | 1 | Nr | 5987.78 | 5987.78 | 0 | 5987.78 | 100% | 70% | 0% | 5119.5519 | 868.2281 | 100% | 70% | 0% | 0 | 0 | 0 | 0
Applications
11 | CCdistribution Contact Center Distribution Starter Pack including 5 agents + 1 mono site supervisor software license | 1 | Nr | 9071.77 | 9071.77 | 0 | 9071.77 | 100% | 70% | 0% | 7756.3634 | 1315.4066 | 100% | 70% | 0% | 0 | 0 | 0 | 0
12 | CSTA 500 bypass software license | 2 | Nr | 0.13 | 0.26 | 0 | 0.26 | 100% | 70% | 0% | 0.2223 | 0.0377 | 100% | 70% | 0% | 0 | 0 | 0 | 0
13 | Local Ticket Accounting service software license - 1 user | 938 | Nr | 10.61 | 9952.18 | 0 | 9952.18 | 100% | 70% | 0% | 8509.1139 | 1443.0661 | 100% | 70% | 0% | 0 | 0 | 0 | 0
14 | External SIP based Voice Mail software license - 1 user | 938 | Nr | 30.06 | 28196.28 | 0 | 28196.28 | 100% | 70% | 0% | 24107.8194 | 4088.4606 | 100% | 70% | 0% | 0 | 0 | 0 | 0
15 | Hospitality Services sotware license - 1 user | 716 | Nr | 19.45 | 13926.2 | 0 | 13926.2 | 100% | 70% | 0% | 11906.901 | 2019.299 | 100% | 70% | 0% | 0 | 0 | 0 | 0
16 | Java Runtime Environment license | 1 | Nr | 0.16 | 0.16 | 0 | 0.16 | 100% | 70% | 0% | 0.1368 | 0.0232 | 100% | 70% | 0% | 0 | 0 | 0 | 0
17 | CCSupervision CD-ROM | 1 | Nr | 102.56 | 102.56 | 0 | 102.56 | 100% | 70% | 0% | 87.6888 | 14.8712 | 100% | 70% | 0% | 0 | 0 | 0 | 0
User software licenses
18 | SIP network link software license | 12 | Nr | 171.51 | 2058.12 | 0 | 2058.12 | 100% | 70% | 0% | 1759.6926 | 298.4274 | 100% | 70% | 0% | 0 | 0 | 0 | 0
19 | OmniPCX Enterprise software server license | 1 | Nr | 0.16 | 0.16 | 0 | 0.16 | 100% | 70% | 0% | 0.1368 | 0.0232 | 100% | 70% | 0% | 0 | 0 | 0 | 0
20 | OmniPCX Enterprise software server license for redundancy | 1 | Nr | 0.16 | 0.16 | 0 | 0.16 | 100% | 70% | 0% | 0.1368 | 0.0232 | 100% | 70% | 0% | 0 | 0 | 0 | 0
21 | IP Premium license - 1 user | 127 | Nr | 252.85 | 32111.95 | 0 | 32111.95 | 100% | 70% | 0% | 27455.7173 | 4656.2327 | 100% | 70% | 0% | 0 | 0 | 0 | 0
22 | Mobile WLAN IP Touch Premium license - 1 user | 5 | Nr | 252.85 | 1264.25 | 0 | 1264.25 | 100% | 70% | 0% | 1080.9337 | 183.3163 | 100% | 70% | 0% | 0 | 0 | 0 | 0
23 | SIP Premium license - 1 user | 806 | Nr | 252.85 | 203797.1 | 0 | 203797.1 | 100% | 70% | 0% | 174246.5205 | 29550.5795 | 100% | 70% | 0% | 0 | 0 | 0 | 0
24 | OmniPCX Enterprise High Availability service - Base license | 1 | Nr | 1555.94 | 1555.94 | 0 | 1555.94 | 100% | 70% | 0% | 1330.3287 | 225.6113 | 100% | 70% | 0% | 0 | 0 | 0 | 0
25 | OmniPCX Enterprise High Availability – 1 Business Telephony user license | 938 | Nr | 1.95 | 1829.1 | 0 | 1829.1 | 100% | 70% | 0% | 1563.8805 | 265.2195 | 100% | 70% | 0% | 0 | 0 | 0 | 0
26 | OmniPCX Enterprise High Availability – 1 Contact Center user license | 5 | Nr | 38.9 | 194.5 | 0 | 194.5 | 100% | 70% | 0% | 166.2975 | 28.2025 | 100% | 70% | 0% | 0 | 0 | 0 | 0
27 | Alcatel-Lucent OmniPCX Enterprise R12.2 software license | 1 | Nr | 0.16 | 0.16 | 0 | 0.16 | 100% | 70% | 0% | 0.1368 | 0.0232 | 100% | 70% | 0% | 0 | 0 | 0 | 0
28 | OmniPCX Entreprise Release R12.2 | 1 | Nr | 0.16 | 0.16 | 0 | 0.16 | 100% | 70% | 0% | 0.1368 | 0.0232 | 100% | 70% | 0% | 0 | 0 | 0 | 0
OEM Hardware
29 | OmniPCX Enterprise basic package equipped with a HP Generic Appliance Server when deployed without OTMS | 1 | Nr | 4584.3 | 4584.3 | 0 | 4584.3 | 100% | 50% | 0% | 3782.0475 | 802.2525 | 100% | 50% | 0% | 0 | 0 | 0 | 0
30 | HP Generic Appliance Server for redundancy when deployed without OTMS, OmniPCX Enterprise software installed | 1 | Nr | 4584.3 | 4584.3 | 0 | 4584.3 | 100% | 50% | 0% | 3782.0475 | 802.2525 | 100% | 50% | 0% | 0 | 0 | 0 | 0
31 | Alcatel-Lucent 8128 WLAN Handset includes set, battery, belt clip, regulatory sheet | 1 | Nr | 841.63 | 841.63 | 0 | 841.63 | 100% | 50% | 0% | 694.3447 | 147.2853 | 100% | 50% | 0% | 0 | 0 | 0 | 0
32 | Desktop charger with UK-US-AUS mains plug for Alcatel-Lucent OmniTouch 8118 and 8128 WLAN Handset | 1 | Nr | 102.56 | 102.56 | 0 | 102.56 | 100% | 50% | 0% | 84.612 | 17.948 | 100% | 50% | 0% | 0 | 0 | 0 | 0
33 | Configuration cradle for Alcatel-Lucent OmniTouch 8118 et 8128 WLAN Handset. Cradle connected to PC with included USB cable. | 1 | Nr | 259.92 | 259.92 | 0 | 259.92 | 100% | 50% | 0% | 214.434 | 45.486 | 100% | 50% | 0% | 0 | 0 | 0 | 0
34 | OT4135 IP Conference Phone Pack, OT4135 IP Conference Phone bundled with Accessories (Network Cable, Expansion Microphones and Transformer) | 4 | Nr | 1702.7 | 6810.8 | 0 | 6810.8 | 100% | 50% | 0% | 5618.91 | 1191.89 | 100% | 50% | 0% | 0 | 0 | 0 | 0
DEM software
35 | 4059EE IP US English Attendant pack including USB attendant keyboard, keys set, DVD attendant software and 4059EEE license | 2 | Nr | 3655.43 | 7310.86 | 0 | 7310.86 | 100% | 0% | 0% | 5483.145 | 1827.715 | 100% | 0% | 0% | 0 | 0 | 0 | 0
36 | Suse Linux SW license | 2 | Nr | 777.97 | 1555.94 | 0 | 1555.94 | 100% | 0% | 0% | 1166.955 | 388.985 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Software support services
37 | OmniPCX Enterprise SPS (Solution Premier Service) | 2 | Nr | 21368.21 | 42736.42 | 0 | 42736.42 | 100% | 0% | 0% | 32052.315 | 10684.105 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Voice mail & call accounting
38 | Voice Mail System | 1 | Nr | 44366.47 | 44366.47 | 0 | 44366.47 | 100% | 0% | 0% | 33274.8525 | 11091.6175 | 100% | 0% | 0% | 0 | 0 | 0 | 0
39 | Call Accounting | 1 | Nr | 43926.12 | 43926.12 | 0 | 43926.12 | 100% | 0% | 0% | 32944.59 | 10981.53 | 100% | 0% | 0% | 0 | 0 | 0 | 0
Services
40 | Installation, Testing & Commissioning | 1 | Lot | 43750 | 43750 | 0 | 43750 |  | 30% | 0% | 11812.5 | 31937.5 |  | 30% | 0% | 0 | 0 | 0 | 0
K | UPS |  |  |  | 150902.075 | 0 | 150902.075 | 87.51% |  |  | 132053.1064 | 18849 | 0% |  |  | 0 | 0 | 0 | 0
UPS IDF
1 | Legrand 2000VA Tower/Rack (convertible),Zero Transfer,USB port and slots communication cards,WEB/SNMP interface(Optional), software included | 23 | Nr | 3250 | 74750 | 0 | 74750 | 100% | 90% | 0% | 66153.75 | 8596.25 | 100% | 90% | 0% | 0 | 0 | 0 | 0
2 | Legrand 2000VA Tower/Rack (convertible),Zero Transfer,USB port and slots communication cards,WEB/SNMP interface(Optional), software included | 3 | Nr | 3250 | 9750 | 0 | 9750 | 100% | 90% | 0% | 8628.75 | 1121.25 | 100% | 90% | 0% | 0 | 0 | 0 | 0
3 | Battery Pack for UPS 2000VA | 3 | Nr | 2425 | 7275 | 0 | 7275 | 100% | 90% | 0% | 6438.375 | 836.625 | 100% | 90% | 0% | 0 | 0 | 0 | 0
4 | Legrand 3000VA Tower/Rack (convertible),Zero Transfer,USB port and slots communication cards,WEB/SNMP interface(Optional), software included | 3 | Nr | 3608.025 | 10824.075 | 0 | 10824.075 | 100% | 90% | 0% | 9579.3064 | 1244.7686 | 100% | 90% | 0% | 0 | 0 | 0 | 0
5 | Battery Pack for UPS3000VA | 5 | Nr | 2528 | 12640 | 0 | 12640 | 100% | 90% | 0% | 11186.4 | 1453.6 | 100% | 90% | 0% | 0 | 0 | 0 | 0
6 | RAILKIT for rackmounting | 37 | Nr | 233 | 8621 | 0 | 8621 | 100% | 90% | 0% | 7629.585 | 991.415 | 100% | 90% | 0% | 0 | 0 | 0 | 0
7 | SNMP | 29 | Nr | 620 | 17980 | 0 | 17980 | 100% | 90% | 0% | 15912.3 | 2067.7 | 100% | 90% | 0% | 0 | 0 | 0 | 0
Services
8 | Installation, Testing & Commissioning | 1 | Lot | 9062 | 9062 | 0 | 9062 |  | 80% | 0% | 6524.64 | 2537.36 |  | 80% | 0% | 0 | 0 | 0 | 0
L | CCTV Recording |  |  |  | 80000 | 0 | 80000 | 88.5% |  |  | 70800 | 9200 | 0% |  |  | 0 | 0 | 0 | 0
1 | CCTV recording for 31 days as per new SIRA law | 1 | Nr | 80000 | 80000 | 0 | 80000 | 88.5% |  |  | 70800 | 9200 | 88.5% |  |  | 0 | 0 | 0 | 0
| Sub contract amount |  |  |  | 9563037.9859 | 646807.589 | 8916230.3968 | 74.24% |  |  | 6619111.33 | 2297118 | 8.643% |  |  | 198538 | 82629 | 115909 | 198538
VO-7 | Additional Data Outlets for LCPs | 1 | Item | 2531.3 | 2531.3 | 0 | 2531.3 | 75% |  |  | 1898.475 | 632.825 | 75% |  |  | 0 | 0 | 0 | 0
| Cat6A F/UTP 23 AWG LSZH cable | 2 | Roll | 683 | 1366 | 0 | 1366 | 100% | 95% |  | 1219.155 | 146.845 | 100% | 95% |  | 0 | 0 | 0 | 0
| 180° Cat6A Unshielded Modular Jack of RIDC | 10 | Nr | 24 | 240 | 0 | 240 | 100% | 95% |  | 214.2 | 25.8 | 100% | 95% |  | 0 | 0 | 0 | 0
| Installation, Termination, Testing & Commissioning | 1 | LOT | 925.3 | 925.3 | 0 | 925.3 |  | 55.85% |  | 465.1262 | 460.1738 |  | 55.85% |  | 0 | 0 | 0 | 0
VO-8 | Additional BOH Offices and Basement 1 Kitchen Points | 1 | Item | 77832.1 | 77832.1 | 0 | 77832.1 | 30% |  |  | 23349.63 | 54482.47 | 59.81% |  |  | 32587.1854 | 31133.25 | 1453.9354 | 32587.1854
Structured Cabling System
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 105 | Nr | 23.53 | 2470.65 | 0 | 2470.65 | 100% | 25% | 0% | 1945.6369 | 525.0131 | 100% | 50% | 0% | 92.6494 |  | 92.6494 | 92.6494
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 105 | Nr | 23.53 | 2470.65 | 0 | 2470.65 | 100% | 0% | 0% | 1852.9875 | 617.6625 | 100% | 50% | 0% | 185.2987 |  | 185.2987 | 185.2987
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M | 105 | Nr | 25.88 | 2717.4 | 0 | 2717.4 | 100% | 0% | 0% | 2038.05 | 679.35 | 100% | 0% | 0% | 0 |  | 0 | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M | 105 | Nr | 25.88 | 2717.4 | 0 | 2717.4 | 0% | 0% | 0% | 0 | 2717.4 | 0% | 0% | 0% | 0 |  | 0 | 0
| 1U, 24 Port Cat6A Patch Panel, unloaded | 5 | Nr | 66 | 330 | 0 | 330 | 100% | 80% | 0% | 287.1 | 42.9 | 100% | 80% | 0% | 0 |  | 0 | 0
| 1U, Cable Manager | 5 | Nr | 63 | 315 | 0 | 315 | 100% | 80% | 0% | 274.05 | 40.95 | 100% | 80% | 0% | 0 |  | 0 | 0
| Cat6A F/UTP 23 AWG LSZH Cable | 24 | Roll | 683 | 16392 | 0 | 16392 | 100% | 100% | 0% | 14752.8 | 1639.2 | 100% | 100% | 0% | 0 |  | 0 | 0
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 5500 | 5500 | 0 | 5500 |  | 44.42% | 0% | 2199.0128 | 3300.9872 |  | 60% | 0% | 770.9872 |  | 770.9872 | 770.9872
Active Components
| Catalyst 9200 48-port PoE+ , Network Essentials | 3 | Nr | 7246 | 21738 | 0 | 21738 |  |  |  | 0 | 21738 | 100% |  |  | 16303.5 | 16303.5 | 0 | 16303.5 | DN-13092
| Catalyst 9200 4*10G , Network Module | 3 | Nr | 2240 | 6720 | 0 | 6720 |  |  |  | 0 | 6720 | 100% |  |  | 5040 | 5040 | 0 | 5040 | DN-12866
| C9200 Cisco DNA Essentials, 48-Port - 3 Year Term Licenses | 3 | Nr | 1255 | 3765 | 0 | 3765 |  |  |  | 0 | 3765 | 100% |  |  | 2823.75 | 2823.75 | 0 | 2823.75 | DN-13092
| 10GBASE-SR SFP Module, Enterprise-Class | 12 | Nr | 774 | 9288 | 0 | 9288 |  |  |  | 0 | 9288 | 100% |  |  | 6966 | 6966 | 0 | 6966 | DN-13015
| SNTC-NO RMA Catalyst 9200 48-port PoE+, Network Esse | 3 | Nr | 636 | 1908 | 0 | 1908 |  |  |  | 0 | 1908 |  |  |  | 0
| Installation | [14 empty] | 0
| Installation,Termination, Testing and Commisioning | 1 | Lot | 1500 | 1500 | 0 | 1500 |  |  |  | 0 | 1500 |  | 30% |  | 405 |  | 405 | 405
VO-9 | Additional Outlets for Engineering Office | 1 | Item | 17614.24 | 17614.24 | 0 | 17614.24 | 20% |  |  | 3522.848 | 14091.392 | 67.8% |  |  | 8419.884 | 7101.75 | 1318.134 | 8419.884
Structured Cabling System
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 32 | Nr | 23.53 | 752.96 | 0 | 752.96 | 100% |  |  | 564.72 | 188.24 | 100% | 60% |  | 67.7664 |  | 67.7664 | 67.7664
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 32 | Nr | 23.53 | 752.96 | 0 | 752.96 | 100% |  |  | 564.72 | 188.24 | 100% | 60% |  | 67.7664 |  | 67.7664 | 67.7664
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M | 32 | Nr | 25.88 | 828.16 | 0 | 828.16 | 0% |  |  | 0 | 828.16 | 0% |  |  | 0 |  | 0 | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M | 32 | Nr | 25.88 | 828.16 | 0 | 828.16 | 0% |  |  | 0 | 828.16 | 0% |  |  | 0 |  | 0 | 0
| 1U, 24 Port Cat6A Patch Panel, unloaded | 1 | Nr | 66 | 66 | 0 | 66 | 100% | 30% |  | 52.47 | 13.53 | 100% | 60% |  | 2.97 |  | 2.97 | 2.97
| 1U, Cable Manager | 1 | Nr | 63 | 63 | 0 | 63 | 100% | 30% |  | 50.085 | 12.915 | 100% | 60% |  | 2.835 |  | 2.835 | 2.835
| Cat6A F/UTP 23 AWG LSZH Cable | 4 | Roll | 683 | 2732 | 0 | 2732 | 100% | 30% |  | 2171.94 | 560.06 | 100% | 60% |  | 122.94 |  | 122.94 | 122.94
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 1320 | 1320 | 0 | 1320 |  | 10.01% |  | 118.9188 | 1201.0812 |  | 20% |  | 118.6812 |  | 118.6812 | 118.6812
Active Components
| Catalyst 9200 24-port PoE+ , Network Essentials | 1 | Nr | 3449 | 3449 | 0 | 3449 |  |  |  | 0 | 3449 | 100% | 50% |  | 2845.425 | 2586.75 | 258.675 | 2845.425 | DN-13092
| Catalyst 9200 4*10G , Network Module | 1 | Nr | 2240 | 2240 | 0 | 2240 |  |  |  | 0 | 2240 | 100% | 50% |  | 1848 | 1680 | 168 | 1848 | DN-12866
| C9200 Cisco DNA Essentials, 24-Port - 3 Year Licenses | 1 | Nr | 684 | 684 | 0 | 684 |  |  |  | 0 | 684 | 100% | 50% |  | 564.3 | 513 | 51.3 | 564.3 | DN-13092
| 10GBASE-SR SFP Module, Enterprise-Class | 4 | Nr | 774 | 3096 | 0 | 3096 |  |  |  | 0 | 3096 | 100% | 50% |  | 2554.2 | 2322 | 232.2 | 2554.2 | DN-13015
| SNTC-NO RMA Catalyst 9200 24-port PoE+, Network Esse | 1 | Nr | 302 | 302 | 0 | 302 |  |  |  | 0 | 302 |  |  |  | 0 |  | 0 | 0
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 500 | 500 | 0 | 500 |  |  |  | 0 | 500 |  | 50% |  | 225 |  | 225 | 225
VO-10 | Additional Points in Level 3 | 1 | Item | 11164.58 | 11164.58 | 0 | 11164.58 | 30% |  |  | 3349.3691 | 7815.2109 | 30% |  |  | 4770.3094 | 3680.25 | 1090.0594 | 4770.3094 | 0
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 19 | Nr | 23.53 | 447.07 | 0 | 447.07 | 100% |  |  | 335.3025 | 111.7675 | 100% | 50% |  | 33.5303 |  | 33.5303 | 33.5303
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 19 | Nr | 23.53 | 447.07 | 0 | 447.07 | 100% |  |  | 335.3025 | 111.7675 | 100% | 50% |  | 33.5303 |  | 33.5303 | 33.5303
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 19 | Nr | 25.88 | 491.72 | 0 | 491.72 | 100% |  |  | 368.79 | 122.93 | 100% | 50% |  | 36.879 |  | 36.879 | 36.879
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 19 | Nr | 25.88 | 491.72 | 0 | 491.72 | 100% |  |  | 368.79 | 122.93 | 100% | 50% |  | 36.879 |  | 36.879 | 36.879
| 1U, 24 Port Cat6A Patch Panel, unloaded | 1 | Nr | 66 | 66 | 0 | 66 | 100% | 65% |  | 55.935 | 10.065 | 100% | 70% |  | 0.495 |  | 0.495 | 0.495
| 1U, Cable Manager | 1 | Nr | 63 | 63 | 0 | 63 | 100% | 65% |  | 53.3925 | 9.6075 | 100% | 70% |  | 0.4725 |  | 0.4725 | 0.4725
| Cat6A F/UTP 23 AWG LSZH Cable | 3 | Lot | 683 | 2049 | 0 | 2049 | 100% | 65% |  | 1736.5275 | 312.4725 | 100% | 70% |  | 15.3675 |  | 15.3675 | 15.3675
| Active Components | [16 empty] | 0 | 0
| Catalyst 9200 24-port PoE+ , Network Essentials | 1 | Nr | 3449 | 3449 | 0 | 3449 |  |  |  | 0 | 3449 | 100% | 70% |  | 2948.895 | 2586.75 | 362.145 | 2948.895 | DN-13092
| Catalyst 9200 4*10G , Network Module | 1 | Nr | 2240 |  | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0
| C9200 Cisco DNA Essentials, 24-Port - 3 Year Term Licenses | 1 | Nr | 684 | 684 | 0 | 684 |  |  |  | 0 | 684 | 100% | 70% |  | 584.82 | 513 | 71.82 | 584.82 | DN-13092
| 10GBASE-SR SFP Module, Enterprise-Class | 1 | Nr | 774 | 774 | 0 | 774 |  |  |  | 0 | 774 | 100% | 70% |  | 661.77 | 580.5 | 81.27 | 661.77 | DN-13015
| SNTC-NO RMA Catalyst 9200 24-port PoE+, Network Esse | 1 | Nr | 302 | 302 | 0 | 302 |  |  |  | 0 | 302 |  |  |  | 0
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 1900 | 1900 | 0 | 1900 |  | 5.575% |  | 95.3291 | 1804.6709 |  | 30% |  | 417.6709 |  | 417.6709 | 417.6709
VO-16 | AV Cost Saving | 1 | Item | -137198 | -137198 | 0 | -137198 | 0% |  |  | 0 | -137198 | 10.29% |  |  | -14118.621 | -7197.2263 | -6921.3947 | -14118.621
| AV Cost Saving | 1 | LOT | -137198 | -137198 | 0 | -137198 | 0% | 0% | 0% | 0 | -137198 | 10.29% |  |  | -14118.621 | -7197.2263 | -6921.3947 | -14118.621
VO-17 | Digital Signage Saving | 1 | Item | -49878.18 | -49878.18 | 0 | -49878.18 | 0% |  |  | 0 | -49878.18 | 10.29% |  |  | -5132.8089 | -2616.5436 | -2516.2653 | -5132.8089
| Digital Signage Saving | 1 | LOT | -49878.18 | -49878.18 | 0 | -49878.18 | 0% | 0% | 0% | 0 | -49878.18 | 10.29% |  |  | -5132.8089 | -2616.5436 | -2516.2653 | -5132.8089
VO-18 | Negotiations Adjustment | 1 | Item | 79231.04 | 79231.04 | 0 | 79231.04 | 0% |  |  | 0 | 79231.04 | 10.29% |  |  | 8153.4208 | 4156.3559 | 3997.0648 | 8153.4208
| Negotiations Adjustment | 1 | Item | 79231.04 | 79231.04 | 0 | 79231.04 | 0% | 0% | 0% | 0 | 79231.04 | 10.29% |  |  | 8153.4208 | 4156.3559 | 3997.0648 | 8153.4208
Overall | Variations |  |  |  | 1297.08 | 0 | 1297.08 | 2476% |  |  | 32120.3221 | -30823.2421 | -112.5% |  |  | 34679.3697 | 36257.8361 |  | 34679.3697

## L. Fire Stop
Plot 18 - Dorchester | [7 empty] | DIRECT WORKS
IPC Ref | IPC-11
Package | Fire Stopping (Sealant) works on MEP Penetrations | [6 empty] | RE-MEASUREMENT
Subcontractor | Fire Stop Middle East LLC
ITEM | DESCRIPTION | AMOUNT AS PER SUBCONTRACT REF. 201F22002/12 WITH KMEP | % OF COMPLETED WORKS | ANTICIPITATED CONTRACT AMOUNT | PREVIOUS | CURRENT | CUMULATIVE
SUBCONTRACT WORKS
A | Supply and apply firestop sealant and mineral wool backing to non-insulated metallic/ non-combustible pipes (Single Sided) | 5755 | 140.9% | 8107 | 7241 | 866 | 8107 | 140.9%
B | Supply and apply firestop sealant and mineral wool backing to insulated metallic/ non-combustible pipes (Single Sided) | 17300 | 122.6% | 21210 | 12422 | 8788 | 21210 | 122.6%
C | Supply and apply firestop sealant and mineral wool backing to PVC/ combustible pipes (Single Sided) | 71475 | 145.7% | 104146 | 87076 | 17070 | 104146 | 145.7%
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings (Single Board) | 67875 | 22.53% | 15295 | 14220 | 1075 | 15295 | 22.53%
E | Supply and apply firestopping materials to Metallic Duct with Fire Damper and L-angle (Single Sided) | 29700 | 83.99% | 24943.6376 | 18921.22 | 6022.4176 | 24943.6376 | 83.99%
Sub-Total (A) |  | 192105 |  | 173701.6376 | 139880.22 | 33821.4176 | 173701.6376 | 90.42%
VARIATIONS
[5 empty] | 0 | 0 | 0
Sub-Total (B) |  | 0 |  | 0 | 0 | 0 | 0
ANTICIPATED SUBCONTRACT AMOUNT (C) = (A+B) |  | 192105 |  | 173701.6376 | 139880.22 | 33821.4176 | 173701.6376 | 90.42%

## FS Progress
FIRE STOP WORKS ON MEP PENETRATIONS AND JOINTS | [11 empty] | FIRE STOP
[6 empty] | Progress Quantity |  |  | Progress Amount (AED)
S.Nr | Description | Qty | Unit | Rate | Amount | Previous | Current | Cumulative | Previous | Current | Cumulative | Remarks
A | Firestop sealant and mineral wool backing to non-insulated metallic/ non-combustible pipes |  |  |  | 5755 |  |  |  | 7241 | 866 | 8107
A1 | Upto and including 2"ɸ | 50 | Nr | 14 | 700 | 268 | 33 | 301 | 3752 | 462 | 4214
A2 | Upto and including 3"ɸ | 50 | Nr | 16 | 800 | 78 | 20 | 98 | 1248 | 320 | 1568
A3 | Upto and including 4"ɸ | 50 | Nr | 21 | 1050 | 36 | 4 | 40 | 756 | 84 | 840
A4 | Upto and including 6"ɸ | 50 | Nr | 27 | 1350 | 55 | 0 | 55 | 1485 | 0 | 1485
A5 | Upto and including 8"ɸ | 25 | Nr | 46 | 1150 | 0 | 0 | 0 | 0 | 0 | 0
A6 | Upto and including 24"ɸ | 5 | Nr | 141 | 705 | 0 | 0 | 0 | 0 | 0 | 0
B | Supply and apply firestop sealant and mineral wool backing to insulated metallic/ non-combustible pipes |  |  |  | 17300 |  |  |  | 12422 | 8788 | 21210
B1 | Upto and including 2"ɸ | 100 | Nr | 20 | 2000 | 318 | 48 | 366 | 6360 | 960 | 7320
B2 | Upto and including 3"ɸ | 100 | Nr | 23 | 2300 | 214 | 10 | 224 | 4922 | 230 | 5152
B3 | Upto and including 4"ɸ | 100 | Nr | 29 | 2900 | 28 | 38 | 66 | 812 | 1102 | 1914
B4 | Upto and including 6"ɸ | 100 | Nr | 35 | 3500 | 4 | 0 | 4 | 140 | 0 | 140
B5 | Upto and including 8"ɸ | 50 | Nr | 47 | 2350 | 4 | 8 | 12 | 188 | 376 | 564
B6 | Upto and including 16"ɸ | 25 | Nr | 170 | 4250 | 0 | 36 | 36 | 0 | 6120 | 6120
C | Supply and apply firestop sealant and mineral wool backing to PVC/ combustible pipes |  |  |  | 71475 |  |  |  | 87076 | 17070 | 104146
| Upto and including 1"ɸ |  |  | 18 |  | 1328 | 310 | 1638 | 23904 | 5580 | 29484
C1 | Upto and including 2"ɸ | 200 | Nr | 28 | 5600 | 904 | 80 | 984 | 25312 | 2240 | 27552
C2 | Upto and including 3"ɸ | 200 | Nr | 30 | 6000 | 294 | 26 | 320 | 8820 | 780 | 9600
C3 | Upto and including 4"ɸ | 200 | Nr | 65 | 13000 | 266 | 38 | 304 | 17290 | 2470 | 19760
C4 | Upto and including 6"ɸ | 125 | Nr | 125 | 15625 | 86 | 16 | 102 | 10750 | 2000 | 12750
C5 | Upto and including 8"ɸ | 125 | Nr | 250 | 31250 | 4 | 16 | 20 | 1000 | 4000 | 5000
D | Supply and apply firestop board material to cable tray openings, shaft openings and openings |  |  |  | 67875 |  |  |  | 14220 | 1075 | 15295
D1 | For an area upto 0.05 m2 | 50 | Nr | 50 | 2500 | 245 | 6 | 251 | 12250 | 300 | 12550
D2 | For an area upto 0.10 m2 | 50 | Nr | 95 | 4750 | 10 | 5 | 15 | 950 | 475 | 1425
D3 | For an area upto 0.15 m2 | 50 | Nr | 150 | 7500 | 2 | 2 | 4 | 300 | 300 | 600
D4 | For an area upto 0.25 m2 | 50 | Nr | 180 | 9000 | 4 | 0 | 4 | 720 | 0 | 720
D5 | For an area upto 0.35 m2 | 50 | Nr | 245 | 12250 | 0 | 0 | 0 | 0 | 0 | 0
D6 | For an area upto 0.50 m2 | 25 | Nr | 310 | 7750 | 0 | 0 | 0 | 0 | 0 | 0
D7 | For an area upto 0.65 m2 | 25 | Nr | 340 | 8500 | 0 | 0 | 0 | 0 | 0 | 0
D8 | For an area upto 0.80 m2 | 25 | Nr | 400 | 10000 | 0 | 0 | 0 | 0 | 0 | 0
D9 | For an area upto 1.00 m2 | 12.5 | m2 | 450 | 5625 | 0 | 0 | 0 | 0 | 0 | 0
E | Supply and apply firestopping materials to Metallic Duct with Fire Damper and L-angle |  |  |  | 29700 |  |  |  | 18921.22 | 6022.4176 | 24943.6376
E1 | For an area upto 0.05 m2 | 50 | Nr | 32 | 1600 | 31 | 11 | 42 | 992 | 352 | 1344
E2 | For an area upto 0.10 m2 | 50 | Nr | 46 | 2300 | 140 | 11 | 151 | 6440 | 506 | 6946
E3 | For an area upto 0.20 m2 | 50 | Nr | 51 | 2550 | 72 | 31 | 103 | 3672 | 1581 | 5253
E4 | For an area upto 0.30 m2 | 50 | Nr | 64 | 3200 | 12 | 14 | 26 | 768 | 896 | 1664
E5 | For an area upto 0.40 m2 | 50 | Nr | 74 | 3700 | 9 | 3 | 12 | 666 | 222 | 888
E6 | For an area upto 0.50 m2 | 50 | Nr | 82 | 4100 | 9 | 0 | 9 | 738 | 0 | 738
E7 | For an area upto 0.60 m2 | 50 | Nr | 88 | 4400 | 0 | 0 | 0 | 0 | 0 | 0
E8 | For an area upto 0.70 m2 | 25 | Nr | 98 | 2450 | 1 | 0 | 1 | 98 | 0 | 98
E9 | For an area upto 0.80 m2 | 25 | Nr | 103 | 2575 | 1 | 0 | 1 | 103 | 0 | 103
E10 | For an area upto 0.90 m2 | 12.5 | Nr | 110 | 1375 | 7 | 0 | 7 | 770 | 0 | 770
E11 | For an area upto 1.00 m2 | 12.5 | m2 | 116 | 1450 | 40.295 | 21.2536 | 61.5486 | 4674.22 | 2465.4176 | 7139.6376
| TOTAL AMOUNT OF MEP PENETRATION |  |  |  | 192105 |  |  |  | 139880.22 | 33821.4176 | 173701.6376

## FS Work done
FIRE STOP - WORK DONE - BREAK-UP
IPC Ref. | Contractor | Work Ref. | Date | Tower | Level | Zone | Location | Penetrant Type | Penetrant Size (in meter) |  | m2 | Opening Size (in meter) |  | m2 | Sides | Rate (AED) | Nos | Total Qty | Total (AED) | Remarks/ WIR Ref.
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | FF Pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.24 | 0.1032 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.2 | 0.1 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.75 | 0.6 | 0.45 | 0.79 | 0.63 | 0.4977 | 2 | 110 | 1 | 2 | 220
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.2 | 0.1 | 0.02 | 2 | 60 | 2 | 4 | 240
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 1.5" |  |  | 2.5" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.75 | 0.6 | 0.45 | 0.78 | 0.64 | 0.4992 | 2 | 110 | 1 | 2 | 220
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.45 | 0.25 | 0.1125 | 0.48 | 0.28 | 0.1344 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#1 May'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.3 | 0.25 | 0.075 | 0.33 | 0.28 | 0.0924 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.3 | 0.09 | 0.33 | 0.33 | 0.1089 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.2 | 0.06 | 0.33 | 0.23 | 0.0759 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | duct | 0.6 | 0.4 | 0.24 | 0.64 | 0.43 | 0.2752 | 2 | 86 | 2 | 4 | 344
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | cable tray |  |  |  | 0.65 | 0.1 | 0.065 | 2 | 115 | 2 | 4 | 460
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.75 | 0.45 | 0.3375 | 2 | 300 | 1 | 2 | 600
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | HDPE pipe | 3" | [5 empty] | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | HDPE pipe | 4" | [5 empty] | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.73 | 0.43 | 0.3139 | 2 | 100 | 1 | 2 | 200
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | cable trunking |  |  |  | 0.18 | 0.18 | 0.0324 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.75 | 0.45 | 0.3375 | 2 | 300 | 1 | 2 | 600
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.73 | 0.43 | 0.3139 | 2 | 100 | 1 | 2 | 200
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | opening |  |  |  | 0.8 | 0.4 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | HDPE pipe | 3" | [5 empty] | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | HDPE pipe | 4" | [5 empty] | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Training Room | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Interview Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Interview Room | duct | 0.6 | 0.4 | 0.24 | 0.63 | 0.43 | 0.2709 | 2 | 86 | 3 | 6 | 516
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.23 | 0.0989 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | HDPE pipe | 3" | [5 empty] | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | HDPE pipe | 4" | [5 empty] | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#1 May'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | Zone 2 | Office | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Driver Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Driver Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Toilet Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Toilet Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Guest Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Guest Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Family Living Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Family Living Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Kitchen Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Kitchen Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Toilet Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Dress Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Powder Room Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Powder Room Flat 2A | CDP pipe (slab) | 1" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Bathroom Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Bathroom Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Master Bathroom Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Master Bathroom Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Master Bathroom Flat 2A | CDP pipe (slab) | 1" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 802 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 802 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 803 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 803 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 804 | PVC pipe (slab) | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 804 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 804 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 805 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 805 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 806 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 806 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 4" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | metal conduit | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | metal conduit | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.15 | 0.0375 | 0.28 | 0.18 | 0.0504 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.2 | 0.13 | 0.026 | 0.23 | 0.16 | 0.0368 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | duct | 0.25 | 0.2 | 0.05 | 0.28 | 0.23 | 0.0644 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | duct | 0.25 | 0.2 | 0.05 | 0.29 | 0.24 | 0.0696 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | duct | 0.25 | 0.2 | 0.05 | 0.28 | 0.24 | 0.0672 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 1 | 62 | 1 | 1 | 62
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#1 May'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1005 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1005 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1004 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1004 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1003 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1003 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1002 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1002 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1001 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 11 | 11 | 308
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1001 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1008 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1008 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37458 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1009 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37458 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1009 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 808 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 808 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 807 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 807 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 910 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 910 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 909 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37456 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 909 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1101 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 7 | 7 | 455
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1101 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1102 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1102 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1103 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1103 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1104 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1104 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1105 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1105 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1106 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1106 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1107 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1107 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1108 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1108 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.18 | 0.0414 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1002 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1002 | duct | 0.25 | 0.2 | 0.05 | 0.25 | 0.2 | 0.05 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1002 | duct | 0.35 | 0.3 | 0.105 | 0.35 | 0.3 | 0.105 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1003 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1003 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | duct | 0.25 | 0.2 | 0.05 | 0.29 | 0.24 | 0.0696 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.17 | 0.0391 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1004, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1004 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1004 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1004 | duct | 0.35 | 0.3 | 0.105 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1006, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1006, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1209 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1209 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1208 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1208 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1206 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1206 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1207 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1207 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1205 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1205 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1204 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1204 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1212 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1212 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1213 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1213 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1214 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1214 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 60 | 3 | 3 | 180
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 2" | [5 empty] | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 1" | [5 empty] | 1 | 18 | 3 | 3 | 54
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.9 | 0.6 | 0.54 | 1 | 410 | 1 | 1 | 410
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 2" | [5 empty] | 1 | 18 | 10 | 10 | 180
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.9 | 0.3 | 0.27 | 1 | 300 | 1 | 1 | 300
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.9 | 0.3 | 0.27 | 1 | 300 | 1 | 1 | 300
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 1 | 23 | 1 | 1 | 23
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 2" | [5 empty] | 1 | 18 | 8 | 8 | 144
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.5 | 0.5 | 0.25 | 1 | 220 | 1 | 1 | 220
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 2" | [5 empty] | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.1 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 9 | 9 | 162
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.28 | 0.28 | 0.0784 | 1 | 62 | 2 | 2 | 124
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 902 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 902 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 902 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 903 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 903 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 906 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 906 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 906 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 4 | 4 | 180
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1101 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1101 | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1101 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | duct | 0.15 | 0.2 | 0.03 | 0.18 | 0.23 | 0.0414 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 7 | 7 | 126
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm1103 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm1103 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm1103 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm1103 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm1103 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 7 | 7 | 126
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1105 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1105 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1105 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106, Shaft | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 1 | 1 | 23
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.15 | 0.15 | 0.0225 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1109 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#1 May'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1109 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#1 May'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Room 1109 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | duct | 0.15 | 0.15 | 0.0225 | 0.15 | 0.15 | 0.0225 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1301 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1301 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1302 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1302 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1303 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1303 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1304 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1304 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1305 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1305 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1306 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1306 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1307 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 37487 | 2020-01-26 | Hotel | 13 | 2 | Room no 1307 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1309 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1309 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1310 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1310 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1313 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1313 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1314 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1314 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1315 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1315 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1316 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1316 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1317 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37488 | 2020-01-26 | Hotel | 13 | 2 | Room no 1317 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37489 | 2020-01-26 | Hotel | 13 | 2 | Room no 1318 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37489 | 2020-01-26 | Hotel | 13 | 2 | Room no 1318 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 37489 | 2020-01-26 | Hotel | 13 | 2 | Room no 1319 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 37489 | 2020-01-26 | Hotel | 13 | 2 | Room no 1319 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1401 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1401 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1402 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1402 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1403 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1403 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1404 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1404 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1405 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1405 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1406 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1406 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1407 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1407 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1408 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1408 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1409 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1409 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1412 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1412 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1413 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1413 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1414 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1414 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1415 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1415 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1416 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1416 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1417 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1417 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1418 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1418 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1201 - Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1201 - Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1201 - Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1201- Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1201- Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1202 - Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1202 - Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1202- Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1202 - Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1203 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1203 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1203 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1204 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1204-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1204-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1204-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1204-Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42507 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1205-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1205-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1205-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1205-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1206-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1206-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1206-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1207-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1207-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1207-Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1207-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1207-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1208-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1208-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1208-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1208-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1208-Shaft | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42508 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1209 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1209 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1209 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1212 -Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1212 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1212 -Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1212-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1212-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1213-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1213-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1213 -Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1213 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1213 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1215 -Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1215 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1215 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42509 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1215 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1216 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1216 -Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1216 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42510 | 2020-03-01 | Hotel | 12 | 2 | Room no. 1216 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | PPR pipe | 3" |  |  | 5 |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1501 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1501 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1502 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1502 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1503 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1503 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1504 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1504 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1505 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1505 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1506 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1506 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1507 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1507 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1508 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1508 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1509 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1509 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1512 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1512 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1513 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1513 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1514 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1514 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1515 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1515 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1516 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1516 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1517 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1517 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1518 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42513 | 2020-03-12 | Hotel | 15 | 2 | Room no 1518 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Female Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Female Wash Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Male Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 23 | 23 | 644
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Male Wash Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 13 | 13 | 364
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Wash Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Lift Lobby | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Lift Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Beverage Store | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Beverage Store | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Beverage Store | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Vegetable Pre Fruit | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Vegetable Pre Fruit | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Vegetable Pre Fruit | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Fish and Seafood | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Fish and Seafood | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Male Staff | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Housekeeping | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Housekeeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Chemical Store | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#1 May'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Patisserie | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Patisserie | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1611 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1611 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1612 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1612 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1613 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1613 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1614 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1614 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1615 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1615 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1616 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1616 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1617 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1617 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1601 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1601 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1602 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1602 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1603 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1603 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1604 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1604 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1605 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1605 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1606 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1606 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1607 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1607 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1608 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1608 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1609 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#1 May'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1609 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 3 | 6 | 138
PC#1 May'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 3 | 6 | 138
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Part.Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Part.Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Part.Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 1 | 44 | 1 | 1 | 44
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.23 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 2 | 62 | 3 | 6 | 372
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | duct | 0.4 | 0.3 | 0.12 | 0.4 | 0.3 | 0.12 | 2 | 69 | 3 | 6 | 414
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Entry Door | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 2A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42518 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Entry Door | gas pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | duct | 0.25 | 0.2 | 0.05 | 0.25 | 0.2 | 0.05 | 2 | 44 | 3 | 6 | 264
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | duct | 0.35 | 0.3 | 0.105 | 0.35 | 0.3 | 0.105 | 2 | 69 | 3 | 6 | 414
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42519 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 2 | 86 | 1 | 2 | 172
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Flat 4A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | duct | 0.4 | 0.3 | 0.12 | 0.4 | 0.3 | 0.12 | 2 | 69 | 2 | 4 | 276
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | metal conduit | 2" | [5 empty] | 2 | 16 | 3 | 6 | 96
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.7 | 0.25 | 0.175 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 |  |  |  | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.75 | 0.4 | 0.3 | 2 | 300 | 1 | 2 | 600
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | conduit pipe | 1" | [5 empty] | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42520 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 | 65 | 4 | 8 | 520
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | conduit pipe | 2" | [5 empty] | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 42521 | 2020-04-18 | Hotel | 7 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Entry Door | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Entry Door | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Entry Door | cable tray |  |  |  | 0.18 | 0.09 | 0.0162 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | PPR pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | PPR pipe | 3" |  |  | 5" |  |  | 1 | 49 | 1 | 1 | 49
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | duct | 0.6 | 0.4 | 0.24 | 0.6 | 0.4 | 0.24 | 2 | 86 | 1 | 2 | 172
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 4B, Riser Shaft | duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 2 | 62 | 3 | 6 | 372
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | duct | 0.4 | 0.3 | 0.12 | 0.4 | 0.3 | 0.12 | 2 | 69 | 3 | 6 | 414
PC#1 May'20 | RPJV | 42522 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | cable tray |  |  |  | 0.15 | 0.05 | 0.0075 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | cable tray |  |  |  | 0.1 | 0.05 | 0.005 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 2 | 4 | 500
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Entry Door | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 2A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | cable tray |  |  |  | 0.18 | 0.09 | 0.0162 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42523 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | cable tray |  |  |  | 0.13 | 0.09 | 0.0117 | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Entry Door | gas pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.25 | 0.2 | 0.05 | 0.25 | 0.2 | 0.05 | 2 | 44 | 3 | 6 | 264
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.35 | 0.3 | 0.105 | 0.35 | 0.3 | 0.105 | 2 | 69 | 3 | 6 | 414
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | PVC pipe | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 69 | 1 | 2 | 138
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 2 | 86 | 1 | 2 | 172
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Flat 4A, Riser Shaft | duct | 0.4 | 0.2 | 0.08 | 0.44 | 0.23 | 0.1012 | 2 | 62 | 1 | 2 | 124
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Corridor | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42524 | 2020-04-18 | Hotel | 9 | 3 | Corridor | duct | 0.4 | 0.3 | 0.12 | 0.4 | 0.3 | 0.12 | 2 | 69 | 2 | 4 | 276
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | conduit pipe | 2" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.7 | 0.25 | 0.175 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 |  |  |  | 2 | 62 | 2 | 4 | 248
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 2 | 4 | 72
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.75 | 0.4 | 0.3 | 2 | 300 | 1 | 2 | 600
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | conduit pipe | 1" | [5 empty] | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 23 | 2 | 4 | 92
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 | 65 | 4 | 8 | 520
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | conduit pipe | 2" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 5 | 10 | 180
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 4 | 8 | 144
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | PVC pipe | 6" | [5 empty] | 2 | 125 | 3 | 6 | 750
PC#1 May'20 | RPJV | 42525 | 2020-04-18 | Hotel | 9 | 3 | Corridor | opening |  |  |  | 0.8 | 0.4 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | CHW Pumps | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | CHW Pumps | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | CHW Pumps | CHW pipe | 8" | [5 empty] | 2 | 0 | 8 | 16 | 0
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | CHW Pumps | opening |  |  |  | 4 | 0.95 | 3.8 | 2 | 275 | 1 | 2 | 550
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | Stair1 Pressurization | duct | 0.9 | 0.65 | 0.585 |  |  |  | 2 | 0 | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | Fire Pump room | opening |  |  |  | 1.15 | 0.9 | 1.035 | 2 | 540 | 1 | 2 | 1080
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | Fire Pump room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | Fire Pump room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | Fire Pump room | HDPE pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 45503 | 2020-05-21 | Residence | B2 | 3 | Fire Pump room | HDPE pipe | 6" |  |  | 8" |  |  | 1 | 125 | 1 | 1 | 125
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | CHW Pumps | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | FTR | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | FTR | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | FTR | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | FTR | opening |  |  |  | 0.5 | 0.15 | 0.075 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | FTR | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Grease Trap Room | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Grease Trap Room | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Grease Trap Room | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Grease Trap Room | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 1 | 69 | 1 | 1 | 69
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Grease Trap Room | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 1 | 86 | 1 | 1 | 86
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Grease Trap Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Stair Room | duct | 0.9 | 0.65 | 0.585 |  |  |  | 2 | 119 | 1 | 2 | 238
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Stair Room | opening |  |  |  | 0.95 | 0.7 | 0.665 | 2 | 480 | 1 | 2 | 960
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Stair Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Stair Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 45501 | 2020-06-01 | Residence | B2 | 3 | Stair Room | cable tray |  |  |  | 0.45 | 0.1 | 0.045 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable tray | 0.4 | 0.05 | 0.02 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | opening |  |  |  | 0.55 | 0.15 | 0.0825 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable tray |  |  |  | 0.45 | 0.1 | 0.045 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable tray | 0.4 | 0.05 | 0.02 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | opening |  |  |  | 0.55 | 0.15 | 0.0825 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | duct | 0.9 | 0.65 | 0.585 | 0.9 | 0.65 | 0.585 | 1 | 119 | 1 | 1 | 119
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | duct | 1 | 0.75 | 0.75 | 1 | 0.75 | 0.75 | 1 | 139 | 1 | 1 | 139
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | HDPE pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable tray |  |  |  | 0.13 | 0.18 | 0.0234 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | cable tray |  |  |  | 0.64 | 0.08 | 0.0512 | 2 | 60 | 2 | 4 | 240
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | duct | 0.9 | 0.65 | 0.585 | 0.9 | 0.65 | 0.585 | 1 | 119 | 1 | 1 | 119
PC#2 Jun'20 | RPJV | 45502 | 2020-06-01 | Residence | B2 | 3 | MEP wall | duct | 1 | 0.75 | 0.75 | 1 | 0.75 | 0.75 | 1 | 139 | 1 | 1 | 139
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Female Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Female Wash Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Male Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 23 | 23 | 644
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Male Wash Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 13 | 13 | 364
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Wash Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Lift Lobby | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Lift Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Beverage Store | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Beverage Store | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Beverage Store | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Vegetable Pre Fruit | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Vegetable Pre Fruit | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Vegetable Pre Fruit | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Fish and Seafood | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Fish and Seafood | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42516 | 2020-03-18 | Hotel | B1 | 2 | Male Staff | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Housekeeping | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Housekeeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Chemical Store | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Patisserie | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 42517 | 2020-03-18 | Hotel | B1 | 2 | Patisserie | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.24 | 0.1032 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.2 | 0.1 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.75 | 0.6 | 0.45 | 0.79 | 0.63 | 0.4977 | 2 | 110 | 1 | 2 | 220
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.2 | 0.1 | 0.02 | 2 | 60 | 2 | 4 | 240
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 1.5" |  |  | 2.5" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.75 | 0.6 | 0.45 | 0.78 | 0.64 | 0.4992 | 2 | 110 | 1 | 2 | 220
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | cable tray |  |  |  | 0.3 | 0.2 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.45 | 0.25 | 0.1125 | 0.48 | 0.28 | 0.1344 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 42546 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.3 | 0.25 | 0.075 | 0.33 | 0.28 | 0.0924 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Flower Room | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.3 | 0.09 | 0.33 | 0.33 | 0.1089 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.2 | 0.06 | 0.33 | 0.23 | 0.0759 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 20 | 1 | 2 | 40
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Uniform Distribution | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42547 | 2020-05-10 | Hotel | B1 | 2 | Training Room | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | duct | 0.6 | 0.4 | 0.24 | 0.64 | 0.43 | 0.2752 | 2 | 86 | 2 | 4 | 344
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable tray |  |  |  | 0.65 | 0.1 | 0.065 | 2 | 115 | 2 | 4 | 460
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.75 | 0.45 | 0.3375 | 2 | 300 | 1 | 2 | 600
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | HDPE pipe | 3" | [5 empty] | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | HDPE pipe | 4" | [5 empty] | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.73 | 0.43 | 0.3139 | 2 | 100 | 1 | 2 | 200
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable trunking |  |  |  | 0.18 | 0.18 | 0.0324 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.75 | 0.45 | 0.3375 | 2 | 300 | 1 | 2 | 600
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | duct | 0.7 | 0.4 | 0.28 | 0.73 | 0.43 | 0.3139 | 2 | 100 | 1 | 2 | 200
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | opening |  |  |  | 0.8 | 0.4 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | HDPE pipe | 3" | [5 empty] | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | HDPE pipe | 4" | [5 empty] | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Training Room | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Interview Room | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Interview Room | duct | 0.6 | 0.4 | 0.24 | 0.63 | 0.43 | 0.2709 | 2 | 86 | 3 | 6 | 516
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Office | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Office | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#2 Jun'20 | RPJV | 42548 | 2020-05-10 | Hotel | B1 | 2 | Office | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.23 | 0.0989 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | HDPE pipe | 3" | [5 empty] | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | HDPE pipe | 4" | [5 empty] | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#2 Jun'20 | RPJV | 42549 | 2020-05-10 | Hotel | B1 | 2 | Office | conduit PVC | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Driver Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Driver Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Toilet Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Toilet Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Guest Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Guest Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Family Living Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Family Living Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Kitchen Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Kitchen Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34788 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Toilet Flat 4A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Dress Room Flat 4A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Utility Room Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Maid Room Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Powder Room Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Powder Room Flat 2A | CDP pipe (slab) | 1" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Bathroom Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Bathroom Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Master Bathroom Flat 2A | PVC pipe (slab) | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Master Bathroom Flat 2A | PVC pipe (slab) | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34789 | 2019-09-11 | Hotel | 9 | 2 | Master Bathroom Flat 2A | CDP pipe (slab) | 1" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 802 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 802 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 803 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 803 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 804 | PVC pipe (slab) | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 804 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 804 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 805 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 805 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 806 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 34794 | 2019-09-19 | Hotel | 8 | 2 | Deluxe Rm. 806 | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 902 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 903 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34796 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 4" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34797 | 2019-10-05 | Hotel | 9 | 2 | Deluxe Rm. 906 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | metal conduit | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | metal conduit | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.15 | 0.0375 | 0.28 | 0.18 | 0.0504 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.2 | 0.13 | 0.026 | 0.23 | 0.16 | 0.0368 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 801 | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37461 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | duct | 0.25 | 0.2 | 0.05 | 0.28 | 0.23 | 0.0644 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 901 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | duct | 0.25 | 0.2 | 0.05 | 0.29 | 0.24 | 0.0696 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | duct | 0.25 | 0.2 | 0.05 | 0.28 | 0.24 | 0.0672 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37462 | 2019-11-28 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 806 | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 1 | 62 | 1 | 1 | 62
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 805 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37451 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 804 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 803 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#2 Jun'20 | RPJV | 37452 | 2019-10-29 | Hotel | 8 | 2 | Deluxe Room 802 | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1005 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1005 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1004 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1004 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1003 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1003 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1002 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1002 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1001 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 11 | 11 | 308
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1001 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1008 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37457 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1008 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37458 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1009 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37458 | 2019-10-29 | Hotel | 10 | 2 | Deluxe Room 1009 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 801 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 808 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 808 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 807 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 807 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 901 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 901 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 910 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 910 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 909 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37456 | 2019-11-28 | Hotel | 8 | 2 | Deluxe Room 909 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1101 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 7 | 7 | 455
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1101 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1102 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1102 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1103 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1103 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1104 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1104 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1105 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1105 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1106 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1106 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1107 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1107 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1108 | PVC pipe | 4'' |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37471 | 2019-12-12 | Hotel | 11 | 2 | Deluxe Room 1108 | PVC pipe | 2'' |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Bed Suite 1001 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1001 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.18 | 0.0414 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall 1001 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1002 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1002 | duct | 0.25 | 0.2 | 0.05 | 0.25 | 0.2 | 0.05 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1002 | duct | 0.35 | 0.3 | 0.105 | 0.35 | 0.3 | 0.105 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37477 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1002 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1003 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1003 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1003 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | duct | 0.25 | 0.2 | 0.05 | 0.29 | 0.24 | 0.0696 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.17 | 0.0391 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Partition Wall Rm 1003 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1004, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1004 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1004 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37478 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1004 | duct | 0.35 | 0.3 | 0.105 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1004 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1005 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser Rm 1005 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1006, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1006, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37479 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1006 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | D Rm 1008, Shaft | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Entry Door Rm 1008 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1009 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 37480 | 2020-01-05 | Hotel | 10 | 2 | Shaft Riser 1009 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37481 | 2020-01-05 | Hotel | 10 | 2 | Deluxe Room 1006 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 801, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 801 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | D Rm 807, Shaft | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37472 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 807 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | D Rm 808, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37473 | 2020-01-05 | Hotel | 8 | 2 | Entry Door Rm 808 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1209 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1209 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1208 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1208 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1206 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1206 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1207 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1207 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1205 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1205 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1204 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Bed Suite 1204 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1212 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37482 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1212 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1213 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1213 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1214 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37483 | 2020-01-09 | Hotel | 12 | 2 | Standard King 1214 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 60 | 3 | 3 | 180
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 2" | [5 empty] | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 1" | [5 empty] | 1 | 18 | 3 | 3 | 54
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.9 | 0.6 | 0.54 | 1 | 410 | 1 | 1 | 410
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 2" | [5 empty] | 1 | 18 | 10 | 10 | 180
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.9 | 0.3 | 0.27 | 1 | 300 | 1 | 1 | 300
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.9 | 0.3 | 0.27 | 1 | 300 | 1 | 1 | 300
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 1 | 23 | 1 | 1 | 23
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 2" | [5 empty] | 1 | 18 | 8 | 8 | 144
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.5 | 0.5 | 0.25 | 1 | 220 | 1 | 1 | 220
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 2" | [5 empty] | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.1 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 1 | 1 | 30
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 9 | 9 | 162
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.28 | 0.28 | 0.0784 | 1 | 62 | 2 | 2 | 124
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 37486 | 2020-01-22 | Hotel | 8 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Bed Suite 901 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 901 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 902 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 902 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 902 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37490 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 902 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 903 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 903 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 903 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 904 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 904 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37491 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 905 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 905 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 906 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 906 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 906 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 906 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 4 | 4 | 180
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37492 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 909 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 909 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 10 | 20 | 360
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Deluxe Room 910 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 37493 | 2020-01-22 | Hotel | 9 | 2 | Shaft Riser Rm 910 | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1101 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1101 | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1101 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser 1101 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | duct | 0.15 | 0.2 | 0.03 | 0.18 | 0.23 | 0.0414 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1101 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 7 | 7 | 126
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1102 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42501 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1103 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm1103 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm1103 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm1103 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm1103 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm1103 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 7 | 7 | 126
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1104 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Room 1105 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42502 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1105 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1105 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1105 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Partition Wall Rm 1105 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106, Shaft | PVC pipe | 1" |  |  | 3" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 1 | 1 | 23
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1106 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.15 | 0.15 | 0.0225 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1108 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1109 | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#2 Jun'20 | RPJV | 42503 | 2020-02-20 | Hotel | 11 | 2 | Room 1109 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Room 1109 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | duct | 0.15 | 0.15 | 0.0225 | 0.15 | 0.15 | 0.0225 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42504 | 2020-02-20 | Hotel | 11 | 2 | Shaft Riser Rm 1109 | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1301 | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1301 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1302 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1302 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1303 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1303 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1304 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1304 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1305 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1305 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1306 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1306 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1307 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 37487 | 2020-01-26 | Hotel | 11 | 2 | Room no 1307 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1309 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1309 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1310 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1310 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1313 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1313 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1314 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1314 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1315 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1315 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1316 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1316 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1317 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37488 | 2020-01-26 | Hotel | 11 | 2 | Room no 1317 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37489 | 2020-01-26 | Hotel | 11 | 2 | Room no 1318 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37489 | 2020-01-26 | Hotel | 11 | 2 | Room no 1318 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 37489 | 2020-01-26 | Hotel | 11 | 2 | Room no 1319 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 37489 | 2020-01-26 | Hotel | 11 | 2 | Room no 1319 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1401 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1401 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1402 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1402 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1403 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1403 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1404 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1404 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1405 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1405 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1406 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1406 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1407 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1407 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1408 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1408 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1409 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42505 | 2020-02-19 | Hotel | 14 | 2 | Room no 1409 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1412 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1412 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1413 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1413 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1414 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1414 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1415 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1415 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1416 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1416 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1417 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1417 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1418 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42506 | 2020-02-19 | Hotel | 14 | 2 | Room no 1418 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1201 - Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1201 - Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1201 - Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1201- Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1201- Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1202 - Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1202 - Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1202- Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1202 - Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1203 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1203 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1203 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1204 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1204-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1204-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1204-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1204-Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42507 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1205-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1205-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1205-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1205-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1206-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1206-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1206-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1207-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1207-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1207-Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1207-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1207-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1208-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1208-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1208-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1208-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1208-Shaft | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42508 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1209 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1209 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1209 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1212 -Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1212 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1212 -Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1212-Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1212-Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1213-Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1213-Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1213 -Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1213 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1213 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1215 -Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1215 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1215 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42509 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1215 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1216 -Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1216 -Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1216 -Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42510 | 2020-03-01 | Hotel | 14 | 2 | Room no. 1216 -Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1202 | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 7 | 14 | 252
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1203 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1204 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1205 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1206 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42511 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1207 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 8 | 8 | 144
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1208 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1209 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1212 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1213 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42512 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1214 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1215 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1216 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42513 | 2020-03-09 | Hotel | 12 | 2 | Room no. 1217 | PVC pipe | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1501 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1501 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1502 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1502 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1503 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1503 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1504 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1504 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1505 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1505 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1506 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1506 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1507 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1507 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1508 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1508 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1509 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42514 | 2020-03-12 | Hotel | 15 | 2 | Room no 1509 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1512 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1512 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1513 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1513 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1514 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1514 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1515 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1515 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1516 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1516 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1517 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1517 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1518 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42515 | 2020-03-12 | Hotel | 15 | 2 | Room no 1518 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1611 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1611 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1612 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1612 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1613 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1613 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1614 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1614 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1615 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1615 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1616 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1616 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1617 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42527 | 2020-04-17 | Hotel | 16 | 2 | Room 1617 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1601 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1601 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1602 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1602 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1603 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1603 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1604 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1604 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1605 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1605 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1606 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1606 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1607 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 7 | 7 | 196
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1607 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1608 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 8 | 8 | 224
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1608 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1609 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 42526 | 2020-04-17 | Hotel | 16 | 2 | Room 1609 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 9 | 2 | Room 907 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 9 | 2 | Room 907 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 9 | 2 | Room 908 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 9 | 2 | Room 908 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 10 | 2 | Room 1007 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 10 | 2 | Room 1007 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 6 | 6 | 390
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 11 | 2 | Room 1107 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 11 | 2 | Room 1107 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 12 | 2 | Room 1210 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 12 | 2 | Room 1210 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 12 | 2 | Room 1211 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 12 | 2 | Room 1211 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 13 | 2 | Room 1310 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 13 | 2 | Room 1310 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 13 | 2 | Room 1311 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 13 | 2 | Room 1311 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 14 | 2 | Room 1410 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45504 | 2020-06-20 | Hotel | 14 | 2 | Room 1410 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#2 Jun'20 | RPJV | 45505 | 2020-06-20 | Hotel | 15 | 2 | Room 1510 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 45505 | 2020-06-20 | Hotel | 15 | 2 | Room 1510 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 45505 | 2020-06-20 | Hotel | 15 | 2 | Room 1511 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45505 | 2020-06-20 | Hotel | 15 | 2 | Room 1511 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 45505 | 2020-06-20 | Hotel | 16 | 2 | Room 1610 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 45505 | 2020-06-20 | Hotel | 16 | 2 | Room 1610 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1412, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1413, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 3 | 6 | 138
PC#2 Jun'20 | RPJV | 42538 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1502, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1503, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42540 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1516, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42545 | 2020-04-17 | Hotel | 15 | 2 | Room 1517, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Part. W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1514, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 3 | 6 | 138
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42544 | 2020-04-17 | Hotel | 15 | 2 | Room 1515, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Part.Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Part.Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Part.Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1509, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1512, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42543 | 2020-04-17 | Hotel | 15 | 2 | Room 1513, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1507, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42542 | 2020-04-17 | Hotel | 15 | 2 | Room 1508, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1414, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 1 | 44 | 1 | 1 | 44
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1415, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42539 | 2020-04-17 | Hotel | 14 | 2 | Room 1416, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1504, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1505, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42541 | 2020-04-17 | Hotel | 15 | 2 | Room 1506, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1407, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42536 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1408, Part W | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1409, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42537 | 2020-04-17 | Hotel | 14 | 2 | Room 1411, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1405, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42535 | 2020-04-17 | Hotel | 14 | 2 | Room 1406, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1315, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1316, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42533 | 2020-04-17 | Hotel | 13 | 2 | Room 1317, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1402, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1403, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42534 | 2020-04-17 | Hotel | 14 | 2 | Room 1404, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1313, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42532 | 2020-04-17 | Hotel | 13 | 2 | Room 1314, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1304, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42529 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1305, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1306, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42530 | 2020-04-17 | Hotel | 13 | 2 | Room 1307, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1308, Part W | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.23 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1309, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 42531 | 2020-04-17 | Hotel | 13 | 2 | Room 1312, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 3 | 3 | 135
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1301, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Entry D | PVC pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1302, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 42528 | 2020-04-17 | Hotel | 13 | 2 | Room 1303, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1050
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 2 | 0 | 23 | 230
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 2 | 1 | 0.08 | 62 | 620
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 1 | 0.15 | 69 | 690
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 2 | 1 | 0.06 | 62 | 620
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | duct | 0.4 | 0.3 | 0.12 | 0.4 | 0.3 | 0.12 | 2 | 1 | 0.12 | 69 | 690
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 1 | 0 | 16 | 160
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | PPR pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1050
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | PPR pipe (Shaft) | 3" |  |  | 5" |  |  | 1 | 2 | 0 | 49 | 490
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 450
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat 4D Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1050
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 180
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 2 | 0 | 30 | 300
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 1 | 0 | 65 | 650
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Entry Door | conduit PVC | 1" |  |  | 2" |  |  | 2 | 3 | 0 | 18 | 180
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 1 | 0.0144 | 60 | 600
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 450
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1050
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | CHW pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 29 | 290
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | PPR pipe (Shaft) | 3" |  |  | 5" |  |  | 1 | 2 | 0 | 49 | 490
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | PPR pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1050
PC#2 Jun'20 | RPJV | 45520 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 2 | 0.18 | 62 | 620
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse Riser | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 2 | 0.32 | 69 | 690
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse | PVC pipe | 2" |  |  | 4" |  |  | 2 | 1 | 0 | 28 | 280
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Flat Penthouse | PVC pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 65 | 650
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 1 | 0.0104 | 60 | 600
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 1 | 0.0144 | 60 | 600
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 1 | 0 | 16 | 160
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 29 | 290
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 450
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1050
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 1 | 0 |  | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 1 | 0 |  | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 1 | 0.16 | 115 | 1150
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 2 | 0.125 | 62 | 620
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 2 | 0.245 | 69 | 690
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Riser | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 1 | 0 | 16 | 160
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 1 | 0 | 16 | 160
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | conduit PVC | 1" |  |  | 2" |  |  | 2 | 8 | 0 | 18 | 180
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 1 | 0.0144 | 60 | 600
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 1 | 0.0529 | 44 | 440
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 180
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 1 | 0 |  | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 2 | 0 |  | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 1 | 0.04 | 60 | 600
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 2 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 5 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45521 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 1 | 0.24 | 115 | 1150
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 1" | [5 empty] | 2 | 5 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.5 | 0.2 | 0.1 | 2 | 1 | 0.1 | 60 | 600
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 2 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 5 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 1 | 0.16 | 115 | 1150
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 1 | 0.01 | 60 | 600
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 30 | 300
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 1" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | PPR pipe | 3" | [5 empty] | 2 | 2 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 1 | 0.16 | 115 | 1150
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 1 | 0.01 | 60 | 600
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 1 | 0 | 16 | 160
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 1 | 0.04 | 60 | 600
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 180
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 2 | 0 | 23 | 230
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 29 | 290
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 2 | 0.125 | 62 | 620
PC#2 Jun'20 | RPJV | 45522 | 2020-06-01 | Residence | 10 | 3 | Corridor | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 2 | 0.245 | 69 | 690
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 1 | 0.04 | 44 | 484
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 1 | 0.09 | 62 | 682
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | PPR pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | PPR pipe (Shaft) | 3" |  |  | 5" |  |  | 1 | 2 | 0 | 49 | 539
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 1 | 0 | 16 | 176
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 2 | 0 | 23 | 253
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 2 | 1 | 0.08 | 62 | 682
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 1 | 0.15 | 69 | 759
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 2 | 1 | 0.06 | 62 | 682
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | duct | 0.4 | 0.3 | 0.12 | 0.4 | 0.3 | 0.12 | 2 | 1 | 0.12 | 69 | 759
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 495
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat 4B Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 1 | 0.0144 | 60 | 660
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 1 | 0.0104 | 60 | 660
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | conduit PVC | 1" |  |  | 2" |  |  | 2 | 6 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 29 | 319
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | gas pipe | 1" |  |  | 2" |  |  | 2 | 1 | 0 | 16 | 176
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 495
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 2 | 0 | 23 | 253
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | PPR pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | PPR pipe (Shaft) | 3" |  |  | 5" |  |  | 1 | 2 | 0 | 49 | 539
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 2 | 0.18 | 62 | 682
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 2 | 0.32 | 69 | 759
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 495
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Flat Penthouse Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 30 | 330
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 65 | 715
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 495
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 1 | 0 | 16 | 176
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 1 | 0.16 | 115 | 1265
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 6" |  |  | 8" |  |  | 1 | 2 | 0 | 205 | 2255
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 1 | 0.0625 | 62 | 682
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 1 | 0.1225 | 69 | 759
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 1 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 6" |  |  | 8" |  |  | 1 | 2 | 0 | 205 | 2255
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 2" |  |  | 4" |  |  | 1 | 1 | 0 | 45 | 495
PC#2 Jun'20 | RPJV | 45516 | 2020-06-01 | Residence | 11 | 3 | Riser | PVC pipe (Shaft) | 4" |  |  | 6" |  |  | 1 | 2 | 0 | 105 | 1155
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Entry Door | fire fighting pipe | 1.5" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Entry Door | conduit PVC | 2" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Entry Door | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 1 | 0.01 | 60 | 660
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Entry Door | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 1 | 0.0144 | 60 | 660
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Entry Door | conduit PVC | 1" |  |  | 2" |  |  | 2 | 10 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 1 | 0.0552 | 62 | 682
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 1 | 0.04 | 60 | 660
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 2 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 6 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 1 | 0.24 | 115 | 1265
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 1" | [5 empty] | 2 | 5 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.5 | 0.2 | 0.1 | 2 | 1 | 0.1 | 60 | 660
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 6 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 2 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 1 | 0.16 | 115 | 1265
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 2" |  |  | 3" |  |  | 2 | 1 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 1 | 0.01 | 60 | 660
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 30 | 330
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 | 3 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | PPR pipe | 3" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 1 | 0.24 | 115 | 1265
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 1 | 0 | 16 | 176
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45518 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 1 | 0.01 | 60 | 660
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 1 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | conduit PVC | 2" | [5 empty] | 2 | 2 | 0 | 0 | 0
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 1 | 0.04 | 60 | 660
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 1 | 0 | 18 | 198
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 2 | 0 | 23 | 253
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 2 | 0 | 29 | 319
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 2 | 0.125 | 62 | 682
PC#2 Jun'20 | RPJV | 45519 | 2020-06-01 | Residence | 11 | 3 | Corridor | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 2 | 0.245 | 69 | 759
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Kitchen Flat 4A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Kitchen Flat 4A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Utility Room Flat 4A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Utility Room Flat 4A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Show Kitchen Flat 4A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Show Kitchen Flat 4A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Maid Room Flat 2A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Maid Room Flat 2A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Utility Room Flat 2A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Utility Room Flat 2A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Living Room Flat 2A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Living Room Flat 2A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Powder Room Flat 2A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34775 | 2019-08-08 | Residence | 8 | 3 | Powder Room Flat 2A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 2A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 2A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Master Bathroom Flat 2A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Master Bathroom Flat 2A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Master Bathroom Flat 4B | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Master Bathroom Flat 4B | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Master Bathroom Flat 4B | PVC pipe (slab) | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4B | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4B | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4B | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4B | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#2 Jun'20 | RPJV | 34776 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34777 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34777 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 34777 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#2 Jun'20 | RPJV | 34777 | 2019-08-08 | Residence | 8 | 3 | Bathroom Flat 4A | PVC pipe (slab) | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-D-E/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-D-E/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-D-E/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-D-E/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34791 | 2019-09-19 | Residence | 9 | 3 | GL-E-G/3-4 Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Dress Room Flat 4A | PVC conduit pipe | 1" |  |  | 3" |  |  | 1 | 18 | 2 | 2 | 36
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Dress Room Flat 4A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Dress Room Flat 4A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Driver Room Flat 4A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Driver Room Flat 4A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Maid Toilet Flat 4A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Maid Toilet Flat 4A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Maid Toilet Flat 4A | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Maid Toilet Flat 4A | blank opening |  |  |  | 0.45 | 0.45 | 0.2025 | 1 | 220 | 1 | 1 | 220
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Guest Toilet Flat 4A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Guest Toilet Flat 4A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Utility Room Flat 4A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Utility Room Flat 4A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Utility Room Flat 4A | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#2 Jun'20 | RPJV | 34792 | 2019-09-20 | Residence | 8 | 3 | Utility Room Flat 4A | blank opening |  |  |  | 0.35 | 0.35 | 0.1225 | 1 | 185 | 1 | 1 | 185
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PPR pipe | 5" |  |  | 7" |  |  | 2 | 125 | 2 | 4 | 500
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | metal conduit | 2" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.7 | 0.25 | 0.175 | 2 | 220 | 1 | 2 | 440
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 8 | 16 | 288
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 |  |  |  | 2 | 62 | 2 | 4 | 248
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.75 | 0.4 | 0.3 | 2 | 300 | 1 | 2 | 600
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 1 | 2 | 46
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | metal conduit | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 | 65 | 4 | 8 | 520
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | conduit pipe | 2" | [5 empty] | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 3 | 6 | 108
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | PVC pipe | 1" |  |  | 3" |  |  | 2 | 18 | 5 | 10 | 180
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | duct | 0.35 | 0.15 | 0.0525 | 0.35 | 0.15 | 0.0525 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | duct | 0.45 | 0.25 | 0.1125 | 0.45 | 0.25 | 0.1125 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | duct | 0.5 | 0.25 | 0.125 | 0.5 | 0.25 | 0.125 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | duct | 0.6 | 0.35 | 0.21 | 0.6 | 0.35 | 0.21 | 2 | 86 | 1 | 2 | 172
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | PPR pipe | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 8 | 3 | Shaft Flat 4B | PPR pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | duct | 0.35 | 0.15 | 0.0525 | 0.35 | 0.15 | 0.0525 | 2 | 44 | 1 | 2 | 88
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | duct | 0.45 | 0.25 | 0.1125 | 0.45 | 0.25 | 0.1125 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | duct | 0.5 | 0.25 | 0.125 | 0.5 | 0.25 | 0.125 | 2 | 69 | 1 | 2 | 138
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | duct | 0.6 | 0.35 | 0.21 | 0.6 | 0.35 | 0.21 | 2 | 86 | 1 | 2 | 172
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#2 Jun'20 | RPJV | 37466 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | PPR pipe | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#2 Jun'20 | RPJV | 37466 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | PPR pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#2 Jun'20 | RPJV | 37466 | 2019-11-26 | Residence | 7 | 3 | Shaft Flat 4B | duct | 0.35 | 0.15 | 0.0525 | 0.45 | 0.25 | 0.1125 | 2 | 69 | 2 | 4 | 276
PC#2 Jun'20 | RPJV | 37466 | 2019-11-26 | Residence | 7 | 3 | Partition wall Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#2 Jun'20 | RPJV | 37466 | 2019-11-26 | Residence | 7 | 3 | Partition wall Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | duct | 0.3 | 0.2 | 0.06 | 0.3 | 0.2 | 0.06 | 1 | 62 | 2 | 2 | 124
PC#2 Jun'20 | RPJV | 37463 | 2019-11-03 | Residence | 8 | 3 | Corridor | duct | 0.3 | 0.2 | 0.06 | 0.4 | 0.3 | 0.12 | 1 | 69 | 2 | 2 | 138
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 1 | 62 | 2 | 2 | 124
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | duct | 0.4 | 0.2 | 0.08 | 0.5 | 0.3 | 0.15 | 1 | 69 | 2 | 2 | 138
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 1 | 29 | 2 | 2 | 58
PC#2 Jun'20 | RPJV | 37464 | 2019-11-03 | Residence | 8 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Entry door Flat 4B | gas pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Entry door Flat 4B | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 1 | 60 | 1 | 1 | 60
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Entry door Flat 4B | CHW pipe | 4" |  |  | 6" |  |  | 1 | 29 | 2 | 2 | 58
PC#2 Jun'20 | RPJV | 37465 | 2019-11-26 | Residence | 7 | 3 | Entry door Flat 4B | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Master Bathrm | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Master Bathrm | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Master Bathrm | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Master Bathrm | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Master Bathrm | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#2 Jun'20 | RPJV | 37468 | 2019-11-27 | Residence | 8 | 3 | 4B, Bathroom | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1601 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1601 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 3 | 3 | 135
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1601 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1601 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1601 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1602 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45506 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 1 | 2 | 36
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1603 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1604 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#3 Jul'20 | RPJV | 45507 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1605 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1606 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 3 | 6 | 270
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1607 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45508 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1608 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 1 | 2 | 36
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 1 | 2 | 36
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1609 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#3 Jul'20 | RPJV | 45509 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 4 | 180
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1611 | PVC conduit | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | PVC conduit | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 4 | 180
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 2 | 4 | 176
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1612 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.23 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1613 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45510 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1613 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1613 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1613 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1614 | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.24 | 0.0576 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1615 | PVC conduit | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1616 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1616 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1616 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#3 Jul'20 | RPJV | 45511 | 2020-07-07 | Hotel | 16 | 2 | Room no. 1616 | PVC conduit | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PPR pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PPR pipe | 3" |  |  | 5" |  |  | 2 | 49 | 1 | 2 | 98
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | duct | 0.2 | 0.3 | 0.06 | 0.2 | 0.3 | 0.06 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | duct | 0.3 | 0.4 | 0.12 | 0.3 | 0.4 | 0.12 | 2 | 69 | 1 | 2 | 138
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | duct | 0.2 | 0.4 | 0.08 | 0.2 | 0.4 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | duct | 0.3 | 0.5 | 0.15 | 0.3 | 0.5 | 0.15 | 2 | 69 | 1 | 2 | 138
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | cable tray |  | 0.15 | 0.05 | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4B | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 2 | 2 | 36
PC#3 Jul'20 | RPJV | 45512 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 69 | 1 | 2 | 138
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.35 | 0.4 | 0.14 | 0.35 | 0.4 | 0.14 | 2 | 69 | 1 | 2 | 138
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#3 Jul'20 | RPJV | 45513 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | gas pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | gas pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 2 | 410
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 2 | 410
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | gas pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 69 | 1 | 2 | 138
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | PVC conduit | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Flat 4C | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.213 | 0.04899 | 2 | 44 | 1 | 2 | 88
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 2" | [5 empty] | 2 |  | 6 | 12 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 115 | 1 | 2 | 230
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.5 | 0.2 | 0.1 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 2" | [5 empty] | 2 |  | 6 | 12 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 |  | 3 | 6 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#3 Jul'20 | RPJV | 45514 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 1 | 4 | 92
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | PVC conduit | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#3 Jul'20 | RPJV | 45515 | 2020-07-01 | Residence | 12 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Duct | 0.2 | 0.4 | 0.08 | 0.2 | 0.4 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 1 | 62
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | PPR pipe | 3" |  |  | 5" |  |  | 2 | 49 | 3 | 6 | 294
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Duct | 0.2 | 0.4 | 0.08 | 0.2 | 0.4 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 69 | 1 | 2 | 138
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | gas pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 4B | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | cable tray |  |  |  | 0.19 | 0.08 | 0.0152 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC conduit pipe | 1" |  |  | 2 |  |  | 2 |  | 12 | 24 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | Fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 3 | 6 | 264
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 1 | 62 | 3 | 3 | 186
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Flat 3C | gas pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.24 | 0.23 | 0.0552 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | Fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 5 | 10 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 115 | 1 | 2 | 230
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 6 | 12 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.5 | 0.2 | 0.1 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 5 | 10 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 13 | 3 | Corridor | duct | 0.35 | 0.35 | 0.1225 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PPR pipe | 3" |  |  | 5" |  |  | 2 | 49 | 3 | 3 | 147
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | duct | 0.3 | 0.15 | 0.045 | 0.3 | 0.15 | 0.045 | 2 | 44 | 1 | 2 | 88
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | duct | 0.4 | 0.25 | 0.1 | 0.4 | 0.25 | 0.1 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | duct | 0.4 | 0.2 | 0.08 | 0.4 | 0.2 | 0.08 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | duct | 0.5 | 0.3 | 0.15 | 0.5 | 0.3 | 0.15 | 2 | 69 | 1 | 2 | 138
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PVC conduit pipe | 1" |  |  | 3" |  |  | 2 | 18 | 3 | 6 | 108
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4B | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | cable tray |  |  |  | 0.13 | 0.09 | 0.0117 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | cable tray |  |  |  | 0.18 | 0.09 | 0.0162 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | cable tray |  |  |  | 0.19 | 0.09 | 0.0171 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 115 | 1 | 2 | 230
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 69 | 1 | 2 | 138
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Flat 4C | gas pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 45523 | 2020-08-12 | Residence | 14 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 1 | 2 | 124
PC#4 Aug'20 | RPJV | 4552X | 2020-08-17 | Residence | 8 | 3 | House Keeping Lobby | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#4 Aug'20 | RPJV | 4552X | 2020-08-17 | Residence | 8 | 3 | House Keeping Lobby | Fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#4 Aug'20 | RPJV | 4552X | 2020-08-17 | Residence | 8 | 3 | House Keeping Lobby | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#4 Aug'20 | RPJV | 4552X | 2020-08-17 | Residence | 8 | 3 | House Keeping Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#4 Aug'20 | RPJV | 4552X | 2020-08-17 | Residence | 8 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#4 Aug'20 | RPJV | 4552X | 2020-08-17 | Residence | 8 | 3 | Waste Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#5 Sep'20 | RPJV | 45530 | 2020-09-01 | Hotel | 20 | 2 | Flat 19A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 2 | 2 | 36
PC#5 Sep'20 | RPJV | 45530 | 2020-09-01 | Hotel | 20 | 2 | Flat 19A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#5 Sep'20 | RPJV | 45530 | 2020-09-01 | Hotel | 20 | 2 | Flat 7A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 1 | 1 | 18
PC#5 Sep'20 | RPJV | 45530 | 2020-09-01 | Hotel | 20 | 2 | Flat 7A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 11B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 11B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 3A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 3A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 2D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 2D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 6A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 20 | 2 | Flat 6A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 7A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 2 | 2 | 36
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 7A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 11B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 11B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 3A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 3A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 2D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 2D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 12A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 12A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 6A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#5 Sep'20 | RPJV | 45531 | 2020-09-01 | Hotel | 21 | 2 | Flat 6A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | Duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | Duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | fire fighting pipe | 2.5" |  |  | 4" |  |  | 2 | 18 | 1 | 2 | 36
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | Duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | Duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | conduit pipe (pvc) | 1" |  |  | 2'' |  |  | 2 | 18 | 13 | 26 | 468
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | PPR pipe | 3'' |  |  | 5'' |  |  | 1 | 30 | 3 | 3 | 90
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | fire fighting pipe | 2'' |  |  | 4'' |  |  | 2 | 16 | 1 | 2 | 32
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | CHW pipe | 3'' |  |  | 5'' |  |  | 2 | 23 | 2 | 4 | 92
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | PVC pipe | 2" |  |  | 4'' |  |  | 1 | 18 | 1 | 1 | 18
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | CDP pipe | 3" |  |  | 5'' |  |  | 2 | 30 | 1 | 2 | 60
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | conduit pipe (pvc) | 1" |  |  | 2'' |  |  | 2 | 18 | 3 | 6 | 108
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 6A | Duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | Duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | duct | 0.2 | 0.3 | 0.06 | 0.24 | 0.33 | 0.0792 | 2 | 62 | 2 | 4 | 248
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 4" |  |  | 6'' |  |  | 2 | 65 | 2 | 4 | 260
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 2" |  |  | 4'' |  |  | 2 | 18 | 1 | 2 | 36
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | Duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 4" |  |  | 6'' |  |  | 1 | 105 | 3 | 3 | 315
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PVC pipe | 2" |  |  | 4'' |  |  | 1 | 45 | 1 | 1 | 45
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | CHW pipe | 3'' |  |  | 5'' |  |  | 2 | 23 | 2 | 4 | 92
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | PPR pipe | 3" |  |  | 5'' |  |  | 2 | 30 | 3 | 6 | 180
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | fire fighting pipe | 2'' |  |  | 4'' |  |  | 2 | 16 | 1 | 2 | 32
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 12A | conduit pipe (pvc) | 1" |  |  | 2'' |  |  | 2 | 18 | 4 | 8 | 144
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | Duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 2 | 44 | 2 | 4 | 176
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | Duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 14 | 28 | 504
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#5 Sep'20 | RPJV | 4553X | 2020-09-09 | Hotel | 20 | 2 | Flat 2D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | cable tray |  |  |  | 0.15 | 0.1 | 0.015 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | duct | 0.2 | 0.15 | 0.03 | 0.24 | 0.18 | 0.0432 | 2 | 44 | 2 | 4 | 176
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | duct | 0.8 | 0.3 | 0.24 | 0.85 | 0.35 | 0.2975 | 2 | 86 | 2 | 4 | 344
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Vegetable Prep Rm | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Fruit Prep Rm | duct | 0.8 | 0.3 | 0.24 | 0.84 | 0.34 | 0.2856 | 2 | 86 | 1 | 2 | 172
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Fruit Prep Rm | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.19 | 0.0437 | 2 | 44 | 2 | 4 | 176
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Fruit Prep Rm | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | duct | 0.8 | 0.3 | 0.24 | 0.84 | 0.34 | 0.2856 | 2 | 86 | 2 | 4 | 344
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.19 | 0.0437 | 2 | 44 | 2 | 4 | 176
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | duct | 0.2 | 0.15 | 0.03 | 0.24 | 0.18 | 0.0432 | 2 | 44 | 2 | 4 | 176
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | duct | 0.8 | 0.3 | 0.24 | 0.83 | 0.34 | 0.2822 | 2 | 86 | 1 | 2 | 172
PC#6 Oct'20 | RPJV | 45542 | 2020-10-01 | Hotel | B1 | 2 | Poultry Prep Rm | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#6 Oct'20 | RPJV | 45543 | 2020-10-01 | Hotel | B1 | 2 | Fish and Seafood | duct | 0.5 | 0.15 | 0.075 | 0.53 | 0.18 | 0.0954 | 2 | 62 | 1 | 2 | 124
PC#6 Oct'20 | RPJV | 45543 | 2020-10-01 | Hotel | B1 | 2 | Fish and Seafood | duct | 0.8 | 0.3 | 0.24 | 0.83 | 0.34 | 0.2822 | 2 | 86 | 2 | 4 | 344
PC#6 Oct'20 | RPJV | 45543 | 2020-10-01 | Hotel | B1 | 2 | Fish and Seafood | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45543 | 2020-10-01 | Hotel | B1 | 2 | Fish and Seafood | duct | 0.2 | 0.15 | 0.03 | 0.23 | 0.18 | 0.0414 | 2 | 44 | 2 | 4 | 176
PC#6 Oct'20 | RPJV | 45543 | 2020-10-01 | Hotel | B1 | 2 | Fish and Seafood | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 12 | 24 | 432
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | cable trunking |  |  |  | 0.14 | 0.14 | 0.0196 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | cable trunking |  |  |  | 0.08 | 0.09 | 0.0072 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | cable tray |  |  |  | 0.28 | 0.08 | 0.0224 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | cable tray |  |  |  | 0.34 | 0.09 | 0.0306 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | cable tray |  |  |  | 0.53 | 0.08 | 0.0424 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | PPR pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | cable tray |  |  |  | 0.29 | 0.08 | 0.0232 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | CHW pipe | 6" |  |  | 8" |  |  | 2 | 35 | 2 | 4 | 140
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Pump Room | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 1 | 44 | 2 | 2 | 88
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 1 | 62 | 2 | 2 | 124
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | PPR pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 1 | 86 | 1 | 1 | 86
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 0.6 | 0.6 | 0.36 | 0.6 | 0.6 | 0.36 | 1 | 100 | 1 | 1 | 100
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 0.95 | 0.7 | 0.665 | 0.95 | 0.7 | 0.665 | 1 | 132 | 2 | 2 | 264
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 1.15 | 0.8 | 0.92 | 1.15 | 0.8 | 0.92 | 1 | 155 | 2 | 2 | 310
PC#6 Oct'20 | RPJV | 45551 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 1.2 | 1 | 1.2 | 1.2 | 1 | 1.2 | 1 | 155 | 1 | 1 | 155
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 1.3 | 1.1 | 1.43 | 1.3 | 1.1 | 1.43 | 1 | 155 | 1 | 1 | 155
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 0.75 | 0.5 | 0.375 | 0.75 | 0.5 | 0.375 | 1 | 100 | 2 | 2 | 200
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 0.8 | 0.6 | 0.48 | 0.8 | 0.6 | 0.48 | 1 | 110 | 2 | 2 | 220
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | duct | 0.7 | 0.5 | 0.35 | 0.7 | 0.5 | 0.35 | 1 | 100 | 1 | 1 | 100
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | duct | 0.8 | 0.6 | 0.48 | 0.8 | 0.6 | 0.48 | 1 | 110 | 1 | 1 | 110
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | CHW pipe | 6" |  |  | 8" |  |  | 2 | 35 | 2 | 4 | 140
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | duct | 0.7 | 0.5 | 0.35 | 0.7 | 0.5 | 0.35 | 1 | 100 | 1 | 1 | 100
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | duct | 0.8 | 0.6 | 0.48 | 0.8 | 0.6 | 0.48 | 1 | 110 | 1 | 1 | 110
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | PPR pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | duct | 1.4 | 0.9 | 1.26 | 1.4 | 0.9 | 1.26 | 1 | 155 | 1 | 1 | 155
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | duct | 0.15 | 1 | 0.15 | 0.15 | 1 | 0.15 | 1 | 69 | 1 | 1 | 69
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | AHU & Ecology Unit | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | Staircase 10 | duct | 0.2 | 0.2 | 0.04 | 0.2 | 0.2 | 0.04 | 1 | 44 | 2 | 2 | 88
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | Staircase 10 | duct | 0.3 | 0.3 | 0.09 | 0.3 | 0.3 | 0.09 | 1 | 62 | 2 | 2 | 124
PC#6 Oct'20 | RPJV | 45552 | 2020-10-01 | Hotel | B2 | 2 | Staircase 10 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Staircase 10 | duct | 0.95 | 0.7 | 0.665 | 0.97 | 0.72 | 0.6984 | 2 | 132 | 1 | 2 | 264
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 1 | 86 | 2 | 2 | 172
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | duct | 0.6 | 0.6 | 0.36 | 0.6 | 0.6 | 0.36 | 1 | 100 | 2 | 2 | 200
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Irigation Tank | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 2 | 4 | 500
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 1.4 | 0.6 | 0.84 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | opening |  |  |  | 1.45 | 0.64 | 0.928 | 2 | 540 | 1 | 2 | 1080
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 5 | 10 | 650
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 1 | 86 | 2 | 2 | 172
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 0.6 | 0.6 | 0.36 | 0.6 | 0.6 | 0.36 | 1 | 100 | 2 | 2 | 200
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 1.4 | 0.6 | 0.84 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | opening |  |  |  | 1.45 | 0.65 | 0.9425 | 2 | 540 | 1 | 2 | 1080
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | duct | 0.95 | 0.7 | 0.665 |  |  |  | 2 |  | 2 | 4 | 0
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | Grease Trap Rm | opening |  |  |  | 1 | 0.73 | 0.73 | 2 | 480 | 1 | 2 | 960
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 1.6 | 1.6 | 2.56 | 1.6 | 1.6 | 2.56 | 1 | 155 | 3 | 3 | 465
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 1.7 | 1.7 | 2.89 | 1.7 | 1.7 | 2.89 | 1 | 155 | 3 | 3 | 465
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | cable tray |  |  |  | 0.23 | 0.08 | 0.0184 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | duct | 1.5 | 1.6 | 2.4 |  |  |  | 2 |  | 3 | 6 | 0
PC#6 Oct'20 | RPJV | 45553 | 2020-10-01 | Hotel | B2 | 2 | CSF Room | opening |  |  |  | 1.53 | 1.63 | 2.4939 | 2 | 325 | 1 | 2 | 650
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | EA Pleanum Rm | duct | 0.7 | 0.65 | 0.455 | 0.7 | 0.65 | 0.455 | 1 | 110 | 1 | 1 | 110
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | EA Pleanum Rm | duct | 0.8 | 0.75 | 0.6 | 0.8 | 0.75 | 0.6 | 1 | 119 | 1 | 1 | 119
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | EA Pleanum Rm | duct | 2 | 0.75 | 1.5 | 2 | 0.75 | 1.5 | 1 | 155 | 2 | 2 | 310
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | EA Pleanum Rm | duct | 2.1 | 0.85 | 1.785 | 2.1 | 0.85 | 1.785 | 1 | 155 | 2 | 2 | 310
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 2 | 4 | 240
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 3 | 6 | 360
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45554 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 2 | 4 | 240
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Laundry Rm | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable tray |  |  |  | 0.9 | 0.1 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable tray |  |  |  | 0.7 | 0.1 | 0.07 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable tray |  |  |  | 0.2 | 0.1 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable tray |  |  |  | 0.55 | 0.1 | 0.055 | 2 | 115 | 2 | 4 | 460
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable trunking |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Lobby | cable tray |  |  |  | 0.18 | 0.09 | 0.0162 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#6 Oct'20 | RPJV | 45555 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 11 | 22 | 396
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | CHW pipe | 6" |  |  | 8" |  |  | 2 | 35 | 2 | 4 | 140
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | cable tray |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 2 | 4 | 120
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Engeenering & Main. | HDPE pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | FF Lobby | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | FF Lobby | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | FF Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Staircase 7 | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#6 Oct'20 | RPJV | 45556 | 2020-10-01 | Hotel | B2 | 2 | Staircase 7 | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 42577 | 2020-10-04 | Hotel | B1 & B2 | 2 | Garbage Chute | Garbage Chute | 24" | [5 empty] | 2 |  | 2 | 4 | 0
PC#6 Oct'20 | RPJV | 42577 | 2020-10-04 | Hotel | B1 & B2 | 2 | Garbage Chute | opening |  |  |  | 0.9 | 0.8 | 0.72 | 2 | 480 | 1 | 2 | 960
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | duct | 0.8 | 0.3 | 0.24 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | opening |  |  |  | 1 | 0.4 | 0.4 | 2 | 375 | 1 | 2 | 750
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | duct | 0.8 | 0.3 | 0.24 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | opening |  |  |  | 0.9 | 0.4 | 0.36 | 2 | 375 | 1 | 2 | 750
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | cable tray |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 11 | 22 | 396
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | duct | 0.15 | 0.15 | 0.0225 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | gas pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | cable tray |  |  |  | 0.7 | 0.3 | 0.21 | 2 | 220 | 1 | 2 | 440
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | duct | 0.9 | 0.4 | 0.36 |  |  |  | 2 |  | 2 | 4 | 0
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | opening |  |  |  | 1 | 0.6 | 0.6 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | cable tray |  |  |  | 0.5 | 0.2 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Baking Pastry | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.6 | 0.3 | 0.18 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.8 | 0.5 | 0.4 | 2 | 375 | 1 | 2 | 750
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 26 | 52 | 936
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45544 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.45 | 0.45 | 0.2025 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.5 | 0.5 | 0.25 | 2 | 220 | 1 | 2 | 440
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.7 | 1.2 | 0.84 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.8 | 1.35 | 1.08 | 2 | 400 | 1 | 2 | 800
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.7 | 0.95 | 0.665 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.85 | 1.2 | 1.02 | 2 | 400 | 1 | 2 | 800
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.7 | 0.95 | 0.665 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.85 | 1 | 0.85 | 2 | 480 | 1 | 2 | 960
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | cable trunking |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | conduit pipe (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.7 | 0.8 | 0.56 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.8 | 1 | 0.8 | 2 | 480 | 1 | 2 | 960
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | cable tray |  |  |  | 0.15 | 0.1 | 0.015 | 2 | 60 | 1 | 2 | 120
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | duct | 0.7 | 0.8 | 0.56 |  |  |  | 2 |  | 1 | 2 | 0
PC#6 Oct'20 | RPJV | 45545 | 2020-10-21 | Hotel | B1 | 2 | Hot Kitchen | opening |  |  |  | 0.8 | 1.5 | 1.2 | 2 | 400 | 1 | 2 | 800
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 7 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 8 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 9 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 10 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 11 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 12 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 13 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 14 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 15 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45537 | 2020-10-06 | Hotel | 16 | 2 | House Keeping | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 16A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 16A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 11B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 5 | 5 | 90
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 11B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 3A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 3A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 2D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 2D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 12A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 5 | 5 | 90
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 12A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 6A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 23 | 2 | Room no. 6A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45538 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 11C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 5 | 5 | 90
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 11C | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 14A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 14A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 6 | 6 | 390
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 1A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 1A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2F | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2F | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45539 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3C | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3F | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 24 | 2 | Room no. 3F | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2G | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 24 | 2 | Room no. 2G | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 11C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 5 | 5 | 90
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 11C | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3E | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3E | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45540 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 14A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 14A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 6 | 6 | 390
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 10B | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 10B | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 1A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 1A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2F | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2F | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3C | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3C | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3F | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 3F | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2G | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2G | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2E | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 2E | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 5A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#6 Oct'20 | RPJV | 45541 | 2020-10-12 | Hotel | 25 | 2 | Room no. 5A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | duct | 1.6 | 1.6 | 2.56 | 1.6 | 1.6 | 2.56 | 1 | 155 | 1 | 1 | 155
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | duct | 1.7 | 1.7 | 2.89 | 1.7 | 1.7 | 2.89 | 1 | 155 | 1 | 1 | 155
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | duct | 1.6 | 1.6 | 2.56 | 1.6 | 1.6 | 2.56 | 1 | 155 | 1 | 1 | 155
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | duct | 1.7 | 1.7 | 2.89 | 1.7 | 1.7 | 2.89 | 1 | 155 | 1 | 1 | 155
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | cable tray |  |  |  | 0.35 | 0.15 | 0.0525 | 1 | 60 | 1 | 1 | 60
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | opening |  |  |  | 1.7 | 1.8 | 3.06 | 2 | 275 | 1 | 2 | 550
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45546 | 2020-11-01 | Hotel | B1 | 2 | Fan Room | opening |  |  |  | 1.7 | 1.85 | 3.145 | 2 | 275 | 1 | 2 | 550
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Changing Room | duct | 0.6 | 0.4 | 0.24 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Changing Room | opening |  |  |  | 0.65 | 0.45 | 0.2925 | 2 | 300 | 1 | 2 | 600
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Changing Room | duct | 0.45 | 0.4 | 0.18 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Changing Room | opening |  |  |  | 0.5 | 0.45 | 0.225 | 2 | 220 | 1 | 2 | 440
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Changing Room | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Changing Room | duct | 0.6 | 0.3 | 0.18 | 0.63 | 0.33 | 0.2079 | 2 | 86 | 1 | 2 | 172
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | duct | 0.4 | 0.3 | 0.12 | 0.43 | 0.33 | 0.1419 | 2 | 69 | 2 | 4 | 276
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | duct | 0.25 | 0.25 | 0.0625 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | opening |  |  |  | 0.5 | 0.45 | 0.225 | 2 | 220 | 1 | 2 | 440
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | duct | 0.25 | 0.25 | 0.0625 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Staff Changing Rm | opening |  |  |  | 0.45 | 0.45 | 0.2025 | 2 | 220 | 1 | 2 | 440
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | fire fighting pipe | 3 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | conduit (pvc) | 1 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | Male Prayer Rm | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#7 Nov'20 | RPJV | 45560 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 21 | 42 | 756
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | duct | 0.4 | 0.25 | 0.1 | 0.43 | 0.28 | 0.1204 | 2 | 69 | 1 | 2 | 138
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | opening |  |  |  | 0.8 | 0.2 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | House Keeping | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | duct | 0.7 | 0.4 | 0.28 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | opening |  |  |  | 0.9 | 0.45 | 0.405 | 2 | 375 | 1 | 2 | 750
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 20 | 40 | 720
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 1 | 2 | 88
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.23 | 0.0989 | 2 | 62 | 1 | 2 | 124
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Linnen Store | duct | 0.3 | 0.2 | 0.06 | 0.33 | 0.23 | 0.0759 | 2 | 62 | 1 | 2 | 124
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 0 | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | duct | 0.4 | 0.3 | 0.12 |  |  |  | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | opening |  |  |  | 0.5 | 0.5 | 0.25 | 2 | 220 | 1 | 2 | 440
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | duct | 0.5 | 0.4 | 0.2 | 0.53 | 0.43 | 0.2279 | 2 | 86 | 1 | 2 | 172
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | duct | 0.4 | 0.3 | 0.12 | 0.43 | 0.33 | 0.1419 | 2 | 69 | 2 | 4 | 276
PC#7 Nov'20 | RPJV | 45561 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#7 Nov'20 | RPJV | 45562 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | duct | 0.45 | 0.3 | 0.135 |  |  |  | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45562 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | opening |  |  |  | 0.5 | 0.4 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#7 Nov'20 | RPJV | 45562 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#7 Nov'20 | RPJV | 45562 | 2020-11-01 | Hotel | B1 | 2 | Female Changing Rm | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.15 | 0.2 | 0.03 | 2 | 44 | 1 | 2 | 88
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.25 | 0.3 | 0.075 | 2 | 62 | 1 | 2 | 124
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | duct | 0.4 | 0.4 | 0.16 | 0.4 | 0.4 | 0.16 | 2 | 69 | 2 | 4 | 276
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | duct | 0.5 | 0.5 | 0.25 | 0.5 | 0.5 | 0.25 | 2 | 86 | 2 | 4 | 344
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Shaft | duct | 0.4 | 0.4 | 0.16 | 0.43 | 0.43 | 0.1849 | 2 | 69 | 1 | 2 | 138
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Entry D | duct | 0.4 | 0.4 | 0.16 | 0.43 | 0.45 | 0.1935 | 2 | 69 | 1 | 2 | 138
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Entry D | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Entry D | conduit (pvc) | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#7 Nov'20 | RPJV | 45548 | 2020-10-26 | Hotel | 11 | 2 | Room no. 16A, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 5A, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 5A, Shaft | PVC pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 5A, Shaft | PVC pipe | 2 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 5A, Shaft | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2G&3F, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2G&3F, Shaft | PVC pipe | 2 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2G&3F, Shaft | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2F&3C, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2F&3C, Shaft | PVC pipe | 2 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2F&3C, Shaft | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2D&3B, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2D&3B, Shaft | PVC pipe | 2 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2D&3B, Shaft | HDPE pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 2D&3B, Shaft | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 14A, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 14A, Shaft | PVC pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45549 | 2020-10-26 | Hotel | 24 | 2 | Room no. 14A, Shaft | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 6A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 6A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 12A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 12A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 11A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 5 | 5 | 140
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 11A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 5 | 5 | 325
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 3D | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 3D | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 2A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45547 | 2020-11-03 | Hotel | 22 | 2 | Room no. 2A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 701 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 701 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 702 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 702 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 703 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 703 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 704 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 704 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 705 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 705 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 706 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 706 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 709 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 709 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 710 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#7 Nov'20 | RPJV | 45557 | 2020-11-05 | Hotel | 7 | 2 | Room no. 710 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 2 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 2 | [5 empty] | 2 |  | 4 | 8 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 4 | [5 empty] | 2 |  | 4 | 8 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 8 | 16 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | opening |  |  |  | 1 | 0.6 | 0.6 | 2 | 410 | 4 | 8 | 3280
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | PVC pipe | 6 | [5 empty] | 2 |  | 2 | 4 | 0
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D, Shaft | opening |  |  |  | 1 | 0.6 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D | PVC pipe | 2" |  |  | 4'' |  |  | 1 | 28 | 14 | 14 | 392
PC#7 Nov'20 | RPJV | 45559 | 2020-11-18 | Hotel | 18 | Void | Room no. 4D | PVC pipe | 4" |  |  | 6'' |  |  | 1 | 65 | 18 | 18 | 1170
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PPR pipe | 3 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PVC conduit pipe | 1 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CDP pipe | 3 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PVC conduit pipe | 2 | [5 empty] | 2 |  | 11 | 22 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PPR pipe | 3 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PPR pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PPR pipe | 6 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PVC conduit pipe | 2 | [5 empty] | 2 |  | 5 | 10 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#8 Dec'20 | RPJV | 45563 | 2020-12-05 | Hotel | 11 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 10A, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 10A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 10A, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 10A, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 5A, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 5A, Entry Door | PPR pipe | 3" |  |  | 3" |  |  | 2 | 30 | 3 | 6 | 180
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 5A, Entry Door | CHW pipe | 3" |  |  | 3" |  |  | 2 | 23 | 2 | 4 | 92
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Room 5A, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Shaft | PVC pipe (riser) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 4 | 180
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Shaft | PVC pipe (riser) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 6 | 630
PC#8 Dec'20 | RPJV | 45564 | 2020-12-09 | Hotel | 12 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.3 | 0.4 | 0.12 | 2 | 69 | 1 | 2 | 138
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 7 | 14 | 0
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 8 | 16 | 0
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45565 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 8 | 16 | 0
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 9 | 18 | 0
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45566 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 7 | 14 | 0
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 7 | 14 | 0
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45567 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4 | [5 empty] | 2 |  | 1 | 2 | 0
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CHW pipe | 3 | [5 empty] | 2 |  | 2 | 4 | 0
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2 | [5 empty] | 2 |  | 7 | 14 | 0
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | opening |  |  |  | 0.9 | 0.5 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#8 Dec'20 | RPJV | 45568 | 2020-12-06 | Residence | 7 | 3 | House Keeping Lobby | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Grease Trap Rm | duct | 0.35 | 0.35 | 0.1225 | 0.45 | 0.45 | 0.2025 | 2 | 69 | 1 | 2 | 138
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Grease Trap Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Grease Trap Rm | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Grease Trap Rm | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Grease Trap Rm | duct | 0.35 | 0.35 | 0.1225 | 0.45 | 0.45 | 0.2025 | 2 | 69 | 1 | 2 | 138
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Staircase | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Staircase | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Staircase | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | FTR | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | FTR | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | FTR | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | FTR | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | duct | 0.3 | 0.2 | 0.06 | 0.4 | 0.3 | 0.12 | 2 | 69 | 3 | 6 | 414
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | fire fighting pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | MEP | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Electrical Rm | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 4 | 8 | 480
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Electrical Rm | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Electrical Rm | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45569 | 2021-01-04 | Residence | B2 | 3 | Electrical Rm | cable tray |  |  |  | 0.95 | 0.1 | 0.095 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Electrical Rm | duct | 0.3 | 0.15 | 0.045 | 0.4 | 0.25 | 0.1 | 1 | 62 | 2 | 2 | 124
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Electrical Rm | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Lobby | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Water Meter Room | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | FF Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | FF Lobby | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Staircase 3 | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Staircase 3 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Plenum Room 1 | duct | 2 | 0.75 | 1.5 | 2.1 | 0.85 | 1.785 | 1 | 277.45 | 2 | 2 | 554.9
PC#9 Jan'21 | RPJV | 45570 | 2021-01-04 | Residence | B2 | 3 | Plenum Room 1 | duct | 2 | 0.75 | 1.5 | 2.1 | 0.85 | 1.785 | 1 | 277.45 | 1 | 1 | 277.45
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 2 |  | 3 | 6 | 0
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | opening |  |  |  | 1.7 | 1.7 | 2.89 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | duct | 0.9 | 0.5 | 0.45 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | opening |  |  |  | 0.95 | 0.65 | 0.6175 | 2 | 410 | 1 | 2 | 820
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 | 1.7 | 1.7 | 2.89 | 1 | 447.95 | 3 | 3 | 1343.85
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | CEF Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 2 | 4 | 240
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Electrical cabinet | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | duct | 0.9 | 0.5 | 0.45 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | opening |  |  |  | 1 | 0.6 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | duct | 2.3 | 0.9 | 2.07 | 2.4 | 1 | 2.4 | 1 | 372 | 1 | 1 | 372
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45571 | 2021-01-04 | Residence | B2 | 3 | Ventilation Shaft | duct | 2 | 0.75 | 1.5 | 2.1 | 0.85 | 1.785 | 1 | 277.45 | 1 | 1 | 277.45
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 2 | 4 | 120
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | CHW pipe | 16" |  |  | 18" |  |  | 2 | 170 | 2 | 4 | 680
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | duct | 0.8 | 0.6 | 0.48 | 0.84 | 0.63 | 0.5292 | 2 | 110 | 1 | 2 | 220
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | opening |  |  |  | 0.7 | 0.55 | 0.385 | 2 | 375 | 1 | 2 | 750
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray | 0.25 | 0.05 | 0.0125 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 2 | 4 | 240
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | opening |  |  |  | 0.5 | 0.2 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable trunking |  |  |  | 0.14 | 0.14 | 0.0196 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | duct | 0.8 | 0.5 | 0.4 | 0.83 | 0.53 | 0.4399 | 2 | 110 | 1 | 2 | 220
PC#9 Jan'21 | RPJV | 45572 | 2021-01-04 | Hotel | B1 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Corridor | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 2 |  | 3 | 6 | 0
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | opening |  |  |  | 1.7 | 1.7 | 2.89 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | cable tray |  |  |  | 0.33 | 0.08 | 0.0264 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | duct | 1.6 | 1.6 | 2.56 | 1.7 | 1.7 | 2.89 | 1 | 447.95 | 3 | 3 | 1343.85
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | PPR pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | opening |  |  |  | 0.5 | 0.3 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | CSF Room | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | duct | 0.7 | 0.4 | 0.28 | 0.73 | 0.43 | 0.3139 | 2 | 86 | 1 | 2 | 172
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | duct | 0.5 | 0.4 | 0.2 | 0.53 | 0.43 | 0.2279 | 2 | 69 | 1 | 2 | 138
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Ice Production | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Ice Production | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Ice Production | PPR pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Ice Production | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Ice Production | duct | 0.5 | 0.3 | 0.15 | 0.53 | 0.33 | 0.1749 | 2 | 69 | 3 | 6 | 414
PC#9 Jan'21 | RPJV | 45573 | 2021-01-04 | Hotel | B1 | 2 | Ice Production | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | duct | 0.15 | 0.15 | 0.0225 | 0.18 | 0.18 | 0.0324 | 2 | 44 | 1 | 2 | 88
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Beverage Store | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | duct | 0.15 | 0.15 | 0.0225 | 0.18 | 0.18 | 0.0324 | 2 | 44 | 1 | 2 | 88
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | duct | 0.3 | 0.3 | 0.33 | 0.33 | 0.33 | 0.1089 | 2 | 69 | 2 | 4 | 276
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Store Control Rm | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45574 | 2021-01-04 | Hotel | B1 | 2 | Vegetable Store | cable tray |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | PVC conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 4 | 8 | 144
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | duct | 0.3 | 0.15 | 0.045 | 0.33 | 0.18 | 0.0594 | 2 | 44 | 1 | 2 | 88
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.23 | 0.0989 | 2 | 62 | 1 | 2 | 124
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | PVC conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Dry store | duct | 0.3 | 0.15 | 0.045 | 0.33 | 0.18 | 0.0594 | 2 | 44 | 1 | 2 | 88
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | duct | 0.4 | 0.2 | 0.08 | 0.43 | 0.23 | 0.0989 | 2 | 62 | 1 | 2 | 124
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | HDPE pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | opening |  |  |  | 0.6 | 0.3 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | cable tray | 0.8 | 0.05 | 0.04 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | opening |  |  |  | 0.9 | 0.2 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | cable tray | 0.6 | 0.05 | 0.03 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45575 | 2021-01-04 | Hotel | B1 | 2 | Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | duct | 1.2 | 0.65 | 0.78 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | gas pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | opening |  |  |  | 1.4 | 1.3 | 1.82 | 2 | 400 | 1 | 2 | 800
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 1 | 2 | 46
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | duct | 1.2 | 0.65 | 0.78 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | PVC conduit pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | opening |  |  |  | 1.7 | 0.85 | 1.445 | 2 | 400 | 1 | 2 | 800
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | opening |  |  |  | 0.4 | 0.2 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable trunking |  |  |  | 0.23 | 0.23 | 0.0529 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 4 | 8 | 0
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | duct | 0.3 | 0.3 | 0.09 | 0.4 | 0.4 | 0.16 | 1 | 62 | 1 | 1 | 62
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray |  |  |  | 0.63 | 0.08 | 0.0504 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | duct | 0.3 | 0.3 | 0.09 | 0.4 | 0.4 | 0.16 | 1 | 62 | 1 | 1 | 62
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray |  |  |  | 0.33 | 0.09 | 0.0297 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray |  |  |  | 0.63 | 0.08 | 0.0504 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#9 Jan'21 | RPJV | 45576 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | duct | 0.3 | 0.3 | 0.09 | 0.4 | 0.4 | 0.16 | 1 | 62 | 1 | 1 | 62
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Staircase | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | opening |  |  |  | 0.7 | 0.5 | 0.35 | 2 | 300 | 1 | 2 | 600
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | opening |  |  |  | 0.7 | 0.5 | 0.35 | 2 | 300 | 1 | 2 | 600
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#9 Jan'21 | RPJV | 45577 | 2021-01-04 | Hotel | B1 | 2 | Staircase | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 6" | [5 empty] | 2 |  | 3 | 6 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 2" | [5 empty] | 2 |  | 3 | 6 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 4" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | PVC pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 12 | 2 | Shaft/Riser | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 24 | 2 | Shaft/Riser | PVC pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 24 | 2 | Shaft/Riser | PVC pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#9 Jan'21 | RPJV | 45558 | 2021-01-02 | Hotel | 24 | 2 | Shaft/Riser | opening |  |  |  | 2.85 | 0.85 | 2.4225 | 2 | 325 | 1 | 2 | 650
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Shaft/Riser | PVC pipe | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Shaft/Riser | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Shaft/Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Shaft/Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Entry Door | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 6A, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Entry Door | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Shaft/Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Shaft/Riser | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 12A, Shaft/Riser | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Entry Door | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Shaft/Riser | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#10 Feb'21 | RPJV | 45578 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Shaft/Riser | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Shaft/Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 2D, Partition Wall | duct | 0.25 | 0.25 | 0.0625 | 0.28 | 0.28 | 0.0784 | 2 | 62 | 2 | 4 | 248
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Shaft/Riser | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Shaft/Riser | PVC pipe | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Shaft/Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Entry Door | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 3A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Shaft/Riser | Duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Shaft/Riser | PVC pipe | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Shaft/Riser | PVC pipe | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 2 | 90
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Entry Door | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#10 Feb'21 | RPJV | 45579 | 2021-02-09 | Hotel | 21 | 2 | Room 11B, Entry Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 10 | 20 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PPR pipe | 5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 5 | 10 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#11 Mar'21 | RPJV | 45580 | 2021-03-10 | Hotel | 9 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45581 | 2021-03-10 | Hotel | 9 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#11 Mar'21 | RPJV | 45581 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#11 Mar'21 | RPJV | 45581 | 2021-03-10 | Hotel | 9 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 | 0 | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 0 | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 | 0 | 5 | 10 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PPR pipe | 5" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 | 0 | 10 | 20 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 0 | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 | 0 | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | conduit pipe | 1" | [5 empty] | 2 | 0 | 1 | 2 | 0
PC#11 Mar'21 | RPJV | 45582 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#11 Mar'21 | RPJV | 45583 | 2021-03-10 | Hotel | 10 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 0 | 3 | 6 | 0
PC#11 Mar'21 | RPJV | 45583 | 2021-03-10 | Hotel | 10 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 0 | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45583 | 2021-03-10 | Hotel | 10 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 | 0 | 2 | 4 | 0
PC#11 Mar'21 | RPJV | 45583 | 2021-03-10 | Hotel | 10 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 10 | 20 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 3 | 6 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45584 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 6" |  |  | 8" |  |  | 2 | 125 | 2 | 4 | 500
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45585 | 2021-04-04 | Hotel | 12 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | duct | 0.25 | 0.3 | 0.075 | 0.35 | 0.4 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | duct | 0.25 | 0.3 | 0.075 | 0.35 | 0.4 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45586 | 2021-04-04 | Hotel | 10 | 2 | Room no. 15A | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 1 | 62 | 1 | 1 | 62
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 6A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 6A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 6A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 6A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 12A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 12A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 12A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 12A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 19A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 19A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 19A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45587 | 2021-04-04 | Hotel | 19 | 2 | Room no. 19A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 6A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 6A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 6A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 6A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 12A | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 12A | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 12A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 12A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 12A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 11A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 11A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 11A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 11A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 3D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 3D | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 3D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 3D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 2A | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 2A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 2A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#12 Apr'21 | RPJV | 45588 | 2021-04-07 | Hotel | 22 | 2 | Room no. 2A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | duct | 0.25 | 0.3 | 0.075 | 0.35 | 0.4 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | duct | 0.25 | 0.3 | 0.075 | 0.35 | 0.4 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#12 Apr'21 | RPJV | 45589 | 2021-04-14 | Hotel | 8 | 2 | Room no. 7A | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 2C, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 2C, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 2C, P. Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.24 | 0.0552 | 2 | 62 | 2 | 4 | 248
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 2C, P. Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 2C, P. Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 2C, P. Wall | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 3A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 3A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 7 | 2 | Room no. 3A, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, E. Door | fire fighting pipe | 2" |  |  | 9 |  |  | 2 | 16 | 1 | 2 | 32
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, P. Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, P. Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, P. Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#12 Apr'21 | RPJV | 45590 | 2021-04-15 | Hotel | 13 | 2 | Room no. 5A, P. Wall | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Room no. 7A | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Room no. 7A | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | FTR | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | FTR | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | FTR | cable trucking |  |  |  | 0.13 | 0.132 | 0.01716 | 2 | 60 | 2 | 4 | 240
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | FTR | cable trucking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | FTR | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | FTR | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Electrical Room | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Electrical Room | cable trunking |  |  |  | 0.07 | 0.08 | 0.0056 | 2 | 60 | 2 | 4 | 240
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Electrical Room | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 2 | 4 | 240
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | duct | 0.25 | 0.25 | 0.0625 | 0.28 | 0.28 | 0.0784 | 2 | 62 | 1 | 2 | 124
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | PPR pipe | 1" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | BOH Service WC | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#13 May'21 | RPJV | 45591 | May'2021 | Hotel | 8 | 2 | Electrical Room | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 10 | 20 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45592 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 11 | 22 | 396
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | cable tray |  |  |  | 0.17 | 0.08 | 0.0136 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45593 | 2021-05-18 | Hotel | 13 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 5A, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 5A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 5A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 5A, Part W | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 5A, Part W | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 5A, Part W | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 7A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 7A, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 3 | 3 | 147
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 7A, E. Dr | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 7A, E. Dr | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, E. Dr | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, E. Dr | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, E. Dr | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 1 | 1 | 49
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | duct | 0.2 | 0.15 | 0.03 | 0.3 | 0.25 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | duct | 0.2 | 0.15 | 0.03 | 0.3 | 0.25 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#13 May'21 | RPJV | 45594 | 2021-05-18 | Hotel | 13 | 2 | Room no. 19, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 1 | 1 | 49
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 10 | 20 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45595 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | duct | 0.3 | 0.25 | 0.075 | 0.4 | 0.35 | 0.14 | 1 | 69 | 1 | 1 | 69
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#13 May'21 | RPJV | 45596 | 2021-05-18 | Hotel | 14 | 2 | Corridor | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, Riser | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, Riser | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, E. Door | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 1C, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, E. Door | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, Riser | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, Riser | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 4B, Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 8A, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 8A, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 8A, E. Door | fire fighting pipe | 2" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 8A, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55201 | 2021-06-19 | Hotel | 7 | 2 | Room no. 8A, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, Riser | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, Riser | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, E. Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2B, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2C, E. Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2C, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2C, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2C, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55202 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 3A, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Partition Wall | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 44 | 2 | 4 | 176
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Partition Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Partition Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, Riser | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, Riser | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, E. Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 2A, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 7A, Riser | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 7A, Riser | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 7A, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 7A, Riser | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 3 | 3 | 147
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, E. Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, E. Door | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, E. Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55203 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, E. Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#14 Jun'21 | RPJV | 55204 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, Riser | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#14 Jun'21 | RPJV | 55204 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, Riser | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#14 Jun'21 | RPJV | 55204 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, Riser | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55204 | 2021-06-19 | Hotel | 7 | 2 | Room no. 19, Riser | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | FTR | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | FTR | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | FTR | cable trunking |  |  |  | 0.13 | 0.132 | 0.01716 | 2 | 60 | 2 | 4 | 240
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | FTR | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | FTR | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | FTR | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Electrical Room | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Electrical Room | cable trunking |  |  |  | 0.07 | 0.08 | 0.0056 | 2 | 60 | 2 | 4 | 240
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Electrical Room | cable trunking |  |  |  | 0.13 | 0.13 | 0.0169 | 2 | 60 | 2 | 4 | 240
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Electrical Room | duct | 0.25 | 0.25 | 0.0625 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 2 | 2 | 138
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | BOH Service WC | PPR pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | BOH Service WC | PVC pipe | 2" |  |  | 4" |  |  | 2 | 18 | 2 | 4 | 72
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | BOH Service WC | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | BOH Service WC | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | cable tray | 0.15 | 0.05 | 0.0075 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PVC conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | fire fighting pipe | 1.5" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.9 | 0.65 | 0.585 | 2 | 540 | 1 | 2 | 1080
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55205 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 10 | 20 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.65 | 0.35 | 0.2275 | 2 | 220 | 1 | 2 | 440
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PVC conduit pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.6 | 0.4 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | PVC conduit pipe | 2" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55206 | 2021-06-19 | Hotel | 7 | 2 | Corridor | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 10 | 3 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 11 | 3 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 12 | 3 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 4 | 2 | Men Rest room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 4 | 4 | 72
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 4 | 2 | Men Rest room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 8 | 8 | 520
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 15 | 2 | 7A (1610) | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 8 | 2 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 9 | 2 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 10 | 2 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 11 | 2 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#14 Jun'21 | RPJV | 55207 | 2021-06-19 | Hotel | 12 | 2 | Housekeeping Lobby | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | duct | 0.35 | 0.35 | 0.1225 | 0.45 | 0.45 | 0.2025 | 1 | 69 | 1 | 1 | 69
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | duct | 0.35 | 0.35 | 0.1225 | 0.45 | 0.45 | 0.2025 | 1 | 69 | 1 | 1 | 69
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 7 | 14 | 910
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Grease Trap Room | PPR pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | cable tray |  |  |  | 0.18 | 0.08 | 0.0144 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Water Filtration | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Lift Lobby | PVC conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Lift Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Lift Lobby | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Lift Lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | Lift Lobby | duct | 0.55 | 0.55 | 0.3025 | 0.65 | 0.65 | 0.4225 | 1 | 110 | 2 | 2 | 220
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | duct | 1.8 | 0.9 | 1.62 | 1.9 | 1 | 1.9 | 1 |  | 3 | 3 | 0
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 2 |  | 3 | 6 | 0
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | opening |  |  |  | 1.7 | 1.7 | 2.89 | 2 | 325 | 1 | 2 | 650
PC#14 Jun'21 | RPJV | 55208 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | cable trunking |  |  |  | 0.18 | 0.18 | 0.0324 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | conduit pipe | 2" |  |  | 4" |  |  | 2 | 18 | 4 | 8 | 144
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | cable tray |  |  |  | 0.33 | 0.08 | 0.0264 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | EA Plenum Room | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Staircase | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable tray | 0.6 | 0.09 | 0.054 |  |  |  | 2 |  | 3 | 6 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 3 | 6 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable tray | 0.1 | 0.05 | 0.005 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | bus bar | 0.3 | 0.1 | 0.03 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | opening |  |  |  | 2.4 | 0.8 | 1.92 | 2 | 400 | 1 | 2 | 800
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | opening |  |  |  | 0.8 | 0.5 | 0.4 | 2 | 375 | 1 | 2 | 750
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.3 | 0.3 | 0.09 | 1 | 44 | 2 | 2 | 88
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Staircase | fire fighting pipe | 6" |  |  | 8" |  |  | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Staircase | duct | 0.55 | 0.55 | 0.3025 |  |  |  | 2 |  | 2 | 4 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Staircase | opening |  |  |  | 0.6 | 0.6 | 0.36 | 2 | 375 | 1 | 2 | 750
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Staircase | duct | 0.9 | 0.8 | 0.72 |  |  |  | 2 |  | 1 | 2 | 0
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Staircase | opening |  |  |  | 0.93 | 0.85 | 0.7905 | 2 | 480 | 1 | 2 | 960
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Irigation Tank | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 5 | 10 | 1250
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Irigation Tank | duct | 0.55 | 0.55 | 0.3025 | 0.6 | 0.6 | 0.36 | 1 | 100 | 2 | 2 | 200
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Irigation Tank | HDPE pipe | 4" |  |  | 6" |  |  | 2 | 65 | 9 | 18 | 1170
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Irigation Tank | HDPE pipe | 6" |  |  | 8" |  |  | 2 | 125 | 3 | 6 | 750
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Irigation Tank | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#14 Jun'21 | RPJV | 55209 | 2021-06-19 | Residence | B1 | 3 | Irigation Tank | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 01 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 01 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 01 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 01 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 02 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 02 | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 02 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 02 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 8 | 8 | 144
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 03 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55210 | 2021-07-03 | Hotel | 25 | 2 | Room no. 04 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 12 | 12 | 216
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 05 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 12 | 12 | 216
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | fire fighting pipe | 2" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | PVC pipe | 2" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 06 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 10 | 10 | 180
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 07 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 07 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 07 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#15 Jul'21 | RPJV | 55211 | 2021-07-03 | Hotel | 25 | 2 | Room no. 07 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 14 | 14 | 252
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 08 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 08 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 08 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 08 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 08 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 08 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 14 | 14 | 252
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 09 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 09 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 09 | fire fighting pipe | 2" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 09 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 09 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 09 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 10 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 10 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 10 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 62 | 1 | 1 | 62
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 10 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 10 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55212 | 2021-07-03 | Hotel | 25 | 2 | Room no. 10 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.25 | 0.065 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 11 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | PVC pipe | 2" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 12 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 12 | 12 | 216
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#15 Jul'21 | RPJV | 55213 | 2021-07-04 | Hotel | 25 | 2 | Room no. 14 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 13 | 13 | 234
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 15 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 7 | 7 | 126
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 16 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 11 | 11 | 198
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 3 | 6 | 108
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55214 | 2021-07-05 | Hotel | 25 | 2 | Room no. 17 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Dish Wash Room | PVC pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Dish Wash Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Dish Wash Room | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 2 | 4 | 240
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | opening |  |  |  | 0.2 | 0.5 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | opening |  |  |  | 0.15 | 0.4 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | cable trunking |  |  |  | 0.1 | 0.15 | 0.015 | 2 | 60 | 1 | 2 | 120
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | opening |  |  |  | 0.18 | 0.4 | 0.072 | 2 | 115 | 1 | 2 | 230
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#15 Jul'21 | RPJV | 55215 | 2021-07-08 | Hotel | 12 | 2 | FTR Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 10 | 10 | 650
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | PVC pipe | 2" |  |  | 4" |  |  | 1 | 18 | 9 | 9 | 162
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | PVC pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | PVC pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | PVC pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | PVC pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55216 | 2021-07-08 | Hotel | 6 | 3 | Slab work | opening |  |  |  | 0.4 | 0.8 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | CHW pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | duct | 0.53 | 0.67 | 0.3551 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | opening |  |  |  | 0.73 | 1.4 | 1.022 | 2 | 400 | 1 | 2 | 817.6
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 5 | 10 | 0
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | opening |  |  |  | 0.4 | 0.8 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#15 Jul'21 | RPJV | 55217 | 2021-07-08 | Hotel | GF | 2 | MEP Work | gas pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PPR pipe | 4" | [5 empty] | 2 |  | 5 | 10 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" | [5 empty] | 2 |  | 6 | 12 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 0.35 | 1.05 | 0.3675 | 2 | 375 | 1 | 2 | 750
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PPR pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | CDP pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" | [5 empty] | 2 |  | 14 | 28 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" | [5 empty] | 2 |  | 9 | 18 | 0
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 0.7 | 1 | 0.7 | 2 | 480 | 1 | 2 | 960
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | cable trunking |  |  |  | 0.16 | 0.16 | 0.0256 | 1 | 60 | 1 | 1 | 60
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 1 | 60 | 1 | 1 | 60
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | duct | 0.3 | 0.6 | 0.18 | 0.35 | 0.65 | 0.2275 | 2 | 69 | 2 | 4 | 276
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | duct | 0.5 | 0.6 | 0.3 | 0.56 | 0.66 | 0.3696 | 2 | 100 | 1 | 2 | 200
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.56 | 0.196 | 2 | 69 | 1 | 2 | 138
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PPR pipe | 2" |  |  | 4" |  |  | 2 | 18 | 6 | 12 | 216
PC#15 Jul'21 | RPJV | 55218 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 6 | 12 | 240
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 4 | 8 | 128
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | duct | 0.55 | 0.95 | 0.5225 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 0.67 | 1.05 | 0.7035 | 2 | 480 | 1 | 2 | 960
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | duct | 0.95 | 1.35 | 1.2825 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 1.05 | 1.47 | 1.5435 | 2 | 400 | 1 | 2 | 1234.8
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | duct | 0.95 | 1.35 | 1.2825 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | opening |  |  |  | 1.07 | 1.47 | 1.5729 | 2 | 400 | 1 | 2 | 1258.32
PC#15 Jul'21 | RPJV | 55219 | 2021-07-11 | Hotel | 4 | 2 | MEP Work | PVC pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 1.6 | 1.6 | 2.56 |  |  |  | 1 |  | 1 | 1 | 0
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 1.67 | 1.86 | 3.1062 | 1 | 275 | 1 | 1 | 854.205
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 1.6 | 1.6 | 2.56 |  |  |  | 1 |  | 1 | 1 | 0
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 1.67 | 1.86 | 3.1062 | 1 | 275 | 1 | 1 | 854.205
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 1.6 | 1.6 | 2.56 |  |  |  | 1 |  | 1 | 1 | 0
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 1.67 | 1.86 | 3.1062 | 1 | 275 | 1 | 1 | 854.205
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 1.6 | 1.6 | 2.56 | 1.65 | 1.65 | 2.7225 | 1 | 100 | 1 | 1 | 272.25
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 1.6 | 1.6 | 2.56 | 1.65 | 1.65 | 2.7225 | 1 | 100 | 1 | 1 | 272.25
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 1.6 | 1.6 | 2.56 | 1.65 | 1.65 | 2.7225 | 1 | 100 | 1 | 1 | 272.25
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | duct | 0.8 | 0.8 | 0.64 |  |  |  | 2 |  | 1 | 2 | 0
PC#15 Jul'21 | RPJV | 55220 | 2021-07-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.9 | 0.9 | 0.81 | 2 | 540 | 1 | 2 | 1080
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | B1 | 3 | FTR Room | opening |  |  |  | 0.5 | 2.2 | 1.1 | 2.2 | 400 | 1 | 2.2 | 880
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | B1 | 3 | FTR Room | blank opening |  |  |  | 0.4 | 1.6 | 0.64 | 2 | 410 | 1 | 2 | 820
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | cable tray |  |  |  | 0.1 | 0.24 | 0.024 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Entry Door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | cable tray |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 2 | 4 | 880
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 1 | 205 | 2 | 2 | 410
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 3BD-3L, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | cable tray |  |  |  | 0.08 | 0.13 | 0.0104 | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 |  | 4 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | PPR pipe | 3" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | PPR pipe | 3" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 2 | 2 | 98
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 17 | 3 | 4BD-4B, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 2 | 2 | 98
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | duct | 0.3 | 0.6 | 0.18 | 0.35 | 0.68 | 0.238 | 1 | 86 | 1 | 1 | 86
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | 4BD-4B, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 3 | 6 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Water Meter Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#16 Aug'21 | RPJV | 552XX | 2021-08-15 | Residence | 18 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | cable tray |  |  |  | 0.08 | 0.13 | 0.0104 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | cable tray |  |  |  | 0.1 | 0.24 | 0.024 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Entry Dr | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Housekeeping | fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Housekeeping | opening |  |  |  | 0.6 | 1.1 | 0.66 | 2 | 480 | 1 | 2 | 960
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Staircase | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | Staircase | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | fire fighting pipe | 1" | [6 empty] | 16 |  | 0 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | cable tray | 0.05 | 0.25 | 0.0125 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | FTR Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-18 | Residence | 18 | 3 | 4BD, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | duct | 0.2 | 0.4 | 0.08 | 0.3 | 0.45 | 0.135 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 4 | 420
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 18 | 3 | 4BD, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 3 | 3 | 84
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 3BD-Simp, Entry Dr | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | PPR pipe | 3" |  |  | 5" |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | PPR pipe | 2" |  |  | 4" |  |  | 1 |  | 2 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | GSM cable | 0.5" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Entry Dr | opening |  |  |  | 0.1 | 0.2 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 1 | 1 | 49
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD-Ldup, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | fire fighting pipe | 6" | [5 empty] | 1 |  | 3 | 3 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | conduit pipe | 1" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | opening |  |  |  | 0.3 | 0.6 | 0.18 | 1 | 220 | 1 | 1 | 220
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 1 | 1 | 18
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | fire fighting pipe | 6" |  |  | 8'' |  |  | 2 | 30 | 3 | 6 | 180
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 19 | 3 | 4BD, Shaft | fire fighting pipe | 3" |  |  | 5'' |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 1 | 1 | 69
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4B, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | cable tray |  |  |  | 0.1 | 0.24 | 0.024 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 3 | 3 | 84
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 1 | 23 | 1 | 1 | 23
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 20 | 3 | 4BD-4D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 1 | 1 | 49
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Entry Door | cable tray |  |  |  | 0.1 | 0.24 | 0.024 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-4B, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 3 | 3 | 84
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 2BD-2A, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 1 | 23 | 1 | 1 | 23
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 21 | 3 | 4BD-2D, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 |  | 2 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Entry Door | PVC pipe | 4" |  |  | 6" |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Entry Door | GSM cable | 0.5" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Entry Door | opening |  |  |  | 0.1 | 0.2 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 49 | 1 | 1 | 49
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 4BD-4B, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 3 | 3 | 84
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Entry Dr | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 1 | 44 | 1 | 1 | 44
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-19 | Residence | 22 | 3 | 3BD-Simp, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | duct | 0.25 | 0.5 | 0.125 | 0.3 | 0.55 | 0.165 | 1 | 69 | 2 | 2 | 138
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | CDP pipe (shaft) | 4" |  |  | 6" |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | duct | 0.1 | 0.25 | 0.025 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | opening |  |  |  | 0.4 | 1.2 | 0.48 | 2 | 375 | 1 | 2 | 750
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | opening |  |  |  | 0.2 | 0.75 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Yoga Studio, Entry Dr | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | PVC pipe | 8" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | opening |  |  |  | 0.5 | 1.1 | 0.55 | 2 | 410 | 1 | 2 | 820
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | opening |  |  |  | 0.3 | 1.1 | 0.33 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 2 | 4 | 72
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | opening |  |  |  | 0.25 | 0.4 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | opening |  |  |  | 0.25 | 0.4 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Housekeeping | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | opening |  |  |  | 0.2 | 0.5 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 0 | 0 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | PVC pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 0 | 0 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | Lobby | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | FHC | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | duct | 0.25 | 1 | 0.25 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | opening |  |  |  | 0.7 | 1.55 | 1.085 | 2 | 400 | 1 | 2 | 868
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | duct | 0.3 | 0.6 | 0.18 | 0.35 | 0.65 | 0.2275 | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 1 | 2 | 138
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | M. Changing Room | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | duct | 0.2 | 0.5 | 0.1 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | PVC pipe | 8" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | PVC pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | opening |  |  |  | 0.8 | 1.15 | 0.92 | 2 | 540 | 1 | 2 | 1080
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | PVC pipe | 8" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | opening |  |  |  | 12" |  |  | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | PVC pipe | 8" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | PVC pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-21 | Residence | 4 | 3 | F. Changing Room | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 5 | 3 | Plant Room | PVC pipe | 4" |  |  | 6" |  |  | 1 |  | 4 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 5 | 3 | Tance Room | PVC pipe | 4" |  |  | 6" |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 5 | 3 | Tance Room | duct | 0.25 | 0.4 | 0.1 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 5 | 3 | Tance Room | opening |  |  |  | 0.4 | 0.5 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 5 | 3 | Tance Room | duct | 0.25 | 0.4 | 0.1 |  |  |  | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 5 | 3 | Tance Room | opening |  |  |  | 0.4 | 0.5 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 4 | 3 | Slab pipe | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 10 | 10 | 650
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 4 | 3 | Slab pipe | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 9 | 9 | 252
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 2 | 3 | Slab pipe | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 23 | 23 | 1495
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | 2 | 3 | Slab pipe | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 6 | 6 | 168
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 10 | 20 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | opening |  |  |  | 0.54 | 0.84 | 0.4536 | 2 | 375 | 1 | 2 | 750
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 15 | 30 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | opening |  |  |  | 0.54 | 0.84 | 0.4536 | 2 | 375 | 1 | 2 | 750
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Residence | GF | 3 | Lift lobby | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | fire fighting pipe | 1" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | cable tray | 0.05 | 0.15 | 0.0075 |  |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 |  | 3 | 3 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 |  | 2 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | conduit pipe | 1" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | opening |  |  |  | 0.65 | 0.9 | 0.585 | 1 | 410 | 1 | 1 | 410
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Corridor | opening |  |  |  | 0.25 | 0.27 | 0.0675 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Lift Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Lift Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Lift Lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 14 | 28 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Lift Lobby | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Water Meter Room | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Room Service | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Room Service | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Room Service | conduit pipe | 1" | [5 empty] | 2 |  | 8 | 16 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Room Service | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | FF Lobby | opening |  |  |  | 4" |  |  | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | FF Lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | FF Lobby | opening |  |  |  | 4" |  |  | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 20 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 13 | 13 | 234
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | fire fighting pipe | 1" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | cable tray | 0.05 | 0.15 | 0.0075 |  |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 |  | 3 | 3 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 |  | 2 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | conduit pipe | 1" | [5 empty] | 1 |  | 1 | 1 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | opening |  |  |  | 0.65 | 0.9 | 0.585 | 1 | 410 | 1 | 1 | 410
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Corridor | opening |  |  |  | 0.25 | 0.27 | 0.0675 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Lift Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Lift Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Lift Lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 12 | 24 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Lift Lobby | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Water Meter Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Room Service | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Room Service | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Room Service | conduit pipe | 1" | [5 empty] | 2 |  | 7 | 14 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Room Service | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | FF Lobby | opening |  |  |  | 4" |  |  | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | FF Lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | FF Lobby | opening |  |  |  | 4" |  |  | 2 | 60 | 1 | 2 | 120
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 21 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 14 | 14 | 252
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 01, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 01, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 01, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 01, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 02, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 02, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 02, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 02, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 03, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 04, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 04, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 04, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 05, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 05, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 05, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 06, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 07, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 07, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 07, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 07, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 08, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 08, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 08, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 09, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 12, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 12, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 12, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 12, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 12, Shaft | CDP pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 13, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 13, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 14, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 14, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 14, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 15, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 15, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 15, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 16, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 17, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 18, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 18, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#16 Aug'21 | RPJV | 552XX | 2021-08-23 | Hotel | 25 | 2 | Room no. 18, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 5 | 10 | 200
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | CDP pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 5 | 5 | 525
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | cable trunking |  |  |  | 0.15 | 0.3 | 0.045 | 2 | 60 | 2 | 4 | 240
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | cable tray |  |  |  | 0.1 | 0.16 | 0.016 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 4 | 8 | 520
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | opening |  |  |  | 0.08 | 0.2 | 0.016 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | cable trunking |  |  |  | 0.15 | 0.25 | 0.0375 | 2 | 60 | 2 | 4 | 240
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 14 | 28 | 504
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | opening |  |  |  | 0.15 | 0.45 | 0.0675 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | Lounge, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 17 | 34 | 612
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | opening |  |  |  | 0.45 | 1 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | gas pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Shaft | duct | 0.3 | 1 | 0.3 | 0.35 | 1.05 | 0.3675 | 1 | 100 | 1 | 1 | 100
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | cable trunking |  |  |  | 0.14 | 0.15 | 0.021 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.15 | 0.2 | 0.03 | 0.2 | 0.25 | 0.05 | 2 | 44 | 1 | 2 | 88
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.15 | 0.2 | 0.03 | 0.2 | 0.25 | 0.05 | 2 | 44 | 1 | 2 | 88
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | gas pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53180 | 2021-09-07 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 2 | 86 | 2 | 4 | 344
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.3 | 0.6 | 0.18 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.3 | 1 | 0.3 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | opening |  |  |  | 0.66 | 1.7 | 1.122 | 2 | 400 | 1 | 2 | 897.6
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | F. Change Rm, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 12 | 24 | 432
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 4 | 8 | 1000
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.3 | 0.8 | 0.24 | 0.35 | 0.85 | 0.2975 | 2 | 86 | 1 | 2 | 172
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 2 | 86 | 2 | 4 | 344
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 4 | 8 | 520
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53182 | 2021-09-14 | Residence | 23 | 3 | M. Change Rm, Wall | opening |  |  |  | 0.7 | 1.4 | 0.98 | 2 | 540 | 1 | 2 | 1080
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.3 | 1 | 0.3 | 0.35 | 1.05 | 0.3675 | 1 | 100 | 1 | 1 | 100
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.45 | 0.2025 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 1 | 86 | 1 | 1 | 86
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | CHW pipe | 4" |  |  | 6" |  |  | 1 | 29 | 2 | 2 | 58
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | F. Change Rm, Wall | duct | 0.15 | 0.25 | 0.0375 | 0.2 | 0.3 | 0.06 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, Wall | cable trunking |  |  |  | 0.14 | 0.14 | 0.0196 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | PPR pipe | 2" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | PVC pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | gas pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | opening |  |  |  | 0.5 | 1.8 | 0.9 | 2 | 540 | 1 | 2 | 1080
PC#17 Sep'21 | RPJV | 53183 | 2021-09-15 | Residence | 23 | 3 | M. Change Rm, E.Door | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | CDP pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Electrical room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 |  | 2 | 2 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Electrical room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 |  | 1 | 1 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Electrical room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 |  | 1 | 1 | 0
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Electrical room | opening |  |  |  | 0.3 | 1 | 0.3 | 1 | 300 | 1 | 1 | 300
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby, E. Door | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 1 | 1 | 125
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby, E. Door | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby, E. Door | fire fighting pipe | 4" |  |  | 6" |  |  | 1 | 23 | 1 | 1 | 23
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby, E. Door | gas pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#17 Sep'21 | RPJV | 53184 | 2021-09-15 | Residence | 23 | 3 | Lift lobby, E. Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | FHC | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Entry Door | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 2 | 4 | 240
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | conduit pipe | 1" | [5 empty] | 2 |  | 6 | 12 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | opening |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | opening |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Telecom Rm | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 6 | 12 | 0
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | opening |  |  |  | 0.4 | 0.8 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53185 | 2021-09-15 | Residence | 23 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Housekeeping | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Electrical Rm | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Electrical Rm | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Electrical Rm | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Electrical Rm | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Electrical Rm | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 7 | 14 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Lift lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | PVC pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | PVC pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53186 | 2021-09-15 | Residence | 23 | 3 | Water Meter Room | opening |  |  |  | 10" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#17 Sep'21 | RPJV | 53187 | 2021-09-15 | Residence | 23 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 4 | 8 | 184
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | PPR pipe | 3" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53188 | 2021-09-15 | Residence | 21 | 3 | Electrical Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.14 | 0.0112 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 6 | 12 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Housekeeping | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | opening |  |  |  | 0.35 | 0.7 | 0.245 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Telecom | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Telecom | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Telecom | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53189 | 2021-09-15 | Residence | 21 | 3 | Telecom | opening |  |  |  | 0.25 | 0.7 | 0.175 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 4" |  |  | 6" |  |  | 1 | 23 | 1 | 1 | 23
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#17 Sep'21 | RPJV | 53190 | 2021-09-18 | Residence | 21 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 4 | 8 | 184
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | FHC | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | PPR pipe | 3" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Electrical Room | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53191 | 2021-09-18 | Residence | 20 | 3 | Electrical Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Housekeeping | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | opening |  |  |  | 0.35 | 0.7 | 0.245 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Telecom | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53192 | 2021-09-18 | Residence | 20 | 3 | Telecom | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#17 Sep'21 | RPJV | 53193 | 2021-09-18 | Residence | 20 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Staircase | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 1 | 29 | 2 | 2 | 58
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Water Meter Room | PVC pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Water Meter Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53194 | 2021-09-19 | Residence | 20 | 3 | Electrical Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 5 | 10 | 650
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 5" |  |  | 7" |  |  | 2 | 35 | 2 | 4 | 140
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | cable tray |  |  |  | 0.1 | 0.35 | 0.035 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.5 | 0.7 | 0.35 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.65 | 0.7 | 0.455 | 2 | 375 | 1 | 2 | 750
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | PVC pipe | 4" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.7 | 1 | 0.7 | 2 | 480 | 1 | 2 | 960
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | cable tray |  |  |  | 0.4 | 1 | 0.4 | 2 | 375 | 1 | 2 | 750
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 | 86 | 2 | 4 | 344
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | fire fighting pipe | 8" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 1 | 1.7 | 1.7 | 2 | 400 | 1 | 2 | 1360
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | fire fighting pipe | 8" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.3 | 0.4 | 0.12 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.35 | 0.35 | 0.1225 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | PPR pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | cable tray |  |  |  | 0.1 | 0.3 | 0.03 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 6" |  |  | 8" |  |  | 2 | 35 | 2 | 4 | 140
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | duct | 0.4 | 0.6 | 0.24 | 0.5 | 0.7 | 0.35 | 2 | 100 | 1 | 2 | 200
PC#17 Sep'21 | RPJV | 55248 | 2021-09-19 | Residence | 3 | 3 | MEP Work | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Housekeeping | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 2 | 4 | 120
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Housekeeping | opening |  |  |  | 0.4 | 0.8 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 4 | 8 | 240
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.7 | 0.21 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53195 | 2021-09-21 | Residence | 19 | 3 | Entry Door | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Telecom Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Telecom Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Telecom Room | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Telecom Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Telecom Room | cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Shaft | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 2 | 2 | 138
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | PPR pipe | 4" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | cable trunking |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | fire fighting pipe | 6" | [5 empty] | 1 |  | 3 | 3 | 0
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.6 | 0.18 | 1 | 220 | 1 | 1 | 220
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53196 | 2021-09-21 | Residence | 19 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Staircase | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | GSM cable | 0.5" | [5 empty] | 1 |  | 1 | 1 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 0.05 | 0.2 | 0.01 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | CHW pipe | 3" | [5 empty] | 1 |  | 1 | 1 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | CHW pipe | 3" | [5 empty] | 1 |  | 1 | 1 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 0.2 | 0.2 | 0.04 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Shaft | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 2 | 2 | 138
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Water Meter Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53197 | 2021-09-22 | Residence | 17 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | CHW pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 2 | 4 | 240
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | conduit pipe | 1" | [5 empty] | 2 |  | 15 | 30 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 0.55 | 1.2 | 0.66 | 2 | 480 | 1 | 2 | 960
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 5 | 10 | 0
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Shaft | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53198 | 2021-09-22 | Residence | 17 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Housekeeping | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Staircase | fire fighting pipe | 6" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Staircase | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Entry Door | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 1 | 60 | 1 | 1 | 60
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53199 | 2021-09-22 | Residence | 17 | 3 | FHC | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 1 | 45 | 2 | 2 | 90
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | duct | 0.15 | 0.25 | 0.0375 | 0.2 | 0.3 | 0.06 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Staircase | conduit pipe | 1" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | duct | 0.25 | 0.4 | 0.1 | 0.3 | 0.45 | 0.135 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | FHC | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | FHC | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | FHC | conduit pipe | 1" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | FHC | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 53200 | 2021-09-22 | Residence | 16 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Water Meter Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | fire fighting pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | PPR pipe | 4" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | PPR pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | duct | 0.25 | 0.25 | 0.0625 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | conduit pipe | 1" | [5 empty] | 2 |  | 12 | 24 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | opening |  |  |  | 0.6 | 1.7 | 1.02 | 2 | 400 | 1 | 2 | 816
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | CDP pipe | 2" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Lift Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 |  | 3 | 6 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | fire fighting pipe | 3" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | conduit pipe | 1" | [5 empty] | 2 |  | 12 | 24 | 0
PC#17 Sep'21 | RPJV | 55360 | 2021-09-23 | Residence | 16 | 3 | Entry Door | opening |  |  |  | 0.6 | 1.4 | 0.84 | 2 | 540 | 1 | 2 | 1080
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Entry door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | opening |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55361 | 2021-09-23 | Residence | 16 | 3 | 4 BED, Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Staircase | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Staircase | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | FHC | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Housekeeping | fire fighting pipe | 4" | [5 empty] | 2 |  | 1 | 2 | 0
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 |  | 2 | 4 | 0
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 |  | 4 | 8 | 0
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Housekeeping | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Shaft | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Wall | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#17 Sep'21 | RPJV | 55362 | 2021-09-23 | Residence | 16 | 3 | Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 01 | CDP pipe | 3" |  |  | 5" |  |  | 1 | 30 | 2 | 2 | 60
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 01, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 01, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 01, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 4 | 4 | 80
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 01, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 02, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 02, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 02, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 4 | 4 | 80
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 02, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 03, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 04, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 04, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 04 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 04 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 04 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 04 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 05 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 06, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 07, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 07, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 3 | 3 | 315
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 07, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55363 | 2021-09-25 | Hotel | 24 | 2 | Room 07, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 4 | 4 | 80
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 08 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 09, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 12, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 12, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 12, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 12, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 4 | 4 | 80
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 12, Shaft | CDP pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 14, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 14, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 14 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 14 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 14 | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 15, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 15, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 16, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 16, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 16, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 16, Shaft | CDP pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 16, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 17, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 17, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55364 | 2021-09-25 | Hotel | 24 | 2 | Room 17, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 18, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 1 | 1 | 105
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 1 | 105 | 2 | 2 | 210
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 2 | 2 | 90
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19, Shaft | CDP pipe (shaft) | 2" |  |  | 4" |  |  | 1 | 45 | 1 | 1 | 45
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 4 | 4 | 248
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19 | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 4 | 4 | 260
PC#17 Sep'21 | RPJV | 55365 | 2021-09-25 | Hotel | 24 | 2 | Room 19 | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | duct | 0.2 | 0.3 | 0.06 |  |  |  | 2 | 62 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | opening |  |  |  | 0.3 | 0.4 | 0.12 | 2 | 185 | 1 | 2 | 370
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | duct | 0.2 | 0.3 | 0.06 |  |  |  | 2 | 62 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | opening |  |  |  | 0.3 | 0.4 | 0.12 | 2 | 185 | 1 | 2 | 370
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | duct | 0.2 | 0.3 | 0.06 |  |  |  | 2 | 62 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | opening |  |  |  | 0.35 | 0.5 | 0.175 | 2 | 220 | 1 | 2 | 440
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | duct | 0.2 | 0.3 | 0.06 |  |  |  | 2 | 62 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55366 | 2021-10-13 | Hotel | 2 | 2 | Lobby Below | opening |  |  |  | 0.35 | 0.5 | 0.175 | 2 | 220 | 1 | 2 | 440
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | PVC pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | opening |  |  |  | 0.3 | 0.4 | 0.12 | 2 | 185 | 1 | 2 | 370
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | MEP | fire fighting pipe | 4" |  |  | 6" |  |  | 1 | 23 | 1 | 1 | 23
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | fire fighting pipe | 3" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | opening |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 115 | 1 | 2 | 230
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | PVC pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | FF Lobby | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Water Meter Room | CDP pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Water Meter Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | CDP pipe | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#18 Oct'21 | RPJV | 55367 | 2021-10-13 | Residence | 2 | 3 | Lift lobby | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Electrical Room | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Electrical Room | opening |  |  |  | 0.3 | 1 | 0.3 | 2 | 300 | 1 | 2 | 600
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | CDP pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 | 20 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | PPR pipe | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Housekeeping | opening |  |  |  | 0.4 | 1 | 0.4 | 2 | 375 | 1 | 2 | 750
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 11 | 22 | 396
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 4 | 8 | 224
PC#18 Oct'21 | RPJV | 55368 | 2021-10-14 | Residence | 2 | 3 | Wall | cable trunking |  |  |  | 0.4 | 0.5 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | PVC pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 | 20 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | PPR pipe | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Stair 08 | fire fighting pipe | 3" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Stair 08 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | CDP pipe | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Lift lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 2 | 185 | 1 | 2 | 370
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Water Meter Room | PPR pipe | 6" | [5 empty] | 2 | 125 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Water Meter Room | PPR pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Water Meter Room | PPR pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Water Meter Room | gas pipe | 3" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | fire fighting pipe | 1" |  |  | 3" |  |  | 1 | 16 | 1 | 1 | 16
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 1 | 30 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | CHW pipe | 2" | [5 empty] | 1 | 20 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | PVC pipe | 6" | [5 empty] | 1 | 125 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | conduit pipe | 1" | [5 empty] | 1 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | opening |  |  |  | 0.5 | 0.65 | 0.325 | 1 | 300 | 1 | 1 | 300
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | PVC pipe | 4" | [5 empty] | 1 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55369 | 2021-10-14 | Hotel | 16 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 1 | 115 | 1 | 1 | 115
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FF Lobby | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FF Lobby | conduit pipe | 1" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FF Lobby | conduit pipe | 1" |  |  | 3" |  |  | 2 | 18 | 2 | 4 | 72
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FF Lobby | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FF Lobby | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Stair 07 | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Stair 07 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | gas pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 11, Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 01 | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 1 | 1 | 49
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 1 | 1 | 205
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 1 | 1 | 49
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 1609 | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Room no. 1609 | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Corridor | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 2 | 62 | 2 | 4 | 248
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Corridor | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55370-1 | 2021-10-16 | Hotel | 16 | 2 | Corridor | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 13 | 26 | 468
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 13 | 26 | 468
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.2 | 0.6 | 0.12 | 0.25 | 0.65 | 0.1625 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.6 | 0.6 | 0.36 | 0.65 | 0.65 | 0.4225 | 2 | 110 | 3 | 6 | 660
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 2 | 4 | 188
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 2 | 4 | 188
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wet Area | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wet Area | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wet Area | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wet Area | duct | 0.15 | 0.15 | 0.0225 | 0.2 | 0.2 | 0.04 | 2 | 44 | 1 | 2 | 88
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wet Area | duct | 0.4 | 0.8 | 0.32 | 0.45 | 0.85 | 0.3825 | 2 | 100 | 3 | 6 | 600
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | duct | 0.4 | 0.6 | 0.24 | 0.46 | 0.66 | 0.3036 | 2 | 86 | 1 | 2 | 172
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | duct | 0.3 | 0.6 | 0.18 | 0.35 | 0.65 | 0.2275 | 2 | 86 | 1 | 2 | 172
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 11 | 22 | 396
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.4 | 0.8 | 0.32 | 0.45 | 0.85 | 0.3825 | 2 | 100 | 3 | 6 | 600
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 2 | 4 | 188
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.4 | 0.8 | 0.32 | 0.45 | 0.85 | 0.3825 | 2 | 100 | 3 | 6 | 600
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | duct | 0.3 | 0.6 | 0.18 | 0.35 | 0.65 | 0.2275 | 2 | 86 | 1 | 2 | 172
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 15 | 30 | 540
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 2 | 4 | 188
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.5 | 0.8 | 0.4 | 0.55 | 0.85 | 0.4675 | 2 | 110 | 1 | 2 | 220
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 2 | 86 | 4 | 8 | 688
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Corridor | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 36 | 72 | 1296
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 2 | 86 | 3 | 6 | 516
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 2 | 86 | 2 | 4 | 344
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.4 | 0.5 | 0.2 | 0.45 | 0.55 | 0.2475 | 2 | 86 | 2 | 4 | 344
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.6 | 0.6 | 0.36 | 0.65 | 0.65 | 0.4225 | 2 | 110 | 2 | 4 | 440
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 7 | 14 | 658
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 01 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | duct | 0.3 | 0.8 | 0.24 | 0.35 | 0.85 | 0.2975 | 2 | 86 | 1 | 2 | 172
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 22 | 44 | 792
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Treatment Room 02 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 3 | 6 | 414
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 2 | 62 | 4 | 8 | 496
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 2 | 4 | 188
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | fiber duct | 8" |  |  | 10" |  |  | 2 | 44 | 4 | 8 | 352
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 5 | 10 | 690
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.4 | 1 | 0.4 | 0.45 | 1.05 | 0.4725 | 2 | 110 | 1 | 2 | 220
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | duct | 0.4 | 0.8 | 0.32 | 0.45 | 0.85 | 0.3825 | 2 | 100 | 1 | 2 | 200
PC#18 Oct'21 | RPJV | 55372-5 | 2021-10-16 | Hotel | 28 | 2 | Men Change Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 2 | 62 | 1 | 2 | 124
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.4 | 0.6 | 0.24 | 0.45 | 0.65 | 0.2925 | 2 | 86 | 2 | 4 | 344
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 3 | 6 | 372
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.25 | 0.4 | 0.1 | 0.3 | 0.45 | 0.135 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 4 | 8 | 376
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | fiber duct | 8" |  |  | 10" |  |  | 2 | 44 | 4 | 8 | 352
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 2 | 69 | 2 | 4 | 276
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.8 | 0.8 | 0.64 | 0.85 | 0.85 | 0.7225 | 2 | 139 | 2 | 4 | 556
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 2 | 69 | 1 | 2 | 138
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55376 | 2021-10-17 | Hotel | 28 | 2 | Women Change Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 01 | PVC pipe | 4" | [5 empty] | 1 | 65 | 5 | 5 | 325
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 01 | PVC pipe | 2" | [5 empty] | 1 | 28 | 4 | 4 | 112
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 02 | PVC pipe | 4" | [5 empty] | 1 | 65 | 6 | 6 | 390
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 02 | PVC pipe | 2" | [5 empty] | 1 | 28 | 4 | 4 | 112
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 03 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 03 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 04 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 04 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 05 | PVC pipe | 4" | [5 empty] | 1 | 65 | 5 | 5 | 325
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 05 | PVC pipe | 2" | [5 empty] | 1 | 28 | 6 | 6 | 168
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 06 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 06 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 07 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 07 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 09 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 09 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 10 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 10 | PVC pipe | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 11 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 11 | PVC pipe | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 12 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 12 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 13 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 13 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 14 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 14 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 15 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55377 | 2021-10-17 | Hotel | 26 | 2 | Room no. 15 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 01 | PVC pipe | 4" | [5 empty] | 1 | 65 | 6 | 6 | 390
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 01 | PVC pipe | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 02 | PVC pipe | 4" | [5 empty] | 1 | 65 | 6 | 6 | 390
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 02 | PVC pipe | 2" | [5 empty] | 1 | 28 | 4 | 4 | 112
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 03 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 03 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 04 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 04 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 05 | PVC pipe | 4" | [5 empty] | 1 | 65 | 5 | 5 | 325
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 05 | PVC pipe | 2" | [5 empty] | 1 | 28 | 4 | 4 | 112
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 06 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 06 | PVC pipe | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 07 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 07 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 08 | PVC pipe | 4" | [5 empty] | 1 | 65 | 5 | 5 | 325
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 08 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 09 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 09 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 10 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 10 | PVC pipe | 2" | [5 empty] | 1 | 28 | 2 | 2 | 56
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 11 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 11 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 12 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 12 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 13 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 13 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 14 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 14 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 15 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55378-9 | 2021-10-17 | Hotel | 27 | 2 | Room no. 15 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55380 | 2021-10-17 | Hotel | 24 & 25 | 2 | Room no. 10 | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#18 Oct'21 | RPJV | 55380 | 2021-10-17 | Hotel | 24 & 25 | 2 | Room no. 10 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55380 | 2021-10-17 | Hotel | 24 & 25 | 2 | Room no. 10 | PVC pipe | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#18 Oct'21 | RPJV | 55380 | 2021-10-17 | Hotel | 24 & 25 | 2 | Room no. 11 | PVC pipe | 4" | [5 empty] | 1 | 65 | 4 | 4 | 260
PC#18 Oct'21 | RPJV | 55380 | 2021-10-17 | Hotel | 24 & 25 | 2 | Room no. 11 | PVC pipe | 2" | [5 empty] | 1 | 28 | 3 | 3 | 84
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 3 | 6 | 168
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | cable trunking |  |  |  | 0.14 | 0.14 | 0.0196 | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 7 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 9 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 5 | 10 | 650
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 9 | 2 | Rework | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 3 | 6 | 750
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 9 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 9 | 2 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 3 | 6 | 96
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 9 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 3 | 3 | 186
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 10 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 10 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 10 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 10 | 2 | Rework | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 1 | 69 | 1 | 1 | 69
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 11 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 11 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 12 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 12 | 2 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55381 | 2021-10-17 | Residence | 12 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 13 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 13 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 14 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 14 | 2 | Rework | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 14 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 15 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 16 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 16 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 16 | 2 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 17 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 4 | 8 | 520
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 17 | 2 | Rework | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 17 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 17 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 18 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 4 | 8 | 520
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 18 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 18 | 2 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 18 | 2 | Rework | gas pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55382 | 2021-10-18 | Residence | 18 | 2 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 19 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 8 | 16 | 1040
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 19 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 19 | 2 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 20 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 7 | 14 | 910
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 20 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 6 | 12 | 336
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 21 | 2 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 8 | 16 | 1040
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 21 | 2 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 21 | 2 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 21 | 2 | Rework | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 3 | 3 | 186
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 18 | 2 | Rework | gas pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 19 | 2 | Rework | gas pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 20 | 2 | Rework | gas pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 21 | 2 | Rework | gas pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55383 | 2021-10-18 | Residence | 22 | 2 | Rework | gas pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 22 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 22 | 3 | Rework | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 22 | 3 | Rework | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 21 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 21 | 3 | Rework | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 21 | 3 | Rework | cable tray |  |  |  | 0.1 | 0.1 | 0.01 | 1 | 60 | 1 | 1 | 60
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 20 | 3 | Rework | conduit pipe | 1" | [5 empty] | 1 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 20 | 3 | Rework | GSM cable | 0.5" | [5 empty] | 1 | 28 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 20 | 3 | Rework | opening |  |  |  | 0.12 | 0.15 | 0.018 | 1 | 60 | 1 | 1 | 60
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 20 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 20 | 3 | Rework | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 1 | 1 | 23
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 19 | 3 | Rework | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 1 | 60 | 1 | 1 | 60
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 19 | 3 | Rework | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 19 | 3 | Rework | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 19 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 19 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 19 | 3 | Rework | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 18 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 11 | 11 | 198
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 17 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 8 | 8 | 144
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 17 | 3 | Rework | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | PPR pipe | 4" | [5 empty] | 1 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | PPR pipe | 3" | [5 empty] | 1 | 30 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | conduit pipe | 1" | [5 empty] | 1 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | opening |  |  |  | 0.24 | 0.5 | 0.12 | 1 | 185 | 1 | 1 | 185
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90
PC#18 Oct'21 | RPJV | 55384 | 2021-10-19 | Residence | 15 | 3 | Rework | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 18 | 1 | 1 | 18
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | CHW pipe | 4" | [5 empty] | 2 | 29 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | opening |  |  |  | 0.25 | 0.45 | 0.1125 | 2 | 185 | 1 | 2 | 370
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | GSM cable | 0.5" |  |  | 2" |  |  | 1 | 28 | 1 | 1 | 28
PC#18 Oct'21 | RPJV | 55385 | 2021-10-19 | Residence | 7 | 3 | Rework | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Slab Work | PVC pipe | 6" | [5 empty] | 2 | 125 | 2 | 4 | 500
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Slab Work | PVC pipe | 4" | [5 empty] | 2 | 65 | 1 | 2 | 130
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Slab Work | gas pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Slab Work | opening |  |  |  | 8" |  |  | 2 | 60 | 1 | 2 | 120
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Slab Work | PVC pipe | 6" | [5 empty] | 2 | 125 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Slab Work | PVC pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 18 | 3 | Wall | opening |  |  |  | 0.4 | 0.82 | 0.328 | 2 | 300 | 1 | 2 | 600
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 19 | 3 | Wall | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 2 | 2 | 250
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 19 | 3 | Wall | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65
PC#18 Oct'21 | RPJV | 55386 | 2021-10-20 | Residence | 19 | 3 | Wall | gas pipe | 2" |  |  | 4" |  |  | 1 | 16 | 1 | 1 | 16
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Entry Door | cable tray |  |  |  | 0.08 | 0.24 | 0.0192 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 3 | 3 | 147
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Staircase | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED - Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | opening |  |  |  | 8" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | PPR pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | PPR pipe | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | 4BED | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 5 | 10 | 180
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | CDP pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 4 | 8 | 224
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 | 44 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Lift Lobby | opening |  |  |  | 0.65 | 1.25 | 0.8125 | 2 | 540 | 1 | 2 | 1080
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | fire fighting pipe | 4" | [5 empty] | 2 | 23 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 | 20 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Housekeeping | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | FHC | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#19 Nov'21 | RPJV | 55387-8 | 2021-11-07 | Residence | 15 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Entry Door | GSM cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 4 | 8 | 224
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Wall | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Wall | opening |  |  |  | 0.05 | 0.4 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Wall | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Wall | cable tray |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 2 | 4 | 880
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55389 | 2021-11-08 | Residence | 15 | 3 | 3BED - Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55400 | 2021-11-14 | Residence | GF | 3 | ETS Room, Smoke Seal | CHW pipe | 14" | [5 empty] | 1 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55400 | 2021-11-14 | Residence | GF | 3 | ETS Room, Smoke Seal | opening |  |  |  | 0.92 | 3.4 | 3.128 | 1 | 275 | 1 | 1 | 860.2
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 11 | 3 | Electrical Room | CHW pipe | 14" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 11 | 3 | Electrical Room | opening |  |  |  | 0.61 | 1.07 | 0.6527 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 12 | 3 | Electrical Room | CHW pipe | 14" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 12 | 3 | Electrical Room | opening |  |  |  | 0.61 | 1.07 | 0.6527 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 13 | 3 | Electrical Room | CHW pipe | 14" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 13 | 3 | Electrical Room | opening |  |  |  | 0.61 | 1.07 | 0.6527 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 14 | 3 | Electrical Room | CHW pipe | 14" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 14 | 3 | Electrical Room | opening |  |  |  | 0.61 | 1.07 | 0.6527 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 15 | 3 | Electrical Room | CHW pipe | 14" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 15 | 3 | Electrical Room | opening |  |  |  | 0.61 | 1.07 | 0.6527 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 16 | 3 | Electrical Room | CHW pipe | 14" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55405 | 2021-11-16 | Residence | 16 | 3 | Electrical Room | opening |  |  |  | 0.61 | 1.07 | 0.6527 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable tray |  |  |  | 0.27 | 0.7 | 0.189 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | duct | 0.45 | 0.45 | 0.2025 |  |  |  | 2 | 69 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.55 | 0.67 | 0.3685 | 2 | 375 | 1 | 2 | 750
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | duct | 0.45 | 0.45 | 0.2025 |  |  |  | 2 | 69 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.55 | 0.67 | 0.3685 | 2 | 375 | 1 | 2 | 750
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.3 | 0.75 | 0.225 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable tray |  |  |  | 0.4 | 1.2 | 0.48 | 2 | 375 | 1 | 2 | 750
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | bus bar | 0.05 | 0.15 | 0.0075 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.7 | 1.07 | 0.749 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable trunking |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable tray |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable tray |  |  |  | 0.15 | 0.36 | 0.054 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 13 | 26 | 468
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.65 | 2.2 | 1.43 | 2 | 400 | 1 | 2 | 1144
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.27 | 1.6 | 0.432 | 2 | 375 | 1 | 2 | 750
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.26 | 1 | 0.26 | 2 | 300 | 1 | 2 | 600
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 4" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | blank opening |  |  |  | 4" |  |  | 2 | 60 | 2 | 4 | 240
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | duct | 0.45 | 0.45 | 0.2025 |  |  |  | 2 | 69 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room | opening |  |  |  | 0.55 | 1.2 | 0.66 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable tray |  |  |  | 0.27 | 0.7 | 0.189 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable trunking |  |  |  | 0.28 | 0.4 | 0.112 | 2 | 185 | 1 | 2 | 370
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | duct | 0.45 | 0.45 | 0.2025 |  |  |  | 2 | 69 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.8 | 1.3 | 1.04 | 2 | 400 | 1 | 2 | 832
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.8 | 2.3 | 1.84 | 2 | 400 | 1 | 2 | 1472
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.8 | 4.2 | 3.36 | 2 | 275 | 1 | 2 | 1848
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 2" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.25 | 2.7 | 0.675 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | bus bar |  |  |  | 0.6 | 0.7 | 0.42 | 2 | 375 | 2 | 4 | 1500
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | bus bar |  |  |  | 0.45 | 0.55 | 0.2475 | 2 | 220 | 2 | 4 | 880
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.6 | 2 | 1.2 | 2 | 400 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | duct | 0.45 | 0.45 | 0.2025 |  |  |  | 2 | 69 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.55 | 1.2 | 0.66 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 16 | 32 | 576
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | cable | 1" | [5 empty] | 2 | 28 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | duct | 0.75 | 1.3 | 0.975 |  |  |  | 2 | 155 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55390-1 | 2021-11-09 | Hotel | GF | 2 | LV Room 02 | opening |  |  |  | 0.85 | 2.2 | 1.87 | 2 | 400 | 1 | 2 | 1496
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 10 | 10 | 180
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 01, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 02 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 02 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 02 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 02, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 02, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 02, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 19 | 38 | 684
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 03 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 10 | 10 | 180
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 04, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 14 | 14 | 252
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05, Shaft | CDP pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 05, Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 06 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 10 | 10 | 180
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 07, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 09, Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 8 | 8 | 144
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55392-4 | 2021-11-10 | Hotel | 26 | 2 | Room no. 10, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 11 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 11 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 11 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 11 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 10 | 10 | 180
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 11, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 12, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 13 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 13 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 13 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 13 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 8 | 8 | 144
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 13, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 13, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 12 | 12 | 216
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14 | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 14, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 15 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 15 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 15 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 11 | 11 | 198
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 15, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 15, Shaft | PVC pipe (shaft) | 2" |  |  | 3" |  |  | 2 | 45 | 2 | 2 | 90
PC#19 Nov'21 | RPJV | 55395-6 | 2021-11-11 | Hotel | 26 | 2 | Room no. 15, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | duct | 0.3 | 0.3 | 0.09 | 0.36 | 0.36 | 0.1296 | 1 | 69 | 5 | 5 | 345
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 30 | 1 | 1 | 30
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | fire fighting pipe | 1" |  |  | 2" |  |  | 1 | 16 | 1 | 1 | 16
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 1 | 1 | 125
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | metal pipe | 22" | [5 empty] | 2 | 141 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Garbage Room | opening |  |  |  | 1 | 1 | 1 | 2 | 540 | 1 | 2 | 1080
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Telecom Room | cable tray |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Telecom Room | cable tray |  |  |  | 0.2 | 0.4 | 0.08 | 1 | 115 | 1 | 1 | 115
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Telecom Room | cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 1 | 115 | 1 | 1 | 115
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Telecom Room | cable tray |  |  |  | 0.25 | 1.2 | 0.3 | 1 | 300 | 2 | 2 | 600
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Telecom Room | cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 1 | 115 | 1 | 1 | 115
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Telecom Room | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | GSM Room | cable tray |  |  |  | 0.2 | 0.7 | 0.14 | 1 | 185 | 2 | 2 | 370
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | GSM Room | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | GSM Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | GSM Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | GSM Room | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | GSM Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | opening |  |  |  | 0.5 | 0.9 | 0.45 | 2 | 375 | 1 | 2 | 750
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Shaft | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Shaft | PVC pipe (shaft) | 4" | [5 empty] | 2 | 105 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Shaft | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Shaft | opening |  |  |  | 0.35 | 1.7 | 0.595 | 2 | 410 | 1 | 2 | 820
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | PVC pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | opening |  |  |  | 0.3 | 0.86 | 0.258 | 2 | 300 | 1 | 2 | 600
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | cable trunking | 0.15 | 0.15 | 0.0225 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | opening |  |  |  | 0.68 | 1 | 0.68 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | opening |  |  |  | 0.56 | 2.4 | 1.344 | 2 | 400 | 1 | 2 | 1075.2
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | blank opening |  |  |  | 0.4 | 1.02 | 0.408 | 2 | 375 | 1 | 2 | 750
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | PVC pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55397-8 | 2021-11-13 | Residence | B1 | 3 | Grease Trap Room | opening |  |  |  | 0.53 | 0.54 | 0.2862 | 2 | 300 | 1 | 2 | 600
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | PVC pipe | 4" | [5 empty] | 2 | 65 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | PVC pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.3 | 1 | 0.3 | 2 | 300 | 1 | 2 | 600
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | cable tray |  |  |  | 0.25 | 0.75 | 0.1875 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | cable tray |  |  |  | 0.25 | 1 | 0.25 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | cable tray |  |  |  | 0.25 | 1 | 0.25 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | cable tray |  |  |  | 0.15 | 0.4 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55399 | 2021-11-14 | Hotel | B1 | 2 | MEP Work | cable tray |  |  |  | 0.2 | 1.65 | 0.33 | 2 | 300 | 3 | 6 | 1800
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CHW Pumps | CHW pipe | 8" | [5 empty] | 2 | 47 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CHW Pumps | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CHW Pumps | CHW pipe | 8" | [5 empty] | 2 | 47 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CHW Pumps | opening |  |  |  | 0.4 | 0.4 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CHW Pumps | cable tray |  |  |  | 0.15 | 0.3 | 0.045 | 1 | 60 | 1 | 1 | 60
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Cabinet | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Cabinet | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Cabinet | opening |  |  |  | 0.35 | 0.6 | 0.21 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Cabinet | cable tray |  |  |  | 0.15 | 0.4 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Plenum Room | duct | 0.74 | 1.74 | 1.2876 |  |  |  | 1 | 155 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Plenum Room | opening |  |  |  | 0.85 | 2 | 1.7 | 1 | 400 | 1 | 1 | 680
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Plenum Room | duct | 0.74 | 1.74 | 1.2876 |  |  |  | 1 | 155 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Plenum Room | opening |  |  |  | 0.85 | 2 | 1.7 | 1 | 400 | 1 | 1 | 680
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | AHU Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | AHU Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CSF Room | duct | 0.75 | 1.75 | 1.3125 | 0.8 | 1.8 | 1.44 | 1 | 120 | 4 | 4 | 691.2
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CSF Room | cable tray |  |  |  | 0.1 | 0.16 | 0.016 | 1 | 60 | 1 | 1 | 60
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CSF Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CSF Room | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CSF Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | PPR pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | opening |  |  |  | 10" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | PPR pipe | 3" | [5 empty] | 2 | 30 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | opening |  |  |  | 10" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | PPR pipe | 8" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | opening |  |  |  | 12" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | PPR pipe | 8" | [5 empty] | 2 | 170 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | opening |  |  |  | 12" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | opening |  |  |  | 0.2 | 0.9 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Pump Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Pump Room | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Pump Room | metal pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Pump Room | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | opening |  |  |  | 0.15 | 0.5 | 0.075 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | cable tray |  |  |  | 0.15 | 0.4 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 2 | 4 | 112
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Entry Door | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CEF - Shaft | duct | 0.65 | 0.8 | 0.52 |  |  |  | 2 | 119 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CEF - Shaft | opening |  |  |  | 0.8 | 0.85 | 0.68 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CEF - Shaft | duct | 0.65 | 0.8 | 0.52 |  |  |  | 2 | 119 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | CEF - Shaft | opening |  |  |  | 0.8 | 0.85 | 0.68 | 2 | 480 | 1 | 2 | 960
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Staircase | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Staircase | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Staircase | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 2 | 4 | 112
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Staircase | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Water Meter Room | PPR pipe | 8" |  |  | 10" |  |  | 2 | 170 | 1 | 2 | 340
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Water Meter Room | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 2" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Water Meter Room | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Lobby | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Lobby | fire fighting pipe | 1" | [5 empty] | 2 | 16 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | FF Lobby | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Room Service | CHW pipe | 6" |  |  | 8" |  |  | 2 | 35 | 2 | 4 | 140
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 7 | 7 | 126
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Shaft | GSM cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 2 | 2 | 98
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Engineering | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Engineering | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 14 | 28 | 504
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Engineering | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Engineering | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 2 | 4 | 112
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Engineering | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | cable trunking |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 2 | 4 | 460
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.4 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 60 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | conduit pipe | 1" | [5 empty] | 2 | 18 | 0 | 0 | 0
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Electrical Room | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Parking Total | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 43 | 86 | 1548
PC#19 Nov'21 | RPJV | 55402-4 | 2021-11-15 | Residence | B2 | 3 | Parking Total | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 20 | 40 | 1120
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PVC pipe | 4" | [5 empty] | 2 | 65 | 1 | 2 | 130
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.2 | 0.25 | 0.05 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | CHW pipe | 14" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | conduit pipe | 1" | [5 empty] | 0 | 18 | 4 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.8 | 1.7 | 1.36 | 1 | 400 | 1 | 1.36 | 544
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PVC pipe | 6" | [5 empty] | 0 | 125 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | CHW pipe | 14" | [5 empty] | 0 | 170 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.9 | 1.1 | 0.99 | 2 | 540 | 1 | 2 | 1080
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | CHW pipe | 14" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 1 | 1.2 | 1.2 | 2 | 400 | 1 | 2.4 | 960
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | CHW pipe | 6" |  |  | 8" |  |  | 2 | 35 | 2 | 4 | 140
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | PPR pipe | 6" | [5 empty] | 0 | 125 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | opening |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55413 | 2021-12-15 | Hotel | B1 | 2 | Service Support Area | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | opening |  |  |  | 1.74 | 1.75 | 3.045 | 1 | 275 | 1 | 3.045 | 837.375
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | duct | 1.58 | 1.58 | 2.4964 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | opening |  |  |  | 1.62 | 1.62 | 2.6244 | 1 | 325 | 1 | 2.6244 | 852.93
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | duct | 1.58 | 1.58 | 2.4964 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | opening |  |  |  | 1.64 | 1.65 | 2.706 | 1 | 325 | 1 | 2.706 | 879.45
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | opening |  |  |  | 1.63 | 1.65 | 2.6895 | 1 | 325 | 1 | 2.6895 | 874.0875
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 2 | CEF Room | opening |  |  |  | 1.74 | 1.74 | 3.0276 | 1 | 275 | 1 | 3.0276 | 832.59
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | opening |  |  |  | 1.64 | 1.86 | 3.0504 | 1 | 275 | 1 | 3.0504 | 838.86
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | opening |  |  |  | 1.73 | 1.86 | 3.2178 | 1 | 275 | 1 | 3.2178 | 884.895
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | opening |  |  |  | 1.62 | 1.87 | 3.0294 | 1 | 275 | 1 | 3.0294 | 833.085
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | opening |  |  |  | 1.64 | 1.63 | 2.6732 | 1 | 325 | 1 | 2.6732 | 868.79
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | opening |  |  |  | 1.63 | 1.63 | 2.6569 | 1 | 325 | 1 | 2.6569 | 863.4925
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | duct | 1.6 | 1.6 | 2.56 |  |  |  | 0 | 155 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55414 | 2021-12-15 | Hotel | B2 | 3 | CEF Room | opening |  |  |  | 1.63 | 1.63 | 2.6569 | 1 | 325 | 1 | 2.6569 | 863.4925
PC#20 Dec'21 | RPJV | 55415 | 2021-12-15 | Hotel | B1 | 2 | MEP FM Room | blank opening |  |  |  | 0.56 | 2.5 | 1.4 | 2 | 400 | 1 | 2.8 | 1120
PC#20 Dec'21 | RPJV | 55415 | 2021-12-15 | Hotel | B1 | 2 | MEP FM Room | blank opening |  |  |  | 0.4 | 0.5 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55415 | 2021-12-15 | Hotel | B2 | 3 | Housekeeping Lobby | blank opening |  |  |  | 0.83 | 0.86 | 0.7138 | 2 | 480 | 1 | 2 | 960
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 22 | 2 | Room no. 06, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 22 | 2 | Room no. 06, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 22 | 2 | Room no. 06, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 22 | 2 | Room no. 06, Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 22 | 2 | Room no. 06, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 23 | 2 | Room no. 06, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 23 | 2 | Room no. 06, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 23 | 2 | Room no. 06, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 23 | 2 | Room no. 06, Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#20 Dec'21 | RPJV | 55410 | 2021-12-09 | Hotel | 23 | 2 | Room no. 06, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 22 | 44 | 792
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 10 | 20 | 600
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 4 | 8 | 496
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 6 | 12 | 564
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | duct | 0.4 | 0.8 | 0.32 | 0.45 | 0.85 | 0.3825 | 2 | 100 | 2 | 4 | 400
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 16 | 32 | 576
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 2 | 4 | 248
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | duct | 0.3 | 0.6 | 0.18 | 0.35 | 0.65 | 0.2275 | 2 | 86 | 4 | 8 | 688
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | CHW pipe | 8" |  |  | 10" |  |  | 2 | 47 | 2 | 4 | 188
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Shaft | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 1 | 69 | 4 | 4 | 276
PC#20 Dec'21 | RPJV | 55411 | 2021-12-14 | Hotel | 28 | 2 | Room, Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 1 | 1 | 49
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 1 | 69 | 1 | 1 | 69
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | gas pipe | 0.5" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | cable tray |  |  |  | 0.1 | 0.25 | 0.025 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | HDPE pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | opening |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | opening |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | cable tray |  |  |  | 0.1 | 0.25 | 0.025 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 12 | 24 | 432
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 6" | [5 empty] | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | conduit pipe | 1" | [5 empty] | 0 | 20 | 7 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Penthouse, Wall | duct | 0.1 | 0.2 | 0.02 | 0.15 | 0.25 | 0.0375 | 1 | 44 | 1 | 1 | 44
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | FHC | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | FHC | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 2 | 62 | 1 | 2 | 124
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | conduit pipe | 1" | [5 empty] | 0 | 20 | 10 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | PPR pipe | 1" | [5 empty] | 0 | 28 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | fire fighting pipe | 6" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | opening |  |  |  | 0.85 | 1.1 | 0.935 | 2 | 540 | 1 | 2 | 1080
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Electrical Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Electrical Room | opening |  |  |  | 0.2 | 0.5 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Lift Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Lift Lobby | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Lift Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 0 | 20 | 9 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Lift Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 2 | 62 | 1 | 2 | 124
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | PPR pipe | 6" | [5 empty] | 0 | 125 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | PPR pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | fire fighting pipe | 6" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | conduit pipe | 1" | [5 empty] | 0 | 20 | 13 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | opening |  |  |  | 1.1 | 1.3 | 1.43 | 2 | 400 | 1 | 2.86 | 1144
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | PPR pipe | 4" | [5 empty] | 0 | 65 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | PPR pipe | 2" | [5 empty] | 0 | 28 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | CDP pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | conduit pipe | 1" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Entry Door, Corridor | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 3 | 3 | 135
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 2 | 2 | 90
PC#20 Dec'21 | RPJV | 55419-22 | 2021-12-19 | Residence | 25 | 3 | Staircase | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 4 | 8 | 184
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 2 | 2 | 124
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 1 | 69 | 1 | 1 | 69
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | gas pipe | 0.5" |  |  | 1" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | gas pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | GSM cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | cable tray |  |  |  | 0.1 | 0.15 | 0.015 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Shaft | opening |  |  |  | 0.2 | 0.8 | 0.16 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | conduit pipe | 1" | [5 empty] | 0 | 20 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | conduit pipe | 1" | [5 empty] | 0 | 20 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | opening |  |  |  | 0.26 | 0.3 | 0.078 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Housekeeping | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Housekeeping | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 0 | 20 | 8 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Housekeeping | opening |  |  |  | 0.35 | 0.9 | 0.315 | 2 | 300 | 1 | 2 | 600
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 2 | 2 | 98
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 2 | 46
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Penthouse, Shaft | duct | 0.15 | 0.2 | 0.03 | 0.2 | 0.25 | 0.05 | 1 | 44 | 1 | 1 | 44
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 | 0.28 | 0.38 | 0.1064 | 2 | 69 | 1 | 2 | 138
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | opening |  |  |  | 0.5 | 0.5 | 0.25 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | cable tray |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | cable tray |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 16 | 32 | 576
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | CDP pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 3 | 6 | 108
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 0 | 20 | 4 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Lift Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Electrical Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 0 | 60 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | opening |  |  |  | 0.4 | 0.8 | 0.32 | 2 | 300 | 1 | 2 | 600
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | CDP pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | PPR pipe | 4" | [5 empty] | 0 | 65 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55423-25 | 2021-12-20 | Residence | 24 | 3 | Corridor, Entry Door | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Corridor, Entry Door | cable tray |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Corridor, Entry Door | cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Corridor, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Corridor, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 14 | 28 | 504
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Corridor, Entry Door | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Water Meter Room | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 0 | 28 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Water Meter Room | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Lobby | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Shaft | PPR pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 5 | 5 | 225
PC#20 Dec'21 | RPJV | 55426 | 2021-12-21 | Residence | 24 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 10 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 10 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 11 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 11 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 12 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 12 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 13 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 13 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 14 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 14 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 15 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 15 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 17 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 17 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 18 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 18 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 19 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 19 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 20 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 20 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 21 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 21 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 22 | 3 | Corridor, Slab opening | CHW pipe | 12" | [5 empty] | 0 | 170 | 2 | 0 | 0
PC#20 Dec'21 | RPJV | 55427 | 2021-12-23 | Residence | 22 | 3 | Corridor, Slab opening | opening |  |  |  | 0.6 | 1 | 0.6 | 2 | 410 | 1 | 2 | 820
PC#21 Jan'22 | RPJV | 55428 | 2022-01-13 | Hotel | 4 | 2 | Slab Work | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 7 | 7 | 455
PC#21 Jan'22 | RPJV | 55428 | 2022-01-13 | Hotel | 4 | 2 | Slab Work | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 23 | 23 | 644
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 6" | [5 empty] | 0 | 125 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 6" | [5 empty] | 0 | 125 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 6" | [5 empty] | 0 | 125 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | duct | 0.5 | 0.5 | 0.25 |  |  |  | 0 | 86 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | duct | 0.4 | 0.4 | 0.16 |  |  |  | 0 | 69 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55429 | 2022-01-13 | Residence | 6 | 3 | Slab Work | opening |  |  |  | 0.86 | 2.26 | 1.9436 | 2 | 400 | 1 | 3.8872 | 1554.88
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 1 | 69 | 1 | 1 | 69
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.25 | 0.02 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | insulated metal pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | cable tray |  |  |  | 0.12 | 0.18 | 0.0216 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | cable tray |  |  |  | 0.1 | 0.28 | 0.028 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | conduit pipe | 1" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FTR Room | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Housekeeping | fire fighting pipe | 5" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Housekeeping | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Housekeeping | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 0 | 20 | 9 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Housekeeping | opening |  |  |  | 0.35 | 0.9 | 0.315 | 2 | 300 | 1 | 2 | 600
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | fire fighting pipe | 5" |  |  | 7" |  |  | 2 | 30 | 1 | 2 | 60
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 2 | 2 | 98
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 2 | 46
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 2 | 2 | 90
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | duct | 0.15 | 0.2 | 0.03 | 0.2 | 0.25 | 0.05 | 1 | 44 | 1 | 1 | 44
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Wall | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Electrical Room | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 4 | 8 | 224
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | opening |  |  |  | 0.4 | 0.9 | 0.36 | 2 | 375 | 1 | 2 | 750
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | PPR pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | fire fighting pipe | 3" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | conduit pipe | 1" | [5 empty] | 0 | 20 | 17 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | opening |  |  |  | 0.9 | 1.2 | 1.08 | 2 | 400 | 1 | 2.16 | 864
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 0 | 20 | 7 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 0 | 115 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 5 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Lift Lobby | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | CDP pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | opening |  |  |  | 0.4 | 0.9 | 0.36 | 2 | 375 | 1 | 2 | 750
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | PPR pipe | 3" | [5 empty] | 0 | 30 | 3 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | CHW pipe | 4" | [5 empty] | 0 | 29 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | PPR pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | fire fighting pipe | 2" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | conduit pipe | 1" | [5 empty] | 0 | 20 | 9 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | opening |  |  |  | 0.8 | 1.45 | 1.16 | 2 | 400 | 1 | 2.32 | 928
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 0 | 30 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 0 | 28 | 4 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 0 | 18 | 3 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Water Meter Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FF Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FF Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FF Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | insulated metal pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | conduit pipe | 1" | [5 empty] | 0 | 18 | 3 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | opening |  |  |  | 0.5 | 0.6 | 0.3 | 2 | 300 | 1 | 2 | 600
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Corridor, Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 2 | 2 | 90
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Shaft | insulated metal pipe | 2" |  |  | 4" |  |  | 2 | 20 | 5 | 10 | 200
PC#21 Jan'22 | RPJV | 55438-41 | 2022-01-20 | Residence | 26 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | gas pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | cable tray |  |  |  | 0.1 | 0.26 | 0.026 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | cable tray |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 4 | 4 | 420
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Wall | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Wall | cable tray |  |  |  | 0.2 | 0.26 | 0.052 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 12 | 24 | 432
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FTR Room | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FTR Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FTR Room | conduit pipe | 1" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FTR Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FTR Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FTR Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Housekeeping | fire fighting pipe | 3" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Housekeeping | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Housekeeping | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 0 | 20 | 6 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Housekeeping | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 2 | 4 | 72
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 2 | 2 | 98
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 2 | 46
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | duct | 0.15 | 0.2 | 0.03 | 0.2 | 0.25 | 0.05 | 1 | 44 | 1 | 1 | 44
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 3 | 3 | 147
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 0.4 | 1 | 0.4 | 2 | 375 | 1 | 2 | 750
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 1.15 | 1.25 | 1.4375 | 2 | 400 | 1 | 2.875 | 1150
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Electrical Room | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 6 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 3 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | CDP pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 10 | 20 | 360
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 0 | 28 | 3 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Water Meter Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | duct | 0.2 | 0.3 | 0.06 |  |  |  | 0 | 62 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 0.28 | 0.36 | 0.1008 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | fire fighting pipe | 3" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | insulated metal pipe | 2" | [5 empty] | 0 | 20 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | conduit pipe | 1" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | insulated metal pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | opening |  |  |  | 0.4 | 0.5 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Corridor, Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FF Lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FF Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FF Lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FF Lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Shaft | insulated metal pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160
PC#21 Jan'22 | RPJV | 55442-5 | 2022-01-21 | Residence | 27 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 4 | 8 | 144
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.5 | 0.8 | 0.4 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.67 | 0.95 | 0.6365 | 1 | 410 | 1 | 1 | 410
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.4 | 0.9 | 0.36 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.43 | 0.75 | 0.3225 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.5 | 1.85 | 0.925 | 1 | 540 | 1 | 1 | 540
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.47 | 0.74 | 0.3478 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.37 | 0.88 | 0.3256 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.58 | 1.9 | 1.102 | 2 | 400 | 1 | 2.204 | 881.6
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.45 | 0.75 | 0.3375 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.37 | 0.83 | 0.3071 |  |  |  | 0 | 100 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.5 | 1.72 | 0.86 | 2 | 540 | 1 | 2 | 1080
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CDP pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 4 | 8 | 224
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 11 | 22 | 396
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 7 | 14 | 392
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | GSM cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 2 | 4 | 112
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 7 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.15 | 0.15 | 0.0225 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 4 | 0 | 0
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | opening |  |  |  | 0.08 | 0.15 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 2 | 4 | 112
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#22 Feb'22 | RPJV | 55449-50 | 2022-02-10 | Hotel | B1 | 2 | MEP Work | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 3 | 6 | 168
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.1 | 0.36 | 0.036 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.08 | 0.26 | 0.0208 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | PPR pipe | 2" | [5 empty] | 0 | 28 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.38 | 0.39 | 0.1482 | 2 | 185 | 1 | 2 | 370
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 4 | 8 | 224
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 3 | 6 | 168
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | duct | 0.1 | 0.2 | 0.02 | 0.14 | 0.24 | 0.0336 | 2 | 44 | 1 | 2 | 88
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | PPR pipe | 2" | [5 empty] | 0 | 28 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.15 | 0.3 | 0.045 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | duct | 0.2 | 0.4 | 0.08 |  |  |  | 0 | 62 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | duct | 0.3 | 0.4 | 0.12 | 0.36 | 0.46 | 0.1656 | 2 | 69 | 1 | 2 | 138
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 2 | 62 | 1 | 2 | 124
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | metal pipe | 3" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 3 | 6 | 372
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 19 | 38 | 684
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120
PC#22 Feb'22 | RPJV | 60301 | 2022-02-15 | Hotel | B2 | 2 | MEP Work | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 3 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | conduit pipe | 1" | [5 empty] | 0 | 20 | 8 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | GSM cable | 0.5" | [5 empty] | 0 |  | 7 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | opening |  |  |  | 0.65 | 0.9 | 0.585 | 2 | 410 | 1 | 2 | 820
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | CDP pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | fire fighting pipe | 6" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Lift Lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Lift Lobby | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Lift Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 11 | 22 | 396
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Lift Lobby | GSM cable | 0.5" |  |  | 1" |  |  | 2 | 28 | 3 | 6 | 168
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Water Meter Room | PPR pipe | 3" | [5 empty] | 0 | 30 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Water Meter Room | PPR pipe | 2" | [5 empty] | 0 | 28 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 | 220 | 1 | 2 | 440
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | fire fighting pipe | 6" | [5 empty] | 0 | 30 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | CDP pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | conduit pipe | 1" | [5 empty] | 0 | 20 | 7 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | opening |  |  |  | 0.5 | 0.65 | 0.325 | 2 | 300 | 1 | 2 | 600
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Room service | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Staircase | fire fighting pipe | 6" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Full Corridor | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 88 | 88 | 1584
PC#22 Feb'22 | RPJV | 60313 | 2022-02-17 | Hotel | 25 | 2 | Full Corridor | cable | 0.5" |  |  | 1" |  |  | 1 | 28 | 12 | 12 | 336
PC#22 Feb'22 | RPJV | 60306 | 2022-02-17 | Hotel | 17 | 2 | MEP work | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60306 | 2022-02-17 | Hotel | 17 | 2 | MEP work | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60306 | 2022-02-17 | Hotel | 17 | 2 | MEP work | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 4 | 8 | 240
PC#22 Feb'22 | RPJV | 60306 | 2022-02-17 | Hotel | 10 | 2 | Staircase, Shaft | PVC pipe (shaft) | 6" |  |  | 8" |  |  | 2 | 205 | 4 | 4 | 820
PC#22 Feb'22 | RPJV | 60306 | 2022-02-17 | Hotel | 10 | 2 | Staircase, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 1 | 1 | 105
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 1 | 30
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 1 | 1 | 49
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 5 | 5 | 310
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | cable trunking |  |  |  | 0.1 | 0.12 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Housekeeping, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#22 Feb'22 | RPJV | 60307 | 2022-02-17 | Hotel | 13 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 2 | 2 | 98
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 1 | 30
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Entry | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 5 | 5 | 310
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | cable trunking |  |  |  | 0.1 | 0.12 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | opening |  |  |  | 0.2 | 0.5 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Housekeeping, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#22 Feb'22 | RPJV | 60308 | 2022-02-18 | Hotel | 14 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 1 | 30
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 1 | 1 | 49
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 5 | 5 | 310
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | opening |  |  |  | 0.2 | 0.4 | 0.08 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | cable trunking |  |  |  | 0.1 | 0.12 | 0.012 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 | 185 | 1 | 2 | 370
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Housekeeping, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 2 | 2 | 130
PC#22 Feb'22 | RPJV | 60309 | 2022-02-18 | Hotel | 15 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 1 | 30
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 2 | 62 | 1 | 2 | 124
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Entry | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 6 | 12 | 216
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 5 | 5 | 310
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 | 220 | 1 | 2 | 440
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | cable trunking | 0.05 | 0.07 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | opening |  |  |  | 0.35 | 0.4 | 0.14 | 2 | 185 | 1 | 2 | 370
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Housekeeping, Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 7 | 14 | 252
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 16 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 17 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195
PC#22 Feb'22 | RPJV | 60310 | 2022-02-19 | Hotel | 17 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 1 | 1 | 28
PC#22 Feb'22 | RPJV | 60312 | 2022-02-19 | Hotel | 4 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 13 | 13 | 845
PC#22 Feb'22 | RPJV | 60312 | 2022-02-19 | Hotel | 4 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 32 | 32 | 896
PC#22 Feb'22 | RPJV | 60312 | 2022-02-19 | Hotel | 2 | 2 | Slab Work | PVC pipe | 4" | [5 empty] | 1 | 65 | 15 | 15 | 975
PC#22 Feb'22 | RPJV | 60312 | 2022-02-19 | Hotel | 2 | 2 | Slab Work | PVC pipe | 2" | [5 empty] | 1 | 28 | 26 | 26 | 728
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 22 | 3 | Rework | duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 69 | 1 | 1 | 69
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 21 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 21 | 3 | Rework | duct | 0.4 | 0.5 | 0.2 | 0.45 | 0.55 | 0.2475 | 1 | 86 | 1 | 1 | 86
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 21 | 3 | Rework | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 20 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 20 | 3 | Rework | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 20 | 3 | Rework | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 19 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 3 | 3 | 186
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 19 | 3 | Rework | duct | 0.4 | 0.5 | 0.2 | 0.45 | 0.55 | 0.2475 | 1 | 86 | 1 | 1 | 86
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 18 | 3 | Rework | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 17 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 17 | 3 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 17 | 3 | Rework | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 16 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 16 | 3 | Rework | duct | 0.3 | 0.4 | 0.12 | 0.35 | 0.45 | 0.1575 | 1 | 69 | 1 | 1 | 69
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 16 | 3 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 16 | 3 | Rework | PVC pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 16 | 3 | Rework | opening |  |  |  | 0.2 | 0.2 | 0.04 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 15 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 14 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 14 | 3 | Rework | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 13 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 13 | 3 | Rework | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 69 | 1 | 1 | 69
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 12 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 11 | 3 | Rework | duct | 0.3 | 0.5 | 0.15 | 0.4 | 0.55 | 0.22 | 1 | 86 | 1 | 1 | 86
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 10 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 10 | 3 | Rework | duct | 0.4 | 0.5 | 0.2 | 0.45 | 0.55 | 0.2475 | 1 | 86 | 1 | 1 | 86
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 10 | 3 | Rework | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 10 | 3 | Rework | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | duct | 0.3 | 0.5 | 0.15 | 0.35 | 0.55 | 0.1925 | 1 | 69 | 1 | 1 | 69
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | PPR pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | PPR pipe | 1" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | opening |  |  |  | 0.25 | 0.3 | 0.075 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 55446-47 | 2022-02-09 | Residence | 9 | 3 | Rework | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 22 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 20 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 18 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 19 | 3 | New Work | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 30 | 4 | 8 | 240
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 17 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 16 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 16 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 15 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 14 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 14 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 13 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 12 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 12 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 11 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 11 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 10 | 3 | New Work | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 10 | 3 | New Work | cable trunking |  |  |  | 0.1 | 0.1 | 0.01 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 9 | 3 | New Work | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 2 | 69 | 4 | 8 | 552
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 9 | 3 | New Work | duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 69 | 2 | 2 | 138
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 9 | 3 | New Work | PVC pipe | 6" | [5 empty] | 0 | 125 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 9 | 3 | New Work | PVC pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 9 | 3 | New Work | opening |  |  |  | 0.35 | 0.8 | 0.28 | 2 | 300 | 1 | 2 | 600
PC#22 Feb'22 | RPJV | 55448 | 2022-02-10 | Residence | 07-22 | 3 | New Work | duct | 0.6 | 0.6 | 0.36 | 0.64 | 0.64 | 0.4096 | 1 | 110 | 24 | 24 | 2640
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 4 | 4 | 420
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | cable tray |  |  |  | 0.12 | 0.25 | 0.03 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | metal pipe | 2" | [5 empty] | 0 | 16 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | opening | 9 |  |  | 0.25 | 0.4 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | metal pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 2 | 4 | 64
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 4 | 4 | 420
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 2 | 2 | 90
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | cable tray |  |  |  | 0.25 | 0.3 | 0.075 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Wall | opening |  |  |  | 0.25 | 0.3 | 0.075 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | FTR | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | FTR | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | FTR | conduit pipe | 1" | [5 empty] | 0 | 20 | 3 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | FTR | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 2 | 2 | 210
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 4" |  |  | 6" |  |  | 2 | 105 | 3 | 3 | 315
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 2" |  |  | 4" |  |  | 2 | 49 | 1 | 1 | 49
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 |  | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Housekeeping | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Housekeeping | conduit pipe | 1" | [5 empty] | 0 | 18 | 7 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Housekeeping | opening |  |  |  | 0.4 | 0.9 | 0.36 | 2 | 375 | 1 | 2 | 750
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 23 | 1 | 2 | 46
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PVC pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 2 | 2 | 98
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | CDP pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 2 | 60
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | duct | 0.15 | 0.2 | 0.03 | 0.2 | 0.25 | 0.05 | 1 | 44 | 1 | 1 | 44
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 16 | 1 | 2 | 32
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Shaft | PPR pipe (shaft) | 3" |  |  | 5" |  |  | 2 | 49 | 3 | 3 | 147
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Shaft | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | duct | 0.2 | 0.25 | 0.05 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | PPR pipe | 3" | [5 empty] | 0 | 30 | 4 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | conduit pipe | 1" | [5 empty] | 0 | 18 | 12 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor, Entry door | opening |  |  |  | 1.2 | 1.2 | 1.44 | 2 | 400 | 1 | 2.88 | 1152
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Electrical Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Electrical Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Electrical Room | conduit pipe | 1" | [5 empty] | 0 | 18 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Electrical Room | opening |  |  |  | 0.25 | 0.4 | 0.1 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Electrical Room | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 2 | 2 | 124
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Electrical Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | CHW pipe | 2" | [5 empty] | 0 | 20 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | CDP pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 6 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | conduit pipe | 1" | [5 empty] | 0 | 18 | 3 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | opening |  |  |  | 6" |  |  | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Lift lobby | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | CDP pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | opening |  |  |  | 0.28 | 0.8 | 0.224 | 2 | 220 | 1 | 2 | 440
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | PPR pipe | 3" | [5 empty] | 0 | 30 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | CHW pipe | 3" | [5 empty] | 0 | 23 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | fire fighting pipe | 4" | [5 empty] | 0 | 23 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 0 | 60 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | conduit pipe | 1" | [5 empty] | 0 | 18 | 10 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Corridor | opening |  |  |  | 1.15 | 1.2 | 1.38 | 2 | 400 | 1 | 2.76 | 1104
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Water Meter Room | PPR pipe | 4" | [5 empty] | 0 | 65 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Water Meter Room | PPR pipe | 3" | [5 empty] | 0 | 30 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Water Meter Room | fire fighting pipe | 1" | [5 empty] | 0 | 16 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Water Meter Room | conduit pipe | 1" | [5 empty] | 0 | 20 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Water Meter Room | opening |  |  |  | 0.25 | 0.8 | 0.2 | 2 | 220 | 1 | 2 | 440
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-16 | Residence | 28 | 3 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | opening |  |  |  | 0.26 | 0.28 | 0.0728 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | PPR pipe | 4" | [5 empty] | 0 | 65 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | PPR pipe | 3" | [5 empty] | 0 | 30 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | PPR pipe | 2" | [5 empty] | 0 | 28 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | opening |  |  |  | 0.3 | 0.5 | 0.15 | 2 | 185 | 1 | 2 | 370
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | cable tray |  |  |  | 0.2 | 0.26 | 0.052 | 2 | 60 | 1 | 2 | 120
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | fire fighting pipe | 3" | [5 empty] | 0 | 18 | 2 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | opening |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | duct | 0.2 | 0.2 | 0.04 |  |  |  | 0 | 44 | 1 | 0 | 0
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | opening |  |  |  | 0.26 | 0.26 | 0.0676 | 2 | 115 | 1 | 2 | 230
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Entry door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 8 | 16 | 288
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Shaft | PPR pipe (shaft) | 1" |  |  | 2" |  |  | 2 | 45 | 1 | 1 | 45
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Shaft | metal pipe | 2" |  |  | 4" |  |  | 2 | 16 | 3 | 6 | 96
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Shaft | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 62 | 1 | 1 | 62
PC#22 Feb'22 | RPJV | 60302-04 | 2022-02-17 | Residence | 28 | 3 | Staircase | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 18 | 1 | 2 | 36
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 9 | 3 | Apart. no. 4B | PVC pipe | 4" |  |  | 5" |  |  | 1 | 65 | 6 | 6 | 390 | MEP-AX-WR-L8-00270
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 9 | 3 | Apart. no. 4B | PVC pipe | 2" |  |  | 3" |  |  | 1 | 28 | 10 | 10 | 280 | MEP-AX-WR-L8-00270
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 9 | 3 | Apart. no. 2B | PVC pipe | 4" |  |  | 5" |  |  | 1 | 65 | 8 | 8 | 520 | MEP-AX-WR-L8-00270
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 9 | 3 | Apart. no. 2B | PVC pipe | 2" |  |  | 3" |  |  | 1 | 28 | 16 | 16 | 448 | MEP-AX-WR-L8-00270
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 9 | 3 | Apart. no. 4A | PVC pipe | 4" |  |  | 5" |  |  | 1 | 65 | 3 | 3 | 195 | MEP-AX-WR-L8-00270
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 9 | 3 | Apart. no. 4A | PVC pipe | 2" |  |  | 3" |  |  | 1 | 28 | 13 | 13 | 364 | MEP-AX-WR-L8-00270
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | CHW pipe | 3" |  | 0.0044156 |  |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 1 | 16 | 1 | 1 | 16 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | fire fighting pipe | 2" |  | 0.0019625 |  |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | duct | 0.2 | 0.2 | 0.04 |  |  |  | 1 | 32 | 1 | 1 | 32 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | PVC pipe | 2" |  | 0.0019625 |  |  |  | 1 | 28 | 2 | 2 | 56 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | PPR pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61020 | June'22 | Residence | 8 | 3 | Apart. no. 4A | opening |  |  |  | 1.2 | 0.52 | 0.624 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L8-00271
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | duct | 0.2 | 0.2 | 0.04 | 0.23 | 0.23 | 0.0529 | 2 | 32 | 3 | 6 | 192 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | duct | 0.3 | 0.3 | 0.09 | 0.33 | 0.33 | 0.1089 | 2 | 46 | 2 | 4 | 184 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | fire damper | 0.3 | 0.4 | 0.12 | 0.33 | 0.43 | 0.1419 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | fire damper | 0.2 | 0.3 | 0.06 | 0.23 | 0.33 | 0.0759 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | duct | 0.27 | 0.27 | 0.0729 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 25 | 3 | Corridor | fire damper | 0.3 | 0.3 | 0.09 | 0.33 | 0.33 | 0.1089 | 1 | 51 | 2 | 2 | 102 | MEP-AX-WR-L25-00277
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.28 | 0.28 | 0.0784 | 2 | 46 | 2 | 4 | 184 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | fire damper | 0.3 | 0.25 | 0.075 | 0.33 | 0.28 | 0.0924 | 1 | 46 | 2 | 2 | 92 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | duct | 0.27 | 0.27 | 0.0729 | 0.3 | 0.3 | 0.09 | 2 | 46 | 1 | 2 | 92 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 2 | 4 | 120 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | CHW pipe | 2" |  |  | 3" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | PPR pipe | 1" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.27 | 0.27 | 0.0729 | 2 | 46 | 1 | 2 | 92 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | duct | 0.25 | 0.25 | 0.0625 | 0.27 | 0.27 | 0.0729 | 2 | 46 | 1 | 2 | 92 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | blank opening |  |  |  | 0.15 | 0.15 | 0.0225 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00333
PC#07 Aug'22 | KMEP | 61022 | June'22 | Residence | 24 | 3 | Corridor | blank opening |  |  |  | 0.3 | 0.15 | 0.045 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00333
0
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D | cable tray |  |  |  | 0.3 | 0.1 | 0.03 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D | PVC conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 3 | 6 | 108 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D | PPR pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D | cable tray |  |  |  | 0.2 | 0.1 | 0.02 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D, Shaft | PVC pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D, Shaft | fire damper | 0.3 | 0.25 | 0.075 | 0.33 | 0.28 | 0.0924 | 1 | 46 | 2 | 2 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D, Shaft | fire damper | 0.45 | 0.5 | 0.225 | 0.48 | 0.52 | 0.2496 | 1 | 64 | 1 | 1 | 64 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D, Shaft | PVC pipe | 6" |  |  | 7" |  |  | 2 | 125 | 2 | 4 | 500 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 3D, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | fire fighting pipe | 4" |  | 0.00785 |  |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | opening |  |  |  | 0.35 | 0.2 | 0.07 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | fire damper | 0.4 | 0.45 | 0.18 | 0.42 | 0.47 | 0.1974 | 1 | 51 | 2 | 2 | 102 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | CHW pipe | 4" |  |  | 5" |  |  | 2 | 29 | 2 | 4 | 116 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 6 | 12 | 276 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | fire damper | 0.45 | 0.5 | 0.225 | 0.47 | 0.52 | 0.2444 | 1 | 64 | 2 | 2 | 128 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Corridor | fire damper | 0.6 | 0.6 | 0.36 | 0.62 | 0.62 | 0.3844 | 1 | 74 | 2 | 2 | 148 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Passanger Lift lobby | fire fighting pipe | 1.5" |  | 0.00080384 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Passanger Lift lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 3 | 6 | 108 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Passanger Lift lobby | opening |  |  |  | 6" |  | 0.017663 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Passanger Lift lobby | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 23 | 1 | 0 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Passanger Lift lobby | CHW pipe | 3" |  | 0.0044156 |  |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Passanger Lift lobby | opening |  |  |  | 0.2 | 0.35 | 0.07 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | opening |  |  |  | 0.6 | 0.2 | 0.12 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | duct | 0.25 | 0.25 | 0.0625 | 0.28 | 0.28 | 0.0784 | 2 | 46 | 2 | 4 | 184 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | fire damper | 0.2 | 0.2 | 0.04 | 0.22 | 0.22 | 0.0484 | 1 | 32 | 2 | 2 | 64 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Staircase 03 | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Staircase 03 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | FF Lobby | PVC conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 4 | 8 | 144 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | FF Lobby | fire fighting pipe | 2" |  | 0.0019625 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | FF Lobby | opening |  |  |  | 0.4 | 0.25 | 0.1 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Water Meter Room | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Water Meter Room | PPR pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Electrical Room | fire damper | 0.35 | 0.2 | 0.07 | 0.37 | 0.22 | 0.0814 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Electrical Room | PVC conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 5 | 10 | 180 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Electrical Room | cable trunking |  |  |  | 0.07 | 0.07 | 0.01 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A | cable pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | fire damper | 0.25 | 0.3 | 0.075 | 0.27 | 0.32 | 0.0864 | 1 | 46 | 2 | 2 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | fire damper | 0.45 | 0.5 | 0.225 | 0.47 | 0.52 | 0.2444 | 1 | 64 | 1 | 1 | 64 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | fire damper | 0.2 | 0.2 | 0.04 | 0.22 | 0.22 | 0.0484 | 1 | 32 | 1 | 1 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | PVC pipe | 6" |  |  | 7" |  |  | 2 | 125 | 2 | 4 | 500 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | PPR pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | cable tray |  |  |  | 0.28 | 0.08 | 0.0224 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | cable tray |  |  |  | 0.13 | 0.08 | 0.0104 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | PVC conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 1 | 2 | 36 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | PVC pipe | 6" |  |  | 7" |  |  | 2 | 125 | 2 | 4 | 500 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 2A, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | cable tray |  |  |  | 0.35 | 0.08 | 0.028 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | fire fighting pipe | 4" |  |  | 5" |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | cable tray |  |  |  | 0.15 | 0.08 | 0.012 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | CHW pipe | 4" |  |  | 5" |  |  | 2 | 29 | 2 | 4 | 116 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | PPR pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 1 | 2 | 46 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A, Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A, Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A, Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A, Shaft | fire damper | 0.5 | 0.5 | 0.25 | 0.52 | 0.52 | 0.2704 | 1 | 64 | 1 | 1 | 64 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Apart. no. 4A, Shaft | fire damper | 0.3 | 0.3 | 0.09 | 0.32 | 0.32 | 0.1024 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 6" |  |  | 7" |  |  | 2 | 125 | 2 | 4 | 500 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | fire damper | 0.2 | 0.2 | 0.04 | 0.22 | 0.22 | 0.0484 | 1 | 32 | 1 | 1 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | fire damper | 0.25 | 0.25 | 0.0625 | 0.27 | 0.27 | 0.0729 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | fire damper | 0.3 | 0.3 | 0.09 | 0.32 | 0.32 | 0.1024 | 1 | 46 | 2 | 2 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | FHC | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | fire fighting pipe | 4" |  |  | 5" |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 2 | 4 | 260 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Shaft | PVC pipe | 2" |  |  | 3" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Garbage Room | fire damper | 0.2 | 0.2 | 0.04 | 0.22 | 0.22 | 0.0484 | 1 | 32 | 1 | 1 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Garbage Room | PVC pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Garbage Room | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Garbage Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Housekeeping | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Housekeeping | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Housekeeping | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 1 | 2 | 46 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | CHW pipe | 3" |  | 0.0044156 |  |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | conduit pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 4 | 8 | 144 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Entry door | opening |  |  |  | 0.8 | 0.3 | 0.24 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L6-00532
PC#07 Aug'22 | KMEP | 61025-31 | June'22 | Residence | 6 | 3 | Telecom Room | cable tray |  |  |  | 0.7 | 0.25 | 0.175 | 2 | 180 | 1 | 2 | 360 | MEP-AX-WR-L6-00532
0
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FF Lobby | PVC pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FF Lobby | fire fighting pipe | 2" |  | 0.0019625 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FF Lobby | opening |  |  |  | 0.3 | 0.25 | 0.075 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FF Lobby | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FF Lobby | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FF Lobby | fire damper | 0.4 | 0.35 | 0.14 | 0.42 | 0.37 | 0.1554 | 1 | 51 | 2 | 2 | 102 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Chill Room | PPR pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Chill Room | fire fighting pipe | 2" |  | 0.0019625 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Chill Room | PVC conduit pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Chill Room | opening |  |  |  | 0.6 | 0.35 | 0.21 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Chill Room | PVC conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Passanger Lobby | CDP pipe | 3" |  | 0.0044156 |  |  |  |  | 23 | 2 | 0 | 0 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Passanger Lobby | CHW pipe | 3" |  | 0.0044156 |  |  |  | 2 | 23 | 1 | 2 | 46 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Passanger Lobby | PVC conduit pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 10 | 20 | 360 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Passanger Lobby | opening |  |  |  | 0.35 | 0.25 | 0.0875 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Passanger Lobby | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Passanger Lobby | duct | 0.5 | 0.25 | 0.125 | 0.53 | 0.28 | 0.1484 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 2 | 4 | 64 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | fire fighting pipe | 4" |  |  | 5" |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | CHW pipe | 3" |  |  | 4" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | HWS pipe | 3" |  |  | 4" |  |  | 2 | 30 | 2 | 4 | 120 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Housekeeping | PVC pipe | 4" |  |  | 5" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Garbage Room | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Garbage Room | fire damper | 0.2 | 0.2 | 0.04 | 0.22 | 0.22 | 0.0484 | 1 | 32 | 1 | 1 | 32 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Garbage Room | HWS pipe | 3" |  |  | 4" |  |  | 2 | 30 | 2 | 4 | 120 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Garbage Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | Garbage Room | fire fighting pipe | 3" |  |  | 4" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | CHW pipe | 3" |  | 0.0044156 |  |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | cable tray | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 95 | 1 | 2 | 190 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | cable tray | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | cable tray | 0.3 | 0.05 | 0.015 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | PVC conduit pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 3 | 6 | 108 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | opening |  |  |  | 1.1 | 0.4 | 0.44 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | CDP pipe | 3" |  |  | 4" |  |  | 2 | 30 | 3 | 6 | 180 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L4-00531
PC#07 Aug'22 | KMEP | 61038-40 | July'22 | Residence | 4 | 3 | FTR Room | metal conduit pipe | 0.5" |  |  | 1" |  |  | 2 | 14 | 2 | 4 | 56 | MEP-AX-WR-L4-00531
0
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | duct | 1.7 | 2 | 3.4 |  |  |  | 2 | 116 | 1 | 2 | 788.8 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | opening |  |  |  | 1.6 | 2.69 | 4.3 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | duct | 1.7 | 2 | 3.4 |  |  |  | 2 | 116 | 1 | 2 | 788.8 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | opening |  |  |  | 2.15 | 2.8 | 6.02 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | duct | 1.7 | 2 | 3.4 |  |  |  | 2 | 116 | 1 | 2 | 788.8 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | opening |  |  |  | 1.9 | 2.15 | 4.085 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | duct | 0.75 | 2 | 1.5 |  |  |  | 2 | 116 | 1 | 2 | 348 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | opening |  |  |  | 0.9 | 2.1 | 1.89 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | duct | 0.75 | 2 | 1.5 |  |  |  | 2 | 116 | 1 | 2 | 348 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Fresh Air plenum | opening |  |  |  | 0.9 | 2.15 | 1.935 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | duct | 1.5 | 1.6 | 2.4 |  |  |  | 1 | 116 | 1 | 1 | 278.4 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | opening |  |  |  | 1.6 | 1.7 | 2.72 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | duct | 1.5 | 1.6 | 2.4 |  |  |  | 1 | 116 | 1 | 1 | 278.4 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | opening |  |  |  | 1.6 | 1.8 | 2.88 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | PVC pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | opening |  |  |  | 0.25 | 0.5 | 0.125 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 5 | 10 | 650 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | fire fighting pipe | 2" |  |  | 3" |  |  | 2 | 14 | 2 | 4 | 56 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | fire fighting pipe | 2" |  | 0.0019625 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | opening |  |  |  | 0.15 | 0.2 | 0.03 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | cable tray |  |  |  | 0.4 | 0.5 | 0.2 | 2 | 180 | 1 | 2 | 360 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | CEF Room | opening |  |  |  | 0.4 | 0.5 | 0.2 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Electrical Cabinet | cable tray |  |  |  | 0.3 | 0.3 | 0.09 | 2 | 95 | 1 | 2 | 190 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Electrical Cabinet | cable tray |  |  |  | 0.3 | 0.35 | 0.105 | 2 | 150 | 1 | 2 | 300 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Electrical Cabinet | cable tray |  |  |  | 0.15 | 0.2 | 0.03 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-B1-00849
PC#07 Aug'22 | KMEP | 61861 | July'22 | Residence | B1 | 3 | Electrical Cabinet | cable trunking |  |  |  | 0.1 | 0.15 | 0.015 | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-B1-00849
0
PC#07 Aug'22 | KMEP | 61021 | June'22 | Hotel | 5 | 2 | FF lobby | duct | 0.4 | 0.4 | 0.16 | 0.9 | 0.5 | 0.45 | 2 | 82 | 2 | 4 | 328 | MEP-AX-WR-L5-00227
PC#07 Aug'22 | KMEP | 61021 | June'22 | Hotel | 5 | 2 | FF lobby | duct | 0.4 | 0.4 | 0.16 | 0.44 | 0.44 | 0.1936 | 2 | 51 | 2 | 4 | 204 | MEP-AX-WR-L5-00227
PC#07 Aug'22 | KMEP | 61021 | June'22 | Hotel | 5 | 2 | Passanger Lift Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 3 | 6 | 120 | MEP-AX-WR-L5-00227
PC#07 Aug'22 | KMEP | 61021 | June'22 | Hotel | 5 | 2 | Passanger Lift Lobby | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L5-00227
PC#07 Aug'22 | KMEP | 61021 | June'22 | Hotel | 5 | 2 | Passanger Lift Lobby | conduit pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L5-00227
PC#07 Aug'22 | KMEP | 61021 | June'22 | Hotel | 5 | 2 | Passanger Lift Lobby | opening |  |  |  | 0.75 | 0.2 | 0.15 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L5-00227
0
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61866-67 | July'22 | Hotel | 26 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L26-00686
0
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Shaft | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61851-52 | July'22 | Hotel | 25 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
0
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61856-57 | July'22 | Hotel | 24 | 2 | Corridor, Entry D. | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L24-00588
0
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 2 | 2 | 92 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 4 | 4 | 112 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 3 | 3 | 84 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 4 | 4 | 112 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 12 | 12 | 336 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 | 3 | 6 | 300 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 10 | 20 | 360 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Lift lobby | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Lift lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Lift lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 9 | 18 | 324 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Lift lobby | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Water Meter Room | PPR pipe | 6" |  | 0.017662 |  |  |  | 1 | 125 | 1 | 1 | 125 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Water Meter Room | PPR pipe | 4" |  | 0.00785 |  |  |  | 1 | 65 | 1 | 1 | 65 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  | 1 | 30 | 1 | 1 | 30 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Room Service | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Room Service | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Room Service | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Room Service | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 8 | 16 | 288 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Room Service | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | FF Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 1 | 2 | 36 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | FF Lobby | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | FF Lobby | opening |  |  |  | 6" |  | 0.017662 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | FF Lobby | cable pipe | 0.5" |  |  | 2" |  |  | 2 | 28 |  | 0 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Staircase | fire fighting pipe | 4" |  | 0.00785 |  |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 7 | 7 | 196 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 8 | 8 | 224 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 6 | 6 | 168 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 2" |  |  | 4" |  |  | 1 | 65 | 2 | 2 | 130 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 6 | 6 | 168 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 7 | 7 | 196 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | FHC | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | FHC | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 20 | 20 | 560 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 3 | 3 | 84 | MEP-AX-WR-L26-00686
PC#07 Aug'22 | KMEP | 61863-65 | July'22 | Hotel | 26 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L26-00686
0
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 1 | 2 | 36 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 1 | 2 | 40 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Passanger Lift | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Passanger Lift | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Passanger Lift | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 1 | 2 | 40 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Passanger Lift | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 1 | 2 | 36 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Passanger Lift | opening |  |  |  | 0.2 | 0.6 | 0.12 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Water Meter Room | PPR pipe | 6" |  | 0.017662 |  |  |  | 1 | 125 | 1 | 1 | 125 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Water Meter Room | PPR pipe | 4" |  | 0.00785 |  |  |  | 1 | 65 | 1 | 1 | 65 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  | 1 | 30 | 1 | 1 | 30 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 1 | 2 | 40 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Lift lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Lift lobby | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Lift lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 1 | 2 | 36 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Lift lobby | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | opening |  |  |  | 4" |  | 0.00785 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Room Service | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Corridor, all conduit | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 101 | 101 | 1818 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | duct | 0.25 | 0.3 | 0.075 | 0.3 | 0.35 | 0.105 | 1 | 51 | 1 | 1 | 51 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 12 | 12 | 336 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | PVC pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | MEP-AX-WR-L25-00608
PC#07 Aug'22 | KMEP | 61854-55 | July'22 | Hotel | 25 | 2 | Entry door | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84 | MEP-AX-WR-L25-00608
0
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 2 | 2 | 92 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Shaft | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Entry door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Entry door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Entry door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 5 | 10 | 280 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Entry door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 4 | 8 | 224 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Entry door | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 | 3 | 6 | 300 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 8 | 16 | 288 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Lift lobby | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Lift lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Lift lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Lift lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 6 | 12 | 216 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Lift lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Water Meter Room | PPR pipe | 6" |  | 0.017662 |  |  |  | 1 | 125 | 1 | 1 | 125 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Water Meter Room | PPR pipe | 4" |  | 0.00785 |  |  |  | 1 | 65 | 1 | 1 | 65 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  | 1 | 30 | 1 | 1 | 30 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Room Service | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Room Service | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Room Service | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Room Service | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 5 | 10 | 180 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Room Service | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | FF Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | FF Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | duct | 0.2 | 0.25 | 0.05 | 0.25 | 0.3 | 0.075 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Corridor, MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Staircase | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61859-60 | July'22 | Hotel | 24 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L24-00588
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Room no. 03 | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Room no. 03 | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Room no. 03 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 7 | 7 | 196 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Room no. 03 | cable pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 2 | 2 | 36 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 | 3 | 3 | 300 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | cable trunking | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 50 | 2 | 2 | 200 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 50 | 2 | 2 | 200 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | fire fighting pipe | 1" |  | 0.00049063 |  |  |  | 2 | 14 | 1 | 1 | 28 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 3 | 6 | 108 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | cable pipe | 0.5" |  | 0.00013266 |  |  |  | 2 | 18 | 6 | 6 | 216 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 2 | 80 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Housekeeping | CDP pipe | 2" |  |  | 4" |  |  | 2 | 29 | 1 | 2 | 58 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Staircase 08 | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 2 | 16 | 1 | 1 | 32 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Staircase 08 | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lift Lobby | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lift Lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 | 29 | 1 | 2 | 58 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lift Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 2 | 80 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lift Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 13 | 26 | 468 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lift Lobby | opening |  |  |  | 0.25 | 0.6 | 0.15 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  | 2 | 30 | 3 | 3 | 180 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 29 | 1 | 2 | 58 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lobby | fire fighting pipe | 4" |  | 0.00785 |  |  |  | 2 | 21 | 1 | 1 | 42 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 2 | 80 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 6 | 12 | 216 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Lobby | opening |  |  |  | 0.4 | 0.8 | 0.32 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Service Lobby | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Service Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61869 | Aug'22 | Hotel | 19 | 2 | Service Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Staircase 07 | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Shaft | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 04 | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 04 | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 04 | fire fighting pipe | 1" |  |  | 3" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 04 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 9 | 9 | 252 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 01 | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 01 | fire fighting pipe | 1" |  |  | 3" |  |  | 1 | 14 | 1 | 1 | 14 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 01 | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 5 | 5 | 140 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 02 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 02 | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 02 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 02 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 02 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Room no. 02 | cable pipe | 0.5" |  |  | 1.5" |  |  | 2 | 28 | 4 | 8 | 224 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61870 | Aug'22 | Hotel | 19 | 2 | FHC | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | MEP-AX-WR-L19-00731
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 4 | 4 | 200 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 17 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L17-00739
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 4 | 4 | 200 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 18 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L18-00733
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61873 | Aug'22 | Hotel | 19 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L19-00734
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 20 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L20-00735
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 21 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L21-00736
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 22 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L22-00737
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61874 | Aug'22 | Hotel | 23 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L23-00738
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 24 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L24-00762
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 25 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L25-00763
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 26 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L26-00764
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61875 | Aug'22 | Hotel | 27 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L27-00765
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.5 | 0.025 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 2.4 | 1.2 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 6 | 6 | 300 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 28 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.25 | 1.63 | 0.4075 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L28-00766
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 29 | 2 | Electrical Rm, slab | busbar | 0.05 | 0.06 | 0.01 |  |  |  | 1 | 50 | 2 | 2 | 100 | MEP-AX-WR-L29-00767
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 29 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.5 | 1.4 | 0.7 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L29-00767
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 29 | 2 | Electrical Rm, slab | cable tray | 0.05 | 0.3 | 0.015 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L29-00767
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 29 | 2 | Electrical Rm, slab | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 1 | 50 | 5 | 5 | 250 | MEP-AX-WR-L29-00767
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 29 | 2 | Electrical Rm, slab | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 | 50 | 1 | 1 | 50 | MEP-AX-WR-L29-00767
PC#07 Aug'22 | KMEP | 61876 | Aug'22 | Hotel | 29 | 2 | Electrical Rm, slab | opening Mortar |  |  |  | 0.4 | 1.5 | 0.6 | 1 |  | 1 | 1 | 0 | MEP-AX-WR-L29-00767
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 4 | 8 | 224 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | GSM cable | 0.5" |  |  | 2" |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 32 | 1 | 1 | 32 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 2 | 46 | 1 | 2 | 92 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61877 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 4 | 8 | 224 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 1 | 2 | 40 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 5 | 10 | 280 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61878 | Aug'22 | Hotel | 27 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Shaft | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | cable tray | 0.05 | 0.2 | 0.01 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 | 50 | 1 | 2 | 100 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 | 4 | 8 | 400 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | fire fighting pipe | 2" |  | 0.0019625 |  |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 5 | 10 | 180 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 2 | 4 | 72 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.4 | 0.12 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Staircase | fire fighting pipe | 3" |  | 0.0044156 |  |  |  | 2 | 16 | 1 | 2 | 32 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lift Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lift Lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lift Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 13 | 26 | 468 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lift Lobby | opening |  |  |  | 0.2 | 0.5 | 0.1 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lift Lobby | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Water Meter Room | PPR pipe | 6" |  | 0.017662 |  |  |  | 2 | 125 | 1 | 2 | 250 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Water Meter Room | PPR pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Water Meter Room | PPR pipe | 3" |  | 0.0044156 |  |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Water Meter Room | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | PVC pipe | 6" |  | 0.017662 |  |  |  | 2 | 125 | 1 | 2 | 250 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | fire fighting pipe | 6" |  | 0.017662 |  |  |  | 2 | 27 | 1 | 2 | 54 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | CHW pipe | 2" |  | 0.0019625 |  |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | CDP pipe | 2" |  | 0.0019625 |  |  |  | 2 | 28 | 1 | 2 | 56 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | conduit pipe | 1" |  | 0.00049063 |  |  |  | 2 | 18 | 10 | 20 | 360 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61879 | Aug'22 | Hotel | 27 | 2 | Lobby | opening |  |  |  | 0.4 | 0.6 | 0.24 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Service Lobby | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Service Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Service Lobby | fire fighting pipe | 4" |  | 0.00785 |  |  |  | 2 | 21 | 1 | 2 | 42 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Service Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | conduit pipe | 1" |  |  | 2" |  |  | 1 | 28 | 2 | 2 | 56 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 10 | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 10 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 10 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 10 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 11 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 11 | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 11 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 11 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 11 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 12 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 12 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 12 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 13 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 13 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 29 | 1 | 2 | 58 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 13 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 13 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61880 | Aug'22 | Hotel | 27 | 2 | Room no. 13 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Shaft | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 14 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 14 | CDP pipe | 2" |  |  | 4" |  |  | 2 | 29 | 1 | 2 | 58 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 14 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 14 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 14 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 15 | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 16 | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 16 | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 16 | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 16 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 16 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Room no. 16 | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 2 | 4 | 112 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Entry door | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 2 | 46 | 2 | 4 | 184 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Entry door | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Entry door | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Entry door | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Entry door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 7 | 14 | 392 | MEP-AX-WR-L27-00786
PC#07 Aug'22 | KMEP | 61881 | Aug'22 | Hotel | 27 | 2 | Entry door | cable pipe | 0.5" |  |  | 1.5" |  |  | 2 | 28 | 10 | 20 | 560 | MEP-AX-WR-L27-00786
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | PPR pipe | 8" |  | 0.03 |  |  |  | 2 | 250 | 1 | 2 | 500 | WIR - 00892
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | PVC pipe | 6" |  | 0.02 |  |  |  | 2 | 125 | 1 | 2 | 250 | WIR - 00892
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | CDP pipe | 2" |  | 0.002 |  |  |  | 2 | 28 | 1 | 2 | 56 | WIR - 00892
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | metal pipe | 6" |  | 0.02 |  |  |  | 2 | 27 | 2 | 4 | 108 | WIR - 00892
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | metal pipe | 4" |  | 0.01 |  |  |  | 2 | 21 | 2 | 4 | 84 | WIR - 00892
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 3 | 6 | 108 | WIR - 00892
PC#08 Sep'22 | KMEP | 61906 | Sep'22 | Residence | 23 | 3 | Water Meter Room | opening |  |  |  | 0.35 | 1.65 | 0.58 | 2 |  | 1 | 2 | 0 | WIR - 00892
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | Cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 | 50 |  | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | Cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 | 50 |  | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 2 | 4 | 72 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | Opening |  |  |  | 0.3 | 0.4 | 0.12 |  |  |  | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | duct | 0.2 | 0.4 | 0.08 | 0.3 | 0.46 | 0.14 | 2 | 51 | 1 | 2 | 102 | WIR - 00950 | Rate Mistake updated in Nov'22 IPC
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | Cable trunking |  |  |  | 0.15 | 0.15 | 0.02 |  |  |  | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | Cable trunking | 0.05 | 0.05 | 0.1 | [6 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 1 | 2 | 36 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Electrical Room | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Telephone Room | Cable trunking | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 3 | Telephone Room | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 2 | 4 | 72 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | Cable trunking | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 2 | 4 | 72 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | Cable trunking | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | Cable trunking | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 3 | 6 | 108 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 6 | 12 | 336 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Telephone Room | GSM pipe | 0.5" |  |  | 1.5" |  |  | 2 | 28 | 2 | 4 | 112 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | Cable trunking | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 3 | 6 | 108 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61907 | Sep'22 | Hotel | 29 | 2 | Male Toilet | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 3 | 6 | 168 | WIR - 00950
PC#08 Sep'22 | KMEP | 61908 | Sep'22 | Hotel | 29 | 2 | Male Toilet | CHW pipe | 2" |  | 0.002 |  |  |  | 2 | 20 | 2 | 4 | 80 | WIR - 00950
PC#08 Sep'22 | KMEP | 61908 | Sep'22 | Hotel | 29 | 2 | Male Toilet | fire fighting pipe | 1" |  | 0.005 |  |  |  | 2 | 14 | 1 | 2 | 28 | WIR - 00950
PC#08 Sep'22 | KMEP | 61908 | Sep'22 | Hotel | 29 | 2 | Male Toilet | Cable trunking | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61908 | Sep'22 | Hotel | 29 | 2 | Male Toilet | conduit pipe | 1" |  | 0.005 |  |  |  | 2 | 18 | 8 | 16 | 288 | WIR - 00950
PC#08 Sep'22 | KMEP | 61908 | Sep'22 | Hotel | 29 | 2 | Male Toilet | Opening | [9 empty] | 0 | 0 | WIR - 00950
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable tray | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable trunking | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable trunking | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Opening | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | CHW pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | CDP pipe | 2" |  |  | 4" |  |  | 2 | 30 | 1 | 2 | 60 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | duct | 0.35 | 0.35 | 0.12 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Opening | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 4 | 8 | 224 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable tray | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable trunking | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable trunking | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | PPR pipe | 2" | 0.002 |  |  |  |  | 2 | 28 | 1 | 2 | 56 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Opening | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable tray | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | CHW pipe | 3" |  | 0.004 |  |  |  | 2 | 23 | 2 | 4 | 92 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | conduit pipe | 1" |  | 0.005 |  |  |  | 2 | 18 | 1 | 2 | 36 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | opening | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | cable tray | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | opening | [9 empty] | 0 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | WIR - 00977
PC#08 Sep'22 | KMEP | 61910 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 8 | 16 | 448 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | CHW pipe | 3" |  | 0.004 |  |  |  | 2 | 23 | 4 | 8 | 184 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | PVC pipe | 4" |  | 0.01 |  |  |  | 2 | 65 | 4 | 8 | 520 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | fire fighting pipe | 2" |  | 0.002 |  |  |  | 2 | 14 | 1 | 2 | 28 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | PPR pipe | 2" |  | 0.002 |  |  |  | 2 | 28 | 1 | 2 | 56 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | Cable trunking | [6 empty] | 2 |  | 1 | 2 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | conduit pipe | 1" |  | 0.0005 |  |  |  | 2 | 18 | 6 | 12 | 216 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | duct | 0.2 | 0.2 | 0.4 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | Opening | [6 empty] | 2 |  | 1 | 2 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | duct | 0.2 | 0.5 | 0.1 |  |  |  | 2 | 32 | 1 | 2 | 64 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | conduit pipe | 1" |  |  | 2" |  |  | 2 | 28 | 5 | 10 | 280 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | CDP pipe | 2" |  |  | 4" |  |  | 2 | 29 | 1 | 2 | 58 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR - 00977 |  | 32000
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 3 | Corridor, Entry D | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | WIR - 00977 |  | 2666.6667
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable tray | [6 empty] | 2 |  | 1 | 2 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61911 | Sep'22 | Hotel | B1 | 2 | Corridor, Entry D | Cable trunking | [6 empty] | 2 |  | 1 | 2 | 0 | WIR - 00977
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | PPR pipe | 8" |  | 0.03 | 8" |  |  | 2 | 250 | 1 | 2 | 500 | WIR-0133
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | PVC pipe | 6" |  | 0.02 | 5" |  |  | 2 | 125 | 1 | 2 | 250 | WIR-0133
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | CDP pipe | 2" |  | 0.002 |  |  |  | 2 | 28 | 1 | 2 | 56 | WIR-0133
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | Insulated metal pipe | 6" |  | 0.02 | 5" |  |  | 2 | 35 | 2 | 4 | 140 | WIR-0133
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | Insulated metal pipe | 4" |  | 0.01 | 5" |  |  | 2 | 29 | 2 | 4 | 116 | WIR-0133
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | conduit pipe | 1" |  | 0.005 |  |  |  | 2 | 18 | 2 | 4 | 72 | WIR-0133
PC#08 Sep'22 | KMEP | 61912 | Sep'22 | Residence | 13 | 3 | Water Meter Room | opening |  |  |  | 0.35 | 1.65 |  | 2 |  | 1 | 2 | 0 | WIR-0133
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 22 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01153
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 22 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01153
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 22 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01153
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 22 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01153
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 22 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01153
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 22 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01153
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 23 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01154
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 23 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01154
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 23 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01154
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 23 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01154
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 23 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01154
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 23 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01154
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 24 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01155
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 24 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01155
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 24 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01155
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 24 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01155
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 24 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01155
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 24 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01155
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 25 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01156
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 25 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01156
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 25 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01156
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 25 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01156
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 25 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01156
PC#08 Sep'22 | KMEP | 61916 | Sep'22 | Hotel | 25 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01156
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 18 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01149
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 18 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01149
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 18 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01149
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 18 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01149
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 18 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01149
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 18 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01149
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 19 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01150
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 19 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01150
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 19 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01150
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 19 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01150
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 19 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01150
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 19 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01150
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 20 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01151
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 20 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01151
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 20 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01151
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 20 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01151
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 20 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01151
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 20 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01151
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 21 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01152
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 21 | 2 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01152
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 21 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01152
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 21 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01152
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 21 | 2 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01152
PC#08 Sep'22 | KMEP | 61915 | Sep'22 | Hotel | 21 | 2 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01152
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 26 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01157
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 26 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01157
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 26 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01157
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 26 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01157
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 26 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01157
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 26 | 3 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01157
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 27 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01158
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 27 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01158
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 27 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01158
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 27 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01158
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 27 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01158
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 27 | 3 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01158
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 28 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01159
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 28 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01159
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 28 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01159
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 28 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01159
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 28 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01159
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 28 | 3 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01159
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 29 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01160
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 29 | 3 | FTR Room | Cable tray | [8 empty] | 1 | 0 | 0 | WIR-01160
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 29 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01160
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 29 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01160
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 29 | 3 | FTR Room | Cable trunking | [8 empty] | 1 | 0 | 0 | WIR-01160
PC#08 Sep'22 | KMEP | 61917 | Sep'22 | Hotel | 29 | 3 | FTR Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01160
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 6 | 6 | 390 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 | 32 | 1 | 2 | 64 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | CHW pipe | 3" | [5 empty] | 2 | 23 | 2 | 4 | 92 | WIR-01191
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01191
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | Cable trunking |  |  |  | 0.08 | 0.08 | 0.01 | 1 | 50 | 1 | 1 | 50 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.9 | 0.9 | 0.81 |  |  |  | 1 | 116 | 1 | 1 | 116 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.8 | 0.8 | 0.64 |  |  |  | 1 | 98 | 1 | 1 | 98 | WIR-01192
PC#09 Oct'22 | KMEP | 61920 | Oct'22 | Hotel | 1 | 2 | Plant Room | opening | [8 empty] | 1 | 0 | 0 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.8 | 0.24 | 0.36 | 0.86 | 0.3096 | 1 | 74 | 2 | 2 | 148 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | Conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.4 | 0.85 | 0.34 | 0.46 | 0.9 | 0.414 | 1 | 82 | 5 | 5 | 410 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 9 | 9 | 585 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 2 | 2 | 250 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | Conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 6" | 0.02 |  |  |  |  | 1 | 125 | 1 | 1 | 125 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 9 | 9 | 585 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 4 | 4 | 112 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | Conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 8 | 8 | 144 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | firefighting pipe | 6" |  |  | 8" |  |  | 1 | 27 | 2 | 2 | 54 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | CHW pipe | 8" |  |  | 10" |  |  | 1 | 47 | 2 | 2 | 94 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.3 | 0.09 | 0.036 | 0.36 | 0.01296 | 1 | 51 | 2 | 2 | 102 | WIR-01192
PC#09 Oct'22 | KMEP | 61918 | Oct'22 | Hotel | GF | 2 | Ball Room | Cable tray |  |  |  | 0.1 | 0.3 | 0.03 | 1 | 50 | 1 | 1 | 50 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 9 | 9 | 1125 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 4" |  |  | 6" |  |  | 1 | 65 | 2 | 2 | 130 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 2 | 2 | 250 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | fire fighting pipe | 1" |  |  | 2" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.5 | 0.15 | 0.36 | 0.56 | 0.2016 | 2 | 51 | 4 | 8 | 408 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | fire fighting pipe | 4" |  |  | 6" |  |  | 1 | 21 | 2 | 2 | 42 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.65 | 1.15 | 0.7475 | 0.7 | 1.2 | 0.84 | 1 | 110 | 5 | 5 | 550 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | CHW pipe | 8" |  |  | 10" |  |  | 1 | 47 | 2 | 2 | 94 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.6 | 0.18 | 0.36 | 0.66 | 0.2376 | 1 | 64 | 1 | 1 | 64 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.5 | 0.15 | 0.36 | 0.56 | 0.2016 | 1 | 51 | 3 | 3 | 153 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | cable trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 1 | 50 | 1 | 1 | 50 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 1 |  | 2 | 2 | 0 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | cable tray | 0.05 | 0.4 | 0.02 |  |  |  | 1 |  | 1 | 1 | 0 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | opening |  |  |  | 0.25 | 0.7 | 0.175 | 1 |  | 1 | 1 | 0 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.4 | 0.12 | 0.36 | 0.46 | 0.1656 | 1 | 51 | 3 | 3 | 153 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 0.9 | 0.27 | 0.36 | 0.96 | 0.3456 | 1 | 74 | 1 | 1 | 74 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.3 | 1 | 0.3 | 0.36 | 1.06 | 0.3816 | 1 | 74 | 1 | 1 | 74 | WIR-01192
PC#09 Oct'22 | KMEP | 61919 | Oct'22 | Hotel | GF | 2 | Ball Room | duct | 0.8 | 0.8 | 0.64 | 0.86 | 0.86 | 0.7396 | 1 | 103 | 1 | 1 | 103 | WIR-01192
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Staircase | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Staircase | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 2 | 4 | 500 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Corridor | PVC pipe | 6" |  | 0.017662 |  |  |  | 2 | 125 | 2 | 4 | 500 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Corridor | PVC pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Corridor | opening |  |  |  | 0.3 | 0.6 | 0.18 | 2 |  | 1 | 2 | 0 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Staircase | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Staircase | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | Staircase | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | High level | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | High level | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | WIR-01416
PC#09 Oct'22 | KMEP | 61933 | Oct'22 | Residence | L9 | 3 | High level | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01416
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 9 | 9 | 162 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | cable pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Entry Door | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Entry Door | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Entry Door | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Entry Door | duct | 0.3 | 0.3 | 0.09 | 0.36 | 0.36 | 0.1296 | 2 | 51 | 2 | 4 | 204 | WIR-01254
PC#09 Oct'22 | KMEP | 61926 | Oct'22 | Hotel | L22 | 2 | Entry Door | cable pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 4 | 8 | 144 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 7 | 7 | 126 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 2 | 30 | 3 | 6 | 180 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 3 | 6 | 84 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 9 | 18 | 324 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 5 | 10 | 180 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 | 14 | 1 | 2 | 28 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 | 18 | 4 | 8 | 144 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | CDP pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 | 16 | 1 | 2 | 32 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 10 | 20 | 360 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | WM room | PPR pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | WM room | PPR pipe | 3" | [5 empty] | 2 | 30 | 2 | 4 | 120 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | WM room | conduit pipe | 1" | [5 empty] | 2 | 18 | 2 | 4 | 72 | WIR-01254
PC#09 Oct'22 | KMEP | 61927 | Oct'22 | Hotel | L22 | 2 | WM room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 4" |  | 0.00785 |  |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" | [5 empty] | 2 | 18 | 6 | 12 | 216 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | opening |  |  |  | 0.35 | 0.4 | 0.14 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 2 | 4 | 72 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | cable pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 2 | 4 | 72 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 3" | [5 empty] | 2 | 16 | 1 | 2 | 32 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01254
PC#09 Oct'22 | KMEP | 61928 | Oct'22 | Hotel | L22 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 7 | 7 | 126 | WIR-01254
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 3 | 3 | 54 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 5 | 5 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 6 | 6 | 108 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 1" |  |  | 2" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61922 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 22 | 22 | 396 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | cable pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | cable tray | 0.05 | 0.1 | 0.005 |  |  |  | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | cable trunking | 0.1 | 0.1 | 0.01 |  |  |  | 2 |  | 3 | 6 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | cable trunking | 0.05 | 0.05 | 0.01 |  |  |  | 2 |  | 2 | 4 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | fire fighting pipe | 1" | [5 empty] | 2 | 14 | 1 | 2 | 28 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | conduit pipe | 1" | [5 empty] | 2 | 18 | 3 | 6 | 108 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | cable pipe | 0.5" | [5 empty] | 2 | 18 | 4 | 8 | 144 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | opening |  |  |  | 0.6 | 0.9 | 0.54 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | CDP pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Housekeeping | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Staircase | fire fighting pipe | 3" | [5 empty] | 2 | 16 | 1 | 2 | 32 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Staircase | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 9 | 18 | 324 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | opening |  |  |  | 0.2 | 0.6 | 0.12 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | WM room | PPR pipe | 4" |  | 0.00785 |  |  |  | 2 | 65 | 1 | 2 | 130 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | WM room | PPR pipe | 3" | [5 empty] | 2 | 30 | 2 | 4 | 120 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | WM room | opening |  |  |  | 0.3 | 0.8 | 0.24 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | fire fighting pipe | 4" |  | 0.00785 |  |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | conduit pipe | 1" | [5 empty] | 2 | 18 | 11 | 22 | 396 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | opening |  |  |  | 0.4 | 0.55 | 0.22 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | conduit pipe | 1" |  |  | 2" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | fire fighting pipe | 3" | [5 empty] | 2 | 16 | 1 | 2 | 32 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Lobby | opening |  |  |  | 0.3 | 0.3 | 0.09 | 2 |  | 1 | 2 | 0 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | duct | 0.25 | 0.25 | 0.0625 | 0.3 | 0.3 | 0.09 | 1 | 46 | 1 | 1 | 46 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 1 | 1 | 18 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | PPR pipe | 3" |  |  | 5" |  |  | 1 | 30 | 3 | 3 | 90 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01253
PC#09 Oct'22 | KMEP | 61923 | Oct'22 | Hotel | L23 | 2 | Corridor MEP | conduit pipe | 1" |  |  | 2" |  |  | 1 | 18 | 7 | 7 | 126 | WIR-01253
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | fire fighting pipe | 3" | [5 empty] | 1 | 16 | 1 | 1 | 16
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | opening |  |  |  | 0.3 | 0.3 | 0.09 | 1 |  | 1 | 1 | 0
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | fire fighting pipe | 1" | [5 empty] | 1 | 14 | 1 | 1 | 14
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | opening |  |  |  | 0.3 | 0.4 | 0.12 | 1 |  | 1 | 1 | 0
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | fire fighting pipe | 1" |  |  | 2" |  |  | 1 | 14 | 1 | 1 | 14
PC#09 Oct'22 | KMEP | 62251 | Oct'22 | Hotel | L24 | 2 | Outer Sleeve | conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 1 | 1 | 18
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | PPR pipe | 3" | [5 empty] | 1 | 30 | 3 | 3 | 90
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | PVC pipe | 4" |  | 0.00785 |  |  |  | 1 | 65 | 2 | 2 | 130
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | opening |  |  |  | 0.3 | 0.7 | 0.21 | 1 |  | 1 | 1 | 0
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | cable trunking |  |  |  | 0.15 | 0.2 | 0.03 | 1 | 50 | 1 | 1 | 50
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | PVC pipe | 6" |  |  | 8" |  |  | 1 | 125 | 1 | 1 | 125
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 46 | 1 | 1 | 46
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14
PC#09 Oct'22 | KMEP | 62252 | Oct'22 | Hotel | L8 | 2 | Outer Sleeve | conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 2 | 2 | 36
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  | 0.00785 |  |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | opening |  |  |  | 0.1 | 1.7 | 0.17 | 1 |  | 1 | 1 | 0 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | duct | 0.3 | 0.3 | 0.09 |  |  |  | 1 | 46 | 1 | 1 | 46 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | conduit pipe | 1" | [5 empty] | 1 | 18 | 5 | 5 | 90 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | opening |  |  |  | 0.4 | 0.8 | 0.32 | 1 |  | 1 | 1 | 0 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | conduit pipe | 1" | [5 empty] | 1 | 18 | 3 | 3 | 54 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | duct | 0.3 | 0.3 | 0.09 |  |  |  | 1 | 46 | 1 | 1 | 46 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | opening |  |  |  | 0.7 | 1 | 0.7 | 1 |  | 1 | 1 | 0 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | CDP pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 3 | 6 | 84 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 1" |  |  | 2" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00175
PC#09 Oct'22 | KMEP | 61930 | Oct'22 | Hotel | L22 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00175
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 5" |  |  | 7" |  |  | 1 | 27 | 1 | 1 | 27 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | CDP pipe | 4" |  |  | 6" |  |  | 1 | 65 | 1 | 1 | 65 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  | 0.00785 |  |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 2" | [5 empty] | 1 | 14 | 1 | 1 | 14 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | opening |  |  |  | 0.2 | 0.7 | 0.14 | 1 |  | 1 | 1 | 0 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | PPR pipe | 4" |  |  | 6" |  |  | 1 | 65 | 3 | 3 | 195 | WIR-00176
PC#09 Oct'22 | KMEP | 61925 | Oct'22 | Hotel | L23 | 2 | Corridor Out. Sleeve | fire fighting pipe | 3" |  |  | 5" |  |  | 1 | 16 | 1 | 1 | 16 | WIR-00176
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 51 | 2 | 2 | 102 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | CHW pipe | 2" |  |  | 4" |  |  | 1 | 20 | 2 | 2 | 40 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 6 | 6 | 108 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PPR pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 2 | 2 | 56 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 51 | 2 | 2 | 102 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Duct | 0.2 | 0.2 | 0.04 |  |  |  | 1 | 32 | 1 | 1 | 32 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Duct | 0.1 | 0.15 | 0.015 |  |  |  | 1 | 32 | 1 | 1 | 32 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Duct | 0.2 | 0.2 | 0.04 |  |  |  | 1 | 32 | 1 | 1 | 32 | WIR-01529
PC#10 Nov'22 | KMEP | 62259 | Nov'22 | Hotel | L19 | 2 | Room no.2 Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 6 | 6 | 108 | WIR-01529
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 2 | 4 | 500 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 3 | 6 | 750 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.4 | 0.4 | 0.16 | 0.45 | 0.45 | 0.2025 | 2 | 51 | 1 | 2 | 102 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 6" |  |  | 8" |  |  | 2 | 27 | 4 | 8 | 216 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Gas pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.35 | 0.55 | 0.1925 |  |  |  | 2 | 51 | 2 | 4 | 204 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.4 | 0.5 | 0.2 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 6" | [5 empty] | 2 | 27 | 1 | 2 | 54 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.35 | 0.82 | 0.287 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.3 | 0.6 | 0.18 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.9 | 1.2 | 1.08 |  |  |  | 2 | 116 | 1 | 2 | 232 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 6" |  |  | 8" |  |  | 1 | 27 | 3 | 3 | 81 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 2 | 2 | 28 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Gas pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.9 | 2.3 | 2.07 |  |  |  | 2 | 116 | 1 | 2 | 480.24 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 1 | 2 | 250 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Gas pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | PVC pipe | 6" |  |  | 8" |  |  | 2 | 125 | 1 | 2 | 250 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | Duct | 0.6 | 1.5 | 0.9 |  |  |  | 2 | 110 | 1 | 2 | 220 | WIR-01579
PC#10 Nov'22 | KMEP | 62261 | Nov'22 | Hotel | L17 | 2 | Plant Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 4 | 8 | 1000 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | CDP pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 1 | 2 | 250 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | Cable Tray |  |  |  | 0.25 | 0.4 | 0.1 | 2 | 95 | 1 | 2 | 190 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 6" |  |  | 5" |  |  | 2 | 27 | 4 | 8 | 216 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | fire fighting pipe | 6" |  |  | 5" |  |  | 1 | 27 | 4 | 4 | 108 | WIR-01579
PC#10 Nov'22 | KMEP | 62262 | Nov'22 | Hotel | L17 | 2 | Plant Room | metal pipe | 1" |  |  | 5" |  |  | 2 | 14 | 2 | 4 | 56 | WIR-01579
PC#10 Nov'22 | KMEP | 62257 | Nov'22 | Hotel | L19 | 2 | Room no.2 Slab | PVC pipe | 4" | [5 empty] | 1 | 65 | 11 | 11 | 715 | WIR-01530
PC#10 Nov'22 | KMEP | 62257 | Nov'22 | Hotel | L19 | 2 | Room no.2 Slab | PVC pipe | 2" | [5 empty] | 1 | 28 | 21 | 21 | 588 | WIR-01530
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 2 | 4 | 500 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Duct | 0.4 | 0.6 | 0.24 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Duct | 0.5 | 0.5 | 0.25 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | fire fighting pipe | 2" | [5 empty] | 2 | 14 | 1 | 2 | 28 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Conduit pipe | 0.5" | [5 empty] | 2 | 18 | 9 | 18 | 324 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Duct | 0.2 | 0.4 | 0.08 |  |  |  | 2 | 46 | 2 | 4 | 184 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | fire fighting pipe | 6" | [5 empty] | 1 | 27 | 5 | 5 | 135 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | CHW pipe | 3" | [5 empty] | 1 | 23 | 2 | 2 | 46 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | PVC pipe | 4" | [5 empty] | 1 | 65 | 3 | 3 | 195 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | PPR pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Cable tray |  |  |  | 0.25 | 0.25 | 0.0625 | 2 | 95 | 1 | 2 | 190 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Duct | 0.2 | 0.4 | 0.08 |  |  |  | 1 | 46 | 2 | 2 | 92 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Duct | 1.05 | 1.6 | 1.68 | 1.15 | 1.7 | 1.955 | 1 | 116 | 1 | 1 | 226.78 | WIR-01698
PC#10 Nov'22 | KMEP | 62269 | Nov'22 | Hotel | L18 | 2 | AHU Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 5 | 5 | 90 | WIR-01698
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 7 | 14 | 252 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Cable Pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 7 | 14 | 252 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 51 | 3 | 3 | 153 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 95 | 1 | 2 | 190 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 0.3 | 0.85 | 0.255 | 0.35 | 0.9 | 0.315 | 1 | 74 | 1 | 1 | 74 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 3 | 3 | 54 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 0.4 | 0.4 | 0.16 |  |  | 0 | 1 | 51 | 1 | 1 | 51 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 2 | 4 | 56 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 6 | 12 | 336 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 10 | 20 | 360 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 18 | 36 | 648 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 0.2 | 1.6 | 0.32 |  |  |  | 2 | 74 | 1 | 2 | 148 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | fire fighting pipe | 1" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 4" |  |  | 1 | 18 | 3 | 3 | 54 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 8" | [5 empty] | 1 | 46 | 1 | 1 | 46 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | PPR pipe | 2" |  |  | 5" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 0.3 | 0.3 | 0.09 | 0.35 | 0.35 | 0.1225 | 1 | 51 | 1 | 1 | 51 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 46 | 2 | 2 | 92 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01466
PC#10 Nov'22 | KMEP | 62253 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260 | WIR-01466
PC#10 Nov'22 | KMEP | 62254 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01466
PC#10 Nov'22 | KMEP | 62254 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01466
PC#10 Nov'22 | KMEP | 62254 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 5 | 5 | 90 | WIR-01466
PC#10 Nov'22 | KMEP | 62254 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01466
PC#10 Nov'22 | KMEP | 62254 | Nov'22 | Hotel | L21 | 2 | Room no.5 Corridor | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01466
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 01 | fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 2 | 4 | 64 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 01 | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 01 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 38 | 76 | 1368 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 01 | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 3 | 6 | 84 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | Duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 | 32 | 1 | 2 | 64 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | Duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 | 32 | 1 | 2 | 64 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 15 | 30 | 540 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 1 | 2 | 130 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 02 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 48 | 96 | 1728 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 03 | Duct | 8" |  |  | 10" |  |  | 2 | 46 | 6 | 12 | 552 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 03 | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 2 | 4 | 56 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | BOH 03 | fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | fire fighting pipe | 1.5" |  |  | 3" |  |  | 2 | 14 | 2 | 4 | 56 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 13 | 26 | 468 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | Duct | 0.2 | 0.25 | 0.05 |  |  |  | 2 | 32 | 3 | 6 | 192 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 6 | 12 | 336 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 2 | 4 | 56 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | Duct | 0.3 | 0.3 | 0.09 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR-01634
PC#10 Nov'22 | KMEP | 62265 | Nov'22 | Hotel | GF | 2 | Female Toilet | Duct | 0.2 | 0.6 | 0.12 | 0.25 | 0.65 | 0.1625 | 2 | 51 | 1 | 2 | 102 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 22 | 44 | 792 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 4 | 8 | 240 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 4 | 8 | 160 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 9 | 18 | 504 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 3 | 6 | 84 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | Duct | 0.2 | 0.2 | 0.04 | 0.26 | 0.26 | 0.0676 | 2 | 46 | 2 | 4 | 184 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | Duct | 0.3 | 0.3 | 0.09 |  |  |  | 2 | 46 | 3 | 6 | 276 | WIR-01634
PC#10 Nov'22 | KMEP | 62266 | Nov'22 | Hotel | GF | 2 | Female Toilet | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 60 | 120 | 2160 | WIR-01634
PC#10 Nov'22 | KMEP | 62264 | Nov'22 | Hotel | GF | 2 | Slab | PVC pipe | 4" | [5 empty] | 1 | 65 | 26 | 26 | 1690 | WIR-01635
PC#10 Nov'22 | KMEP | 62264 | Nov'22 | Hotel | GF | 2 | Slab | PVC pipe | 2" | [5 empty] | 1 | 28 | 10 | 10 | 280 | WIR-01635
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | Duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 46 | 2 | 2 | 92 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | Duct | 0.2 | 0.6 | 0.12 | 0.25 | 0.65 | 0.1625 | 1 | 51 | 1 | 1 | 51 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 4 | 8 | 520 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | Gas pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 2 | 4 | 72 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 3 | 6 | 390 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Cable tray |  |  |  | 0.15 | 0.2 | 0.03 | 2 | 50 | 1 | 2 | 100 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Cable Trunking |  |  |  | 0.08 | 0.08 | 0.0064 | 2 | 50 | 1 | 2 | 100 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 13 | 26 | 468 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Wall | Opening | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | FTR Work | Cable tray | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | FTR Work | Cable Trunking | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | FTR Work | Opening | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 4" |  |  | 6" |  |  | 2 | 65 | 2 | 4 | 260 | WIR-01839
PC#11 Dec'22 | KMEP | 62274 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Staircase | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Housekeeping | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Housekeeping | Fire fighting pipe | 3" | [5 empty] | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Housekeeping | Conduit pipe | 0.5" | [5 empty] | 2 | 18 | 4 | 8 | 144 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Housekeeping | Opening | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | Fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Shaft | Duct | 0.2 | 0.3 | 0.06 | 0.25 | 0.35 | 0.0875 | 1 | 46 | 2 | 2 | 92 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 | 32 | 2 | 4 | 128 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Opening | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Duct | 0.2 | 0.3 | 0.06 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Opening | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 95 | 1 | 2 | 190 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 18 | 36 | 648 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Lobby | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Lobby | Conduit pipe | 0.5" | [5 empty] | 2 | 18 | 8 | 16 | 288 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Lobby | Opening |  |  |  | 0.3 | 0.3 | 0.09 |  |  |  | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Lobby | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Lobby | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Lobby | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Electrical Room | Duct | 0.2 | 0.4 | 0.08 | 0.25 | 0.45 | 0.1125 | 1 | 51 | 1 | 1 | 51 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Electrical Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 5 | 10 | 180 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Duct | 0.2 | 0.2 | 0.04 |  |  |  | 2 | 32 | 3 | 6 | 192 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Opening |  |  |  | 0.26 | 0.3 | 0.078 |  |  |  | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01839
PC#11 Dec'22 | KMEP | 62275 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Fire fighting pipe | 4" |  |  | 6" |  |  | 2 | 21 | 1 | 2 | 42 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Cable tray |  |  |  | 0.1 | 0.3 | 0.03 | 2 | 50 | 1 | 2 | 100 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Corridor Entry | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Corridor Entry | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 10 | 20 | 360 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Shaft | CHW pipe | 4" |  |  | 6" |  |  | 2 | 29 | 2 | 4 | 116 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Shaft | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Water Meter Room | PPR pipe | 2" | [5 empty] | 2 | 28 | 2 | 4 | 112 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Water Meter Room | Fire fighting pipe | 1" | [5 empty] | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Water Meter Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 1 | 2 | 36 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Water Meter Room | Opening | [9 empty] | 0 | 0 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Water Meter Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | FF Lobby | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | FF Lobby | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | FHC | Fire fighting pipe | 2" |  |  | 4" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Shaft | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Shaft | Duct | 0.2 | 0.2 | 0.04 | 0.25 | 0.25 | 0.0625 | 1 | 46 | 1 | 1 | 46 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Shaft | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 4 | 8 | 144 | WIR-01839
PC#11 Dec'22 | KMEP | 62276 | Dec'22 | Residence | L29 | 3 | Staircase | Fire fighting pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01839
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Duct | 0.86 | 22.76 | 19.5736 |  |  |  | 1 | 116 | 1 | 1 | 2270.5376 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Duct | 0.32 | 0.34 | 0.1088 |  |  |  | 1 | 51 | 1 | 1 | 51 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 3" |  |  | 5" |  |  | 1 | 30 | 1 | 1 | 30 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 8" |  |  | 10" |  |  | 1 | 47 | 2 | 2 | 94 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 8 | 8 | 144 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PPR pipe | 1" |  |  | 3" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 3" |  |  | 5" |  |  | 1 | 23 | 2 | 2 | 46 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Cable tray |  |  |  | 0.33 | 0.42 | 0.1386 | 1 | 150 | 2 | 2 | 300 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Cable Trunking |  |  |  | 0.2 | 0.32 | 0.064 | 1 | 95 | 1 | 1 | 95 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Fire fighting pipe | 2" |  |  | 4" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 4" |  |  | 6" |  |  | 1 | 29 | 2 | 2 | 58 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 8" |  |  | 10" |  |  | 1 | 47 | 2 | 2 | 94 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 8" | [5 empty] | 1 | 250 | 2 | 2 | 500 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 6" | [5 empty] | 1 | 125 | 2 | 2 | 250 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 8" | [5 empty] | 1 | 47 | 2 | 2 | 94 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Cable tray | [9 empty] | 0 | 0 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PPR pipe | 1" | [5 empty] | 1 | 28 | 1 | 1 | 28 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | Duct | 1.05 | 1.6 | 1.68 |  |  |  | 1 | 116 | 1 | 1 | 194.88 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 8" | [5 empty] | 1 | 47 | 2 | 2 | 94 | WIR-01768
PC#11 Dec'22 | KMEP | 62271 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 4" | [5 empty] | 1 | 65 | 1 | 1 | 65 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 2 | 4 | 500 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 2 | 4 | 500 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 6" | [5 empty] | 2 | 125 | 2 | 4 | 500 | WIR-01768
PC#11 Dec'22 | KMEP | 62272 | Dec'22 | Hotel | L18 | 2 | AHU for FB - NX Room | PVC pipe | 2" | [5 empty] | 2 | 28 | 1 | 2 | 56 | WIR-01768
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | Duct | 0.3 | 0.5 | 0.15 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | Duct | 0.25 | 0.4 | 0.1 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | Duct | 0.25 | 0.6 | 0.15 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | PPR pipe | 2" | [5 empty] | 2 | 28 | 3 | 6 | 168 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | Fire fighting pipe | 3" | [5 empty] | 2 | 16 | 1 | 2 | 32 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | PVC pipe | 4" | [5 empty] | 2 | 65 | 1 | 2 | 130 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | PVC pipe | 8" | [5 empty] | 2 | 250 | 2 | 4 | 1000 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | Conduit pipe | 0.5" | [5 empty] | 2 | 18 | 8 | 16 | 288 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | Duct | 0.2 | 0.5 | 0.1 |  |  |  | 2 | 46 | 1 | 2 | 92 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01955
PC#11 Dec'22 | KMEP | 62280 | Dec'22 | Hotel | GF | 2 | BOH Corridor | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Duct | 8" | [5 empty] | 1 | 32 | 1 | 1 | 32 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Fire fighting pipe | 2" | [5 empty] | 1 | 14 | 2 | 2 | 28 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | PVC pipe | 3" | [5 empty] | 1 | 30 | 1 | 1 | 30 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CHW pipe | 2" | [5 empty] | 1 | 20 | 2 | 2 | 40 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Gas pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Duct | 0.3 | 0.5 | 0.15 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CDP pipe | 3" |  |  | 5" |  |  | 2 | 30 | 1 | 2 | 60 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Gas pipe | 3" |  |  | 5" |  |  | 2 | 16 | 1 | 2 | 32 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Duct | 0.2 | 1 | 0.2 | 0.26 | 1.05 | 0.273 | 2 | 64 | 1 | 2 | 128 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Duct | 0.4 | 0.6 | 0.24 | 0.46 | 0.68 | 0.3128 | 2 | 74 | 1 | 2 | 148 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Duct | 0.2 | 0.9 | 0.18 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 6 | 12 | 216 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Duct | 0.4 | 0.6 | 0.24 | 0.48 | 0.68 | 0.3264 | 1 | 74 | 1 | 1 | 74 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CDP pipe | 2" |  |  | 4" |  |  | 1 | 28 | 1 | 1 | 28 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 4 | 4 | 72 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | CHW pipe | 2" | [5 empty] | 1 | 20 | 2 | 2 | 40 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Fire fighting pipe | 1" |  |  | 3" |  |  | 1 | 14 | 1 | 1 | 14 | WIR-01955
PC#11 Dec'22 | KMEP | 62281 | Dec'22 | Hotel | GF | 2 | Kitchen | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 1 | 18 | 2 | 2 | 36 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Duct | 0.2 | 1 | 0.2 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Duct | 0.2 | 1 | 0.2 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | PVC pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 5 | 10 | 280 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | CHW pipe | 2" |  |  | 4" |  |  | 2 | 20 | 2 | 4 | 80 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Cable tray |  |  |  | 0.2 | 0.3 | 0.06 | 2 | 95 | 1 | 2 | 190 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | PVC pipe | 3" |  |  | 5" |  |  | 2 | 30 | 2 | 4 | 120 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 2 | 4 | 72 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Duct | 0.25 | 1 | 0.25 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 4 | 8 | 144 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Duct | 0.25 | 1 | 0.25 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | CHW pipe | 2" | [5 empty] | 2 | 20 | 2 | 4 | 80 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 3 | 6 | 168 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 1 | 2 | 36 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Window High | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 1 | 2 | 28 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | CHW pipe | 3" |  |  | 5" |  |  | 2 | 23 | 2 | 4 | 92 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | CDP pipe | 2" |  |  | 4" |  |  | 2 | 28 | 1 | 2 | 56 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 2 | 4 | 72 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | PVC pipe | 8" |  |  | 10" |  |  | 2 | 250 | 5 | 10 | 2500 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | PVC pipe | 6" |  |  | 4" |  |  | 2 | 65 | 3 | 6 | 390 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | PVC pipe | 2" |  |  | 4" |  |  | 1 | 28 | 3 | 3 | 84 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | PPR pipe | 2" |  |  | 4" |  |  | 2 | 28 | 2 | 4 | 112 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | Fire fighting pipe | 1" |  |  | 3" |  |  | 2 | 14 | 2 | 4 | 56 | WIR-01955
PC#11 Dec'22 | KMEP | 62282 | Dec'22 | Hotel | GF | 2 | Food Storage Room | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 7 | 14 | 252 | WIR-01955
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 01 | Duct | 0.4 | 0.4 | 0.16 |  |  |  | 2 | 51 | 2 | 4 | 204 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 01 | Duct | 0.3 | 0.75 | 0.225 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 01 | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 02 | Duct | 0.4 | 0.4 | 0.16 |  |  |  | 2 | 51 | 2 | 4 | 204 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 02 | Duct | 0.3 | 0.75 | 0.225 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 02 | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 02 | PVC pipe | 4" | [5 empty] | 2 | 65 | 1 | 2 | 130 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 03 | Duct | 0.4 | 0.4 | 0.16 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 03 | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 03 | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 03 | Duct | 0.4 | 0.4 | 0.16 |  |  |  | 2 | 51 | 1 | 2 | 102 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 03 | Duct | 0.3 | 0.75 | 0.225 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 04 | Duct | 0.4 | 0.4 | 0.16 |  |  |  | 2 | 51 | 2 | 4 | 204 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 04 | Duct | 0.3 | 0.75 | 0.225 |  |  |  | 2 | 64 | 1 | 2 | 128 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 04 | PVC pipe | 6" | [5 empty] | 2 | 125 | 1 | 2 | 250 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 04 | CDP pipe | 3" | [5 empty] | 2 | 30 | 1 | 2 | 60 | WIR-00188
PC#11 Dec'22 | KMEP | 62279 | Dec'22 | Hotel | L28 | 2 | Shaft Opening 04 | CHW pipe | 4" | [5 empty] | 2 | 29 | 2 | 4 | 116 | WIR-00188
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L30 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00184
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L30 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 6 | 12 | 216 | WIR-00184
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L29 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00184
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L29 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 5 | 10 | 180 | WIR-00184
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L27 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00187
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L27 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 3 | 6 | 108 | WIR-00187
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L26 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00187
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L22 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00186
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L22 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 5 | 10 | 180 | WIR-00186
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L21 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00186
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L21 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 6 | 12 | 216 | WIR-00186
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L09 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00183
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L09 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 6 | 12 | 216 | WIR-00183
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L07 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00183
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L07 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 5 | 10 | 180 | WIR-00183
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L06 | 3 | Corridor Shaft 03 | CHW pipe | 12" | [5 empty] | 2 | 170 | 2 | 4 | 680 | WIR-00183
PC#11 Dec'22 | KMEP | 62278 | Dec'22 | Residence | L06 | 3 | Corridor Shaft 03 | Conduit pipe | 0.5" |  |  | 1.5" |  |  | 2 | 18 | 5 | 10 | 180 | WIR-00183
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
[18 empty] | 0 | 0
| TOTAL | [17 empty] | 173701.6376
[18 empty] | RPJV | 1193478.3125
[17 empty] | Overall (RPJV & KMEP) Certification / Payment to Fire Sealant Contractor |  | 1367179.9501
[18 empty] | June'2022 | 15462
[18 empty] | July'2022 | 32429.2
[18 empty] | Aug'2022 | 30618
[18 empty] | Sep'2022 | 7942
[18 empty] | Oct'2022 | 23297
[18 empty] | Nov'2022 | 30132.02
[18 empty] | Dec'2022 | 33821.4176

## M. PS Lift
Plot 18 - Dorchester | [10 empty] | PS Works
IPC Ref | IPC-11
Package | Lift works
Subcontractor | KONE
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | MATERIALS ON SITE | BALANCE WORKS | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
PROVISIONAL SUM WORKS
A | Apartment tower lifts | 4137155 | 2188667.35 | 52.9% | 1948487.65 | -1737643.32 | 210844.33 |  | 0 | 0 | 0% | 2188667.35 | 52.9%
B | Hotel tower lifts | 8774014 | 4501591.816 | 51.31% | 4272422.184 | -3685085.88 | 587336.304 |  | 0 | 0 | 0% | 4501591.816 | 51.31%
C | CTU lifts | 528000 | 528000 | 100% | 0 | [6 empty] | 528000 | 100%
D | Scaffolding | 60000 | 60000 | 100% | 0 | [6 empty] | 60000 | 100%
E | Builders work | 127750 | 127750 | 100% | 0 | [6 empty] | 127750 | 100%
F | Landing entrance protection | 300000 | 300000 | 100% | 0 | [6 empty] | 300000 | 100%
G | Lifting hooks/ beams | 61800 | 61800 | 100% | 0 | [6 empty] | 61800 | 100%
Sub-Total (A) |  | 13988719 | 7767809.166 | 55.53% | 6220909.834 | -5422729.2 | 798180.634 | 0 | 0 | 0 | 0% | 7767809.166 | 55.53%
VARIATIONS
| Variations determined by RPJV on 27-Jan-22 (refer separate list) | 822395 | 808715 | 98.34% | 13680 | 0 | 13680 | 0 | 0 | 0 | 0% | 808715 | 98.34%
| Extend provision of CTU to end Feb-22 | 204000 | 204000 | 100% | 0 | 0 | 0
| Relocation of hall lanterns | 25219 | 25219 | 100% | 0 | 0 | 0
Sub-Total (B) |  | 1051614 | 1037934 | 98.7% | 13680 | 0 | 13680 | 0 | 0 | 0 |  | 808715 | 76.9%
SUBCONTRACT AMOUNT (C) = (A+B) |  | 15040333 | 8805743.166 | 58.55% | 6234589.834 | -5422729.2 | 811860.634 | 0 | 0 | 0 | 0% | 8805743.166 | 58.55%
WORK APPROVALS
WA-M141 | Ball room lift works | [5 empty] | 101250 | 60750 | 0 | 60750 | 60%
WA-M315 | Dismantling and reinstallation due to landing doors changes | [5 empty] | 5300 | 0 | 0 | 0
Sub-Total (D) |  | 0 | 0 |  | 0 |  | 106550 | 60750 | 0 | 60750
ANTICIPATED SUBCONTRACT AMOUNT (E) = (C+D) |  | 15040333 | 8805743.166 | 58.55% | 6234589.834 | -5422729.2 | 918410.634 | 60750 | 0 | 60750 | 0.9744% | 8805743.166 | 58.55%

## Kone
Lift works | [16 empty] | Kone
S.Nr | Description | Qty | Unit | Rate | Amount | Progress completion at RPJV termination |  | Amount under KMEP subcontract |  |  | Progress (%) |  |  | Progress Amount (AED) |  |  | Remarks
[6 empty] | % | Amount | Amount (A) | MoS (B) | Balance works (C) = (A-B) | Previous | Current | Cumulative | Previous | Current | Cumulative
A | Apartment tower lifts |  |  |  | 4137155 | 52.9% | 2188667.35 | 1948487.65 | -1737643.32 | 210844.33 |  |  |  | 0 | 0 | 0
| Passenger lift SA-PA-01 | 1 | Nr | 642269 | 642269 | 53.2% | 341687.108 | 300581.892 | -269752.98 | 30828.912 |  | 0% |  | 0 | 0 | 0
| Passenger lift SA-PA-03 | 1 | Nr | 642269 | 642269 | 53.2% | 341687.108 | 300581.892 | -269752.98 | 30828.912 |  | 0% |  | 0 | 0 | 0
| Penthouse lift PH-PA-01 | 1 | Nr | 779758 | 779758 | 53.2% | 414831.256 | 364926.744 | -327498.36 | 37428.384 |  | 0% |  | 0 | 0 | 0
| Penthouse lift PH-PA-02 | 1 | Nr | 779758 | 779758 | 53.2% | 414831.256 | 364926.744 | -327498.36 | 37428.384 |  | 0% |  | 0 | 0 | 0
| Goods lift | 1 | Nr | 778712 | 778712 | 53.2% | 414274.784 | 364437.216 | -327059.04 | 37378.176 |  | 0% |  | 0 | 0 | 0
| Retail goods lift | 2 | Nr | 177412 | 354824 | 50.8% | 180250.59 | 174573.41 | -149026.08 | 25547.33 |  | 0% |  | 0 | 0 | 0
| Retail lift | 1 | Nr | 159565 | 159565 | 50.83% | 81105.248 | 78459.752 | -67055.52 | 11404.232 |  | 0% |  | 0 | 0 | 0
B | Hotel tower lifts |  |  |  | 8774014 | 51.31% | 4501591.816 | 4272422.184 | -3685085.88 | 587336.304 |  |  |  | 0 | 0 | 0
| Passenger lift HO-PA-01 | 1 | Nr | 756606 | 756606 | 50.8% | 384355.848 | 372250.152 | -317774.52 | 54475.632 |  | 0% |  | 0 | 0 | 0
| Passenger lift HO-PA-02 | 1 | Nr | 756606 | 756606 | 50.8% | 384355.848 | 372250.152 | -317774.52 | 54475.632 |  | 0% |  | 0 | 0 | 0
| Passenger lift HO-PA-03 | 1 | Nr | 756606 | 756606 | 50.8% | 384355.848 | 372250.152 | -317774.52 | 54475.632 |  | 0% |  | 0 | 0 | 0
| Passenger lift HO-PA-04 | 1 | Nr | 756606 | 756606 | 50.8% | 384355.848 | 372250.152 | -317774.52 | 54475.632 |  | 0% |  | 0 | 0 | 0
| Passenger lift HO-PA-05 | 1 | Nr | 756606 | 756606 | 50.8% | 384355.848 | 372250.152 | -317774.52 | 54475.632 |  | 0% |  | 0 | 0 | 0
| Passenger lift HO-PA-06 | 1 | Nr | 756606 | 756606 | 50.8% | 384355.848 | 372250.152 | -317774.52 | 54475.632 |  | 0% |  | 0 | 0 | 0
| Hotel service lift HO-GD-01 | 1 | Nr | 608696 | 608696 | 53.2% | 323826.272 | 284869.728 | -255652.32 | 29217.408 |  | 0% |  | 0 | 0 | 0
| Hotel service lift HO-GD-02 | 1 | Nr | 608696 | 608696 | 50.8% | 309217.568 | 299478.432 | -255652.32 | 43826.112 |  | 0% |  | 0 | 0 | 0
| Hotel service lift HO-GD-03 | 1 | Nr | 585320 | 585320 | 50.8% | 297342.56 | 287977.44 | -245834.4 | 42143.04 |  | 0% |  | 0 | 0 | 0
| Hotel service lift HO-GD-04 | 1 | Nr | 585320 | 585320 | 50.8% | 297342.56 | 287977.44 | -245834.4 | 42143.04 |  | 0% |  | 0 | 0 | 0
| Hotel fire/House keeping lift HO-FD-01 | 1 | Nr | 695000 | 695000 | 53.2% | 369740 | 325260 | -291900 | 33360 |  | 0% |  | 0 | 0 | 0
| Hotel room service lift | 1 | Nr | 616346 | 616346 | 50.8% | 313103.768 | 303242.232 | -258865.32 | 44376.912 |  | 0% |  | 0 | 0 | 0
| Hotel restaurant lift | 1 | Nr | 171000 | 171000 | 50.8% | 86868 | 84132 | -71820 | 12312 |  | 0% |  | 0 | 0 | 0
| Hotel amenities lift HO-RP-01 | 1 | Nr | 182000 | 182000 | 50.8% | 92456 | 89544 | -76440 | 13104 |  | 0% |  | 0 | 0 | 0
| Hotel amenities lift HO-RP-02 | 1 | Nr | 182000 | 182000 | 58% | 105560 | 76440 | -76440 | 0 |  | 0% |  | 0 | 0 | 0
C | CTU lifts |  |  |  | 528000 | 100% | 528000 | 0 | 0 | 0
| CTU lifts | 11 | Month | 48000 | 528000 | 100% | 528000 | 0 | 0 | 0 |  | 0%
D | Scaffolding |  |  |  | 60000 | 100% | 60000 | 0 | 0 | 0
| Scaffolding | 1 | Item | 60000 | 60000 | 100% | 60000 | 0 | 0 | 0 |  | 0%
E | Builders work |  |  |  | 127750 | 100% | 127750 | 0 | 0 | 0
| Builders work | 1 | Item | 127750 | 127750 | 100% | 127750 | 0 | 0 | 0 |  | 0%
F | Landing entrance protection |  |  |  | 300000 | 100% | 300000 | 0 | 0 | 0
| Landing entrance protection | 1 | Item | 300000 | 300000 | 100% | 300000 | 0 | 0 | 0 |  | 0%
G | Lifting hooks/ beams |  |  |  | 61800 | 100% | 61800 | 0 | 0 | 0
| Lifting hooks/ beams | 1 | Item | 61800 | 61800 | 100% | 61800 | 0 | 0 | 0 |  | 0%
| Total amount |  |  |  | 13988719 | 55.53% | 7767809.166 | 6220909.834 | -5422729.2 | 798180.634 |  |  |  | 0 | 0 | 0
| Variations |  |  |  | 1051614 |  | 1037934 | 13680 | 0 | 13680 |  |  |  | 0 | 0 | 0
| VO-01 Addition of 6 stops to L7 & L10 & Omission of stops to L6&L9 | 1 | Item | 202208 | 202208 | 100% | 202208 | 0 | 0
| VO-02 Changes in door specification of Lift 1&2 | 1 | Nr | 26192 | 26192 | 100% | 26192 | 0 | 0
| VO-03 Addition of new lift room from L23 to L24 | 1 | Nr | 190000 | 190000 | 92.8% | 176320 | 13680 | 0 | 13680 |  | 0% |  | 0 | 0 | 0
| VO-04 Combining lift 4&5 | 1 | Nr | 210000 | 210000 | 100% | 210000 | 0 | 0
| VO-05 Changes in lift finishes for Lift-3,6,7,9&10 | 1 | Nr | 196000 | 196000 | 100% | 196000 | 0 | 0
| VO-06 Additional 1 stop for L2 elevator | 1 | Nr | 36172 | 36172 | 100% | 36172 | 0 | 0
| VO-07 Cancellation of Lift-13 | -1 | Nr | 185782 | -185782 | 100% | -185782 | 0 | 0
| VO-08 Additional temporaray machine room to L19 - L24 lifts | 1 | Nr | 66780 | 66780 | 100% | 66780 | 0 | 0
| VO-09 Additional temporaray machine room to L16 & L14 lifts | 1 | Nr | 22260 | 22260 | 100% | 22260 | 0 | 0
| VO-10 Additional temporaray machine room to L6,7,9,10,16,19-24 lifts | 1 | Nr | 36570 | 36570 | 100% | 36570 | 0 | 0
| VO-11 Additional manpower for nightshift to L4,6,7,9&10 lifts | 1 | Nr | 21995 | 21995 | 100% | 21995 | 0 | 0
| Extended CTU Oct'21 - Feb'22 | 1 | Nr | 204000 | 204000 | 100% | 204000 | 0 | 0
| Relocation & installation of lift hall indicators | 1 | Nr | 25219 | 25219 | 100% | 25219 | 0 | 0

## N. PS GRMS
Plot 18 - Dorchester | [8 empty] | PS Works
IPC Ref | IPC-11
Package | GRMS and Access Control Systems
Subcontractor | Creation Gulf Trading LLC
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
PROVISIONAL SUM WORKS
A | GRMS and access control systems (supply) | 3115027.5 | 3020150 | 96.95% | 94877.5 | 0 | 0 | 0 | 0% | 3020150 | 96.95%
B | GRMS and access control systems (install) | 350805 | 194095 | 55.33% | 156710 | 0 | 0 | 0 | 0% | 194095 | 55.33%
C | GRMS and access control systems (testing and commissioning) | 139717.5 | 0 | 0% | 139717.5 | 0 | 0 | 0 | 0% | 0 | 0%
D | Provisional sum for double height, Presidential and Royal suites | 78459 | 0 | 0% | 78459 | 0 | 0 | 0 | 0% | 0 | 0%
Sub-Total (A) |  | 3684009 | 3214245 | 87.25% | 469764 | 0 | 0 | 0 | 0% | 3214245 | 87.25%
VARIATIONS
| GRMS and access control to room type 15A, 17A and 18A (extra over PS) | 72589 | 0 | 0% | 72589 | 50812.3 | 0 | 50812.3 | 70% | 50812.3 | 70%
| Changes to lighting control system philosophy | 309967 | 307240 | 99.12% | 2727 | 0 | 0 | 0 | 0% | 307240 | 99.12%
| Changes to hotel guest room external access control panel | 86252 | 80792 | 93.67% | 5460 | 0 | 0 | 0 | 0% | 80792 | 93.67%
| Changes to lighting control system to 11 series guest rooms | 11290 | 0 | 0% | 11290 | 10822 | 0 | 10822 | 95.85% | 10822 | 95.85%
| Changes to access control system to 11 series guest rooms | 10945 | 0 | 0% | 10945 | 9722.5 | 0 | 9722.5 | 88.83% | 9722.5 | 88.83%
| Lighting control system for hotel and residence public areas | 221365 | 93528 | 42.25% | 127837 | 25113.2869 | 0 | 25113.2869 | 19.64% | 118641.2869 | 53.6%
| Lighting control system to L29 | 19266 | 0 | 0% | 19266 | 7102.5 | 0 | 7102.5 | 36.87% | 7102.5 | 36.87%
| Lighting control system to gym at L28 | 6753 | 0 | 0% | 6753 | 2198 | 0 | 2198 | 32.55% | 2198 | 32.55%
Sub-Total (B) |  | 738427 | 481560 | 65.21% | 256867 | 105770.5869 | 0 | 105770.5869 |  | 587330.5869 | 79.54%
SUBCONTRACT AMOUNT (C) = (A+B) |  | 4422436 | 3695805 | 83.57% | 726631 | 105770.5869 | 0 | 105770.5869 | 14.56% | 3801575.5869 | 85.96%
WORK APPROVALS
WA-M157 | Supply of missing GRMS materials |  |  |  | 4193 | 0 | 0 | 0 | 0% | 0 | #DIV/0!
Sub-Total (D) |  | 0 | 0 |  | 4193 | 0 | 0 | 0 |  | 0 | #DIV/0!
ANTICIPATED SUBCONTRACT AMOUNT (E) = (C+D) |  | 4422436 | 3695805 | 83.57% | 730824 | 105770.5869 | 0 | 105770.5869 | 14.47% | #REF! | #REF!

## CGT
GRMS and Access Control Systems | [14 empty] | Creation Gulf Trading
S.Nr | Description | Qty | Unit | Rate | Amount under RPJV subcontract | Progress completion at RPJV termination |  | Amount under KMEP subcontract | Progress (%) |  |  | Amount (AED) |  |  | Remarks
[9 empty] | Previous | Current | Cumulative | Previous | Current | Cumulative
A | GRMS system; Supply |  |  |  | 3115027.5 | 96.95% | 3020149.7115 | 94877.7885 |  |  |  | 0 | 0 | 0
INNCOM MATERIAL NON-VC - EST
| Remote thermistor wired (RT1) for X47 | 272 | no. | 55.1909 | 15011.9323 | 100% | 15011.9323 | 0
| 8 Relay Control Board 15 amp - DIN rail mount (X05R.8) | 272 | no. | 240.0046 | 65281.2469 | 100% | 65281.2469 | 0
| PC50X DALI Module w built-in DALI power supply | 226 | no. | 1030.3994 | 232870.2708 | 100% | 232870.2708 | 0
| Relay Module - 5 relays (4-3 amp and 1-5amp) 100-277Vac (X47.H.P) | 427 | no. | 227.3461 | 97076.791 | 100% | 97076.791 | 0
| Low Voltage interface board - DIN rail mount 8 inputs-outputs (X10) | 544 | no. | 227.3461 | 123676.2864 | 100% | 123676.2864 | 0
| Door Chime (CHM-S) | 221 | no. | 90.8878 | 20086.2065 | 100% | 20086.2065 | 0
| Ceiling mounted motion sensor (PIR) (K594C) | 864 | no. | 130.1291 | 112431.5146 | 100% | 112431.5146 | 0
| Magnetic Door Switch, SENTROL 1058 1/4" Dia., Wire leads (S241) | 323 | no. | 32.912 | 10630.5828 | 100% | 10630.5828 | 0
| Low Voltage Controller Module (MCM4) - require one for each switch plate supporting upto 6 buttons on that switch plate | 663 | no. | 129.7746 | 86040.5802 | 100% | 86040.5802 | 0
| JARD Transformer - 24 VAC for Modulating valves,208/240 VAC | 427 | no. | 58.4821 | 24971.8694 | 100% | 24971.8694 | 0
| SMPS 2000 mA 12 VDC power supply (PS567) | 221 | no. | 132.6608 | 29318.0284 | 100% | 29318.0284 | 0
| S5 to RF protocol converter 20db radio (PC502.2) | 272 | no. | 168.7121 | 45889.6867 | 100% | 45889.6867 | 0
| Ethernet to RF Room Gateway DIN RAIL 0db radio No Power Supply (PC803-DIN) - requires power supply | 221 | no. | 288.9169 | 63850.6373 | 100% | 63850.6373 | 0
INNCOM MATERIAL VC
| DDC Thermostat Metallic Brushed Bronze (standard black frame and window) | 272 | no. | 614.4725 | 167136.519 | 100% | 167136.519 | 0
| ELEMENTS Switch Metallic Brushed Bronze (standard black frame and window) with 1 Push Button | 379 | no. | 338.2444 | 128194.641 | 100% | 128194.641 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (standard black frame and window) with 2 Push Buttons | 300 | no. | 338.2444 | 101473.3306 | 100% | 101473.3306 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (standard black frame and window) with 3 Push Buttons | 226 | no. | 423.8157 | 95782.346 | 100% | 95782.346 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (standard black frame and window) with 4 Push Buttons | 430 | no. | 423.8056 | 182236.3923 | 100% | 182236.3923 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (Double gang black frame and window) with 5 Push Buttons | 38 | no. | 704.6616 | 26777.1393 | 100% | 26777.1393 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (Double gang black frame and window) with 6 Push Buttons | 43 | no. | 704.6616 | 30300.4471 | 100% | 30300.4471 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (Double gang black frame and window) with 7 Push Buttons | 21 | no. | 790.2227 | 16594.6765 | 100% | 16594.6765 | 0
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (Double gang black frame and window) with 8 Push Buttons | 447 | no. | 790.2227 | 353229.542 | 100% | 353229.542 | 0
| ELEMENTS Metallic Brushed Bronze - INTERNATIONAL SOCKET + TWIN USB | 442 | no. | 336.2495 | 148622.2616 | 100% | 148622.2616 | 0
| DS-12 BUTTON - MATTE BLACK | 6664 | no. | 29.7221 | 198067.9858 | 100% | 198067.9858 | 0
| DS-12 BUTTON - SPECIAL DND/MUR BUTTON WITH ILLUMINATION | 884 | no. | 29.7221 | 26274.3246 | 100% | 26274.3246 | 0
INNCOM MATERIAL SERVER & SOFTWARE
| Dell PC Tower Server | 1 | no. | 12420.0144 | 12420.0144 | 75% | 9315.0108 | 3105.0036 | 0% | 0% | 0% | 0 | 0 | 0
| Monitor / keyboard / mouse | 1 | no. | 1868.461 | 1868.461 | 54.6% | 1020.0863 | 848.3747 | 0% | 0% | 0% | 0 | 0 | 0
| IC3 Software License | 1 | no. | 9757.837 | 9757.837 | 0% | 0 | 9757.837 | 0% | 0% | 0% | 0 | 0 | 0
| 3D layout for building | 1 | no. | 4065.7688 | 4065.7688 | 0% | 0 | 4065.7688 | 0% | 0% | 0% | 0 | 0 | 0
| Energy Management Software | 1 | no. | 10570.9867 | 10570.9867 | 0% | 0 | 10570.9867 | 0% | 0% | 0% | 0 | 0 | 0
| Suite Linking Software | 1 | no. | 6505.2179 | 6505.2179 | 0% | 0 | 6505.2179 | 0% | 0% | 0% | 0 | 0 | 0
| PMS Interface Software | 1 | no. | 5979.061 | 5979.061 | 0% | 0 | 5979.061 | 0% | 0% | 0% | 0 | 0 | 0
| CELS Software Interface to Door lock | 1 | no. | 12197.2963 | 12197.2963 | 0% | 0 | 12197.2963 | 0% | 0% | 0% | 0 | 0 | 0
| BACnet interface Software | 1 | no. | 23988.0025 | 23988.0025 | 0% | 0 | 23988.0025 | 0% | 0% | 0% | 0 | 0 | 0
| Application Engineering | 5 | no. | 3572.048 | 17860.2399 | 0% | 0 | 17860.2399 | 0% | 0% | 0% | 0 | 0 | 0
LOCAL MATERIALS
| ENC. FOR STANDARD ROOMS & JUNIOR SUITES | 170 | no. | 169.1172 | 28749.9162 | 100% | 28749.9162 | 0
| ENC. FOR SUITE ROOMS | 46 | no. | 214.6876 | 9875.6317 | 100% | 9875.6317 | 0
| ENC. FOR DUPLEX SUITE ROOMS | 5 | no. | 214.6876 | 1073.4382 | 100% | 1073.4382 | 0
| CAT6 CABLES (In 305 MTR Rolls) | 136 | no. | 358.4879 | 48754.349 | 100% | 48754.349 | 0
| LIMIT SWITCHES | 323 | no. | 9.8736 | 3189.1748 | 100% | 3189.1748 | 0
ACCESS CONTROL SYSTEM (SAFLOK)
| SAFLOK CONCEIRGE - SR2/SR3 Unassembled Reader Behind Panel | 238 | no. | 1325.5949 | 315491.5958 | 100% | 315491.5958 | 0
| EN Mechanical Anti-Panic Mortise | 238 | no. | 108.3565 | 25788.847 | 100% | 25788.847 | 0
| EN Electric Strike - 12/24 VDC Fail Safe/Fail Secure | 238 | no. | 349.3738 | 83150.9554 | 100% | 83150.9554 | 0
| Cable Bridge - KU480 | 17 | no. | 145.3192 | 2470.4269 | 100% | 2470.4269 | 0
| Mechanical Key Override - Keyed Alike Keys | 238 | no. | 62.786 | 14943.0702 | 100% | 14943.0702 | 0
| Power Supply - 12V | 238 | no. | 184.3073 | 43865.1417 | 100% | 43865.1417 | 0
| Saflok Windows CS650003 - Package Including (Application Software, Customised Hotel Software - Database, Software for PMS system & Point of Sale, including 1 No. of RFID Network Encoder & 1 Handheld 6 For Interrogation & Programming) | 1 | no. | 9868.5024 | 9868.5024 | 100% | 9868.5024 | 0
| Messenger Software - LENS RF Zigbee | 1 | no. | 4425.401 | 4425.401 | 100% | 4425.401 | 0
| RFID Network Encoder | 2 | no. | 2892.2071 | 5784.4143 | 100% | 5784.4143 | 0
| Corridor Display Panel | 238 | no. | 0 | 0 | 100% | 0 | 0
| Guest RFID Mini | 1000 | no. | 2.5317 | 2531.6939 | 100% | 2531.6939 | 0
| Staff RFID Mifare 1k byte | 100 | no. | 10.1166 | 1011.6649 | 100% | 1011.6649 | 0
INNCOM MATERIAL NON-VC -COMMON CORRIDOR INTEGRATION MATERIAL
| S5 to RF protocol converter 20db radio (PC502.2) | 17 | no. | 168.7121 | 2868.1054 | 100% | 2868.1054 | 0
| Low Voltage Controller Module (MCM4) - require one for each switch plate supporting upto 6 buttons on that switch plate | 17 | no. | 129.7746 | 2206.1687 | 100% | 2206.1687 | 0
| SMPS 200 mA 12 VDC power supply (PS564) | 17 | no. | 114.1693 | 1940.8776 | 100% | 1940.8776 | 0
| INSTALLATION |  |  |  | 350805 | 55.33% | 194095.2 | 156709.8 |  |  |  | 0 | 0 | 0
| Cable Pulling - Std Room & Juniour Suites | 170 | no. | 390 | 66300 | 100% | 66300 | 0
| Cable Pulling - Suite Rooms | 46 | no. | 507 | 23322 | 100% | 23322 | 0
| Cable Pulling - Duplex Suite | 5 | no. | 546 | 2730 | 100% | 2730 | 0
| Installation of Field Device - Std Room & Juniour Suites | 170 | no. | 243.75 | 41437.5 | 0% | 0 | 41437.5 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of Field Device - Suite Rooms | 46 | no. | 331.5 | 15249 | 0% | 0 | 15249 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of Field Device - Duplex Suites | 5 | no. | 341.25 | 1706.25 | 0% | 0 | 1706.25 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of GRMS Panel - Standard & Junior Suite Rooms | 170 | no. | 195 | 33150 | 98.82% | 32760 | 390 | 0% | 0% | 0% | 0 | 0 | 0
| Dressing of GRMS Panel - Standard & Junior Suite Rooms | 170 | no. | 146.25 | 24862.5 | 91.18% | 22668.75 | 2193.75 | 0% | 0% | 0% | 0 | 0 | 0
| Termination of GRMS Panel - Standard & Junior Suite Rooms | 170 | no. | 146.25 | 24862.5 | 91.18% | 22668.75 | 2193.75 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of GRMS Panel - Suite Rooms | 46 | no. | 198.9 | 9149.4 | 93.48% | 8552.7 | 596.7 | 0% | 0% | 0% | 0 | 0 | 0
| Dressing of GRMS Panel - Suite Rooms | 46 | no. | 175.5 | 8073 | 93.48% | 7546.5 | 526.5 | 0% | 0% | 0% | 0 | 0 | 0
| Termination of GRMS Panel - Suite Rooms | 46 | no. | 175.5 | 8073 | 93.48% | 7546.5 | 526.5 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of GRMS Panel - Duplex Suite Rooms | 5 | no. | 205.725 | 1028.625 | 0% | 0 | 1028.625 | 0% | 0% | 0% | 0 | 0 | 0
| Dressing of GRMS Panel - Duplex Suite Rooms | 5 | no. | 180.375 | 901.875 | 0% | 0 | 901.875 | 0% | 0% | 0% | 0 | 0 | 0
| Termination of GRMS Panel - Duplex Suite Rooms | 5 | no. | 180.375 | 901.875 | 0% | 0 | 901.875 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of Common Corridor Equipment | 17 | no. | 188.175 | 3198.975 | 0% | 0 | 3198.975 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of Corridor Panel | 238 | no. | 214.5 | 51051 | 0% | 0 | 51051 | 0% | 0% | 0% | 0 | 0 | 0
| Installation of Lock on Pre-Drilled Doors | 238 | no. | 146.25 | 34807.5 | 0% | 0 | 34807.5 | 0% | 0% | 0% | 0 | 0 | 0
| TESTING & COMMISSIONING |  |  |  | 139717.5 | 0% | 0 | 139717.5 |  |  |  | 0 | 0 | 0
| Testing & Commissioning - Standard & Juniour Suites | 170 | no. | 594.75 | 101107.5 | 0% | 0 | 101107.5 | 0% | 0% | 0% | 0 | 0 | 0
| Testing & Commissioning - Suite Rooms | 46 | no. | 755.625 | 34758.75 | 0% | 0 | 34758.75 | 0% | 0% | 0% | 0 | 0 | 0
| Testing & Commissioning - Duplex Suite | 5 | no. | 770.25 | 3851.25 | 0% | 0 | 3851.25 | 0% | 0% | 0% | 0 | 0 | 0
| PS Works |  |  |  | 78459 | 0% | 0 | 78459 |  |  |  | 0 | 0 | 0
| Double height suite (1 no.), Presidential suite (1 no.) and Royal suite (1 no.) | 1 | Item | 78459 | 78459 | 0% | 0 | 78459 | 0% | 0% | 0% | 0 | 0 | 0
| Subcontract amount |  |  |  | 3684009 |  | 3214244.9115 | 469764.0885 |  |  |  | 0 | 0 | 0
1 | Design & Construction of Guestroom Management System and access control system for Type 15A,17A & 18A Hotel Guestroom | 1 | Item | 72589 | 72589 | 0% | 0 | 72589 | 70% | 0% | 70% | 50812.3 | 0 | 50812.3
| Supply, Installation and Testing & Commissioning | 2 | LS | 10806.8078 | 21613.6056 | 0% | 0 | 21613.6056 | 70% | 0% | 70% | 15129.5239 | 0 | 15129.5239
| Supply, Installation and Testing & Commissioning | 1 | LS | 28480.3573 | 28480.3573 | 0% | 0 | 28480.3573 | 70% | 0% | 70% | 19936.2501 | 0 | 19936.2501
| Supply, Installation and Testing & Commissioning | 1 | LS | 22495.0371 | 22495.0371 | 0% | 0 | 22495.0371 | 70% | 0% | 70% | 15746.5259 | 0 | 15746.5259
2 | Changes in lighting control system philosophy | 1 | Item | 309967 | 309967 | 99.12% | 307239.55 | 2727 | 0% | 0% | 0% | 0 | 0 | 0
| D454 FET 2 Channel Phase Dimmer (LED Loads - 400W Per Channel) | 366 | Nr | 588.2467 | 215298.3101 | 100% | 215298.3101 | 0
| 8 Relay Control Board (15A per Relay) | 194 | Nr | 231.075 | 44828.5499 | 100% | 44828.5499 | 0
| Additional Installation, Termination per Module | 560 | Nr | 39.67 | 22215.2 | 90.54% | 20113.2 | 2102 |  | 0% | 0% |  | 0
| Additional Impact on GRMS Enclosure Sizes & Additional Local Accessories per Room | 221 | Nr | 125 | 27625 | 97.74% | 27000 | 625 |  | 0% | 0% |  | 0
3 | Changes in Hotel guest room access control panel | 1 | Item | 86251.74 | 86251.74 | 94% | 80792.2474 | 5459.9986 | 0% | 0% | 0% | 0 | 0 | 0
| External Panel Fascia - Exactly as Per Provided sample, Supplier: Joseph Advertisers | 245 | Nr | 610 | 149450 | 100% | 149450 | 0 | [5 empty] | 0
| Custom Metallic Button - Matching Brass Colour, Supplier: EEC, Canada | 245 | Nr | 175 | 42875 | 100% | 42875 | 0 | [5 empty] | 0
| Low Voltage interface board - DIN rail mount 8 inputs-outputs (X10) | 57 | Nr | 224.5 | 12797.01 | 0% | 0 | 12797.01 |  | 0% | 0% |  |  | 0
| Removal of existing external touch panel | -238 | Nr | 499.4528 | -118869.764 | 93.83% | -111532.7526 | -7337.0114 |  | 0% | 0% |  |  | 0
4 | Variation for 11-Series - Change in ID Design | 1 | Item | 11290 | 11290 | 0% | 0 | 11290 | 95.85% | 0% | 95.85% | 10822 | 0 | 10822
| D454 FET 2 Channel Phase Dimmer (LED Loads - 400W Per Channel) | 6 | Nr | 603.33 | 3620 |  | 0 | 3620 | 100% | 0% | 100% | 3620 | 0 | 3620
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (standard black frame and window) without Buttons | 12 | Nr | 418.51 | 5022 |  | 0 | 5022 | 100% | 0% | 100% | 5022 | 0 | 5022
| ELEMENTS Switch Push Button Switch Metallic Brushed Bronze (standard black frame and window) with 1 Push Button | 6 | Nr | 363.36 | 2180 |  | 0 | 2180 | 100% | 0% | 100% | 2180 | 0 | 2180
| Accessories, Additional Installation and Termination of (1 no. of Phase Dimmable module + 1 nos. of Control Plate (New Desk Panel) per Room | 6 | Nr | 78 | 468 |  | 0 | 468 | 0% | 0% | 0% | 0 | 0 | 0
5 | Access condroll in duplex upper floors | 1 | Item | 10945 | 10945 | 0% | 0 | 10945 | 88.83% | 0% | 88.83% | 9722.5 | 0 | 9722.5
| SAFLOK CONCEIRGE - SR2/SR3 Unassembled Reader Behind Panel | 5 | Nr | 1308.57 | 6543 |  | 0 | 6543 | 100% | 0% | 100% | 6543 | 0 | 6543
| EN Mechanical Anti-Panic Mortis | 5 | Nr | 104.89 | 524 |  | 0 | 524 | 100% | 0% | 100% | 524 | 0 | 524
| EN Electric Strike - 12/24 VDC Fail Safe/Fail Secure | 5 | Nr | 343.37 | 1717 |  | 0 | 1717 | 100% | 0% | 100% | 1717 | 0 | 1717
| Mechanical Key Override - Keyed Alike Keys | 5 | Nr | 62.43 | 312 |  | 0 | 312 | 0% | 0% | 0% | 0 | 0 | 0
| Power Supply - 12V | 5 | Nr | 182.3 | 911.5 |  | 0 | 911.5 | 100% | 0% | 100% | 911.5 | 0 | 911.5
| Lock Installation on Pre-Drilled Doors | 5 | Nr | 150 | 750 |  | 0 | 750 | 0% | 0% | 0% | 0 | 0 | 0
| Lock Programming | 5 | Nr | 37.5 | 187.5 |  | 0 | 187.5 | 14.4% | 0% | 14.4% | 27 | 0 | 27
6 | Lighting control system for residence & hotel public area | 1 | Item | 221365 | 221365.2914 | 42% | 93528.2903 | 127837.0012 | 19.64% | 0% | 19.64% | 25113.2869 | 0 | 25113.2869
HOTEL - ADD AREA
| 4 Channel Mains Dimmable Module | 6 | Nr | 1090.3437 | 6542.0623 | 100% | 6542.0623 | 0 |  | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 5 | Nr | 419.95 | 2099.7499 | 100% | 2099.7499 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 3 | Nr | 1275.8062 | 3827.4187 | 133.3% | 5103.9349 | -1276.5162 |  | 0% |  | 0 | 0 | 0
| DIGIDIM Router (1 DALI Subnet) | 1 | Nr | 1017.7312 | 1017.7312 | 0% | 0 | 1017.7312 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 2 | Nr | 114.7 | 229.4 | 100% | 229.4 | 0 |  | 0% |  | 0 | 0 | 0
| AV Interface | 1 | Nr | 763.3562 | 763.3562 | 100% | 763.3562 | 0 |  | 0% |  | 0 | 0 | 0
| BMS Interface | 1 | Nr | 5451.4874 | 5451.4874 | 0% | 0 | 5451.4874 | 100% | 0% | 100% | 5451.4874 | 0 | 5451.4874
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| Door Contact Switch | 3 | Nr | 32.375 | 97.125 | 0% | 0 | 97.125 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 | 0% | 0 | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 462.5 | 462.5 | 0% | 0 | 462.5 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 3 | Nr | 430.125 | 1290.375 | 0% | 0 | 1290.375 | 100% | 0% | 100% | 1290.375 | 0 | 1290.375
| 2C x 1.5Sqmm DALI standard Cable | 120 | m | 2.0442 | 245.31 | 100% | 245.31 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1477.8857 | 1477.8857 | 0% | 0 | 1477.8857 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 1400 | m | 2.0442 | 2861.9499 | 100% | 2861.9499 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 11055.5997 | 11055.5997 | 0% | 0 | 11055.5997 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 4113.4749 | 4113.4749 | 0% | 0 | 4113.4749 |  | 0% |  | 0 | 0 | 0
HOTEL - GF AREA
| 4 Channel Mains Dimmable Module | 2 | Nr | 1090.3437 | 2180.6874 | 100% | 2180.6874 | 0 |  | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 2 | Nr | 419.95 | 839.9 | 100% | 839.9 | 0 |  | 0% |  | 0 | 0 | 0
| 4 Channel Relay Module | 1 | Nr | 376.2437 | 376.2437 | 100% | 376.2437 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets + 1DMX Output) | 1 | Nr | 1882.6062 | 1882.6062 | 100% | 1882.6062 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 6 | Nr | 1275.8062 | 7654.8373 | 100% | 7654.8373 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 4 | Nr | 114.7 | 458.8 | 100% | 458.8 | 0 |  | 0% |  | 0 | 0 | 0
| AV Interface | 1 | Nr | 763.3562 | 763.3562 | 100% | 763.3562 | 0 |  | 0% |  | 0 | 0 | 0
| 1 in – 6 out DMX Splitter | 1 | Nr | 1533.1875 | 1533.1875 | 100% | 1533.1875 | 0 |  | 0% |  | 0 | 0 | 0
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 |  | 0 | 196.1 | 100% | 0% | 100% | 196.1 | 0 | 196.1
| Door Contact Switch | 2 | Nr | 32.375 | 64.75 |  | 0 | 64.75 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  | 0 | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 462.5 | 462.5 |  | 0 | 462.5 |  | 0% |  | 0 | 0 | 0
| Control Plate (White Buttons with White Plastic Fascia) | 2 | Nr | 245.125 | 490.25 |  | 0 | 490.25 | 100% | 0% | 100% | 490.25 | 0 | 490.25
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 4 | Nr | 430.125 | 1720.5 |  | 0 | 1720.5 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 160 | m | 2.0442 | 327.08 | 100% | 327.08 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1798.2 | 1798.2 |  |  | 1798.2 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 3235 | m | 2.0442 | 6613.1486 | 100% | 6613.1486 | 0 |  | 0% |  | 0 | 0 | 0
| DMX Standard Cable | 100 | m | 5.9847 | 598.475 |  |  | 598.475 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 24270.1494 | 24270.1494 |  |  | 24270.1494 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 3486.3249 | 3486.3249 |  |  | 3486.3249 |  | 0% |  | 0 | 0 | 0
HOTEL - LOBBY-L2
| 4 Channel Mains Dimmable Module | 1 | Nr | 1090.3437 | 1090.3437 | 100% | 1090.3437 | 0 |  | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 4 | Nr | 419.95 | 1679.8 | 100% | 1679.8 | 0 |  | 0% |  | 0 | 0 | 0
| 4 Channel Relay Module | 1 | Nr | 376.2437 | 376.2437 | 100% | 376.2437 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 3 | Nr | 1275.8062 | 3827.4187 | 100% | 3827.4187 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 1 | Nr | 114.7 | 114.7 | 100% | 114.7 | 0 |  | 0% |  | 0 | 0 | 0
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 323.75 | 323.75 |  |  | 323.75 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 3 | Nr | 430.125 | 1290.375 |  |  | 1290.375 | 100% | 0% | 100% | 1290.375 | 0 | 1290.375
| 2C x 1.5Sqmm DALI standard Cable | 130 | m | 2.0442 | 265.7525 | 100% | 265.7525 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1415.25 | 1415.25 |  |  | 1415.25 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 1270 | m | 2.0442 | 2596.1974 | 100% | 2596.1974 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 9483.0998 | 9483.0998 |  |  | 9483.0998 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 1667.775 | 1667.775 |  |  | 1667.775 |  | 0% |  | 0 | 0 | 0
HOTEL - SPA
| 4 Channel Mains Dimmable Module | 1 | Nr | 1090.3437 | 1090.3437 | 100% | 1090.3437 | 0 |  | 0% |  | 0 | 0 | 0
| 4 Channel Relay Module | 1 | Nr | 376.2437 | 376.2437 | 100% | 376.2437 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 4 | Nr | 1275.8062 | 5103.2249 | 100% | 5103.2249 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 1 | Nr | 114.7 | 114.7 | 100% | 114.7 | 0 |  | 0% |  | 0 | 0 | 0
| AV Interface | 1 | Nr | 763.3562 | 763.3562 | 100% | 763.3562 | 0 |  | 0% |  | 0 | 0 | 0
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 370 | 370 |  |  | 370 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 9 | Nr | 430.125 | 3871.1249 |  |  | 3871.1249 | 100% | 0% | 100% | 3871.1249 | 0 | 3871.1249
| 2C x 1.5Sqmm DALI standard Cable | 150 | m | 2.0442 | 306.6375 | 100% | 306.6375 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1689.5772 | 1689.5772 |  |  | 1689.5772 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 1550 | m | 2.0442 | 3168.5874 | 100% | 3168.5874 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 12413.4997 | 12413.4997 |  |  | 12413.4997 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 2226.4749 | 2226.4749 |  |  | 2226.4749 |  | 0% |  | 0 | 0 | 0
HOTEL - PROVISIONAL (ROOFTOP LOBBY@GF AND L1-LOBBY,CORRIDORS & PRAYER ROOMS)
| 4 Channel Mains Dimmable Module | 1 | Nr | 1090.3437 | 1090.3437 |  |  | 1090.3437 | 100% | 0% | 100% | 1090.3437 | 0 | 1090.3437
| 4 Channel Relay Module | 1 | Nr | 376.2437 | 376.2437 |  |  | 376.2437 | 100% | 0% | 100% | 376.2437 | 0 | 376.2437
| Imagine Router (2 DALI Subnets) | 1 | Nr | 1275.8062 | 1275.8062 |  |  | 1275.8062 | 100% | 0% | 100% | 1275.8062 | 0 | 1275.8062
| Mini-Input Unit | 1 | Nr | 114.7 | 114.7 |  |  | 114.7 | 100% | 0% | 100% | 114.7 | 0 | 114.7
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 |  |  | 196.1 | 100% | 0% | 100% | 196.1 | 0 | 196.1
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 277.5 | 277.5 |  |  | 277.5 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 2 | Nr | 430.125 | 860.25 |  |  | 860.25 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 100 | m | 2.0442 | 204.425 | 100% | 204.425 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1232.1 | 1232.1 |  |  | 1232.1 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 250 | m | 2.0442 | 511.0625 | 100% | 511.0625 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 2830.4999 | 2830.4999 |  |  | 2830.4999 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 573.5 | 573.5 |  |  | 573.5 |  | 0% |  | 0 | 0 | 0
RESIDENCE - L4
| 4 Channel Mains Dimmable Module | 1 | Nr | 1090.3437 | 1090.3437 | 100% | 1090.3437 | 0 |  | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 1 | Nr | 419.95 | 419.95 | 100% | 419.95 | 0 |  | 0% |  | 0 | 0 | 0
| PIR Occupancy Sensor – 8mtr x 6mtr Range | 9 | Nr | 152.8562 | 1375.7062 | 100% | 1375.7062 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 1 | Nr | 1275.8062 | 1275.8062 | 100% | 1275.8062 | 0 |  | 0% |  | 0 | 0 | 0
| DIGIDIM Router (1 DALI Subnet) | 1 | Nr | 1017.7312 | 1017.7312 | 100% | 1017.7312 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 2 | Nr | 114.7 | 229.4 | 100% | 229.4 | 0 |  | 0% |  | 0 | 0 | 0
| BMS Interface | 1 | Nr | 5451.4874 | 5451.4874 |  |  | 5451.4874 | 100% | 0% | 100% | 5451.4874 | 0 | 5451.4874
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 370 | 370 |  |  | 370 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 2 | Nr | 430.125 | 860.25 |  |  | 860.25 | 100% | 0% | 100% | 860.25 | 0 | 860.25
| 2C x 1.5Sqmm DALI standard Cable | 130 | m | 2.0442 | 265.7525 | 100% | 265.7525 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1772.0317 | 1772.0317 |  |  | 1772.0317 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 620 | m | 2.0442 | 1267.435 | 100% | 1267.435 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 4861.7999 | 4861.7999 | 50% | 2430.8999 | 2430.8999 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 2035 | 2035 | 30% | 610.5 | 1424.5 |  | 0% |  | 0 | 0 | 0
RESIDENCE - L23
| 4 Channel Mains Dimmable Module | 2 | Nr | 1090.3437 | 2180.6874 | 100% | 2180.6874 | 0 |  | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 2 | Nr | 419.95 | 839.9 | 50% | 419.95 | 419.95 |  | 0% |  | 0 | 0 | 0
| PIR Occupancy Sensor – 8mtr x 6mtr Range | 8 | Nr | 152.8562 | 1222.85 | 100% | 1222.85 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 1 | Nr | 1275.8062 | 1275.8062 | 100% | 1275.8062 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 1 | Nr | 114.7 | 114.7 | 100% | 114.7 | 0 |  | 0% |  | 0 | 0 | 0
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 323.75 | 323.75 |  |  | 323.75 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 5 | Nr | 430.125 | 2150.6249 |  |  | 2150.6249 | 100% | 0% | 100% | 2150.6249 | 0 | 2150.6249
| 2C x 1.5Sqmm DALI standard Cable | 120 | m | 2.0442 | 245.31 | 100% | 245.31 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1652.3182 | 1652.3182 |  |  | 1652.3182 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 620 | m | 2.0442 | 1267.435 | 100% | 1267.435 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 4151.3999 | 4151.3999 | 50% | 2075.7 | 2075.7 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 1202.5 | 1202.5 | 30% | 360.75 | 841.75 |  | 0% |  | 0 | 0 | 0
| RESIDENCE - GF | [8 empty] | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 1 | Nr | 419.95 | 419.95 | 100% | 419.95 | 0 |  | 0% |  | 0 | 0 | 0
| 4 Channel Relay Module | 1 | Nr | 376.2437 | 376.2437 | 100% | 376.2437 | 0 |  | 0% |  | 0 | 0 | 0
| PIR Occupancy Sensor – 8mtr x 6mtr Range | 6 | Nr | 152.8562 | 917.1375 | 100% | 917.1375 | 0 |  | 0% |  | 0 | 0 | 0
| Imagine Router (2 DALI Subnets) | 1 | Nr | 1275.8062 | 1275.8062 | 100% | 1275.8062 | 0 |  | 0% |  | 0 | 0 | 0
| DIGIDIM Router (1 DALI Subnet) | 1 | Nr | 1017.7312 | 1017.7312 | 100% | 1017.7312 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 2 | Nr | 114.7 | 229.4 | 100% | 229.4 | 0 |  | 0% |  | 0 | 0 | 0
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 277.5 | 277.5 |  |  | 277.5 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 1 | Nr | 430.125 | 430.125 |  |  | 430.125 | 100% | 0% | 100% | 430.125 | 0 | 430.125
| 2C x 1.5Sqmm DALI standard Cable | 75 | m | 2.0442 | 153.3187 | 100% | 153.3187 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1341.1205 | 1341.1205 |  |  | 1341.1205 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 410 | m | 2.0442 | 838.1425 | 100% | 838.1425 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 3570.4999 | 3570.4999 | 50% | 1785.25 | 1785.25 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 878.75 | 878.75 | 30% | 263.625 | 615.125 |  | 0% |  | 0 | 0 | 0
| RESIDENCE - L2 | [8 empty] | 0% |  | 0 | 0 | 0
| Single Channel Mains Dimmable Module | 1 | Nr | 419.95 | 419.95 | 100% | 419.95 | 0 |  | 0% |  | 0 | 0 | 0
| PIR Occupancy Sensor – 8mtr x 6mtr Range | 4 | Nr | 152.8562 | 611.425 | 100% | 611.425 | 0 |  | 0% |  | 0 | 0 | 0
| DIGIDIM Router (1 DALI Subnet) | 1 | Nr | 1017.7312 | 1017.7312 | 100% | 1017.7312 | 0 |  | 0% |  | 0 | 0 | 0
| Mini-Input Unit | 1 | Nr | 114.7 | 114.7 | 100% | 114.7 | 0 |  | 0% |  | 0 | 0 | 0
| DIN-Rail Enclosure | 1 | Nr | 196.1 | 196.1 | 100% | 196.1 | 0 |  | 0% |  | 0 | 0 | 0
| White Plastic - Single Gang Switch | 1 | Nr | 16.4187 | 16.4187 |  |  | 16.4187 | 100% | 0% | 100% | 16.4187 | 0 | 16.4187
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 277.5 | 277.5 |  |  | 277.5 |  | 0% |  | 0 | 0 | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 1 | Nr | 430.125 | 430.125 |  |  | 430.125 | 100% | 0% | 100% | 430.125 | 0 | 430.125
| 2C x 1.5Sqmm DALI standard Cable | 75 | m | 2.0442 | 153.3187 | 100% | 153.3187 | 0 |  | 0% |  | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1233.2932 | 1233.2932 |  |  | 1233.2932 |  | 0% |  | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 200 | m | 2.0442 | 408.85 | 100% | 408.85 | 0 |  | 0% |  | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 1539.2 | 1539.2 | 50% | 769.6 | 769.6 |  | 0% |  | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 573.5 | 573.5 | 30% | 172.05 | 401.45 |  | 0% |  | 0 | 0 | 0
7 | Lighting Control System L29 | 1 | Item | 19266 | 19266 | 0% | 0 | 19266 | 36.87% | 0% | 36.87% | 7102.5 | 0 | 7102.5
| Imagine Router (2 DALI Subnets) | 2 | Nr | 1379.25 | 2758.5 |  | 0 | 2758.5 | 100% | 0% | 100% | 2758.5 | 0 | 2758.5
| 4 Channel Mains Dimmable Module | 3 | Nr | 1178.75 | 3536.25 |  | 0 | 3536.25 | 100% | 0% | 100% | 3536.25 | 0 | 3536.25
| Single Channel Mains Dimmable Module | 1 | Nr | 454 | 454 |  | 0 | 454 | 100% | 0% | 100% | 454 | 0 | 454
| Mini-Input Unit | 1 | Nr | 124 | 124 |  | 0 | 124 | 100% | 0% | 100% | 124 | 0 | 124
| DIN-Rail Enclosure | 1 | Nr | 212 | 212 |  | 0 | 212 | 100% | 0% | 100% | 212 | 0 | 212
| White Plastic - Single Gang Switch | 1 | Nr | 17.75 | 17.75 |  | 0 | 17.75 | 100% | 0% | 100% | 17.75 | 0 | 17.75
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 400 | 400 |  | 0 | 400 |  | 0% | 0% | 0 | 0 | 0
| Control Plate (White Buttons with White Plastic Fascia Fascia) - for BOH areas | 1 | Nr | 265 | 265 |  | 0 | 265 |  | 0% | 0% | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 90 | m | 2.21 | 198.9 |  | 0 | 198.9 |  | 0% | 0% | 0 | 0 | 0
| Installation of LCS | 1 | LS | 1215 | 1215 |  | 0 | 1215 |  | 0% | 0% | 0 | 0 | 0
| 2C x 1.5Sqmm DALI standard Cable | 360 | m | 2.21 | 795.6 |  | 0 | 795.6 |  | 0% | 0% | 0 | 0 | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 5483 | 5483 |  | 0 | 5483 |  | 0% | 0% | 0 | 0 | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 3806 | 3806 |  | 0 | 3806 |  | 0% | 0% | 0 | 0 | 0
8 | Level 28 - Gym Work | 1 | Item | 6753 | 6753 | 0% | 0 | 6753 | 32.55% | 0% | 32.55% | 2198 | 0 | 2198
| Imagine Router (2 DALI Subnets) | 1 | Nr | 1379 | 1379 |  |  | 1379 | 100% | 0% | 100% | 1379 | 0 | 1379
| Mini-Input Unit | 1 | Nr | 124 | 124 |  | 0 | 124 | 100% | 0% | 100% | 124 | 0 | 124
| DIN-Rail Enclosure | 1 | Nr | 212 | 212 |  | 0 | 212 | 100% | 0% | 100% | 212 | 0 | 212
| White Plastic - Single Gang Switch | 1 | Nr | 18 | 18 |  | 0 | 18 | 100% | 0% | 100% | 18 | 0 | 18
| Accessories (Network Switch, Panel Accessories) | 1 | LS | 300 | 300 |  | 0 | 300 |  |  |  | 0
| Control Plate (Black Buttons with Black Nickel Metallic Fascia) | 1 | Nr | 465 | 465 |  | 0 | 465 | 100% | 0% | 100% | 465 | 0 | 465
| 2C x 1.5Sqmm DALI standard Cable | 90 | m | 2.21 | 199 |  | 0 | 199 |  |  |  | 0
| Installation of LCS | 1 | LS | 1200 | 1200 |  | 0 | 1200 |  |  |  | 0
| 2C x 1.5Sqmm DALI standard Cable | 180 | m | 2.21 | 398 |  | 0 | 398 |  |  |  | 0
| DALI/DMX Control Cable Pulling & Termination at Light Fixtures | 1 | LS | 1952 | 1952 |  | 0 | 1952 |  |  |  | 0
| Engineering, Project Management, Testing & Commissioning | 1 | LS | 506 | 506 |  | 0 | 506 |  |  |  | 0
| Variations |  |  |  | 738427.0314 |  | 481560.0877 | 256866.9997 |  |  |  | 105770.5869 | 0 | 105770.5869

## O. FOH ELV
Plot 18 - Dorchester | [8 empty] | PS Works
IPC Ref | IPC-11
Package | ELV PS Works
Subcontractor | SIS
ITEM | DESCRIPTION | PREVIOUS SUBCONTRACT AMOUNT | PREVIOUS WORKS COMPLETED AMOUNT | % PREVIOUS WORKS COMPLETED | REMAINING WORKS AMOUNT | PREVIOUS | CURRENT | CUMULATIVE |  | TOTAL CLAIM AMOUNT
PROVISIONAL SUM WORKS
1 | Disabled Toilet / Medical Alarm System | 77000 | 40809.9979 | 53% | 36190.0021 | 0 | 0 | 0 | 0% | 40809.9979 | 53%
2 | Residential Video Intercom System | 56951 | 48408.35 | 85% | 8542.65 | 0.0018991 | 0 | 0.0018991 | 2.223e-05% | 48408.3519 | 85%
3 | Additional SMATV Dish | 30980 | 19207.5979 | 62% | 11772.4021 | 0 | 0 | 0 | 0% | 19207.5979 | 62%
4 | Additional Outlets for Guestrooms in L12-16 (RJ45 only) | 97726.22 | 41045.0124 | 42% | 56681.2076 | 0 | 3386.2311 | 3386.2311 | 5.974% | 44431.2435 | 45.47%
5 | Additional Outlets for Guestrooms in L19-27 | 235860.34 | 153309.2199 | 65% | 82551.1201 | 9600 | 3932.0094 | 13532.0094 | 16.39% | 166841.2293 | 70.74%
6 | Additional FOH Access Control for Lifts (Dormakaba) | 95000 | 61750.0024 | 65% | 33249.9976 | 1.941e-12 | 0 | 1.941e-12 | 5.838e-15% | 61750.0024 | 65%
7 | Hotel Public Areas Provisional Sum | 202379.26 | 60713.778 | 30% | 141665.482 | 31775.25 | 477 | 32252.25 | 22.77% | 92966.028 | 45.94%
8 | Residential Public Areas Provisional Sum | 184529.98 | 47977.7948 | 26% | 136552.1852 | 24784.5 | 0 | 24784.5 | 18.15% | 72762.2948 | 39.43%
9 | Landscape Areas Provisional Sum | 502918.47 | 150875.541 | 30% | 352042.929 | 101455.5 | 226.5 | 101682 | 28.88% | 252557.541 | 50.22%
10 | Royal and Presidential Suit Provisional Sum | 30141.6 | 0 | 0% | 30141.6 | 5499.7752 | 2024.9316 | 7524.7069 | 24.96% | 7524.7069 | 24.96%
11 | Gym area Provisional Sum | 12550.76 | 2510.152 | 20% | 10040.608 | 5835.1408 | 182.5594 | 6017.7002 | 59.93% | 8527.8522 | 67.95%
SUBCONTRACT AMOUNT (A) |  | 1526037.63 | 626607.4462 | 41.06% | 899430.1838 | 178950.168 | 10229.2315 | 189179.3995 | 21.03% | 815786.8457 | 53.46%
W.A Ref | WORK APPROVALS
WA-M131 | Supply of Structure Cabling Works |  |  |  | 131894.2 | 36704.25 | 33896.67 | 70600.92 | 53.53% | 70600.92 | #DIV/0!
WA-M139 | Supply of ELV System works at ball, meeting rooms |  |  |  | 833824 | 0 | 27733.305 | 27733.305 | 3.326%
WA-M287 | Disable Toilet Alarm System |  |  |  | 8249 |  |  |  | 0%
Sub-Total (B) |  | 0 | 0 |  | 973967.2 | 36704.25 | 61629.975 | 98334.225 |  | 70600.92 | #DIV/0!
ANTICIPATED SUBCONTRACT AMOUNT (C) = (A+B) |  | 1526037.63 | 626607.4462 |  | 1873397.3838 | 215654.418 | 71859.2065 | 287513.6245 | 15.35% | #REF! | #REF!
2274721.7579
| Overall SIS variations under RPJV |  |  |  | 868606.9417 |  |  | 223858.7691

## SIS (FOH)
ELV PS Works | [19 empty] | SIS
S.Nr | Description | Qty | Unit | Rate | Amount | Certified amount under FM subcontract | Amount under RPJV subcontract | Progress completion at RPJV termination |  |  |  | Amount under KCE subcontract | Progress continuation after RPJV termination |  |  |  | Progress Amount (AED) |  |  | Remarks
[8 empty] | 75% | 15% | 10% | TOTAL |  | 75% | 15% | 10% | TOTAL | Previous | Current | Cumulative
1 | Disabled Toilet / Medical Alarm System | 1 | Item | 77000 | 77000 | 0 | 77000 | 53% |  |  | 40809.9979 | 36190.0021 | 53% |  |  |  | 0 | 0 | 0
Disable Toilet Alarm system - Public area
| 6 Zone DTA Panel | 2 | Nr | 7306 | 14612 | 0 | 14612 |  |  |  | 0 | 14612 | 0% |  |  | 0 | 0 | 0 | 0
| Pull cord | 9 | Nr | 126 | 1134 | 0 | 1134 | 100% |  |  | 850.5 | 283.5 | 100% |  |  | 0 | 0 | 0 | 0
| Over door Sounder | 9 | Nr | 574 | 5166 | 0 | 5166 | 100% |  |  | 3874.5 | 1291.5 | 100% |  |  | 0 | 0 | 0 | 0
| Hideaway panel | 9 | Nr | 996 | 8964 | 0 | 8964 | 100% |  |  | 6723 | 2241 | 100% |  |  | 0 | 0 | 0 | 0
| Reset Button | 9 | Nr | 504 | 4536 | 0 | 4536 | 100% |  |  | 3402 | 1134 | 100% |  |  | 0 | 0 | 0 | 0
| Integration with ACS /I/O Board | 3 |  | 1190 | 3570 | 0 | 3570 | 100% |  |  | 2677.5 | 892.5 | 100% |  |  | 0 | 0 | 0 | 0
| battery | 3 | Nr | 59 | 177 | 0 | 177 | 100% |  |  | 132.75 | 44.25 | 100% |  |  | 0 | 0 | 0 | 0
| Installation | 1 | Nr | 11000 | 11000 | 0 | 11000 |  | 55% | 0% | 6050 | 4950 |  | 61.11% |  | 8.8e-05
| 8 core Cable | 1 | Lot | 6000 | 6000 | 0 | 6000 | 100% | 90% |  | 5310 | 690 | 100% | 90% |  | 0 | 0 | 0 | 0
Panic Button
| Panic Button | 2 | Nr | 375 | 750 | 0 | 750 | 100% |  |  | 562.5 | 187.5 | 100% |  |  | 0 | 0 | 0 | 0
Disable Toilet Alarm system - Guest Rooms (Room Type 1B)
| 6 Zone DTA Panel | 1 | Nr | 7306 | 7306 | 0 | 7306 | 0% |  |  | 0 | 7306 | 0% |  |  | 0 | 0 | 0 | 0
| Pull cord | 4 | Nr | 126 | 504 | 0 | 504 | 100% |  |  | 378 | 126 | 100% |  |  | 0 | 0 | 0 | 0
| Over door Sounder | 4 | Nr | 574 | 2296 | 0 | 2296 | 100% |  |  | 1722 | 574 | 100% |  |  | 0 | 0 | 0 | 0
| Hideaway panel | 4 | Nr | 996 | 3984 | 0 | 3984 | 100% |  |  | 2988 | 996 | 100% |  |  | 0 | 0 | 0 | 0
| Reset Button | 4 | Nr | 504 | 2016 | 0 | 2016 | 100% |  |  | 1512 | 504 | 100% |  |  | 0 | 0 | 0 | 0
| Integration with ACS /I/O Board | 1 | Nr | 1190 | 1190 | 0 | 1190 | 100% |  |  | 892.5 | 297.5 | 100% |  |  | 0 | 0 | 0 | 0
| battery | 1 | Nr | 59 | 59 | 0 | 59 | 100% |  |  | 44.25 | 14.75 | 100% |  |  | 0 | 0 | 0 | 0
| Installation | 1 | Nr | 5000 | 5000 | 0 | 5000 |  | 62.99% |  | 3149.42 | 1850.58 |  | 69.99% |  | 0.00355
| 8 core Cable | 1 | Nr | 3500 | 3500 | 0 | 3500 | 100% | 84% |  | 3066 | 434 | 100% | 84% |  | 0 | 0 | 0 | 0
| Discount | 1 | Nr | -4764 | -4764 | 0 | -4764 |  |  |  | -2524.9221 | -2239.0779 |  |  |  | -0.00021197 |  |  | 0
2 | Residential Video Intercom System | 1 | Item | 56951 | 56951 | 0 | 56951 | 85% |  |  | 48408.35 | 8542.65 | 85% |  |  | 0 | 0.0018991 | 0 | 0.0018991
| RJ45 Modular Plug, 8P8C for Round Cable (C6A) with Boot | 48 | Nr | 5.8824 | 282.3529 | 0 | 282.3529 | 100% | 85% | 0% | 247.7647 | 34.5882 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| 180° Cat6A Unshielded Modular Jack of RIDC | 48 | Nr | 25.2942 | 1214.1216 | 0 | 1214.1216 | 100% | 85% | 0% | 1065.3917 | 148.7299 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 3M, LSZH, Blue | 48 | Nr | 35.484 | 1703.232 | 0 | 1703.232 | 100% | 85% | 0% | 1494.5861 | 208.6459 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| 1U, 24Port Cat 6A Patch Panel , unloaded | 6 | Nr | 66 | 396 | 0 | 396 | 100% | 85% | 0% | 347.49 | 48.51 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| 1U, Cable Manager | 6 | Nr | 63 | 378 | 0 | 378 | 100% | 85% | 0% | 331.695 | 46.305 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| Cat6A F/UTP 23 AWG LSZH cable | 12 | Roll | 696 | 8352 | 0 | 8352 | 100% | 85% | 0% | 7328.88 | 1023.12 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| Multi Mode, OM3, 50/125um, 4 Core, | 3000 | m | 9.2308 | 27692.313 | 0 | 27692.313 | 100% | 85% | 0% | 24300.0047 | 3392.3083 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| F/O Patch Cord, LC/LC Type, Duplex, OM3, 3m, LSZH | 48 | Nr | 55 | 2640 | 0 | 2640 | 100% | 85% | 0% | 2316.6 | 323.4 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| LC/APC, MM Duplex adapter | 48 | Nr | 13 | 624 | 0 | 624 | 100% | 85% | 0% | 547.56 | 76.44 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| F/O Pig Tail, LC Type, Simplex, OM3, 1m, LSZH | 96 | Nr | 15 | 1440 | 0 | 1440 | 100% | 85% | 0% | 1263.6 | 176.4 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| Heat shrink sleeve (Pack of 50) | 2 | Pairs | 22 | 44 | 0 | 44 | 100% | 85% | 0% | 38.61 | 5.39 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| 24 Port Fiber patch Panel | 8 | Nr | 210 | 1680 | 0 | 1680 | 100% | 85% | 0% | 1474.2 | 205.8 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| 1U, Cable Manager | 8 | Nr | 63 | 504 | 0 | 504 | 100% | 85% | 0% | 442.26 | 61.74 | 100% | 85% | 0% | 0 | 0 | 0 | 0
| Installation, Termination, Testing & Commissioning | 1 | LOT | 10001 | 10001 | 0 | 10001 |  | 72.09% | 0% | 7209.71 | 2791.27 |  | 80.1% | 0% | 0.0018991 | 0.0018991 | 0 | 0.0018991
3 | Additional SMATV Dish | 1 | Item | 30980 | 30980 | 0 | 30980 | 62% |  |  | 19207.5979 | 11772.4021 | 62% |  |  | 0 | 0 | 0 | 0
ADDITIONAL KU BAND DISH AND ACCESSORIES
| OFFSET DISH 1300 AL G42dBi WHI.10U | 1 | Nr | 1590 | 1590 | 0 | 1590 | 100% |  |  | 1192.5 | 397.5 | 100% |  |  | 0 | 0 | 0 | 0
| "T" BRACKET RCP GROUND 750x200/ Ø60x2.9mm | 1 | Nr | 140 | 140 | 0 | 140 | 100% |  |  | 105 | 35 | 100% |  |  | 0 | 0 | 0 | 0
| LNB G72dB Po7dBm 32x GR. | 1 | Nr | 939 | 939 | 0 | 939 | 100% |  |  | 704.25 | 234.75 | 100% |  |  | 0 | 0 | 0 | 0
| F.O. SPLITTER 1310/1550nm "FC/ PC" 2W 4dB | 4 | Nr | 939 | 3756 | 0 | 3756 | 100% |  |  | 2817 | 939 | 100% |  |  | 0 | 0 | 0 | 0
| F.O. ATTENUATOR 1310/1550nm "FC/ PC" 10dB | 5 | Nr | 69 | 345 | 0 | 345 | 100% |  |  | 258.75 | 86.25 | 100% |  |  | 0 | 0 | 0 | 0
| OP./ RF CONVERTER QUATTRO FM/ DAB/ UHF- SAT | 5 |  | 782 | 3910 | 0 | 3910 | 100% |  |  | 2932.5 | 977.5 | 100% |  |  | 0 | 0 | 0 | 0
| PSU 20V-1.2A (OPTICAL CONV.) | 5 | Nr | 108 | 540 | 0 | 540 | 100% |  |  | 405 | 135 | 100% |  |  | 0 | 0 | 0 | 0
| COAX.CAB.T100 PVC Eca/ A 16VAtC BL.250m | 100 | Nr | 16 | 1600 | 0 | 1600 | 0% |  |  | 0 | 1600 |  |  |  | 0 | 0 | 0 | 0
| Fiber Cable | 100 | Lot | 12 | 1200 | 0 | 1200 | 0% |  |  | 0 | 1200 |  |  |  | 0 | 0 | 0 | 0
ADDITIONAL C BAND DISH AND ACCESSORIES
| T.0X SM PSU 120W 24V-5A | 1 | Nr | 851 | 851 | 0 | 851 | 100% |  |  | 638.25 | 212.75 | 100% |  |  | 0 | 0 | 0 | 0
| 19" RACK FRAME 5RU | 2 | Nr | 308 | 616 | 0 | 616 | 100% |  |  | 462 | 154 | 100% |  |  | 0 | 0 | 0 | 0
| T.0X FO TX 1310nm 6dBm "SC/ APC" W/ O RET | 3 | Nr | 2429 | 7287 | 0 | 7287 | 100% |  |  | 5465.25 | 1821.75 | 100% |  |  | 0 | 0 | 0 | 0
| T.0X F.O.SPLITT.1260...1650nm "SC/ APC" 2W 4dB | 4 | Nr | 501 | 2004 | 0 | 2004 | 100% |  |  | 1503 | 501 | 100% |  |  | 0 | 0 | 0 | 0
| MINIKOM AMP.SAT 2/1 "F" G35..45dB +MATV MIX | 5 | Nr | 410 | 2050 | 0 | 2050 | 100% |  |  | 1537.5 | 512.5 | 100% |  |  | 0 | 0 | 0 | 0
| TAP 5...2400MHz "F" 2W 12dB TA | 6 | Nr | 31 | 186 | 0 | 186 | 100% |  |  | 139.5 | 46.5 | 100% |  |  | 0 | 0 | 0 | 0
| DOMESTIC F.O.RX MATV/ SAT W/ AUTO.ADJUSTM. | 2 | Nr | 608 | 1216 | 0 | 1216 | 100% |  |  | 912 | 304 | 100% |  |  | 0 | 0 | 0 | 0
| Installation, Testing & Commissioning | 1 | Nr | 2750 | 2750 | 0 | 2750 | 0% | 5.458% |  | 135.0979 | 2614.9021 |  |  |  | 0 |  |  | 0
4 | Additional Outlets for Guestrooms in L12-16 (RJ45 only) | 1 | Item | 97726.22 | 97726.22 | 0 | 97726.22 | 42% |  |  | 41045.0124 | 56681.2076 | 42% |  |  | 0 | 0 | 3386.2311 | 3386.2311
STRUCTURED CABLING SYSTEM
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 858 | Nr | 23.53 | 20188.74 | 0 | 20188.74 | 100% | 80% |  | 17564.2038 | 2624.5362 | 100% | 85% |  | 151.4156 | 0 | 151.4156 | 151.4156
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 858 | Nr | 23.53 | 20188.74 | 0 | 20188.74 | 100% | 80% |  | 17564.2038 | 2624.5362 | 100% | 85% |  | 151.4156 | 0 | 151.4156 | 151.4156
| Unshielded Cat6A Patch Cord w/T568B Wiring, 1M, LSZH | 858 | Nr | 17.65 | 15143.7 | 0 | 15143.7 |  |  |  | 0 | 15143.7 |  |  |  | 0 | 0 | 0 | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 858 | Nr | 25.88 | 22205.04 | 0 | 22205.04 |  |  |  | 0 | 22205.04 |  |  |  | 0 | 0 | 0 | 0
Installation
| Installation, Termination, Testing & Commissioning | 1 | Lot | 20000 | 20000 | 0 | 20000 |  | 32.87% |  | 5916.6 | 14083.4 |  | 50% |  | 3083.4 | 0 | 3083.4 | 3083.4
5 | Additional Outlets for Guestrooms in L19-27 | 1 | Item | 235860.34 | 235860.34 | 0 | 235860.34 | 65% |  |  | 153309.2199 | 82551.1201 | 65% |  |  | 13532.0094 | 9600 | 3932.0094 | 13532.0094
STRUCTURED CABLING SYSTEM
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 961 | Nr | 23.53 | 22612.33 | 0 | 22612.33 | 100% | 90% |  | 20011.9121 | 2600.4179 | 100% | 90% |  | 0 | 0 | 0 | 0
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 961 | Nr | 23.53 | 22612.33 | 0 | 22612.33 | 100% | 0% |  | 16959.2475 | 5653.0825 | 100% | 50% |  | 1695.9248 | 0 | 1695.9248 | 1695.9248
| Unshielded Cat6A Patch Cord w/T568B Wiring, 1M, LSZH | 961 | Nr | 18 | 17298 | 0 | 17298 | 100% | 0% |  | 12973.5 | 4324.5 | 100% | 50% |  | 1297.35 | 0 | 1297.35 | 1297.35
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 961 | Nr | 25.88 | 24870.68 | 0 | 24870.68 | 0% | 0% |  | 0 | 24870.68 | 0% | 0% |  | 0 | 0 | 0 | 0
| 1U, 24 Port Cat6A Patch Panel, unloaded | 93 | Nr | 66 | 6138 | 0 | 6138 | 100% | 90% |  | 5432.13 | 705.87 | 100% | 90% |  | 0 | 0 | 0 | 0
| 1U, Cable Manager | 93 | Nr | 63 | 5859 | 0 | 5859 | 100% | 90% |  | 5185.215 | 673.785 | 100% | 90% |  | 0 | 0 | 0 | 0
| Cat6A F/UTP 23 AWG LSZH Cable | 90 | Roll | 683 | 61470 | 0 | 61470 | 100% | 90% |  | 54400.95 | 7069.05 | 100% | 90% |  | 0 | 0 | 0 | 0
| HDMI Cable for Setup Box (Aten-2L7D) | 128 | Nr | 100 | 12800 | 0 | 12800 |  | 0% |  | 0 | 12800 | 100% | 0% |  | 9600 | 9600 | 0 | 9600 | DN-12934, 12987, 13109 | 123
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 49000 | 49000 | 0 | 49000 |  | 82.87% |  | 36546.2654 | 12453.7346 |  | 85% |  | 938.7346 | 0 | 938.7346 | 938.7346
| Installation of HDMI Cables | 1 | Lot | 11200 | 11200 | 0 | 11200 |  | 0% |  | 0 | 11200 |  | 0% |  | 0 | 0 | 0 | 0
| Engineering Works | 1 | Lot | 2000 | 2000 | 0 | 2000 |  | 100% |  | 1800 | 200 |  | 100% |  | 0 | 0 | 0 | 0
6 | Additional FOH Access Control for Lifts (Dormakaba) | 1 | Item | 95000 | 95000 | 0 | 95000 | 65% |  |  | 61750.0024 | 33249.9976 | 65% |  |  | 1.941e-12 | 1.941e-12 | 0 | 1.941e-12
| Lift reader – Quantum Round RFID - FLUSH with 32 Relays 2-Version MF-MFC 5-32 RELAY 2-FLUSH 1-SINGLE READER 2-INTERNATIONAL B-BLE READY 0-STANDARD 0-STANDARD 0-STANDARD SC-SATIN CHROME SC-SATIN CHROME | 6 | Nr | 15348 | 92088 | 0 | 92088 | 90% | 0% |  | 62159.39 | 29928.61 | 90% | 0% |  | 2.0373e-12 | 2.0373e-12 | 0 | 2.0373e-12
| Enclosure | 6 | Nr | 625 | 3750 | 0 | 3750 | 94% | 0% |  | 2643.75 | 1106.25 | 94% | 0% |  | 0 | 0 | 0 | 0
| Accessories | 1 | Nr | 125 | 125 | 0 | 125 | 11% | 0% |  | 10.3125 | 114.6875 | 11% | 0% |  | 0 | 0 | 0 | 0 |  |  | 0.047266
| Installation Testing & Commissioning | 6 | Lot | 625 | 3750 | 0 | 3750 | 0% | 0% |  | 0 | 3750 | 0% | 0% |  | 0 | 0 | 0 | 0
| Discount | 1 | Lot | -4713 | -4713 | 0 | -4713 | 0% | 0% |  | -3063.4501 | -1649.5499 | 0% | 0% |  | -9.6293e-14 | -9.6293e-14 | 0 | -9.6293e-14
7 | Hotel Public Areas Provisional Sum | 1 | Item | 202379.26 | 202379.26 | 0 | 202379.26 | 30% |  |  | 60713.778 | 141665.482 | 30.83% |  |  | 1680 | 31775.25 | 477 | 32252.25
Levels 2 & 4
| Loud Speaker Type (CM,CM1 & CF) | 29 | Nr | 525 | 15225 | 0 | 15225 | 100% |  |  | 11418.75 | 3806.25 | 100% |  |  | 0
| Loudspeaker Type (BS) | 5 | Nr | 280 | 1400 | 0 | 1400 | 100% |  |  | 1050 | 350 | 100% |  |  | 0
| Self Powered Speaker (Type FR) | 14 | Nr | 5500 | 77000 | 0 | 77000 |  |  |  | 0 | 77000 |  |  |  | 0
| Cables and Connectors | 1 | Nr | 10500 | 10500 | 0 | 10500 | 100% | 75% |  | 9056.25 | 1443.75 | 100% | 75% |  | 0
Installation
| Installation, Testing and Commisioning | 1 | Lot | 7200 | 7200 | 0 | 7200 |  | 44.44% |  | 2880.0036 | 4319.9964 |  | 44.44% |  | 0
Level 28
| Loud Speaker Type (CM,CM1 & CF) | -3 | Nr | 525 | -1575 | 0 | -1575 | 100% |  |  | -1181.25 | -393.75 | 100% |  |  | 0
| Ceiling Subwoofer (Type CS) | -1 | Nr | 910 | -910 | 0 | -910 | 100% |  |  | -682.5 | -227.5 | 100% |  |  | 0
| Loudspeaker Type (BS) | 8 | Nr | 280 | 2240 | 0 | 2240 | 100% |  |  | 1680 | 560 | 100% |  |  | 0
| Amplifier (Type 1) | 2 | Nr | 8989 | 17978 | 0 | 17978 | 100% |  |  | 13483.5 | 4494.5 | 100% |  |  | 0
| Auxillary Input (AI) | -3 | Nr | 3276 | -9828 | 0 | -9828 | 100% |  |  | -7371 | -2457 | 100% |  |  | 0
| Source Selection Panel with Headphone Out (VSH) | -3 | Nr | 1572 | -4716 | 0 | -4716 | 100% |  |  | -3537 | -1179 | 100% |  |  | 0
| Cables and Connectors | 4 | Nr | 683 | 2732 | 0 | 2732 | 100% | 75% |  | 2356.35 | 375.65 | 100% | 75% |  | 0
Installation
| Installation, Testing and Commisioning | 1 | Lot | 3000 | 3000 | 0 | 3000 |  | 44.44% | 0% | 1200 | 1800 |  | 44.44% | 0% | 0
Structured Cabling System
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 83 | Nr | 23.53 | 1952.99 | 0 | 1952.99 | 100% | 100% |  | 1757.691 | 195.299 | 100% | 100% |  | 0
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 83 | Nr | 23.53 | 1952.99 | 0 | 1952.99 | 100% |  |  | 1464.7425 | 488.2475 | 100% |  |  | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 83 | Nr | 25.88 | 2148.04 | 0 | 2148.04 | 100% |  |  | 1611.03 | 537.01 | 100% |  |  | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 83 | Nr | 25.88 | 2148.04 | 0 | 2148.04 | 100% |  |  | 1611.03 | 537.01 | 100% |  |  | 0
| 1U, 24 Port Cat6A Patch Panel, unloaded | 4 | Nr | 66 | 264 | 0 | 264 | 100% | 100% |  | 237.6 | 26.4 | 100% | 100% |  | 0
| 1U, Cable Manager | 4 | Nr | 63 | 252 | 0 | 252 | 100% | 100% |  | 226.8 | 25.2 | 100% | 100% |  | 0
| Cat6A F/UTP 23 AWG LSZH Cable | 16 | Lot | 683 | 10928 | 0 | 10928 | 100% | 100% |  | 9835.2 | 1092.8 | 100% | 100% |  | 0
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 5000 | 5000 | 0 | 5000 |  | 80.37% |  | 3616.59 | 1383.41 |  | 80.37% |  | 0
Active Components
| 802.11ac W2 AP w/CA; 4*4:3; Int Ant; 2*GbE E | 15 | Nr | 1653 | 24795 | 0 | 24795 |  |  |  | 0 | 24795 | 100% |  |  | 18596.25 | 18596.25 | 0 | 18596.25 | DN-13015
| Aironet CISCO DNA Essentials 3 Year Term License | 15 | Nr | 249 | 3735 | 0 | 3735 |  |  |  | 0 | 3735 | 100% |  |  | 2801.25 | 2801.25 | 0 | 2801.25 | DN-13015
| Catalyst 9200 48-port PoE+ , Network Essentials | 1 | Nr | 7246 | 7246 | 0 | 7246 |  |  |  | 0 | 7246 | 100% |  |  | 5434.5 | 5434.5 | 0 | 5434.5 | DN-12866
| Catalyst 9200 4*10G , Network Module | 1 | Nr | 2240 | 2240 | 0 | 2240 |  |  |  | 0 | 2240 | 100% |  |  | 1680 | 1680 | 0 | 1680 | DN-12866
| C9200 Cisco DNA Essentials, 48-Port - 3 Year Term Licenses | 1 | Nr | 1255 | 1255 | 0 | 1255 |  |  |  | 0 | 1255 | 100% |  |  | 941.25 | 941.25 | 0 | 941.25 | DN-12866
| 10GBASE-SR SFP Module, Enterprise-Class | 4 | Nr | 774 | 3096 | 0 | 3096 |  |  |  | 0 | 3096 | 100% |  |  | 2322 | 2322 | 0 | 2322 | DN-13015
| SNTC-NO RMA Catalyst 9200 48-port PoE+, Network Esse | 1 | Nr | 636 | 636 | 0 | 636 |  |  |  | 0 | 636 | 100% |  |  | 477 |  | 477 | 477 | DN-13015
| License for Additional Telephones (Excluding Handsets) | 12 | Nr | 252.85 | 3034.2 | 0 | 3034.2 |  |  |  | 0 | 3034.2 |  |  |  | 0
Installation
| Installation, Testing & Commissioning | 1 | Lot | 1450 | 1450 | 0 | 1450 |  |  |  | 0 | 1450 |  |  |  | 0
Prelims and Engineering
| Prelims and Engineering | 1 | Lot | 10000 | 10000 | 0 | 10000 |  | 100% | 100% | 10000 | 0 |  | 100% | 100% | 0
8 | Residential Public Areas Provisional Sum | 1 | Item | 184529.98 | 184529.98 | 0 | 184529.98 | 26% |  |  | 47977.7948 | 136552.1852 | 29.64% |  |  | 6720 | 24784.5 | 0 | 24784.5
IP AV Intercom
| Guard Station | 1 | Nr | 3800 | 3800 | 0 | 3800 |  |  |  | 0 | 3800 |  |  |  | 0
| Lift Lobby Entrance Panel | 5 | Nr | 3600 | 18000 | 0 | 18000 |  |  |  | 0 | 18000 |  |  |  | 0
Installation
| Installation, Testing and Commisioning | 1 | Lot | 750 | 750 | 0 | 750 |  |  |  | 0 | 750 |  |  |  | 0
Structured Cabling System
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 39 | Nr | 23.53 | 917.67 | 0 | 917.67 | 100% | 95% |  | 819.0205 | 98.6495 | 100% | 95% |  | 0
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 39 | Nr | 23.53 | 917.67 | 0 | 917.67 | 100% | 0% |  | 688.2525 | 229.4175 | 100% | 0% |  | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 39 | Nr | 25.88 | 1009.32 | 0 | 1009.32 | 100% | 0% |  | 756.99 | 252.33 | 100% | 0% |  | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 39 | Nr | 25.88 | 1009.32 | 0 | 1009.32 | 100% | 0% |  | 756.99 | 252.33 | 100% | 0% |  | 0
| 1U, 24 Port Cat6A Patch Panel, unloaded | 2 | Nr | 66 | 132 | 0 | 132 | 100% | 95% |  | 117.81 | 14.19 | 100% | 95% |  | 0
| 1U, Cable Manager | 2 | Nr | 63 | 126 | 0 | 126 | 100% | 95% |  | 112.455 | 13.545 | 100% | 95% |  | 0
| Cat6A F/UTP 23 AWG LSZH Cable | 8 | Nr | 683 | 5464 | 0 | 5464 | 100% | 95% |  | 4876.62 | 587.38 | 100% | 95% |  | 0
| Aruba 2930F 24G PoE + 4SFP + Switch | 2 | Nr | 3449 | 6898 | 0 | 6898 |  |  |  | 0 | 6898 | 100% |  |  | 5173.5 | 5173.5 | 0 | 5173.5 | DN-13092
| Aruba 10G SFP + LC SR 300m MMF Transceiver | 4 | Nr | 2240 | 8960 | 0 | 8960 |  |  |  | 0 | 8960 | 100% |  |  | 6720 | 6720 | 0 | 6720 | DN-12866
| Aruba AP-305 Wireless Access Point 802.11n/ac, 4x4:4, Dual Radio Integrated | 2 | Nr | 684 | 1368 | 0 | 1368 |  |  |  | 0 | 1368 | 100% |  |  | 1026 | 1026 | 0 | 1026 | DN-13015
| Aruba 320 Series Access Points Ceiling Tile Mount Kit | 8 | Nr | 774 | 6192 | 0 | 6192 |  |  |  | 0 | 6192 |  |  |  | 0
| Aruba Licenses | 2 | Nr | 302 | 604 | 0 | 604 |  |  |  | 0 | 604 | 100% |  |  | 453 | 453 | 0 | 453 | DN-13015
| 802.11ac W2 AP w/CA; 4*4:3; Int Ant; 2*GbE E | 8 | Nr | 1653 | 13224 | 0 | 13224 |  |  |  | 0 | 13224 | 100% |  |  | 9918 | 9918 | 0 | 9918 | DN-13015
| Aironet CISCO DNA Essentials 3 Year Term License | 8 | Nr | 249 | 1992 | 0 | 1992 |  |  |  | 0 | 1992 | 100% |  |  | 1494 | 1494 | 0 | 1494 | DN-13015
Installation
| Installation,Termination, Testing and Commisioning | 1 | Lot | 3900 | 3900 | 0 | 3900 |  | 83.33% |  | 2925 | 975 |  | 83.33% |  | 0
Background Music System
Level 4 & 23
| Loud Speaker Type (CM,CM1 & CF) | 24 | Nr | 525 | 12600 | 0 | 12600 | 100% |  |  | 9450 | 3150 | 100% |  |  | 0
| Ceiling Subwoofer (Type CS) | 1 | Nr | 910 | 910 | 0 | 910 | 100% |  |  | 682.5 | 227.5 | 100% |  |  | 0
| Loudspeaker Type (BS) | 4 | Nr | 280 | 1120 | 0 | 1120 | 100% |  |  | 840 | 280 | 100% |  |  | 0
| Wall Mounted Speaker Type (EFR) |  | Nr | 1050 | 0 | 0 | 0 |  |  |  | 0 | 0 |  |  |  | 0
| Dual USB Charger with Auxillary Input (AI 1) | 3 | Nr | 5242 | 15726 | 0 | 15726 |  |  |  | 0 | 15726 |  |  |  | 0
| Amplifier (Type 1) | 2 | Nr | 8989 | 17978 | 0 | 17978 | 100% |  |  | 13483.5 | 4494.5 | 100% |  |  | 0
| Cables and Connectors | 1 | Nr | 8400 | 8400 | 0 | 8400 | 100% | 75% |  | 7245 | 1155 | 100% | 75% |  | 0
Installation
| Installation, Testing and Commisioning | 1 | Lot | 5500 | 5500 | 0 | 5500 |  | 28.48% |  | 1409.902 | 4090.098 |  | 28.48% |  | 0 | [5 empty] | 0.25635
Level 23 Meeting Room
| Cable Cubby | 2 | Nr | 1960 | 3920 | 0 | 3920 |  |  |  | 0 | 3920 |  |  |  | 0
| VGA to HDMI Scalar | 2 | Nr | 1584 | 3168 | 0 | 3168 |  |  |  | 0 | 3168 |  |  |  | 0
| Digital Media Switcher | 1 | Nr | 22384 | 22384 | 0 | 22384 |  |  |  | 0 | 22384 |  |  |  | 0
| Blu Ray Player | 1 | Nr | 820 | 820 | 0 | 820 |  |  |  | 0 | 820 |  |  |  | 0
| Small Form Factor PC | 1 | Nr | 3592 | 3592 | 0 | 3592 |  |  |  | 0 | 3592 |  |  |  | 0
| Loud Speaker Type (CM,CM1 & CF) | 2 | Nr | 525 | 1050 | 0 | 1050 | 100% |  |  | 787.5 | 262.5 | 100% |  |  | 0
| Amplifier | 1 | Nr | 2035 | 2035 | 0 | 2035 | 100% |  |  | 1526.25 | 508.75 | 100% |  |  | 0
| Touch Panel | 1 | Nr | 3125 | 3125 | 0 | 3125 |  |  |  | 0 | 3125 |  |  |  | 0
| Docking Station | 1 | Nr | 3438 | 3438 | 0 | 3438 |  |  |  | 0 | 3438 |  |  |  | 0
| Cables and Connectors | 1 | Nr | 2000 | 2000 | 0 | 2000 | 100% |  |  | 1500 | 500 | 100% |  |  | 0
Installation
| Installation, Testing and Commisioning | 1 | Lot | 1500 | 1500 | 0 | 1500 |  |  |  | 0 | 1500 |  |  |  | 0
9 | Landscape Areas Provisional Sum | 1 | Item | 502918.47 | 502918.47 | 0 | 502918.47 | 30% |  |  | 150875.541 | 352042.929 | 50.22% |  |  | 101682 | 101455.5 | 226.5 | 101682 | DN-12866
Background Music System - Residence
Level G
| Loud Speaker Type (CM,CM1 & CF) | 9 | Nr | 525 | 4725 | 0 | 4725 | 100% |  |  | 3543.75 | 1181.25 | 100% |  |  | 0
| Amplifier (Type 1) | 1 | Nr | 8989 | 8989 | 0 | 8989 | 100% |  |  | 6741.75 | 2247.25 | 100% |  |  | 0
Level 2
| Loud Speaker Type (CM,CM1 & CF) | 9 | Nr | 525 | 4725 | 0 | 4725 | 100% |  |  | 3543.75 | 1181.25 | 100% |  |  | 0
| Amplifier (Type 1) | 2 | Nr | 8989 | 17978 | 0 | 17978 | 100% |  |  | 13483.5 | 4494.5 | 100% |  |  | 0
Level 4
| Landscape Speaker Type (E) | 30 | Nr | 895 | 26850 | 0 | 26850 | 100% |  |  | 20137.5 | 6712.5 | 100% |  |  | 0
| Amplifier (Type 1) | 4 | Nr | 8989 | 35956 | 0 | 35956 |  |  |  | 0 | 35956 |  |  |  | 0
| Amplifier (Type 2) | 1 | Nr | 8072 | 8072 | 0 | 8072 |  |  |  | 0 | 8072 |  |  |  | 0
Level 23
| Landscape Speaker Type (E) | 6 | Nr | 895 | 5370 | 0 | 5370 | 100% |  |  | 4027.5 | 1342.5 | 100% |  |  | 0
| Amplifier (Type 1) | 1 | Nr | 8989 | 8989 | 0 | 8989 |  |  |  | 0 | 8989
Headend
| Networked Digital Signal Processor I/O Expander | 1 | Nr | 9073.3333 | 9073.3333 | 0 | 9073.3333 |  |  |  | 0 | 9073.3333
| Cables, Connectors & Accessories | 11 | Nr | 683 | 7513 | 0 | 7513 | 100% | 20% |  | 5860.14 | 1652.86 | 100% | 20% |  | 0
Services
| Installation, Testing and Commisioning | 1 | Lot | 10000 | 10000 | 0 | 10000 |  | 5.556% |  | 500 | 9500 |  | 5.556% |  | 0
| Programming & Training | 1 | Lot | 4000 | 4000 | 0 | 4000 | [8 empty] | 0
Background Music System - Hotel
Level G
| Landscape Speaker Type (E) | 16 | Nr | 895 | 14320 | 0 | 14320 | 100% |  |  | 10740 | 3580 | 100% |  |  | 0
| Amplifier (Type 1) | 2 | Nr | 8989 | 17978 | 0 | 17978 | 100% |  |  | 13483.5 | 4494.5 | 100% |  |  | 0
Level 2
| Landscape Speaker Type (E) | 14 | Nr | 895 | 12530 | 0 | 12530 | 100% |  |  | 9397.5 | 3132.5 | 100% |  |  | 0
| Amplifier (Type 1) | 1 | Nr | 8989 | 8989 | 0 | 8989 | 100% |  |  | 6741.75 | 2247.25 | 100% |  |  | 0
Level 4
| Landscape Speaker Type (E) | 20 | Nr | 895 | 17900 | 0 | 17900 | 100% |  |  | 13425 | 4475 | 100% |  |  | 0
| Amplifier (Type 1) | 2 | Nr | 8989 | 17978 | 0 | 17978 |  |  |  | 0 | 17978
Level 17
| Landscape Speaker Type (E) | 10 | Nr | 895 | 8950 | 0 | 8950 | 100% |  |  | 6712.5 | 2237.5 | 100% |  |  | 0
Level 29
| Wall Speaker Type (EFR) | 10 | Nr | 1050 | 10500 | 0 | 10500 |  |  |  | 0 | 10500
| Landscape Speaker Type (E) | 2 | Nr | 895 | 1790 | 0 | 1790 | 100% |  |  | 1342.5 | 447.5 | 100% |  |  | 0
| Wireless Touch Panel | 2 | Nr | 3276 | 6552 | 0 | 6552 |  |  |  | 0 | 6552
| Docking Station | 2 | Nr | 3604 | 7208 | 0 | 7208 |  |  |  | 0 | 7208
| Auxillary Input Panel (AI) | 1 | Nr | 3276 | 3276 | 0 | 3276 |  |  |  | 0 | 3276
| Dual USB Charger with Auxillary Input (AI 1) | 1 | Nr | 5242 | 5242 | 0 | 5242 |  |  |  | 0 | 5242
| Outdoor Enclosure | 2 | Nr | 1200 | 2400 | 0 | 2400 |  |  |  | 0 | 2400
Headend
| Networked Digital Signal Processor I/O Expander | 1 | Nr | 9073.3333 | 9073.3333 | 0 | 9073.3333 |  |  |  | 0 | 9073.3333
| Control System | 1 | Nr | 4892 | 4892 | 0 | 4892 |  |  |  | 0 | 4892
| Cables, Connectors & Accessories | 14 | Nr | 683 | 9562 | 0 | 9562 | 100% | 20% |  | 7458.36 | 2103.64 | 100% | 20% |  | 0
Services
| Installation, Testing and Commisioning | 1 | Lot | 15000 | 15000 | 0 | 15000 |  | 5.556% |  | 750 | 14250 |  | 5.556% |  | 0
| Programming & Training | 1 | Lot | 4000 | 4000 | 0 | 4000 |  |  |  | 0 | 4000 |  |  |  | 0
| Structured Cabling System | [9 empty] | 0 | 0
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 90 | Nr | 23.53 | 2117.7 | 0 | 2117.7 | 100% | 90% |  | 1874.1645 | 243.5355 | 100% | 90% |  | 0
| 180◦ Cat6A Unshielded Modular Jack of RIDC | 90 | Nr | 23.53 | 2117.7 | 0 | 2117.7 | 100% | 90% |  | 1874.1645 | 243.5355 | 100% | 90% |  | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 90 | Nr | 25.88 | 2329.2 | 0 | 2329.2 | 100% | 0% |  | 1746.9 | 582.3 | 100% | 0% |  | 0
| Unshielded Cat6A Patch Cord w/T568B Wiring, 2M, LSZH | 90 | Nr | 25.88 | 2329.2 | 0 | 2329.2 | 100% | 0% |  | 1746.9 | 582.3 | 100% | 0% |  | 0
| 1U, 24 Port Cat6A Patch Panel, unloaded | 6 | Nr | 66 | 396 | 0 | 396 | 100% | 86% |  | 348.084 | 47.916 | 100% | 86% |  | 0
| 1U, Cable Manager | 6 | Nr | 63 | 378 | 0 | 378 | 100% | 85% |  | 331.695 | 46.305 | 100% | 85% |  | 0
| Cat6A F/UTP 23 AWG LSZH Cable | 18 | Nr | 683 | 12294 | 0 | 12294 | 100% | 100% |  | 11064.6 | 1229.4 | 100% | 100% |  | 0
| Installation | [9 empty] | 0 | 0
| Installation,Termination, Testing and Commisioning | 1 | Lot | 5000 | 5000 | 0 | 5000 |  | 88.89% |  | 4000 | 1000 |  | 88.89% |  | 0
Active Components
| 802.11ac W2 Value Outdoor AP, Internal Ant, M Reg Dom | 50 | Nr | 1101 | 55050 | 0 | 55050 |  |  |  | 0 | 55050 | 100% |  |  | 41287.5 | 41287.5 | 0 | 41287.5 | DN-12866
| Standard Pole/Wall Mount Kit for AP1530/1560 Series | 50 | Nr | 121 | 6050 | 0 | 6050 |  |  |  | 0 | 6050 | 100% |  |  | 4537.5 | 4537.5 | 0 | 4537.5 | DN-12866
| Aironet CISCO DNA Essentials 3 Year Term License | 50 | Nr | 249 | 12450 | 0 | 12450 |  |  |  | 0 | 12450 | 100% |  |  | 9337.5 | 9337.5 | 0 | 9337.5 | DN-12866
| SNTC-8X5XNBD 802.11ac W2 Value Outdoor AP, Internal A | 50 | Nr | 68 | 3400 | 0 | 3400 |  |  |  | 0 | 3400 | 100% |  |  | 2550 | 2550 | 0 | 2550 | DN-12866
| Catalyst 9200 24-port PoE+ , Network Essentials | 6 | Nr | 3449 | 20694 | 0 | 20694 |  |  |  | 0 | 20694 | 100% |  |  | 15520.5 | 15520.5 | 0 | 15520.5 | DN-12866, 13092
| Catalyst 9200 4*10G , Network Module | 6 | Nr | 2240 | 13440 | 0 | 13440 |  |  |  | 0 | 13440 | 100% |  |  | 10080 | 10080 | 0 | 10080 | DN-12866
| C9200 Cisco DNA Essentials, 24-Port - 3 Year Term Licenses | 6 | Nr | 684 | 4104 | 0 | 4104 |  |  |  | 0 | 4104 | 100% |  |  | 3078 | 3078 | 0 | 3078 | DN-12866, 13092
| 10GBASE-SR SFP Module, Enterprise-Class | 24 | Nr | 774 | 18576 | 0 | 18576 |  |  |  | 0 | 18576 | 100% |  |  | 13932 | 13932 | 0 | 13932 | DN-13015
| SNTC-NO RMA Catalyst 9200 24-port PoE+, Network Esse | 6 | Nr | 302 | 1812 | 0 | 1812 |  |  |  | 0 | 1812 | 100% |  |  | 1359 | 1132.5 | 226.5 | 1359 | DN-12866
| Installation | [9 empty] | 0 | 0 |  |  |  | 0
| Installation, Testing & Commissioning | 1 | Lot | 10000 | 10000 | 0 | 10000 |  |  |  | 0 | 10000 |  |  |  | 0
10 | Royal and Presidential Suit Provisional Sum | 1 | Item | 30141.6 | 30141.6 | 0 | 30141.6 | 0% |  |  | 0 | 30141.6 | 0% |  |  | 7524.7069 | 5499.7752 | 2024.9316 | 7524.7069
Horizontal Cabling for Presidential Suite
| 180° Cat6A Unshielded Modular Jack of RIDC | 45 | Nr | 23.53 | 1058.85 | 0 | 1058.85 |  |  |  | 0 | 1058.85 |  |  |  | 0 |  | 0 | 0
| 180° Cat6A Unshielded Modular Jack of RIDC | 45 | Nr | 23.53 | 1058.85 | 0 | 1058.85 |  |  |  | 0 | 1058.85 |  |  |  | 0 |  | 0 | 0 |  |  | 0.15469
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 45 | Nr | 25.88 | 1164.6 | 0 | 1164.6 |  |  |  | 0 | 1164.6 |  |  |  | 0 |  | 0 | 0
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 45 | Nr | 25.88 | 1164.6 | 0 | 1164.6 |  |  |  | 0 | 1164.6 |  |  |  | 0 |  | 0 | 0
| 1U, 24Port Cat 6A Patch Panel , unloaded | 2 | Nr | 66 | 132 | 0 | 132 |  |  |  | 0 | 132 |  |  |  | 0 |  | 0 | 0
| 1U, Cable Manager | 2 | Nr | 63 | 126 | 0 | 126 |  |  |  | 0 | 126 |  |  |  | 0 |  | 0 | 0
| Cat6A F/UTP 23 AWG LSZH cable (305) | 1 | Roll | 2732 | 2732 | 0 | 2732 |  |  |  | 0 | 2732 | 100% |  |  | 2049 | 2049 | 0 | 2049 | DN-12927
| HDMI Cable for Set-top box | 4 | Nr | 100 | 400 | 0 | 400 |  |  |  | 0 | 400 | 100% |  |  | 300 | 300 | 0 | 300 | DN-12934
| SMATV Cables | 1 | Roll | 1377.5 | 1377.5 | 0 | 1377.5 |  |  |  | 0 | 1377.5 |  |  |  | 0 | 0 | 0 | 0
| 802.11ac W2 Value Outdoor AP, Internal Ant, M Reg Dom | 2 | Nr | 1300 | 2600 | 0 | 2600 |  |  |  | 0 | 2600 | 100% |  |  | 1950 | 1950 | 0 | 1950 | DN-13015
| Standard Pole/Wall Mount Kit for AP1530/1560 Series | 2 | Nr | 153 | 306 | 0 | 306 |  |  |  | 0 | 306 |  |  |  | 0 | 0 | 0 | 0
| Aironet CISCO DNA Essentials 3 Year Term License | 2 | Nr | 297 | 594 | 0 | 594 |  |  |  | 0 | 594 | 100% |  |  | 445.5 | 445.5 | 0 | 445.5 | DN-13015
| Installation, Termination, Testing & Commissioning | 1 | LOT | 6200 | 6200 | 0 | 6200 |  |  |  | 0 | 6200 |  |  |  | 0 |  | 0 | 0
| Engineering Works | 1 | LOT | 500 | 500 | 0 | 500 |  |  |  | 0 | 500 |  |  |  | 0 |  | 0 | 0
Horizontal Cabling for Royal Suite
| 180° Cat6A Unshielded Modular Jack of RIDC | 35 | Nr | 23.53 | 823.55 | 0 | 823.55 |  |  |  | 0 | 823.55 |  |  |  | 0 |  | 0 | 0
| 180° Cat6A Unshielded Modular Jack of RIDC | 35 | Nr | 23.53 | 823.55 | 0 | 823.55 |  |  |  | 0 | 823.55 |  |  |  | 0 |  | 0 | 0
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 35 | Nr | 25.88 | 905.8 | 0 | 905.8 |  |  |  | 0 | 905.8 |  |  |  | 0 |  | 0 | 0
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 35 | Nr | 25.88 | 905.8 | 0 | 905.8 |  |  |  | 0 | 905.8 |  |  |  | 0 |  | 0 | 0
| 1U, 24Port Cat 6A Patch Panel , unloaded | 2 | Nr | 66 | 132 | 0 | 132 |  |  |  | 0 | 132 |  |  |  | 0 |  | 0 | 0
| 1U, Cable Manager | 2 | Nr | 63 | 126 | 0 | 126 |  |  |  | 0 | 126 |  |  |  | 0 |  | 0 | 0
| Cat6A F/UTP 23 AWG LSZH cable (305) | 1 | Roll | 2049 | 2049 | 0 | 2049 |  |  |  | 0 | 2049 | 100% |  |  | 1536.75 | 1536.75 | 0 | 1536.75 | DN-12927
| HDMI Cable for Set-top box | 3 | Nr | 100 | 300 | 0 | 300 |  |  |  | 0 | 300 | 100% |  |  | 225 | 225 | 0 | 225 | DN-12934
| SMATV Cables | 1 | Roll | 1377.5 | 1377.5 | 0 | 1377.5 |  |  |  | 0 | 1377.5 |  |  |  | 0 | 0 | 0 | 0
| 802.11ac W2 Value Outdoor AP, Internal Ant, M Reg Dom | 2 | Nr | 1300 | 2600 | 0 | 2600 |  |  |  | 0 | 2600 | 100% |  |  | 1950 |  | 1950 | 1950 | DN-13015
| Standard Pole/Wall Mount Kit for AP1530/1560 Series | 2 | Nr | 153 | 306 | 0 | 306 |  |  |  | 0 | 306 |  |  |  | 0 | 0 | 0 | 0
| Aironet CISCO DNA Essentials 3 Year Term License | 2 | Nr | 297 | 594 | 0 | 594 |  |  |  | 0 | 594 | 100% |  |  | 445.5 |  | 445.5 | 445.5 | DN-13015
| Installation, Termination, Testing & Commissioning | 1 | LOT | 4800 | 4800 | 0 | 4800 |  |  |  | 0 | 4800 |  |  |  | 0 | 0 | 0 | 0
| Engineering Works | 1 | LOT | 500 | 500 | 0 | 500 |  |  |  | 0 | 500 |  |  |  | 0 | 0 | 0 | 0
| Discout | 1 | LOT | -5516 | -5516 | 0 | -5516 |  |  |  | 0 | -5516 |  |  |  | -1377.0431 | -1006.4748 | -370.5684 | -1377.0431
11 | Gym area Provisional Sum | 1 | Item | 12550.76 | 12550.76 | 0 | 12550.76 | 20% |  |  | 2510.152 | 10040.608 | 30.83% |  |  | 1358.62 | 5835.1408 | 182.5594 | 6017.7002
| 180° Cat6A Unshielded Modular Jack of RIDC (28-10) | 18 | Nr | 23.53 | 423.54 | 0 | 423.54 | 100% | 20% |  | 330.3612 | 93.1788 | 100% | 20% |  | 0
| 180° Cat6A Unshielded Modular Jack of RIDC | 18 | Nr | 23.53 | 423.54 | 0 | 423.54 | 100% | 20% |  | 330.3612 | 93.1788 | 100% | 20% |  | 0
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 18 | Nr | 25.88 | 465.84 | 0 | 465.84 | 100% | 0% |  | 349.38 | 116.46 | 100% | 0% |  | 0
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 18 | Nr | 25.88 | 465.84 | 0 | 465.84 | 100% | 0% |  | 349.38 | 116.46 | 100% | 0% |  | 0
| 1U, 24Port Cat 6A Patch Panel , unloaded | 1 | Nr | 66 | 66 | 0 | 66 | 100% | 20% |  | 51.48 | 14.52 | 100% | 20% |  | 0
| 1U, Cable Manager | 1 | Nr | 63 | 63 | 0 | 63 | 100% | 20% |  | 49.14 | 13.86 | 100% | 20% |  | 0
| Cat6A F/UTP 23 AWG LSZH cable (305) | 1 | Roll | 2732 | 2732 | 0 | 2732 | 100% | 30% |  | 2171.94 | 560.06 | 100% | 30% |  | 0
| Catalyst 9200 24-port PoE+, Network Essentials | 1 | Nr | 4138.8 | 4138.8 | 0 | 4138.8 | [5 empty] | 100% |  |  | 3104.1 | 3104.1 | 0 | 3104.1 | DN-13092
| Catalyst 9200 4 x 10G Network Module | 1 | Nr | 2697 | 2697 | 0 | 2697 | [5 empty] | 100% |  |  | 2022.75 | 2022.75 | 0 | 2022.75 | DN-12866
| C9200 Cisco DNA Essentials, 24-port - 3 Year Term License | 1 | Nr | 820 | 820 | 0 | 820 | [5 empty] | 100% |  |  | 615 | 615 | 0 | 615 | DN-13092
| 10GBASE-SR SFP Module, Enterprise-Class | 4 | Nr | 982 | 3928 | 0 | 3928 | [5 empty] | 100% |  |  | 2946 | 2946 | 0 | 2946 | DN-13015
| SNTC-NO RMA Catalyst 9200 24-port PoE+, Network Esse | 1 | Nr | 362.4 | 362.4 | 0 | 362.4 | [5 empty] | 100% |  |  | 271.8 |  | 271.8 | 271.8 | DN-13015
| Installation, Termination, Testing & Commissioning | 1 | LOT | 2100 | 2100 | 0 | 2100 |  | 5.556% |  | 105 | 1995 |  | 5.556% |  | 0
| Discount | 1 | LOT | -6135.1986 | -6135.1986 | 0 | -6135.1986 |  |  |  | -1227.04 | -4908.1586 |  |  |  | -2941.9498 | -2852.7092 | -89.2406 | -2941.9498
| ELV PS WORKS |  |  |  | 1526037.63 | 0 | 1526037.63 | 41.06% |  |  | 626607.4462 | 899430.1838 | 14.73% |  |  | 132497.1263 | 178950.168 |  | 189179.3995
WA-M131 | HDMI Cables for IPTV/SMATV at L7 to L16 |  |  |  | 28400 | [6 empty] | 28400 | 26.67% |  |  | 7575 | 7575 | 0 | 7575
| HDMI Cables for Set top Box | 154 | Roll | 100 | 15400 |  | 15400 |  |  |  |  | 15400 | 65.58% |  |  | 7575 | 7575 | 0 | 7575 | DN-13109
| Installation of HDMI Cables | 1 | Lot | 13000 | 13000 |  | 13000 |  |  |  |  | 13000
WA-M131 | Changes in Landscape requirement at L17 and L29 |  |  |  | 33299.2 | [6 empty] | 33299.2 | 31.52% |  |  | 10496.52 | 10224.6 | 271.92 | 10496.52
| Wall Speaker EFR | 1 | Nr | 1050 | 1050 |  | 1050 |  |  |  |  | 1050
| Volume Controller (BGM) | 3 | Nr | 2913 | 8739 |  | 8739 |  |  |  |  | 8739
| Installation, testing and commissioning | 1 | Lot | 500 | 500 |  | 500 |  |  |  |  | 500
| Programming and training | 1 | Lot | 100 | 100 |  | 100 |  |  |  |  | 100
| 180° Cat6A Unshielded Modular Jack of RIDC | 12 | Nr | 23.53 | 282.36 |  | 282.36 |  |  |  |  | 282.36
| 180° Cat6A Unshielded Modular Jack of RIDC | 12 | Nr | 23.53 | 282.36 |  | 282.36 |  |  |  |  | 282.36
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 12 | Nr | 25.88 | 310.56 |  | 310.56 |  |  |  |  | 310.56
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 12 | Nr | 25.88 | 310.56 |  | 310.56 |  |  |  |  | 310.56
| 1U, 24Port Cat 6A Patch Panel , unloaded | 1 | Nr | 66 | 66 |  | 66 |  |  |  |  | 66
| 1U, Cable Manager | 1 | Nr | 63 | 63 |  | 63 |  |  |  |  | 63
| Cat6A F/UTP 23 AWG LSZH cable | 3 | Lot | 683 | 2049 |  | 2049 |  |  |  |  | 2049 | 100% |  |  | 1536.75 | 1536.75 | 0 | 1536.75 | DN-12927
| Installation, Termination, Testing & Commissioning | 1 | Lot | 3600 | 3600 |  | 3600 |  |  |  |  | 3600
| Catalyst 9200 24-port PoE+ , Network Essentials | 1 | Lot | 4138.8 | 4138.8 |  | 4138.8 |  |  |  |  | 4138.8 | 100% |  |  | 3104.1 | 3104.1 | 0 | 3104.1 | DN-13092
| C9200 Network Essentials, 24-port License | 1 | Lot |  | Included |  | Included |  |  |  |  | Included
| Catalyst 9200 4*10G , Network Module | 1 | Lot | 2697 | 2697 |  | 2697 |  |  |  |  | 2697 | 100% |  |  | 2022.75 | 2022.75 | 0 | 2022.75 | DN-13092
| UK AC Type A Power cable | 1 | Lot |  | Included |  | Included |  |  |  |  | Included
| Config 5 Power supply blank | 1 | Lot |  | Included |  | Included |  |  |  |  | Included
| C9200 Cisco DNA Essentials, 24-Port Licenses | 1 | Lot |  | Included |  | Included |  |  |  |  | Included
| C9200 Cisco DNA Essentials, 24-Port 3 year term Licenses | 1 | Lot | 820 | 820 |  | 820 |  |  |  |  | 820 | 100% |  |  | 615 | 615 | 0 | 615 | DN-13015
| Network plug-n-play license for zero-touch device development | 1 | Lot |  | Included |  | Included |  |  |  |  | Included
| 10GBASE-SR SFP Module, Enterprise-Class | 1 | Lot | 3928 | 3928 |  | 3928 |  |  |  |  | 3928 | 100% |  |  | 2946 | 2946 | 0 | 2946 | DN-13015
| SNTC-NO RMA Catalyst 9200 24-port PoE+, Network Esse | 1 | Lot | 362.56 | 362.56 |  | 362.56 |  |  |  |  | 362.56 | 100% |  |  | 271.92 |  | 271.92 | 271.92 | DN-13015
| Installation, Testing & Commissioning | 1 | Lot | 4000 | 4000 |  | 4000 |  |  |  |  | 4000
WA-M131 | Changes in Landscape requirement at GF, L2 and L4 |  |  |  | 9219 | [6 empty] | 9219 | 27.78% |  |  | 2561.25 | 2561.25 | 0 | 2561.25
| 180° Cat6A Unshielded Modular Jack of RIDC | 22 | Nr | 23.53 | 517.66 |  | 517.66 |  |  |  |  | 517.66
| 180° Cat6A Unshielded Modular Jack of RIDC | 22 | Nr | 23.53 | 517.66 |  | 517.66 |  |  |  |  | 517.66
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 22 | Nr | 25.88 | 569.36 |  | 569.36 |  |  |  |  | 569.36
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 22 | Nr | 25.88 | 569.36 |  | 569.36 |  |  |  |  | 569.36
| 1U, 24Port Cat 6A Patch Panel , unloaded | 1 | Nr | 66 | 66 |  | 66 |  |  |  |  | 66
| 1U, Cable Manager | 1 | Nr | 63 | 63 |  | 63 |  |  |  |  | 63
| Cat6A F/UTP 23 AWG LSZH cable | 1 | Lot | 3415 | 3415 |  | 3415 |  |  |  |  | 3415 | 100% |  |  | 2561.25 | 2561.25 | 0 | 2561.25 | DN-12927
| Installation, Termination, Testing & Commissioning | 1 | Lot | 3500.96 | 3500.96 |  | 3500.96 |  |  |  |  | 3500.96
WA-M131 | Additional Data Points at Front office |  |  |  | 36102 | [6 empty] | 36102 | 45.07% |  |  | 16270.65 | 15743.4 | 527.25 | 16270.65
| 180° Cat6A Unshielded Modular Jack of RIDC | 40 | Nr | 23.53 | 941.2 |  | 941.2 |  |  |  |  | 941.2
| 180° Cat6A Unshielded Modular Jack of RIDC | 40 | Nr | 23.53 | 941.2 |  | 941.2 |  |  |  |  | 941.2
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 40 | Nr | 25.88 | 1035.2 |  | 1035.2 |  |  |  |  | 1035.2
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 40 | Nr | 25.88 | 1035.2 |  | 1035.2 |  |  |  |  | 1035.2
| 1U, 24Port Cat 6A Patch Panel , unloaded | 2 | Nr | 66 | 132 |  | 132 |  |  |  |  | 132
| 1U, Cable Manager | 2 | Nr | 63 | 126 |  | 126 |  |  |  |  | 126
| Cat6A F/UTP 23 AWG LSZH Cable | 1 | Lot | 6830 | 6830 |  | 6830 |  |  |  |  | 6830 | 100% |  |  | 5122.5 | 5122.5 | 0 | 5122.5 | DN-12927
| Catalyst 9200 48-port PoE+ , Network Essentials | 1 | Lot | 8723 | 8723 |  | 8723 |  |  |  |  | 8723 | 100% |  |  | 6542.25 | 6542.25 | 0 | 6542.25 | DN-13092
| Catalyst 9200 4*10G , Network Module | 1 | Lot | 2697 | 2697 |  | 2697 |  |  |  |  | 2697
| C9200 Cisco DNA Essentials, 48-Port 3 year term Licenses | 1 | Lot | 1510.2 | 1510.2 |  | 1510.2 |  |  |  |  | 1510.2 | 100% |  |  | 1132.65 | 1132.65 | 0 | 1132.65 | DN-13092
| 10GBASE-SR SFP Module, Enterprise-Class | 4 | Lot | 982 | 3928 |  | 3928 |  |  |  |  | 3928 | 100% |  |  | 2946 | 2946 | 0 | 2946 | DN-13015
| SNTC-NO RMA Catalyst 9200 48-port PoE+, Network Esse | 1 | Lot | 703 | 703 |  | 703 |  |  |  |  | 703 | 100% |  |  | 527.25 |  | 527.25 | 527.25 | DN-13015
| Installation, Termination, Testing & Commissioning | 1 | Lot | 7500 | 7500 |  | 7500 |  |  |  |  | 7500
WA-M131 | Additional DTAS at L29 Gym Area |  |  |  | 6749 | [6 empty] | 6749 | 8.89% |  |  | 600 | 600 | 0 | 600
| Pull Cord | 1 | Nr | 126 | 126 |  | 126 |  |  |  |  | 126
| Overdoor Sounder | 1 | Nr | 574 | 574 |  | 574 |  |  |  |  | 574
| Hideaway panel | 1 | Nr | 996 | 996 |  | 996 |  |  |  |  | 996
| Reset Button | 1 | Nr | 504 | 504 |  | 504 |  |  |  |  | 504
| Integration with ACS/I/O Board | 1 | Nr | 1190 | 1190 |  | 1190 |  |  |  |  | 1190
| Battery | 1 | Nr | 59 | 59 |  | 59 |  |  |  |  | 59
| Installation, Termination, Testing & Commissioning | 1 | Nr | 2500 | 2500 |  | 2500 |  |  |  |  | 2500
| 8 Core Cable | 1 | Nr | 800 | 800 |  | 800 |  |  |  |  | 800 | 100% |  |  | 600 | 600 | 0 | 600 | DN-12508
WA-M131 | Change of BGM Volume Controller |  |  |  | 18125 | [6 empty] | 18125 | 182.6% |  |  | 33097.5 | 0 | 33097.5 | 33097.5
| 5" Wall mount touch screen | 10 | Nr | 4413 | 44130 |  | 44130 |  |  |  |  | 44130 | 100% |  |  | 33097.5 |  | 33097.5 | 33097.5 | DN-13136
| Volume controoler and source selector | -10 | Nr | 2913 | -29130 |  | -29130 |  |  |  |  | -29130
| Installation, Programming, Testing & Commissioning | 1 | Nr | 3125 | 3125 |  | 3125 |  |  |  |  | 3125
WA-M139 | Ballroom 1 |  |  |  | 227878.97 | [6 empty] | 227878.97 | 1.809% |  |  | 4122 | 0 | 4122 | 4122
| Motorized Projection Screen 222" 16:10 Matte White | 1 | Nr | 15900 | 15900 |  | 15900 |  |  |  |  | 15900
| Professional Installation Projector 9,400 ANSI Lumens, WUXGA, 1-DLP, Laser | 1 | Nr | 58500 | 58500 |  | 58500 |  |  |  |  | 58500
| Projector Scissor Lift 3m drop, 710x640mm, 45Kg Capacity, Incl: - LV Relay control, Wall Manual Override - Closure Panel & Housing to hide cables | 1 | Nr | 16764 | 16764 |  | 16764 |  |  |  |  | 16764
| Video & Control Scaler Receiver | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Wall Plate Video Transmiter | 2 | Nr | 3560 | 7120 |  | 7120 |  |  |  |  | 7120
| Wall Plate & Back box | 2 | Nr | 1765 | 3530 |  | 3530 |  |  |  |  | 3530
| Wall Plate Audio Connectors | 4 | Nr | 36 | 144 |  | 144 |  |  |  |  | 144
| 2Ch Dante Input Expander | 2 | Nr | 3501 | 7002 |  | 7002 |  |  |  |  | 7002
| 2Ch Dante Output Expander | 2 | Nr | 3501 | 7002 |  | 7002 |  |  |  |  | 7002
| Ceiling Loudspeaker | 12 | Nr | 2144 | 25728 |  | 25728 |  |  |  |  | 25728
| Ceiling Subwoofer | 3 | Nr | 1832 | 5496 |  | 5496 |  |  |  |  | 5496 | 100% |  |  | 4122 |  | 4122 | 4122 | DN-13136
| Column Array Loudspeaker Type H Recessed In-Wall Self-Powered Steerable | 2 | Nr | 25829 | 51658 |  | 51658 |  |  |  |  | 51658
| High Level DIN Rail Junction Box | 1 | Nr | 9380.97 | 9380.97 |  | 9380.97 |  |  |  |  | 9380.97
| Lavalier Lapel Wireless Microphone |  | Nr | 1695 | 0 |  | 0 |  |  |  |  | 0
| Handheld Wireless Microphone |  | Nr | 1239 | 0 |  | 0 |  |  |  |  | 0
| Microphone Antenna |  | Nr | 2785 | 0 |  | 0 |  |  |  |  | 0
| 9.7" Wireless Touch Control Panel | 1 | Nr | 1948 | 1948 |  | 1948 |  |  |  |  | 1948
| Wall Mount Charging Locakable Dock | 1 | Nr | 3182 | 3182 |  | 3182 |  |  |  |  | 3182
| 4 Relay Control Expander | 2 | Nr | 1070 | 2140 |  | 2140 |  |  |  |  | 2140
| Cables and Connectors | 1 | Nr | 8824 | 8824 |  | 8824 |  |  |  |  | 8824
WA-M139 | Ballroom 2 |  |  |  | 290277.97 | [6 empty] | 290277.97 | 0% |  |  | 0 | 0 | 0 | 0
| Motorized Projection Screen 255" 16:10 Matte White | 1 | Nr | 22151 | 22151 |  | 22151 |  |  |  |  | 22151
| Professional Installation Projector 12,000 ANSI Lumens, WUXGA, 1-DLP, Laser | 1 | Nr | 76532 | 76532 |  | 76532 |  |  |  |  | 76532
| Projector Scissor Lift 3m drop, 710x640mm, 45Kg Capacity | 1 | Nr | 16764 | 16764 |  | 16764 |  |  |  |  | 16764
| Video & Control Scaler Receiver | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Wall Plate Video Transmiter | 4 | Nr | 3560 | 14240 |  | 14240 |  |  |  |  | 14240
| Wall Plate & Back box | 4 | Nr | 1765 | 7060 |  | 7060 |  |  |  |  | 7060
| Wall Plate Audio Connectors | 8 | Nr | 36 | 288 |  | 288 |  |  |  |  | 288
| 2Ch Dante Input Expander | 4 | Nr | 3501 | 14004 |  | 14004 |  |  |  |  | 14004
| 2Ch Dante Output Expander | 2 | Nr | 3501 | 7002 |  | 7002 |  |  |  |  | 7002
| Ceiling Loudspeaker Type L | 12 | Nr | 2144 | 25728 |  | 25728 |  |  |  |  | 25728
| Ceiling Subwoofer Type J | 3 | Nr | 1832 | 5496 |  | 5496 |  |  |  |  | 5496
| Column Array Loudspeaker Type G Recessed In-Wall Self-Powered Steerable | 2 | Nr | 35989 | 71978 |  | 71978 |  |  |  |  | 71978
| High Level DIN Rail Junction Box | 1 | Nr | 9380.97 | 9380.97 |  | 9380.97 |  |  |  |  | 9380.97
| Lavalier Lapel Wireless Microphone |  | Nr | 1695 | 0 |  | 0 |  |  |  |  | 0
| Handheld Wireless Microphone |  | Nr | 1239 | 0 |  | 0 |  |  |  |  | 0
| Microphone Antenna |  | Nr | 2785 | 0 |  | 0 |  |  |  |  | 0
| 9.7" Wireless Touch Control Panel | 1 | Nr | 1948 | 1948 |  | 1948 |  |  |  |  | 1948
| Wall Mount Charging Locakable Dock | 1 | Nr | 3182 | 3182 |  | 3182 |  |  |  |  | 3182
| 4 Relay Control Expander | 2 | Nr | 1070 | 2140 |  | 2140 |  |  |  |  | 2140
| Cables and Connectors | 1 | Nr | 8824 | 8824 |  | 8824 |  |  |  |  | 8824
WA-M139 | IT Systems & Installation |  |  |  | 172262.12 | [6 empty] | 122675.6912 | 12.54% |  |  | 15382.5 | 0 | 15382.5 | 15382.5
| Ball Room Structured cabling | 1 | Lot | 51321.12 | 51321.12 |  | 51321.12 |  |  |  | 37977.6288 | 13343.4912
| Catalyst 9200 48-port PoE+, Network Essentials & Accs | 1 | Lot | 27737 | 27737 |  | 27737 |  |  |  |  | 27737
| 802.11ac W2 AP w/CA; 4x4:3; Int Ant; 2xGbE E | 12 | Lot | 2930 | 35160 |  | 35160 |  |  |  |  | 35160 | 58.33% |  |  | 15382.5 |  | 15382.5 | 15382.5 | DN-13015
| Ball Room Structured cabling | 1 | Lot | 58044 | 58044 |  | 58044 |  |  |  | 11608.8 | 46435.2
WA-M139 | Board Room |  |  |  | 28684 | [6 empty] | 28684 | 0% |  |  | 0 | 0 | 0 | 0
| 98" LED Screen |  | Nr |  | 0 |  | 0 |  |  |  |  | 0
| Video & Control Scaling Receiver | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Floor/Wall Plate Video Transmiter | 2 | Nr | 3560 | 7120 |  | 7120 |  |  |  |  | 7120
| Ceiling Loudspeaker Type D | 6 | Nr | 969 | 5814 |  | 5814 |  |  |  |  | 5814
| Custom Engraved Floor Plate [AVP-1] | 2 | Nr | 1177 | 2354 |  | 2354 |  |  |  |  | 2354
| 9.7" Wireless Touch Control Panel | 1 | Nr | 1948 | 1948 |  | 1948 |  |  |  |  | 1948
| Wall Mount Dock | 1 | Nr | 3182 | 3182 |  | 3182 |  |  |  |  | 3182
| Cables and Connectors | 1 | Nr | 4706 | 4706 |  | 4706 |  |  |  |  | 4706
WA-M139 | Meeting Room-1 |  |  |  | 20829 | [6 empty] | 20829 | 0% |  |  | 0 | 0 | 0 | 0
| 85" LED Screen |  | Nr |  | 0 |  | 0 |  |  |  |  | 0
| Video & Control Scaling Receiver | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Floor/Wall Plate Video Transmiter | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Ceiling Loudspeaker Type D | 4 | Nr | 969 | 3876 |  | 3876 |  |  |  |  | 3876
| Custom Engraved Floor Plate [AVP-1] | 1 | Nr | 1177 | 1177 |  | 1177 |  |  |  |  | 1177
| 9.7" Wireless Touch Control Panel | 1 | Nr | 1948 | 1948 |  | 1948 |  |  |  |  | 1948
| Wall Mount Dock | 1 | Nr | 2002 | 2002 |  | 2002 |  |  |  |  | 2002
| Cables and Connectors | 1 | Nr | 4706 | 4706 |  | 4706 |  |  |  |  | 4706
WA-M139 | Meeting Room-2 |  |  |  | 63009.604 | [6 empty] | 63009.604 | 0% |  |  | 0 | 0 | 0 | 0
| 85" LED Screen |  | Nr |  | 0 |  | 0 |  |  |  |  | 0
| Video & Control Scaling Receiver | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Floor/Wall Plate Video Transmiter | 1 | Nr | 3560 | 3560 |  | 3560 |  |  |  |  | 3560
| Ceiling Loudspeaker Type D | 4 | Nr | 969 | 3876 |  | 3876 |  |  |  |  | 3876
| Custom Engraved Floor Plate [AVP-1] | 1 | Nr | 1177 | 1177 |  | 1177 |  |  |  |  | 1177
| 9.7" Wireless Touch Control Panel | 1 | Nr | 1948 | 1948 |  | 1948 |  |  |  |  | 1948
| Wall Mount Dock | 1 | Nr | 2002 | 2002 |  | 2002 |  |  |  |  | 2002
| Cables and Connectors | 1 | Nr | 4706 | 4706 |  | 4706 |  |  |  |  | 4706
| Installation, Programming., Testing, Commissioning & Training | 1 | Lot | 42180.604 | 42180.604 |  | 42180.604 |  |  |  |  | 42180.604
WA-M139 | BGM - Internal Speakers |  |  |  | 40025.064 | [6 empty] | 40025.064 | 0% |  |  | 0 | 0 | 0 | 0
| Loudspeaker Type (CM, CM1 & CF) | 27 | Nr | 960 | 25920 |  | 25920 |  |  |  |  | 25920
| Cables and Connectors | 1 | Nr | 6565 | 6565 |  | 6565 |  |  |  |  | 6565
| Installation,Testing and Commisioning | 1 | Lot | 7540.064 | 7540.064 |  | 7540.064 |  |  |  |  | 7540.064
WA-M139 | Additional Data Point for SH |  |  |  | 50290.36 | [6 empty] | 40444.1 | 20.35% |  |  | 8228.805 | 0 | 8228.805 | 8228.805
| 180° Cat6A Unshielded Modular Jack of RIDC (28-10) | 48 | Nr | 23.53 | 1129.44 |  | 1129.44 |  |  |  |  | 1129.44
| 180° Cat6A Unshielded Modular Jack of RIDC | 48 | Nr | 23.53 | 1129.44 |  | 1129.44 |  |  |  |  | 1129.44
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 48 | Nr | 25.88 | 1242.24 |  | 1242.24 |  |  |  |  | 1242.24
| Unshielded Cat. 6A Patch Cord w/ T568B Wiring, 2M, LSZH, Blue | 48 | Nr | 25.88 | 1242.24 |  | 1242.24 |  |  |  |  | 1242.24
| 1U, 24Port Cat 6A Patch Panel , unloaded | 2 | Nr | 66 | 132 |  | 132 |  |  |  |  | 132
| 1U, Cable Manager | 2 | Nr | 63 | 126 |  | 126 |  |  |  |  | 126
| Cat6A F/UTP 23 AWG LSZH cable | 1 | Nr | 8879 | 8879 |  | 8879 |  |  |  | 8346.26 | 532.74 | 100% |  |  | 399.555 |  | 399.555 | 399.555 | DN-13136
| Catalyst 9200 48-port PoE+, Network Essentials | 1 | Nr | 14109 | 14109 |  | 14109 |  |  |  |  | 14109
| Catalyst 9200 4 x 10G Network Module | 1 | Nr | 4362 | 4362 |  | 4362 |  |  |  |  | 4362
| C9200 Cisco DNA Essentials, 48-port - 3 Year Term License | 1 | Nr | 2443 | 2443 |  | 2443 |  |  |  |  | 2443 | 100% |  |  | 1832.25 |  | 1832.25 | 1832.25 | DN-13092
| 10GBASE-SR SFP Module, Enterprise-Class | 4 | Nr | 1588 | 6352 |  | 6352 |  |  |  |  | 6352 | 100% |  |  | 4764 |  | 4764 | 4764 | DN-13015
| SNTC-NO RMA Catalyst 9200 48-port PoE+, Network Esse | 1 | Nr | 1644 | 1644 |  | 1644 |  |  |  |  | 1644 | 100% |  |  | 1233 |  | 1233 | 1233 | DN-13015
| Installation, Termination, Testing & Commissioning | 1 | Lot | 7500 | 7500 |  | 7500 |  |  |  | 1500 | 6000
| ELV WORK APPROVALS | [10 empty] | 965718.5992 |  |  |  | 98334.225 | 36704.25 |  | 98334.225