## KCE-PC 11
PAYMENT CERTIFICATE
PROJECT: |  | Plot 18, BUSINESS BAY DUBAI, UAE |  | Certificate No: | KCE-11
|  |  |  | Date of Certificate : | 2023-01-23
| Issued By : | Employer's Representative |  | Invoice No. | Khansaheb IPA -11
|  | Omniyat Concept Investments LLC |  | Cost Code: | D167
Dubai, UAE
|  |  |  | Contract Start Date : | 2022-03-31
|  |  |  | Date of Application: | 2023-01-06 |  | 2023-01-06
| Employer : | Sky Palaces Real Estate Development LLC |  | Period for Works Certified: | December 2022 |  | 2023-01-16
|  | PO Box 12501 |  | Payment Due Date : | 2023-01-27
|  | Dubai, UAE |  | Certificate Currency: | AED
| Contractor : | Khansaheb Civil Engineering LLC
|  | P.O. Box 2716 |  | VALUE COMPLETE (BASED
|  | Dubai, UAE |  | ON EFC VALUE) | 66.83%
|  |  |  | CERTIFIED FOR PAYMENT | 77.63%
(BASED ON EFC VALUE)
|  |  |  | Currency | AED
|  |  |  | Estimated Contract Price | 194951735
|  |  |  | Variations | 0
|  |  |  | Estimated Final Contract (EFC) Value | 194951735
| (A) Contract Advance Payment in this certificate |  |  |  | 21059022.8797
| Total Advance Payment |  | 23638476.02
| Advance Payment Recovery - Refer Annexure 11 |  | 2579453.1403
| Advance Payment in this certificate |  | 21059022.8797
| (B) Value of Works Completed To Date (Valuation of Work In Place) - Refer Annexure-1 |  |  |  | 130291639.3628
| (C=A+B) Certified Value - Cumulative |  |  |  | 151350662.2425 | 139350662.2425
s
| (D) LESS Retention (10%) - Refer Annexure 10 |  |  |  | -5896303.4575
| (E) LESS: Deferred (0%) |  |  |  | 0
| (F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 145454358.785
| (G) LESS Previous Certified Value - Refer Annexure 12 |  |  |  | -125482803.906
| (H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  | AED | 19971554.879
| (I) 5% (VAT ON NETT PAYMENT) |  |  |  | 998577.744
| (J) 5% (VAT ON ADVANCE RECOVERY) |  |  |  | 0
(K=H+I+J) NET AMOUNT CERTIFIED FOR PAYMENT INCLUDING VAT (CHANGE OVER LAST CERTIFICATE): |  |  |  | AED | 20970132.623
Notes: |  | This IPC is issued for the KHANSAHAB IPA No.11
Payment Terms: |  | The Payment shall be released within 30 days of the IPA
EMPLOYER REPRESENTATIVE CERTIFICATION
We certify that the above to be true and correct.
| For on behalf of OMNIYAT CONCEPT INVESTMENTS LLC |  |  |  | DATE
APPROVAL BY EMPLOYER
Employer's approval of the net amount certified
| For on behalf of SKY PALACES REAL ESTATE DEVELOPMENT LLC |  |  |  | DATE

## KCE-PC 11 INT
PAYMENT CERTIFICATE
PROJECT: |  | Plot 18, BUSINESS BAY DUBAI, UAE |  | Certificate No: | KCE-11
|  |  |  | Date of Certificate : | 2023-01-23
| Issued By : | Employer's Representative |  | Invoice No. | Khansaheb IPA -11
|  | Omniyat Concept Investments LLC |  | Cost Code: | D167
Dubai, UAE
|  |  |  | Contract Start Date : | 2022-03-31
|  |  |  | Date of Application: | 2023-01-06
| Employer : | Sky Palaces Real Estate Development LLC |  | Period for Works Certified: | December 2022
|  | PO Box 12501 |  | Payment Due Date : | 2023-01-27
|  | Dubai, UAE |  | Certificate Currency: | AED
| Contractor : | Khansaheb Civil Engineering LLC
|  | P.O. Box 2716 |  | VALUE COMPLETE (BASED
|  | Dubai, UAE |  | ON EFC VALUE) | 66.83%
|  |  |  | CERTIFIED FOR PAYMENT | 77.63%
(BASED ON EFC VALUE)
|  |  |  | Currency | AED
|  |  |  | Estimated Contract Price | 194951735
|  |  |  | Variations | 0
|  |  |  | Estimated Final Contract (EFC) Value | 194951735
| (A) Contract Advance Payment in this certificate |  |  |  | 21059022.8797
| Total Advance Payment |  | 23638476.02
| Advance Payment Recovery - Refer Annexure 11 |  | 2579453.1403
| Advance Payment in this certificate |  | 21059022.8797
| (B) Value of Works Completed To Date (Valuation of Work In Place) - Refer Annexure-1 |  |  |  | 130291639.3628
| (C=A+B) Certified Value - Cumulative |  |  |  | 151350662.2425
| (D) LESS Retention (10%) - Refer Annexure 10 |  |  |  | -5896303.4575
| (E) LESS: Deferred (0%) |  |  |  | 0
| (F=C-D-E) Net Certificate Value After Retention & Advances |  |  |  | 145454358.785
| (G) LESS Previous Certified Value - Refer Annexure 12 |  |  |  | -125482803.906
| (H=F-G) NET AMOUNT CERTIFIED FOR PAYMENT (CHANGE OVER LAST CERTIFICATE): |  |  | AED | 19971554.879
| (I) 5% (VAT ON NETT PAYMENT) |  |  |  | 998577.744
| (J) 5% (VAT ON ADVANCE RECOVERY) |  |  |  | 0
(K=H+I+J) NET AMOUNT CERTIFIED FOR PAYMENT INCLUDING VAT (CHANGE OVER LAST CERTIFICATE): |  |  |  | AED | 20970132.623
Notes: |  | This IPC is issued for the KHANSAHAB IPA No.11
Payment Terms: |  | The Payment shall be released within 30 days of the IPA
INTERNAL CERTIFICATION ONLY
We certify that the above to be true and correct for and on behalf of OMNIYAT CONCEPT INVESTMENTS LLC
| Christopher Thomas |  |  | Peter Stephenson
| Commercial Director |  |  | Managing Director - Development
SKY PALACES REAL ESTATE DEVELOPMENT LLC approval to proceed the net amount certified for approval
| Ishan Garga |  |  | Mahdi Amjad
| Managing Director - Corporate Finance & Investments |  |  | Executive Chairman

## Annexure-1 Est. Contract Price
Sky Palaces Real Estate Development LLC
INTERIM PAYMENT CERTIFICATE-Annexure 1
Project: Plot - 18 |  |  |  |  | Certificate Date: |  | 2023-01-23
Contractor :Khansaheb Civil Engineering LLC |  |  |  |  | Certificate No: |  | KCE-11 |  |  | KCE
Contract :Main Works |  |  |  |  | Currency: |  | AED | [6 empty] | Material | Labour | Plant | Sub | Com' Orders | Staff | OH | Debts
Description of Works | Estimated Contract Price | Current Awarded Amount | Previously Certified | Certified This Month | Certified to Date |  |  |  | Annexure No. | Claim |  |  | Staff - Civil | [5 empty] | 9548987.6218 |  |  | 9548987.6218 | TRUE
[5 empty] | Civil Works | MEP Works | Total | % |  |  |  |  | Labour- Civil | 20920.01 | 8139012.98 |  | 830285 |  |  |  |  | 8990217.99 | TRUE
[13 empty] | Prelims - Civil | 5125705.57 |  | 2315622.34 | 5173392.01 | 371666.73 |  | 1121275.85 | 659033.57 | 14766696.07 | FALSE
PRELIMINARIES | [12 empty] | WA - Civil | 2178657.51 |  | 0 | 5953001.8124 | 473591.41 |  |  |  | 8605250.7324 | TRUE
Management and Staff (10 months) | 9449750 | 9449750 | 8249552.44 | 1299435.1818 | 9548987.6218 |  | 9548987.6218 | 101.1% |  | 1227292.55 |  |  | Sub |  |  |  | 31640521.631 | 831086.1 |  |  |  | 32471607.731 | TRUE
MEP Subcontractor Staff (10 months) | 10059900 | 10059900 | 7474618.4055 | 1113659.7716 |  | 8588278.1772 | 8588278.1772 | 85.37% |  | 1138806.26 |  |  | Debts | 218423.22 |  | 440610.35
General Preliminaries (10 months) | 4000000 | 8707572.45 | 12632018.4831 | 2027756.6678 | 14659775.151 |  | 14659775.151 | 366.5% | Annexure 2 | 1410311.36 |  |  |  | 7543706.31 | 8139012.98 | 2756232.69 | 43597200.4534 | 1676344.24 | 9548987.6218 | 1121275.85 | 659033.57
MEP Subcontractor Preliminaries (10 months) | 1000000 | 1000000 | 1359330.28 | 128007.66 |  | 1487337.94 | 1487337.94 | 148.7% |  | 321088.26 |  |  |  | FALSE | TRUE | TRUE | TRUE | TRUE | TRUE | FALSE
Total Preliminaries | 24509650 | 29217222.45 | 29715519.6086 | 4568859.2813 | 24208762.7728 | 10075616.1172 | 34284378.8899 | 139.9% |  | 4097498.43 | 34284378.8899 | TRUE
[16 empty] | Civil Sub Advances | 7654725.8837
DIRECT WORKS | [15 empty] | Sub Total | 51251926.3371
Civil Work
Civil Work Approvals | 8300000 | 15197560.09 | 7295870.5501 | 1309380.1823 | 8605250.7324 |  | 8605250.7324 | 103.7% | Annexure 3,5,6,8 | 1167096.5 | [5 empty] | AS per SC Summary | 51251926.3371
Civil Labour | 1034790 | 1034790 | 7391369.31 | 1598848.68 | 8990217.99 |  | 8990217.99 | 868.8% | Annexure 4
MEP Work | [15 empty] | Difference | 0
MEP Work Approvals | 22000000 | 13860981.78 | 8334407.1083 | 1522383.0894 |  | 9856790.1977 | 9856790.1977 | 44.8% |  | 2306983.96
MEP Labour |  | 9001291 | 12853596.905 | 2268453.83 |  | 15122050.735 | 15122050.735 | 109.1% |  | 448275.51
Total Direct Works | 31334790 | 39094622.87 | 35875243.8734 | 6699065.7817 | 17595468.7224 | 24978840.9327 | 42574309.6551 | 135.9% |  | 3922355.97 | 42574309.6551 | TRUE
PROVISIONAL SUM PACKAGES
MEP: Lifts | 1800000 | 811861 | 60750 | 0 | 0 | 60750 | 60750 | 3.375%
MEP: ELV Works | 2300000 | 1573369 | 215654.418 | 71859.2065 | 0 | 287513.6245 | 287513.6245 | 12.5%
Creation Gulf (BB)+FOH Point wiring |  | 726631 | 105770.5869 |  |  | 105770.5869 | 105770.5869
MEP: Sanitaryware | 1000000 | 1000000 | 195616.76 | 37946.1 | 0 | 233562.86 | 233562.86 | 23.36%
MEP: Lighting Fixtures | 4300000 | 3067842 | 1213405.46 | 442669.48 | 0 | 1656074.94 | 1656074.94 | 38.51%
Façade: Aluminium and Glass | 15600000 | 10273402 | 4013615.7277 | 1029594.8738 | 5043210.6015 | 0 | 5043210.6015 | 32.33% | Annexure 6,8
Façade: GRC | 4200000 | 4155655 | 1564643.1819 | 739279.6157 | 2303922.7976 | 0 | 2303922.7976 | 54.86% | Annexure 6 | 153815.69 |  |  |  | 37398129.0612
Façade: Balustrades | 2900000 | 1670254 | 0 | 0 | 0 | 0 | 0 | 0%
|  |  | 0 |  |  |  | 0
Interiors: Joinery & Finishes | 39200000 | 17574621 | 12310319.6658 | 2588426.8654 | 14898746.5311 | 0 | 14898746.5311 | 38.01% | Annexure 6,8 | 739977.4
Interiors: Commercial Kitchens | 8500000 | 9719682 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
Interiors: Signage | 2000000 | 2000000 | 0 | 0 | 0 | 0 | 0 | 0% |  | 199830
|  |  | 0 |  |  |  | 0
External: Secondary Structure | 3400000 | 1391469 | 409986.6913 | 185460.2233 | 595446.9146 | 0 | 595446.9146 | 17.51% | Annexure 6 | 0
External: Hard Landscaping | 10300000 | 5523719.12 | 6355119.5192 | 1751802.8627 | 8106922.382 | 0 | 8106922.382 | 78.71% | Annexure 6 | 2310029.06
External: Soft Landscaping | 5700000 | 3186640.6 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
External: Swimming Pools | 5600000 | 3465990.23 | 1345291.0508 | 178067.4534 | 1523358.5042 | 0 | 1523358.5042 | 27.2% | Annexure 6 | 0
External: Soffits | 800000 | 800000 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0
External: BMU | 800000 | 628861 | 0 | 0 | 0 | 0 | 0 | 0%
Total Provisional Sum Packages | 108400000 | 69041277.95 | 27790173.0615 | 7025106.6809 | 32471607.731 | 2343672.0114 | 34815279.7424 | 32.12% |  | 3403652.15 | 34815279.7424 | TRUE
DEFECT NOTIFICATION PERIOD
Staff and Indirect Labour (12 months) | 3600000 | 3600000 |  | 0
General Preliminaries (12 months) | 1200000 | 1200000 |  | 0
Total DNP | 4800000 | 4800000
OHP
MEP Subcontractor's OHP (12.5%) | 5307488 | 4240271.5975 | 4177836.413 | 672466.8442 |  | 4850303.2572 | 4850303.2572 | 91.39% | Annexure 9 | 470859.81
Main Contractor's OHP on MEP (10%) | 4776739 | 3816244.4378 | 3578979.3664 | 628310.153 | 4207289.5194 |  | 4207289.5194 | 88.08% | Annexure 9 | 423773.8294
Main Contractor's OHP (12.5%) | 15823068 | 13528868.8113 | 7989732.9077 | 1570345.3911 | 9560078.2989 |  | 9560078.2989 | 60.42% | Annexure 9 | 957078.508
Total OHP | 25907295 | 21585384.8465 | 15746548.6871 | 2871122.3883 | 13767367.8182 | 4850303.2572 | 18617671.0754 | 71.86% |  | 1851712.1474 | 18617671.0754 | TRUE
Total Carried to Payment Certificate | 194951735 | 163738508.1165 | 109127485.2306 | 21164154.1322 | 88043207.0444 | 42248432.3184 | 130291639.3628 | 66.83% |  | 13275218.6974 | 130291639.3628 | TRUE
|  | Main Contractor's OHP on MEP |  | MEP Sub OH/P | -4207289.5194
| ADD | ADVANCES |  | Advance Balance | 8981903.715
92817821.2401
| DDT | MEP ADVANCES (It is in MEP not CIVIL) |  | MEP Advances | -1404296.996
|  | KCE Civil Certified Amount |  |  | 91413524.2441
|  | KCE Claimed Amount |  |  | 96511337.57
|  | Difference |  |  | 5097813.3259
4009602.3229
501200.2904
4510802.6133

## Annexure-2 GENERAL PRELIMS
Sky Palaces Real Estate Development LLC
Annexure 2 - Breakdown of KCE's General Preleminaries Cost
Project: | Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor : | Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : | Base Build Works |  | Currency: | AED
| KCE IPA Section Description | Previous | This Month | Cumulative
1 | Subcontractor Payments | 4259846.0788 | 913545.9312 | 5173392.01
2 | Material | 4673929.89 | 670198.9 | 5344128.79
3 | Plant | 2300533.63 | 455699.06 | 2756232.69
4 | Overhead | 1022048.4 | 99227.45 | 1121275.85
5 | Committed Orders | 461945.4033 | -90278.6733 | 371666.73
| TOTAL | 12718303.4022 | 2048392.6678 | 14766696.07

## Annexure -3 Material Summary
Sky Palaces Real Estate Development LLC
Annexure 3 - Breakdown of KCE's Material Cost
Project: | Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor: | Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : | Base Build Works |  | Currency: | AED
Sn | KCE IPA Section Description | Previous | This Month | Cumulative
1 | General Preleminaries | 4455506.67 | 670198.9 | 5125705.57
2 | Civil Works | 1655882.88 | 522774.63 | 2178657.51
3 | RPJV Debt Payments | 218423.22 |  | 218423.22
4 | Direct Labor | 20920.01 |  | 20920.01
5 | Adjustments | -39042.73 | -19197 | -58239.73
| Total | 6311690.05 | 1173776.53 | 7485466.58

## Annexure-4 Labour Cost Summary
Sky Palaces Real Estate Development LLC
Annexure 4 - Breakdown of KCE's Civil Labour Cost
Project: Plot - 18 | [5 empty] | Certificate Date: | 2023-01-23
Contractor:Khansaheb Civil Engineering LLC | [5 empty] | Certificate No: | KCE-11
Contract :Base Build Works | [5 empty] | Currency: | AED
Sn | KCE IPA Section Description | Previous |  | This Month |  | Cumulative
|  | Total Hours | Amount | Total Hours | Amount | Total Hours | Amount
1 | Unskilled Labour | 145352.5 | 1699366.75 | 41289.5 | 386040.11 | 186642 | 2085406.86
2 | Skilled Labour | 107106.5 | 1429867.61 | 29187 | 292071.18 | 136293.5 | 1721938.79
3 | Operators costs | 28699 | 443737.83 | 7452 | 96434.77 | 36151 | 540172.6
4 | Tradesmen costs | 227695 | 2969945.41 | 633383.06 | 633383.06 | 861078.06 | 3603328.47
5 | Charge hand labour costs | 11456.5 | 157398.91 | 33399.56 | 33399.56 | 44856.06 | 190798.47
6 | PRAVEEN-July (Office Boy) | 1 | 1425 |  | 0 | 1 | 1425
7 | Adjustments |  | -4057.21 |  | 0 |  | -4057.21
| Total |  | 6697684.3 |  | 1441328.68 |  | 8139012.98 | 8141645 | 2632.02

## Annexure-5 Plant Summary
Sky Palaces Real Estate Development LLC
Annexure 5 - Breakdown of KCE's Plant Cost
Project: | Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor: | Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : | Base Build Works |  | Currency: | AED
Sn | KCE IPA Section Description | Previous | This Month | Cumulative
1 | General Preliminaries | 1859923.28 | 455699.06 | 2315622.34
2 | RPJV Debt Payments | 440610.35 | 0 | 440610.35
3 | Civil Work | 0 | 0 | 0
4 | Adjustments | 0 | 0 | 0
| TOTAL | 2300533.63 | 455699.06 | 2756232.69

## Annexure 6-SC Summary
Sky Palaces Real Estate Development LLC
Annexure 6 - SUBCONTRACTOR PAYMENT CERTIFICATION (CIVIL WORKS) - SUMMARY
SN No | Item | Scope of work | Subcontract Order Amount | Work Approval Reference | Value Complete |  |  |  |  | BOQ Category | Materials On Site | Materials On Site | Material Off site | Material Off site | Variations WFA | Variations WFA | Variations KCE | Variations KCE | Sub-Total | Sub-Total | Advance Payment | [7 empty] | Total Certified | Total Claimed
[5 empty] | Previous Valuation | This Month | This Month | To Date | To Date | [11 empty] | Advance | Advance | Advance % | Recovery % | Recovery | Recovery | Balance | Balance
| Subcontractors | [8 empty] | 889912.9856
1 | Arcadia Metal Industries | External Metal works | 3330440 | N/A | 218243.9 | 0 | -84602.5 | 218243.9 | 133641.4 | Landscape |  |  | 566813.46 |  | 227500 | 766500 | 1822468.7133 | 2283336.52 | 2835026.0733 | 3183477.92 | 499566 | 499566 |  | 15% | 499566 | 477521.69 | 0 | 22044.31 | 2835026.0733 | 3205522.23 | -370496.1567 |  |  |  | -348451.8467
2 | Watermaster Technical Services LLC | Swimming Pool & Water Feature works | 2128651 | N/A | 1295741.6073 | 205002.8643 | 722058.9327 | 1500744.4716 | 2017800.54 | Swimming Pools | -320048.8312 | -584620 | 342662.8639 | 151321.72 |  |  |  |  | 1523358.5042 | 1650462.71 |  |  |  |  | 0 | 0 | 0 | 0 | 1523358.5042 | 1650462.71 | -127104.2058 |  |  |  | -127104.2058
3 | Dar Al Rokham LLC | Internal Stone works | 4111821 | N/A | 1870362.1499 | 148165.5838 | 538970.4701 | 2018527.7337 | 2409332.62 | ID - Joinery & Finishes | -97030.7336 | -132458 |  |  | 1090574.3724 | 1298439.8 | 328306.0138 | 446253.6 | 3340377.3863 | 4021568.02 |  |  |  |  | 0 | 0 | 0 | 0 | 3340377.3863 | 4021568.02 | -681190.6337 |  |  |  | -681190.6337
4 | Al Shirawi Contracting Co LLC | Waterproofing works | 1391469 | N/A | 394672.5223 | 200774.3923 | 250700.9577 | 595446.9146 | 645373.48 | Secondary Structures | [7 empty] | 15314.52 | 595446.9146 | 660688 |  |  |  |  | 0 | 0 | 0 | 0 | 595446.9146 | 660688 | -65241.0854 |  |  |  | -65241.0854
5 | Alshafar Interiors Co LLC | Joinery to Guest Rooms | 5169165 | N/A | 1997743.9674 | 202258.4145 | 242051.0026 | 2200002.3819 | 2239794.97 | ID - Joinery & Finishes | -369409.908 | -400717.8 |  |  | 333333.3333 | 501328.76 | 0 | 0 | 2163925.8072 | 2340405.93 | 887874.75 | 887874.75 |  | 17.5% | 378687.0163 | 409571.0378 | 509187.7337 | 478303.7122 | 2673113.5409 | 2818709.6423 | -145596.1013 |  |  |  | -176480.1228
6 | Isam Kabbani & Partners | Guniting & Waterproofing works | 1155933 | N/A | 428480.5156 | 7058.2176 | 1734.1644 | 435538.7332 | 430214.68 | Landscape | [6 empty] | 0 | 10595.14 | 435538.7332 | 440809.82 |  |  |  |  | 0 | 0 | 0 | 0 | 435538.7332 | 440809.82 | -5271.0868 |  |  |  | -5271.0868
7 | Fiona Environs UAE | Soft Landscaping & Irrigation works | 3313028.6 | N/A | 1576197.1379 | 314185.9 | 403901.3221 | 1890383.0379 | 1980098.46 | Landscape | [8 empty] | 1890383.0379 | 1980098.46 |  |  |  |  | 0 | 0 | 0 | 0 | 1890383.0379 | 1980098.46 | -89715.4221 |  |  |  | -89715.4221
8 | Al Reem Marble & Granite LLC | External Stoneworks | 4556481 | N/A | 513090.8076 | 944220.13 | 1068976.7224 | 1457310.9376 | 1582067.53 | Landscape | 99782.26 | 99782.26 | 1214151.88 | 1214151.88 |  |  | 174729.46 | 174729.46 | 2945974.5376 | 3070731.13 | 361591.15 | 216955.15 | 20% | 20% | 13848.56 | 13848.56 | 347742.59 | 203106.59 | 3293717.1276 | 3273837.72 | 19879.4076 |  |  |  | -124756.5924
9 | Joyz Overseas Technical Services LLC | EIFS works | 1538156.94 | N/A | 283571.5314 | 250314.5484 | 415254.2776 | 533886.0798 | 698825.809 | GRC - EIFS |  |  |  |  | 125273.8178 | 117584.7081 | 412935 | 470099.6729 | 1072094.8976 | 1286510.19 | 153815.69 | 153815.69 |  | 10% | 107209.4898 | 128651.02 | 46606.2002 | 25164.67 | 1118701.0978 | 1311674.86 | -192973.7622 |  |  |  | -214415.2924
10 | Bond Interiors Design LLC | Fitout of Hotel Lobby, All Day Dining & Spa Works | 4325954.46 | N/A | 1639622.09 | 561705.45 | 706363.28 | 2201327.54 | 2345985.37 | ID - Joinery & Finishes | [6 empty] | 101025.8 | 101025.8 | 2302353.34 | 2447011.17 |  |  |  |  | 0 | 0 | 0 | 0 | 2302353.34 | 2447011.17 | -144657.83 |  |  |  | -144657.83
11 | Al Rawda General Maint. & Decoration Co LLC | Partition & Ceiling works | 1954843 | N/A | 840251.0145 | 111776.93 | 174638.0255 | 952027.9445 | 1014889.04 | ID - Joinery & Finishes | [6 empty] | 1760923.43 | 1760923.43 | 2712951.3745 | 2775812.47 |  |  |  |  | 0 | 0 | 0 | 0 | 2712951.3745 | 2775812.47 | -62861.0955 |  |  |  | -62861.0955
12 | Joseph Advertisers LLC | Signage works | 999150 | N/A | 0 | 0 | 0 | 0 | 0 | ID - Signage | [8 empty] | 0 | 0 | 199830 | 199830 |  |  | 0 | 0 | 199830 | 199830 | 199830 | 199830 | 0 |  |  |  | 0
13 | Joseph Decorative Glass | Internal Glazing works | 1262387 | N/A | 383554.7679 | 29623 | 220296.8421 | 413177.7679 | 603851.61 | ID - Joinery & Finishes | [6 empty] | 394 | 394 | 413571.7679 | 604245.61 | 252477.4 | 252477.4 |  | 20% | 82714.3536 | 120849.11 | 169763.0464 | 131628.29 | 583334.8144 | 735873.9 | -152539.0856 |  |  |  | -190673.8421
14 | Walltracts | Wall Coverings | 712173.7 | N/A | 0 | 0 | 0 | 0 | 0 | ID - Joinery & Finishes |  |  | 381900.4 | 381900.4 |  |  |  |  | 381900.4 | 381900.4 | 282376.94 | 282376.94 |  |  | 0 | 0 | 282376.94 | 282376.94 | 664277.34 | 664277.34 | 0 |  |  |  | 0
15 | Goodrich Global Trading LLC | Carpets to Guest Rooms | 839675.05 | N/A | 23097.25 | 509683.8214 | 594224.46 | 532781.0714 | 617321.71 | ID - Joinery & Finishes |  |  |  |  | 23097.25 |  |  |  | 555878.3214 | 617321.71 |  |  |  |  | 0 | 0 | 0 | 0 | 555878.3214 | 617321.71 | -61443.3886 |  |  |  | -61443.3886
16 | Arabian Profile C Ltd | GRC Works | 4155655 | N/A | 769033 | 223170 | 451488 | 992203 | 1220521 | Façade - GRC | 0 | [5 empty] | 65711.9 | 65711.9 | 1057914.9 | 1286232.9 |  |  |  |  | 0 | 0 | 0 | 0 | 1057914.9 | 1286232.9 | -228318 |  |  |  | -228318
17 | Glass Line Aluminium LLC | Aluminium & Glazing Façade works | 10273402 | N/A | 2005979.8496 | 696905.4479 | 1437910.2604 | 2702885.2975 | 3443890.11 | Façade - Aluminium and Glass | -847423 | -759403.75 |  |  | 2894971.024 | 3278137.54 | 276277.28 | 317466.94 | 5026710.6015 | 6280090.84 |  |  |  |  | 0 | 0 | 0 | 0 | 5026710.6015 | 6280090.84 | -1253380.2385 |  |  |  | -1253380.2385
18 | EW COX Middle East LLC | BMU System | 628861 | N/A | 0 | 0 | 0 |  |  | Civil | [8 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
19 | Mohammed Tayyeb Khoory & Sons | Garbage & Linen Chutes | 287122 | N/A | 140609.4 | 0 | 22652.2 | 140609.4 | 163261.6 | Civil | [8 empty] | 140609.4 | 163261.6 |  |  |  |  | 0 | 0 | 0 | 0 | 140609.4 | 163261.6 | -22652.2 |  |  |  | -22652.2
20 | HTS Carpets Trading LLC | Carpets to lift lobbies & Corridors | 356512.42 | N/A | 0 | 0 | 0 |  |  | ID - Joinery & Finishes | [8 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
21 | Khansaheb Interior Division | Restaurant Works | 22617386 | N/A | 962551.45 | 195525.4488 | 502638.53 | 1158076.8988 | 1465189.98 | ID - Joinery & Finishes | [8 empty] | 1158076.8988 | 1465189.98 | 4523477.2 | 4523477.2 | 20% | 20% | 231615.3798 | 293038 | 4291861.8202 | 4230439.2 | 5449938.7191 | 5695629.18 | -245690.4609 |  |  |  | -307113.0812
[19 empty] | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0
| MEP Subcontract Advances | [17 empty] | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 |  |  |  | 0
22 | Faisal Jassim Trading Co |  |  | N/A | [14 empty] | 0 | 0 | 256680 | 256680 |  |  | 0 |  | 256680 | 256680 |  |  | 0 |  |  |  | 0
23 | SIS |  |  | N/A | [14 empty] | 0 | 0 | 399954.9 | 399954.9 |  |  | 52073.099 |  | 347881.801 | 399954.9 |  |  | 0 |  | 124208.64 |  | 0
0
24 | Sun Star Electromichanical LLC |  |  | N/A | [14 empty] | 0 | 0 | 278780.88 | 278780.88 |  |  | 127621.2 | 124208.64 | 151159.68 | 154572.24 |  |  | 0 |  | 85750 |  | 0
25 | ISTA Middle East |  |  | N/A | [14 empty] | 0 | 0 | 122500 | 122500 |  |  | 85750 | 85750 | 36750 | 36750 |  |  | 0 |  | 332660.46 |  | 0
26 | Project & Supplies |  |  | N/A | [14 empty] | 0 | 0 | 1031744.7 | 1031744.7 |  |  | 419919.185 | 332660.46 | 611825.515 | 699084.24 |  |  | 0 |  | 542619.1 |  | 0
27 | HS Energy Solutions |  |  | N/A | [14 empty] | 0 | 0 | 62500 | 62500 |  |  | 62500 |  | 0 | 62500 |  |  | 0 |  |  |  | 0
[20 empty] | 0 | [9 empty] | 0 | 0 |  |  |  | 0
| Subcontractors ( Domestic ) | [17 empty] | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
28 | Blue Sky LLC | Supply of MEP Maintenance team | 396000 | P006 | 306300 | 41700 | 42300 | 348000 | 348600 | Prelims | [6 empty] | 387847.04 | 387847.04 | 735847.04 | 736447.04 |  |  |  |  | 0 | 0 | 0 | 0 | 735847.04 | 736447.04 | -600 |  |  |  | -600
29 | Al Rawda General Maint. & Decoration Co LLC | Ceiling & Partition repairs, painting works | 26960 | C036 | 34460 | 0 | 11238.1 | 34460 | 45698.1 | Prelims | [6 empty] | 10988 |  | 45448 | 45698.1 |  |  |  |  | 0 | 0 | 0 | 0 | 45448 | 45698.1 | -250.1 |  |  |  | -250.1
30 | Creative House Scaffolding | Scaffolding | 157030 | C001 | 2217615.6388 | 279001.4812 | 348021.4812 | 2496617.12 | 2565637.12 | Prelims | [8 empty] | 2496617.12 | 2565637.12 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 2496617.12 | 2565637.12 | -69020 |  |  |  | -69020
31 | TWIC Insulation Materials Supply LLC | Epoxy Coating & Dust Sealer works | 570509.8 | C-015, 16 R1 | 263347.1475 | 35689.9025 | 49242.3125 | 299037.05 | 312589.46 | Civil | [8 empty] | 299037.05 | 312589.46 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 299037.05 | 312589.46 | -13552.41 |  |  |  | -13552.41
32 | Al Maraya Marble & Granite Factory LLC | Tile Installation | 514481.6 | C011 | 244297.8528 | 6063.2272 | 12929.1372 | 250361.08 | 257226.99 | Civil | [8 empty] | 250361.08 | 257226.99 | 25000 | 25000 |  |  | 25000 | 25000 | 0 | 0 | 250361.08 | 257226.99 | -6865.91 |  |  |  | -6865.91
33 | Greenwood General Trading LLC | Wooden Flooring | 353975.01 | C017 |  | 0 | 0 |  |  | Civil | [8 empty] | 0 | 0 | 176987.51 | 176987.51 |  |  | 0 | 0 | 176987.51 | 176987.51 | 176987.51 | 176987.51 | 0 |  |  |  | 0
34 | Data Link Technical Services LLC | Wild Air Partitions | 54387.15 | C006R1 | 327505.934 | 73620.996 | 74032.066 | 401126.93 | 401538 | Prelims | [8 empty] | 401126.93 | 401538 |  |  |  |  | 0 | 0 | 0 | 0 | 401126.93 | 401538 | -411.07 |  |  |  | -411.07
35 | Corecut Engineering LLC | Coring & Scanning | 35410 | C010 | 398708.45 | 55405 | 60483.005 | 454113.45 | 459191.455 | Civil | [8 empty] | 454113.45 | 459191.455 |  |  |  |  | 0 | 0 | 0 | 0 | 454113.45 | 459191.455 | -5078.005 |  |  |  | -5078.005
36 | Firestop Middle East | Firestopping works | 441760 | C-001, 002 R1 | 120749.016 | 46903.384 | 47409.784 | 167652.4 | 168158.8 | Prelims | [8 empty] | 167652.4 | 168158.8 |  |  |  |  | 0 | 0 | 0 | 0 | 167652.4 | 168158.8 | -506.4 |  |  |  | -506.4
37 | Inventure Façade Contracting LLC | Glass Balustrade, Door and Louvres | 1331893 | C-011 | 1507019.04 | 283215.54 | 292139.84 | 1790234.58 | 1799158.88 | Civil | [6 empty] | 178335.2 | 179740 | 1968569.78 | 1978898.88 | 66594.65 | 66594.65 | 5% | 5% | 66594.65 | 66594.65 | 0 | 0 | 1968569.78 | 1978898.88 | -10329.1 |  |  |  | -10329.1
38 | Vulcan Industries LLC | Steel Doors | 685405 | C-032 | 82852.5 | 50674.2524 | 56888.19 | 133526.7524 | 139740.69 | Civil | [8 empty] | 133526.7524 | 139740.69 | 60640 | 60640 | 20% |  | 0 | 0 | 60640 | 60640 | 194166.7524 | 200380.69 | -6213.9376 |  |  |  | -6213.9376
39 | Polaris International Industries LLC | Timber Doors | 961039 | C-029 | 329479 | 296363.41 | 325546 | 625842.41 | 655025 | Civil | [6 empty] | 26074.56 | 26074.56 | 651916.97 | 681099.56 | 96103.9 | 96103.9 | 10% | 12% | 78230.0364 | 81731.9472 | 17873.8636 | 14371.9528 | 669790.8336 | 695471.5128 | -25680.6792 |  |  |  | -29182.59
40 | German Concrete Works & Building Contracting LLC | Screed & Insulation works | 645526.09 | C018R1 | 376545.9998 | 2350.8402 | 9855.7702 | 378896.84 | 386401.77 | Civil | [8 empty] | 378896.84 | 386401.77 |  |  |  |  | 0 | 0 | 0 | 0 | 378896.84 | 386401.77 | -7504.93 |  |  |  | -7504.93
41 | Al Hayat Fiberglass Ind LLC | GRP Lining works | 313333 | C027 | 118320 | 0 | 0 | 118320 | 118320 | Civil | [8 empty] | 118320 | 118320 |  |  |  |  | 0 | 0 | 0 | 0 | 118320 | 118320 | 0 |  |  |  | 0
42 | Center Core Professional Technical Services LLC | Slab cutting & strengthening works | 88900 | C-033 | 88900 | 0 | 0 | 88900 | 88900 | Civil | [8 empty] | 88900 | 88900 |  |  |  |  | 0 | 0 | 0 | 0 | 88900 | 88900 | 0 |  |  |  | 0
43 | Weserve Technical Services LLC | Miscellaneous Steel works | 47795 | C-052 | 237860.85 | 247596.45 | 247596.45 | 485457.3 | 485457.3 | Civil | [8 empty] | 485457.3 | 485457.3 |  |  |  |  | 0 | 0 | 0 | 0 | 485457.3 | 485457.3 | 0 |  |  |  | 0
44 | Venus Engineering LLC | RC column removal & strengthening works | 110965 | C-039 | 77965 | 0 | 0 | 77965 | 77965 | Civil | [8 empty] | 77965 | 77965 | 33290 | 33290 | 30% | N/A | 33290 | 33290 | 0 | 0 | 77965 | 77965 | 0 |  |  |  | 0
45 | Global Composites Solutions LLC | GRP Cladding to Planter Wall | 225683 | C-053 |  | 0 | 0 |  |  | Landscape | [8 empty] | 0 | 0 | 45136.6 | 45136.6 | 20% |  | 0 | 0 | 45136.6 | 45136.6 | 45136.6 | 45136.6 | 0 |  |  |  | 0
46 | Indiga Tech Trading LLC | Steel Doors | 154496.05 | C-047 |  | 22602.85 | 22602.85 | 22602.85 | 22602.85 | Civil | [8 empty] | 22602.85 | 22602.85 | 24449.21 | 24449.21 | 15.83% | 20% | 4520.57 | 4520.57 | 19928.64 | 19928.64 | 42531.49 | 42531.49 | 0 |  |  |  | 0
47 | Hygienic Solutions Chemical Trading LLC | MMA Flooring | 474794.1 | C-016 |  | 0 | 0 |  |  | Civil | [8 empty] | 0 | 0 | 274195.05 | 274195.05 | 50% |  | 0 | 0 | 274195.05 | 274195.05 | 274195.05 | 274195.05 | 0 |  |  |  | 0
48 | Monrac LLC | Ceiling & Partition repairs, painting works | 918183.61 | PS-021 | 534726.625 | 171403.22 | 206951.175 | 706129.845 | 741677.8 | ID - Joinery & Finishes | [8 empty] | 706129.845 | 741677.8 | 75000 | 75000 |  | 10% | 70612.9845 | 75000 | 4387.0155 | 0 | 710516.8605 | 741677.8 | -31160.9395 | Adv. Bond submitted |  | No Perf. Bond submitted | -35547.955
49 | Technical Access Services (L.L.C.) | Scaffolding Works | 265036 | C-065 | 188189.03 | 218786.89 | 221964.39 | 406975.92 | 410153.42 | Prelims | [6 empty] | 617916.64 | 617916.64 | 1024892.56 | 1028070.06 |  |  |  |  | 0 | 0 | 0 | 0 | 1024892.56 | 1028070.06 | -3177.5 |  |  |  | -3177.5
50 | Progress Fabrication | Metal 2Cladding Works and Misc Metal Works | 1264100.14 | C-078 | 105000 | 165000 | 165000 | 270000 | 270000 | Civil | [8 empty] | 270000 | 270000 | 133278.25 | 133278.25 | 10.54% | 10% | 27000 | 27000 | 106278.25 | 106278.25 | 376278.25 | 376278.25 | 0 | No Adv. Bond submitted |  | No Perf. Bond submitted | 0
51 | Ferco Shutters LLC | Fire Curtains | 33685 | P-027 |  | 0 | 0 |  |  | ID - Joinery & Finishes | [8 empty] | 0 | 0 | 3368.5 | 3368.5 |  |  | 0 | 0 | 3368.5 | 3368.5 | 3368.5 | 3368.5 | 0 | No Adv. Bond submitted |  | No Perf. Bond submitted | 0
52 | Jeel Alfan Technical Services | Decorative Paint | 128266 | P-015 |  | 0 | 0 |  |  | ID - Joinery & Finishes | [8 empty] | 0 | 0 | 32066.5 | 32066.5 |  |  | 0 | 0 | 32066.5 | 32066.5 | 32066.5 | 32066.5 | 0 | No Adv. Bond submitted |  | No Perf. Bond submitted | 0
53 | Technoserve Technical works LLC | Painting works | 73379.6 | P-012 | 3638.29 | 0 | 0 | 3638.29 | 3638.29 | Civil | [8 empty] | 3638.29 | 3638.29 | 14675.92 | 14675.92 | 20% | 20% | 727.658 | 727.66 | 13948.262 | 13948.26 | 17586.552 | 17586.55 | 0.002 | No Adv. Bond submitted |  | No Perf. Bond submitted | 0
54 | International Foundation Group LLC | Waterproofing Concrete works | 450000 | C-061 R4 | 450000 | 0 | 0 | 450000 | 450000 | Civil | [8 empty] | 450000 | 450000 | 90000 | 90000 |  | 20% | 90000 | 90000 | 0 | 0 | 450000 | 450000 | 0 |  |  |  | 0
55 | X-Calibur Emirates LLC | Stair nosing works | 221889 | C-064 |  | 173913 | 173913 | 173913 | 173913 | Façade - GRC | [8 empty] | 173913 | 173913 | 52173.9 | 52173.9 | 23.51% | 100% | 52173.9 | 52173.9 | 0 | 0 | 173913 | 173913 | 0 |  |  |  | 0
56 | Master Rubber Manufacturing | Wall & Corner Guard works | 169069 | C-062 | [5 empty] | Civil | [8 empty] | 0 | 0 | 50720.55 | 50720.55 |  |  | 0 | 0 | 50720.55 | 50720.55 | 50720.55 | 50720.55 | 0 |  |  |  | 0
57 | DNK Engineering Equipment Trading LLC | Rolling Shutter works | 75530 | C-026 | [5 empty] | Civil | [8 empty] | 0 | 0 | 37765 | 37765 |  |  | 0 | 0 | 37765 | 37765 | 37765 | 37765 | 0 |  |  |  | 0
58 | Dormakaba Middle East | Movable Partition Works- AHK Balance | 366250 | PS-025 | [5 empty] | ID - Joinery & Finishes | [8 empty] | 0 | 0 | 109875 | 109875 |  |  | 0 | 0 | 109875 | 109875 | 109875 | 109875 | 0 |  |  |  | 0
59 | Khansaheb Joinery DIvision ( KJD ) | Joinery Works- AHK Balance | 2105730 | PS-023 |  | 320752.09 | 320752.09 | 320752.09 | 320752.09 | ID - Joinery & Finishes | [8 empty] | 320752.09 | 320752.09 | 421145.97 | 421145.97 | 20% | 20% | 64150.418 | 64150.42 | 356995.552 | 356995.55 | 677747.642 | 677747.64 | 0.002 |  |  |  | 0
60 | Al Burhani General Trading LLC | Wooden Flooring & Carpet works- AHK | 133457 | PS-032 | [5 empty] | ID - Joinery & Finishes | [8 empty] | 0 | 0 | 53002.5 | 53002.5 |  |  | 0 | 0 | 53002.5 | 53002.5 | 53002.5 | 53002.5 | 0 |  |  |  | 0
61 | Rattan House Factory for Furniture and Decoration | Res Lobbies, Joinery works- AHK Balance | 279759 | PS-044 |  | 28243.2 | 28243.2 | 28243.2 | 28243.2 | ID - Joinery & Finishes | [8 empty] | 28243.2 | 28243.2 | 102424 | 102424 | 36.61% | 20% | 5648.64 | 5648.64 | 96775.36 | 96775.36 | 125018.56 | 125018.56 | 0 |  |  |  | 0
62 | Vijayraj Contracting Co LLC | Plastering works | 206250 | C-019 | 151575.25 | 27431.8 | 27431.8 | 179007.05 | 179007.05 | Civil | -19920 | -19920 | [6 empty] | 159087.05 | 159087.05 |  |  |  |  | 0 | 0 | 0 | 0 | 159087.05 | 159087.05 |  |  |  |  | 0
63 | Doormax Building Material Trading LLC | Glass Door work | 128000 | C-090 |  | 0 | 0 | 0 | 0 | ID - Joinery & Finishes | [8 empty] | 0 | 0 | 32000 | 32000 | 25% |  | 0 | 0 | 32000 | 32000 | 32000 | 32000 |  |  |  |  | 0
64 | KTC International Cont LLC | RTA Works | 1043942 | C-091 |  |  |  | 0 | 0 | [9 empty] | 0 | 0 | 208788.4 | 208788.4 | 20% |  | 0 | 0 | 208788.4 | 208788.4 | 208788.4 | 208788.4 |  |  |  |  | 0
65 | Urban Science Building Contracting LLC | Joinery-Cupboards | 533125 | C-097 |  |  |  | 0 | 0 | [11 empty] | 106625 | 106625 | 20% |  |  |  | 106625 | 106625 | 106625 | 106625 | 0 |  |  |  | 0
| Subcontractors ( Labour Only ) | [17 empty] | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0
66 | Al Qannati Electromechanical LLC | Labour Supply ( Block Works ) |  | N/A | 672765 | 157520 | 157520 | 830285 | 830285 | Direct Labour - Civil | [8 empty] | 830285 | 830285 |  |  |  |  | 0 | 0 | 0 | 0 | 830285 | 830285 | 0 |  |  |  | 0
67 | Focus Power Security Services LLC | Supply of Site Security Service | 252000 | P004 | 161000 | 21000 | 21000 | 182000 | 182000 | Prelims | [8 empty] | 182000 | 182000 |  |  |  |  | 0 | 0 | 0 | 0 | 182000 | 182000 | 0 |  |  |  | 0
68 | Service plus Technical Services LLC | Cleaning Service | 162400 | P005 | 96587.96 | 16800 | 16800 | 113387.96 | 113387.96 | Prelims | [8 empty] | 113387.96 | 113387.96 |  |  |  |  | 0 | 0 | 0 | 0 | 113387.96 | 113387.96 | 0 |  |  |  | 0
69 | Purchases (Pest Control) |  |  | N/A | 6420 | 0 | 0 | 6420 | 6420 | Prelims | [8 empty] | 6420 | 6420 |  |  |  |  | 0 | 0 | 0 | 0 | 6420 | 6420 | 0 |  |  |  | 0
[31 empty] | 0 |  |  |  | 0
|  |  | 91508661.32 |  | 24444631.5453 | 7342407.6826 | 10609117.5887 | 31787039.2279 | 35053749.134 |  | -1554050.2129 | -1797337.29 | 2505528.6039 | 1747374 | 4694749.7975 | 5961990.8081 | 6163933.0371 | 6857429.2229 | 43597200.4534 | 47889166.325 | 11638476.02 | 11493840.02 |  |  | 2579453.1403 | 2511936.3049 | 9059022.8797 | 8981903.715 | 51251926.3371 | 55261528.66 | -4009602.3229 |  |  |  | -4291965.8716
| BOQ Categroy | This Month | Cumulative | Previous
| Prelims | 913545.9312 | 5173392.01 | 4259846.0788
| Civil | 1218797.8323 | 5953001.8124 | 4734203.9801
| Labour Sub | 157520 | 830285 | 672765
|  |  | 0 | 0
| Provisonal Sums | 0 | 0 | 0
| Landscape | 1751802.8627 | 8106922.382 | 6355119.5192
| GRC - EIFS | 337976.1157 | 1072094.8976 | 734118.7819
| Façade - GRC | 401303.5 | 1231827.9 | 830524.4
| Façade - Aluminium and Glass | 1029594.8738 | 5026710.6015 | 3997115.7277
| ID - Signage | 0 | 0 | 0
| ID - Joinery & Finishes | 2613528.8654 | 14084160.4311 | 11470631.5658
| Swimming Pools | 178067.4534 | 1523358.5042 | 1345291.0508
| Secondary Structures | 185460.2233 | 595446.9146 | 409986.6913
| TOTAL | 8787597.6579 | 43597200.4534 | 34809602.7955
|  | 10204668.76 | 12797199.9808 | [17 empty] | 0
|  | -1417071.1021 | [17 empty] | 4291965.8716 | [7 empty] | -77119.1647
| BOQ Categroy | This Month | Cumulative | Previous
| Prelims | 987511.0012 | 5247357.08 | 4259846.0788
| Civil | 1320176.9149 | 6054380.895 | 4734203.9801
| Labour Sub | 157520 | 830285 | 672765
|  |  | 0 | 0
| Provisonal Sums | 0 | 0 | 0
| Landscape | 2319997.8108 | 8675117.33 | 6355119.5192
| GRC - EIFS | 552391.4081 | 1286510.19 | 734118.7819
| Façade - GRC | 629621.5 | 1460145.9 | 830524.4
| Façade - Aluminium and Glass | 2282975.1123 | 6280090.84 | 3997115.7277
| ID - Signage | 0 | 0 | 0
| ID - Joinery & Finishes | 4273496.8142 | 15744128.38 | 11470631.5658
| Swimming Pools | 305171.6592 | 1650462.71 | 1345291.0508
| Secondary Structures | 250701.3087 | 660688 | 409986.6913
| TOTAL | 13079563.5295 | 47889166.325 | 34809602.7955
Note on R11: Himal Kosala: discount
Note on I51: Himal Kosala: here 130,492.69 is including VAT

## Annexure 7-Overhead Summary
Sky Palaces Real Estate Development LLC
Annexure 07 - Breakdown of KCE's Overhead Cost
Project: | Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor: | Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : | Base Build Works |  | Currency: | AED
Sn | KCE IPA Section Description | Previous | This Month | Cumulative
1 | General Preliminaries | 1022048.4 | 99227.45 | 1121275.85
2 | Adjustments | -48681.189 | 0 | -48681.189
TOTAL |  | 973367.211 | 99227.45 | 1072594.661

## Annexure 8-Committed Orders
Sky Palaces Real Estate Development LLC
Annexure 8 - Breakdown of KCE's Committed Orders Cost
Project: | Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor: | Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : | Base Build Works |  | Currency: | AED
Sn | KCE IPA Section Description | Previous | This Month | Cumulative
1 | General Preliminaries | 463384.4033 | -91717.6733 | 371666.73
2 | Civil Work | 905783.69 | -432192.28 | 473591.41
3 | Façade: Aluminium and Glass | 16500 | 0 | 16500
4 | ID - Joinery & Finishes | 839688.1 | -25102 | 814586.1
| TOTAL | 2225356.1933 | -549011.9533 | 1676344.24

## Committed Orders - Dec 22
Sky Palaces Real Estate Development LLC
Committed Orders Cost Breakdown
SN | Description | Total Amount (AED ) | Applied Amount (AED) | Category
01 | AHK Works- Alternatives SC's | 528371.34 | 83360 | ID - Joinery & Finishes | BOQ Categroy | Amount
02 | Al Ihsan Building Materials Trading (LPO HM-201A22002/0056)- Balcony Tiles | 154032 | 30240 | ID - Joinery & Finishes | Prelims | 371666.73
03 | Al Majid LLC (LPO HM-201A22002/0167 ) - GRP Tank | 6500 | 6500 | Civil | Civil | 473591.41
04 | Al Najar LLC (LPO HM-201A22002/0162 ) - DC Furniture | 4900 | 0 | Prelims | Façade: Aluminium and Glass | 16500
05 | AST Digital Print Centre (LPO HM-201A22002/0037)- Printer charges | 15000 | 3438.16 | Prelims | ID - Joinery & Finishes | 814586.1
06 | Carpet Land LLC (LPO HM-201A22002/0151) - Carpet | 13790 | 0 | Prelims | TOTAL | 1676344.24
07 | Consent (LPO HM-201A22002/0172) - Tile & Coping | 166700 | 98422.2 | Civil
08 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0069)- Scissor Lift | 72900 | 72900 | Prelims
09 | Dosteen Doors & Shutters LLC (LPO HM-201A22002/0117)- Scissor Lift | 72900 | 72900 | Prelims
10 | Dutco LLC (LPO HM-201A22002/0155) - Modular Seal | 7600 | 0 | Prelims
11 | Fluid Codes Testing- (LPO HM-201A22002/0149) | 28207 | 0 | Prelims
12 | Golden Ready Mix LLC (LPO HM-201A22002/0023 R1)- Concrete supply | 587200 | 78601 | Civil
13 | High Class Decor & Curtains Works LLC ( HM-201A22002/0080 ) | 19435 | 9717.5 | ID - Joinery & Finishes
14 | High Glass Decore & Curtain Works LLC (LPO HM-201A22002/0080)- Turkish Acrylic carpet | 19435 | 19435 | ID - Joinery & Finishes
15 | Indigatech (LPO HM-201A22002/0095)- Fire rated Windows | 91817 | 64271.9 | Civil
16 | Indigatech (LPO HM-201A22002/0132)- Window Glass | 42920 | 42920 | Civil
17 | Inter Metal LLC (LPO HM-201A22002/0168 ) - DC Furniture | 5350 | 0 | Prelims
18 | IT infra-strucure set up to Offices | 10000 | 10000 | Prelims
19 | Jabel Ali Tra. LLC (LPO HM-201A22002/0161 ) -Dune Sand | 11110 | 2110.9 | Civil
20 | Kone (LPO HM-201A22002/0002) - CTU use Lifts (2 Nos)- June 22 | 160000 | 16000 | Prelims
21 | Kone (LPO HM-201A22002/0048)- CTU use Lifts no 10 & 21 (2 Nos)- Dec 22 | 128000 | 16000 | Prelims
22 | Kone (LPO HM-201A22002/0086) - CTU use Lifts (1 Nos)- from 19.06.22 | 64000 | 16000 | Prelims
23 | Kone (LPO HM-201A22002/0138) - CTU Lifts (2 Nos)- for Dec 22 | 96000 | 16000 | Prelims
24 | Laidlow (LPO HM-201A22002/0176)- Ironmongery | 240812.4 | 88258 | ID - Joinery & Finishes
25 | Master Builders Solutions LLC (LPO HM-201A22002/0159) - Emaco | 8400 | 0 | Civil
26 | Master Builders Solutions LLC (LPO HM-201A22002/0170) - Mater top | 18000 | 0 | Civil
27 | Momentum (LPO HM-201A22002/0179)- Ironmongery | 62299.3 | 32454.8 | ID - Joinery & Finishes
28 | New Era Construction (LPO HM-201A22002/00113)- Cobiax Permanent Formwork | 67371.21 | 51376.14 | Civil
29 | Osler Access LLC (LPO HM-201A22002/0166 ) - Cradle Works | 12760 | 0 | Prelims
30 | Smart Office LLC (LPO HM-201A22002/169 ) - DC Furnitire | 9742 | 0 | Prelims
31 | Schirmer- Façade Testing( HM-201A22002/0224) | 5000 | 5000 | Façade: Aluminium and Glass
32 | Spider Access (LPO HM-201A22002/0130)- Column rectification & paint Mock up | 15300 | 0 | Civil
33 | Ostermeier- Supply of manhole covers ( HM-201A22002/0277) | 420090 |  | Civil
34 | Hilti RE 500V4 (HM-201A22002/0183) | 18900 | 0 | Civil
35 | Mobility General- Ironmongery ( HM-201A22002/0185) | 150516 | 11129 | Civil
36 | Osler- Cradle ( HM-201A22002/0188) | 137000 | 137000 | Prelims
37 | Momentum- Ironmongery ( HM-201A22002/0192) | 12202 | 11952 | ID - Joinery & Finishes
38 | Master Emaco ( HM-201A22002/0195) | 9000 | 2952 | Civil
39 | Betec CAD Louvers (HM-201A22002/0267) | 90586.4 | 90586.4 | ID - Joinery & Finishes
40 | Door Controls Glass Trading( HM-201A22002/0206) | 57018 |  | ID - Joinery & Finishes
41 | Osler- Cradle Maintenance ( HM-201A22002/0207) | 14928.57 | 11428.57 | Prelims
42 | Amalgam- Traffic Signs ( HM-201A22002/0210) | 3003 | 0 | Prelims
43 | Al Areej AC- Temp AC's ( HM-201A22002/0216) | 26500 | 0 | Prelims
44 | Mobility General- Ironmongery ( HM-201A22002/0222) | 13640 | 13640 | ID - Joinery & Finishes
45 | Schirmer Safety Consultants (LPO HM-201A22002/0065)- Façade Inspection Services | 11500 | 11500 | Façade: Aluminium and Glass
46 | Neotech Engineering (HM-201A22002/228) | 8518 | 0 | Civil
47 | Neotech Engineering (HM-201A22002/229) | 2770 | 0 | Civil
48 | Hilti RE 500V4 (HM-201A22002/0231) | 31500 | 12600 | Civil
49 | Styro polystyrene (HM-201A22002/0234) | 6875 | 3079.99 | Civil
50 | Arabuild Tiles (HM-201A22002/0237) | 480000 | 358694.4 | ID - Joinery & Finishes
51 | Smart Office Furnitures ( HM-201A22002/0240) | 1439 | 0 | Prelims
52 | Doormax Ironmongery (HM-201A22002/0252) | 223860.28 | 99628.28 | Civil
53 | Mobility General Trading (HM-201A22002/0273) | 17100 | 17100 | ID - Joinery & Finishes
54 | Doormax Ironmongery (HM-201A22002/0280) | 13148 | 13148 | ID - Joinery & Finishes
55 | Styro Polystyrene (HM-201A22002/0281) | 46000 | 46000 | ID - Joinery & Finishes
| TOTAL AMOUNT | 4541946.5 | 1676344.24
Note on E42: Himal Kosala: HVAC covers

## Annexure 9-OHP
Sky Palaces Real Estate Development LLC
PAYMENT CERTIFICATE - Annexure 09 - OVERHEAD & PROFIT CALCULATION
Project: Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor :Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : Base Build Works |  | Currency: | AED
Description |  |  | Value
A | MEP Subcontractor's OHP (12.5%)
| Total Preliminaries - MEP |  |  | 10075616.1172
| Total Direct Works - MEP |  |  | 24978840.9327
| Total Provisional Sum Packages - MEP |  |  | 2343672.0114
| Advcances - MEP |  |  | 1404296.996
| Amount Considered for MEP Subcontractor's OHP (12.5%) |  |  | 38802426.0572
B | Main Contractor's OHP on MEP (10%)
Add
| Total Carried to Payment Certificate |  |  | 42248432.3184
Ddt
| KMEP OHP for MEP Advances |  |  | -175537.1245
| Amount Considered for Main Contractor's OHP on MEP (10%) |  |  | 42072895.1939
C | Main Contractor's OHP (12.5%)
Add
| Total Preliminaries - Civil |  |  | 24208762.7728
| Total Direct Works - Civil |  |  | 17595468.7224
| Total Provisional Sum Packages - Civil |  |  | 32471607.731
| Advances - Civil |  |  | 3362864.0635
Ddt
| KID Work Done |  |  | -1158076.8988
| Amount Considered for Main Contractor's OHP (12.5%) |  |  | 76480626.3909

## Annexure 10-Retention
Sky Palaces Real Estate Development LLC
Annexure 10 - RETENTION CALCULATION
Project: Plot - 18 | Certificate Date: | 2023-01-23
Contractor :Khansaheb Civil Engineering LLC | Certificate No: | KCE-11
Contract :Main Works | Currency: | AED
Description |  | Value
Value of MEP works completed in this Certificate |  |  | 42248432.3184
Ddt: MEP Preliminaries |  |  | -1487337.94
Ddt: MEP OH/Profit |  |  | -4850303.2572
Ddt: MEP Staff |  |  | -8588278.1772
Value of Provisional Sum works completed in this Certificate |  |  | 31640521.631
Total value of works applicable for the retention |  |  | 58963034.5751
Retention of this Certificate |  | 10% | 5896303.4575

## Annexure 11-Advance Recovery
Sky Palaces Real Estate Development LLC
PAYMENT CERTIFICATE - Annexure 11 - ADVANCE PAYMENTS AND RECOVERY
Project: Plot - 18 |  | Certificate Date: | 2023-01-23
Contractor :Khansaheb Civil Engineering LLC |  | Certificate No: | KCE-11
Contract : Base Build Works |  | Currency: | AED
Description |  |  | Value
A | Advance Payments
1 | Mobilization Payment as per Clause 30 |  |  | 6000000
2 | On Account Payment as per Clause 33 |  |  | 6000000
3 | Advances to Sub-Contractors -Refer to the attached Summary for details |  |  | 11638476.02
| Total Advance Payment |  |  | 23638476.02
B | Advance Payment Recovery
4 | Recovery from Mobilization Payment - A.1 |  |  | 0
5 | Recovery from on Account Payment -A.2 |  |  | 0
6 | Recovery from advances to Sub-Contractors- A.3 |  |  | 2579453.1403
7 | Total -Advance Payment Recovery |  |  | 2579453.1403
| Employer's Representative | Contractor's Representative

## Annexure 12-Previous Payments
Previous Certified Value - Refer Annexure 12
Project Name : |  | Plot 18, Business Bay Dubai, UAE
Employer : |  | Sky Palaces Real Estate Development LLC
Consultant: |  | Khansaheb Civil Engineering LLC
Payment Cert. No. |  | KCE-11 | Budget |  | 194951735 | Dated Raised: | 2023-01-23
Contract Title: |  | Main Works
SN | PC No. | INVOICE NO. |  | PHASE |  | PREVIOUS CERTIFIED VALUE | CERTIFIED TO DATE
1 | PC-1 | Application No. 1 |  | Mobilization Payment as per Clause 30 |  | 6000000 | 6000000
2 | PC-2 | Application No. 2 |  | On Account Payment as per Clause 33 |  | 6000000 | 6000000
3 | PC-3 | Application No. 3 |  | IPA No.3-Period Ending April 2022 |  | 2104452.12 | 2104452.12
4 | PC-4 | Application No. 4 |  | IPA No.4 -Period Ending May 2022 |  | 11118319.2 | 11118319.2
5 | PC-5 | Application No. 5 |  | IPA No.5 -Period Ending June 2022 |  | 11047382.2133 | 11047382.2133
6 | PC-6 | Application No. 6 |  | IPA No.6 -Period Ending July 2022 |  | 12807977.889 | 12807977.889
7 | PC-7 | Application No. 7 |  | IPA No.7 -Period Ending August 2022 |  | 19982204.0294 | 19982204.0294
8 | PC-8 | Application No. 8 |  | IPA No.8 -Period Ending September 2022 |  | 15491078.9473 | 15491078.9473
9 | PC-9 | Application No. 9 |  | IPA No.9 -Period Ending October 2022 |  | 19804921.867 | 19804921.867
10 | PC-10 | Application No. 10 |  | IPA No.10 -Period Ending November 2022 |  | 21126467.64 | 21126467.64
11 | PC-11 | Application No. 11 |  | IPA No.11 -Period Ending December 2022 |  |  | 19971554.879
TOTAL CERTIFIED | [5 empty] | 125482803.906 | 145454358.785

## Staff Cost Summary
Sky Palaces Real Estate Development LLC
PAYMENT CERTIFICATE - STAFF COST
STAFF COST SUMMARY
| Staff Cost | Previous | This Month | Cumulative
| Civil -staff | 8249552.44 | 1299435.1818 | 9548987.6218
| MEP staff | 6303944.1655 | 2284334.0116 | 8588278.1772

## Civil Staff Cost Dec 22
KHANSAHEB CIVIL ENGINEERING | [32 empty] | Calendar days | Calendar days | 31
DORCHESTER HOTEL & RESIDENCES | [33 empty] | Ddt Saturdays & Sundays, Holidays | 9
[33 empty] | Working days (exc Sat & Sun) | Working days (exc Sat & Sun) | 22
STAFF ALLOCATION - DECEMBER 2022
| DESIGNATION | NAME | Tender Headcount | 2022-12-01 | [30 empty] | Alloc'n (wkg days) | Alloc'n (Mth) | MONTHLY RATE | TOTAL AMOUNT (AED)
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31
[35 empty] | 0 | 0
Project Management Team
| Contracts Manager | Darren Cook |  | 0.45 | 0.45 |  |  | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 |  |  | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 |  |  | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 |  |  | 0.45 | 0.45 | 0.45 | 0.45 | 0.45 |  | 9.9 | 0.45 | 78000 | 35100
1 | Project Director (SPM) | Chris McCann | 1 | [31 empty] | 22 | 1 | 71500 | 71500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
2 | Project Manager |  | 0 | [31 empty] | 0 | 0 | 54200 | 0
Execution Team
3 | Snr. Construction Manager |  | 0 | [31 empty] | 0 | 0 | 0 | 0
4a | Construction Manager | Hussein Naser Hussein | 1 | [31 empty] | 22 | 1 | 49800 | 49800 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
4b | Construction Manager | Sam Sutherland | 1 | [31 empty] | 22 | 1 | 49800 | 49800 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
4c | Construction Manager | Nanjappa | [32 empty] | 22 | 1 | 49800 | 49800 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
5 | Project Eng. / PM (Finishes) | Ali Saadeddine | 4 | [31 empty] | 22 | 1 | 37700 | 37700 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
5a | Project Eng. / PM (Finishes) | Shivakumaran P | [32 empty] | 22 | 1 | 37700 | 37700 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
5b | Project Eng. / PM (Finishes) | Justus Angelus | [32 empty] | 22 | 1 | 37700 | 37700 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
5c | Project Eng. / PM (Finishes) | Vinod Nandikaramadam | [32 empty] | 22 | 1 | 37700 | 37700 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6 | Snr. Engineer (Finishes) | Prabakaran Kuppusamy | 8 | [31 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6a | Senior Site Engineer | Mohammed Shahid | [32 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6b | Senior Site Engineer | Riyaz Mohammed | [32 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6c | Senior Site Engineer | Nicholas Amoah | [32 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6d | Senior Site Engineer | Mahmoud Ibrahim | [32 empty] | 12 | 0.54545 | 16100 | 8781.8182 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16
6e | Senior Site Engineer | Karthick Kannan | [32 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6f | Senior Site Engineer | Saibalaji Samulu | [32 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6g | Senior Site Engineer | Jijo Jacob | [32 empty] | 7 | 0.31818 | 16100 | 5122.7273 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9
6h | Senior Site Engineer | Masco Thangaraju | [32 empty] | 22 | 1 | 16100 | 16100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6j | Snr. Engineer (Finishes) | Mani Kandan | [32 empty] | 15 | 0.68182 | 16100 | 10977.2727 | bar: 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6k | Snr. Engineer (Finishes) | Sawaf Manamkandath | [32 empty] | 10 | 0.45455 | 16100 | 7318.1818 | bar: 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6l | Snr. Engineer (Finishes) | Anuj Johnson | [32 empty] | 8 | 0.36364 | 16100 | 5854.5455 | bar: 2022-12-01 21 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6m | Snr. Engineer (Finishes) | Ahmed Hosny | [32 empty] | 6 | 0.27273 | 16100 | 4390.9091 | bar: 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6n | Site Engineer - Hired | Saneesh Melethil Mohan | [32 empty] | 22 | 1 | 9697 | 9697 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
6p | Site Engineer - Hired | Lawrence Chute | [32 empty] | 22 | 1 | 9500 | 9500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7 | Foreman (Finishes) | Sharwan Kumar Jangid | 15 | [31 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7a | Foreman (Finishes) | Vanarasu Mokkai | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7b | Foreman (Finishes) | Kuttaiah Voterira P | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7c | Foreman (Finishes) | Victor Benatefame | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7d | Foreman (Finishes) | Jagan Shanmugam | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7e | Foreman (Finishes) | Rajendra Kumar Jangir | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7f | Foreman (Finishes) | Abdul Malik | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7g | Foreman (Finishes) | Jagroop Singh | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7h | Foreman (Finishes) | Mohan Kammarj | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7J | Foreman (Finishes) | Bahuleyan | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7k | Foreman (Finishes) | Babyajith | [32 empty] | 0 | 0 | 8100 | 0
7L | Foreman (Finishes) | Vikas Chavan | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7m | Foreman (Finishes) | Viral kumar | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7n | Foreman (Finishes) | Zahidul Hussain | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7o | Foreman (Finishes) | Thatchinamoorthy | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7p | Foreman (Finishes) | Abdul Jaleel | [32 empty] | 22 | 1 | 8100 | 8100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7q | Foreman - Hired | Bilal Rashed | [32 empty] | 7 | 0.31818 | 4420 | 1406.3636 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9
7r | Foreman - Hired | MD Akramul | [32 empty] | 22 | 1 | 4420 | 4420 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7s | Foreman - Hired | Usama Amir | [32 empty] | 22 | 1 | 4420 | 4420 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7t | Foreman - Hired | Senthil Kalian | [32 empty] | 22 | 1 | 4420 | 4420 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7u | Foreman - Hired | Saiful Islam | [32 empty] | 22 | 1 | 4420 | 4420 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
7v | Foreman - Hired | Mohammed Rajib | [32 empty] | 22 | 1 | 4420 | 4420 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
8 | Charge Hand |  | 0 | [31 empty] | 0 | 0 | 4000 | 0
Support Staff (Technical)
9 | Design Manager | Matt Ibbotson | 0 | [31 empty] | 5 | 0.22727 | 56800 | 12909.0909 | bar: 2022-12-01 2; 2022-12-01 9; 2022-12-01 16; 2022-12-01 23; 2022-12-01 30
10 | Design Coordinator | Sukesh Nair | 2 | [31 empty] | 22 | 1 | 25200 | 25200 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
10a | Design Coordinator | Shihab Chandrathil | [32 empty] | 22 | 1 | 25200 | 25200 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
10b | Design Coordinator | Sreejith Mala Thodikayil | [32 empty] | 22 | 1 | 25200 | 25200 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
10c | Design Coordinator | Anitha Kumari | [32 empty] | 22 | 1 | 25200 | 25200 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
11 | MEP Coordinator (Engineering) | Jainulabudeen | 2 | [31 empty] | 22 | 1 | 22600 | 22600 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
11a | MEP Coordinator (Engineering) | Murali Krishnan | [32 empty] | 22 | 1 | 22600 | 22600 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
12 | BIM Modeller | Olivia Castro | 1 | [31 empty] | 0 | 0 | 25200 | 0
13 | Draughtsman | Dileep Mathew | 2 | [31 empty] | 22 | 1 | 14300 | 14300 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
13a | Draughtsman | Sumesh Thekkath | [32 empty] | 22 | 1 | 14300 | 14300 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
13b | Draughtsman | Sunil Samuel | [32 empty] | 22 | 1 | 14300 | 14300 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
14 | QA/QC Manager | Kurian Rajesh | 1 | [31 empty] | 22 | 1 | 29100 | 29100 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
15 | QA/QC Inspectors |  | 1 | [31 empty] | 0 | 0 | 19500 | 0
16 | HSE Manager | Andrew Cook | 0.2 | [31 empty] | 0 | 0 | 68500 | 0
17 | HSE Officer | Arjun Anand | 2 | [31 empty] | 0 | 0 | 19500 | 0
17a | HSE Officer | Albin Bijesh | [32 empty] | 22 | 1 | 19500 | 19500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
17b | HSE Officer | Srinivas T | [32 empty] | 22 | 1 | 19500 | 19500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
17c | HSE Officer | Anoop R P | [32 empty] | 9 | 0.40909 | 19500 | 7977.2727 | bar: 2022-12-01 20 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
18 | Commercial Manager | Kevin Davies | 0.6 | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  |  | 0.8 | 0.8 | 0.8 | 0.8 | 0.8 |  | 17.6 | 0.8 | 78000 | 62400
19 | Procurement Manager (SQS) |  | 2 | [31 empty] | 0 | 0 | 28000 | 0
20 | Procurement Assistant | Donavelle B Maquimot | 1 | [31 empty] | 22 | 1 | 8300 | 8300 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
20a | Procurement Assistant | Sirajudeen N. M. | [32 empty] | 22 | 1 | 8300 | 8300 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
21 | Snr. / Project Quantity Surveyor | Saman kulasooriya | 0 | [31 empty] | 22 | 1 | 54200 | 54200 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
22 | Quantity Surveyor / Cost Control | Anil Kumar | 2 | [31 empty] | 22 | 1 | 17500 | 17500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
22a | Quantity Surveyor / Cost Control | Mithun Vallar Veetil | [32 empty] | 22 | 1 | 17500 | 17500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
22b | Quantity Surveyor / Cost Control | Shari reji | [32 empty] | 22 | 1 | 17500 | 17500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
23 | Planning Manager / Project Control | Aeneas Cameron | 0.2 | [31 empty] | 0 | 0 | 63700 | 0
24 | Planning Engineer / Logistics Eng. | Taha | 1 | [31 empty] | 22 | 1 | 23900 | 23900 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
24a | Planning Engineer / Logistics Eng. | Farman Karim/Arnold | [32 empty] | 0 | 0 | 23900 | 0
25 | Surveyor | Malik Ijaz Hussain | 3 | [31 empty] | 22 | 1 | 11000 | 11000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
25a | Surveyor | Ahmed Khan | [32 empty] | 22 | 1 | 11000 | 11000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
25b | Surveyor | Nasrullah Khan | [32 empty] | 22 | 1 | 11000 | 11000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
| Administrative Staff | [36 empty] | 0
49 | IT |  | 1 | [31 empty] | 22 | 1 | 14000 | 14000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
50 | Secretary | Queennie Aba | 1 | [31 empty] | 22 | 1 | 7000 | 7000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
50a | Secretary | Cynthia Anne | [32 empty] | 0 | 0 | 7000 | 0
51 | Document Controller | Krishan Kumar | 1 | [31 empty] | 0 | 0 | 7000 | 0
51a | Document Controller | Pitchappan Perikarappan | [32 empty] | 22 | 1 | 7000 | 7000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
51b | Document Controller | Sanjiv Kumar | [32 empty] | 22 | 1 | 7000 | 7000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
52 | Male Nurse | Sonu Varghese | 1 | [31 empty] | 22 | 1 | 6500 | 6500 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
52a | Male Nurse | Sunil Thomas | [32 empty] | 0 | 0 | 6500 | 0
Accounts Staff
53 | Accts. Asst. |  | 0 | [31 empty] | 0 | 0 | 8300 | 0
54 | Store Keeper | Mohammad Rizwanullah | 1 | [31 empty] | 22 | 1 | 7000 | 7000 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
55 | Store Asst. |  | 1 | [31 empty] | 0 | 0 | 4300 | 0
56 | Time Keeper | Sarvjit | 1 | [31 empty] | 22 | 1 | 4300 | 4300 | bar: 2022-12-01 1 to 2022-12-01 2; 2022-12-01 5 to 2022-12-01 9; 2022-12-01 12 to 2022-12-01 16; 2022-12-01 19 to 2022-12-01 23; 2022-12-01 26 to 2022-12-01 30
| TOTAL FOR STAFF |  | 58 | [34 empty] | 1299435.1818
Notes:
1 | All rates are Net and subject to overhead and profit in accordance with Schedule 2 - Basis of Calculating the Contract Price.
2 | The Contractor shall be reimbursed for its staff (and that of its MEP Subcontractor) in accordance with Schedule 2 - Basis of Calculating the Contact Price.
3 | We have not made any amendment to the designations as these and the duration on site will need further development and agreement in due course in conjunction with the agreement of Programme.
4 | We have provided for MEP Subcontractor staff and these MEP personnel will form part of the separate MEP contractors management team | [35 empty] | TOTAL STAFF COST BILLED FOR DEC-22 (KCE IPA 11) | 1299435.1818
5 | We note that the role of Contracts Manager is absent from your schedule, this designation we will be an integral part of the on-site management team.
6 | We have left the rate for Senior Construction Manager blank as this role is equivalent to our designation of a Construction Manager
7 | We have used the KCE rate for a QA/QC Engineer as QA/QC Inspector in item 15.
8 | We have used the KCE rate for HSE Supervisor as HSE Officer in item 17.

## KMEP -IPC
PROJECT |  |  | DORCHESTER HOTEL AND RESIDENCES | [7 empty] | KCE-11
EMPLOYER |  |  | SKY PALACES REAL ESTATE DEVELOPMENT LLC
EMPLOYER'S REP |  |  | OMNIYAT CONCEPT INVESTMENTS LLC
ENGINEER |  |  | BREWER SMITH BREWER GULG ( BSBG )
CONTRACTOR |  |  | KHANSAHEB CIVIL ENGINEERING - MEP DIVISION
FOR THE PERIOD ENDING |  |  | 2022-10-31
Item | Description | Contractor | Contract Amount (AED) | Anticipated Contract Amount (AED) | Progress Completion (%) |  |  | Work Done (AED) |  |  | Remarks
[5 empty] | Previous | This Month | Cumulative | Previous | This Month | Cumulative
| PRELIMINARIES |  | 11059900 | 11547237.94 |  |  |  | 8833948.6855 | 1241667.4316 | 10075616.1172
A | MEP Staff | KMEP | 10059900 | 10059900 | 74.3% | 11.07% | 85.37% | 7474618.4055 | 1113659.7716 | 8588278.1772
B | MEP Preliminaries | KMEP | 1000000 | 1487337.94 | 91.39% | 8.606% | 100% | 1359330.28 | 128007.66 | 1487337.94
| DIRECT WORKS |  | 22000000 | 32351673.7929 |  |  |  | 21188004.0133 | 3790836.9194 | 24978840.9327
C | MEP Labour Supply | KMEP | 9691616.2421 | 15122050.735 | 85% | 15% | 100% | 12853596.905 | 2268453.83 | 15122050.735
D | MEP Work Approvals | KMEP | 6850000 | 9911100.37 | 59.39% | 12.85% | 72.24% | 5760553.09 | 1370625.36 | 7131178.45
E | MEP Material Purchases | KMEP | [5 empty] | 125828.59 | -97397.42 | 28431.17
F | Historical Cost under W.A | KMEP |  | 892511.93 | 90.99% | -1.381% | 89.61% | 812072.34 | -12324.05 | 799748.29
G | Fire Protection | FIREX | 1848858 | 2012658 | 56.76% | 4.607% | 61.37% | 1142381.4423 | 92719.2482 | 1235100.6905
H | BMS works | JCI | 400386 | 413786 | 15.94% | 0% | 15.94% | 65964.5899 | 0 | 65964.5899
I | Gas works | UGAZ | 374640 | 374640 | 45.07% | 5.501% | 50.57% | 168840 | 20608 | 189448
J | HWS Equipments | FJT | 359100 | 1158100 | 0% | 0% | 0% | 0 | 0 | 0
K | ELV works | SIS | 2266294.7579 | 2274721.7579 | 5.226% | 5.026% | 10.25% | 118886.8361 | 114330.5336 | 233217.3697
L | Fire Stop - Sealant Works | FSME | 209105 | 192105 | 72.81% | 17.61% | 90.42% | 139880.22 | 33821.4176 | 173701.6376
| PS WORKS |  | 9400000 | 9686412.1578 |  |  |  | 1791197.2249 | 552474.7865 | 2343672.0114
M | Lifts | KONE | 1800000 | 918410.634 | 6.615% | 0% | 6.615% | 60750 | 0 | 60750
N | GRMS and Access control system | Creation Gulf | 2300000 | 730824 | 14.47% | 0% | 14.47% | 105770.5869 | 0 | 105770.5869
O | FOH LV/ ELV Final Point wiring |  |  | 1873397.3838 | 11.51% | 3.836% | 15.35% | 215654.418 | 71859.2065 | 287513.6245
P | Sanitarywares | SANIPEX/ AF | 1000000 | 1746063.96 | 11.2% | 2.173% | 13.38% | 195616.76 | 37946.1 | 233562.86
Q | Lighting fixtures | P&S and HSE | 4300000 | 4417716.18 | 27.47% | 10.02% | 37.49% | 1213405.46 | 442669.48 | 1656074.94
| Total MEP Amount |  | 42459900 | 53585323.8907 |  |  |  | 31813149.9237 | 5584979.1375 | 37398129.0612
|  |  | 12.5% | 12.5% |  |  |  | 12.5% | 12.5% | 12.5%
|  |  | 5307487.5 | 5137734.47 |  |  |  | 1227949.53 | 554747.4 | 1782696.93
|  |  | 47767387.5 | 46239610.25 |  |  |  | 11051545.8 | 4992726.58 | 16044272.38
PRELIMINARIES
[7 empty] | MEP Staff | 0.314 | 0.242 | 0.292
[7 empty] | MEP Preliminaries | 0.046 | 0.024 | 0.039
DIRECT WORKS
[7 empty] | MEP Labour Supply | 0.366 | 0.502 | 0.408
[7 empty] | MEP Work Approvals | 0.143 | 0.151 | 0.146
[7 empty] | MEP Material Purchases | 0.013 | 0.01 | 0.012
[7 empty] | Historical Cost under W.A | 0.076 | 0.005 | 0.054
[7 empty] | Fire Protection | 0.026 | 0.052 | 0.034
[7 empty] | BMS works | 0 | 0 | 0
[7 empty] | Gas works | 0 | 0 | 0
[7 empty] | HWS Equipments | 0 | 0 | 0
[7 empty] | ELV works | 0.01 | 0.007 | 0.009
[7 empty] | Fire Stop - Sealant Works | 0.005 | 0.009 | 0.006
PS WORKS
[7 empty] | Lifts | 0 | 0 | 0
[7 empty] | GRMS and Access control system | 0 | 0 | 0
[7 empty] | FOH LV/ ELV Final Point wiring | 0 | 0 | 0
[7 empty] | Sanitarywares | 0 | 0 | 0
[7 empty] | Lighting fixtures | 0 | 0 | 0

## Adjustments
Sky Palaces Real Estate Development LLC
Adjustments
Project: Plot - 18 |  |  |  | Certificate Date: | 2023-01-23
Contractor:Khansaheb Civil Engineering LLC |  |  |  | Certificate No: | KCE-11
Contract :Base Build Works |  |  |  | Currency: | AED
SN | Description | Bill Category | IPA Ref | Amount | Remarks
01 | Visa Cost of labours | Labour cost | IPA 08 | 2797.41 | Visa cost is already included in the hiring rate | Category | Amount
02 | Visa Cost of labours | Labour cost | IPA 09 | 1259.8 | Visa cost is already included in the hiring rate | Material Cost | 58239.73
03 | Included VAT | Overheads | IPA 10 | 521.189 | Telecommunication, Chris McCann (Petty Cash) | Labour cost | 4057.21
04 | TXM Manpower cost adjustment from material transaction- August 22 | Material Cost | IPA 10 | 9071.54 |  | Plant Cost | 0
05 | TXM Manpower cost adjustment from material transaction- September 22 | Material Cost | IPA 10 | 9384.76 |  | Overheads | 48681.189
06 | TXM Manpower cost adjustment from material transaction- October 22 | Material Cost | IPA 10 | 9051.18 |  | TOTAL | 110978.129
07 | TXM Manpower cost adjustment from material transaction- November 22 | Material Cost | IPA 10 | 9951.73
08 | TXM Manpower cost adjustment from material transaction- November 22 | Material Cost | IPA 10 | 1583.52
09 | TXM Manpower cost adjustment from material transaction- December 22 | Material Cost | IPA 11 | 19197
10 | IT costs adjustment from Overhead transaction for June 22 | Overheads | IPA 10 | 8370.53
11 | IT costs adjustment from Overhead transaction July 22 | Overheads | IPA 10 | 11789.47
12 | IT costs adjustment from Overhead transaction August 22 | Overheads | IPA 10 | 14000
13 | IT costs adjustment from Overhead transaction September 22 | Overheads | IPA 10 | 14000
110978.129

## Historical Debts
Project: Plot - 18
Contractor :Khansaheb Civil Engineering LLC
Contract : Base Build Works
RPJV Historical Debts
Item No. | Cost Items | Previous | This Month | Cumulative | Remarks
1 | Culligan International Emirate | 218423.22 | 0 | 218423.22
2 | Derrick Crane Historical Debt | 162500 | 0 | 162500
3 | Generators Historical Debt | 278110.35 | 0 | 278110.35 | Paid to KCE for Al SHOLA
659033.57
4 | Al Hayath- GRP Lining | 110160 | 0 | 110160
5 | TWIC Insulation Materials Supply | 51944.8 | 0 | 51944.8
TOTAL COST FOR HISTORICAL DEBTS |  | 821138.37 | 0 | 821138.37