## SUMMARY
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA
SUMMARY
Sr. No. | Work Item | Agreed Amount | Previous (from Assessment Nov 22) |  | Approved Workdone Dec 22 |  | Previous (from PC Dec 22) |  | This Month |  | Cumulative
|  |  | % | Amount (Dhs) | % | Amount (Dhs) | % | Amount (Dhs) | % | Amount (Dhs) | % | Amount (Dhs)
1 | Remaining Works - BOQ | 1954843.0357 | 42.98% | 840251.0145 | 5.718% | 111776.9255 | 48.7% | 952027.94 | 5.378% | 105139.7964 | 54.08% | 1057167.7364
2 | Variations | 0 |  | 1080100.8013 |  | 561507.8287 |  | 1641608.63 |  | 304506.5225 |  | 1946115.1525
3 | Dayworks | 0 |  | 93967.65 |  | 25347.15 |  | 119314.8 |  | 11592 |  | 130906.8
TOTAL |  | 1954843.0357 | 103% | 2014319.4658 | 35.74% | 698631.9042 | 138.8% | 2712951.37 | 21.55% | 421238.3189 | 160.3% | 3134189.6889
2094443.6128
-1039746.0762

## BOQ
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [5 empty] | 0
PROGRESS BOQ | [5 empty] | 0
| SN NO. | Description | BOQ |  |  |  | CLAIMED - AL RAWDA | [8 empty] | CERTIFIED - OCI | [8 empty] | Remark
[7 empty] | Previous |  |  | This Month |  |  | Cumulative |  |  | Previous |  |  | This Month |  |  | Cumulative
|  |  | QTY | Unit | Rate | Amount UAE Dirhams | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount
EXTERNAL CEMENT BOARD WORKS
| A | ORIGINAL SUBCONTRACT WORKS
EXTERNAL CEMENT BOARD WORKS
| A | External Fibre Cement Board Ceiling | [9 empty] | 0 | [8 empty] | 0
|  | External Fibre Cement board ceiling including,all fixings, fittings, tapping, jointing, supporting frame work, sealant between panels and accessories complete all in accordance with the drawings and specifications | 3688.0215 | m2 | 140 | 516323.003 | [5 empty] | 0 |  |  |  | 2646.425 | 71.76% | 370499.5 | 0 | 0% | 0 | 2646.425 | 71.76% | 370499.5
[12 empty] | 0 | [8 empty] | 0
| B | Coffered Ceiling
[12 empty] | 0 | [8 empty] | 0
|  | Coffered ceiling including,all fixings, fittings, tapping, jointing, supporting frame work, sealant between panels and accessories complete all in accordance with the drawings and specifications | 412.92 | m2 | 375 | 154845 | [9 empty] | 355.9 | 0.86191 | 133462.5 | 15.728 | 3.809% | 5898 | 371.628 | 90% | 139360.5
[12 empty] | 0 | [8 empty] | 0
| C | External Dry Wall System | [9 empty] | 0 | [8 empty] | 0 |  |  |  | 0
| D | Bulkhead and Shadow Gap
[12 empty] | 0 | [8 empty] | 0
|  | Bulkhead all around the columns and shadow gaps for all the types of external ceilings as per the drawings and specifications | 1 | Item |  | 87017 | [10 empty] | 0 | 0 | 0.9 | 90% | 78315.3 | 0.9 | 90% | 78315.3
[12 empty] | 0 | [8 empty] | 0 |  |  |  | 0
| E | BOH Painting
| 1 | Skim Coat 1-2mm to receive Low VOC | 1470 | m2 | 13.5 | 19845 | 209.116 | 14.23% | 2823.066 |  | 0% | 0 | 209.116 | 14.23% | 2823.066 | 1234.8772 | 84.01% | 16670.8422 | 88.1228 | 5.995% | 1189.6578 | 1323 | 90% | 17860.5
| 2 | Low VOC acrylic emulsion paint applied to a base (PA.04) | 13659.4 | m2 | 15 | 204891 | 167.44 | 1.226% | 2511.6 |  | 0% | 0 | 167.44 | 1.226% | 2511.6 | 233.3765 | 1.709% | 3500.6478 | 497.2935 | 3.641% | 7459.4022 | 730.67 | 5.349% | 10960.05
| 3 | Epoxy Resin Painting to Wall | 4452 | m2 | 45 | 200340 | [9 empty] | 945.216 | 21.23% | 42534.72 | 592.564 | 13.31% | 26665.38 | 1537.78 | 34.54% | 69200.1
| GRAND TOTAL - UAE DIRHAMS - EXTERNAL CEILING |  |  |  | 100% | 1183261.003 |  | 0.4508% | 5334.666 |  | 0 | 0 |  | 0.4508% | 5334.666 |  | 47.89% | 566668.21 |  |  | 119527.74 |  | 57.99% | 686195.95 | 1177926.337
CEILING, PARTITION AND WALL PANELLING
| 1 | Guest room Ceiling
To bathroom & toilet
|  | White N* 2005-Matte Finish Ceiling finishes HTL-PT-04 | 184.5145 | m2 | 95 | 17528.8775 | [10 empty] | 0 | 0 | 166.0631 | 90% | 15775.9897 | 166.0631 | 90% | 15775.9897
0
PARTITIONS
| 2 | WALL PANELLING
0
|  | Supply and fixing of Gypsum Sheet Panel & GRG Mouldings | 129.6 | m2 | 230 | 29808
0
| 3 | INTERNAL PAINTING WORKS | 3632.53 | m2 | 17 | 61753.01
|  | Guest room | [9 empty] | 0 |  |  |  | 544.8795 | 15% | 9262.9515 | 0 | 0% | 0 | 544.8795 | 15% | 9262.9515
| 4 | EXTERNAL PAINTING WORKS | [9 empty] | 0
|  | External Fibre Cement Board Ceiling | 6477.318 | m2 | 22 | 142500.996 | [9 empty] | 2437.975 | 0.37639 | 53635.45 | 1076.604 | 16.62% | 23685.288 | 3514.579 | 54.26% | 77320.738
(Hotel Level 1 to L28) (Res L1 to L29)
| 5 | Corridor Ceilings | [9 empty] | 0
| a | Gypsum board Ceiling | 448.036 | m2 | 80 | 35842.88 |  |  |  | 117 | 26.11% | 9360 | 117 | 26.11% | 9360 | 327 | 0.72985 | 26160 | 76.2324 | 17.01% | 6098.592 | 403.2324 | 90% | 32258.592
0
| b | bulk head, 120mm high | 392.767 | m2 | 20 | 7855.34 |  |  |  | 114 | 29.02% | 2280 | 114 | 29.02% | 2280 | 337.056 | 85.82% | 6741.12 | 16.4343 | 4.184% | 328.686 | 353.4903 | 90% | 7069.806
| c | Ceiling Painting HTL-PT-09 | 661.216 | m2 | 17 | 11240.672 |  |  |  | 66.88 | 10.11% | 1136.96 | 66.88 | 10.11% | 1136.96 | 431.808 | 65.31% | 7340.736 | 0 | 0% | 0 | 431.808 | 65.31% | 7340.736
0
| d | bulk head, 120mm high Painting | 590.38 | m2 | 10 | 5903.8 |  |  |  | 109.6 | 18.56% | 1096 | 109.6 | 18.56% | 1096 | 399.968 | 67.75% | 3999.68 | 0 | 0% | 0 | 399.968 | 67.75% | 3999.68
| e | Light cove 100x40mm | 501.5475 | m2 | 85 | 42631.5375 |  |  |  | 220.55 | 43.97% | 18746.75 | 220.55 | 43.97% | 18746.75 | 400.864 | 0.79925 | 34073.44 | 50.5287 | 10.07% | 4294.9437 | 451.3927 | 90% | 38368.3837
| f | Light cove, Painting | 625.29 | m2 | 10 | 6252.9 |  |  |  | 135.2 | 21.62% | 1352 | 135.2 | 21.62% | 1352 | 427.1552 | 68.31% | 4271.552 | 0 | 0% | 0 | 427.1552 | 68.31% | 4271.552
| g | Supply and Installation of Drywall Lining Work (Level 7 to 10 Corridor) and (Level 11 to 16 & 19 to 27) in front fo corewall-Corridor),(Level 7 to 16 & 19 to 27 - Lift Lobby) Furring Chanel 600mm @with 15mm RG Gypsum board | 757.5294 | m2 | 100 | 75752.94 | 492.3941 | 65% | 49239.411 | 122.7841 | 0% | 12278.414 | 615.1783 | 65% | 61517.825 | 659.333 | 87.04% | 65933.3 | 22.4435 | 2.963% | 2244.346 | 681.7765 | 90% | 68177.646
| 6 | BOH Painting to Basement & Staircase | 2117.2727 | m2 | 11 | 23289.9997
[12 empty] | 0 | [8 empty] | 0
| 7 | Gypsum Shaft wall to Hotel tower service areas L1 to Roof | 730.452 | m2 | 290 | 211831.08 | [12 empty] | 130.6862 | 17.89% | 37898.9864 | 130.6862 | 17.89% | 37898.9864
[12 empty] | 0 | [8 empty] | 0
| 8 | Rockwool insulation above External Soffits | 2650.4 | m2 | 37.5 | 99390 | [9 empty] | 1657.722 | 0.62546 | 62164.575 | 188.324 | 7.105% | 7062.15 | 1846.046 | 69.65% | 69226.725
[12 empty] | 0 | [8 empty] | 0
| GRAND TOTAL - UAE DIRHAMS - (Internal Painting Works) |  |  |  | 100% | 771582.0327 |  | 0% | 0 |  | 5.994% | 46250.124 |  | 12.38% | 95489.535 |  | 35.46% | 273582.8045 |  | 12.62% | 97388.9819 |  | 48.08% | 370971.7864
| GRAND TOTAL - UAE DIRHAMS |  |  |  | 100% | 1954843.0357 |  |  |  |  | 2.366% | 46250.124 |  |  | 100824.201 |  | 42.98% | 840251.0145 |  | 11.1% | 216916.7219 |  | 54.08% | 1057167.7364
178435.799
184055.83
|  |  | 1840.5583 |  |  | 41.16% | [14 empty] | -38480.9229
41.12%
Note on X24: Himal Kosala: As discuss, until approved WIR submit only allow 90%
Note on X32: Himal Kosala: As discuss, until approved WIR submit only allow 90%
Note on X35: Himal Kosala: As discuss, until approved WIR submit only allow 90%
Note on X51: Himal Kosala: As discuss, until approved WIR submit only allow 90%
Note on X68: Himal Kosala: As discuss, until approved WIR submit only allow 90%

## VO List
SECTION 03 - VARIATION SCHEDULE
No | Sub Cont VO No | Description | WA Ref # | SUBMITTED AMOUNT | PROGRESS QUANTITY |  |  | PROGRESS AMOUNT
[5 empty] | Previous | This Month | To Date | Previous | This Month | To Date
1 | 1 | Royal crown works & Other balance work | C021 | 456402 | 33.5% | 17.61% | 51.11% | 152878.961 | 80374.9406 | 233253.9016
2 | 2 | VO :02 Supply and Installation of Demise Wall & Shaft Wall at Level -21 &27 & BOH Ceiling G.F To L4 | C036 | 350327 | 64.55% | 6.57% | 71.12% | 226124.308 | 23016.9824 | 249141.2904
3 | 3 | Basement Car parking Painting Works -Anti carbonation | PS010 R2 | 371286.43 | 10% | 35% | 45% | 37128.643 | 129950.2505 | 167078.8935
4 | 4 | External Ceiling Cutting and Finishing Works at Level -5 | PS010 Rev.3 | 47193.6 | 90% | 10% | 100% | 42474.24 | 4719.36 | 47193.6
5 | 5 | Shaft Wall between the electrical and mechanical services works at Level -29 |  | 945.4 | 0% | 0% | 0%
6 | 6 | Supply and Installation of Insulationto wall and edge of slab at Level -24 |  | 477.6 | 0% | 100% | 100% | 0 | 477.6 | 477.6
7 | 7 | Additional Gypsum Wall liner Corridir works at Level -11 to -27 | PS010 Rev.1 | 76286 | 80% | 20% | 100% | 61028.8 | 15257.2 | 76286
8 | 8 | Required plasterboard ceiling @B1 Staff dining room | PS010 Rev.3 | 11473 | 60% | 0% | 60% | 6883.8 | 0 | 6883.8
9 | 9 | Royal Suits, Presidential Suits, Lobbies and Prayer & GYM | PS020 | 668085.92 | 26.66% | 23.19% | 49.85% | 178113.9835 | 154953.6015 | 333067.585
10 | 10 | Shaft Wall between the LPG Pipe services works at all Level | [6 empty] | 0
11 | 11 | Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works | PS010 Rev.3 | 42385 | 100% | 0% | 100% | 42385 | 0 | 42385
12 | 12 | External Ceiling Cutting and Finishing Works at Level -16 | PS010 Rev.4 | 17184 | 95% | 5% | 100% | 16324.8 | 859.2 | 17184
13 | 13 | 2HR FR 150mm thk partition wall at stair 6 between L24 to L28 | PS010 Rev.5 | 25244.36 | 0% | 40% | 40% |  | 10097.744 | 10097.744
14 | 15 | Glass partition secondry support around Acoustic dry wall partition installation at Hotel Level -2 & 3 | PS010 R6 | 18505.31 | 100% | 0% | 100% | 18505.31 | 0 | 18505.31
15 | 16 | Gypsum cladding around steel frame/Aluminium frame & glass to the Duplex suites of 7A type and bed suite 15A type- total 7 floors | PS010 R6 | 17056.2 | 100% | 0% | 100% | 17056.2 | 0 | 17056.2
16 | 16a | Staircase painting work | PS010 R6 | 474871.34 | 29.37% | 25.9% | 55.27% | 139447.8618 | 123003.2512 | 262451.113
17 | 17 | 700X500 mm Core wall opening closing requirement inside stairs mid landing levels | PS010 R6 | 22044.96 | 55.4% | 44.6% | 100% | 12214 | 9830.96 | 22044.96
18 | 18 | Water meter room gypsum tiled false ceiling at Residentiel Level -G.F to 31 | PS010 R6 | 11807.35 | 0% | 0% | 0%
19 | 19 | Corridor arae door partitions -17 Door locations | PS010 R7 | 10200 | 50% | 50% | 100% | 5100 | 5100 | 10200
20 | 20 | Hotel Corridor Level 7-28 Wooden Feature palels are deleted & Proceed with plaster board ceiling and wall | PS010 R7 | 17476.4 | 60% | 40% | 100% | 10485.84 | 6990.56 | 17476.4
21 | 21 | 300X300 Ceiling Cutting and Finishing Works at Level -7 | PS010 R8 | 825 | 100% | 0% | 100% | 825 | 0 | 825
22 | 22 | Ceiling board removal reinstatement at Hotel Level -24,25 | PS010 R8 | 1340.85 | 100% | 0% | 100% | 1340.85 |  | 1340.85
23 | 23 | Removal of balcony Ceiling & Reinstatement at Residential Level -28 | PS010 R8 | 14669.52 | 20% | 0% | 20% | 2933.904 | 0 | 2933.904
24 | 24 | Temporary opening for FAHU Air balancing Level -7 to11 | PS010 R10 | 20130 | 0% | 100% | 100% | 0 | 20130 | 20130
25 | 25 | Repainting to wall and ceiling at Guest level 8 to 16 | PS010 R8 | 185106 | 25% | 60% | 85% | 46276.5 | 111063.6 | 157340.1
26 | 26 | Temporary Internal ceiling openings cutting & Closing at Hotel Level -19 &20 | PS010 R10 | 6600 | 60% | 40% | 100% | 3960 | 2640 | 6600
27 | 27 | Ceiling opening at GF RTL landscape area and lift lobby | PS010 R10 | 5388 | 60% | 40% | 100% | 3232.8 | 2155.2 | 5388
28 | 28 | Ceiling cutting & refinishing works at Residence GF lobby | PS010 R10 | 15890 | 60% | 40% | 100% | 9534 | 6356 | 15890
29 | 29 | Ground floor External ceiling cove alteration for X-L10 light | PS010 R10 | 14400 | 60% | 40% | 100% | 8640 | 5760 | 14400
30 | 30 | Revised shop drawing and necessary moditication as required at Level -3 | PS010 R11 | 2525.25 | 0% | 100% | 100% | 0 | 2525.25 | 2525.25
31 | 31 | Level 2 Residential Podium Corridor ceiling levels & details to be revised | PS010 R11 | 32310 | 60% | 40% | 100% | 19386 | 12924 | 32310
32 | 32 | Temporary Internal ceiling openings cutting & Closing at Hotel Level -10-14 &16 | PS010 R11 | 29700 | 60% | 40% | 100% | 17820 | 11880 | 29700
33 |  | Ceiling board removal reinstatement at Residentiel Level -17 | PS010 R12 | 7812.48 | 0% | 100% | 100% | 0 | 7812.48 | 7812.48
34 |  | Proceed to refix only ceiling grid works House keeping lobby & Garbage room from level 24 to level 29 | PS010 R12 | 2520 | 0% | 100% | 100% | 0 | 2520 | 2520
35 |  | 8A Ceiling board removal reinstatement at Residentiel Level - 8 & 9 | PS010 R12 | 1039.34 | 0% | 100% | 100% | 0 | 1039.34 | 1039.34
36 |  | Ceiling board removal reinstatement balcony foor Drain pipe line at Hotel -9 Level | PS010 R12 | 3259.54 | 0% | 100% | 100% | 0 | 3259.54 | 3259.54
37 |  | Temporary ceiling opening for Electrical de-snagging Hotel Level -11 ,12 & 13 | PS010 R12 | 1320 | 0% | 100% | 100% | 0 | 1320 | 1320
38 |  | 2hr FR 150mm thk Partition wall at Stair 6 between L17 TO L23 | PS010 R12 | 37007.77 | 0% | 40% | 40% | 0 | 14803.108 | 14803.108
39 |  | Supply and Installation of Non -Combustible board in Res Electrical room | PS010 R12 | 5280 | 0% | 100% | 100% | 0 | 5280 | 5280
40 |  | Gypsum Ceiling board removal reinstatement at Hotel Level - 10, 11 | PS010 R12 | 660 | 0% | 100% | 100% | 0 | 660 | 660
41 |  | Installation of Cement board backing for wall marble cladding | PS010 R13 | 51857.8 | 0% | 100% | 100% | 0 | 51857.8 | 51857.8
42 |  | Temporary ceiling opening for Hotel Level -07 to 12 (BW-0933) | PS010 R13 | 24750 | 0% | 100% | 100% | 0 | 24750 | 24750
43 |  | Removing and replacing existing calcium silicate board & Painting worksLevel 5 Residential Heat Cool Pump Room | PS010 R13 | 23960.16 | 0% | 50% | 50% | 0 | 11980.08 | 11980.08
44 |  | Supply and Installation of Shaft Wall at Level -1 to 4 Hotel (House Keeping Lobby ) | PS010 R13 | 8961.44 | 0% | 100% | 100% | 0 | 8961.44 | 8961.44
45 |  | Gypsum board wall cladding over the Main door frame to the corridor areas in Level 7 to 27 | PS010 R13 | 52200 | 0% | 50% | 50% | 0 | 26100 | 26100
46 |  | Room Service Support Area Shaft Wall change from Ground to Level 28 | PS010 R13 | 20262.55 | 0% | 0% |  | 0 | 0 | 0
47 |  | Ceiling board removal reinstatement balcony foor Drain pipe line at Hotel Level | PS010 R13 | 41856 | 0% | 100% | 100% | 0 | 41856 | 41856
48 |  | Additional Access Panel for Hotel Guest Room Level 7 to 16 & 19 to L 27 | PS010R13 | 173135 | 0% | 70% | 70% | 0 | 121194.5 | 121194.5
49 |  | External Ceiling cutting & refixing in Residence GF Corridor | PS010R13 | 4295 | 0% | 100% | 100% | 0 | 4295 | 4295
50 |  | External Ceiling cutting & refixing in Residence GF House keeping lobby entrance | PS010R13 | 4673.28 | 0% | 100% | 100% | 0 | 4673.28 | 4673.28
51 |  | Temporary Internal ceiling openings cutting & Closing -L08 ,Residential Ref BW-0826 | PS010R13 | 7260 | 0% | 100% | 100% | 0 | 7260 | 7260
52 |  | Temporary External ceiling openings cutting & Closing in Ground Floor with Hotel & Residential Ref BW-0925 &928 | PS010R13 | 9800 | 0% | 0% | 0% | 0 | 0 | 0
53 |  | Proceed with additional partitions & Painting for Hotel Level 3 Gen. Management Offices (BW-0937) | PS010R13 | 1465.1 | 0% | 100% | 100% | 0 | 1465.1 | 1465.1
54 |  | Supply & installation of insulation of Ceiling at hotel L2 House keeping lift lobby | PS010R13 | 1096 | 0% | 100% | 100% | 0 | 1096 | 1096
0
[8 empty] | 0 | 0 | 0
TOTAL SUMMARY |  |  |  | 3452607.95 |  |  |  | 1080100.8013 | 1082249.3682 | 2162350.1695
1080100.8013
[5 empty] | Note: Only 90% of Variation Value will approve until OME approval |  |  |  | 1946115.1525
1290257.7805
1191331.5083
-971018.6612

## Dayworks
| Day works | [6 empty] | IPA-05
0 | SECTION 04 - VARIATION SCHEDULE
1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 9 | 10 | 8 | 12 | 13 | 11
|  |  |  | Ref. KCE to Sub-Cont |  |  |  | SVN budged Amount (Total) | PROGRESS Qunatity |  |  | PROGRESS AMOUNT
No | Sub Cont VO No | RGM VON | Description | KCE VO Ref # | qty | Rate |  |  | Previous | This Month | To Date | Previous | This Month | To Date
1 | 14 | 2 | Day Works 1& 2 (29-8-22 to 24-09-22 ) | E11-K121-SS-dm-138 |  |  | PS010 R6 | 38295 | 100% | 0% | 100% | 38295 | 0 | 38295
2 | 25 | 2 | Day Works 3,4,5& 6 (26-9-22 to 22-10-22 ) | E11-K121-SS-dm-138 |  |  | PS010 R9 | 47403 | 75% | 25% | 100% | 35552.25 | 11850.75 | 47403
2 | 33 |  | Day Works 7 & 8 (22-10-22 to 24-11-22 ) |  |  |  | PS010 R11 | 26827.2 | 75% | 25% | 100% | 20120.4 | 6706.8 | 26827.2
|  |  | Day Works 9 |  |  |  |  | 6789.6 | 0% | 100% | 100% | 0 | 6789.6 | 6789.6
|  |  | Day Works 10 |  |  |  |  | 11592 | 0% | 100% | 100% | 0 | 11592 | 11592
0
0
[12 empty] | 0 | 0 | 0
TOTAL SUMMARY | [7 empty] | 130906.8 |  |  |  | 93967.65 | 36939.15 | 130906.8
93967.65
[10 empty] | (CARRIED TO PA) |  |  | 130906.8
COMPANY STAMP
0

## VO 01
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA
VARIATION ORDER 01
| S.N | Description | QTY | Unit | Rate | Amount UAE Dirhams | PROGRESS |  | Remark
[7 empty] | Quantity | Amount
Royal crown works
(USG BORAL TILES )
Hotel -G.F to L28 ,Res G.F to L30 (BOH)
| A | Full System Gypsum Tiles Ceiling -600X600mm | 730.83 | m2 | 90 | 65774.7 | 102.402 | 9216.18
| B | Gypsum Ceiling Tiles Only -600X600mm | 475.72 | m2 | 55 | 26164.6 | 385.578 | 21206.79
Basement -1 (BOH )
(USG BORAL TILES )
| C/1 | Full System -600X600mm Metal Tiles | 448.29 | m2 | 160 | 71726.4 | 292.99 | 46878.4
| C/2 | 600X600mm Metal Tiles only | 441.52 | m2 | 125 | 55190 | 420.37 | 52546.25
| C/3 | Full System Gypsum Tiles Ceiling -600X600mm | 129.46 | m2 | 90 | 11651.4
| C/4 | Gypsum Ceiling Tiles Only -600X600mm | 45.67 | m2 | 55 | 2511.85
Level 3-BOH
CEILING
(USG BORAL TILES )
| D/1 | PB.01 - 600X600X12mm Gypsum Ceiling | 290.182 | m2 | 90 | 26116.38 |  |  |  |  | QTY checked okay
( GYPSEMNA )
| D/2 | MBP.01 - Moisture Resistant Ceiling | 11.34 | m2 | 120 | 1360.8
| D/3 | ACCESS PANEL FOR FCU 600 X 600mm -AP-1 | 2 | Nos | 285 | 570
| D/4 | ACCESS PANEL FOR FCU 300 X 300mm -AP-3 | 1 | Nos | 250 | 250
PARTITIONS - Level 03
( GYPSEMNA )
| E/1 | 100mm Partition Wall To Internal Area Wall Partitions | 164.0764 | m2 | 160 | 26252.224 | 164.0764 | 26252.224
| E/2 | 50mm Partition Wall To Internal Area Wall Partition | 38.304 | m2 | 135 | 5171.04 | 38.304 | 5171.04
| E/3 | Supply and Installation of Drywall Lining Work | 123.428 | m2 | 110 | 13577.08 | 111.0852 | 12219.372
Painting works
| E/4 | Wall & ceiling internal painting works | 537.688 | m2 | 18 | 9678.384 | 483.9192 | 8710.5456
RESIDENTIAL - LEVEL-31
| F | External Fibre Cement Board Ceiling
| F/1 | External Fibre Cement board ceiling including,all fixings, fittings, tapping, jointing, supporting frame work, sealant between panels and accessories complete all in accordance with the drawings and specifications | 470.42 | m2 | 140 | 65858.8 | 296.3646 | 41491.044
| F/2 | Supply and Installation of Rockwool External Ceiling | 470.42 | m2 | 40 | 18816.8
| F/3 | External Painting Cement board Ceiling work | 470.42 | m2 | 28 | 13171.76
| F/4 | Bulkhead all around the columns and shadow gaps for all the types of external ceilings as per the drawings and specifications | 7 | Nos | 1850 | 12950
| F/5 | External Column Painting workS (Type PT 201) | 276.36 | m2 | 28 | 7738.08 | 193.452 | 5416.656 |  | 275.088
| F/6 | External Concrete Column Skimming | 276.36 | m2 | 15 | 4145.4 | 276.36 | 4145.4 | 122680.84 | 275.088
| TOTAL - UAE DIRHAMS - |  |  |  |  | 438675.698 |  | 233253.9016 | #REF!

## 1.Ceiling Tiles
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [10 empty] | 2022-11-01
PAINT WORK QUANTITY CALCULATION | [10 empty] | IPA-06
SUBJECT | Grid work done -( only Gypsum Tiles Ceiling -600X600mm)
VO-001
[7 empty] | Quantity |  |  | CLAIMED | CERTIFIED
SN |  | Dwg .NO | Level | Room Name | No. | Total | Units | Grid | Tiles | Work done | Work Done
1 | Hotel |  | CLG -01 -Gypsum Tiles Ceiling -600X600mm
| Hotel |  | L1 ,2,3,4,5,7,11,12,13,14,15,16,19,20,21,22, L23
| Hotel | A-1304-3 | L1 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 5.02
| Hotel |  | L2 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 5.02
| Hotel |  | L3 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 5.02
| Hotel |  | L4 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.016
| Hotel |  | L5 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 5.02
| Hotel |  | L7 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L11 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L12 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L13 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L14 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L15 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L16 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L19 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L20 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L21 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L22 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
| Hotel |  | L23 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02 | 4.518
L3,4,7,11 to 16, & L19 to L23
| Hotel | A-1304-3 | L3 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L4 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L7 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L11 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L12 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L13 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L14 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L15 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L16 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L19 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L20 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L21 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L22 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel |  | L23 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36 | 9.36
| Hotel | A-1304-3 | L5 | Lift Lobby | 1 | 25.21 | m2 |  |  | 25.21 | 25.21
2 | Residential | A-1320-1 | CLG -01 -Gypsum Tiles Ceiling -600X600mm
| Residential | A-1320-1 | L4 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01 | 14.01
| Residential | A-1320-1 | L5 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01 | 14.01
| Residential | A-1320-1 | L6 | FF Lobby | 1 | 14.01 | m2
| Residential | A-1320-1 | L22 | FF Lobby | 1 | 14.01 | m2
| Residential | A-1320-1 | L24 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01 | 14.01
| Residential | A-1320-1 | L25 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01 | 14.01
| Residential | A-1320-1 | L26 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01 | 14.01
| Residential | A-1320-1 | L27 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01 | 14.01
| Residential | A-1320-1 | L28 | FF Lobby | 1 |  | m2 |  |  | 0
| Residential | A-1320-1 | L29 | FF Lobby | 1 |  | m2 |  |  | 0
| Residential | A-1320-1 | L4 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L5 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L6 | HK Lobby | 1 | 9.64 | m2
| Residential | A-1320-1 | L22 | HK Lobby | 1 | 9.64 | m2
| Residential | A-1320-1 | L24 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L25 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L26 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L27 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L28 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
| Residential | A-1320-1 | L29 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64 | 9.64
0
| Residential | A-1320-1 | L5 | Lift Lobby | 1 | 25.65 | m2 |  |  | 25.65 | 25.65
[6 empty] | 475.72 |  |  |  | 428.42 | 421.392
Full System Gypsum Tiles Ceiling -600X600mm
Hotel |  | CLG -01 -Gypsum Tiles Ceiling -600X600mm
Hotel |  | G,F, L17,L18 & L24 to L28
Hotel | A-1304-3 | GF | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L17 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L18 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L24 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L25 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L26 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L27 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L28 | FF Lobby | 1 |  |  | 5.02
Hotel |  | G,F, L1,2,3,4,5,7,8,10,11 & L13 to L28 |  |  | 26
Hotel | A-1304-3 | GF |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 | L28 |  |  | 1 |  | 1.88
Hotel |  | G,F, L1,2,4,5, L17,18,24 ,25,26,27, L28
Hotel | A-1304-3 | GF |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  |  |  | Room service arae | 1 |  | 18.34
|  | L28 |  | Room service arae | 1 |  | 18.34
| Hotel |  | G,F, L1,2,5, L17 ,L18,L24 to L28 |  | 11
| Hotel | A-1304-3 | G.F | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L1 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L2 | House keeping Lobby | 1 |  | 9.36
|  |  | L5 | House keeping Lobby | 1 |  | 9.36
|  |  | L17 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L18 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L24 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L25 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L26 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L27 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L28 | House keeping Lobby | 1 |  | 9.36
| Residential | A-1320-1 | CLG -01 -Gypsum Tiles Ceiling -600X600mm
|  |  | B1 | FF Lobby | 1 |  | 14.01
|  |  | L23 | FF Lobby | 1 |  | 14.01
|  |  | L30 | FF Lobby | 1 |  | 14.01
|  |  | L23 | HK Lobby | 1 |  | 9.64
|  |  | L30 | HK Lobby | 1 |  | 9.64
|  |  | L4 | Waste chute room | 1 |  | 2.5
|  |  | L5 | Waste chute room | 1 |  | 2.5
|  |  | L23 | Waste chute room | 1 |  | 2.5
|  |  | L24 | Waste chute room | 1 |  | 2.5
|  |  | L25 | Waste chute room | 1 |  | 2.5
|  |  | L26 | Waste chute room | 1 |  | 2.5
|  |  | L27 | Waste chute room | 1 |  | 2.5
|  |  | L29 | Waste chute room | 1 |  | 2.5
|  |  | L30 | Waste chute room | 1 |  | 2.5
[7 empty] | 730 |  |  | 113.78
C/1 |  | Full System -600X600mm Metal Tiles
| Hotel | A-1301-5 | B1 | SPRTING | 1 | 33.78 | m2 |  |  | 33.78
| Hotel | A-1302-5/60028 | B1 | CORRIDOR | 1 | 272.75 | m2 |  |  | 272.75
| Hotel | A-1302-5 | B1 | SECURITY OFFICE | 1 | 9.57 | m2 |  |  | 9.57
| Hotel | A-1302-5 | B1 | TIMEKEEPER'S OFFICE | 1 | 10.67 | m2 |  |  | 10.67
| Hotel | A-1302-5 | B1 | HK HOT KITCHEN | 1 | 108.85 | m2
| Hotel | A-1302-5 | B1 | POTWASH | 1 | 12.67 | m2
[6 empty] | Total m2 |  |  |  | 292.99
C/2 |  | Grid work done - ( 600X600mm Metal Tiles only)
| Hotel | A-1301-5 | B1 | BIN STORE | 1 | 23.65 | m2 |  |  | 23.65
| Hotel | A-1302-5/60028 | B1 | BEVERAG STORAGE-2 | 1 | 22.1 | m2 |  |  | 22.1
| Hotel | A-1302-5/60028 | B1 | BEVERAG STORAGE-1 | 1 | 27.88 | m2 |  |  | 27.88
| Hotel | A-1302-5/60028 | B1 | VEGETABLE STORE | 1 | 5.94 | m2 |  |  | 5.94
| Hotel | A-1302-5/60028 | B1 | CENTRAL FOOD | 1 | 46.55 | m2 |  |  | 46.55
| Hotel | A-1302-5/60028 | B1 | DRY STORE | 1 | 20.43 | m2 |  |  | 20.43
| Hotel | A-1302-5/60028 | B1 | CORRIDOR | 1 | 40.06 | m2 |  |  | 40.06
| Hotel | A-1302-5/60028 | B1 | LINEN STORE | 1 | 13.56 | m2 |  |  | 13.56
| Hotel | A-1302-5/60028 | B1 | LINEN STORE | 1 | 13.15 | m2 |  |  | 13.15
| Hotel | A-1302-5/60028 | B1 | EXECUTIVE HOUSEKEEPER | 1 | 5.32 | m2 |  |  | 5.32
| Hotel | A-1302-5/60028 | B1 | HOUSEKEEPING & GUEST | 1 | 92.09 | m2 |  |  | 92.09
| Hotel | A-1302-5/60028 | B1 | WASTE HOLDING | 1 | 3.5 | m2 |  |  | 3.5
| Hotel | A-1302-5/60028 | B1 | DRY STORE | 1 | 4.21 | m2 |  |  | 4.21
| Hotel | A-1302-5/60028 | B1 | POTWASH | 1 | 9.91 | m2 |  |  | 9.91
| Hotel | A-1302-5/60028 | B1 | PATISSERIE | 1 | 25.01 | m2 |  |  | 25.01
| Hotel | A-1302-5/60028 | B1 | BAKERY PASTRY | 1 | 63.72 | m2 |  |  | 63.72
| Hotel | A-1302-5/60028 | B1 | COLD AREA | 1 | 3.29 | m2 |  |  | 3.29
| Hotel | A-1302-5/60028 | B1 | HK HOT KITCHEN | 1 | 21.15 | m2
[6 empty] | Total m2 |  |  |  | 420.37
C/3 |  | Full System Gypsum Tiles Ceiling -600X600mm
| Hotel | A-1302-5 | B1 | STAFF DINING ROOM | 1 | 129.46 | m2
Total m2
C/4 |  | Grid work done -( Gypsum Tiles Ceiling -600X600mm)
| Hotel | A-1302-5 | B1 | WAREWASH & CUTLERY | 1 | 45.67 | m2
Total m2

## VO 02
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [10 empty] | 2022-06-01
VARIATION ORDER 02 | [10 empty] | KCE PC 05
| Item Ref | Description | BoQ Ref | Rate Ref | Quantity | Unit | Rate (AED) | Addition (AED) | PROGRESS |  | Remarks
[5 empty] | Quantity | Unit |  |  | Qunatity | AMOUNT
| VO-002/1 | Supply and Installation of Demise Wall - One Side Board Only |  |  | 363.8 | m2 | 120 | 43656 | 327.42 | 39290.4 | 90% until WIR | 0.9 | 39290.4 | 0
0
| VO-002/02 | Supply and Installation of Shaft Wall |  |  | 253.64 | m2 | 290 | 73555.6 | 228.276 | 66200.04 | 90% until WIR |  | 66200.04 | 0
0
| VO-002/03 | Supply and Installation of Shaft Wall - One Side Board Only |  |  | 290.02 | m2 | 190 | 55103.8 | 246.33 | 46802.7 | 90% until WIR |  | 46802.7 | 0
| VO-002/04 | Supply and Installation of Partition Wall |  |  | 12.58 | m2 | 170 | 2138.6 | 11.322 | 1924.74 | 90% until WIR |  |  | 0
0
| VO-002/05 | Supply and Installation of 600X600X12mm Gypsum tiles |  |  | 255.4435 | m2 | 90 | 22989.915 | 202.35 | 18211.5
| VO-002/06 | 600X600X0.7MM Non-Perforated Metal Ceiling -FCF-01 |  |  | 335.36 | m2 | 160 | 53657.6 |  | 0
| VO-002/07 | Supply and Installation of Regur Gypsumboard -FCF 05 |  |  | 11.85 | m2 | 110 | 1303.5 |  | 0
| VO-002/08 | BH 650mm Hight |  |  | 68 | m | 70 | 4760 |  | 0
| VO-002/09 | Access Panel 600x600 mm |  |  | 19 | Nos | 285 | 5415 |  | 0
| VO-002/10 | Access Panel 450 x450 mm |  |  | 19 | m | 250 | 4750 |  | 0
| VO-002/11 | Supply and Installation of Cement board at Stone work cladding area - (Vanity ,bathtubs Unit ) |  |  | 392.8466 | m2 | 160 | 62855.456 | 353.5619 | 56569.9104 | 90% until WIR
| VO-002/12 | Supply and Installation of Cement board at Stone work cladding area - (Corridor ) |  |  | 67.7025 | m2 | 160 | 10832.4 | 60.93 | 10832 | 90% until WIR
| VO-002/13 | Supply and Installation of Columns Side Gypsum board - (Corridor ) |  |  | 98 | Nos | 95 | 9310 | 88.2 | 9310 | 90% until WIR
|  | Grand Total | [5 empty] | 350327.871 |  | 249141.2904

## Partition Work-VO 01
v |  | PROJECT | Plot BB.B03.018, Business Bay, Dubai
v |  | CONTRACTOR | Roberts Constructions
v |  | SUB CONTRACTOR | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v |  | SUBJECT | PAINTING WORKS
VO-01 |  |  | Gypsum Partition Works at Hotel Level 3
[6 empty] | Quantity |  |  |  | Deduction
SN | Types | Dwg .NO | Room No | No. | Length | Height / Width | Total | Length | Height / Width | No. | Total | Units | Sub. Total Qty |  | Cum Qty
E/1 |  | 100mm Partition Wall To Internal Area Wall Partition As Specified Type PTID-02
|  | AR-PL-SD-L3-50108 | Finance Office | 1 | 3.25 | 3.8 | 12.35 |  |  |  |  | m2 | 12.35 | 100% | 12.35
|  |  | Quality Manager | 1 | 3.25 | 3.8 | 12.35 |  |  |  |  | m2 | 12.35 | 100% | 12.35
|  |  | Hotel Manager | 1 | 1.93 | 3.8 | 7.334 |  |  |  |  | m2 | 7.334 | 100% | 7.334
|  |  | Ex Ass | 1 | 1.368 | 3.8 | 5.1984 |  |  |  |  | m2 | 5.1984 | 100% | 5.1984
|  |  | Gen. Manager | 1 | 3.25 | 3.8 | 12.35 |  |  |  |  | m2 | 12.35 | 100% | 12.35
|  |  |  | 1 | 4.2 | 3.8 | 15.96 |  |  |  |  | m2 | 15.96 | 100% | 15.96
|  |  | Regional Dir | 1 | 3.16 | 3.8 | 12.008 |  |  |  |  | m2 | 12.008 | 100% | 12.008
0
0
|  | AR-PL-SD-L3-50109 | Meeting room | 1 | 4.56 | 2.95 | 13.452 |  |  |  |  | m2 | 13.452 | 100% | 13.452
|  |  |  | 1 | 1.4 | 3.8 | 5.32 |  |  |  |  | m2 | 5.32 | 100% | 5.32
|  |  | Male & Female | 2 | 4 | 3.8 | 30.4 |  |  |  |  | m2 | 30.4 | 100% | 30.4
|  |  | Male & Female | 2 | 2 | 3.8 | 15.2 |  |  |  |  | m2 | 15.2 | 100% | 15.2
|  |  | Pantry | 1 | 1.76 | 3.8 | 6.688 |  |  |  |  | m2 | 6.688 | 100% | 6.688
|  |  | Corridor | 1 | 4.07 | 3.8 | 15.466 |  |  |  |  | m2 | 15.466 | 100% | 15.466
0
164.0764
|  | 100mm Partition Wall To Internal Area Wall Partition As Specified Type PTID-02 | [12 empty] | 164.0764
E/2 |  | 50mm Partition Wall To Internal Area Wall Partition
|  | AR-PL-SD-L3-50108 | Hotel Manager | 2 | 1.22 | 3.8 | 9.272 |  |  |  |  | m2 | 9.272 | 100% | 9.272
|  |  |  | 1 | 4.44 | 3.8 | 16.872 |  |  |  |  | m2 | 16.872 | 100% | 16.872
|  |  |  | 1 | 3.2 | 3.8 | 12.16 |  |  |  |  | m2 | 12.16 | 100% | 12.16
[13 empty] | 38.304 |  | 38.304
E/3 |  | Wall Cladding
|  | AR-PL-SD-L3-50108 | Corridor | 1 | 16.34 | 2.95 | 48.203 |  |  |  |  | m2 | 48.203 | 100% | 43.3827
|  |  |  | 1 | 2.83 | 2.95 | 8.3485 |  |  |  |  | m2 | 8.3485 | 100% | 7.5137
|  |  |  | 1 | 5.42 | 2.95 | 15.989 |  |  |  |  | m2 | 15.989 | 100% | 14.3901
0
|  | AR-PL-SD-L3-50108 | Corridor | 1 | 17.25 | 2.95 | 50.8875 |  |  |  |  | m2 | 50.8875 | 100% | 45.7988
[13 empty] | 123.428 |  | 111.0852
0
0
E/4 |  | Wall & ceiling internal painting works | [10 empty] | 0
Wall Painting
|  | AR-PL-SD-L3-50109 | Store | 1 | 13.93 | 2.4 | 33.432 | 1 | 2.1 | -1 | -2.1 | m2 | 31.332 | 90% | 28.1988
|  | AR-PL-SD-L3-50109 | Meeting room | 1 | 24.75 | 2.4 | 59.4 | 1 | 2.1 | -2 | -4.2 | m2 | 55.2 | 90% | 49.68
|  | AR-PL-SD-L3-50109 | W.C | 1 | 7.35 | 2.4 | 17.64 | 1 | 2.1 | -1 | -2.1 | m2 | 15.54 | 90% | 13.986
|  | AR-PL-SD-L3-50109 | F.W.C | 1 | 8.14 | 2.4 | 19.536 | 1 | 2.1 | -1 | -2.1 | m2 | 17.436 | 90% | 15.6924
|  | AR-PL-SD-L3-50109 | Pantry | 1 | 7.87 | 2.4 | 18.888 | 1 | 2.1 | -1 | -2.1 | m2 | 16.788 | 90% | 15.1092
|  | AR-PL-SD-L3-50109 | F& M Manager | 1 | 8.19 | 2.4 | 19.656 |  |  |  |  | m2 | 19.656 | 90% | 17.6904
|  | AR-PL-SD-L3-50109 | F& M Office | 1 | 11.1 | 2.4 | 26.64 |  |  |  |  | m2 | 26.64 | 90% | 23.976
|  | AR-PL-SD-L3-50109 | Corridor | 1 | 27.07 | 2.4 | 64.968 | 1 | 2.1 | -4 | -8.4 | m2 | 56.568 | 90% | 50.9112
|  | AR-PL-SD-L3-50109 | Corridor | 1 |  |  |  | 1.2 | 2.1 | -2 | -5.04 | m2 | -5.04 | 90% | -4.536
|  | AR-PL-SD-L3-50108 | Finance Manager& O | 1 | 20.52 | 2.4 | 49.248 |  |  |  |  | m2 | 49.248 | 90% | 44.3232
|  | AR-PL-SD-L3-50108 | Quality Manager | 1 | 9.08 | 2.4 | 21.792 |  |  |  |  | m2 | 21.792 | 90% | 19.6128
|  | AR-PL-SD-L3-50108 | Hotel Manager | 1 | 8.86 | 2.4 | 21.264 |  |  |  |  | m2 | 21.264 | 90% | 19.1376
|  | AR-PL-SD-L3-50108 | Exee Assistant Area | 1 | 12.84 | 2.4 | 30.816 |  |  |  |  | m2 | 30.816 | 90% | 27.7344
|  | AR-PL-SD-L3-50108 | General Manager | 1 | 14.21 | 2.4 | 34.104 |  |  |  |  | m2 | 34.104 | 90% | 30.6936
|  | AR-PL-SD-L3-50108 | Corridor | 1 | 23.51 | 2.4 | 56.424 | 1 | 2.24 | -3 | -6.72 | m2 | 49.704 | 90% | 44.7336
|  | AR-PL-SD-L3-50108 | Sale & Marking | 1 | 14.19 | 2.4 | 34.056 | 1 | 1.1 | -1 | -1.1 | m2 | 32.956 | 90% | 29.6604
|  | AR-PL-SD-L3-50108 | Regional Director | 1 | 8.84 | 2.4 | 21.216 |  |  |  |  | m2 | 21.216 | 90% | 19.0944
|  | AR-PL-SD-L3-50108 | Event Director | 1 | 12.97 | 2.4 | 31.128 |  |  |  |  | m2 | 31.128 | 90% | 28.0152
Ceiling Painting
|  | AR-PL-SD-L3-50109 | Male W.C | 1 | 1.7 | 2 | 3.4 |  |  |  |  | m2 | 3.4 | 90% | 3.06
|  | AR-PL-SD-L3-50109 | Female W.C | 1 | 2.1 | 2 | 4.2 |  |  |  |  | m2 | 4.2 | 90% | 3.78
|  | AR-PL-SD-L3-50109 | Pantry | 1 | 2.2 | 1.7 | 3.74 |  |  |  |  | m2 | 3.74 | 90% | 3.366
[13 empty] | 537.688 |  | 483.9192

## Demising & Shaft Walls-VO 02
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [9 empty] | 2022-11-01
QUANTITY CALCULATION FOR THE WORK DONE | [9 empty] | IPA-06
v | SUBJECT |  |  | Demise Wall & Shaft Wall
VO :02 Supply and Installation of Demise Wall & Shaft Wall at Level -21 to 27
Quantity
SN | DWG .NO | BLG | Level | Grid | No. | Length | Height / Width | Total |  | Work done
VO/01 | Supply and Installation of Demise Wall - One Side Board Only
| RP-PL-SD-L27 | Hotel | 27 | Corridor | 1 | 95.7 | 3.4 | 325.38 | 100% | 325.38
| RP-PL-SD-L25 -50671 | Hotel | 24 | Corridor | 1 | 11.3 | 3.4 | 38.42 | 100% | 38.42
[9 empty] | 363.8 | 363.8
VO/02 | Supply and Installation of Shaft Wall
| RP-PL-SD-L27 | Hotel | 27 | Corridor | 1 | 25.5 | 3.4 | 86.7 | 100% | 86.7
| RP-PL-SD-L26 -50691 | Hotel | 26 | Corridor | 1 | 36.7 | 3.4 | 124.78 | 100% | 124.78
| RP-PL-SD-L25 -50681 | Hotel | 25 | Corridor | 1 | 12.4 | 3.4 | 42.16 | 100% | 42.16
[9 empty] | 253.64 | 253.64
VO/03 | Supply and Installation of Shaft Wall - One Side Board Only
| RP-PL-SD-L27 | Hotel | 27 | Corridor | 1 | 4.1 | 3.4 | 13.94 | 100% | 13.94
| p | Hotel | 26 | Corridor | 1 | 10.6 | 3.4 | 36.04 | 100% | 36.04
| RP-PL-SD-L25 -50681 | Hotel | 25 | Corridor | 1 | 28.9 | 3.4 | 98.26 | 100% | 98.26
| RP-PL-SD-L25 -50671 | Hotel | 24 | Corridor | 1 | 36.9 | 3.4 | 125.46 | 100% | 125.46
| RP-PL-SD-L25 -50641 | Hotel | 21 | Corridor | 1 | 4.8 | 3.4 | 16.32 |  | 0
[9 empty] | 290.02 | 273.7
VO/04 | Supply and Installation of Partition Wall
| RP-PL-SD-L25 -50651 | Hotel | 22 | Corridor | 1 | 3.7 | 3.4 | 12.58 | 100% | 12.58
[9 empty] | 12.58 | 12.58

## VO 02 - Cement Boards
v | PROJECT |  |  | Plot BB.B03.018, Business Bay, Dubai
v | CONTRACTOR |  |  | KCE
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v | SUBJECT
VO :02 Supply and Installation of Cement board at Level -19 to 27
Quantity
SN | DWG .NO | Level | Room | Room No | No. | Length | Height / Width | Sub.Total | Total
VO/11 | Supply and Installation of Cement board at Stone work cladding area - (Vanity ,bathtubs Unit )
|  | 27 | 10B |  | 1 |  |  | 16.424 | 16.424 | 16.424
|  | 27 | 14A |  | 1 |  |  | 21.2954 | 21.2954 | 21.2954
|  | 27 | 2D |  | 2 |  |  | 15.024 | 30.048 | 30.048
|  | 27 | 3A |  | 2 |  |  | 21.2954 | 42.5908 | 42.5908
|  | 27 | 11D |  | 2 |  |  | 11.4733 | 22.9466 | 22.9466
|  | 27 | 2C |  | 1 |  |  | 14.754 | 14.754 | 14.754
|  | 27 | 16C |  | 1 |  |  | 7.291 | 7.291 | 7.291
|  | 27 | 5A |  | 1 |  |  | 21.2954 | 21.2954 | 21.2954
|  | 27 | 2E |  | 1 |  |  | 16.154 | 16.154 | 16.154
|  | 27 | 2G |  | 1 |  |  | 16.154 | 16.154 | 16.154
|  | 27 | 3F |  | 1 |  |  | 21.2954 | 21.2954 | 21.2954
|  | 27 | 3C |  | 1 |  |  | 21.2954 | 21.2954 | 21.2954
|  | 27 | 2F |  | 1 |  |  | 7.691 | 7.691 | 7.691
|  | 27 | 1A |  | 1 |  |  | 5.891 | 5.891 | 5.891
|  | 26 | 10B |  | 1 |  |  | 2.97 | 2.97 | 2.97
|  | 26 | 14A |  | 1 |  |  | 0 | 0 | 0
|  | 26 | 2D |  | 2 |  |  | 2.7 | 5.4 | 5.4
|  | 26 | 3A |  | 2 |  |  | 18.0954 | 36.1908 | 36.1908
|  | 26 | 11D |  | 1 |  |  | 4.6104 | 4.6104 | 4.6104
|  | 26 | 2C |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 26 | 18A |  | 1 |  |  | 21.2954 | 21.2954 | 21.2954
|  | 26 | 5A |  | 1 |  |  | 0 | 0 | 0
|  | 26 | 2E |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 26 | 2G |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 26 | 3F |  | 1 |  |  | 18.1 | 18.1 | 18.1
|  | 25 | 10B |  | 1 |  |  | 2.97 | 2.97 | 2.97
|  | 25 | 3A | Wash bottam only | 1 | 2.86 | 0.4 | 1.144 | 1.144 | 1.144
|  | 25 | 2B |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 25 | 11C |  | 1 |  |  | 4.61 | 4.61 | 4.61
|  | 25 | 2A |  | 2 |  |  | 2.7 | 5.4 | 5.4
|  | 25 | 2E |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 25 | 2G |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 25 | 7A |  | 1 | 2 | 0.4 | 0.8 | 0.8 | 0.8
|  | 24 | 13A |  | 1 | 1.8 | 0.4 | 0.72 | 0.72 | 0.72
|  | 24 | 2D |  | 1 |  |  | 2.7 | 2.7 | 2.7
|  | 24 | 11C |  | 1 |  |  | 4.61 | 4.61 | 4.61
[9 empty] | 392.8466 | 392.8466
VO/12 | Supply and Installation of Cement board at Stone work cladding area - (Corridor )
|  | 19 |  | Corridor | 3 | 0.59 | 2.55 | 4.5135 | 4.5135 | 4.5135
|  | 24 |  | Corridor | 7 | 0.59 | 2.55 | 10.5315 | 10.5315 | 10.5315
|  | 25 |  | Corridor | 4 | 0.59 | 2.55 | 6.018 | 6.018 | 6.018
|  | 26 |  | Corridor | 3 | 0.59 | 2.55 | 4.5135 | 4.5135 | 4.5135
|  | 27 |  | Corridor | 28 | 0.59 | 2.55 | 42.126 | 42.126 | 42.126
[9 empty] | 67.7025 | 67.7025
VO/13 | Supply and Installation of Columns Side Gypsum board - (Corridor )
|  | 19 |  | Corridor -Columns | 1 |  |  | 3 | 3 | 3
|  | 22 |  | Corridor -Columns | 1 |  |  | 1 | 1 | 1
|  | 23 |  | Corridor -Columns | 1 |  |  | 1 | 1 | 1
|  | 24 |  | Corridor -Columns | 1 |  |  | 19 | 19 | 19
|  | 25 |  | Corridor -Columns | 1 |  |  | 22 | 22 | 22
|  | 26 |  | Corridor -Columns | 1 |  |  | 24 | 24 | 24
|  | 27 |  | Corridor -Columns | 1 |  |  | 28 | 28 | 28
[9 empty] | 98 | 98

## Paint - BOQ
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [19 empty] | 2022-11-01
PAINT WORK QUANTITY CALCULATION | [19 empty] | IPA-06
E/1.Skim Coat 1-2mm to recive Low VOC | [14 empty] | 1 X Primer | 2 X Stucco | 1st -Paint | Final | Cum.Qty
Sn No | Drawing | BLG | Level | Room No/Grid | DESCRIPTION | WALL |  |  |  | Deduction |  |  |  |  | 20% | 30% | 30% | 20% | Net Total | Remarks
| 1212-3 | Res | B1 | P-B1-12 | Fresh Air Plenum | 24.56 | 5.5 | 1 | 135.08 | 5.9 | 2.4 | -1 | -14.16 | 120.92 | 24.184 | 36.276 | 36.276 | 24.184 | 120.92
[10 empty] | 2.9 | 2.4 | -1 | -6.96 | -6.96 | -1.392 | -2.088 | -2.088 | -1.392 | -6.96
| A-1214-7 | Res | G.F | P-GF-002 | Corridor | 35 | 4.8 | 1 | 143.5 | 2.1 | 2.1 | -1 | -4.41 | 139.09
| A-1214-7 | Res | G.F | P-GF-015 | FF Lobby | 16.2 | 3.3 | 1 | 53.46 | 1.2 | 2.1 | -2 | -5.04 | 48.42
| A-1215-7 | Hotel | G.F | P-GF-065 | BOH Cooridor | 57.2 | 3 | 1 | 171.6 | 0.9 | 2.1 | -6 | -11.34 | 160.26 |  |  |  |  | 160.26
| A-1215-7 | Hotel | G.F | P-GF-065 | BOH Cooridor |  |  |  |  | 1.8 | 2.1 | -2 | -7.56 | -7.56 |  |  |  |  | -7.56
| A-1215-7 | Hotel | G.F | P-GF-073 | FOOD STORAGE | 25.7 | 3 | 1 | 77.1 | 2 | 2.1 | -2 | -8.4 | 68.7 |  |  |  |  | 68.7
| A-1215-7 | Hotel | G.F | P-GF-051 | Lift Lobby | 21.8 | 3 | 1 | 65.4 | 1.1 | 2.1 | -6 | -13.86 | 51.54 |  |  |  |  | 51.54
| A-1215-7 | Hotel | G.F | [6 empty] | 3 | 2.1 | -1 | -6.3 | -6.3 |  |  |  |  | -6.3
| A-1215-7 | Hotel | G.F | P-GF-051 | House keeping Lift Lobby | 19.6 | 3 | 1 | 58.8 | 0.8 | 2.1 | -4 | -6.72 | 52.08 |  |  |  |  | 52.08
| A-1215-7 | Hotel | G.F | P-GF-059 | Lift Lobby | 10 | 3 | 1 | 30 | 1 | 2.1 | -2 | -4.2 | 25.8 |  |  |  |  | 25.8
| A-1215-7 | Hotel | G.F | P-GF-060 | Finishing Kitchen | 34 | 3 | 1 | 102 | 1 | 2.1 | -4 | -8.4 | 93.6 |  |  |  |  | 93.6
| A-1215-7 | Hotel | G.F | P-GF-035 | Pool bar lobby | 26.73 | 4.8 | 1 | 128.304 | 1 | 2.1 | -4 | -8.4 | 119.904 |  |  |  |  | 119.904
| A-1215-7 | Hotel | G.F | P-GF-0 | Pool bar lobby near | 12.3 | 4.8 | 1 | 59.04 | 1 | 2.1 | -4 | -8.4 | 50.64 |  |  |  |  | 50.64
| A-1215-7 | Hotel | L1 | P-01-013 | PR Cooridor | 20.9 | 3.2 | 1 | 66.88 | 1 | 2.1 | -2 | -4.2 | 62.68 |  |  |  |  | 62.68
| A-1215-7 | Hotel | L1 | P-01-026 | AV Contorl room | 20.9 | 3.2 | 1 | 66.88 | 1 | 2.1 | -2 | -4.2 | 62.68 |  |  |  |  | 62.68
| A-1215-7 | Hotel | L1 | P-01-017 | AV/SUITE EQUIP ROOM | 15.8 | 3.8 | 1 | 60.04 | 1 | 2.1 | -1 | -2.1 | 57.94 |  |  |  |  | 57.94
| A-1215-7 | Hotel | L1 | P-01-011 | Male prayer room | 18 | 3 | 1 | 54 | 1 | 2.1 | -2 | -4.2 | 49.8 |  |  |  |  | 49.8
| A-1215-7 | Hotel | L1 | P-01-015 | Female prayer room | 14.7 | 3 | 1 | 44.1 | 1 | 2.1 | -2 | -4.2 | 39.9 |  |  |  |  | 39.9
| A-1217-7 | Hotel | L2 | P-02-012 | Luggage Corridor | 52.14 | 4.2 | 1 | 218.988 | 1 | 2.1 | -5 | -10.5 | 208.488 |  |  |  |  | 208.488
| A-1217 | Hotel
| A-1218-7 | Res | L4 | P-04-011 | STO. | 18.56 | 3.87 | 1 | 71.8272 | 1 | 2.1 | -1 | -2.1 | 69.7272 |  |  |  |  | 69.7272
| A-1218-7 | Res | L4 | P-04-011 | House keeping Lobby | 15.2 | 3.87 | 1 | 58.824 | 1 | 2.1 | -3 | -6.3 | 52.524 |  |  |  |  | 52.524
| A-1235-6 | Res | L23 | R-24-07 | Elec Room | 9.85 | 5.6 | 1 | 55.16 | 0.8 | 2.1 | -1 | -1.68 | 53.48 | 10.696 | 16.044 | 16.044 | 10.696 | 53.48
| A-1226-11 | Hotel | L23 | H-24-08 | House Keep | 15.6 | 3 | 1 | 46.8 | 0.9 | 2.1 | -3 | -5.67 | 41.13 |  |  |  |  | 41.13
| A-1235-6 | Res | L23 | R-24-35 | BMU Storage
| A-1239-15 | Res | L31 | R-32-09 | Lift Machine room | 13.68 | 3.2 | 1 | 43.776 | 1 | 2.1 | -1 | -2.1 | 41.676 | 8.3352 | 12.5028 | 12.5028 | 8.3352 | 41.676
| A-1239-15 | Res | L31 | R-32-05 | Plant room | 48 | 3.3 | 1 | 158.4 | 1.2 | 2.1 | -2 | -5.04 | 153.36 |  |  |  |  | 153.36
[10 empty] | 1 | 2.1 | -1 | -2.1 | -2.1 |  |  |  |  | -2.1
[14 empty] | 1801.4192 |  |  |  |  | 1613.9092 | 0
E/2 .Low VOC acrylic emulsion paint applied to a base (PA.04)
Sn No | Drawing | BLG | Level | Room No/Grid | DESCRIPTION | WALL |  |  |  | Deduction |  |  |  |  | 1 X Primer | 2 X Stucco | 1st -Paint | Final | Cum.Qty | Remarks
| 1212-3 | Res | B1 | P-B1-12 | Fresh Air Plenum | 24.56 | 5.5 | 1 | 135.08 | 5.9 | 2.4 | -1 | -14.16 | 120.92 | 24.184 | 36.276 | 36.276 | 24.184 | 120.92
[10 empty] | 2.9 | 2.4 | -1 | -6.96 | -6.96 | -1.392 | -2.088 | -2.088 | -1.392 | -6.96
| A-1235-6 | Res | L23 | R-24-07 | Elec Room | 9.85 | 5.6 | 1 | 55.16 | 0.8 | 2.1 | -1 | -1.68 | 53.48 | 10.696 | 16.044 | 16.044 | 10.696 | 53.48
|  | Res | B1 | P-B1-0113 | Irrigation Tank | 52.73 | 5.4 | 1 | 284.742 | 1 | 2.1 | -2 | -4.2 | 280.542 | 11.2842 | 11.2842 | 22.5684 | 15.0456
|  | Res | B1 | P-B1-143 | Balancing tank | 14.32 | 5.4 | 1 | 77.328 | 1 | 2.1 | -1 | -2.1 | 75.228 | 11.2842 | 11.2842 | 22.5684 | 15.0456
|  | Hotel | B1 | P-B1-018 | Garbage Room | 33.6 | 5.4 | 1 | 181.44 | 1 | 2.1 | -1 | -2.1 | 179.34 | 11.2842 | 11.2842 | 22.5684 | 15.0456
|  | Hotel | B1 | P-B1-019 | MAIN SERVER | 26.6 | 5.3 | 1 | 140.98 | 1.8 | 2.4 | -1 | -4.32 | 136.66 | 11.2842 | 11.2842 | 22.5684 | 15.0456
| A-1215-7 | Hotel | G.f | P-GF-056 | FTR | 10.36 | 4.2 | 1 | 43.512 | 1 | 2.1 | -1 | -2.1 | 41.412 |  |  |  | 8.2824 | 8.2824
| A-1215-7 | Hotel | G.f | P-GF-057 | ELEC RM | 11.23 | 4.2 | 1 | 47.166 | 1 | 2.1 | -1 | -2.1 | 45.066 |  |  |  | 9.0132 | 9.0132
| A-1215-7 | Hotel | L1 | P-01-021 | FIR | 10.4 | 3.7 | 1 | 38.48 | 1 | 2.1 | -1 | -2.1 | 36.38 |  |  |  | 7.276 | 7.276
| A-1215-7 | Hotel | L1 | P-01-022 | Elec Room | 11.2 | 3.7 | 1 | 41.44 | 1 | 2.1 | -1 | -2.1 | 39.34 |  |  |  | 7.868 | 7.868
| A-1217 | Hotel | L3 | P-03-23 | Elec Room | 11.1 | 3.3 | 1 | 36.63 | 1 | 2.1 | -1 | -2.1 | 34.53 |  |  |  | 6.906 | 6.906
| A-1217 | Hotel | L3 | P-03-24 | FIR | 11.75 | 3.3 | 1 | 38.775 | 1 | 2.1 | -1 | -2.1 | 36.675 |  |  |  | 7.335 | 7.335
| A-1218-7 | Res | L4 | P-04-008 | Elec Room | 9.88 | 3.87 | 1 | 38.2356 | 1 | 2.1 | -1 | -2.1 | 36.1356 |  |  |  | 7.2271 | 7.2271
| A-1218-2 | Res | L5 | P-05-04 | Elec Room | 9.88 | 6.3 | 1 | 62.244 | 1.1 | 2.1 | -1 | -2.1 | 60.144 |  |  |  | 12.0288 | 12.0288
[19 empty] | 233.3765 | 0
E/3 .Epoxy Resin Painting to Wall
Sn No | Drawing | BLG | Level | Room No/Grid | DESCRIPTION | WALL |  |  |  | Deduction |  |  |  |  | 1 X Primer | 2 X Stucco | 1st -Paint | Final | Cum.Qty | Remarks
| 1213-3 | Hotel | B1 |  | Corridor | 318 | 2.7 | 1 | 858.6 | 0.9 | 2.1 | -20 | -37.8 | 820.8 | 164.16 | 246.24 | 246.24 |  | 656.64
[10 empty] | 1.8 | 2.1 | -16 | -60.48 | -60.48 | -12.096 | -18.144 | -18.144 |  | -48.384
[10 empty] | 1.2 | 1.25 | -12 | -18 | -18 | -3.6 | -5.4 | -5.4 |  | -14.4
| 1220-3 | Hotel | 7 | H-07-08 | Housekeeping and Linen | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 8 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 9 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 10 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 11 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 12 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 13 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 14 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 15 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 16 | H-16-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[14 empty] | 1181.52 |  |  |  |  | 945.216 | 0

## Corridor - BOQ
PROJECT: Plot BB.B03.018, Business Bay, Dubai
CONTRACTOR : Roberts Constructions
SUB CONTRACTOR : AL RAWDA
VO-04 | CORRIDOR CEILING WORKS
[6 empty] | Framing | Boarding | Finishing | Total | Cum.Amount
S.Nos | BLG | Level | Drawing No | No | QTY | 65% | 30% | 5% | % | Net Total
A |  | Matte Ceiling Finish HTL-PT-09
Hotel
Hotel
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 58 | 100% | 100% | 100% | 100% | 58
|  |  |  | 1 | 28.06 |  |  |  | 0% | 0
| Hotel | 25 | AR-CI-SD-L25-51684 | 1 | 35 | 100% | 100% | 100% | 100% | 35
37.06
| Hotel | 26 | AR-CI-SD-L25-51691 | 1 | 82 | 100% | 100% | 100% | 100% | 82
28.06
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 152 | 100% | 100% | 100% | 100% | 152
28.06
a |  |  |  |  | 448.24 |  |  |  |  | 327 | a
b | Bulk head, 120mm high
1
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 103.54 | 80% | 80% | 80% | 80% | 82.832
| Hotel | 26 | AR-CI-SD-L25-51691 | 1 | 114 | 100% | 100% | 100% | 100% | 114
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 175.28 | 80% | 80% | 80% | 80% | 140.224
[5 empty] | 392.82 |  |  |  | 13.68% | 337.056 | 2
E | Light cove 100 X 40
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 107.28 | 80% | 80% | 80% | 80% | 85.824
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 46.1 | 80% | 80% | 80% | 80% | 36.88
| Hotel | 26 | AR-CI-SD-L25-51691 | 1 | 174.45 | 80% | 80% | 80% | 80% | 139.56
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 173.25 | 80% | 80% | 80% | 80% | 138.6
[5 empty] | 501.08 |  |  |  | 16.84% | 400.864 | 5
CORRIDOR CEILING WORKS
7 | Drywall Lining Work
| Hotel | 7 | AR-CI-SD-L7-61011 | 1 | 77 | 100% | 100% | 100% | 100% | 77
|  |  |  | 1 | 22.62 | 100% | 100% | 100% | 100% | 22.62
| Hotel | 19 | AR-PL-SD-ML-51014 | 1 | 43 | 100% | 100% | 100% | 100% | 43
|  |  |  | 1 | 22.62 |  |  |  | 0% | 0
| Hotel | 21 | AR-PL-SD-ML-51014 | 1 | 52.13 | 100% | 100% | 100% | 100% | 52.13
|  |  |  | 1 | 22.62 |  |  |  | 0% | 0
| Hotel | 22 | AR-PL-SD-ML-51015 | 1 | 56.13 | 100% | 100% | 100% | 100% | 56.13
|  |  |  | 1 | 22.62 | 100% | 100% | 100% | 100% | 22.62
| Hotel | 23 | AR-PL-SD-ML-51015 | 1 | 56.13 | 100% | 100% | 100% | 100% | 56.13
|  |  |  | 1 | 22.62 | 100% |  |  | 65% | 14.703
| Hotel | 24 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
|  |  |  | 1 | 22.62
| Hotel | 25 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
|  |  |  | 1 | 22.62 |  |  |  | 0% | 0
| Hotel | 26 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
| Hotel | 27 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
[5 empty] | 757.73 |  |  |  |  | 659.333 | 5.g
[6 empty] | Primer+Stucco | 1st coat | Final | Total | Cum.Amount
C | Ceiling Painting HTL-PT-09 |  |  |  |  | 50% | 30% | 20% | % | Net Total
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 89.1 | 100% | 100% |  | 80% | 71.28
|  | 19 | AR-CI-SD-L19-61023 |  | 28.06
|  | 24 | Lift lobby | 1 | 28.06 | 100% | 100% |  | 80% | 22.448
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 83.6 | 100% | 100% |  | 80% | 66.88
37.06
| Hotel | 26 | AR-CI-SD-L26-61032 | 1 | 179 | 100% | 100% |  | 80% | 143.2
28.06
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 160 | 100% | 100% |  | 80% | 128
28.06
[5 empty] | 661 |  |  |  | 21.05% | 431.808 | C
D | Bulk head, 120mm high Painting
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 103.54 | 80% | 80% |  | 64% | 66.2656
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 137 | 100% | 100% |  | 80% | 109.6
| Hotel | 26 | AR-CI-SD-L26-61032 | 1 | 174.88 | 80% | 80% |  | 64% | 111.9232
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 175.28 | 80% | 80% |  | 64% | 112.1792
[5 empty] | 590.7 |  |  |  | 14.32% | 399.968 | d
f | Light cove, Painting
Hotel
Hotel
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 107.28 | 80% | 80% |  | 64% | 68.6592
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 169 | 100% | 100% |  | 80% | 135.2
| Hotel | 26 | AR-CI-SD-L26-61032 | 1 | 174.45 | 80% | 80% |  | 64% | 111.648
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 174.45 | 80% | 80% |  | 64% | 111.648
[5 empty] | 625.18 |  |  |  | 14.32% | 427.1552 | f

## Rockwool External - BOQ
v | PROJECT |  |  | Plot BB.B03.018, Business Bay, Dubai
v | CONTRACTOR |  |  | Roberts Constructions
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v | SUBJECT |  |  | Rockwool For External Ceiling
BOQ | :08.Supply and Installation of Rockwool External Ceiling
[7 empty] | Quantity |  |  | Work Done
SN | DWG .NO | BLG | Level | Grid | No. | Length | Height / Width | Total Qty | % | Total Qty
1 | L1-60001 | Hotel | 1 |  | 1 |  |  | 180 | 100% | 180
2 | L1-60001 | Hotel | 1 |  | 1
3 | L3-60005 | Hotel | 3 |  | 1
3 | L5-60005 | Hotel | 5 |  | 1
4 | L7-60010-02 | Hotel | 7 |  | 1 |  |  |  |  | 0
5 | L7-60010-02 | Hotel | 7 |  | 1 |  |  |  |  | 0
6 | L8-60011-02 | Hotel | 8 |  | 1 |  |  |  |  | 0
7 | L9-60012-02 | Hotel | 9 |  | 1 |  |  |  |  | 0
8 | L10-60013 | Hotel | 10 |  | 1 |  |  |  |  | 0
9 | L10-60014 | Hotel | 11 |  | 1 |  |  |  |  | 0
10 | L10-60014 | Hotel | 11 |  | 1 |  |  |  |  | 0
11 | L12-60018 | Hotel | 12 |  | 1 |  |  |  |  | 0
12 | L13-600119 | Hotel | 13 |  | 1 |  |  |  |  | 0
13 | L14-600120 | Hotel | 14 |  | 1 |  |  |  |  | 0
14 | L15-600119 | Hotel | 15 |  | 1 |  |  |  |  | 0
15 | L16-600120 | Hotel | 16 |  | 1 |  |  |  |  | 0
16 | L17-600121 | Hotel | 17 |  | 1
17 | L17-600121 | Hotel | 17 |  | 1
18 | L18-600122 | Hotel | 18 |  | 1
19 | L19-600123 | Hotel | 19 |  | 1 |  |  |  |  | 0
20 | L20-600124 | Hotel | 20 |  | 1 |  |  |  |  | 0
21 | L21-600125 | Hotel | 21 |  | 1 |  |  |  |  | 0
22 | L22-600126 | Hotel | 22 |  | 1 |  |  |  |  | 0
23 | L23-600127 | Hotel | 23 |  | 1 |  |  |  |  | 0
24 | L23-600127 | Hotel | 23 |  | 1 |  |  |  |  | 0
25 | L24-600130 | Hotel | 24 |  | 1 |  |  |  |  | 0
26 | L25-600131 | Hotel | 25 |  | 1 | 48 | 0.6 | 116.1 | 70% | 81.27
27 | L26-600132 | Hotel | 26 |  | 1 | 62 | 0.6 | 116.1 | 70% | 81.27
28 | L27-600133 | Hotel | 27 |  | 1 | 193.5 | 0.6 | 116.1 | 70% | 81.27
29 | L28-600134 | Hotel | 28 |  | 1 | 112.2 | 0.6 | 67.32 | 70% | 47.124
1 | L1-61001-02 | Residential | 1 |  | 1 |  |  | 456 | 100% | 456
2 | L3-61005 | Residential | 3 |  | 1 |  |  | 470.42 | 100% | 470.42
3 | L3-61005 | Residential | 3 |  | 1 | 52.77 | 0.6 | 31.662 | 100% | 31.662
3 | L3-61009 | Residential | 5 |  | 1 | 863 |  |  |  | 0
4 | L6-61017-02 | Residential | 6 |  | 1 | 157.6 |  |  |  | 0
5 | L7-61010-02 | Residential | 7 |  | 1 | 131 |  |  |  | 0
6 | L8-61011-02 | Residential | 8 |  | 1 | 161.39 |  |  |  | 0
7 | L9-61012-02 | Residential | 9 |  | 1 | 149.4 |  |  |  | 0
8 | L10-61013-01 | Residential | 10 |  | 1 | 96.5 |  |  |  | 0
9 | L11-61014-01 | Residential | 11 |  | 1 | 75 |  |  |  | 0
10 | L12-61018-01 | Residential | 12 |  | 1 | 102.7 |  |  |  | 0
11 | L13-61019 | Residential | 13 |  | 1 | 78.3 |  |  |  | 0
12 | L14-61020 | Residential | 14 |  | 1 | 104.6 |  |  |  | 0
13 | L15-61015 | Residential | 15 |  | 1 | 77.2 |  |  |  | 0
14 | L16-61016 | Residential | 16 |  | 1 | 103.1 |  |  |  | 0
15 | L17-61021 | Residential | 17 |  | 1 | 119.5 |  |  |  | 0
16 | L17-61021 | Residential | 17 |  | 1 |  |  |  |  | 0
17 | L18-61022 | Residential | 18 |  | 1 | 166.1 |  |  |  | 0
18 | L19-61023 | Residential | 19 |  | 1 | 146.5 |  |  |  | 0
19 | L20-61024 | Residential | 20 |  | 1 | 166.2 |  |  |  | 0
20 | L21-61025 | Residential | 21 |  | 1 | 145.6 |  |  |  | 0
21 | L22-61026 | Residential | 22 |  | 1 | 203.2 |  |  |  | 0
22 | L23-61027 | Residential | 23 |  | 1 | 143.5 | 0.6 | 86.1 | 100% | 86.1
23 | L24-61030 | Residential | 24 |  | 1 | 110.6 | 0.6 | 66.36 | 100% | 66.36
24 | L24-61030 | Residential | 24 |  | 1 |  |  | 176.2 | 100% | 176.2
25 | L25-61031 | Residential | 25 |  | 1 | 68.9 | 0.6 | 41.34 |  | 0
26 | L26-61032 | Residential | 26 |  | 1 | 51.942 | 0.6 | 31.1652 |  | 0
27 | L26-61032 | Residential | 26 |  | 1 |  |  | 176.74 | 50% | 88.37
28 | L27-61033 | Residential | 27 |  | 1 | 45.5 | 0.6 | 27.3 |  | 0
29 | L28-61034 | Residential | 28 |  | 1 | 77.5 | 0.6 | 46.5 |  | 0
30 | L28-61034 | Residential | 28 |  | 1 |  |  | 176 |  | 0
[8 empty] | 2650 |  | 1846.046
69.66%

## External - BOQ
PROJECT: Plot BB.B03.018, Business Bay, Dubai
CONTRACTOR :KCE
SUB CONTRACTOR :AL Rawda
EXTERNAL CEMENT BOARD CEILING WORKS
[9 empty] | Framing | Boarding | Finishing | Total | Cum.Qty
BOQ | BLG | Level | Drawing No | Zone | Grid | No | QTY | Work Done | 65% | 30% | 5% | % | Net Total
1 |  | 1 | L1-61001 |  | 1 | 1 | 1359 | 1223 | 90% | 87% | 87% | 87% | 1182.33
L1-60001
2 |  | ESS-405; Level-2 and 3 ceiling as per the drawings A-1305 and A-1306 |  |  |  | 1
3 | Hotel | 3 | L3-60005 |  | 1 | 1 | 973 | 883 | 90.75% | 90.75% | 90.75% | 90.75% | 883
| Res | 3 |  |  | 1 |  | 266.6 | 266 | 99.77% | 99.77% | 99.77% | 99.77% | 266
4 |  | ESS-405; Level-5 ceiling as per the drawings A-1307 and A-1308 |  |  |  | 1 | 122 | 122 | 85% | 85% | 85% | 85% | 103.7
[12 empty] | 0% | 0
[12 empty] | 0% | 0
4 |  | ESS-405; Level-5 ceiling as per the drawings A-1307 and A-1308 |  |  |  |  | 0 | [5 empty] | 0
5 |  | ESS-405; Levels 7 to 28 Hotel suit balconies and viod areas
| Hotel | 18 | AR-CI-SD-L18-61022 | 2 |  | 1 | 12 | 12 | 100% | 100% | 100% | 100% | 12 | f
| Hotel | 19 | AR-CI-SD-L19-61023 | 2 |  | 1 | 9 |  |  |  |  | 0% | 0 | f
| Hotel | 20 | AR-CI-SD-L20-61024 | 2 |  | 1 | 10 |  |  |  |  | 0% | 0
| Hotel | 21 | AR-CI-SD-L21-61025 | 2 |  | 1 | 10 |  |  |  |  | 0% | 0
| Hotel | 22 | AR-CI-SD-L22-61026 | 2 |  | 1 | 36 | 26 | 72.22% | 72.22% | 72.22% | 72.22% | 26
| Hotel | 23 | AR-CI-SD-L23-61027 | 2 |  | 1 | 26 | 18 | 69.23% | 69.23% | 69.23% | 69.23% | 18
| Hotel | 24 | AR-CI-SD-L24-61030 | 2 |  | 1 | 48 |  |  |  |  | 0% | 0
| Hotel | 25 | AR-CI-SD-L25-61031 | 2 |  | 1 | 41 | 31 | 75.61% | 75.61% | 75.61% | 75.61% | 31
| Hotel | 26 | AR-CI-SD-L26-61032 | 2 |  | 1 | 72 | 40 | 55.56% | 55.56% | 55.56% | 55.56% | 40
| Hotel | 27 | AR-CI-SD-L27-61033 | 2 |  | 1 | 81 | 32 | 39.51% | 39.51% | 39.51% | 39.51% | 32
| Hotel | 28 | AR-CI-SD-L28-61034 | 2 |  | 1 | 209.58 | 209.58 | 25% | 25% | 25% | 25% | 52.395
5 |  | ESS-405; Levels 7 to 28 Hotel suit balconies and viod areas
6 |  | ESS-405; Levels 6 to 29 Apartment suit balconies and viod areas
| Res | 23 | AR-CI-SD-L23-61027 | 3 |  | 1 | 99 |  |  |  |  | 0% | 0
| Res | 24 | AR-CI-SD-L24-61030 | 3 |  | 1 | 82 |  |  |  |  | 0% | 0
| Res | 25 | AR-CI-SD-L25-61031 | 3 |  | 1 | 52 |  |  |  |  | 0% | 0
| Res | 26 | AR-CI-SD-L26-61032 | 3 |  | 1 | 48 |  |  |  |  | 0% | 0
| Res | 27 | AR-CI-SD-L27-61033 | 3 |  | 1 | 43 |  |  |  |  | 0% | 0
| Res | 28 | AR-CI-SD-L28-61034 | 3 |  | 1 | 152 |  |  |  |  | 0% | 0
| Res | 29 | AR-CI-SD-L29-61035 | 3 |  | 1 | 27.93
| Res | 30 |  | 3 |  | 1
A | External Fibre Cement Board Ceiling | [11 empty] | 2646.425
B | Coffered Ceiling
|  | L1 | L1-60001 | 2 |  | 1 | 83 | 83 | 100% | 100% | 100% | 100% | 83
|  | L3 | L3-60005 | 2 |  | 1 | 272.9 | 272.9 | 100% | 100% | 100% | 100% | 272.9
B | Coffered Ceiling | [11 empty] | 355.9

## 7.Shaft
v | PROJECT |  |  | Plot BB.B03.018, Business Bay, Dubai
v | CONTRACTOR |  |  | KCE
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v | SUBJECT
BOQ -7- Supply and Installation of Shaft Wall at Level -1 to Roof Level
Quantity
SN | DWG .NO | BLG | Level | Grid | No. | Length | Height / Width | Total | Workdone
1 | RP-PL-SD-L11-50186-2 | Hotel | 1 | 19-20/ V-W | 1 | 5.9 | 3.03 | 17.877
[5 empty] | 1 | 0.956 | 3.03 | 2.8967
8 | RP-PL-SD-L11-50186-2 | Hotel | 2 to 3 | 19-20/ V-W | 1 | 5.9 | 8.15 | 48.085
[5 empty] | 1 | 0.956 | 8.15 | 7.7914
9 | RP-PL-SD-L11-50186-2 | Hotel | 4 | 19-20/ V-W | 1 | 5.9 | 3.6 | 21.24 | 12.744 | 60%
[5 empty] | 1 | 0.956 | 3.6 | 3.4416 | 2.065 | 60%
10 | RP-PL-SD-L11-50186-2 | Hotel | 5 to 6 | 19-20/ V-W | 1 | 5.9 | 8.6 | 50.74
[5 empty] | 1 | 0.956 | 8.6 | 8.2216
12 | RP-PL-SD-L11-50186-2 | Hotel | 7 | 19-20/ V-W | 1 | 5.9 | 3.15 | 18.585
[5 empty] | 1 | 0.956 | 3.15 | 3.0114
12 | RP-PL-SD-L11-50186-2 | Hotel | 8 | 19-20/ V-W |  |  |  | 21.6 | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 9 | 19-20/ V-W |  |  |  | 21.6 | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 10 | 19-20/ V-W |  |  |  | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 11 | 19-20/ V-W |  |  |  | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 12 | 19-20/ V-W |  |  |  | 21.6 | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 13 | 19-20/ V-W |  |  |  | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 14 | 19-20/ V-W |  |  |  | 21.6
12 | RP-PL-SD-L11-50186-2 | Hotel | 15 | 19-20/ V-W |  |  |  | 21.6
13 | RP-PL-SD-L11-50186-2 | Hotel | 16 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945
[5 empty] | 1 | 0.956 | 3.55 | 3.3938
14
| RP-PL-SD-L11-50186-2 | Hotel | 17 | 19-20/ V-W | 1 | 5.9 | 3.717 | 21.9303
[5 empty] | 1 | 0.956 | 3.717 | 3.5535
15 | RP-PL-SD-L11-50186-2 | Hotel | 18 | 19-20/ V-W | 1 | 5.9 | 5.425 | 32.0075
[5 empty] | 1 | 0.956 | 5.425 | 5.1863
16 | RP-PL-SD-L11-50186-2 | Hotel | 19 to 21 | 19-20/ V-W | 3 | 5.9 | 3.15 | 55.755
[5 empty] | 3 | 0.956 | 3.15 | 9.0342
17 | RP-PL-SD-L11-50186-2 | Hotel | 22 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945 | 12.567 | 60%
[5 empty] | 1 | 0.956 | 3.55 | 3.3938 | 2.0363 | 60%
17 | RP-PL-SD-L11-50186-2 | Hotel | 23 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945
[5 empty] | 1 | 0.956 | 3.55 | 3.3938
18 | RP-PL-SD-L11-50186-2 | Hotel | 24 to 26 | 19-20/ V-W | 3 | 5.9 | 3.15 | 55.755
[5 empty] | 3 | 0.956 | 3.15 | 9.0342
19 | RP-PL-SD-L11-50186-2 | Hotel | 27 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945
[5 empty] | 1 | 0.956 | 3.55 | 3.3938
|  |  | 28 | 19-20/ V-W | 1 | 5.9 | 7.25 | 42.775
[5 empty] | 1 | 0.956 | 7.25 | 6.931
|  |  | 29 | 19-20/ V-W | 1 | 5.9 | 5.32 | 31.388 | 31.388
[5 empty] | 1 | 0.956 | 5.32 | 5.0859 | 5.0859
[8 empty] | 730.4808 | 130.6862

## External (Paint) - BOQ
PROJECT: Plot BB.B03.018, Business Bay, Dubai
CONTRACTOR : Roberts Constructions
SUB CONTRACTOR :AL Rawda
EXTERNAL CEILING PAINTING WORKS
[9 empty] | Surface | Primer | 1st Coat | Final Coat | Total | Cum.Qty
BOQ | BLG | Level | Drawing No | Zone | Grid | No | QTY | Total | 10% | 30% | 30% | 30% | % | Net Total
1 |  | ESS-405; Level-1 ceiling as per the drawings A-1303 and A-1304 |  |  |  | 1 | 1359 | 1223.1 | 85% | 85% | 85% | 85% | 85% | 1039.635
| Hotel | 3 | L3-60005 |  | 1 | 1 | 973 | 678.1 | 69.69% | 69.69% | 69.69% | 69.69% | 69.69% | 678.1
| Res | 3 |  |  | 1 |  | 266.6 | 239.94 | 90% | 90% | 90% | 90% | 90% | 239.94
3 |  | ESS-405; Level-4 ceiling as per the drawings A-1307 |  |  |  | 1 | 102.86
345 |  | ESS-405; Level-5 ceiling as per the drawings A-1307 and A-1308
| Hotel | 5 |  | 3 |  | 1 | [7 empty] | 0
| Res | 5 |  | 3 |  | 1 | 129 | 129 | [5 empty] | 0
[14 empty] | 0 | #DIV/0!
346 |  | ESS-405; Levels 7 to 28 Hotel suit balconies and viod areas
| Hotel | 18 | AR-CI-SD-L18-61020 | 2 |  | 1 | 12 | 12 | 100% | 100% | 100% | 100% | 100% | 12
| Hotel | 19 | AR-CI-SD-L19-61020 | 2 |  | 1 | 12.5 | 12.5 | 100% | 100% | 100% | 100% | 100% | 12.5
| Hotel | 20 | AR-CI-SD-L20-61020 | 2 |  | 1 | 35 | 35 | 100% | 100% | 100% | 100% | 100% | 35
| Hotel | 21 | AR-CI-SD-L21-61020 | 2 |  | 1 | 47 | 47 | 100% | 100% | 100% | 100% | 100% | 47
| Hotel | 22 | AR-CI-SD-L22-61020 | 2 |  | 1 | 110 | 110 | 70% | 70% | 70% | 70% | 70% | 77
| Hotel | 23 | AR-CI-SD-L23-61028 | 1 |  | 1 | 180 | 180 | 70% | 70% | 70% | 70% | 70% | 126
| Hotel | 24 | AR-CI-SD-L24-61029 | 1 |  | 1 | 84 | 84 | 25% | 25% | 25% |  | 17.5% | 14.7
| Hotel | 25 |  |  |  | 1 | 102 | 102 | 85% | 85% | 85% |  | 59.5% | 60.69
| Hotel | 26 |  |  |  | 1 | 80 | 80 | 50% | 50% | 50% |  | 35% | 28
| Hotel | 27 |  |  |  | 1 | 112 | 112 | 40% | 40% | 40% |  | 28% | 31.36
1
| Hotel | 28 | AR-CI-SD-L28-61034 | 2 |  | 1 | 206 | 206 | 25% | 25% | 25% |  | 17.5% | 36.05
347 |  | ESS-405; Levels 6 to 29 Apartment suit balconies and viod areas
| Res | 6 | AR-CI-SD-L8-61017 | 3 | 02-09/C-H | 1 | 44 | 44
| Res | 7 | AR-CI-SD-L8-61010 | 3 | 3-10/ C-D | 1 | 8 | 8
[5 empty] | 7-11/ G-H | 1 | 16 | 16
[5 empty] | 3-4/ G-H | 1 | 22 | 22
| Res | 8 | AR-CI-SD-L8-61011 | 3 | 2-11/C-H | 1 | 10 | 10 | [6 empty] | K
| Res | 9 | AR-CI-SD-L8-61012-2 | 3 |  | 1 |  | 0
| Res | 10 | AR-CI-SD-L10-61013-1 | 3 |  | 1 | 12 | 12
| Res | 11 | AR-CI-SD-L11-61014-1 | 3 |  | 1 | 10 | 10
[6 empty] | 1 | 20 | 20
| Res | 12 | AR-CI-SD-L12-61018-1 | 3 |  | 1 | 10.5 | 10.5
| Res | 13 | AR-CI-SD-L13-61019 | 3 |  | 1 | 10.5 | 10.5
| Res | 13 | AR-CI-SD-L13-61019 | 3 |  | 1 | 10.5 | 10.5
| Res | 14 | AR-CI-SD-L14-61020 | 3 |  | 1 | 10.5 | 10.5
| Res | 15 | AR-CI-SD-L15-61015 | 3 |  | 1 | 10.5 | 10.5
| Res | 15 | AR-CI-SD-L15-61015 | 3 |  | 1 | 10.5 | 10.5
| Res | 16 | AR-CI-SD-L16-61016 | 3 |  | 1 | 10.5 | 10.5
| Res | 17 | AR-CI-SD-L17-61021 | 3 |  | 1 | 18 | 18
| Res | 18 | AR-CI-SD-L18-61022 | 3 |  | 1 | 20 | 20
| Res | 19 | AR-CI-SD-L19-61023 | 3 |  | 1 | 18 | 18
| Res | 20 | AR-CI-SD-L20-61024 | 3 |  | 1 | 18 | 18
| Res | 21 | AR-CI-SD-L21-61025 | 3 |  | 1 | 21 | 21
| Res | 22 | AR-CI-SD-L22-61026 | 3 |  | 1 | 12 | 12
| Res | 23 | AR-CI-SD-L23-61027 | 3 |  | 1 | 321.5 | 321.5
| Res | 24 | AR-CI-SD-L24-61030 | 3 |  | 1 | 421 | 421
| Res | 25 | AR-CI-SD-L25-61031 | 3 |  | 1 | 163.902 | 163.902
| Res | 26 | AR-CI-SD-L26-61032 | 3 |  | 1 | 291 | 291
| Res | 27 | AR-CI-SD-L27-61033 | 3 |  | 1 | 83.8 | 83.8
| Res | 28 | AR-CI-SD-L28-61034 | 3 |  | 1 | 342 | 342
| Res | 29 | AR-CI-SD-L29-61035 | 3 |  | 1 | 27.93 | 27.93
347 | [13 empty] | 0 | #DIV/0!
Coffered Ceiling
348 | Level | 1 |  | 3 |  | 1 | [7 empty] | 0
349 | Level | 2 |  | 3 |  | 1 | 411 | 411 | 100% | 100% | 100% | 100% | 100% | 411
349 | Hotel | L3 | L3-60005 | 3 |  | 1 | 272.9 | 272.9 | 100% | 100% | 100% | 100% | 100% | 272.9
Hotel | L-2 -3 | A-1306-1 | Columns | 48:00 | 13 | 4.72 | 8 | 490.88 |  |  |  | 0% | 80% | 392.704
3514.579

## Wall Liner - KCE
Hotel Corridor Works - Wall Liner
[12 empty] | Work Done under Roberts |  |  |  | Work Done under KCE |  |  |  | Cumulative Work Done (Both Roberts & KCE)
SN | Level | Dwg .NO | Types | Room No | No. | Length | Height / Width | Total | Units | Total Qty |  | Progress |  |  | Progress Qty | Progress |  |  | Progress Qty | Progress |  |  | Progress Qty
[12 empty] | Frame | Board | Finish |  | Frame | Board | Finish |  | Frame | Board | Finish
[12 empty] | 65% | 30% | 5% |  | 65% | 30% | 5% |  | 65% | 30% | 5%
| 7 | P18-IDR-H-L7-20-COR-002.1 |  | Corridor | 1 | 75.1 | 2.51 | 188.501 | m2
|  | Door |  |  | -14 | 1.1 | 2.4 | -36.96 | m2
|  | Door |  |  | -1 | 1.4 | 2.4 | -3.36 | m2
[10 empty] | 148.181 | 77.795 | 50% | 50% |  | 70.386 | 0% | 0% | 0% | 0 | 50% | 50% |  | 70.386
| 8 | P18-IDR-H-L8-21-COR-002.1 |  | Corridor | 1 | 67.05 | 2.51 | 168.2955 | m2
[5 empty] | -13 | 1.1 | 2.4 | -34.32 | m2
[5 empty] | -1 | 0.9 | 2.4 | -2.16 | m2
[10 empty] | 131.8155 | 0 | 100% | 100% | 100% | 131.8155 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 131.8155
| 9 | P18-IDR-H-L9-COR-002.1 |  | Corridor | 1 | 78.66 | 2.51 | 197.4366 | m2
[5 empty] | -15 | 1.1 | 2.4 | -39.6 | m2
[5 empty] | -1 | 2.14 | 2.4 | -5.136 | m2
[10 empty] | 152.7006 | 0 | 100% | 100% | 100% | 152.7006 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 152.7006
| 10 | P18-IDR-H-L10-22-COR-002.1 |  | Corridor | 1 | 69.13 | 2.51 | 173.5163 | m2
[5 empty] | -13 | 1.1 | 2.4 | -34.32 | m2
[5 empty] | -1 | 1.27 | 2.4 | -3.048 | m2
[10 empty] | 136.1483 | 0 | 100% | 100% | 100% | 136.1483 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 136.1483
| 11 | A-1211 |  | Corridor | 1 | 27.62 | 2.51 | 69.3262 | m2
[5 empty] | -5 | 1.1 | 2.4 | -13.2 | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 12 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 13 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 14 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 15 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 16 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 8.5592 | 90% | 75% | 75% | 47.567 | 0% | 25% | 25% | 4.911 | 90% | 100% | 100% | 52.478
| 19 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 43.0769 | 25% | 20% | 20% | 13.0493 | 75% | 80% | 80% | 43.0769 | 100% | 100% | 100% | 56.1262
| 20 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 5.6126 | 100% | 80% | 20% | 50.5136 | 0% | 20% | 80% | 5.6126 | 100% | 100% | 100% | 56.1262
| 21 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 7.0158 | 100% | 75% |  | 49.1104 | 0% | 25% | 100% | 7.0158 | 100% | 100% | 100% | 56.1262
| 22 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 11.2252 | 100% | 50% |  | 44.901 | 0% | 50% | 100% | 11.2252 | 100% | 100% | 100% | 56.1262
| 23 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 56.1262 |  |  |  | 0 | 100% | 100% | 100% | 56.1262 | 100% | 100% | 100% | 56.1262
| 24 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 28.0631 | 50% | 50% | 50% | 28.0631 | 45% | 40% | 40% | 24.2746 | 95% | 90% | 90% | 52.3377
| 25 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 28.0631 | 50% | 50% | 50% | 28.0631 | 45% | 40% | 40% | 24.2746 | 95% | 90% | 90% | 52.3377
| 26 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 16.8379 | 70% | 70% | 70% | 39.2883 | 25% | 20% | 20% | 13.0493 | 95% | 90% | 90% | 52.3377
| 27 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 56.1262 |  |  |  | 0 | 95% | 0% | 0% | 34.6579 | 95% |  |  | 34.6579
|  | Lift Lobby Ceiling Work (Level 7 to 16 , L19 to L27 ) |  | Lift lobby | 1 | 19.11 | 2.51 | 47.9661 | m2 |  | 0
[5 empty] | -6 | 1.76 | 2.4 | -25.344 | m2 |  | 0
| 7 |  |  | Lift lobby | 1 |  |  | 22.6221 | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 8 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 9 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 10 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 11 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 12 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 13 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 14 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 15 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 16 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 19 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 20 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 21 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 22 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 23 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 24 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 25 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 26 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
| 27 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 22.6221 |  |  |  | 0 |  |  |  | 0 |  |  |  | 0
[10 empty] | 1840.5583 | 609.9664 |  |  |  | 1230.5919 |  |  |  | 224.2242 |  |  |  | 1454.816
|  |  |  | Total Progress percentage carried to summery | [10 empty] | 66.86% |  |  |  | 36.76% |  |  |  | 79.04%

## VO-11
v | PROJECT |  |  | Dorchestor Hotel & Residence
v | CONTRACTOR |  |  | KHANSAHEB CIVIL ENGINEERING LLC
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
VO :011. Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works
Quantity
SN | Level | Room | Type | Room | No. |  | Work done | Total | Remarks
| L08 | 801 | 8A | 1 Bed Suite | 1 |  | 1
| L08 | 802 | 2B | Deluxe Room | 1 |  | 1
| L08 | 803 | 2C | Deluxe Room | 1 |  | 1
| L08 | 806 | 2A | Deluxe Room | 1 |  | 1
| L08 | 807 | 1B | Deluxe Room | 1 |  | 1
| L08 | 707.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L08 | 808 | 4A | Junior Twin Suite | 1 |  | 1
| L09 | 901 | 8A | 1 Bed Suite | 1 |  | 1
| L09 | 902 | 2B | Deluxe Room | 1 |  | 1
| L09 | 903 | 2C | Deluxe Room | 1 |  | 1
| L09 | 906 | 2A | Deluxe Room | 1 |  | 1
| L09 | 907 | 9A | 1 Bed Suite | 1 |  | 1
| L09 | 908 | 9B | 1 Bed Suite | 1 |  | 1
| L09 | 909 | 1B | Deluxe Room | 1 |  | 1
| L09 | 910 | 4A | Junior Twin Suite | 1 |  | 1
| L10 | 1001 | 8A | 1 Bed Suite | 1 |  | 1
| L10 | 1002 | 2B | Deluxe Room | 1 |  | 1
| L10 | 1003 | 2C | Deluxe Room | 1 |  | 1
| L10 | 1006 | 2A | Deluxe Room | 1 |  | 1
| L10 | 1007 | 15a | 1 Bed Suite | 1 |  | 1
| L10 | 1008 | 1B | Deluxe Room | 1 |  | 1
| L10 | 1009 | 4A | Junior Twin Suite | 1 |  | 1
| L11 | 1101 | 8A | 1 Bed Suite | 1 |  | 1
| L11 | 1102 | 2B | Deluxe Room | 1 |  | 1
| L11 | 1103 | 2C | Deluxe Room | 1 |  | 1
| L11 | 1106 | 2A | Deluxe Room | 1 |  | 1
| L11 | 1107 | 16A | Deluxe Room | 1 |  | 1
| L11 | 1108 | 1B | Deluxe Room | 1 |  | 1
| L11 | 1109 | 4A | Junior Twin Suite | 1 |  | 1
| L12 | 1201 | 10A | 1 Bed Suite | 1 |  | 1
| L12 | 1203 | 2B | Deluxe Room | 1 |  | 1
| L12 | 1204 | 11C | 1 Bed Suite | 1 |  | 1
| L12 | 1206 | 2B | Deluxe Room | 1 |  | 1
| L12 | 1207 | 11C | 1 Bed Suite | 1 |  | 1
| L12 | 1209 | 2A | Deluxe Room | 1 |  | 1
| L12 | 1210 | 9A | 1 Bed Suite | 1 |  | 1
| L12 | 1211 | 9B | 1 Bed Suite | 1 |  | 1
| L12 | 1212 | 1A | Deluxe Room | 1 |  | 1
| L12 | 1213 | 2F | Deluxe Room | 1 |  | 1
| L12 | 1216 | 2G | Deluxe Room | 1 |  | 1
| L12 | 1217 | 2E | Deluxe Room | 1 |  | 1
| L12 | 1218 | 5A | 1 Bed Suite | 1 |  | 1
| L13 | 1401 | 10A | 1 Bed Suite | 1 |  | 1
| L13 | 1403 | 2B | Deluxe Room | 1 |  | 1
| L13 | 1404 | 11C | 1 Bed Suite | 1 |  | 1
| L13 | 1406 | 2B | Deluxe Room | 1 |  | 1
| L13 | 1407 | 11C | 1 Bed Suite | 1 |  | 1
| L13 | 1409 | 2A | Deluxe Room | 1 |  | 1
| L13 | 1410 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L13 | 1411 | 19A | Deluxe Room | 1 |  | 1
| L13 | 1412 | 1A | Deluxe Room | 1 |  | 1
| L13 | 1413 | 2F | Deluxe Room | 1 |  | 1
| L13 | 1416 | 2G | Deluxe Room | 1 |  | 1
| L13 | 1417 | 2E | Deluxe Room | 1 |  | 1
| L13 | 1418 | 5A | 1 Bed Suite | 1 |  | 1
| L14 | 1501 | 10A | 1 Bed Suite | 1 |  | 1
| L14 | 1503 | 2B | Deluxe Room | 1 |  | 1
| L14 | 1504 | 11C | 1 Bed Suite | 1 |  | 1
| L14 | 1506 | 2B | Deluxe Room | 1 |  | 1
| L14 | 1507 | 11C | 1 Bed Suite | 1 |  | 1
| L14 | 1509 | 2A | Deluxe Room | 1 |  | 1
| L14 | 1510 | 1A | Deluxe Room | 1 |  | 1
| L14 | 1511 | 2F | Deluxe Room | 1 |  | 1
| L14 | 1510.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L14 | 1514 | 2G | Deluxe Room | 1 |  | 1
| L14 | 1515 | 2E | Deluxe Room | 1 |  | 1
| L14 | 1516 | 5A | 1 Bed Suite | 1 |  | 1
| L15 | 1601 | 10A | 1 Bed Suite | 1 |  | 1
| L15 | 1603 | 2B | Deluxe Room | 1 |  | 1
| L15 | 1604 | 11C | 1 Bed Suite | 1 |  | 1
| L15 | 1606 | 2B | Deluxe Room | 1 |  | 1
| L15 | 1607 | 11C | 1 Bed Suite | 1 |  | 1
| L15 | 1609 | 2A | Deluxe Room | 1 |  | 1
| L15 | 1610 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L15 | 1611 | 19A | Deluxe Room | 1 |  | 1
| L15 | 1612 | 1A | Deluxe Room | 1 |  | 1
| L15 | 1613 | 2F | Deluxe Room | 1 |  | 1
| L15 | 1616 | 2G | Deluxe Room | 1 |  | 1
| L15 | 1617 | 2E | Deluxe Room | 1 |  | 1
| L15 | 1618 | 5A | 1 Bed Suite | 1 |  | 1
| L16 | 1701 | 10A | 1 Bed Suite | 1 |  | 1
| L16 | 1702 | 11D | 1 Bed Suite | 1 |  | 1
| L16 | 1703 | 2C | Deluxe Room | 1 |  | 1
| L16 | 1706 | 2B | Deluxe Room | 1 |  | 1
| L16 | 1707 | 11C | 1 Bed Suite | 1 |  | 1
| L16 | 1709 | 2A | Deluxe Room | 1 |  | 1
| L16 | 1710.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L16 | 1710 | 1C | Deluxe Room | 1 |  | 1
| L16 | 1711 | 2H | Deluxe Room | 1 |  | 1
| L16 | 1714 | 2G | Deluxe Room | 1 |  | 1
| L16 | 1715 | 2E | Deluxe Room | 1 |  | 1
| L16 | 1716 | 5A | 1 Bed Suite | 1 |  | 1
| L07 | 701 | 8A | 1 Bed Suite | 1 |  | 1
| L07 | 702 | 2B | Deluxe Room | 1 |  | 1
| L07 | 703 | 2C | Deluxe Room | 1 |  | 1
| L07 | 706 | 2A | Deluxe Room | 1 |  | 1
| L07 | 707 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L07 | 708 | 19A | Deluxe Room | 1 |  | 1
| L07 | 709 | 1C | Deluxe Room | 1 |  | 1
| L07 | 710 | 4B | Junior Twin Suite | 1 |  | 1
| L19 | 2001 | 12A | 1 Bed Suite | 1 |  | 1
| L19 | 2002 | 17A | Presidential Suite | 1 |  | 1
| L19 | 2003 | 19A | Deluxe Room | 1 |  | 1
| L19 | 2004 | 6A | 1 Bed Suite | 1 |  | 1
| L20 | 2101 | 12A | 1 Bed Suite | 1 |  | 1
| L20 | 2102 | 2D | Deluxe Room | 1 |  | 1
| L20 | 2104 | 11B | 1 Bed Suite | 1 |  | 1
| L20 | 2105 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L20 | 2106 | 19A | Deluxe Room | 1 |  | 1
| L20 | 2107 | 6A | 1 Bed Suite | 1 |  | 1
| L21 | 2201 | 12A | 1 Bed Suite | 1 |  | 1
| L21 | 2202 | 2D | Deluxe Room | 1 |  | 1
| L21 | 2204 | 11B | 1 Bed Suite | 1 |  | 1
| L21 | 2205.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L21 | 2205 | 6A | 1 Bed Suite | 1 |  | 1
| L22 | 2301 | 12A | 1 Bed Suite | 1 |  | 1
| L22 | 2302 | 11A | 1 Bed Suite | 1 |  | 1
| L22 | 2304 | 2A | Deluxe Room | 1 |  | 1
| L22 | 2305 | 15A | 1 Bed Suite | 1 |  | 1
| L22 | 2306 | 6A | 1 Bed Suite | 1 |  | 1
| L23 | 2401 | 12A | 1 Bed Suite | 1 |  | 1
| L23 | 2402 | 2D | Deluxe Room | 1 |  | 1
| L23 | 2404 | 11B | 1 Bed Suite | 1 |  | 1
| L23 | 2405 | 16A | Deluxe Room | 1 |  | 1
| L23 | 2406 | 6A | 1 Bed Suite | 1 |  | 1
| L24 | 2501 | 13A | 1 Bed Suite | 1 |  | 1
| L24 | 2502 | 14A | 1 Bed Suite | 1 |  | 1
| L24 | 2503 | 2D | Deluxe Room | 1 |  | 1
| L24 | 2506 | 2B | Deluxe Room | 1 |  | 1
| L24 | 2507 | 11C | 1 Bed Suite | 1 |  | 1
| L24 | 2509 | 2A | Deluxe Room | 1 |  | 1
| L24 | 2510 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L24 | 2511 | 19A | Deluxe Room | 1 |  | 1
| L24 | 2512 | 1A | Deluxe Room | 1 |  | 1
| L24 | 2513 | 2F | Deluxe Room | 1 |  | 1
| L24 | 2516 | 2G | Deluxe Room | 1 |  | 1
| L24 | 2517 | 2E | Deluxe Room | 1 |  | 1
| L24 | 2518 | 5A | 1 Bed Suite | 1 |  | 1
| L25 | 2601 | 10B | 1 Bed Suite | 1 |  | 1
| L25 | 2602 | 14A | 1 Bed Suite | 1 |  | 1
| L25 | 2603 | 2D | Deluxe Room | 1 |  | 1
| L25 | 2606 | 2B | Deluxe Room | 1 |  | 1
| L25 | 2607 | 11C | 1 Bed Suite | 1 |  | 1
| L25 | 2609 | 2A | Deluxe Room | 1 |  | 1
| L25 | 2610.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L25 | 2610 | 1A | Deluxe Room | 1 |  | 1
| L25 | 2611 | 2F | Deluxe Room | 1 |  | 1
| L25 | 2614 | 2G | Deluxe Room | 1 |  | 1
| L25 | 2615 | 2E | Deluxe Room | 1 |  | 1
| L25 | 2616 | 5A | 1 Bed Suite | 1 |  | 1
| L26 | 2701 | 10B | 1 Bed Suite | 1 |  | 1
| L26 | 2702 | 14A | 1 Bed Suite | 1 |  | 1
| L26 | 2703 | 2D | Deluxe Room | 1 |  | 1
| L26 | 2705 | 11D | 1 Bed Suite | 1 |  | 1
| L26 | 2706 | 2C | Deluxe Room | 1 |  | 1
| L26 | 2708 | 18A | Royal Suite | 1 |  | 1
| L26 | 2709 | 1A | Deluxe Room | 1 |  | 1
| L26 | 2710 | 2F | Deluxe Room | 1 |  | 1
| L26 | 2713 | 2G | Deluxe Room | 1 |  | 1
| L26 | 2714 | 2E | Deluxe Room | 1 |  | 1
| L26 | 2715 | 5A | 1 Bed Suite | 1 |  | 1
| L27 | 2801 | 10B | 1 Bed Suite | 1 |  | 1
| L27 | 2802 | 14A | 1 Bed Suite | 1 |  | 1
| L27 | 2803 | 2D | Deluxe Room | 1 |  | 1
| L27 | 2806 | 2C | Deluxe Room | 1 |  | 1
| L27 | 2805 | 11D | 1 Bed Suite | 1 |  | 1
| L27 | 2808 | 11B | 1 Bed Suite | 1 |  | 1
| L27 | 2809 | 16A | Deluxe Room | 1 |  | 1
| L27 | 2810 | 1A | Deluxe Room | 1 |  | 1
| L27 | 2811 | 2F | Deluxe Room | 1 |  | 1
| L27 | 2814 | 2G | Deluxe Room | 1 |  | 1
| L27 | 2815 | 2E | Deluxe Room | 1 |  | 1
| L27 | 2816 | 5A | 1 Bed Suite | 1 |  | 1
[5 empty] | 173 |  | 173 | 173
| VO-011 | Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works |  |  | 173 | Nos | 245 | 42385
work down
| VO-011 | Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works |  |  | 173 | Nos | 245 | 42385

## VO-09
AL RAWDA GENERAL MAINTENANCE & DÉCOR CO. LLC
PROJECT: PLOT 18, DORCHESTER HOTEL
CONTRACTOR: KHANSAHEB CIVIL ENGINEERING
BOQ - PARTITIONS
VO -09 | Royal Suits, Presidential Suits, Lobbies and Prayer & GYM
BOQ - Dry Wall
Item | Description | Unit | Qty. | Rate | Amount | Progress |  |  | Progress Qty | Progress Amount
[5 empty] | (Dhs.) | Frame | Board | Finish
[6 empty] | 55% | 40% | 5%
PACKAGE -3 - ROYAL SUITE FIT-OUT
WALL FINISHES - RIGHT WING
Additional Items
The Tenderer is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum Tender price for this section of the works. Should the Tenderer fail to insert any items hereunder, it will be deemed that his lump sum price for the Tender includes all works as required by the tender drawings and specification and no subsequent claim for any additional item will be entertained.
Additional Items
Drywall Partitions
1 | DW-1 Type -100mm thick | m2 | 85.05 | 210 | 17860.5 | 55% | 40% |  | 95% | 16967.475
2 | DW-3 Type -150mm thick | m2 | 13.94 | 260 | 3624.4 | 55% | 40% |  | 95% | 3443.18
3 | DW-4 Type -200mm thick | m2 | 7.8 | 270 | 2106 | 55% | 40% |  | 95% | 2000.7
4 | DW-5 Type -Wall lining | m2 | 128.75 | 205 | 26393.75 | 55% | 40% |  | 95% | 25074.0625
5 | DW-7 Type -100 to 250mm thick | m2 | 38.35 | 155 | 5944.25 | 55% | 40% |  | 95% | 5647.0375
.
Wet Area wall Partitions
6 | DW-1.1 - Type -100mm thick | m2 | 21.8 | 220 | 4796 | 55% | 20% |  | 75% | 3597
7 | DW-5.1- Type -Wall | m2 | 42 | 205 | 8610 | 55% | 20% |  | 75% | 6457.5
8 | DW-6.2- Type -100mm thick | m2 | 88.46 | 210 | 18576.6 | 55% | 20% |  | 75% | 13932.45
PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT
Additional Items
Drywall Partitions
1 | DW-1 Type -100mm thick | m2 | 99.28 | 210 | 20848.8 | 55% | 40% |  | 95% | 19806.36
2 | DW-3 Type -150mm thick | m2 | 23.7 | 260 | 6162 | 55% | 40% |  | 95% | 5853.9
0
3 | DW-4 Type -200mm thick | m2 | 41.95 | 270 | 11326.5 | 55% | 40% |  | 95% | 10760.175
0
4 | DW-5 Type -Wall | m2 | 42.6 | 205 | 8733 | 55% | 40% |  | 95% | 8296.35
0
5 | DW-6 Type -Wall | m2 | 92.73 | 160 | 14836.8 | 55% | 40% |  | 95% | 14094.96
6 | DW-7 Type -100 to 250mm thick | m2 | 33.48 | 155 | 5189.4 | 55% | 40% |  | 95% | 4929.93
7 | DW-8 Type -180mm thick | m2 | 6.37 | 270 | 1719.9 | 55% | 20% |  | 75% | 1289.925
8 | DW-9 Type -220mm thick | m2 | 61.06 | 310 | 18928.6 | 55% | 20% |  | 75% | 14196.45
Wet Area wall Partitions
9 | DW-1.1 - Type -100mm thick | m2 | 131.99 | 220 | 29037.8 | 55% | 32% |  | 87% | 25262.886
10 | DW-3.1- Type -150mm thick | m2 | 2.24 | 280 | 627.2 | 55% | 32% |  | 87% | 545.664
11 | DW-5.1- Type -Wall | m2 | 36.18 | 205 | 7416.9 | 55% | 32% |  | 87% | 6452.703
12 | DW-6.1- Type -Wall | m2 | 13.23 | 165 | 2182.95 | 55% | 32% |  | 87% | 1899.1665
13 | DW-7.1 Type -100 to 250mm thick | m2 | 9.5 | 160 | 1520 | 55% | 32% |  | 87% | 1322.4
PACKAGE -4 - HOTEL - GYM - L28
GYPSUM PARTITIONS PACKAGE
WALL LINING
Supply and installation of wall linings, including all necessary related works, complete; all in accordance with the Drawings, Specifications and Scope of Works.
A | Gypsum Wall Lining to receive wall finishes at round pillars | m2 | 38.4 | 390 | 14976
B | Gypsum Wall Lining to receive wall finishes | m2 | 21 | 160 | 3360
Additional Items
| Gypsum Wall Lining to receive wall finishes- WC only | m2 | 160.8 | 15 | 2412
| DW-08- 220mm sliding door pocket wall, one side with Regular gypsum board, MR board inner side | m2 | 18.6 | 470 | 8742 | 55% | 20% |  | 75% | 6556.5
Level -1
Corridor
24 | Gypsum Wall Cladding | m2 | 244.5 | 155 | 37897.5 | 60% | 40% |  | 100% | 37897.5
| TOTAL AMOUNT IN AED |  |  |  | 283828.85 |  |  |  |  | 236284.2745
BOQ - CEILING
Item | Description | Qty. | Unit | Rate | Amount | Progress |  |  | Progress Qty | Progress Amount
[5 empty] | (Dhs.) | Frame | Board | Finish
[6 empty] | 60% | 35% | 5%
PACKAGE -3 - ROYAL SUITE FIT-OUT
CEILING FINISHES - RIGHT WING
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
B | Supply and fixing of Ceiling System including the finishes type; HTL-WC-24 (Gypsum ceiling by others) | 0 | m2 |  | 0
| Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others) | 8.35 | m2 | 130 | 1085.5
C | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others) | 1.58 | m2 | 130 | 205.4
D | Supply and fixing of cornice including the finishes type; HTL-ME-01, brushed bronze patina |  | m | N/A | N/A
CEILING FINISHES - LEFT WING
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
B | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others) | 33.94 | m2 | 130 | 4412.2
C | Supply and fixing of Ceiling System including the finishes type; HTL-WC-24 (Gypsum ceiling by others) | 0 | m2 | N/A | N/A
D | Supply and fixing of Ceiling System including the finishes type; HTL-WC-25 (Gypsum ceiling by others) | 0 | m2 | N/A | N/A
E | Supply and fixing of Ceiling System including the finishes type; HTL-ST-51 | 3.18 | m2 | 130 | 413.4
F | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others) | 3 | m2 | 130 | 390
CEILING FINISHES - LEFT WING (CONT'D)
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
A | Supply and fixing of Ceiling System including the finishes type; HTL-WD-02 | 7.7168 | m2 | 130 | 1003.1905
B | Ditto, Light cove ceiling, 85x155mm wide | 13.21 | m | 140 | 1849.4
C | Supply and fixing of Ceiling System including the finishes type; HTL-WD-19 | 2.3895 | m2 | 130 | 310.635
D | Ditto, Light cove ceiling, 130x165mm wide | 5.52 | m | 150 | 828
E | Supply and fixing of cornice including the finishes type; HTL-ME-01, brushed bronze patina
1 | 55mm high | 7.07 | m | N/A | N/A
2 | 85mm high | 11.01 | m | N/A | N/A
3 | 280mm high | 12.72 | m | N/A | N/A
Additional Items
CEILING FINISHES - RIGHT WING
B | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others) | 106.23 | m2 | 130 | 13809.9
C1 | Supply and fixing of Ceiling System including the finishes (M.R board Gypsum ceiling Only) | 24 | m2 | 140 | 3360
B.1 | Bulkhead upto 250 mm height | 94.3 | m | 70 | 6601
B.2 | Bulkhead 350 mm height | 20 | m | 80 | 1600
B.3 | Bulkhead 450 mm height | 4.4 | m | 85 | 374
B.4 | Bulkhead 750 mm height | 17.12 | m | 105 | 1797.6
B.5 | Bulkhead 3300 mm height | 70.3 | m | 475 | 33392.5
B.6 | Light cove ceiling, 100x50mm wide | 26 | m | 140 | 3640
B.7 | Light cove ceiling, 150x100mm wide | 45.14 | m | 140 | 6319.6
B.8 | Light cove ceiling, 300x100mm wide | 22 | m | 220 | 4840
B.9 | Curtain Pelmet | 26 | m | 180 | 4680
B.10 | 350 x 200 mm Cement Board Backing Panel | 8 | m2 | 320 | 2560
CEILING FINISHES - LEFT WING
B | Ditto, Light cove ceiling, 85x155mm wide | 13.79 | m | 140 | 1930.6
B.1 | Bulkhead 180 mm height | 42 | m | 60 | 2520
B.9 | Curtain Pelmet | 13 | m | 180 | 2340
| Sub-total |  |  |  | 100262.9255
PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT
CEILING FINISHES - RIGHT WING
C | Supply and fixing of Ceiling System including the finishes type; HTL-WC-00
1 | Dining Room | 6.346 | m2 | 130 | 824.98 | 60% |  |  | 60% | 494.988
D | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others)
1 | Dining Room | 5.714 | m2 | 130 | 742.82 | 60% |  |  | 60% | 445.692
2 | Twin Bedroom | 13.272 | m2 | 130 | 1725.36 | 60% |  |  | 60% | 1035.216
E | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others)
1 | Open Kitchen | 4.768 | m2 | 140 | 667.52
F | Supply and fixing of Ceiling System including the finishes type; HTL-ST-35 (Gypsum ceiling by others)
1 | Twin Bathroom | 1.26 | m2 | 140 | 176.4
CEILING FINISHES - LEFT WING
C | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others)
1 | Living Room | 15.832 | m2 | 130 | 2058.16 | 60% |  |  | 60% | 1234.896
D | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others)
1 | Living Room | 10.346 | m2 | 130 | 1344.98 | 60% |  |  | 60% | 806.988
2 | Master Bedroom | 19.376 | m2 | 130 | 2518.88 | 15% |  |  | 15% | 377.832
E | Supply and fixing of Ceiling System including the finishes type; HTL-WC-24 (Gypsum ceiling by others)
1 | Master Bedroom | 9.331 | m2 | 130 | 1213.03 | 15% |  |  | 15% | 181.9545
F | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others)
1 | Entry Vestibule | 3.56 | m2 | 130 | 462.8
G | Supply and fixing of Ceiling System including the finishes type, bulkhead, light cove, etc; HTL-ST-35 (Gypsum ceiling by others)
1 | Master Bathroom | 0.928 | m2 | 140 | 129.92
CEILING FINISHES - LEFT WING (CONT'D)
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
D | Supply and fixing of Ceiling Type HTL-ME-01 incl. light cove, cornice, bulkhead and etc; Brass, Brushed bronze patina
1 | Study | 0.84 | m2 | 260 | 218.4
Additional Items
CEILING FINISHES - RIGHT WING
C | Supply and fixing of Ceiling System including the finishes type; Regalur gypsum ceiling | 72.2 | m2 | 130 | 9386
G | Supply and fixing of Ceiling System including the finishes type; M.R gypsum ceiling | 25.8 | m2 | 140 | 3612
B.1 | Bulkhead upto 250 mm height | 137 | m | 70 | 9590
B.6 | Light cove ceiling, 65x70mm wide | 34.61 | m | 140 | 4845.4
B.6a | Light cove ceiling, 115x100mm wide | 37.71 | m | 140 | 5279.4
B.8 | Light cove ceiling, 300x110mm wide | 21.42 | m | 220 | 4712.4
B.8a | Light cove ceiling, 175x90mm wide | 77.3 | m | 175 | 13527.5
B.9 | Curtain Pelmet -150X200mm | 4.75 | m | 180 | 855
B.9a | Curtain Pelmet -175X200mm | 28.54 | m | 180 | 5137.2
B.9d | Curtain Pelmet -350X450mm | 24.93 | m | 275 | 6855.75
CEILING FINISHES - LEFT WING
C | Supply and fixing of Ceiling System including the finishes type; Regalur gypsum ceiling | 52.72 | m2 | 130 | 6853.6
G | Supply and fixing of Ceiling System including the finishes type; M.R gypsum ceiling | 48.3 | m2 | 140 | 6762
B.1 | Bulkhead upto 250 mm height | 147.18 | m | 70 | 10302.6
B.6 | Light cove ceiling, 100x80mm wide | 46.77 | m | 140 | 6547.8
B.7 | Light cove ceiling, 150x100mm wide | 49.26 | m | 140 | 6896.4
B.8 | Light cove ceiling, 300x100mm wide | 8.82 | m | 220 | 1940.4
B.9 | Curtain Pelmet -150X205mm | 22.7 | m | 180 | 4086
B.9a | Curtain Pelmet -250X550mm | 4.32 | m | 280 | 1209.6
B.9b | Curtain Pelmet -350X200mm | 4.35 | m | 340 | 1479
B.9c | Curtain Pelmet -350X400mm | 8.82 | m | 350 | 3087
B.10 | Curved Light cove ceiling, 130x100mm wide | 18.82 | m | 280 | 5269.6
| Sub-total |  |  |  | 130317.9
PACKAGE -4 - HOTEL - GYM - L28
CEILING WORKS
Note: The Sub-contractor is referred to the Specifications and Drawings for all details related to this Section of the Works and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the item description.
CEILING FINISHES
Suspended ceilings including frame work, suspension system, bulkheads, fittings, fixtures, accessories, preparation of surface to receive paint, etc. & ceiling rate shall be included for required paint finish (supplied and installed complete)
A | Gypsum board ceiling in finish Type HTL-PT-04 | 134 | M2 | 130 | 17420 | 60% |  |  | 60% | 10452
B | Ditto: beams overall size 200 x 200 x 200mm | 188 | m | 240 | 45120 | 60% |  |  | 60% | 27072
C | Ditto; curtain box 205 x 365mm high | 26 | m | 150 | 3900 | 60% |  |  | 60% | 2340
D | Ditto; light cove 200 x 200mm high | 36 | m | 150 | 5400 | 60% |  |  | 60% | 3240
| Sub-total |  |  |  | 71840
PACKAGE -4 - HOTEL LEVEL 01:- PRAYER ROOM & ABLUTION
CEILING FINISHES
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
A | Supply and fixing of Ceiling System including the finishes type; HTL-PT-03, White Paint, Color Terre Blanche - Matte Finish
1 | Male Ablution | 9.85 | m2 | 140 | 1379 | 60% |  |  | 60% | 827.4
2 | Female Ablution | 10.232 | m2 | 140 | 1432.48 | 60% |  |  | 60% | 859.488
3 | Male Prayer Room | 20.338 | m2 | 140 | 2847.32 | 60% |  |  | 60% | 1708.392
4 | Female Prayer Room | 13.983 | m2 | 140 | 1957.62 | 60% |  |  | 60% | 1174.572
5 | Store | 2.213 | m2 | 140 | 309.82 | 60% |  |  | 60% | 185.892
B | Ditto, Ceiling Bulkhead; 150mm high | 35.95 | m | 60 | 2157 | 60% |  |  | 60% | 1294.2
C | Ditto, Light Cove Ceiling, 50x100mm wide | 35.95 | m | 140 | 5033 | 60% |  |  | 60% | 3019.8
| Sub-total |  |  |  | 15116.24
PACKAGE - 4 - HOTEL GF LOBBY AND L1 CORRIDOR
CEILING FINISHES
Suspended Ceiling System and Finishes
Supply and installation of Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
1 | Ceiling System to GF Lobby including the finishes type; HTL-PT-04, White Paint, color All white N° 2005 - Matte finish | 40 | m2 | 280 | 11200 | 60% |  |  | 60% | 6720
2 | Ditto, Ceiling Bulkhead; 150mm high | 21 | m | 130 | 2730 | 60% |  |  | 60% | 1638
3 | Ditto, Light Cove Ceiling, 50x100mm wide | 21 | m | 260 | 5460 | 60% |  |  | 60% | 3276
4 | Ceiling System to L1 Corridor including the finishes type; HTL-PT-09, Light Grey Paint, color Argile Grisée - matte finish | 167 | m2 | 130 | 21710 | 60% |  |  | 60% | 13026
5 | Ditto, Ceiling Bulkhead; 150mm high | 126 | m | 60 | 7560 | 60% |  |  | 60% | 4536
6 | Ditto, Light Cove Ceiling, 50x100mm wide | 129 | m | 140 | 18060 | 60% |  |  | 60% | 10836
CEILING FINISHES (CONT'D)
Additional Items
| Allow for structural support above ceiling to suspend chandelier | 1 | No. | TBC | No details available
A | Supply and Installation of permanent access panels, maximum size up to 600mm x 600mm size | RO | No | 260 | Rate Only
B | Supply and Installation of Temporary access panels, maximum size up to 600mm x 600mm size | RO | No | 110 | Rate Only
| Sub-total |  |  |  | 66720
| TOTAL AMOUNT IN AED |  |  |  | 384257.0655 |  |  |  |  | 96783.3105
[7 empty] | VO -09 - Total Amount |  |  | 333067.585

## VO-12
PROJECT:Dorchestor Hotel & Residence
KHANSAHEB CIVIL ENGINEERING LLC
VALUATION OF VARIATION
PACKAGE: | Ceiling & Partitions
DATE: | 2022-08-30
VARIATION REF: | VO-012
DESCRIPTION: | External Ceiling Cutting and Finishing Works at Hoel Level -16
Item Ref | Description | BoQ Ref | Rate Ref | Quantity | Unit | Rate (AED) | Omission (AED) | Addition (AED) | Remarks
|  |  |  | Quantity | Unit
VO-012/1 | Removal & Disposal , Refixing Ceiling and Painting works |  |  | 89.5 | m2 | 192 |  | 17184
Measure
| AR-CI-SD--ML-60020 | Hotel | Level -16 | 89.5
| Sub Total | [5 empty] | 0 | 17184
| Grand Total | [6 empty] | 17184

## VO-16a (2)
v | PROJECT | Dorchestor Plot BB. B03.018, Business Bay
v | CONTRACTOR | KCE
v | SUB CONTRACTOR | AL RAWDA
v | SUBJECT | VO-016a STAIRCASE
| Paint to Stairsace Wall |  |  |  |  | Quantity |  |  |  | Deduction |  | Net Total |  | Skim coat | Primer | Stucco | 1st cot Paint | Final coat | Paint
SN | DWG .NO | Level | Location | No. | Length | Height / Width | Total | Length | Height / Width | No. | Total | Wall Net Total |  | 100% | 20% | 30% | 30% | 20% | TOTAL QTY | Total Amount
1 | A-4101-4 | B2 to B1 | ST-01 | 1 | 19.46 | 9.1 | 177.086 | 1.1 | 2.1 | -1 | -2.31 | 174.776 |  | 174.776 | 34.9552 | 52.4328 | 52.4328 | 34.9552 | 174.776
|  | G.F | ST-01 | 1 | 19.95 | 1 | 19.95 |  |  |  |  | 19.95 |  | 19.95 | 3.99 | 5.985 | 5.985 | 3.99 | 19.95
0
| A-4101-4 | B2 to B1 | ST-02 | 1 | 18.95 | 10.88 | 206.176 | 1.1 | 2.1 | -2 | -4.62 | 201.556 |  | 201.556 | 40.3112 | 60.4668 | 60.4668 | 40.3112 | 201.556
| A-4101-4 | G.F | ST-02 | 1 | 31.65 | 3.05 | 96.5325 | 1.1 | 2.1 | -4 | -9.24 | 87.2925 |  | 87.2925 | 17.4585 | 26.1877 | 26.1877 | 17.4585 | 87.2925
| A-4101-4 | L2 | ST-02 | 1 | 18.95 | 3.05 | 57.7975 | 1.1 | 2.1 | -1 | -2.31 | 55.4875 |  | 55.4875 | 11.0975 | 16.6462 | 16.6462 |  | 44.39
| A-4101-4 | L3 | ST-02 | 1 | 25.95 | 4.25 | 110.2875 | 1.1 | 2.1 | -3 | -6.93 | 103.3575 |  | 103.3575 | 20.6715 | 31.0072 | 31.0072 |  | 82.686
| A-4102-5 | B2 to B1 | ST-03 | 1 | 21.06 | 11.2 | 235.872 | 1.2 | 2.1 | -2 | -5.04 | 230.832 |  | 230.832
[8 empty] | 1.1 | 2.1 | -2 | -4.62 | -4.62 |  | -4.62
| A-4102-5 | G.F | ST-03 | 1 | 31.48 | 4.57 | 143.8636 | 1.2 | 2.1 | -2 | -5.04 | 138.8236 |  | 138.8236
| A-4102-5 | L1 to L31 | ST-03 | 1 | 21.06 | 129 | 2716.74 | 1.2 | 2.1 | -29 | -73.08 | 2643.66 | L5-29 | 2114.928 | 422.9856 | 634.4784 | 634.4784 |  | 1691.9424 | L5-29
[8 empty] | 1.1 | 2.1 | -30 | -69.3 | -69.3 | L5-29 | -55.44 | -11.088 | -16.632 | -16.632 |  | -44.352
0
| A-4102-5 | B2 to B1 | ST-04 | 1 | 21.06 | 11.2 | 235.872 | 1.2 | 2.1 | -2 | -5.04 | 230.832 |  | 230.832 | 46.1664 | 69.2496 | 69.2496 |  | 184.6656
[8 empty] | 1.1 | 2.1 | -2 | -4.62 | -4.62 |  | -4.62 | -0.924 | -1.386 | -1.386 |  | -3.696
| A-4102-5 | G.F | ST-04 | 1 | 31.48 | 4.57 | 143.8636 | 1.2 | 2.1 | -2 | -5.04 | 138.8236 |  | 138.8236 | 27.7647 | 41.6471 | 41.6471 |  | 111.0589
| A-4102-5 | L1 to L31 | ST-04 | 1 | 21.06 | 129 | 2716.74 | 1.2 | 2.1 | -29 | -73.08 | 2643.66 |  | 1057.464 | 31.7239 | 47.5859 | 47.5859 |  | 126.8957 | L1-5 -6%
[8 empty] | 1.1 | 2.1 | -30 | -69.3 | -69.3 |  | -27.72 | -0.8316 | -1.2474 | -1.2474 |  | -3.3264
0
| A-4103-5 | B2 to B1 | ST-05 | 1 | 19.14 | 11.4 | 218.196 | 1.2 | 2.1 | -2 | -5.04 | 213.156 |  | 213.156 | 42.6312 | 63.9468 | 63.9468 | 42.6312 | 213.156
0
| A-4104-5 | B2 to B1 | ST-06 | 1 | 18.4 | 11.22 | 206.448 | 1.1 | 2.1 | -2 | -4.62 | 201.828 |  | 201.828 | 40.3656 | 60.5484 | 60.5484 |  | 161.4624
| A-4104-5 | G.F | ST-06 | 1 | 21.06 | 3.14 | 66.1284 | 1.1 | 2.1 | -2 | -4.62 | 61.5084 |  | 61.5084 | 12.3017 | 18.4525 | 18.4525 |  | 49.2067
| A-4104-5 | L2 to L28 | ST-06 | 1 | 18.4 | 105.24 | 1936.416 | 1.1 | 2.1 | -28 | -64.68 | 1871.736 |  | 187.1736 | 18.7174 | 28.076 | 28.076 |  | 74.8694 | L2-5 -5%
| A-4106-5 | B2 to B1 | ST-07 | 1 | 21.16 | 11.22 | 237.4152 | 1.1 | 2.1 | -2 | -4.62 | 232.7952 |  | 232.7952
| A-4106-5 | G.F | ST-07 | 1 | 37.24 | 6.5 | 242.06 | 1.1 | 2.1 | -2 | -4.62 | 237.44 |  | 225.568
| A-4106-5 | L2 to R | ST-07 | 1 | 21.16 | 112.4 | 2378.384 | 1.1 | 2.1 | -56 | -129.36 | 2249.024 | L2 to 29 | 2136.5728 | 427.3146 | 640.9718 | 640.9718 |  | 1709.2582 | L2-29
| A-4108-5 | B2 to B1 | ST-08 | 1 | 21.16 | 11.22 | 237.4152 | 1.1 | 2.1 | -2 | -4.62 | 232.7952
| A-4108-5 | G.F | ST-08 | 1 | 42 | 6.5 | 273 | 1.1 | 2.1 | -2 | -4.62 | 268.38
| A-4108-5 | L2 to R | ST-08 | 1 | 21.16 | 112.4 | 2378.384 | 1.1 | 2.1 | -28 | -64.68 | 2313.704 | L19-28 | 1735.278 | 347.0556 | 520.5834 | 520.5834 |  | 1388.2224 | L7-18L19-29
L7-18
| A-4107-5 | B2 to G.F | ST-09 | 1 | 18.6 | 14.17 | 263.562 | 1.1 | 2.1 | -3 | -6.93 | 256.632 |  | 256.632 | 51.3264 | 76.9896 | 76.9896 | 51.3264 | 256.632
| A-4107-5 | B2 to G.F | ST-10 | 1 | 18.6 | 9.9 | 184.14 | 1.1 | 2.1 | -2 | -4.62 | 179.52 |  | 179.52 | 35.904 | 53.856 | 53.856 | 35.904 | 179.52
VO-16a/1 |  | Skim Coat Paint -Staircase Wall | [10 empty] | 16 | 9891.7547 | [5 empty] | 158268.0752
VO-16a/2 |  | Paint to Staircase wall | [10 empty] | 16 | [5 empty] | 6511.4399 | 104183.0378
| VO-16A Total Amount | [18 empty] | 262451.113

## VO-16a
v | PROJECT | Dorchestor Plot BB. B03.018, Business Bay
v | CONTRACTOR | KCE
v | SUB CONTRACTOR | AL RAWDA
v | SUBJECT | VO-016a STAIRCASE
| Paint to Stairsace Wall |  |  |  |  | Quantity |  |  |  | Deduction |  | Net Total |  | Skim coat | Primer | Stucco | 1st cot Paint | Final coat | Paint
SN | DWG .NO | Level | Location | No. | Length | Height / Width | Total | Length | Height / Width | No. | Total | Wall Net Total |  | 100% | 20% | 30% | 30% | 20% | TOTAL QTY | Total Amount
1 | A-4101-4 | B2 to B1 | ST-01 | 1 | 19.46 | 9.1 | 177.086 | 1.1 | 2.1 | -1 | -2.31 | 174.776 |  | 174.776 | 34.9552 | 52.4328 | 52.4328 | 34.9552 | 174.776
|  | G.F | ST-01 | 1 | 19.95 | 1 | 19.95 |  |  |  |  | 19.95 |  | 19.95 | 3.99 | 5.985 | 5.985 | 3.99 | 19.95
0
| A-4101-4 | B2 to B1 | ST-02 | 1 | 18.95 | 10.88 | 206.176 | 1.1 | 2.1 | -2 | -4.62 | 201.556 |  | 201.556 | 40.3112 | 60.4668 | 60.4668 | 40.3112 | 201.556
| A-4101-4 | G.F | ST-02 | 1 | 31.65 | 3.05 | 96.5325 | 1.1 | 2.1 | -4 | -9.24 | 87.2925 |  | 87.2925 | 17.4585 | 26.1877 | 26.1877 | 17.4585 | 87.2925
| A-4101-4 | L2 | ST-02 | 1 | 18.95 | 3.05 | 57.7975 | 1.1 | 2.1 | -1 | -2.31 | 55.4875 |  | 55.4875
| A-4101-4 | L3 | ST-02 | 1 | 25.95 | 4.25 | 110.2875 | 1.1 | 2.1 | -3 | -6.93 | 103.3575 |  | 103.3575
| A-4102-5 | B2 to B1 | ST-03 | 1 | 21.06 | 11.2 | 235.872 | 1.2 | 2.1 | -2 | -5.04 | 230.832
[8 empty] | 1.1 | 2.1 | -2 | -4.62 | -4.62
| A-4102-5 | G.F | ST-03 | 1 | 31.48 | 4.57 | 143.8636 | 1.2 | 2.1 | -2 | -5.04 | 138.8236
| A-4102-5 | L1 to L31 | ST-03 | 1 | 21.06 | 129 | 2716.74 | 1.2 | 2.1 | -29 | -73.08 | 2643.66 | L5-29 | 2114.928 | 211.4928 | 317.2392 | 317.2392 |  | 845.9712 | L15-29
[8 empty] | 1.1 | 2.1 | -30 | -69.3 | -69.3 | L5-29 | -55.44 | -5.544 | -8.316 | -8.316 |  | -22.176
0
| A-4102-5 | B2 to B1 | ST-04 | 1 | 21.06 | 11.2 | 235.872 | 1.2 | 2.1 | -2 | -5.04 | 230.832 |  | 230.832
[8 empty] | 1.1 | 2.1 | -2 | -4.62 | -4.62 |  | -4.62
| A-4102-5 | G.F | ST-04 | 1 | 31.48 | 4.57 | 143.8636 | 1.2 | 2.1 | -2 | -5.04 | 138.8236 |  | 138.8236
| A-4102-5 | L1 to L31 | ST-04 | 1 | 21.06 | 129 | 2716.74 | 1.2 | 2.1 | -29 | -73.08 | 2643.66 |  | 660.915
[8 empty] | 1.1 | 2.1 | -30 | -69.3 | -69.3 |  | -17.325
0
| A-4103-5 | B2 to B1 | ST-05 | 1 | 19.14 | 11.4 | 218.196 | 1.2 | 2.1 | -2 | -5.04 | 213.156 |  | 213.156 | 42.6312 | 63.9468 | 63.9468 | 42.6312 | 213.156
0
| A-4104-5 | B2 to B1 | ST-06 | 1 | 18.4 | 11.22 | 206.448 | 1.1 | 2.1 | -2 | -4.62 | 201.828 |  | 201.828
| A-4104-5 | G.F | ST-06 | 1 | 21.06 | 3.14 | 66.1284 | 1.1 | 2.1 | -2 | -4.62 | 61.5084 |  | 61.5084
| A-4104-5 | L2 to L28 | ST-06 | 1 | 18.4 | 105.24 | 1936.416 | 1.1 | 2.1 | -28 | -64.68 | 1871.736 |  | 187.1736
| A-4106-5 | B2 to B1 | ST-07 | 1 | 21.16 | 11.22 | 237.4152 | 1.1 | 2.1 | -2 | -4.62 | 232.7952
| A-4106-5 | G.F | ST-07 | 1 | 37.24 | 6.5 | 242.06 | 1.1 | 2.1 | -2 | -4.62 | 237.44
| A-4106-5 | L2 to R | ST-07 | 1 | 21.16 | 112.4 | 2378.384 | 1.1 | 2.1 | -56 | -129.36 | 2249.024 | L7-19 | 742.1779 | 89.961 | 134.9414 | 134.9414 |  | 359.8438 | L7-19
| A-4108-5 | B2 to B1 | ST-08 | 1 | 21.16 | 11.22 | 237.4152 | 1.1 | 2.1 | -2 | -4.62 | 232.7952
| A-4108-5 | G.F | ST-08 | 1 | 42 | 6.5 | 273 | 1.1 | 2.1 | -2 | -4.62 | 268.38
| A-4108-5 | L2 to R | ST-08 | 1 | 21.16 | 112.4 | 2378.384 | 1.1 | 2.1 | -28 | -64.68 | 2313.704 | L19-28 | 578.426 | 115.6852 | 173.5278 | 173.5278 |  | 462.7408 | L19-24
| A-4107-5 | B2 to G.F | ST-09 | 1 | 18.6 | 14.17 | 263.562 | 1.1 | 2.1 | -3 | -6.93 | 256.632 |  | 256.632 | 51.3264 | 76.9896 | 76.9896 | 51.3264 | 256.632
| A-4107-5 | B2 to G.F | ST-10 | 1 | 18.6 | 9.9 | 184.14 | 1.1 | 2.1 | -2 | -4.62 | 179.52 |  | 179.52 | 35.904 | 53.856 | 53.856 | 35.904 | 179.52
VO-16a/1 |  | Skim Coat Paint -Staircase Wall | [10 empty] | 16 | 6130.955 | [5 empty] | 98095.2803
VO-16a/2 |  | Paint to Staircase wall | [10 empty] | 16 | [5 empty] | 2584.5363 | 41352.5814
| VO-16A Total Amount | [18 empty] | 139447.8618

## Valuation
DORCHESTER COLLECTION HOTEL & RESIDENCES (PLOT 18) |  |  |  |  | 2022-05-05
VALUATION OF REMAINING SUBCONTRACT WORKS |  |  |  |  | Ver. 2
Trade Package: | Partitions and Ceilings
Subcontractor: | Al Rawda General Maint. & Decoration Co. L.L.C.
Subcontract Ref: | 17001DH/SCA/D&B/40-4-5-ALRAWDA
17001DH/SCA/B/20-1-1-ALRAWDA
ORIGINAL SUBCONTRACT WORKS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
A | External cement sheet soffits | 2458680 | 79% | 1942357 | 516323
B | External coffered ceilings | 249750 | 38% | 94905 | 154845
C | External dry wall partitions | 450000 | 100% | 450000 | 0
D | Bulkheads and shadow gaps | 322285 | 73% | 235268 | 87017
E | BOH painting | 1416921 | 70% | 991845 | 425076
Sub-Totals |  | 4897636 | 75.84% | 3714375 | 1183261
VARIATIONS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| Guest room ceilings | 1287184 | 98.64% | 1269655 | 17529
| Guest room partitions | 2362610 | 100% | 2362610 | 0
| Guest room wall panels | 4451650 | 99.33% | 4421842 | 29808
| Internal painting | 626689 | 90.15% | 564936 | 61753
| External painting | 712504 | 80% | 570003 | 142501
| Corridor ceilings | 806420 | 77% | 620940 | 185480
| BOH painting to basement and staircases | 211500 | 88.99% | 188210 | 23290
| Gypsum shaft wall system to hotel tower L7-10 | 226200 | 100% | 226200 | 0
| Gypsum shaft wall system to hotel tower L11, L14 | 106494 | 100% | 106494 | 0
| Gypsum shaft wall system to hotel tower service areas L1 to roof | 211831 | 0% | 0 | 211831
| Gypsum demise wall system to hotel tower L11, L14 | 114342 | 100% | 114342 | 0
| Rockwool insulation above external soffits | 299390 | 66.8% | 200000 | 99390
| Temporary partitions and ceilings to site offices | 73000 | 100% | 73000 | 0
| Partitions and ceilings to sales suite corridor | 42684 | 100% | 42684 | 0
| Partitions and ceilings to guest room type 15A | 27505 | 100% | 27505 | 0
| Changes to ceilings to guest room types 7A, 15A | 16720 | 100% | 16720 | 0
| Wall preparation for wall paper | 73606 | 100% | 73606 | 0
Sub-Totals |  | 11650329 | 93.38% | 10878747 | 771582
MATERIALS ON SITE |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| None | 0 |  | 0 | 0
Sub-Totals |  | 0 |  | 0 | 0
Totals |  | 16547965 | 88.19% | 14593122 | 1954843
NOTES |  | NEW SUBCONTRACT
|  | Value of Remaining Subcontract Works |  |  | 1183261
1) The amount included at "Payments to Date" is subject to final validation by the Employer's Representative. The Subcontractor shall provide evidence substantiating the amount paid to date under the previous subcontract. 2) Payment of amounts due under the previous RPJV subcontract (including retention) will be made pursuant to the terms of the WFA between the Employer and the Subcontractor. 3) The subcontract shall provide security for its performance of the Subcontract Works in the amount of AED 1,654,797.00 in the form of an unconditional and irrevocable bank guarantee for the benefit of the Employer. |  | Value of Remaining Variation Works |  |  | 771582
|  | Less Value of Materials on Site at 28-Feb-22 |  |  | 0
|  | New Subcontract Price |  |  | 1954843
WORKS COMPLETED TO 28-FEB-22
|  | Value of Completed Subcontract Works |  |  | 3714375
|  | Value of Completed Variation Works |  |  | 10878747
|  | Value of Materials on Site at 28-Feb-22 |  |  | 0
|  | Value of Works Completed to 28-Feb-22 |  |  | 14593122
|  | Less Retention to 28-Feb-22 (10%) |  |  | -1459312.2
|  | Less Payments to Date (incl. Advance Payment) |  |  | -10980036
|  | Outstanding amount for Works Completed to 28-Feb-22 |  |  | 2153773.8
All amounts exclude VAT