## INV (hidden)
RGM-20222-INV-7589/AKB/BT/KR/23 |  |  | 2023-02-25
M/s. Khansaheb Civil Engineering L.L.C
PO Box- 2716
Dubai, U.A.E
Tel.No:: +971 46057200
Attn | :Mr. Mr. Kevin Davies ,Commercial Manager.
:Mr. Mithun Vallarveettil, Quantity Surveyor .
Project | :Dorchestor Plot BB. B03.018, Business Bay
Subject | : Payment Application No.09 for Ceiling , Partitions & Painting Works
We have the pleasure in submitting hereunder our 09th Payment Application for Ceiling , Partitions & Painting Works being carried out at the above site. Details are attached herewith for your record your perusal and approval.
SN | Description |  | Cumulative Amount (AED)
1 | Total Value of this Invoice will be : AED |  | 4416168.7476
2 | Less Retention 10% : AED |  | -441616.8748
3 | Less Amount Certified up to Sep :AED |  | 1795613.4
4 | Manpower Supply |  | 152227.8
5 | Balance Amount to be Certified As per this Inovice will be Dhs |  | 2331166.2729
(Dirham’s. : One million Nine Hundred Thirty Fifty Nine Thousand Five Hunded Twenty Four & Fils 97 /100 Only.)
We hope our above bill will reach your immediate attention for an early settlement of the same.
Thanking you and assuring you of our best services and attention at all times, we remain,
With Regards,
For AL RAWDA GENERAL MAINT. & DECO.CO.
Babu Thankachan,
Project Manager
Encl :
Invoice Copy
Summary Sheet
Highlighted Drawings
Note : If you have any clarification, please do contact us within a week's period or else we will consider this invoice has been accepted by you.
This is not a tax invoice

## IPA (hidden)
18 B Street, Al Qouz Indl Area - 2
P.O.Box-5500, Dubai, U.A.E E-mail : rgmdco@eim.ae
Tel: 04-3470555, Tel: 04-3470044
INTERIM PAYMENT APPLICATION FOR THE MONTH OF FEBRUARY 2023
PROJECT: | Plot BB.B03.018, Business Bay, Dubai |  |  |  | TRADE: | Partitions , Ceilings & Painting
MAIN CONTR: | KHANSAHEB CIVIL ENGINEERING |  |  |  | PROJECT NO:
[5 empty] | SUBCONTRACT REFERENCE : | 201A22002/SW/ARM/157
PRINT DATE |  |  | : | [25-Feb-2023] | APPLICATION NO: | 9
[5 empty] | INVOICE NO: | RGM-20222-INV-7589
[5 empty] | PERIOD ENDING: | [28-Feb -2023]
[5 empty] | REMARKS: | [Interim]
SUBCONTRACT VALUE |  |  | : | 1954843 | Currency | AED
MEASURED VARIATION WORK VALUE |  |  | : | 4160246.901 | Vat | Excluding
TOTAL VALUE |  |  | : | 6115089.901 | % COMPLETED: | 72.22%
Scope of Work | External Ceiling , Partitions ,Ceiling & Painting
|  |  |  | CUMULATIVE | PREVIOUS | CURRENT
Measured Works |  | 0 | = | 1315978.2575 | 1113509.5364 | 202468.7211
MOS |  | 0 | = |  |  | 0
Variations |  | 0 | = | 3100190.4901 | 2218007.3455 | 882183.1447
SUB TOTAL |  | 0 | = | 4416168.7476 | 3331516.8819 | 1084651.8658
Less Retention |  | 10% | = | -441616.8748 | -333151.6882 | -108465.1866
Retention Recovery |  |  | = |  | 0 | 0
Advance Payment |  |  | =
Recovery of Advance Payment |  |  | =
Damages / Claims |  |  | =
Manpower Supply |  |  | = | 152227.8 | 130906.8 | 21321
Additional Arrangement Value |  |  | =
TOTAL |  |  | = | 4126779.6729 | 3129271.9937 | 997507.6792
Amount in Words:
(Dirhams : Six Hundred Twenty Five Thousand Eight Hundred Sixty Six & Fils 37/100 Only.)
SUMMARY: CERTIFICATION
Net invoice as on |  | [25-Feb-2023] |  | 4126779.6729
Less : Amount certified as on date Gross |  | 2022-11-01 |  | 1795613.4
Cumulative Balance to Certify |  |  |  | 2331166.2729 |  | 2331166.2729
Notes:
Prepared by |  |  |  | Authorized by
Kamaraj Rasuthevar |  |  | Babu Thankachan
Quantity Surveyor |  |  | Project Manager
Date: 25-Feb-2023 |  |  | Date: 25-Feb-2023 |  | COMPANY STAMP
Note : If you have any clarification, please do contact us within a week's period or else we will consider this invoice has been accepted by you.

## SUMMARY (hidden)
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [7 empty] | 2022-08-01
SUMMARY | [7 empty] | KCE PC 07
Sr. No. | Work Item | Agreed Amount | Previous |  | This Month |  | Cumulative
|  |  | % | Amount (Dhs) | % | Amount (Dhs) | % | Amount (Dhs)
1 | Remaining Works - BOQ | 1954843.0357 | 3.435% | 67153.2203 | #REF! | #REF! | #REF! | #REF!
2 | VO - 01 | 438675.698 | 15.41% | 69765.456 | #REF! | #REF! | #REF! | #REF!
3 | VO - 02 | 382703.071 | 37.12% | 130024.704 | 3.764% | 14403.224 | 37.74% | 144427.928
4 | VO - 03 | 371286.43 |  | 7388.1 |  | -7388.1 |  | 278464.8225
5 | VO - 04 | 47193.6 |  | 0 |  | 0 |  | 47193.6
6 | VO - 05 | 945.4 |  | 0 |  | 0 |  | 0
7 | VO - 06 | 477.6 |  | 0 |  | 477.6 | 100% | 477.6
8 | VO - 07 | 76286 |  | 0 |  | 76286 | 100% | 76286
9 | VO - 08 | 11473 |  | 0 |  | 6883.8 | 60% | 6883.8
TOTAL |  | 3283883.8347 | 2.784% | 76776.7032 | #REF! | #REF! | #REF! | #REF!

## SUMMARY (2)
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA
SUMMARY
Sr. No. | Work Item | Agreed Amount | Previous (from PC Dec 22) |  | This Month |  | Cumulative
|  |  | % | Amount (Dhs) | % | Amount (Dhs) | % | Amount (Dhs)
1 | Remaining Works - BOQ | 1954843.0357 | 60.41% | 1180937.0012 | 6.908% | 135041.2563 | 67.32% | 1315978.2575
2 | Variations | 0 |  | 2351077.4771 |  | 439093.9641 |  | 2790171.4411
3 | Dayworks | 0 |  | 152227.8 |  | 0 |  | 152227.8
TOTAL |  | 1954843.0357 | 188.5% | 3684242.2782 | 29.37% | 574135.2204 | 217.8% | 4258377.4986
2094443.6128
|  |  | KCE Claim | 4155461.76 |  | 840247.18 |  | 4995708.94 | -2163933.8858
|  |  | Difference | -471219.4818 |  | -266111.9596 |  | -737331.4414

## BOQ
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [5 empty] | 2023-02-01
PROGRESS BOQ | [5 empty] | IPA-09
| SN NO. | Description | BOQ |  |  |  | CLAIMED - AL RAWDA | [8 empty] | Subcon Claimed IPA | [8 empty] | CERTIFIED - OCI | [8 empty] | Remark
[7 empty] | Previous |  |  | This Month |  |  | Cumulative |  |  | Previous |  |  | This Month |  |  | Cumulative |  |  | Previous |  |  | This Month |  |  | Cumulative
|  |  | QTY | Unit | Rate | Amount UAE Dirhams | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount | QTY | Progress in % | Total Amount
EXTERNAL CEMENT BOARD WORKS
| A | ORIGINAL SUBCONTRACT WORKS
EXTERNAL CEMENT BOARD WORKS
| A | External Fibre Cement Board Ceiling | [9 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  | External Fibre Cement board ceiling including,all fixings, fittings, tapping, jointing, supporting frame work, sealant between panels and accessories complete all in accordance with the drawings and specifications | 3688.0215 | m2 | 140 | 516323.003 | [5 empty] | 0 |  |  |  | 2646.425 | 71.76% | 370499.5 | 0 | 0% | 0 | 2646.425 | 71.76% | 370499.5 | [5 empty] | 89040 | 636 | 17.25% | 89040
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
| B | Coffered Ceiling
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  | Coffered ceiling including,all fixings, fittings, tapping, jointing, supporting frame work, sealant between panels and accessories complete all in accordance with the drawings and specifications | 412.92 | m2 | 375 | 154845 | [9 empty] | 371.63 | 90% | 139361.25 | 0 | 0% | 0 | 371.63 | 90% | 139361.25 | [10 empty] | 90% Until submit the approved WIR
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
| C | External Dry Wall System | [9 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  |  |  | 0
| D | Bulkhead and Shadow Gap
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
|  | Bulkhead all around the columns and shadow gaps for all the types of external ceilings as per the drawings and specifications | 1 | Item |  | 87017 | [9 empty] | 0.9 | 90% | 78315.3 | 0 | 0% | 0 | 0.9 | 90% | 78315.3 | [10 empty] | 90% Until submit the approved WIR
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0 |  |  |  | 0
| E | BOH Painting
| 1 | Skim Coat 1-2mm to receive Low VOC | 1470 | m2 | 13.5 | 19845 | 209.116 | 14.23% | 2823.066 |  | 0% | 0 | 209.116 | 14.23% | 2823.066 | 1323 | 90% | 17860.5 | 0 | 0% | 0 | 1323 | 90% | 17860.5 | 209.116 | 14.23% | 2823.066 |  | 108.3% | 21496.0932 | 1801.4192 | 122.5% | 24319.1592 |  | 90% Until submit the approved WIR
| 2 | Low VOC acrylic emulsion paint applied to a base (PA.04) | 13659.4 | m2 | 15 | 204891 | 167.44 | 1.226% | 2511.6 |  | 0% | 0 | 167.44 | 1.226% | 2511.6 | 2930.6303 | 21.46% | 43959.4548 | 3309.9221 | 24.23% | 49648.8317 | 6240.5524 | 45.69% | 93608.2865 | 167.44 | 1.226% | 2511.6 |  | #REF! | #REF! | #REF! | #REF! | #REF!
| 3 | Epoxy Resin Painting to Wall | 4452 | m2 | 45 | 200340 | [9 empty] | 1852.616 | 41.61% | 83367.72 | 848.202 | 19.05% | 38169.09 | 2700.818 | 60.67% | 121536.81 | 0 | 0% | 0 |  | 19.81% | 39690 | 882 | 19.81% | 39690
| GRAND TOTAL - UAE DIRHAMS - EXTERNAL CEILING |  |  |  | 100% | 1183261.003 |  | 0.4508% | 5334.666 |  | 0 | 0 |  | 0.4508% | 5334.666 |  | 61.98% | 733363.7248 |  |  | 87817.9217 |  | 69.4% | 821181.6465 |  | 0.4508% | 5334.666 |  | #REF! | #REF! |  | #REF! | #REF! | 1177926.337
CEILING, PARTITION AND WALL PANELLING
| 1 | Guest room Ceiling
To bathroom & toilet
|  | White N* 2005-Matte Finish Ceiling finishes HTL-PT-04 | 184.5145 | m2 | 95 | 17528.8775 | [9 empty] | 166.06 | 90% | 15775.7 | 0 | 0% | 0 | 166.06 | 90% | 15775.7
[12 empty] | 0 | [17 empty] | 0
PARTITIONS
| 2 | WALL PANELLING
[12 empty] | 0 | [17 empty] | 0
|  | Supply and fixing of Gypsum Sheet Panel & GRG Mouldings | 129.6 | m2 | 230 | 29808
[12 empty] | 0 | [17 empty] | 0
| 3 | INTERNAL PAINTING WORKS | 3632.53 | m2 | 17 | 61753.01 | [9 empty] | 1089.759 | 30% | 18525.903 | 0 | 0% | 0 | 1089.759 | 30% | 18525.903
|  | Guest room | [27 empty] | 0
| 4 | EXTERNAL PAINTING WORKS | [9 empty] | 0 | [17 empty] | 0
|  | External Fibre Cement Board Ceiling | 6477.318 | m2 | 22 | 142500.996 | [9 empty] | 3514.579 | 54.26% | 77320.738 | 0 | 0% | 0 | 3514.579 | 54.26% | 77320.738
(Hotel Level 1 to L28) (Res L1 to L29)
| 5 | Corridor Ceilings | [9 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
| a | Gypsum board Ceiling | 448.036 | m2 | 80 | 35842.88 |  |  |  | 117 | 26.11% | 9360 | 117 | 26.11% | 9360 | 403.23 | 90% | 32258.4 | 0 | 0% | 0 | 403.23 | 90% | 32258.4 | 117 | 0.26114 | 9360 | 210 | 46.87% | 16800 | 327 | 72.99% | 26160 |  | 90% Until submit the approved WIR
0
| b | bulk head, 120mm high | 392.767 | m2 | 20 | 7855.34 |  |  |  | 114 | 29.02% | 2280 | 114 | 29.02% | 2280 | 353.49 | 90% | 7069.8 | 0 | 0% | 0 | 353.49 | 90% | 7069.8 | 114 | 29.02% | 2280 | 223.056 | 56.79% | 4461.12 | 337.056 | 85.82% | 6741.12 |  | 90% Until submit the approved WIR
| c | Ceiling Painting HTL-PT-09 | 661.216 | m2 | 17 | 11240.672 |  |  |  | 66.88 | 10.11% | 1136.96 | 66.88 | 10.11% | 1136.96 | 431.808 | 65.31% | 7340.736 | 0 | 0% | 0 | 431.808 | 65.31% | 7340.736 | 66.88 | 10.11% | 1136.96 | 342.48 | 51.8% | 5822.16 | 409.36 | 61.91% | 6959.12
0
| d | bulk head, 120mm high Painting | 590.38 | m2 | 10 | 5903.8 |  |  |  | 109.6 | 18.56% | 1096 | 109.6 | 18.56% | 1096 | 399.968 | 67.75% | 3999.68 | 0 | 0% | 0 | 399.968 | 67.75% | 3999.68 | 109.6 | 18.56% | 1096 | 362.96 | 61.48% | 3629.6 | 472.56 | 80.04% | 4725.6
| e | Light cove 100x40mm | 501.5475 | m2 | 85 | 42631.5375 |  |  |  | 220.55 | 43.97% | 18746.75 | 220.55 | 43.97% | 18746.75 | 451.39 | 90% | 38368.15 | 0 | 0% | 0 | 451.39 | 90% | 38368.15 | 220.55 | 0.43974 | 18746.75 | 224.424 | 44.75% | 19076.04 | 444.974 | 88.72% | 37822.79 |  | 90% Until submit the approved WIR
| f | Light cove, Painting | 625.29 | m2 | 10 | 6252.9 |  |  |  | 135.2 | 21.62% | 1352 | 135.2 | 21.62% | 1352 | 427.1552 | 68.31% | 4271.552 | 0 | 0% | 0 | 427.1552 | 68.31% | 4271.552 | 135.2 | 21.62% | 1352 | 364.944 | 58.36% | 3649.44 | 500.144 | 79.99% | 5001.44
| g | Supply and Installation of Drywall Lining Work (Level 7 to 10 Corridor) and (Level 11 to 16 & 19 to 27) in front fo corewall-Corridor),(Level 7 to 16 & 19 to 27 - Lift Lobby) Furring Chanel 600mm @with 15mm RG Gypsum board | 757.5294 | m2 | 100 | 75752.94 | 492.3941 | 65% | 49239.411 | 122.7841 | 0% | 12278.414 | 615.1783 | 65% | 61517.825 | 681.78 | 90% | 68178 | 0 | 0% | 0 | 681.78 | 90% | 68178 | 278.4684 | 36.76% | 27846.8443 | 764.5407 | 100.9% | 76454.0703 | 1043.0091 | 137.7% | 104300.9146 |  | 90% Until submit the approved WIR
| 6 | BOH Painting to Basement & Staircase | 2117.2727 | m2 | 11 | 23289.9997
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
| 7 | Gypsum Shaft wall to Hotel tower service areas L1 to Roof | 730.452 | m2 | 290 | 211831.08 | [9 empty] | 362.8893 | 49.68% | 105237.8924 | 162.8391 | 22.29% | 47223.3346 | 525.7284 | 71.97% | 152461.227
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
| 8 | Rockwool insulation above External Soffits | 2650.4 | m2 | 37.5 | 99390 | [9 empty] | 1846.046 | 69.65% | 69226.725 | 0 | 0% | 0 | 1846.046 | 69.65% | 69226.725 |  |  |  | 652.83 | 24.63% | 24481.125 | 652.83 | 24.63% | 24481.125
[12 empty] | 0 | [8 empty] | 0 | [8 empty] | 0
| GRAND TOTAL - UAE DIRHAMS - (Internal Painting Works) |  |  |  | 100% | 771582.0327 |  | 0% | 0 |  | 5.994% | 46250.124 |  | 12.38% | 95489.535 |  | 58.01% | 447573.2764 |  | 6.12% | 47223.3346 |  | 64.13% | 494796.611 |  | 34.79% | 17129.8172 |  | 20.01% | 154373.5553 |  | 28.02% | 216192.1096
| GRAND TOTAL - UAE DIRHAMS |  |  |  | 100% | 1954843.0357 |  |  |  |  | 2.366% | 46250.124 |  |  | 100824.201 |  | 59.99% | 1180937.0012 |  |  | 135041.2563 |  | 66.76% | 1315978.2575 |  |  | 22464.4832 |  | #REF! | #REF! |  | #REF! | #REF!
[6 empty] | 638864.7782 | [10 empty] | 32.68%

## VO List
IPA-09
0 | SECTION 03 - VARIATION SCHEDULE
1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 9 | 10 | 8 | 12 | 13 | 11
|  |  |  | Ref. KCE to Sub-Cont |  |  |  | SVN budged Amount (Total) | PROGRESS Qunatity |  |  | PROGRESS AMOUNT
No | Sub Cont VO No | RGM VON | Description | KCE VO Ref # | qty | Rate | WA Ref. |  | Previous | This Month | To Date | Previous | This Month | To Date | WIR ref
1 | 1 | 2 | Royal crown works & Other balance work |  |  |  | C021 | 456402 | 54.16% | 21.36% | 75.52% | 247175.55 | 97497.644 | 344673.194
2 | 2 | 2 | VO :02 Supply and Installation of Demise Wall & Shaft Wall at Level -21 &27 & BOH Ceiling G.F To L4 | E11/K105/SK/dm/030-1 |  |  | C036 | 382703.071 | 81.02% | 0% | 81.02% | 310070.9644 | 0 | 310070.9644
3 | 3 |  | Basement Car parking Painting Works -Anti carbonation | E11/K121/AK/dm/127 |  |  | PS010 R2 | 371286.43 | 60% | 15% | 75% | 222771.858 | 55692.9645 | 278464.8225
4 | 4 |  | External Ceiling Cutting and Finishing Works at Level -5 | E11/K121/PK/dm/038 |  |  | PS010 R3 | 47193.6 | 100% | 0% | 100% | 47193.6 | 0 | 47193.6
5 | 5 |  | Shaft Wall between the electrical and mechanical services works at Level -29 | E11/K121/PK/dm/043 |  |  | PS010 R6 | 945.4
6 | 6 |  | Supply and Installation of Insulationto wall and edge of slab at Level -24 | E11/K121/PK/dm/060 |  |  | PS010 R6 | 477.6 | 100% |  | 100% | 477.6 | 0 | 477.6
7 | 7 |  | Additional Gypsum Wall liner Corridir works at Level -11 to -27 | E11/K121/AK/dm/127 | 762.86 | 100 | PS010 R1 | 76286 | 100% | 0% | 100% | 76286 | 0 | 76286
8 | 8 |  | Required plasterboard ceiling @B1 Staff dining room | KCE-AX-RFI-B1-00010 |  |  | PS010 R3 | 11473 | 60% | 0% | 60% | 6883.8 | 0 | 6883.8
9 | 9 |  | Royal Suits, Presidential Suits, Lobbies and Prayer & GYM | E11/K121/S R/dm/140 |  |  | PS020 | 668085.92 | 65.93% | 22.02% | 87.95% | 440456.8245 | 147121.7942 | 587578.6187
10 | 10 |  | Shaft Wall between the LPG Pipe services works at all Level | E11/K121/PK/dm/069 |  |  | PS010 R6
11 | 11 |  | Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works | E11-K121-KK-dm-097 |  |  | PS010 R3 | 42385 | 100% | 0% | 100% | 42385 | 0 | 42385
12 | 12 |  | External Ceiling Cutting and Finishing Works at Level -16 | E11/K121/PK/dm/059 |  |  | PS010 R4 | 17184 | 100% | 0% | 100% | 17184 | 0 | 17184
13 | 13 |  | 2HR FR 150mm thk partition wall at stair 6 between L24 to L28 | E11-K121-SN-dm-107 |  |  | PS010 R5 | 25244.36 | 60% | 0% | 60% | 15146.616 | 0 | 15146.616
14 | 15 |  | Glass partition secondry support around Acoustic dry wall partition installation at Hotel Level -2 & 3 | E11/K121/NA/dm/079 |  |  | PS010 R6 | 18505.31 | 100% | 0% | 100% | 18505.31 | 0 | 18505.31
15 | 16 |  | Gypsum cladding around steel frame/Aluminium frame & glass to the Duplex suites of 7A type and bed suite 15A type- total 7 floors | E11/K121/PK/dm/063 |  |  | PS010 R6 | 17056.2 | 100% | 0% | 100% | 17056.2 | 0 | 17056.2
16 | 16a |  | Staircase painting work |  |  |  | PS010 R6 | 474871.34 | 66.03% | 2.266% | 68.29% | 313540.6026 | 10761.673 | 324302.2755
17 | 17 |  | 700X500 mm Core wall opening closing requirement inside stairs mid landing levels | RP-AX-RFI-PW-001422 |  |  | PS010 R6 | 22044.96 | 100% |  | 100% | 22044.96 | 0 | 22044.96
18 | 18 |  | Water meter room gypsum tiled false ceiling at Residentiel Level -G.F to 31 | E11-K121-SN-dm-234 |  |  | PS010 R6 | 11807.35
19 | 19 |  | Corridor arae door partitions -17 Door locations | E11/K121/PK/dm/062 |  |  |  | 10200 | 100% | 0% | 100% | 10200 | 0 | 10200
20 | 20 |  | Hotel Corridor Level 7-28 Wooden Feature palels are deleted & Proceed with plaster board ceiling and wall | E11-K121-SN-dm-201 |  |  |  | 17476.4 | 100% | 0% | 100% | 17476.4 | 0 | 17476.4
21 | 21 |  | 300X300 Ceiling Cutting and Finishing Works at Level -7 | E11-K121-SS-dm-118 |  |  |  | 825 | 100% | 0% | 100% | 825 | 0 | 825
22 | 22 |  | Ceiling board removal reinstatement at Hotel Level -24,25 | E11/K121/JA/dm/132 |  |  |  | 1340.85 | 100% |  | 100% | 1340.85 | 0 | 1340.85
23 | 23 |  | Removal of balcony Ceiling & Reinstatement at Residential Level -28 | E11-K121-JJ-dm-297 |  |  |  | 14669.52 | 20% | 0% | 20% | 2933.904 | 0 | 2933.904
24 | 24 |  | Temporary opening for FAHU Air balancing Level -7 to11 | E11-K121-SS-dm-165 |  |  |  | 20130 | 100% | 0% | 100% | 20130 | 0 | 20130
25 | 26 |  | Repainting to wall and ceiling at Guest level 8 to 16 | E11-K121-SK-mv-356 |  |  |  | 185106 | 85% | 5% | 90% | 157340.1 | 9255.3 | 166595.4
26 | 27 |  | Temporary Internal ceiling openings cutting & Closing at Hotel Level -19 &20 | E11-K121-JA-dm-437 |  |  |  | 6600 | 100% | 0% | 100% | 6600 | 0 | 6600
27 | 28 |  | Ceiling opening at GF RTL landscape area and lift lobby | E11/K121/NA/dm/078 |  |  |  | 5388 | 100% | 0% | 100% | 5388 | 0 | 5388
28 | 29 |  | Ceiling cutting & refinishing works at Residence GF lobby | E11/K121/NA/dm/187 |  |  |  | 15890 | 100% | 0% | 100% | 15890 | 0 | 15890
29 | 30 |  | Ground floor External ceiling cove alteration for X-L10 light | E11-K121-SN-dm-310 |  |  |  | 14400 | 100% | 0% | 100% | 14400 | 0 | 14400
30 | 31 |  | Revised shop drawing and necessary moditication as required at Level -3 | E11-K121-SK-dm-344 |  |  |  | 2525.25 | 100% | 0% | 100% | 2525.25 | 0 | 2525.25
31 | 32 |  | Level 2 Residential Podium Corridor ceiling levels & details to be revised | E11-K121-SN-dm-393 |  |  |  | 32310 | 100% | 0% | 100% | 32310 | 0 | 32310
32 | 34 |  | Temporary Internal ceiling openings cutting & Closing at Hotel Level -10-14 &16 | E11-K121-SS-mv-473 |  |  |  | 29700 | 100% | 0% | 100% | 29700 | 0 | 29700
33 | 35 |  | Ceiling board removal reinstatement at Residentiel Level -17 | E11-K121-KK-dm-176 |  |  |  | 7812.48 | 100% | 0% | 100% | 7812.48 | 0 | 7812.48
34 | 36 |  | Proceed to refix only ceiling grid works House keeping lobby & Garbage room from level 24 to level 29 | E11-K121-MS-dm-228 |  |  |  | 2520 | 100% | 0% | 100% | 2520 | 0 | 2520
35 | 37 |  | 8A Ceiling board removal reinstatement at Residentiel Level - 8 & 9 | E11-K121-SS-dm-255 |  |  |  | 1039.34 | 100% | 0% | 100% | 1039.34 | 0 | 1039.34
36 | 38 |  | Ceiling board removal reinstatement balcony foor Drain pipe line at Hotel -9 Level | E11-K121-SS-dm-308 |  |  |  | 3259.54 | 100% | 0% | 100% | 3259.54 | 0 | 3259.54
37 | 39 |  | Temporary ceiling opening for Electrical de-snagging Hotel Level -11 ,12 & 13 | E11-K121-SS-dm-309 |  |  |  | 1320 | 100% | 0% | 100% | 1320 | 0 | 1320
38 | 40 |  | 2hr FR 150mm thk Partition wall at Stair 6 between L17 TO L23 | E11/K121/SN/dm/466 |  |  |  | 37007.77 | 40% | 0% | 40% | 14803.108 | 0 | 14803.108
39 | 41 |  | Supply and Installation of Non -Combustible board in Res Electrical room | E11-K121-MS-dm-311 |  |  |  | 5280 | 100% | 0% | 100% | 5280 | 0 | 5280
40 | 42 |  | Gypsum Ceiling board removal reinstatement at Hotel Level - 10, 11 | E11-K121-AK-dm-326 |  |  |  | 660 | 100% | 0% | 100% | 660 | 0 | 660
41 | 44 |  | Installation of Cement board backing for wall marble cladding | E11-K121-KK-dm-477 |  |  |  | 51857.8 | 100% | 0% | 100% | 51857.8 | 0 | 51857.8
42 | 45 |  | Temporary ceiling opening for Hotel Level -07 to 12 (BW-0933) | E11-K121-SK-MV-554 |  |  |  | 24750 | 100% | 0% | 100% | 24750 | 0 | 24750
43 | 46 |  | Removing and replacing existing calcium silicate board & Painting worksLevel 5 Residential Heat Cool Pump Room | E11-K121-SS-dm-166 |  |  |  | 23960.16 | 100% | 0% | 100% | 23960.16 | 0 | 23960.16
44 | 47 |  | Supply and Installation of Shaft Wall at Level -1 to 4 Hotel (House Keeping Lobby ) | MEP-MX-RFI-PW-00097 |  |  |  | 8961.44 | 100% | 0% | 100% | 8961.44 | 0 | 8961.44 | wir
45 | 48 |  | Gypsum board wall cladding over the Main door frame to the corridor areas in Level 7 to 27 | E11-K121-JA-dm-453 |  |  |  | 52200 | 80% | 0% | 80% | 41760 | 0 | 41760 | Level - 7-15 | 16-24
46 | 49 |  | Room Service Support Area Shaft Wall change from Ground to Level 28 |  |  |  |  | 20262.55
47 | 50 |  | Ceiling board removal reinstatement balcony foor Drain pipe line at Hotel Level |  |  |  |  | 41856 | 100% | 0% | 100% | 41856 | 0 | 41856
48 | 51 |  | Additional Access Panel for Hotel Guest Room Level 7 to 16 & 19 to L 27 |  |  |  |  | 173135 | 70% | 10% | 80% | 121194.5 | 17313.5 | 138508 | Level - 7-23
49 | 52 |  | External Ceiling cutting & refixing in Residence GF Corridor |  |  |  |  | 4295 | 100% | 0% | 100% | 4295 | 0 | 4295
50 | 53 |  | External Ceiling cutting & refixing in Residence GF House keeping lobby entrance |  |  |  |  | 4673.28 | 100% | 0% | 100% | 4673.28 | 0 | 4673.28
51 | 54 |  | Temporary Internal ceiling openings cutting & Closing -L08 ,Residential Ref BW-0826 |  |  |  |  | 7260 | 100% | 0% | 100% | 7260 | 0 | 7260
52 | 55 |  | Temporary External ceiling openings cutting & Closing in Ground Floor with Hotel & Residential Ref BW-0925 &928 |  |  |  |  | 9800 | 100% | 0% | 100% | 9800 | 0 | 9800
53 | 56 |  | Proceed with additional partitions & Painting for Hotel Level 3 Gen. Management Offices (BW-0937) |  |  |  |  | 1465.1 | 100% | 0% | 100% | 1465.1 | 0 | 1465.1
54 | 57 |  | Supply & installation of insulation of Ceiling at hotel L2 House keeping lift lobby |  |  |  |  | 1096 | 100% | 0% | 100% | 1096 | 0 | 1096
55 | 59 |  | Gypsum board opening at Hotel Level 14 & 15 (B.W-0669,670& 686 ) |  |  |  |  | 2970 | 100% | 0% | 100% | 2970 | 0 | 2970
56 | 60 |  | Cutting Existing gypsum board around BOH timber door and fix with 9mm gypsum around door frame to maintain the finish line with mirror cladding |  |  |  |  | 17955 | 80% | 0% | 80% | 14364 | 0 | 14364
57 | 61 |  | Proceed with closing of Extenal ceiling at Level 2 high level |  |  |  |  | 1960 | 100% | 0% | 100% | 1960 | 0 | 1960
58 | 62 |  | Cement board modification works on either side on corridor to passenger lift lobby from level 7 to16 & 19 to 27 |  |  |  |  | 11685 | 60% | 0% | 60% | 7011 | 0 | 7011 | Level - 7-20
59 | 63 |  | Ceiling grid / Tile changes to suit revised partition wall layout for Hotel L3 |  |  |  |  | 500 | 100% | 0% | 100% | 500 | 0 | 500
60 | 64 |  | Proceed with opening of ceiling for relocating FCU unit and afterwards closing the areas properly |  |  |  |  | 1977 |  | 100% | 100% | 0 | 1977 | 1977
61 | 65 |  | Gypsum board opening for chilled water work at Hotel Level 25 rooms 2501, 2502, 2510 and 2516 |  |  |  |  | 660 | 100% | 0% | 100% | 660 | 0 | 660
62 | 66 |  | Skim coat and painting for LPG shaft Block work mech room from Level -17 to 28 |  |  |  |  | 2148.38 | 100% | 0% | 100% | 2148.38 | 0 | 2148.38
63 | 67 |  | Boarding for Lift door jamb |  |  |  |  | 12470 | 10% | 0.3448% | 10.34% | 1247 | 43 | 1290 | Level - 18,17,29
64 | 68 |  | Cutting of gypsum wall, for fixing of decorative fins bracket at Level 5 |  |  |  |  | 194790 | 10% | 0% | 10% | 19479 | 0 | 19479
65 | 69 |  | Revised shop drawing and necessary moditication as required at Level -L1 ,L19 & L26 |  |  |  |  | 37044.86 | 80% | 10% | 90% | 29635.888 | 3704.486 | 33340.374
66 | 70 |  | Water meter room Shaft wall at G.F to 31 Residential |  |  |  |  | 63819.06 |  | 0% |  | 10187.6304 | -10187.6304 | 0
67 | 71 |  | Ceiling, partition wall, wall painting works L18 |  |  |  |  | 17512.69 |  | 80% | 80% | 0 | 14010.152 | 14010.152
68 | 72 |  | Repainting works of all the rooms at B2 due to Water leakage |  |  |  |  | 22212.54 |  | 50% | 50% | 0 | 11106.27 | 11106.27
69 | 73 |  | Proceed with the painting work at CEF shaft opening wall at B2 to G.F |  |  |  |  | 22468.62 | 20% | 0% | 20% | 4493.724 | 0 | 4493.724
70 | 74 |  | Proceed with wall partition wall at GF for sliding door, refer to attached mark up dwg. |  |  |  |  | 24450.56 | 80% | 0% | 80% | 19560.448 | 0 | 19560.448
71 | 75 |  | Proceed with Epoxy final coat to Basement1 walls |  |  |  |  | 42291 | 10% | 90% | 100% | 4229.1 | 38061.9 | 42291
72 | 77 |  | Proceed with 2 layers of 12.5 mm thick boarded gypsum ceiling at Hotel Guest Room Type 11A, B, C, D , 7A & Presidential Suite ceiling for fabric fixing |  |  |  |  | 19303.76 |  | 50% | 50% |  | 9651.88 | 9651.88
73 | 78 |  | Temporary Internal ceiling & Corridor Wall openings cutting & Closing -Hotel |  |  |  |  | 1650 |  | 80% | 80% |  | 1320 | 1320
74 | 79 |  | PB.01 ceiling/ PA.04 Emulsion Wall paint works at Hotel L29 & G.F |  |  |  |  | 10423.25 |  | 50% | 50% |  | 5211.625 | 5211.625
75 | 80 |  | Proceed with the reinstatement of the ceiling with necessary painting works on level 7 of the Hotel tower as per the attached highlighted drawing. Note that the works have to be completed before 11.02.22 for the Client visit. |  |  |  |  | 9900 |  | 80% | 80% |  | 7920 | 7920
76 | 81 |  | 2 Hr Fire rated Permant Access door in Corridor Shaft Wall from Level 7,10,13,16,20,23 & 26 |  |  |  |  | 46900
77 | 82 |  | 60x60 cm gypsum tile false ceiling to GF BOH egress circulation Corridor |  |  |  |  | 2498.4
78 | 83 |  | Additional supports in 15A series flats for cladding works above minibar unit |  |  |  |  | 14327.4 |  | 80% | 80% |  | 11461.92 | 11461.92
79 | 84 |  | Grund Floor Ballroom external ceiling works (RFI ref. KCE-AX-RFI-GF-00443 Rev 00) |  |  |  |  | 10481.5 |  | 80% | 80% |  | 8385.2 | 8385.2
80 | 85 |  | Service Kitchen Partition wall at Hotel Level - 4 |  |  |  |  | 9654.88 |  | 80% | 80% |  | 7723.904 | 7723.904
81 | 86 |  | Podium Ceiling cutting and reinstatement with finishes |  |  |  |  | 30240 |  | 80% | 80% |  | 24192 | 24192
82 | 87 |  | Ceiling opening required to do MEP works |  |  |  |  | 3300 |  | 80% | 80% |  | 2640 | 2640
83 | 88 |  | Works as per detail on email from OME dated 13.02.23 for Basement 1 dining room area |  |  |  |  | 16272 |  | 80% | 80% |  | 13017.6 | 13017.6
84 | 89 |  | Proceed with the reinstatement of the ceiling with necessary painting works on level 8,910 & 11 of the Hotel tower as per the attached highlighted drawing. |  |  |  |  | 23396.98
0
0
[12 empty] | 0 | 0 | 0
TOTAL SUMMARY | [7 empty] | 4160246.901 |  |  |  | 2612308.3079 | 487882.1823 | 3100190.4901
2612308.3079
[10 empty] | (CARRIED TO PA) |  |  | 2790171.4411
COMPANY STAMP
1060056.4109
4328041.101

## VO -Day work)
| Day works | [6 empty] | IPA-07
0 | SECTION 04 - VARIATION SCHEDULE
1 | 2 |  | 3 | 4 | 5 | 6 |  | 7 | 9 | 10 | 8 | 12 | 13 | 11
|  |  |  | Ref. KCE to Sub-Cont |  |  |  | SVN budged Amount (Total) | PROGRESS Qunatity |  |  | PROGRESS AMOUNT
No | Sub Cont VO No | RGM VON | Description | KCE VO Ref # | qty | Rate |  |  | Previous | This Month | To Date | Previous | This Month | To Date
1 | 14 | 2 | Day Works 1& 2 (29-8-22 to 24-09-22 ) | E11-K121-SS-dm-138 |  |  | PS010 R6 | 38295 | 100% | 0% | 100% | 38295 | 0 | 38295
2 | 25 | 2 | Day Works 3,4,5& 6 (26-9-22 to 22-10-22 ) | E11-K121-SS-dm-138 |  |  |  | 47403 | 100% | 0% | 100% | 47403 | 0 | 47403
3 | 33 |  | Day Works 7 & 8 (22-10-22 to 24-11-22 ) |  |  |  |  | 26827.2 | 100% | 0% | 100% | 26827.2 | 0 | 26827.2
4 | 43 |  | Day Works 9 |  |  |  |  | 6789.6 | 100% | 0% | 100% | 6789.6 | 0 | 6789.6
5 | 58 |  | Day Works 10 |  |  |  |  | 11592 | 100% | 0% | 100% | 11592 | 0 | 11592
6 | 76 |  | Day Works 11 |  |  |  |  | 21321 | 100% | 0% | 100% | 21321 | 0 | 21321
7 | 90 |  | Day Works 12 |  |  |  |  | 15566.4 |  | 0% |  | 0 | 0 | 0 | Please provide supporting for this claim
8
9
10
0
0
[12 empty] | 0 | 0 | 0
TOTAL SUMMARY | [7 empty] | 167794.2 |  |  |  | 152227.8 | 0 | 152227.8
152227.8
[10 empty] | (CARRIED TO PA) |  |  | 152227.8
COMPANY STAMP
15566.4

## Paint
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [19 empty] | 2023-02-01
PAINT WORK QUANTITY CALCULATION | [19 empty] | IPA-09
E/1.Skim Coat 1-2mm to recive Low VOC | [14 empty] | 1 X Primer | 2 X Stucco | 1st -Paint | Final | Cum.Qty
Sn No | Drawing | BLG | Level | Room No/Grid | DESCRIPTION | WALL |  |  |  | Deduction |  |  |  |  | 20% | 30% | 30% | 20% | Net Total | Remarks
| 1212-3 | Res | B1 | P-B1-12 | Fresh Air Plenum | 24.56 | 5.5 | 1 | 135.08 | 5.9 | 2.4 | -1 | -14.16 | 120.92 | 24.184 | 36.276 | 36.276 | 24.184 | 120.92
[10 empty] | 2.9 | 2.4 | -1 | -6.96 | -6.96 | -1.392 | -2.088 | -2.088 | -1.392 | -6.96
| A-1214-7 | Res | G.F | P-GF-002 | Corridor | 35 | 4.8 | 1 | 143.5 | 2.1 | 2.1 | -1 | -4.41 | 139.09
| A-1214-7 | Res | G.F | P-GF-015 | FF Lobby | 16.2 | 3.3 | 1 | 53.46 | 1.2 | 2.1 | -2 | -5.04 | 48.42
| A-1215-7 | Hotel | G.F | P-GF-065 | BOH Cooridor | 57.2 | 3 | 1 | 171.6 | 0.9 | 2.1 | -6 | -11.34 | 160.26 |  |  |  |  | 160.26
| A-1215-7 | Hotel | G.F | P-GF-065 | BOH Cooridor |  |  |  |  | 1.8 | 2.1 | -2 | -7.56 | -7.56 |  |  |  |  | -7.56
| A-1215-7 | Hotel | G.F | P-GF-073 | FOOD STORAGE | 25.7 | 3 | 1 | 77.1 | 2 | 2.1 | -2 | -8.4 | 68.7 |  |  |  |  | 68.7
| A-1215-7 | Hotel | G.F | P-GF-051 | Lift Lobby | 21.8 | 3 | 1 | 65.4 | 1.1 | 2.1 | -6 | -13.86 | 51.54 |  |  |  |  | 51.54
| A-1215-7 | Hotel | G.F | [6 empty] | 3 | 2.1 | -1 | -6.3 | -6.3 |  |  |  |  | -6.3
| A-1215-7 | Hotel | G.F | P-GF-051 | House keeping Lift Lobby | 19.6 | 3 | 1 | 58.8 | 0.8 | 2.1 | -4 | -6.72 | 52.08 |  |  |  |  | 52.08
| A-1215-7 | Hotel | G.F | P-GF-059 | Lift Lobby | 10 | 3 | 1 | 30 | 1 | 2.1 | -2 | -4.2 | 25.8 |  |  |  |  | 25.8
| A-1215-7 | Hotel | G.F | P-GF-060 | Finishing Kitchen | 34 | 3 | 1 | 102 | 1 | 2.1 | -4 | -8.4 | 93.6 |  |  |  |  | 93.6
| A-1215-7 | Hotel | G.F | P-GF-035 | Pool bar lobby | 26.73 | 4.8 | 1 | 128.304 | 1 | 2.1 | -4 | -8.4 | 119.904 |  |  |  |  | 119.904
| A-1215-7 | Hotel | G.F | P-GF-0 | Pool bar lobby near | 12.3 | 4.8 | 1 | 59.04 | 1 | 2.1 | -4 | -8.4 | 50.64 |  |  |  |  | 50.64
| A-1215-7 | Hotel | L1 | P-01-013 | PR Cooridor | 20.9 | 3.2 | 1 | 66.88 | 1 | 2.1 | -2 | -4.2 | 62.68 |  |  |  |  | 62.68
| A-1215-7 | Hotel | L1 | P-01-026 | AV Contorl room | 20.9 | 3.2 | 1 | 66.88 | 1 | 2.1 | -2 | -4.2 | 62.68 |  |  |  |  | 62.68
| A-1215-7 | Hotel | L1 | P-01-017 | AV/SUITE EQUIP ROOM | 15.8 | 3.8 | 1 | 60.04 | 1 | 2.1 | -1 | -2.1 | 57.94 |  |  |  |  | 57.94
| A-1215-7 | Hotel | L1 | P-01-011 | Male prayer room | 18 | 3 | 1 | 54 | 1 | 2.1 | -2 | -4.2 | 49.8 |  |  |  |  | 49.8
| A-1215-7 | Hotel | L1 | P-01-015 | Female prayer room | 14.7 | 3 | 1 | 44.1 | 1 | 2.1 | -2 | -4.2 | 39.9 |  |  |  |  | 39.9
| A-1217-7 | Hotel | L2 | P-02-012 | Luggage Corridor | 52.14 | 4.2 | 1 | 218.988 | 1 | 2.1 | -5 | -10.5 | 208.488 |  |  |  |  | 208.488
| A-1217 | Hotel
| A-1218-7 | Res | L4 | P-04-011 | STO. | 18.56 | 3.87 | 1 | 71.8272 | 1 | 2.1 | -1 | -2.1 | 69.7272 |  |  |  |  | 69.7272
| A-1218-7 | Res | L4 | P-04-039 | House keeping Lobby | 15.2 | 3.87 | 1 | 58.824 | 1 | 2.1 | -3 | -6.3 | 52.524 |  |  |  |  | 52.524
| A-1235-6 | Res | L23 | R-24-07 | Elec Room | 9.85 | 5.6 | 1 | 55.16 | 0.8 | 2.1 | -1 | -1.68 | 53.48 | 10.696 | 16.044 | 16.044 | 10.696 | 53.48
| A-1226-11 | Hotel | L23 | H-24-08 | House Keep | 15.6 | 3 | 1 | 46.8 | 0.9 | 2.1 | -3 | -5.67 | 41.13 |  |  |  |  | 41.13
| A-1235-6 | Res | L23 | R-24-35 | BMU Storage
| A-1239-15 | Res | L31 | R-32-09 | Lift Machine room | 13.68 | 3.2 | 1 | 43.776 | 1 | 2.1 | -1 | -2.1 | 41.676 | 8.3352 | 12.5028 | 12.5028 | 8.3352 | 41.676
| A-1239-15 | Res | L31 | R-32-05 | Plant room | 48 | 3.3 | 1 | 158.4 | 1.2 | 2.1 | -2 | -5.04 | 153.36 |  |  |  |  | 153.36
[10 empty] | 1 | 2.1 | -1 | -2.1 | -2.1 |  |  |  |  | -2.1
[14 empty] | 1801.4192 |  |  |  |  | 1452.5183 | done
E/2 .Low VOC acrylic emulsion paint applied to a base (PA.04)
Sn No | Drawing | BLG | Level | Room No/Grid | DESCRIPTION | WALL |  |  |  | Deduction |  |  |  |  | 1 X Primer | 2 X Stucco | 1st -Paint | Final | Cum.Qty | Remarks
| 1212-3 | Res | B1 | P-B1-12 | Fresh Air Plenum | 24.56 | 5.5 | 1 | 135.08 | 5.9 | 2.4 | -1 | -14.16 | 120.92 | 24.184 | 36.276 | 36.276 | 24.184 | 120.92
[10 empty] | 2.9 | 2.4 | -1 | -6.96 | -6.96 | -1.392 | -2.088 | -2.088 | -1.392 | -6.96
| A-1235-6 | Res | L23 | R-24-07 | Elec Room | 9.85 | 5.6 | 1 | 55.16 | 0.8 | 2.1 | -1 | -1.68 | 53.48 | 10.696 | 16.044 | 16.044 | 10.696 | 53.48
|  | Res | B1 | P-B1-0113 | Irrigation Tank | 52.73 | 5.4 | 1 | 284.742 | 1 | 2.1 | -2 | -4.2 | 280.542 | 56.1084 | 84.1626 | 84.1626 | 56.1084 | 280.542
0
|  | Res | B1 | P-B1-143 | Balancing tank | 14.32 | 5.4 | 1 | 77.328 | 1 | 2.1 | -1 | -2.1 | 75.228 | 15.0456 | 22.5684 | 22.5684 | 15.0456 | 75.228
0
|  | Hotel | B1 | P-B1-018 | Garbage Room | 33.6 | 5.4 | 1 | 181.44 | 1 | 2.1 | -1 | -2.1 | 179.34 | 35.868 | 53.802 | 53.802 | 35.868 | 179.34
|  | Hotel | B1 | P-B1-019 | MAIN SERVER | 26.6 | 5.3 | 1 | 140.98 | 1.8 | 2.4 | -1 | -4.32 | 136.66 | 27.332 | 40.998 | 40.998 | 27.332 | 136.66
|  | Hotel | B1 | P-B1-019 | Dining | 64 | 3 | 1 | 140.98 | 1.8 | 2.4 | -4 | -4.32 | 136.66 | 27.332 | 40.998 | 40.998 | 27.332 | 136.66
0
| A-1214-7 | Res | G.F | P-GF-001 | SECURITY & EQUIPMENT ROOM | 17.1 | 6.08 | 1 | 103.968 | 1.2 | 2.1 | -1 | -2.52 | 101.448 | 20.2896 | 30.4344 | 25.362 |  | 76.086
| A-1214-7 | Res | G.F | P-GF-004 | BOH CIRCULATION | 19.8 | 4.8 | 1 | 95.04 | 2 | 2.1 | -2 | -8.4 | 86.64 | 17.328 | 25.992 | 25.992 |  | 69.312
| A-1214-7 | Res | G.F | P-GF-006 | PRESSURE | 15.75 | 6.08 | 1 | 95.76 | 1.1 | 2.1 | -1 | -2.31 | 93.45 | 18.69 | 28.035 | 23.3625 |  | 70.0875
| A-1214-7 | Res | G.F | [15 empty] | 0
| A-1214-7 | Res | G.F | P-GF-014 | WM ROOM | 6.3 | 6.08 | 1 | 38.304 | 0.9 | 2.3 | -2 | -4.14 | 34.164 | 6.8328 | 10.2492 | 10.2492 | 6.8328 | 34.164
| A-1214-7 | Res | G.F | P-GF-015 | FF Lobby | 16.2 | 3.3 | 1 | 53.46 | 1.2 | 2.1 | -2 | -5.04 | 48.42 | 9.684 | 14.526 | 14.526 | 9.684 | 48.42
| A-1214-7 | Res | G.F | P-GF-017 | HOUSEKEEPING LOBBY | 13.9 | 3.2 | 1 | 44.48 | 1 | 2.1 | -2 | -4.2 | 40.28 | 8.056 | 12.084 | 10.07 | 10.07 | 40.28
| A-1214-7 | Res | G.F |  | j | 5.2 | 0.5 | 1 | 2.6 | 0.8 | 2.1 | -1 | -1.68 | 0.92 | 0.184 | 0.276 | 0.23 | 0.23 | 0.92
| A-1214-7 | Res | G.F | P-GF-018 | ELEC RM | 9.9 | 6.08 | 1 | 60.192 | 1.1 | 2.1 | -1 | -2.31 | 57.882 |  |  |  |  | 0
| A-1214-7 | Res | G.F | [15 empty] | 0
| A-1214-7 | Res | G.F | P-GF-071 | BREACHING INLET | 4.3 | 6.1 | 1 | 26.23 |  |  |  |  | 26.23 |  |  |  |  | 0
| A-1214-7 | Res | G.F | P-GF-072 | FIRE COMMAND CENTRE | 19.7 | 6.1 | 1 | 120.17 | 0.9 | 2.1 | -1 | -1.89 | 118.28 | 23.656 | 35.484 | 29.57 |  | 88.71
| A-1214-7 | Res | G.F | P-GF-080 | FTR | 5.9 | 6.1 | 1 | 35.99 | 1 | 2.1 | -1 | -2.1 | 33.89 |  |  |  |  | 0
0
0
| A-1215-7 | Hotel | G.f | P-GF-022 | [10 empty] | 0 | 0 | 0 |  | 0
| A-1215-7 | Hotel | G.f | P-GF-022 | FF Lobby | 9.56 | 2.7 | 1 | 25.812 | 1 | 2.1 | -2 | -4.2 | 21.612 | 4.3224 | 6.4836 | 6.4836 | 4.3224 | 21.612
| A-1215-7 | Hotel | G.f | P-GF-056 | FTR | 10.36 | 4.2 | 1 | 43.512 | 1 | 2.1 | -1 | -2.1 | 41.412 |  |  |  |  | 0
| A-1215-7 | Hotel | G.f | P-GF-057 | ELEC RM | 11.23 | 4.2 | 1 | 47.166 | 1 | 2.1 | -1 | -2.1 | 45.066 |  |  |  | 9.0132 | 9.0132
| A-1215-7 | Hotel | G.F | P-GF-035 | Pool bar lobby | 26.73 | 4.8 | 1 | 128.304 | 1 | 2.1 | -4 | -8.4 | 119.904 | 23.9808 | 35.9712 | 35.9712 | 23.9808 | 119.904
| A-1215-7 | Hotel | G.F | P-GF-073 | Food storage | 25.8 | 2.7 | 1 | 69.66 | 1.9 | 2.1 | -2 | -7.98 | 61.68 | 12.336 | 18.504 | 18.504 | 12.336 | 61.68
| A-1215-7 | Hotel | G.F | P-GF-059 | Lift Lobby | 10 | 3 | 1 | 30 | 1 | 2.1 | -2 | -4.2 | 25.8 | 5.16 | 7.74 | 7.74 | 5.16 | 25.8
| A-1215-7 | Hotel | G.F | P-GF-055 | Egress Circulation | 42 | 3 | 1 | 126 | 0.9 | 2.1 | -3 | -5.67 | 120.33 | 24.066 | 36.099 | 36.099 | 24.066 | 120.33
| A-1215-7 | Hotel | G.F | P-GF-045 | Mech Room | 7.5 | 4.1 | 1 | 30.75 | 1.1 | 2.1 | -1 | -2.31 | 28.44 | 5.688 | 8.532 | 8.532 | 5.688 | 28.44
0
| A-1215-7 | Hotel | L1 | P-01-018 | Plant Room | 95.17 | 3.7 | 1 | 352.129 | 1.1 | 2.1 | -1 | -2.31 | 349.819 | 69.9638 | 104.9457 | 104.9457 |  | 279.8552
| A-1215-7 | Hotel | L1 |  |  | 2.82 | 3.7 | 3 | 31.302 |  |  |  |  | 31.302 | 6.2604 | 9.3906 | 9.3906 |  | 25.0416
| A-1215-7 | Hotel | L1 |  |  | 4.71 | 3.7 | 2 | 34.854 |  |  |  |  | 34.854 | 6.9708 | 10.4562 | 10.4562 |  | 27.8832
| A-1215-7 | Hotel | L1 | P-01-002 | Plant Room | 23.5 | 3.8 | 1 | 89.3 | 1.1 | 2.1 | -1 | -2.31 | 86.99 | 17.398 | 26.097 | 26.097 | 17.398 | 86.99
| A-1215-7 | Hotel | L1 | P-01-003 | Plant Room | 13.66 | 3.8 | 1 | 51.908 | 1.1 | 2.1 | -1 | -2.31 | 49.598 | 9.9196 | 14.8794 | 14.8794 | 9.9196 | 49.598
| A-1215-7 | Hotel | L1 | P-01-005 | FF Lobby | 9.5 | 3.2 | 1 | 30.4 | 1.1 | 2.1 | -2 | -4.62 | 25.78 | 5.156 | 7.734 | 7.734 | 5.156 | 25.78
| A-1215-7 | Hotel | L1 |  |  | 5.3 | 0.5 | 1 | 2.65 |  |  |  |  | 2.65 | 0.53 | 0.795 | 0.795 | 0.53 | 2.65
| A-1215-7 | Hotel | L1 | P-01-006 | Mech Room | 7.4 | 3.8 | 1 | 28.12 | 1 | 2.1 | -1 | -2.1 | 26.02 |  |  |  |  | 0
| A-1215-7 | Hotel | L1 | P-01-008 | Corridor | ceiling | [7 empty] | 88.65 | 17.73 | 26.595 | 26.595 |  | 70.92
| A-1215-7 | Hotel | L1 | P-01-011 | M.Prayer room | ceiling | [7 empty] | 20.7 | 4.14 | 6.21 | 6.21 |  | 16.56
| A-1215-7 | Hotel | L1 | P-01-013 | PR .Corridor | ceiling | [7 empty] | 15.93 | 3.186 | 4.779 | 4.779 |  | 12.744
|  |  |  | P-01-013 | PR .Corridor | 20.9 | 3.2 | 1 | 66.88 | 1 | 2.1 | -2 | -4.2 | 62.68 | 12.536 | 18.804 | 18.804 | 12.536 | 62.68
| A-1215-7 | Hotel | L1 | P-01-015 | F.Prayer room | ceiling | [7 empty] | 14.34 | 2.868 | 4.302 | 4.302 |  | 11.472
| A-1215-7 | Hotel | L1 | P-01-017 | AV/Suite Equip | 15.8 | 3.8 | 1 | 60.04 | 1 | 2.1 | -1 | -2.1 | 57.94 | 11.588 | 17.382 | 17.382 | 11.588 | 57.94
| A-1215-7 | Hotel | L1 | P-01-026 | AV Control room | 27.3 | 3.8 | 1 | 103.74 | 1 | 2.1 | -1 | -2.1 | 101.64 | 20.328 | 30.492 | 30.492 | 20.328 | 101.64
| A-1215-7 | Hotel | L1 | P-01-021 | FIR | 10.4 | 3.7 | 1 | 38.48 | 1 | 2.1 | -1 | -2.1 | 36.38 |  |  |  |  | 0
| A-1215-7 | Hotel | L1 | P-01-022 | Elec Room | 11.2 | 3.7 | 1 | 41.44 | 1 | 2.1 | -1 | -2.1 | 39.34 |  |  |  |  | 0
0
| A-1217 | Hotel | L2 | P-02-40 | House keeping Lobby | 13.3 | 2.7 | 1 | 35.91 | 1.1 | 2.1 | -2 | -4.62 | 31.29 | 6.258 | 9.387 | 9.387 |  | 25.032
| A-1217 | Hotel | L2 | P-02-98 | BOH Corridor | 33 | 2.7 | 1 | 89.1 | 1.1 | 2.1 | -2 | -4.62 | 84.48 | 16.896 | 25.344 | 25.344 |  | 67.584
| A-1217 | Hotel | L2 | P-02-92 | Bev | 14.9 | 2.7 | 1 | 40.23 | 1.1 | 2.1 | -1 | -2.31 | 37.92 | 7.584 | 11.376 | 11.376 |  | 30.336
| A-1217 | Hotel | L2 | P-02-90 |  | 16.2 | 2.7 | 1 | 43.74 | 1.1 | 2.1 | -1 | -2.31 | 41.43 | 8.286 | 12.429 | 12.429 |  | 33.144
| A-1217 | Hotel | L2 | P-02-12 | Luggage Corridor | 23.1 | 4.2 | 1 | 97.02 | 0.8 | 2.1 | -1 | -1.68 | 95.34 | 19.068 | 28.602 | 28.602 |  | 76.272
0
| A-1216 | Res | L2 | P-02-004 | FF Lobby | 16.3 | 3 | 1 | 48.9 | 1.1 | 2.1 | -3 | -6.93 | 41.97 | 8.394 | 12.591 | 10.4925 | 10.4925 | 41.97
| A-1216 | Res | L2 |  | J O | 11.4 | 0.5 | 1 | 5.7 | 2 | 2.1 | -1 | -4.2 | 1.5 | 0.3 | 0.45 | 0.375 | 0.375 | 1.5
| A-1216 | Res | L2 | P-02-005 | W M Room | 6.3 | 4.2 | 1 | 26.46 | 1 | 2.1 | -2 | -4.2 | 22.26 | 4.452 | 6.678 | 5.565 | 5.565 | 22.26
| A-1216 | Res | L2 |  | J O | 5.2 | 0.5 | 2 | 5.2 |  |  |  |  | 5.2 | 1.04 | 1.56 | 1.3 | 1.3 | 5.2
| A-1216 | Res | L2 | P-02-006 | Housekeeping | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -3 | -6.93 | 38.37 | 7.674 | 11.511 | 9.5925 | 9.5925 | 38.37
| A-1216 | Res | L2 |  | J O | 5.2 | 0.5 | 1 | 2.6 |  |  |  | 0 | 2.6 | 0.52 | 0.78 | 0.65 | 0.65 | 2.6
| A-1216 | Res | L2 | P-02-007 | [10 empty] | 0 | 0 | 0 | 0 | 0
| A-1216 | Res | L2 | P-02-008 | FTR | 11.74 | 4.2 | 1.1 | 54.2388 | 1 | 2.1 | -1 | -2.1 | 52.1388 |  |  |  |  | 0
| A-1216 | Res | L2 | P-02-009 | Elec Room | 9.88 | 4.2 | 1 | 41.496 | 1.1 | 2.1 | -1 | -2.31 | 39.186 |  |  |  |  | 0
0
| A-1217 | Hotel | L3 | P-03-23 | Elec Room | 11.1 | 3.3 | 1 | 36.63 | 1 | 2.1 | -1 | -2.1 | 34.53 |  |  |  |  | 0
| A-1217 | Hotel | L3 | P-03-24 | FIR | 11.75 | 3.3 | 1 | 38.775 | 1 | 2.1 | -1 | -2.1 | 36.675 |  |  |  |  | 0
0
| A-1216 | Res | L3 | P-03-002 | Pool Plant | 50.13 | 3.7 | 1 | 185.481 | 0.9 | 2.1 | -1 | -1.89 | 183.591 | 36.7182 | 55.0773 | 55.0773 |  | 146.8728
| A-1216 | Res | L3 | P-03-027 | Plant Space room | 49 | 3 | 1 | 147 | 1.1 | 2.1 | -2 | -4.62 | 142.38 | 28.476 | 42.714 | 42.714 |  | 113.904
| A-1216 | Res | L3 | P-03-001 | MEP CORRIDOR | 15.9 | 3.7 | 1 | 58.83 | 0.9 | 2.1 | -2 | -3.78 | 55.05 | 11.01 | 16.515 | 16.515 |  | 44.04
| A-1216 | Res | L3 | P-03-008 | WM | 6.3 | 4.4 | 1 | 27.72 | 0.9 | 2.1 | -1 | -1.89 | 25.83 |  |  |  |  | 0
| A-1216 | Res | L3 | P-03-009 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.1 | 2.1 | -3 | -6.93 | 41.67 | 8.334 | 12.501 | 10.4175 | 10.4175 | 41.67
| A-1216 | Res | L3 | P-03-009 | J O | 11.4 | 0.5 | 1 | 5.7 | 2 | 2.1 | -1 | -4.2 | 1.5 | 0.3 | 0.45 | 0.375 | 0.375 | 1.5
| A-1216 | Res | L3 | P-03-028 | DRIVER'S CORRIDOR | 20.4 | 3 | 1 | 61.2 | 1.1 | 2.1 | -3 | -6.93 | 54.27 |  |  |  |  | 0
| A-1216 | Res | L3 | P-03-029 | DRIVER'S CORRIDOR | 32.75 | 3.7 | 1 | 121.175 | 1.1 | 2.1 | -1 | -2.31 | 118.865
| A-1216 | Res | L3 | P-03-030 | MEP | 26.3 | 3.7 | 1 | 97.31 | 1.1 | 2.1 | -1 | -2.31 | 95
| A-1216 | Res | L3 | P-03-031 | DRIVER'S LIVING SPACE |  | 3.7 | 1 | 0 | 1.1 | 2.1 | -1 | -2.31 | -2.31
| A-1218-7 | Res | L4 | P-04-008 | Elec Room | 9.88 | 3.87 | 1 | 38.2356 | 1 | 2.1 | -1 | -2.1 | 36.1356 |  |  |  |  | 0
| A-1218-7 | Res | L4 | P-04-003 | F F Lobby | 16.2 | 2.5 | 1 | 40.5 | 2 | 2.1 | -1 | -4.2 | 36.3 | 7.26 | 10.89 | 10.89 | 9.075 | 38.115
| A-1218-7 | Res | L4 |  |  | 6.2 | 0.5 | 2 | 6.2 |  |  |  |  | 6.2 | 1.24 | 1.86 | 1.86 | 1.55 | 6.51
| A-1218-7 | Res | L4 | P-04-039 | House keeping Lobby | 15.2 | 3.87 | 1 | 58.824 | 1 | 2.1 | -3 | -6.3 | 52.524 | 10.5048 | 15.7572 | 15.7572 | 13.131 | 55.1502
| A-1218-7 | Res | L4 | P-04-005 | WMR | 6.28 | 3.87 | 1 | 24.3036 | 0.8 | 2.1 | -1 | -1.68 | 22.6236 | 4.5247 | 6.7871 | 5.6559 | 5.6559 | 22.6236
| A-1218-7 | Res | L4 | P-04-007 | FTR | 5.4 | 3.87 | 1 | 20.898 | 1 | 2.1 | -1 | -2.1 | 18.798 | 3.7596 | 5.6394 | 4.6995 | 4.6995 | 18.798
| A-1218-7 | Res | L4 | P-04-011 | STO. | 18.56 | 3.87 | 1 | 71.8272 | 1 | 2.1 | -1 | -2.1 | 69.7272 | 13.9454 | 20.9182 | 17.4318 | 17.4318 | 69.7272
0
| A-1218-2 | Res | L5 | P-05-001 | F F Lobby | 16.2 | 2.6 | 1 | 42.12 | 1.1 | 2.1 | -1 | -2.31 | 39.81 | 7.962 | 11.943 | 9.9525 | 9.9525 | 39.81
| A-1218-2 | Res | L5 |  | J O | 5.3 | 0.5 | 1 | 2.65 | 0.9 | 2.1 | -3 | -5.67 | -3.02 | -0.604 | -0.906 | -0.755 | -0.755 | -3.02
| A-1218-2 | Res | L5 | P-05-002 | WMR | 6.28 | 6.3 | 1 | 39.564 | 0.8 | 2.1 | -1 | -1.68 | 37.884 | 7.5768 | 11.3652 | 9.471 | 9.471 | 37.884
| A-1218-2 | Res | L5 | P-05-04 | Elec Room | 9.88 | 6.3 | 1 | 62.244 | 1.1 | 2.1 | -1 | -2.31 | 59.934 |  |  |  | 14.9835 | 14.9835
| A-1218-2 | Res | L5 | P-05-05 | FTR | 11.74 | 6.3 | 1 | 73.962 | 1 | 2.1 | -1 | -2.1 | 71.862 | 14.3724 | 21.5586 | 17.9655 | 17.9655 | 71.862
| A-1218-2 | Res | L5 | P-05-14 | Tele Room | 5.4 | 6.3 | 1 | 34.02 | 1.1 | 2.1 | -1 | -2.31 | 31.71 | 6.342 | 9.513 | 7.9275 | 7.9275 | 31.71
| A-1218-2 | Res | L5 | P-05-17 | SERVICE CORRIDOR | 15.2 | 3 | 1 | 45.6 | 1.1 | 2.1 | -1 | -2.31 | 43.29 | 8.658 | 12.987 | 10.8225 | 10.8225 | 43.29
| A-1219 | Hotel | L5 | P-05-10 | Mech Room | 7.5 | 8.8 | 1 | 66 | 1 | 2.1 | -1 | -2.1 | 63.9 | 12.78 | 19.17 | 19.17 | 12.78 | 63.9
| A-1219 | Hotel | L5 | P-05-13 | Elec Room | 11.2 | 8.8 | 1 | 98.56 | 1 | 2.1 | -1 | -2.1 | 96.46 | 19.292 | 28.938 | 28.938 | 19.292 | 96.46
| A-1219 | Hotel | L5 | P-05-15 | FIR | 10.4 | 8.8 | 1 | 91.52 | 1 | 2.1 | -1 | -2.1 | 89.42 | 17.884 | 26.826 | 26.826 | 17.884 | 89.42
| A-1219 | Hotel | L5 | P-05-20 | F F Lobby | 9.45 | 3 | 1 | 28.35 | 1 | 2.1 | -3 | -6.3 | 22.05 | 4.41 | 6.615 | 6.615 | 4.41 | 22.05
| A-1219 | Hotel | L5
| 1220-3 | Hotel | 7 | P-07-01 | FF Lobby | 9.5 | 2.7 | 1 | 25.65 | 1.2 | 2.1 | -3 | -7.56 | 18.09 |  |  |  |  | 0
| 1220-3 | Hotel | 7 |  |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| 1220-3 | Hotel | 7 | P-07-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| 1220-3 | Hotel | 7 | P-07-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| 1220-3 | Hotel | 7 | P-07-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1220-2 | Hotel | L8 | P-08-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
| 1220-3 | Hotel |  |  |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| 1220-3 | Hotel | L8 | P-08-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| 1220-3 | Hotel | L8 | P-08-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| 1220-3 | Hotel | L8 | P-08-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-12201-2 | Hotel | L9 | P-09-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
| A-12201-2 | Hotel |  |  |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-12201-2 | Hotel | L9 | P-09-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-12201-2 | Hotel | L9 | P-09-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-12201-2 | Hotel | L9 | P-09-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-12201-2 | Hotel | L10 | P-10-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
| A-12201-2 | Hotel | L10 |  |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-12201-2 | Hotel | L10 | P-10-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-12201-2 | Hotel | L10 | P-10-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-12201-2 | Hotel | L10 | P-10-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1221-2 | Hotel | L11 | P-11-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
[6 empty] | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
|  |  |  | P-11-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1221-2 | Hotel | L11 | P-11-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1221-2 | Hotel | L11 | P-11-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1221-2 | Hotel | L12 | P-12-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
| A-1221-2 | Hotel | L12 | P-12-01 |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-1221-2 | Hotel | L12 | P-12-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1221-2 | Hotel | L12 | P-12-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1221-2 | Hotel | L12 | P-12-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1222-2 | Hotel | L13 | P-13-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
[6 empty] | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-1222-2 | Hotel | L13 | P-13-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1222-2 | Hotel | L13 | P-13-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1222-2 | Hotel | L13 | P-13-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1222-2 | Hotel | L14 | P-14-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
[6 empty] | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-1222-2 | Hotel | L14 | P-14-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1222-2 | Hotel | L14 | P-14-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1222-2 | Hotel | L14 | P-14-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1222-2 | Hotel | L15 | P-15-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
| A-1222-2 | Hotel | L15 | P-15-01 |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-1222-2 | Hotel | L15 | P-15-03 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1222-2 | Hotel | L15 | P-15-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1222-2 | Hotel | L15 | P-15-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1222-2 | Hotel | L16 | P-16-01 | FF Lobby | 9.5 | 3 | 1 | 28.5 | 1.2 | 2.1 | -3 | -7.56 | 20.94 |  |  |  |  | 0
| A-1222-2 | Hotel | L16 | P-16-01 |  | 4.3 | 0.4 | 2 | 3.44 |  |  |  |  | 3.44 |  |  |  |  | 0
| A-1222-2 | Hotel | L16 | P-16-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1222-2 | Hotel | L16 | P-16-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1222-2 | Hotel | L16 | P-16-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1223-3 | Hotel | L17 | H-17-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1223-3 | Hotel | L17 | H-17-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1223-3 | Hotel | L17 | H-17-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1223-3 | Hotel | L18 | H-18-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1223-3 | Hotel | L18 | H-18-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1223-3 | Hotel | L18 | H-18-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1223-3 | Hotel | L18 | H-18-011 | Fire Pump Tank | 33.8 | 3.3 | 1 | 111.54 | 1 | 2.1 | -1 | -2.1 | 109.44 |  |  |  |  | 0
| A-1223-3 | Hotel | L18 | H-18-012 | Pump Room | 34 | 3.3 | 1 | 112.2 | 1 | 2.1 | -1 | -2.1 | 110.1 |  |  |  |  | 0
| A-1224-3 | Hotel | L19 | H-19-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1224-3 | Hotel | L19 | H-19-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1224-3 | Hotel | L19 | H-19-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1224-3 | Hotel | L20 | H-20-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1224-3 | Hotel | L20 | H-20-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1224-3 | Hotel | L20 | H-20-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1225-3 | Hotel | L21 | H-21-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1225-3 | Hotel | L21 | H-21-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1225-3 | Hotel | L21 | H-21-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1225-3 | Hotel | L22 | H-22-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1225-3 | Hotel | L22 | H-22-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1225-3 | Hotel | L22 | H-22-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1226-3 | Hotel | L23 | H-23-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1226-3 | Hotel | L23 | H-23-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1226-3 | Hotel | L23 | H-23-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1226-3 | Hotel | L24 | H-24-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1226-3 | Hotel | L24 | H-24-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1226-3 | Hotel | L24 | H-24-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1227-3 | Hotel | L25 | H-25-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1227-3 | Hotel | L25 | H-25-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1227-3 | Hotel | L25 | H-25-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1227-3 | Hotel | L26 | H-26-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1227-3 | Hotel | L26 | H-26-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1227-3 | Hotel | L26 | H-26-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1227-3 | Hotel | L27 | H-27-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1227-3 | Hotel | L27 | H-27-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1227-3 | Hotel | L27 | H-27-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1227-3 | Hotel | L28 | H-26-02 | Mech Room | 7.5 | 3.3 | 1 | 24.75 | 1 | 2.1 | -1 | -2.1 | 22.65 |  |  |  |  | 0
| A-1227-3 | Hotel | L28 | H-28-06 | Elec Room | 11.2 | 3.3 | 1 | 36.96 | 1 | 2.1 | -1 | -2.1 | 34.86 |  |  |  |  | 0
| A-1227-3 | Hotel | L28 | H-28-07 | FIR | 10.4 | 3.3 | 1 | 34.32 | 1 | 2.1 | -1 | -2.1 | 32.22 |  |  |  |  | 0
| A-1227-3 | Hotel | L29 | H-32-02 | Lift Machine | 48.1 | 3.3 | 1 | 158.73 | 1 | 2.1 | -1 | -2.1 | 156.63
| A-1235-6 | Res | L23 | R-24-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
| A-1235-6 | Res | L23 | R-24-01 | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1235-6 | Res | L23 | R-24-07 | Elec Room | 9.85 | 5.6 | 1 | 55.16 | 0.8 | 2.1 | -1 | -1.68 | 53.48 | 10.696 | 16.044 | 16.044 | 16.044 | 58.828
| A-1235-6 | Res | L23 | R-24-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
| A-1235-6 | Res | L23 | R-24-15 | Plant Room | 52.86 | 5.6 | 1 | 296.016 | 1.2 | 2.1 | -1 | -2.52 | 293.496 | 58.6992 | 88.0488 | 88.0488 | 88.0488 | 322.8456
| A-1235-6 | Res | L23 |  |  | 4.4 | 5.6 | 1 | 24.64 | 0.8 |  |  |  | 24.64 | 4.928 | 7.392 | 7.392 | 7.392 | 27.104
| A-1235-6 | Res | L23 | R-24-16 | Plant Room | 70.8 | 5.6 | 1 | 396.48 | 1.9 | 2.1 | -1 | -3.99 | 392.49 | 78.498 | 117.747 | 117.747 | 117.747 | 431.739
| A-1235-6 | Res | L23 | R-24-02 | WM room | 6.28 | 5.6 | 1 | 35.168 | 0.9 | 2.1 | -1 | -1.89 | 33.278 | 6.6556 | 9.9834 | 9.9834 | 9.9834 | 36.6058
| A-1235-6 | Res | L23 | R-24-10 | Telcom Room | 8.3 | 5.6 | 1 | 46.48 | 0.8 | 2.1 | -1 | -1.68 | 44.8 | 8.96 | 13.44 | 13.44 | 13.44 | 49.28
| A-1235-6 | Res | L23 | R-24-35 | BMU STORAGE | 26.1 | 5.6 | 1 | 146.16 | 1.6 | 2.1 | -1 | -3.36 | 142.8 | 28.56 | 42.84 | 42.84 | 42.84 | 157.08
| A-1236-7 | Res | L24 | R-25-001 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
[5 empty] | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1236-7 | Res | L24 | R-25-07 | Elec Room | 9.85 | 4.85 | 1 | 47.7725 | 0.8 | 2.1 | -1 | -1.68 | 46.0925 | 9.2185 | 13.8277 | 13.8277 | 13.8277 | 50.7017
| A-1236-7 | Res | L24 | R-25-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
[5 empty] | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-1236-7 | Res | L25 | R-26-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
[5 empty] | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1236-7 | Res | L25 | R-26-07 | Elec Room | 9.85 | 4.2 | 1 | 41.37 | 0.8 | 2.1 | -1 | -1.68 | 39.69 | 7.938 | 11.907 | 11.907 | 11.907 | 43.659
| A-1236-7 | Res | L25 | R-26-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
[5 empty] | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-12361-14 | Res | L26 | R-27-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
| A-12361-14 | Res | L26 | R-27-01 | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-12361-14 | Res | L26 | R-27-02 | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-12361-14 | Res | L26 | R-27-07 | Elec Room | 9.85 | 4.2 | 1 | 41.37 | 0.8 | 2.1 | -1 | -1.68 | 39.69 | 7.938 | 11.907 | 11.907 | 11.907 | 43.659
| A-12361-14 | Res | L26 | R-27-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99
[5 empty] | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-1237-7 | Res | L27 | R-28-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
| A-1237-7 | Res | L27 | R-28-02 | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1237-7 | Res | L27 | R-28-07 | Elec Room | 9.85 | 4.2 | 1 | 41.37 | 0.8 | 2.1 | -1 | -1.68 | 39.69 | 7.938 | 11.907 | 11.907 | 11.907 | 43.659
| A-1237-7 | Res | L27 | R-28-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
[5 empty] | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-1237-7 | Res | L28 | R-29-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
| A-1237-7 | Res | L28 | R-29-01 | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1237-7 | Res | L28 | R-29-07 | Elec Room | 9.85 | 4.2 | 1 | 41.37 | 0.8 | 2.1 | -1 | -1.68 | 39.69 | 7.938 | 11.907 | 11.907 | 11.907 | 43.659
| A-1237-7 | Res | L28 | R-29-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
[5 empty] | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-1238-15 | Res | L29 | R-30-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
| A-1238-15 | Res | L29 | R-30-01 | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1238-15 | Res | L29 | R-30-07 | Elec Room | 9.85 | 4.2 | 1 | 41.37 | 0.8 | 2.1 | -1 | -1.68 | 39.69 | 7.938 | 11.907 | 11.907 | 11.907 | 43.659
| A-1238-15 | Res | L29 | R-30-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
| A-1238-15 | Res | L29 |  | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-1238-15 | Res | L30 | R-31-01 | FF Lobby | 16.2 | 3 | 1 | 48.6 | 1.9 | 2.1 | -1 | -3.99 | 44.61 | 8.922 | 13.383 | 13.383 | 13.383 | 49.071
| A-1238-15 | Res | L30 | R-31-02 | J O | 11.3 | 0.5 | 1 | 5.65 | 1 | 2.1 | -3 | -6.3 | -0.65 | -0.13 | -0.195 | -0.195 | -0.195 | -0.715
| A-1238-15 | Res | L30 | R-31-07 | Elec Room | 9.85 | 4.2 | 1 | 41.37 | 0.8 | 2.1 | -1 | -1.68 | 39.69 | 7.938 | 11.907 | 11.907 | 11.907 | 43.659
| A-1238-15 | Res | L30 | R-31-08 | House Keep Lobby | 15.1 | 3 | 1 | 45.3 | 1.1 | 2.1 | -1 | -2.31 | 42.99 | 8.598 | 12.897 | 12.897 | 12.897 | 47.289
| A-1238-15 | Res | L30 | R-31-02 | WM room | 6.28 | 4.2 | 1 | 26.376 | 0.9 | 2.1 | -1 | -1.89 | 24.486 | 4.8972 | 7.3458 | 7.3458 | 7.3458 | 26.9346
| A-1238-15 | Res | L30 | R-31-13 | Lift Machine room | 26.9 | 4.2 | 1 | 112.98 | 1 | 2.1 | -1 | -2.1 | 110.88 | 22.176 | 33.264 | 33.264 | 33.264 | 121.968
| A-1239-15 | Res | L31 | R-32-05 | Plant room | 48 | 3.3 | 1 | 158.4 | 1.2 | 2.1 | -2 | -5.04 | 153.36 | 30.672 | 46.008 | 46.008 | 46.008 | 168.696
[10 empty] | 1 | 2.1 | -1 | -2.1 | -2.1 | -0.42 | -0.63 | -0.63 | -0.63 | -2.31
| A-1239-15 | Res | L31 | R-32-06 | Fire Exit Lobby | 8.6 | 3.3 | 1 | 28.38 | 1 | 2.1 | -2 | -4.2 | 24.18 | 4.836 | 7.254 | 7.254 | 7.254 | 26.598
| A-1239-15 | Res | L31 | R-32-07 | Fire Exit Lobby | 9 | 3.3 | 1 | 29.7 | 1 | 2.1 | -3 | -6.3 | 23.4 | 4.68 | 7.02 | 7.02 | 7.02 | 25.74
| A-1239-15 | Res | L31 | R-32-08 | MEP Plant room | 21.7 | 3.3 | 1 | 71.61 | 1 | 2.1 | -1 | -2.1 | 69.51 | 13.902 | 20.853 | 20.853 | 20.853 | 76.461
| A-1239-15 | Res | L31 | R-32-09 | Lift Machine room | 13.68 | 3.2 | 1 | 43.776 | 1 | 2.1 | -1 | -2.1 | 41.676 | 8.3352 | 12.5028 | 12.5028 | 12.5028 | 45.8436
| A-1239-15 | Res | L31 | R-32-12 | GSM Room | 11.56 | 3.2 | 1 | 36.992 | 1 | 2.1 | -1 | -2.1 | 34.892 | 6.9784 | 10.4676 | 10.4676 | 10.4676 | 38.3812
| A-1239-15 | Res | L31 | R-32-13 | FTR Room | 11.86 | 3.2 | 1 | 37.952 | 1 | 2.1 | -1 | -2.1 | 35.852 | 7.1704 | 10.7556 | 10.7556 | 10.7556 | 39.4372
| A-1239-15 | Res | L31 | R-32-16 | MEP Corridor | 9.76 | 3.2 | 1 | 31.232 | 1 | 2.1 | -2 | -4.2 | 27.032 | 5.4064 | 8.1096 | 8.1096 | 8.1096 | 29.7352
[14 empty] | 10473.2417 |  |  |  |  | 6240.5524 | 0
E/3 .Epoxy Resin Painting to Wall
Sn No | Drawing | BLG | Level | Room No/Grid | DESCRIPTION | WALL |  |  |  | Deduction |  |  |  |  | 1 X Primer | 2 X Stucco | 1st -Paint | Final | Cum.Qty | Remarks
| 1213-3 | Hotel | B1 |  | Corridor | 318 | 2.7 | 1 | 858.6 | 0.9 | 2.1 | -20 | -37.8 | 820.8 | 164.16 | 246.24 | 246.24 | 246.24 | 902.88
[10 empty] | 1.8 | 2.1 | -16 | -60.48 | -60.48 | -12.096 | -18.144 | -18.144 | -18.144 | -66.528
[10 empty] | 1.2 | 1.25 | -12 | -18 | -18 | -3.6 | -5.4 | -5.4 | -5.4 | -19.8
| A-1215-7 | Hotel | G.F | P-GF-065 | BOH Cooridor | 57.2 | 3 | 1 | 171.6 | 0.9 | 2.1 | -6 | -11.34 | 160.26 | 32.052 | 48.078 | 48.078 | 48.078 | 176.286
| A-1215-7 | Hotel | G.F | P-GF-065 | BOH Cooridor |  |  |  |  | 1.8 | 2.1 | -2 | -7.56 | -7.56 | -1.512 | -2.268 | -2.268 | -2.268 | -8.316
| A-1215-7 | Hotel | G.F | P-GF-073 | FOOD STORAGE | 25.7 | 3 | 1 | 77.1 | 2 | 2.1 | -2 | -8.4 | 68.7 | 13.74 | 20.61 | 20.61 | 20.61 | 75.57
| A-1215-7 | Hotel | G.F | P-GF-074 | Vestibule | 11.3 | 3 | 1 | 33.9 | 1 | 2.1 | -1 | -2.1 | 31.8 | 6.36 | 9.54 | 9.54 | 9.54 | 34.98
| A-1215-7 | Hotel | G.F | P-GF-053 | House keeping Lift Lobby | 19.6 | 3 | 1 | 58.8 | 0.8 | 2.1 | -4 | -6.72 | 52.08 | 10.416 | 15.624 | 15.624 | 15.624 | 57.288
| A-1215-7 | Hotel | G.F | P-GF-059 | Lift Lobby | 10 | 3 | 1 | 30 | 1 | 2.1 | -2 | -4.2 | 25.8 | 5.16 | 7.74 | 7.74 | 7.74 | 28.38
| A-1215-7 | Hotel | G.F | P-GF-060-a | Finishing Kitchen | 24.9 | 3 | 1 | 74.7 | 1 | 2.1 | -1 | -2.1 | 72.6 | 14.52 | 21.78 | 21.78 | 21.78 | 79.86
| A-1215-7 | Hotel | G.F | P-GF-060-1 | Near room | 20.95 | 3 | 1 | 62.85 | 1 | 2.1 | -2 | -4.2 | 58.65 | 11.73 | 17.595 | 17.595 | 17.595 | 64.515
| A-1215-7 | Hotel | G.F | P-GF-043 | Service Support Area | 22.2 | 2.4 | 1 | 53.28 | 0.9 | 2.1 | -5 | -9.45 | 43.83 | 8.766 | 13.149 | 13.149 | 13.149 | 48.213
| A-1215-7 | Hotel | L1 | P-01-004 | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 1 | 2.1 | -2 | -4.2 | 47.88 | 9.576 | 14.364 | 14.364 | 14.364 | 52.668
| A-1215-7 | Hotel | L1 | [6 empty] | 1.2 | 2.1 | -3 | -7.56 | -7.56 | -1.512 | -2.268 | -2.268 | -2.268 | -8.316
| A-1215-7 | Hotel | L1 | P-01-020 | House keeping Lobby | 15.57 | 2.4 | 1 | 37.368 | 0.9 | 2.1 | -5 | -9.45 | 27.918 | 5.5836 | 8.3754 | 8.3754 | 8.3754 | 30.7098
| A-1217-7 | Hotel | L2 | P-02-015 | Service Support Area | 21.7 | 2.7 | 1 | 58.59 | 1 | 2.1 | -2 | -4.2 | 54.39 | 10.878 | 16.317 | 16.317 |  | 43.512
| A-1217-7 | Hotel | L2 | [6 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -3.024 |  | -8.064
| A-1217-7 | Hotel | L2 | P-02-020 | CORRIDOR | 24.45 | 2.4 | 1 | 58.68 | 0.9 | 2.1 | -5 | -9.45 | 49.23 | 9.846 | 14.769 | 14.769 |  | 39.384
| A-1217-7 | Hotel | L2 | P-02-021 | WAITER SUPPORT | 6.95 | 2.4 | 1 | 16.68 |  |  |  |  | 16.68 | 3.336 | 5.004 | 5.004 |  | 13.344
| A-1217-7 | Hotel | L2 | P-02-022 | STORE | 7.84 | 2.4 | 1 | 18.816 | 0.9 | 2.1 | -1 | -1.89 | 16.926 | 3.3852 | 5.0778 | 5.0778 |  | 13.5408
| A-1217-7 | Hotel | L2 | P-02-023 | WASH UP | 12.47 | 2.4 | 1 | 29.928 | 0.9 | 2.1 | -1 | -1.89 | 28.038 | 5.6076 | 8.4114 | 8.4114 |  | 22.4304
| A-1217-7 | Hotel | L2 | P-02-024 | FOOD SET UP | 14.6 | 2.4 | 1 | 35.04 | 1 | 2.1 | -1 | -2.1 | 32.94 | 6.588 | 9.882 | 9.882 |  | 26.352
| A-1217-7 | Hotel | L2 | P-02-025 | FRONT OFFICE | 12.4 | 2.4 | 1 | 29.76 | 0.9 | 2.1 | -1 | -1.89 | 27.87 | 5.574 | 8.361 | 8.361 |  | 22.296
| A-1217-7 | Hotel | L2 | P-02-026 | FRONT OFFICE SUPPORT | 16.7 | 2.4 | 1 | 40.08 | 0.9 | 2.1 | -1 | -1.89 | 38.19 | 7.638 | 11.457 | 11.457 |  | 30.552
| A-1217-7 | Hotel | L2 | P-02-028 | CORRIDOR | 36.28 | 2.4 | 1 | 87.072 | 0.9 | 2.1 | -7 | -13.23 | 73.842 | 14.7684 | 22.1526 | 22.1526 |  | 59.0736
| A-1217-7 | Hotel | L2 | [6 empty] | 1.5 | 2.1 | -1 | -3.15 | -3.15 | -0.63 | -0.945 | -0.945 |  | -2.52
| A-1217-7 | Hotel | L2 | P-02-040 | House keeping Lobby | 15.54 | 2.7 | 1 | 41.958 | 0.9 | 2.1 | -5 | -9.45 | 32.508 | 6.5016 | 9.7524 | 9.7524 |  | 26.0064
| A-1219-2 | Hotel | L4 | P-04-018 | House keeping Lobby | 15.54 | 2.5 | 1 | 38.85 | 0.9 | 2.1 | -5 | -9.45 | 29.4 | 5.88 | 8.82 | 8.82 |  | 23.52
| A-1219-2 | Hotel | L4 | P-04-031 | Service Support Area | 21.7 | 2.5 | 1 | 54.25 | 0.9 | 2.1 | -3 | -5.67 | 48.58 | 9.716 | 14.574 | 14.574 |  | 38.864
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -3.024 |  | -8.064
| A-1219-2 | Hotel | L4 |  | BOH Kitchen | 43 | 2.75 | 1 | 118.25 | 1 | 2.1 | -1 | -2.1 | 116.15 | 23.23 | 34.845 | 34.845 |  | 92.92
| A-1219-2 | Hotel | L4 |  | BOH Kitchen | 80 | 2.75 | 1 | 220 | 1 | 2.1 | -5 | -10.5 | 209.5 | 41.9 | 62.85 | 62.85 |  | 167.6
| A-1219-2 | Hotel | L5 | P-05-019 | House keeping Lobby | 15.54 | 2.4 | 1 | 37.296 | 0.9 | 2.1 | -5 | -9.45 | 27.846 | 5.5692 | 8.3538 | 6.9615 | 6.9615 | 27.846
| A-1219-2 | Hotel | L5 | P-05-021 | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 |  |  |  |  | 0
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 |  |  |  |  | 0
| 1220-3 | Hotel | 7 | H-07-08 | Housekeeping and Linen | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| 1220-3 | Hotel | 7 |  | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
| 1220-3 | Hotel | 7 | [6 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| 1220-3 | Hotel | 8 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-12201-2 | Hotel | 9 | H-09-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-12201-2 | Hotel | L10 | P-10-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-1221-2 | Hotel | 11 | H-08-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-1221-2 | Hotel | 12 | H-12-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-1222-2 | Hotel | 13 | H-13-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-1222-2 | Hotel | 14 | H-14-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-1222-2 | Hotel | 15 | H-15-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
[5 empty] | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
| A-1222-2 | Hotel | L16 | H-16-08 | Housekeeping | 15.6 | 3.3 | 1 | 51.48 | 3.6 | 2.1 | -1 | -7.56 | 43.92 | 8.784 | 13.176 | 13.176 |  | 35.136
| A-1222-2 | Hotel | L16 |  | Service Support Area | 21.7 | 2.4 | 1 | 52.08 | 0.9 | 2.1 | -3 | -5.67 | 46.41 | 9.282 | 13.923 | 11.6025 |  | 34.8075
[10 empty] | 1.2 | 2.1 | -4 | -10.08 | -10.08 | -2.016 | -3.024 | -2.52 |  | -7.56
[14 empty] | 2934.328 |  |  |  |  | 2700.818 | 0
Note on T44: Himal Kosala: No WIR until that only 90%
Note on T333: Himal Kosala: Most of the claim is for final paint, but no WIR ref mention, so only 90% certified

## Corridor
PROJECT: Plot BB.B03.018, Business Bay, Dubai
CONTRACTOR : Roberts Constructions
SUB CONTRACTOR : AL RAWDA
VO-04 | CORRIDOR CEILING WORKS
[6 empty] | Framing | Boarding | Finishing | Total | Cum.Amount
S.Nos | BLG | Level | Drawing No | No | QTY | 65% | 30% | 5% | % | Net Total
A |  | Matte Ceiling Finish HTL-PT-09
Hotel
Hotel
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 58 | 100% | 100% | 100% | 100% | 58
|  |  |  | 1 | 28.06 |  |  |  | 0% | 0
| Hotel | 25 | AR-CI-SD-L25-51684 | 1 | 35 | 100% | 100% | 100% | 100% | 35
37.06
| Hotel | 26 | AR-CI-SD-L25-51691 | 1 | 82 | 100% | 100% | 100% | 100% | 82
28.06
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 152 | 100% | 100% | 100% | 100% | 152
28.06
a |  |  |  |  | 448.24 |  |  |  |  | 327 | a
b | Bulk head, 120mm high
1
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 103.54 | 80% | 80% | 80% | 80% | 82.832
| Hotel | 26 | AR-CI-SD-L25-51691 | 1 | 114 | 100% | 100% | 100% | 100% | 114
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 175.28 | 80% | 80% | 80% | 80% | 140.224
[5 empty] | 392.82 |  |  |  | 13.68% | 337.056 | 2
E | Light cove 100 X 40
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 107.28 | 80% | 80% | 80% | 80% | 85.824
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 46.1 | 80% | 80% | 80% | 80% | 36.88
| Hotel | 26 | AR-CI-SD-L25-51691 | 1 | 174.45 | 80% | 80% | 80% | 80% | 139.56
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 173.25 | 80% | 80% | 80% | 80% | 138.6
[5 empty] | 501.08 |  |  |  | 16.84% | 400.864 | 5
CORRIDOR CEILING WORKS
7 | Drywall Lining Work
| Hotel | 7 | AR-CI-SD-L7-61011 | 1 | 77 | 100% | 100% | 100% | 100% | 77
|  |  |  | 1 | 22.62 | 100% | 100% | 100% | 100% | 22.62
| Hotel | 19 | AR-PL-SD-ML-51014 | 1 | 43 | 100% | 100% | 100% | 100% | 43
|  |  |  | 1 | 22.62 |  |  |  | 0% | 0
| Hotel | 21 | AR-PL-SD-ML-51014 | 1 | 52.13 | 100% | 100% | 100% | 100% | 52.13
|  |  |  | 1 | 22.62 |  |  |  | 0% | 0
| Hotel | 22 | AR-PL-SD-ML-51015 | 1 | 56.13 | 100% | 100% | 100% | 100% | 56.13
|  |  |  | 1 | 22.62 | 100% | 100% | 100% | 100% | 22.62
| Hotel | 23 | AR-PL-SD-ML-51015 | 1 | 56.13 | 100% | 100% | 100% | 100% | 56.13
|  |  |  | 1 | 22.62 | 100% |  |  | 65% | 14.703
| Hotel | 24 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
|  |  |  | 1 | 22.62
| Hotel | 25 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
|  |  |  | 1 | 22.62 |  |  |  | 0% | 0
| Hotel | 26 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
| Hotel | 27 | AR-PL-SD-ML-51015 | 1 | 78.75 | 100% | 100% | 100% | 100% | 78.75
[5 empty] | 757.73 |  |  |  |  | 659.333 | 5.g
[6 empty] | Primer+Stucco | 1st coat | Final | Total | Cum.Amount
C | Ceiling Painting HTL-PT-09 |  |  |  |  | 50% | 30% | 20% | % | Net Total
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 89.1 | 100% | 100% |  | 80% | 71.28
|  | 19 | AR-CI-SD-L19-61023 |  | 28.06
|  | 24 | Lift lobby | 1 | 28.06 | 100% | 100% |  | 80% | 22.448
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 83.6 | 100% | 100% |  | 80% | 66.88
37.06
| Hotel | 26 | AR-CI-SD-L26-61032 | 1 | 179 | 100% | 100% |  | 80% | 143.2
28.06
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 160 | 100% | 100% |  | 80% | 128
28.06
[5 empty] | 661 |  |  |  | 21.05% | 431.808 | C
D | Bulk head, 120mm high Painting
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 103.54 | 80% | 80% |  | 64% | 66.2656
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 137 | 100% | 100% |  | 80% | 109.6
| Hotel | 26 | AR-CI-SD-L26-61032 | 1 | 174.88 | 80% | 80% |  | 64% | 111.9232
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 175.28 | 80% | 80% |  | 64% | 112.1792
[5 empty] | 590.7 |  |  |  | 14.32% | 399.968 | d
f | Light cove, Painting
Hotel
Hotel
| Hotel | 19 | AR-CI-SD-L19-61023 | 1 | 107.28 | 80% | 80% |  | 64% | 68.6592
| Hotel | 25 | AR-CI-SD-L25-61031 | 1 | 169 | 100% | 100% |  | 80% | 135.2
| Hotel | 26 | AR-CI-SD-L26-61032 | 1 | 174.45 | 80% | 80% |  | 64% | 111.648
| Hotel | 27 | AR-CI-SD-L27-61033 | 1 | 174.45 | 80% | 80% |  | 64% | 111.648
[5 empty] | 625.18 |  |  |  | 14.32% | 427.1552 | f

## 1.Ceiling Tiles
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA
PAINT WORK QUANTITY CALCULATION
SUBJECT | Grid work done -( only Gypsum Tiles Ceiling -600X600mm)
VO-001
[7 empty] | Quantity |  |  | CLAIMED
SN |  | Dwg .NO | Level | Room Name | No. | Total | Units | Grid | Tiles | Work done
1 | Hotel |  | CLG -01 -Gypsum Tiles Ceiling -600X600mm
| Hotel |  | L1 ,2,3,4,5,7,11,12,13,14,15,16,19,20,21,22, L23
| Hotel | A-1304-3 | L1 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L2 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L3 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L4 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L5 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L7 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L11 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L12 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L13 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L14 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L15 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L16 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L19 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L20 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L21 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L22 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
| Hotel |  | L23 | FF Lobby | 1 | 5.02 | m2 |  |  | 5.02
L3,4,7,11 to 16, & L19 to L23
| Hotel | A-1304-3 | L3 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L4 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L7 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L11 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L12 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L13 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L14 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L15 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L16 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L19 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L20 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L21 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L22 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel |  | L23 | House keeping Lobby | 1 | 9.36 | m2 |  |  | 9.36
| Hotel | A-1304-3 | L5 | Lift Lobby | 1 | 25.21 | m2 |  |  | 25.21
2 | Residential | A-1320-1 | CLG -01 -Gypsum Tiles Ceiling -600X600mm
| Residential | A-1320-1 | L4 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L5 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L6 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L22 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L24 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L25 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L26 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L27 | FF Lobby | 1 | 14.01 | m2 |  |  | 14.01
| Residential | A-1320-1 | L28 | FF Lobby | 1 |  | m2 |  |  | 0
| Residential | A-1320-1 | L29 | FF Lobby | 1 |  | m2 |  |  | 0
| Residential | A-1320-1 | L4 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L5 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L6 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L22 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L24 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L25 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L26 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L27 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L28 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L29 | HK Lobby | 1 | 9.64 | m2 |  |  | 9.64
| Residential | A-1320-1 | L5 | Lift Lobby | 1 | 25.65 | m2 |  |  | 25.65
[6 empty] | 475.72 |  |  |  | 428.148
Full System Gypsum Tiles Ceiling -600X600mm
Hotel |  | CLG -01 -Gypsum Tiles Ceiling -600X600mm
Hotel |  | G,F, L17,L18 & L24 to L28
Hotel | A-1304-3 | GF | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L17 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L18 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L24 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L25 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L26 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L27 | FF Lobby | 1 |  |  | 5.02 |  |  | 5.02
Hotel |  | L28 | FF Lobby | 1 |  |  | 5.02
Hotel |  | G,F, L1,2,3,4,5,7,8,10,11 & L13 to L28 |  |  | 26
Hotel | A-1304-3 | GF |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | L1 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | L2 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | L3 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 4 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 5 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 7 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 8 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 10 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 11 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 13 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 14 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 15 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 | 16 |  |  | 1 |  | 1.88 |  |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 |  |  |  | 1 |  | 1.88
Hotel | A-1304-3 | L28 |  |  | 1 |  | 1.88
Hotel |  | G,F, L1,2,4,5, L17,18,24 ,25,26,27, L28
Hotel | A-1304-3 | GF |  | Room service arae | 1 |  | 18.34 |  |  | 18.34
|  | L1 |  | Room service arae | 1 |  | 18.34
|  | L2 |  | Room service arae | 1 |  | 18.34
|  | L3 |  | Room service arae | 1 |  | 18.34
|  | L4 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L5 |  | Room service arae | 1 |  | 18.34 |  |  | 0
|  | L7 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L8 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L9 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L10 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L11 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L12 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L13 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L14 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L15 |  | Room service arae | 1 |  | 18.34 | 11.004 | 7.336 | 18.34
|  | L16 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L17 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L18 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L19 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L20 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L21 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L22 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L23 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L24 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L25 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L26 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
|  | L27 |  | Room service arae | 1 |  | 18.34 | 11.004 |  | 11.004
| Hotel |  | G,F, L1,2,5, L17 ,L18,L24 to L28 |  | 11
| Hotel | A-1304-3 | G.F | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L1 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L2 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L5 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L17 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L18 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L24 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L25 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L26 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L27 | House keeping Lobby | 1 |  | 9.36 |  |  | 9.36
|  |  | L28 | House keeping Lobby | 1 |  | 9.36
| Residential | A-1320-1 | CLG -01 -Gypsum Tiles Ceiling -600X600mm
|  |  | B1 | FF Lobby | 1 |  | 14.01
|  |  | L23 | FF Lobby | 1 |  | 14.01 |  |  | 14.01
|  |  | L30 | FF Lobby | 1 |  | 14.01 |  |  | 14.01
|  |  | L23 | HK Lobby | 1 |  | 9.64 |  |  | 9.64
|  |  | L30 | HK Lobby | 1 |  | 9.64 |  |  | 9.64
|  |  | L4 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L5 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L23 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L24 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L25 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L26 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L27 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L29 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
|  |  | L30 | Waste chute room | 1 |  | 2.5 |  |  | 2.5
[7 empty] | 730 |  |  | 551.312
C/1 |  | Full System -600X600mm Metal Tiles
| Hotel | A-1301-5 | B1 | SPRTING | 1 | 33.78 | m2 |  |  | 33.78
| Hotel | A-1302-5/60028 | B1 | CORRIDOR | 1 | 272.75 | m2 |  |  | 272.75
| Hotel | A-1302-5 | B1 | SECURITY OFFICE | 1 | 9.57 | m2 |  |  | 9.57
| Hotel | A-1302-5 | B1 | TIMEKEEPER'S OFFICE | 1 | 10.67 | m2 |  |  | 10.67
| Hotel | A-1302-5 | B1 | HK HOT KITCHEN | 1 | 108.85 | m2
| Hotel | A-1302-5 | B1 | POTWASH | 1 | 12.67 | m2
[6 empty] | Total m2 |  |  |  | 292.99
C/2 |  | Grid work done - ( 600X600mm Metal Tiles only)
| Hotel | A-1301-5 | B1 | BIN STORE | 1 | 23.65 | m2 |  |  | 23.65
| Hotel | A-1302-5/60028 | B1 | BEVERAG STORAGE-2 | 1 | 22.1 | m2 |  |  | 22.1
| Hotel | A-1302-5/60028 | B1 | BEVERAG STORAGE-1 | 1 | 27.88 | m2 |  |  | 27.88
| Hotel | A-1302-5/60028 | B1 | VEGETABLE STORE | 1 | 5.94 | m2 |  |  | 5.94
| Hotel | A-1302-5/60028 | B1 | CENTRAL FOOD | 1 | 46.55 | m2 |  |  | 46.55
| Hotel | A-1302-5/60028 | B1 | DRY STORE | 1 | 20.43 | m2 |  |  | 20.43
| Hotel | A-1302-5/60028 | B1 | CORRIDOR | 1 | 40.06 | m2 |  |  | 40.06
| Hotel | A-1302-5/60028 | B1 | LINEN STORE | 1 | 13.56 | m2 |  |  | 13.56
| Hotel | A-1302-5/60028 | B1 | LINEN STORE | 1 | 13.15 | m2 |  |  | 13.15
| Hotel | A-1302-5/60028 | B1 | EXECUTIVE HOUSEKEEPER | 1 | 5.32 | m2 |  |  | 5.32
| Hotel | A-1302-5/60028 | B1 | HOUSEKEEPING & GUEST | 1 | 92.09 | m2 |  |  | 92.09
| Hotel | A-1302-5/60028 | B1 | WASTE HOLDING | 1 | 3.5 | m2 |  |  | 3.5
| Hotel | A-1302-5/60028 | B1 | DRY STORE | 1 | 4.21 | m2 |  |  | 4.21
| Hotel | A-1302-5/60028 | B1 | POTWASH | 1 | 9.91 | m2 |  |  | 9.91
| Hotel | A-1302-5/60028 | B1 | PATISSERIE | 1 | 25.01 | m2 |  |  | 25.01
| Hotel | A-1302-5/60028 | B1 | BAKERY PASTRY | 1 | 63.72 | m2 |  |  | 63.72
| Hotel | A-1302-5/60028 | B1 | COLD AREA | 1 | 3.29 | m2 |  |  | 3.29
| Hotel | A-1302-5/60028 | B1 | HK HOT KITCHEN | 1 | 21.15 | m2
[6 empty] | Total m2 |  |  |  | 420.37
C/3 |  | Full System Gypsum Tiles Ceiling -600X600mm
| Hotel | A-1302-5 | B1 | STAFF DINING ROOM | 1 | 129.46 | m2 |  |  | 77.676
Total m2
C/4 |  | Grid work done -( Gypsum Tiles Ceiling -600X600mm)
| Hotel | A-1302-5 | B1 | WAREWASH & CUTLERY | 1 | 45.67 | m2
Total m2
Note on K75: Himal Kosala: No WIR ref mention, only 90%

## 1.P
v |  | PROJECT | Plot BB.B03.018, Business Bay, Dubai
v |  | CONTRACTOR | Roberts Constructions
v |  | SUB CONTRACTOR | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v |  | SUBJECT | PAINTING WORKS
VO-01 |  |  | Gypsum Partition Works at Hotel Level 3
[6 empty] | Quantity |  |  |  | Deduction
SN | Types | Dwg .NO | Room No | No. | Length | Height / Width | Total | Length | Height / Width | No. | Total | Units | Sub. Total Qty |  | Cum Qty
E/1 |  | 100mm Partition Wall To Internal Area Wall Partition As Specified Type PTID-02
|  | AR-PL-SD-L3-50108 | Finance Office | 1 | 3.25 | 3.8 | 12.35 |  |  |  |  | m2 | 12.35 | 100% | 12.35
|  |  | Quality Manager | 1 | 3.25 | 3.8 | 12.35 |  |  |  |  | m2 | 12.35 | 100% | 12.35
|  |  | Hotel Manager | 1 | 1.93 | 3.8 | 7.334 |  |  |  |  | m2 | 7.334 | 100% | 7.334
|  |  | Ex Ass | 1 | 1.368 | 3.8 | 5.1984 |  |  |  |  | m2 | 5.1984 | 100% | 5.1984
|  |  | Gen. Manager | 1 | 3.25 | 3.8 | 12.35 |  |  |  |  | m2 | 12.35 | 100% | 12.35
|  |  |  | 1 | 4.2 | 3.8 | 15.96 |  |  |  |  | m2 | 15.96 | 100% | 15.96
|  |  | Regional Dir | 1 | 3.16 | 3.8 | 12.008 |  |  |  |  | m2 | 12.008 | 100% | 12.008
0
0
|  | AR-PL-SD-L3-50109 | Meeting room | 1 | 4.56 | 2.95 | 13.452 |  |  |  |  | m2 | 13.452 | 100% | 13.452
|  |  |  | 1 | 1.4 | 3.8 | 5.32 |  |  |  |  | m2 | 5.32 | 100% | 5.32
|  |  | Male & Female | 2 | 4 | 3.8 | 30.4 |  |  |  |  | m2 | 30.4 | 100% | 30.4
|  |  | Male & Female | 2 | 2 | 3.8 | 15.2 |  |  |  |  | m2 | 15.2 | 100% | 15.2
|  |  | Pantry | 1 | 1.76 | 3.8 | 6.688 |  |  |  |  | m2 | 6.688 | 100% | 6.688
|  |  | Corridor | 1 | 4.07 | 3.8 | 15.466 |  |  |  |  | m2 | 15.466 | 100% | 15.466
0
164.0764
|  | 100mm Partition Wall To Internal Area Wall Partition As Specified Type PTID-02 | [12 empty] | 164.0764
E/2 |  | 50mm Partition Wall To Internal Area Wall Partition
|  | AR-PL-SD-L3-50108 | Hotel Manager | 2 | 1.22 | 3.8 | 9.272 |  |  |  |  | m2 | 9.272 | 100% | 9.272
|  |  |  | 1 | 4.44 | 3.8 | 16.872 |  |  |  |  | m2 | 16.872 | 100% | 16.872
|  |  |  | 1 | 3.2 | 3.8 | 12.16 |  |  |  |  | m2 | 12.16 | 100% | 12.16
[13 empty] | 38.304 |  | 38.304
E/3 |  | Wall Cladding
|  | AR-PL-SD-L3-50108 | Corridor | 1 | 16.34 | 2.95 | 48.203 |  |  |  |  | m2 | 48.203 | 100% | 48.203
|  |  |  | 1 | 2.83 | 2.95 | 8.3485 |  |  |  |  | m2 | 8.3485 | 100% | 8.3485
|  |  |  | 1 | 5.42 | 2.95 | 15.989 |  |  |  |  | m2 | 15.989 | 100% | 15.989
0
|  | AR-PL-SD-L3-50108 | Corridor | 1 | 17.25 | 2.95 | 50.8875 |  |  |  |  | m2 | 50.8875 | 100% | 50.8875
[13 empty] | 123.428 |  | 123.428
0
0
E/4 |  | Wall & ceiling internal painting works | [10 empty] | 0
Wall Painting
|  | AR-PL-SD-L3-50109 | Store | 1 | 13.93 | 2.4 | 33.432 | 1 | 2.1 | -1 | -2.1 | m2 | 31.332 | 100% | 31.332
|  | AR-PL-SD-L3-50109 | Meeting room | 1 | 24.75 | 2.4 | 59.4 | 1 | 2.1 | -2 | -4.2 | m2 | 55.2 | 100% | 55.2
|  | AR-PL-SD-L3-50109 | W.C | 1 | 7.35 | 2.4 | 17.64 | 1 | 2.1 | -1 | -2.1 | m2 | 15.54 | 100% | 15.54
|  | AR-PL-SD-L3-50109 | F.W.C | 1 | 8.14 | 2.4 | 19.536 | 1 | 2.1 | -1 | -2.1 | m2 | 17.436 | 100% | 17.436
|  | AR-PL-SD-L3-50109 | Pantry | 1 | 7.87 | 2.4 | 18.888 | 1 | 2.1 | -1 | -2.1 | m2 | 16.788 | 100% | 16.788
|  | AR-PL-SD-L3-50109 | F& M Manager | 1 | 8.19 | 2.4 | 19.656 |  |  |  |  | m2 | 19.656 | 100% | 19.656
|  | AR-PL-SD-L3-50109 | F& M Office | 1 | 11.1 | 2.4 | 26.64 |  |  |  |  | m2 | 26.64 | 100% | 26.64
|  | AR-PL-SD-L3-50109 | Corridor | 1 | 27.07 | 2.4 | 64.968 | 1 | 2.1 | -4 | -8.4 | m2 | 56.568 | 100% | 56.568
|  | AR-PL-SD-L3-50109 | Corridor | 1 |  |  |  | 1.2 | 2.1 | -2 | -5.04 | m2 | -5.04 | 100% | -5.04
|  | AR-PL-SD-L3-50108 | Finance Manager& O | 1 | 20.52 | 2.4 | 49.248 |  |  |  |  | m2 | 49.248 | 100% | 49.248
|  | AR-PL-SD-L3-50108 | Quality Manager | 1 | 9.08 | 2.4 | 21.792 |  |  |  |  | m2 | 21.792 | 100% | 21.792
|  | AR-PL-SD-L3-50108 | Hotel Manager | 1 | 8.86 | 2.4 | 21.264 |  |  |  |  | m2 | 21.264 | 100% | 21.264
|  | AR-PL-SD-L3-50108 | Exee Assistant Area | 1 | 12.84 | 2.4 | 30.816 |  |  |  |  | m2 | 30.816 | 100% | 30.816
|  | AR-PL-SD-L3-50108 | General Manager | 1 | 14.21 | 2.4 | 34.104 |  |  |  |  | m2 | 34.104 | 100% | 34.104
|  | AR-PL-SD-L3-50108 | Corridor | 1 | 23.51 | 2.4 | 56.424 | 1 | 2.24 | -3 | -6.72 | m2 | 49.704 | 100% | 49.704
|  | AR-PL-SD-L3-50108 | Sale & Marking | 1 | 14.19 | 2.4 | 34.056 | 1 | 1.1 | -1 | -1.1 | m2 | 32.956 | 100% | 32.956
|  | AR-PL-SD-L3-50108 | Regional Director | 1 | 8.84 | 2.4 | 21.216 |  |  |  |  | m2 | 21.216 | 100% | 21.216
|  | AR-PL-SD-L3-50108 | Event Director | 1 | 12.97 | 2.4 | 31.128 |  |  |  |  | m2 | 31.128 | 100% | 31.128
Ceiling Painting
|  | AR-PL-SD-L3-50109 | Male W.C | 1 | 1.7 | 2 | 3.4 |  |  |  |  | m2 | 3.4 | 100% | 3.4
|  | AR-PL-SD-L3-50109 | Female W.C | 1 | 2.1 | 2 | 4.2 |  |  |  |  | m2 | 4.2 | 100% | 4.2
|  | AR-PL-SD-L3-50109 | Pantry | 1 | 2.2 | 1.7 | 3.74 |  |  |  |  | m2 | 3.74 | 100% | 3.74
[13 empty] | 537.688 |  | 537.688

## 7.Shaft
v | PROJECT |  |  | Plot BB.B03.018, Business Bay, Dubai
v | CONTRACTOR |  |  | KCE
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v | SUBJECT
BOQ -7- Supply and Installation of Shaft Wall at Level -1 to Roof Level
Quantity
SN | DWG .NO | BLG | Level | Grid | No. | Length | Height / Width | Total | Workdone |  | WIR
1 | RP-PL-SD-L11-50186-2 | Hotel | 1 | 19-20/ V-W | 1 | 5.9 | 3.03 | 17.877 | 16.0893 | 90%
[5 empty] | 1 | 0.956 | 3.03 | 2.8967 | 2.607 | 90%
8 | RP-PL-SD-L11-50186-2 | Hotel | 2 to 3 | 19-20/ V-W | 1 | 5.9 | 8.15 | 48.085 | 43.2765 | 90%
[5 empty] | 1 | 0.956 | 8.15 | 7.7914 | 7.0123 | 90%
9 | RP-PL-SD-L11-50186-2 | Hotel | 4 | 19-20/ V-W | 1 | 5.9 | 3.6 | 21.24 | 19.116 | 90%
[5 empty] | 1 | 0.956 | 3.6 | 3.4416 | 3.0974 | 90%
10 | RP-PL-SD-L11-50186-2 | Hotel | 5 to 6 | 19-20/ V-W | 1 | 5.9 | 8.6 | 50.74
[5 empty] | 1 | 0.956 | 8.6 | 8.2216
12 | RP-PL-SD-L11-50186-2 | Hotel | 7 | 19-20/ V-W | 1 | 5.9 | 3.15 | 18.585 | 18.585 | 100% | AR-AX-WR-L7-01544_00_B
[5 empty] | 1 | 0.956 | 3.15 | 3.0114 | 3.0114 | 100%
12 | RP-PL-SD-L11-50186-2 | Hotel | 8 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01517_00._B
12 | RP-PL-SD-L11-50186-2 | Hotel | 9 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01517_00._B
12 | RP-PL-SD-L11-50186-2 | Hotel | 10 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01619_00_B
12 | RP-PL-SD-L11-50186-2 | Hotel | 11 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01546_00_B
12 | RP-PL-SD-L11-50186-2 | Hotel | 12 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01517_00._B
12 | RP-PL-SD-L11-50186-2 | Hotel | 13 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01654_00-B
12 | RP-PL-SD-L11-50186-2 | Hotel | 14 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01546_00_B
12 | RP-PL-SD-L11-50186-2 | Hotel | 15 | 19-20/ V-W |  |  |  | 21.6 | 21.6 | 100% | ML-01546_00_B
13 | RP-PL-SD-L11-50186-2 | Hotel | 16 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945 | 20.945 | 100% | ML-01619_00_B
[5 empty] | 1 | 0.956 | 3.55 | 3.3938 | 3.3938 | 100% | ML-01619_00_B
14
| RP-PL-SD-L11-50186-2 | Hotel | 17 | 19-20/ V-W | 1 | 5.9 | 3.717 | 21.9303 | 19.7373 | 90%
[5 empty] | 1 | 0.956 | 3.717 | 3.5535 | 3.1981 | 90%
15 | RP-PL-SD-L11-50186-2 | Hotel | 18 | 19-20/ V-W | 1 | 5.9 | 5.425 | 32.0075
[5 empty] | 1 | 0.956 | 5.425 | 5.1863
16 | RP-PL-SD-L11-50186-2 | Hotel | 19 to 21 | 19-20/ V-W | 3 | 5.9 | 3.15 | 55.755 | 55.755 | 100% | ML-01620_00_B
[5 empty] | 3 | 0.956 | 3.15 | 9.0342 | 9.0342 | 100% | ML-01620_00_B
17 | RP-PL-SD-L11-50186-2 | Hotel | 22 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945 | 12.567 | 60%
[5 empty] | 1 | 0.956 | 3.55 | 3.3938 | 2.0363 | 60%
17 | RP-PL-SD-L11-50186-2 | Hotel | 23 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945 | 20.945 | 100% | ML-01620_00_B
[5 empty] | 1 | 0.956 | 3.55 | 3.3938 | 3.3938 | 100% | ML-01620_00_B
18 | RP-PL-SD-L11-50186-2 | Hotel | 24 to 26 | 19-20/ V-W | 3 | 5.9 | 3.15 | 55.755 | 55.755 | 100% | ML-01619_00_B
[5 empty] | 3 | 0.956 | 3.15 | 9.0342 | 9.0342 | 100% | ML-01619_00_B
19 | RP-PL-SD-L11-50186-2 | Hotel | 27 | 19-20/ V-W | 1 | 5.9 | 3.55 | 20.945 | 20.945 | 100% | ML-01654_00-B
[5 empty] | 1 | 0.956 | 3.55 | 3.3938 | 3.3938 | 100% | ML-01654_00-B
|  |  | 28 | 19-20/ V-W | 1 | 5.9 | 7.25 | 42.775
[5 empty] | 1 | 0.956 | 7.25 | 6.931
|  |  | 29 | 19-20/ V-W | 1 | 5.9 | 5.32 | 31.388 |  |  | Check this
[5 empty] | 1 | 0.956 | 5.32 | 5.0859 |  |  | Check this
[8 empty] | 730.4808 | 525.7284

## Rockwool External
v | PROJECT |  |  | Plot BB.B03.018, Business Bay, Dubai
v | CONTRACTOR |  |  | Roberts Constructions
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v | SUBJECT |  |  | Rockwool For External Ceiling
BOQ | :08.Supply and Installation of Rockwool External Ceiling
[7 empty] | Quantity |  |  | Work Done
SN | DWG .NO | BLG | Level | Grid | No. | Length | Height / Width | Total Qty | % | Total Qty
1 | L1-60001 | Hotel | 1 |  | 1 |  |  | 180 | 100% | 180
2 | L1-60001 | Hotel | 1 |  | 1
3 | L3-60005 | Hotel | 3 |  | 1
3 | L5-60005 | Hotel | 5 |  | 1
4 | L7-60010-02 | Hotel | 7 |  | 1 |  |  |  |  | 0
5 | L7-60010-02 | Hotel | 7 |  | 1 |  |  |  |  | 0
6 | L8-60011-02 | Hotel | 8 |  | 1 |  |  |  |  | 0
7 | L9-60012-02 | Hotel | 9 |  | 1 |  |  |  |  | 0
8 | L10-60013 | Hotel | 10 |  | 1 |  |  |  |  | 0
9 | L10-60014 | Hotel | 11 |  | 1 |  |  |  |  | 0
10 | L10-60014 | Hotel | 11 |  | 1 |  |  |  |  | 0
11 | L12-60018 | Hotel | 12 |  | 1 |  |  |  |  | 0
12 | L13-600119 | Hotel | 13 |  | 1 |  |  |  |  | 0
13 | L14-600120 | Hotel | 14 |  | 1 |  |  |  |  | 0
14 | L15-600119 | Hotel | 15 |  | 1 |  |  |  |  | 0
15 | L16-600120 | Hotel | 16 |  | 1 |  |  |  |  | 0
16 | L17-600121 | Hotel | 17 |  | 1
17 | L17-600121 | Hotel | 17 |  | 1
18 | L18-600122 | Hotel | 18 |  | 1
19 | L19-600123 | Hotel | 19 |  | 1 |  |  |  |  | 0
20 | L20-600124 | Hotel | 20 |  | 1 |  |  |  |  | 0
21 | L21-600125 | Hotel | 21 |  | 1 |  |  |  |  | 0
22 | L22-600126 | Hotel | 22 |  | 1 |  |  |  |  | 0
23 | L23-600127 | Hotel | 23 |  | 1 |  |  |  |  | 0
24 | L23-600127 | Hotel | 23 |  | 1 |  |  |  |  | 0
25 | L24-600130 | Hotel | 24 |  | 1 |  |  |  |  | 0
26 | L25-600131 | Hotel | 25 |  | 1 | 48 | 0.6 | 116.1 | 70% | 81.27
27 | L26-600132 | Hotel | 26 |  | 1 | 62 | 0.6 | 116.1 | 70% | 81.27
28 | L27-600133 | Hotel | 27 |  | 1 | 193.5 | 0.6 | 116.1 | 70% | 81.27
29 | L28-600134 | Hotel | 28 |  | 1 | 112.2 | 0.6 | 67.32 | 70% | 47.124
1 | L1-61001-02 | Residential | 1 |  | 1 |  |  | 456 | 100% | 456
2 | L3-61005 | Residential | 3 |  | 1 |  |  | 470.42 | 100% | 470.42
3 | L3-61005 | Residential | 3 |  | 1 | 52.77 | 0.6 | 31.662 | 100% | 31.662
3 | L3-61009 | Residential | 5 |  | 1 | 863 |  |  |  | 0
4 | L6-61017-02 | Residential | 6 |  | 1 | 157.6 |  |  |  | 0
5 | L7-61010-02 | Residential | 7 |  | 1 | 131 |  |  |  | 0
6 | L8-61011-02 | Residential | 8 |  | 1 | 161.39 |  |  |  | 0
7 | L9-61012-02 | Residential | 9 |  | 1 | 149.4 |  |  |  | 0
8 | L10-61013-01 | Residential | 10 |  | 1 | 96.5 |  |  |  | 0
9 | L11-61014-01 | Residential | 11 |  | 1 | 75 |  |  |  | 0
10 | L12-61018-01 | Residential | 12 |  | 1 | 102.7 |  |  |  | 0
11 | L13-61019 | Residential | 13 |  | 1 | 78.3 |  |  |  | 0
12 | L14-61020 | Residential | 14 |  | 1 | 104.6 |  |  |  | 0
13 | L15-61015 | Residential | 15 |  | 1 | 77.2 |  |  |  | 0
14 | L16-61016 | Residential | 16 |  | 1 | 103.1 |  |  |  | 0
15 | L17-61021 | Residential | 17 |  | 1 | 119.5 |  |  |  | 0
16 | L17-61021 | Residential | 17 |  | 1 |  |  |  |  | 0
17 | L18-61022 | Residential | 18 |  | 1 | 166.1 |  |  |  | 0
18 | L19-61023 | Residential | 19 |  | 1 | 146.5 |  |  |  | 0
19 | L20-61024 | Residential | 20 |  | 1 | 166.2 |  |  |  | 0
20 | L21-61025 | Residential | 21 |  | 1 | 145.6 |  |  |  | 0
21 | L22-61026 | Residential | 22 |  | 1 | 203.2 |  |  |  | 0
22 | L23-61027 | Residential | 23 |  | 1 | 143.5 | 0.6 | 86.1 | 100% | 86.1
23 | L24-61030 | Residential | 24 |  | 1 | 110.6 | 0.6 | 66.36 | 100% | 66.36
24 | L24-61030 | Residential | 24 |  | 1 |  |  | 176.2 | 100% | 176.2
25 | L25-61031 | Residential | 25 |  | 1 | 68.9 | 0.6 | 41.34 |  | 0
26 | L26-61032 | Residential | 26 |  | 1 | 51.942 | 0.6 | 31.1652 |  | 0
27 | L26-61032 | Residential | 26 |  | 1 |  |  | 176.74 | 50% | 88.37
28 | L27-61033 | Residential | 27 |  | 1 | 45.5 | 0.6 | 27.3 |  | 0
29 | L28-61034 | Residential | 28 |  | 1 | 77.5 | 0.6 | 46.5 |  | 0
30 | L28-61034 | Residential | 28 |  | 1 |  |  | 176 |  | 0
[8 empty] | 2650 |  | 1846.046
69.66%

## VO 01
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA
VARIATION ORDER 01
| S.N | Description | QTY | Unit | Rate | Amount UAE Dirhams | CLAIM - AL RAWDA
[7 empty] | Quantity | Amount
Royal crown works
(USG BORAL TILES )
Hotel -G.F to L28 ,Res G.F to L30 (BOH)
| A | Full System Gypsum Tiles Ceiling -600X600mm | 730.83 | m2 | 90 | 65774.7 | 551.312 | 49618.08
| B | Gypsum Ceiling Tiles Only -600X600mm | 475.72 | m2 | 55 | 26164.6 | 428.148 | 23548.14
Basement -1 (BOH )
(USG BORAL TILES )
| C/1 | Full System -600X600mm Metal Tiles | 448.29 | m2 | 160 | 71726.4 | 292.99 | 46878.4
| C/2 | 600X600mm Metal Tiles only | 441.52 | m2 | 125 | 55190 | 420.37 | 52546.25
| C/3 | Full System Gypsum Tiles Ceiling -600X600mm | 129.46 | m2 | 90 | 11651.4 | 77.676 | 6990.84
| C/4 | Gypsum Ceiling Tiles Only -600X600mm | 45.67 | m2 | 55 | 2511.85
Level 3-BOH
CEILING
(USG BORAL TILES )
| D/1 | PB.01 - 600X600X12mm Gypsum Ceiling | 290.182 | m2 | 90 | 26116.38
( GYPSEMNA )
| D/2 | MBP.01 - Moisture Resistant Ceiling | 11.34 | m2 | 120 | 1360.8
| D/3 | ACCESS PANEL FOR FCU 600 X 600mm -AP-1 | 2 | Nos | 285 | 570
| D/4 | ACCESS PANEL FOR FCU 300 X 300mm -AP-3 | 1 | Nos | 250 | 250
PARTITIONS
( GYPSEMNA )
| E/1 | 100mm Partition Wall To Internal Area Wall Partitions | 164.0764 | m2 | 160 | 26252.224 | 164.0764 | 26252.224
| E/2 | 50mm Partition Wall To Internal Area Wall Partition | 38.304 | m2 | 135 | 5171.04 | 38.304 | 5171.04
| E/3 | Supply and Installation of Drywall Lining Work | 123.428 | m2 | 110 | 13577.08 | 123.428 | 13577.08
Painting works
| E/4 | Wall & ceiling internal painting works | 537.688 | m2 | 18 | 9678.384 | 537.688 | 9678.384
RESIDENTIAL - LEVEL-31
| F | External Fibre Cement Board Ceiling
| F/1 | External Fibre Cement board ceiling including,all fixings, fittings, tapping, jointing, supporting frame work, sealant between panels and accessories complete all in accordance with the drawings and specifications | 470.42 | m2 | 140 | 65858.8 | 423.378 | 59272.92
| F/2 | Supply and Installation of Rockwool External Ceiling | 470.42 | m2 | 40 | 18816.8 | 423.378 | 16935.12
| F/3 | External Painting Cement board Ceiling work | 470.42 | m2 | 28 | 13171.76 | 423.378 | 11854.584
| F/4 | Bulkhead all around the columns and shadow gaps for all the types of external ceilings as per the drawings and specifications | 7 | Nos | 1850 | 12950 | 6.3 | 11655
| F/5 | External Column Painting workS (Type PT 201) | 276.36 | m2 | 28 | 7738.08 | 248.724 | 6964.272
| F/6 | External Concrete Column Skimming | 276.36 | m2 | 15 | 4145.4 | 248.724 | 3730.86
| TOTAL - UAE DIRHAMS - |  |  |  |  | 438675.698 |  | 344673.194

## VO 02
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [12 empty] | 2023-02-01
VARIATION ORDER 02 | [12 empty] | IPA-09
| Item Ref | Description | BoQ Ref | Rate Ref | Quantity | Unit | Rate (AED) | Addition (AED) | CLAIM - AL RAWDA |  | CERTFICATION - OCI |  | Remarks
[5 empty] | Quantity | Unit |  |  | PROGRESS Qunatity | PROGRESS AMOUNT | PROGRESS Qunatity | PROGRESS AMOUNT
| VO-002/1 | Supply and Installation of Demise Wall - One Side Board Only |  |  | 363.8 | m2 | 120 | 43656 | 327.42 | 39290.4 | 265.51 | 31861.2 |  | 90% | Until WIR approve
| VO-002/02 | Supply and Installation of Shaft Wall |  |  | 253.64 | m2 | 290 | 73555.6 | 228.276 | 66200.04 | 195.98 | 56834.2 |  | 90% | Until WIR approve
| VO-002/03 | Supply and Installation of Shaft Wall - One Side Board Only |  |  | 290.02 | m2 | 190 | 55103.8 | 261.018 | 49593.42 | 217 | 41230 |  | 90% | Until WIR approve
| VO-002/04 | Supply and Installation of Partition Wall |  |  | 12.58 | m2 | 170 | 2138.6 | 11.322 | 1924.74 |  |  |  | 90% | Until WIR approve
0
| VO-002/05 | Supply and Installation of 600X600X12mm Gypsum tiles |  |  | 255.4435 | m2 | 90 | 22989.915 | 122.2066 | 10998.594
0
| VO-002/06 | 600X600X0.7MM Non-Perforated Metal Ceiling -FCF-01 |  |  | 537.705 | m2 | 160 | 86032.8 | 403.561 | 64569.76
| VO-002/07 | Supply and Installation of Regur Gypsumboard -FCF 05 |  |  | 11.85 | m2 | 110 | 1303.5 | 7.11 | 782.1
| VO-002/08 | BH 650mm Hight |  |  | 68 | m | 70 | 4760 | 0
| VO-002/09 | Access Panel 600x600 mm |  |  | 19 | Nos | 285 | 5415 | 0
| VO-002/10 | Access Panel 450 x450 mm |  |  | 19 | Nos | 250 | 4750
| VO-002/11 | Supply and Installation of Cement board at Stone work cladding area - (Vanity ,bathtubs Unit ) |  |  | 392.8466 | m2 | 160 | 62855.456 | 353.5619 | 56569.9104 |  |  |  | 90% | Until WIR approve
| VO-002/12 | Supply and Installation of Cement board at Stone work cladding area - (Corridor ) |  |  | 67.7025 | m2 | 160 | 10832.4 | 60.9322 | 10832 | 48.7458 | 7799.328 |  | 90% | Until WIR approve
| VO-002/13 | Supply and Installation of Columns Side Gypsum board - (Corridor ) |  |  | 98 | Nos | 95 | 9310 | 88.2 | 9310 | 70.56 | 6703.2 |  | 90% | Until WIR approve
|  | Grand Total | [5 empty] | 382703.071 |  | 310070.9644 |  | 144427.928

## External
PROJECT: Plot BB.B03.018, Business Bay, Dubai
CONTRACTOR :KCE
SUB CONTRACTOR :AL Rawda
EXTERNAL CEMENT BOARD CEILING WORKS
[9 empty] | Framing | Boarding | Finishing | Total | Cum.Qty
BOQ | BLG | Level | Drawing No | Zone | Grid | No | QTY | Work Done | 65% | 30% | 5% | % | Net Total
1 |  | 1 | L1-61001 |  | 1 | 1 | 1359 | 1223 | 90% | 87% | 87% | 87% | 1182.33
L1-60001
2 |  | ESS-405; Level-2 and 3 ceiling as per the drawings A-1305 and A-1306 |  |  |  | 1
3 | Hotel | 3 | L3-60005 |  | 1 | 1 | 973 | 883 | 90.75% | 90.75% | 90.75% | 90.75% | 883
| Res | 3 |  |  | 1 |  | 266.6 | 266 | 99.77% | 99.77% | 99.77% | 99.77% | 266
4 |  | ESS-405; Level-5 ceiling as per the drawings A-1307 and A-1308 |  |  |  | 1 | 122 | 122 | 85% | 85% | 85% | 85% | 103.7
[12 empty] | 0% | 0
[12 empty] | 0% | 0
4 |  | ESS-405; Level-5 ceiling as per the drawings A-1307 and A-1308 |  |  |  |  | 0 | [5 empty] | 0
5 |  | ESS-405; Levels 7 to 28 Hotel suit balconies and viod areas
| Hotel | 18 | AR-CI-SD-L18-61022 | 2 |  | 1 | 12 | 12 | 100% | 100% | 100% | 100% | 12 | f
| Hotel | 19 | AR-CI-SD-L19-61023 | 2 |  | 1 | 9 |  |  |  |  | 0% | 0 | f
| Hotel | 20 | AR-CI-SD-L20-61024 | 2 |  | 1 | 10 |  |  |  |  | 0% | 0
| Hotel | 21 | AR-CI-SD-L21-61025 | 2 |  | 1 | 10 |  |  |  |  | 0% | 0
| Hotel | 22 | AR-CI-SD-L22-61026 | 2 |  | 1 | 36 | 26 | 72.22% | 72.22% | 72.22% | 72.22% | 26
| Hotel | 23 | AR-CI-SD-L23-61027 | 2 |  | 1 | 26 | 18 | 69.23% | 69.23% | 69.23% | 69.23% | 18
| Hotel | 24 | AR-CI-SD-L24-61030 | 2 |  | 1 | 48 |  |  |  |  | 0% | 0
| Hotel | 25 | AR-CI-SD-L25-61031 | 2 |  | 1 | 41 | 31 | 75.61% | 75.61% | 75.61% | 75.61% | 31
| Hotel | 26 | AR-CI-SD-L26-61032 | 2 |  | 1 | 72 | 40 | 55.56% | 55.56% | 55.56% | 55.56% | 40
| Hotel | 27 | AR-CI-SD-L27-61033 | 2 |  | 1 | 81 | 32 | 39.51% | 39.51% | 39.51% | 39.51% | 32
| Hotel | 28 | AR-CI-SD-L28-61034 | 2 |  | 1 | 209.58 | 209.58 | 25% | 25% | 25% | 25% | 52.395
5 |  | ESS-405; Levels 7 to 28 Hotel suit balconies and viod areas
6 |  | ESS-405; Levels 6 to 29 Apartment suit balconies and viod areas
| Res | 23 | AR-CI-SD-L23-61027 | 3 |  | 1 | 99 |  |  |  |  | 100% | 0
| Res | 24 | AR-CI-SD-L24-61030 | 3 |  | 1 | 82 |  |  |  |  | 0% | 0
| Res | 25 | AR-CI-SD-L25-61031 | 3 |  | 1 | 52 |  |  |  |  | 0% | 0
| Res | 26 | AR-CI-SD-L26-61032 | 3 |  | 1 | 48 |  |  |  |  | 0% | 0
| Res | 27 | AR-CI-SD-L27-61033 | 3 |  | 1 | 43 |  |  |  |  | 0% | 0
| Res | 28 | AR-CI-SD-L28-61034 | 3 |  | 1 | 152 |  |  |  |  | 0% | 0
| Res | 29 | AR-CI-SD-L29-61035 | 3 |  | 1 | 27.93
| Res | 30 |  | 3 |  | 1
A | External Fibre Cement Board Ceiling | [11 empty] | 2646.425
B | Coffered Ceiling
|  | L1 | L1-60001 | 2 |  | 1 | 83 | 83 | 100% | 100% | 100% | 100% | 83
|  | L3 | L3-60005 | 2 |  | 1 | 272.9 | 272.9 | 100% | 100% | 100% | 100% | 272.9
B | Coffered Ceiling | [11 empty] | 355.9

## External (Paint)
PROJECT: Plot BB.B03.018, Business Bay, Dubai
CONTRACTOR : Roberts Constructions
SUB CONTRACTOR :AL Rawda
EXTERNAL CEILING PAINTING WORKS
[9 empty] | Surface | Primer | 1st Coat | Final Coat | Total | Cum.Qty
BOQ | BLG | Level | Drawing No | Zone | Grid | No | QTY | Total | 10% | 30% | 30% | 30% | % | Net Total
1 |  | ESS-405; Level-1 ceiling as per the drawings A-1303 and A-1304 |  |  |  | 1 | 1359 | 1223.1 | 85% | 85% | 85% | 85% | 85% | 1039.635
| Hotel | 3 | L3-60005 |  | 1 | 1 | 973 | 678.1 | 69.69% | 69.69% | 69.69% | 69.69% | 69.69% | 678.1
| Res | 3 |  |  | 1 |  | 266.6 | 239.94 | 90% | 90% | 90% | 90% | 90% | 239.94
3 |  | ESS-405; Level-4 ceiling as per the drawings A-1307 |  |  |  | 1 | 102.86
345 |  | ESS-405; Level-5 ceiling as per the drawings A-1307 and A-1308
| Hotel | 5 |  | 3 |  | 1 | [7 empty] | 0
| Res | 5 |  | 3 |  | 1 | 129 | 129 | [5 empty] | 0
[14 empty] | 0 | #DIV/0!
346 |  | ESS-405; Levels 7 to 28 Hotel suit balconies and viod areas
| Hotel | 18 | AR-CI-SD-L18-61020 | 2 |  | 1 | 12 | 12 | 100% | 100% | 100% | 100% | 100% | 12
| Hotel | 19 | AR-CI-SD-L19-61020 | 2 |  | 1 | 12.5 | 12.5 | 100% | 100% | 100% | 100% | 100% | 12.5
| Hotel | 20 | AR-CI-SD-L20-61020 | 2 |  | 1 | 35 | 35 | 100% | 100% | 100% | 100% | 100% | 35
| Hotel | 21 | AR-CI-SD-L21-61020 | 2 |  | 1 | 47 | 47 | 100% | 100% | 100% | 100% | 100% | 47
| Hotel | 22 | AR-CI-SD-L22-61020 | 2 |  | 1 | 110 | 110 | 70% | 70% | 70% | 70% | 70% | 77
| Hotel | 23 | AR-CI-SD-L23-61028 | 1 |  | 1 | 180 | 180 | 70% | 70% | 70% | 70% | 70% | 126
| Hotel | 24 | AR-CI-SD-L24-61029 | 1 |  | 1 | 84 | 84 | 25% | 25% | 25% |  | 17.5% | 14.7
| Hotel | 25 |  |  |  | 1 | 102 | 102 | 85% | 85% | 85% |  | 59.5% | 60.69
| Hotel | 26 |  |  |  | 1 | 80 | 80 | 50% | 50% | 50% |  | 35% | 28
| Hotel | 27 |  |  |  | 1 | 112 | 112 | 40% | 40% | 40% |  | 28% | 31.36
1
| Hotel | 28 | AR-CI-SD-L28-61034 | 2 |  | 1 | 206 | 206 | 25% | 25% | 25% |  | 17.5% | 36.05
347 |  | ESS-405; Levels 6 to 29 Apartment suit balconies and viod areas
| Res | 6 | AR-CI-SD-L8-61017 | 3 | 02-09/C-H | 1 | 44 | 44
| Res | 7 | AR-CI-SD-L8-61010 | 3 | 3-10/ C-D | 1 | 8 | 8
[5 empty] | 7-11/ G-H | 1 | 16 | 16
[5 empty] | 3-4/ G-H | 1 | 22 | 22
| Res | 8 | AR-CI-SD-L8-61011 | 3 | 2-11/C-H | 1 | 10 | 10 | [6 empty] | K
| Res | 9 | AR-CI-SD-L8-61012-2 | 3 |  | 1 |  | 0
| Res | 10 | AR-CI-SD-L10-61013-1 | 3 |  | 1 | 12 | 12
| Res | 11 | AR-CI-SD-L11-61014-1 | 3 |  | 1 | 10 | 10
[6 empty] | 1 | 20 | 20
| Res | 12 | AR-CI-SD-L12-61018-1 | 3 |  | 1 | 10.5 | 10.5
| Res | 13 | AR-CI-SD-L13-61019 | 3 |  | 1 | 10.5 | 10.5
| Res | 13 | AR-CI-SD-L13-61019 | 3 |  | 1 | 10.5 | 10.5
| Res | 14 | AR-CI-SD-L14-61020 | 3 |  | 1 | 10.5 | 10.5
| Res | 15 | AR-CI-SD-L15-61015 | 3 |  | 1 | 10.5 | 10.5
| Res | 15 | AR-CI-SD-L15-61015 | 3 |  | 1 | 10.5 | 10.5
| Res | 16 | AR-CI-SD-L16-61016 | 3 |  | 1 | 10.5 | 10.5
| Res | 17 | AR-CI-SD-L17-61021 | 3 |  | 1 | 18 | 18
| Res | 18 | AR-CI-SD-L18-61022 | 3 |  | 1 | 20 | 20
| Res | 19 | AR-CI-SD-L19-61023 | 3 |  | 1 | 18 | 18
| Res | 20 | AR-CI-SD-L20-61024 | 3 |  | 1 | 18 | 18
| Res | 21 | AR-CI-SD-L21-61025 | 3 |  | 1 | 21 | 21
| Res | 22 | AR-CI-SD-L22-61026 | 3 |  | 1 | 12 | 12
| Res | 23 | AR-CI-SD-L23-61027 | 3 |  | 1 | 321.5 | 321.5
| Res | 24 | AR-CI-SD-L24-61030 | 3 |  | 1 | 421 | 421
| Res | 25 | AR-CI-SD-L25-61031 | 3 |  | 1 | 163.902 | 163.902
| Res | 26 | AR-CI-SD-L26-61032 | 3 |  | 1 | 291 | 291
| Res | 27 | AR-CI-SD-L27-61033 | 3 |  | 1 | 83.8 | 83.8
| Res | 28 | AR-CI-SD-L28-61034 | 3 |  | 1 | 342 | 342
| Res | 29 | AR-CI-SD-L29-61035 | 3 |  | 1 | 27.93 | 27.93
347 | [13 empty] | 0 | #DIV/0!
Coffered Ceiling
348 | Level | 1 |  | 3 |  | 1 | [7 empty] | 0
349 | Level | 2 |  | 3 |  | 1 | 411 | 411 | 100% | 100% | 100% | 100% | 100% | 411
349 | Hotel | L3 | L3-60005 | 3 |  | 1 | 272.9 | 272.9 | 100% | 100% | 100% | 100% | 100% | 272.9
Hotel | L-2 -3 | A-1306-1 | Columns | 48:00 | 13 | 4.72 | 8 | 490.88 |  |  |  | 0% | 80% | 392.704
3514.579

## Demising & Shaft Walls
DORCHESTER HOTEL & RESIDNECIES
SUBCONTRACTOR: AL RAWDA | [9 empty] | 2023-02-01
QUANTITY CALCULATION FOR THE WORK DONE | [9 empty] | IPA-09
v | SUBJECT |  |  | Demise Wall & Shaft Wall
VO :02 Supply and Installation of Demise Wall & Shaft Wall at Level -21 to 27
Quantity
SN | DWG .NO | BLG | Level | Grid | No. | Length | Height / Width | Total |  | Work done
VO/01 | Supply and Installation of Demise Wall - One Side Board Only
| RP-PL-SD-L27 | Hotel | 27 | Corridor | 1 | 95.7 | 3.4 | 325.38 | 90% | 292.842
| RP-PL-SD-L25 -50671 | Hotel | 24 | Corridor | 1 | 11.3 | 3.4 | 38.42 | 100% | 38.42
[9 empty] | 363.8 | 331.262
VO/02 | Supply and Installation of Shaft Wall
| RP-PL-SD-L27 | Hotel | 27 | Corridor | 1 | 25.5 | 3.4 | 86.7 | 90% | 78.03
| RP-PL-SD-L26 -50691 | Hotel | 26 | Corridor | 1 | 36.7 | 3.4 | 124.78 | 100% | 124.78
| RP-PL-SD-L25 -50681 | Hotel | 25 | Corridor | 1 | 12.4 | 3.4 | 42.16 | 100% | 42.16
[9 empty] | 253.64 | 244.97
VO/03 | Supply and Installation of Shaft Wall - One Side Board Only
| RP-PL-SD-L27 | Hotel | 27 | Corridor | 1 | 4.1 | 3.4 | 13.94 | 90% | 12.546
| p | Hotel | 26 | Corridor | 1 | 10.6 | 3.4 | 36.04 | 100% | 36.04
| RP-PL-SD-L25 -50681 | Hotel | 25 | Corridor | 1 | 28.9 | 3.4 | 98.26 | 100% | 98.26
| RP-PL-SD-L25 -50671 | Hotel | 24 | Corridor | 1 | 36.9 | 3.4 | 125.46 | 100% | 125.46
| RP-PL-SD-L25 -50641 | Hotel | 21 | Corridor | 1 | 4.8 | 3.4 | 16.32 |  | 0
[9 empty] | 290.02 | 272.306
VO/04 | Supply and Installation of Partition Wall
| RP-PL-SD-L25 -50651 | Hotel | 22 | Corridor | 1 | 3.7 | 3.4 | 12.58
12.58

## Wall Liner - KCE
Hotel Corridor Works - Wall Liner
[12 empty] | Work Done under Roberts |  |  |  | Work Done under KCE |  |  |  | Cumulative Work Done (Both Roberts & KCE)
SN | Level | Dwg .NO | Types | Room No | No. | Length | Height / Width | Total | Units | Total Qty |  | Progress |  |  | Progress Qty | Progress |  |  | Progress Qty | Progress |  |  | Progress Qty
[12 empty] | Frame | Board | Finish |  | Frame | Board | Finish |  | Frame | Board | Finish
[12 empty] | 65% | 30% | 5% |  | 65% | 30% | 5% |  | 65% | 30% | 5%
| 7 | P18-IDR-H-L7-20-COR-002.1 |  | Corridor | 1 | 75.1 | 2.51 | 188.501 | m2
|  | Door |  |  | -14 | 1.1 | 2.4 | -36.96 | m2
|  | Door |  |  | -1 | 1.4 | 2.4 | -3.36 | m2
[10 empty] | 148.181 | 77.795 | 50% | 50% |  | 70.386 | 0% | 0% | 0% | 0 | 50% | 50% |  | 70.386
| 8 | P18-IDR-H-L8-21-COR-002.1 |  | Corridor | 1 | 67.05 | 2.51 | 168.2955 | m2
[5 empty] | -13 | 1.1 | 2.4 | -34.32 | m2
[5 empty] | -1 | 0.9 | 2.4 | -2.16 | m2
[10 empty] | 131.8155 | 0 | 100% | 100% | 100% | 131.8155 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 131.8155
| 9 | P18-IDR-H-L9-COR-002.1 |  | Corridor | 1 | 78.66 | 2.51 | 197.4366 | m2
[5 empty] | -15 | 1.1 | 2.4 | -39.6 | m2
[5 empty] | -1 | 2.14 | 2.4 | -5.136 | m2
[10 empty] | 152.7006 | 0 | 100% | 100% | 100% | 152.7006 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 152.7006
| 10 | P18-IDR-H-L10-22-COR-002.1 |  | Corridor | 1 | 69.13 | 2.51 | 173.5163 | m2
[5 empty] | -13 | 1.1 | 2.4 | -34.32 | m2
[5 empty] | -1 | 1.27 | 2.4 | -3.048 | m2
[10 empty] | 136.1483 | 0 | 100% | 100% | 100% | 136.1483 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 136.1483
| 11 | A-1211 |  | Corridor | 1 | 27.62 | 2.51 | 69.3262 | m2
[5 empty] | -5 | 1.1 | 2.4 | -13.2 | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 12 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 13 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 14 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 15 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 0 | 100% | 100% | 100% | 56.1262 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 56.1262
| 16 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 8.5592 | 90% | 75% | 75% | 47.567 | 0% | 25% | 25% | 4.911 | 90% | 100% | 100% | 52.478
| 19 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 43.0769 | 25% | 20% | 20% | 13.0493 | 75% | 80% | 80% | 43.0769 | 100% | 100% | 100% | 56.1262
| 20 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 5.6126 | 100% | 80% | 20% | 50.5136 | 0% | 20% | 80% | 5.6126 | 100% | 100% | 100% | 56.1262
| 21 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 7.0158 | 100% | 75% |  | 49.1104 | 0% | 25% | 100% | 7.0158 | 100% | 100% | 100% | 56.1262
| 22 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 11.2252 | 100% | 50% |  | 44.901 | 0% | 50% | 100% | 11.2252 | 100% | 100% | 100% | 56.1262
| 23 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 56.1262 |  |  |  | 0 | 100% | 100% | 100% | 56.1262 | 100% | 100% | 100% | 56.1262
| 24 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 28.0631 | 50% | 50% | 50% | 28.0631 | 45% | 40% | 40% | 24.2746 | 95% | 90% | 90% | 52.3377
| 25 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 28.0631 | 50% | 50% | 50% | 28.0631 | 45% | 40% | 40% | 24.2746 | 95% | 90% | 90% | 52.3377
| 26 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 16.8379 | 70% | 70% | 70% | 39.2883 | 25% | 20% | 20% | 13.0493 | 95% | 90% | 90% | 52.3377
| 27 |  |  | Corridor |  |  |  |  | m2 | 56.1262 | 56.1262 |  |  |  | 0 | 95% | 0% | 0% | 34.6579 | 95% |  |  | 34.6579
|  | Lift Lobby Ceiling Work (Level 7 to 16 , L19 to L27 ) |  | Lift lobby | 1 | 19.11 | 2.51 | 47.9661 | m2 |  | 0
[5 empty] | -6 | 1.76 | 2.4 | -25.344 | m2 |  | 0
| 7 |  |  | Lift lobby | 1 |  |  | 22.6221 | m2 | 22.6221 | 21.491 |  |  | 100% | 1.1311 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 8 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 9 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 10 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 11 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 12 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 13 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 14 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0 | 100% | 100% | 100% | 22.6221 | 0% | 0% | 0% | 0 | 100% | 100% | 100% | 22.6221
| 15 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 16 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 19 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 20 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 21 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 22 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 23 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 24 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 25 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 26 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
| 27 |  |  | Lift lobby | 1 |  |  |  | m2 | 22.6221 | 0.0021 |  |  | 100% | 22.62 | 100% | 100% | 100% | 22.6221 |  |  |  | 0
[10 empty] | 1840.5583 | 360.0153 |  |  |  | 1480.543 |  |  |  | 495.6894 |  |  |  | 1454.816
|  |  |  | Total Progress percentage carried to summery | [10 empty] | 80.44% |  |  |  | 137.7% |  |  |  | 79.04%

## VO-09
AL RAWDA GENERAL MAINTENANCE & DÉCOR CO. LLC
PROJECT: PLOT 18, DORCHESTER HOTEL
CONTRACTOR: KHANSAHEB CIVIL ENGINEERING
BOQ - PARTITIONS
VO -09 | Royal Suits, Presidential Suits, Lobbies and Prayer & GYM
BOQ - Dry Wall
Item | Description | Unit | Qty. | Rate | Amount | Progress |  |  | Progress Qty | Progress Amount
[5 empty] | (Dhs.) | Frame | Board | Finish
[6 empty] | 55% | 40% | 5%
PACKAGE -3 - ROYAL SUITE FIT-OUT
WALL FINISHES - RIGHT WING
Additional Items
The Tenderer is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum Tender price for this section of the works. Should the Tenderer fail to insert any items hereunder, it will be deemed that his lump sum price for the Tender includes all works as required by the tender drawings and specification and no subsequent claim for any additional item will be entertained.
Additional Items
Drywall Partitions
1 | DW-1 Type -100mm thick | m2 | 85.05 | 210 | 17860.5 | 55% | 40% |  | 95% | 16967.475 | 95% until WIR approve
2 | DW-3 Type -150mm thick | m2 | 13.94 | 260 | 3624.4 | 55% | 40% |  | 95% | 3443.18 | 95% until WIR approve
3 | DW-4 Type -200mm thick | m2 | 7.8 | 270 | 2106 | 55% | 40% |  | 95% | 2000.7 | 95% until WIR approve
4 | DW-5 Type -Wall lining | m2 | 128.75 | 205 | 26393.75 | 55% | 40% |  | 95% | 25074.0625 | 95% until WIR approve
95% until WIR approve
5 | DW-7 Type -100 to 250mm thick | m2 | 38.35 | 155 | 5944.25 | 55% | 40% |  | 95% | 5647.0375
.
Wet Area wall Partitions
6 | DW-1.1 - Type -100mm thick | m2 | 21.8 | 220 | 4796 | 55% | 40% |  | 95% | 4556.2 | 95% until WIR approve
7 | DW-5.1- Type -Wall | m2 | 42 | 205 | 8610 | 55% | 40% |  | 95% | 8179.5 | 95% until WIR approve
8 | DW-6.2- Type -100mm thick | m2 | 88.46 | 210 | 18576.6 | 55% | 40% |  | 95% | 17647.77 | 95% until WIR approve
PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT
Additional Items
Drywall Partitions
1 | DW-1 Type -100mm thick | m2 | 99.28 | 210 | 20848.8 | 55% | 40% |  | 95% | 19806.36 | 95% until WIR approve
2 | DW-3 Type -150mm thick | m2 | 23.7 | 260 | 6162 | 55% | 40% |  | 95% | 5853.9 | 95% until WIR approve
0
3 | DW-4 Type -200mm thick | m2 | 41.95 | 270 | 11326.5 | 55% | 40% |  | 95% | 10760.175 | 95% until WIR approve
0
4 | DW-5 Type -Wall | m2 | 42.6 | 205 | 8733 | 55% | 40% |  | 95% | 8296.35 | 95% until WIR approve
0
5 | DW-6 Type -Wall | m2 | 92.73 | 160 | 14836.8 | 55% | 40% |  | 95% | 14094.96 | 95% until WIR approve
6 | DW-7 Type -100 to 250mm thick | m2 | 33.48 | 155 | 5189.4 | 55% | 40% |  | 95% | 4929.93 | 95% until WIR approve
7 | DW-8 Type -180mm thick | m2 | 6.37 | 270 | 1719.9 | 55% | 40% |  | 95% | 1633.905 | 95% until WIR approve
8 | DW-9 Type -220mm thick | m2 | 61.06 | 310 | 18928.6 | 55% | 40% |  | 95% | 17982.17 | 95% until WIR approve
Wet Area wall Partitions
9 | DW-1.1 - Type -100mm thick | m2 | 131.99 | 220 | 29037.8 | 55% | 40% |  | 95% | 27585.91 | 95% until WIR approve
10 | DW-3.1- Type -150mm thick | m2 | 2.24 | 280 | 627.2 | 55% | 40% |  | 95% | 595.84 | 95% until WIR approve
11 | DW-5.1- Type -Wall | m2 | 36.18 | 205 | 7416.9 | 55% | 40% |  | 95% | 7046.055 | 95% until WIR approve
12 | DW-6.1- Type -Wall | m2 | 13.23 | 165 | 2182.95 | 55% | 40% |  | 95% | 2073.8025 | 95% until WIR approve
13 | DW-7.1 Type -100 to 250mm thick | m2 | 9.5 | 160 | 1520 | 55% | 40% |  | 95% | 1444 | 95% until WIR approve
PACKAGE -4 - HOTEL - GYM - L28
GYPSUM PARTITIONS PACKAGE
WALL LINING
Supply and installation of wall linings, including all necessary related works, complete; all in accordance with the Drawings, Specifications and Scope of Works.
A | Gypsum Wall Lining to receive wall finishes at round pillars | m2 | 38.4 | 390 | 14976 | 55% |  |  | 55% | 8236.8
B | Gypsum Wall Lining to receive wall finishes | m2 | 21 | 160 | 3360
Additional Items
| Gypsum Wall Lining to receive wall finishes- WC only | m2 | 160.8 | 15 | 2412
| DW-08- 220mm sliding door pocket wall, one side with Regular gypsum board, MR board inner side | m2 | 18.6 | 470 | 8742 | 55% | 20% |  | 75% | 6556.5
Level -1
Corridor
24 | Gypsum Wall Cladding | m2 | 244.5 | 155 | 37897.5 | 60% | 40% |  | 100% | 37897.5
| TOTAL AMOUNT IN AED |  |  |  | 283828.85 |  |  |  |  | 258310.0825
BOQ - CEILING
Item | Description | Qty. | Unit | Rate | Amount | Progress |  |  | Progress Qty | Progress Amount
[5 empty] | (Dhs.) | Frame | Board | Finish
[6 empty] | 60% | 35% | 5%
PACKAGE -3 - ROYAL SUITE FIT-OUT
CEILING FINISHES - RIGHT WING
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
B | Supply and fixing of Ceiling System including the finishes type; HTL-WC-24 (Gypsum ceiling by others) | 0 | m2 |  | 0
| Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others) | 8.35 | m2 | 130 | 1085.5 | 60% | 35% |  | 95% | 1031.225
C | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others) | 1.58 | m2 | 130 | 205.4 | 60% | 35% |  | 95% | 195.13
D | Supply and fixing of cornice including the finishes type; HTL-ME-01, brushed bronze patina |  | m | N/A | N/A
CEILING FINISHES - LEFT WING
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
B | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others) | 33.94 | m2 | 130 | 4412.2 | 60% | 35% |  | 95% | 4191.59
C | Supply and fixing of Ceiling System including the finishes type; HTL-WC-24 (Gypsum ceiling by others) | 0 | m2 | N/A | N/A
D | Supply and fixing of Ceiling System including the finishes type; HTL-WC-25 (Gypsum ceiling by others) | 0 | m2 | N/A | N/A
E | Supply and fixing of Ceiling System including the finishes type; HTL-ST-51 | 3.18 | m2 | 130 | 413.4 | 60% | 35% |  | 95% | 392.73
F | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others) | 3 | m2 | 130 | 390 | 60% | 35% |  | 95% | 370.5
CEILING FINISHES - LEFT WING (CONT'D)
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
A | Supply and fixing of Ceiling System including the finishes type; HTL-WD-02 | 7.7168 | m2 | 130 | 1003.1905 | 60% | 35% |  | 95% | 953.031
B | Ditto, Light cove ceiling, 85x155mm wide | 13.21 | m | 140 | 1849.4 | 60% | 35% |  | 95% | 1756.93
C | Supply and fixing of Ceiling System including the finishes type; HTL-WD-19 | 2.3895 | m2 | 130 | 310.635 | 60% | 35% |  | 95% | 295.1033
D | Ditto, Light cove ceiling, 130x165mm wide | 5.52 | m | 150 | 828 | 60% | 35% |  | 95% | 786.6
E | Supply and fixing of cornice including the finishes type; HTL-ME-01, brushed bronze patina
1 | 55mm high | 7.07 | m | N/A | N/A
2 | 85mm high | 11.01 | m | N/A | N/A
3 | 280mm high | 12.72 | m | N/A | N/A
Additional Items
CEILING FINISHES - RIGHT WING
B | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others) | 106.23 | m2 | 130 | 13809.9 | 60% |  |  | 60% | 8285.94
C1 | Supply and fixing of Ceiling System including the finishes (M.R board Gypsum ceiling Only) | 24 | m2 | 140 | 3360 | 60% |  |  | 60% | 2016
B.1 | Bulkhead upto 250 mm height | 94.3 | m | 70 | 6601 | 60% |  |  | 60% | 3960.6
B.2 | Bulkhead 350 mm height | 20 | m | 80 | 1600 | 60% |  |  | 60% | 960
B.3 | Bulkhead 450 mm height | 4.4 | m | 85 | 374 | 60% |  |  | 60% | 224.4
B.4 | Bulkhead 750 mm height | 17.12 | m | 105 | 1797.6 | 60% |  |  | 60% | 1078.56
B.5 | Bulkhead 3300 mm height | 70.3 | m | 475 | 33392.5 | 60% |  |  | 60% | 20035.5
B.6 | Light cove ceiling, 100x50mm wide | 26 | m | 140 | 3640 | 60% |  |  | 60% | 2184
B.7 | Light cove ceiling, 150x100mm wide | 45.14 | m | 140 | 6319.6 | 60% |  |  | 60% | 3791.76
B.8 | Light cove ceiling, 300x100mm wide | 22 | m | 220 | 4840 | 60% |  |  | 60% | 2904
B.9 | Curtain Pelmet | 26 | m | 180 | 4680 | 60% |  |  | 60% | 2808
B.10 | 350 x 200 mm Cement Board Backing Panel | 8 | m2 | 320 | 2560 | 60% |  |  | 60% | 1536
CEILING FINISHES - LEFT WING
B | Ditto, Light cove ceiling, 85x155mm wide | 13.79 | m | 140 | 1930.6 | 60% |  |  | 60% | 1158.36
B.1 | Bulkhead 180 mm height | 42 | m | 60 | 2520 | 60% |  |  | 60% | 1512
B.9 | Curtain Pelmet | 13 | m | 180 | 2340 | 60% |  |  | 60% | 1404
| Sub-total |  |  |  | 100262.9255
PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT
CEILING FINISHES - RIGHT WING
C | Supply and fixing of Ceiling System including the finishes type; HTL-WC-00
1 | Dining Room | 6.346 | m2 | 130 | 824.98 | 60% | 35% |  | 95% | 783.731 | 95% until WIR approve
D | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others)
1 | Dining Room | 5.714 | m2 | 130 | 742.82 | 60% | 35% |  | 95% | 705.679 | 95% until WIR approve
2 | Twin Bedroom | 13.272 | m2 | 130 | 1725.36 | 60% |  |  | 60% | 1035.216
E | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others)
1 | Open Kitchen | 4.768 | m2 | 140 | 667.52 | 60% | 35% |  | 95% | 634.144
F | Supply and fixing of Ceiling System including the finishes type; HTL-ST-35 (Gypsum ceiling by others)
1 | Twin Bathroom | 1.26 | m2 | 140 | 176.4 | 60% | 35% |  | 95% | 167.58
CEILING FINISHES - LEFT WING
C | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others)
1 | Living Room | 15.832 | m2 | 130 | 2058.16 | 60% | 35% |  | 95% | 1955.252 | 95% until WIR approve
D | Supply and fixing of Ceiling System including the finishes type; HTL-WC-22 (Gypsum ceiling by others)
1 | Living Room | 10.346 | m2 | 130 | 1344.98 | 60% | 35% |  | 95% | 1277.731 | 95% until WIR approve
2 | Master Bedroom | 19.376 | m2 | 130 | 2518.88 | 60% | 35% |  | 95% | 2392.936
E | Supply and fixing of Ceiling System including the finishes type; HTL-WC-24 (Gypsum ceiling by others)
1 | Master Bedroom | 9.331 | m2 | 130 | 1213.03 | 60% | 35% |  | 95% | 1152.3785
F | Supply and fixing of Ceiling System including the finishes type; HTL-GL-01 (Gypsum ceiling by others)
1 | Entry Vestibule | 3.56 | m2 | 130 | 462.8 | 60% |  |  | 60% | 277.68
35%
G | Supply and fixing of Ceiling System including the finishes type, bulkhead, light cove, etc; HTL-ST-35 (Gypsum ceiling by others)
1 | Master Bathroom | 0.928 | m2 | 140 | 129.92 | 60% | 35% |  | 95% | 123.424
CEILING FINISHES - LEFT WING (CONT'D)
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
D | Supply and fixing of Ceiling Type HTL-ME-01 incl. light cove, cornice, bulkhead and etc; Brass, Brushed bronze patina
1 | Study | 0.84 | m2 | 260 | 218.4 | 60% | 35% |  | 95% | 207.48
Additional Items
CEILING FINISHES - RIGHT WING
C | Supply and fixing of Ceiling System including the finishes type; Regalur gypsum ceiling | 72.2 | m2 | 130 | 9386 | 60% | 35% |  | 95% | 8916.7
G | Supply and fixing of Ceiling System including the finishes type; M.R gypsum ceiling | 25.8 | m2 | 140 | 3612 | 60% | 35% |  | 95% | 3431.4
B.1 | Bulkhead upto 250 mm height | 137 | m | 70 | 9590 | 60% | 35% |  | 95% | 9110.5
B.6 | Light cove ceiling, 65x70mm wide | 34.61 | m | 140 | 4845.4 | 60% | 35% |  | 95% | 4603.13
B.6a | Light cove ceiling, 115x100mm wide | 37.71 | m | 140 | 5279.4 | 60% | 35% |  | 95% | 5015.43
B.8 | Light cove ceiling, 300x110mm wide | 21.42 | m | 220 | 4712.4 | 60% | 35% |  | 95% | 4476.78
B.8a | Light cove ceiling, 175x90mm wide | 77.3 | m | 175 | 13527.5 | 60% | 35% |  | 95% | 12851.125
B.9 | Curtain Pelmet -150X200mm | 4.75 | m | 180 | 855 | 60% | 35% |  | 95% | 812.25
B.9a | Curtain Pelmet -175X200mm | 28.54 | m | 180 | 5137.2 | 60% | 35% |  | 95% | 4880.34
B.9d | Curtain Pelmet -350X450mm | 24.93 | m | 275 | 6855.75 | 60% | 35% |  | 95% | 6512.9625
CEILING FINISHES - LEFT WING
C | Supply and fixing of Ceiling System including the finishes type; Regalur gypsum ceiling | 52.72 | m2 | 130 | 6853.6 | 60% | 35% |  | 95% | 6510.92
G | Supply and fixing of Ceiling System including the finishes type; M.R gypsum ceiling | 48.3 | m2 | 140 | 6762 | 60% | 35% |  | 95% | 6423.9
B.1 | Bulkhead upto 250 mm height | 147.18 | m | 70 | 10302.6 | 60% | 35% |  | 95% | 9787.47
B.6 | Light cove ceiling, 100x80mm wide | 46.77 | m | 140 | 6547.8 | 60% | 35% |  | 95% | 6220.41
B.7 | Light cove ceiling, 150x100mm wide | 49.26 | m | 140 | 6896.4 | 60% | 35% |  | 95% | 6551.58
B.8 | Light cove ceiling, 300x100mm wide | 8.82 | m | 220 | 1940.4 | 60% | 35% |  | 95% | 1843.38
B.9 | Curtain Pelmet -150X205mm | 22.7 | m | 180 | 4086 | 60% | 35% |  | 95% | 3881.7
B.9a | Curtain Pelmet -250X550mm | 4.32 | m | 280 | 1209.6 | 60% | 35% |  | 95% | 1149.12
B.9b | Curtain Pelmet -350X200mm | 4.35 | m | 340 | 1479 | 60% | 35% |  | 95% | 1405.05
B.9c | Curtain Pelmet -350X400mm | 8.82 | m | 350 | 3087 | 60% | 35% |  | 95% | 2932.65
B.10 | Curved Light cove ceiling, 130x100mm wide | 18.82 | m | 280 | 5269.6 | 60% | 35% |  | 95% | 5006.12
| Sub-total |  |  |  | 130317.9
PACKAGE -4 - HOTEL - GYM - L28
CEILING WORKS
Note: The Sub-contractor is referred to the Specifications and Drawings for all details related to this Section of the Works and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the item description.
CEILING FINISHES
Suspended ceilings including frame work, suspension system, bulkheads, fittings, fixtures, accessories, preparation of surface to receive paint, etc. & ceiling rate shall be included for required paint finish (supplied and installed complete)
A | Gypsum board ceiling in finish Type HTL-PT-04 | 134 | M2 | 130 | 17420 | 60% | 30% |  | 90% | 15678
B | Ditto: beams overall size 200 x 200 x 200mm | 188 | m | 240 | 45120 | 60% | 30% |  | 90% | 40608
C | Ditto; curtain box 205 x 365mm high | 26 | m | 150 | 3900 | 60% | 30% |  | 90% | 3510
D | Ditto; light cove 200 x 200mm high | 36 | m | 150 | 5400 | 60% | 30% |  | 90% | 4860
| Sub-total |  |  |  | 71840
PACKAGE -4 - HOTEL LEVEL 01:- PRAYER ROOM & ABLUTION
CEILING FINISHES
Suspended Ceiling System and Finishes
Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
A | Supply and fixing of Ceiling System including the finishes type; HTL-PT-03, White Paint, Color Terre Blanche - Matte Finish
1 | Male Ablution | 9.85 | m2 | 140 | 1379 | 60% | 35% |  | 95% | 1310.05
2 | Female Ablution | 10.232 | m2 | 140 | 1432.48 | 60% | 35% |  | 95% | 1360.856
3 | Male Prayer Room | 20.338 | m2 | 140 | 2847.32 | 60% | 35% |  | 95% | 2704.954 | 95% until WIR approve
4 | Female Prayer Room | 13.983 | m2 | 140 | 1957.62 | 60% | 35% |  | 95% | 1859.739 | 95% until WIR approve
5 | Store | 2.213 | m2 | 140 | 309.82 | 60% | 35% |  | 95% | 294.329
B | Ditto, Ceiling Bulkhead; 150mm high | 35.95 | m | 60 | 2157 | 60% | 35% |  | 95% | 2049.15
C | Ditto, Light Cove Ceiling, 50x100mm wide | 35.95 | m | 140 | 5033 | 60% | 35% |  | 95% | 4781.35
| Sub-total |  |  |  | 15116.24
PACKAGE - 4 - HOTEL GF LOBBY AND L1 CORRIDOR
CEILING FINISHES
Suspended Ceiling System and Finishes
Supply and installation of Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
1 | Ceiling System to GF Lobby including the finishes type; HTL-PT-04, White Paint, color All white N° 2005 - Matte finish | 40 | m2 | 280 | 11200 | 60% | 35% |  | 95% | 10640
2 | Ditto, Ceiling Bulkhead; 150mm high | 21 | m | 130 | 2730 | 60% | 35% |  | 95% | 2593.5
3 | Ditto, Light Cove Ceiling, 50x100mm wide | 21 | m | 260 | 5460 | 60% | 35% |  | 95% | 5187
4 | Ceiling System to L1 Corridor including the finishes type; HTL-PT-09, Light Grey Paint, color Argile Grisée - matte finish | 167 | m2 | 130 | 21710 | 60% | 35% |  | 95% | 20624.5 | 95% until WIR approve
5 | Ditto, Ceiling Bulkhead; 150mm high | 126 | m | 60 | 7560 | 60% | 35% |  | 95% | 7182 | 95% until WIR approve
6 | Ditto, Light Cove Ceiling, 50x100mm wide | 129 | m | 140 | 18060 | 60% | 35% |  | 95% | 17157 | 95% until WIR approve
CEILING FINISHES (CONT'D)
Additional Items
| Allow for structural support above ceiling to suspend chandelier | 1 | No. | TBC | No details available
A | Supply and Installation of permanent access panels, maximum size up to 600mm x 600mm size | RO | No | 260 | Rate Only
B | Supply and Installation of Temporary access panels, maximum size up to 600mm x 600mm size | RO | No | 110 | Rate Only
| Sub-total |  |  |  | 66720
| TOTAL AMOUNT IN AED |  |  |  | 384257.0655 |  |  |  |  | 329268.5362
[7 empty] | VO -09 - Total Amount |  |  | 587578.6187

## VO-11
v | PROJECT |  |  | Dorchestor Hotel & Residence
v | CONTRACTOR |  |  | KHANSAHEB CIVIL ENGINEERING LLC
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
VO :011. Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works
Quantity
SN | Level | Room | Type | Room | No. |  | Work done | Total | Remarks
| L08 | 801 | 8A | 1 Bed Suite | 1 |  | 1
| L08 | 802 | 2B | Deluxe Room | 1 |  | 1
| L08 | 803 | 2C | Deluxe Room | 1 |  | 1
| L08 | 806 | 2A | Deluxe Room | 1 |  | 1
| L08 | 807 | 1B | Deluxe Room | 1 |  | 1
| L08 | 707.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L08 | 808 | 4A | Junior Twin Suite | 1 |  | 1
| L09 | 901 | 8A | 1 Bed Suite | 1 |  | 1
| L09 | 902 | 2B | Deluxe Room | 1 |  | 1
| L09 | 903 | 2C | Deluxe Room | 1 |  | 1
| L09 | 906 | 2A | Deluxe Room | 1 |  | 1
| L09 | 907 | 9A | 1 Bed Suite | 1 |  | 1
| L09 | 908 | 9B | 1 Bed Suite | 1 |  | 1
| L09 | 909 | 1B | Deluxe Room | 1 |  | 1
| L09 | 910 | 4A | Junior Twin Suite | 1 |  | 1
| L10 | 1001 | 8A | 1 Bed Suite | 1 |  | 1
| L10 | 1002 | 2B | Deluxe Room | 1 |  | 1
| L10 | 1003 | 2C | Deluxe Room | 1 |  | 1
| L10 | 1006 | 2A | Deluxe Room | 1 |  | 1
| L10 | 1007 | 15a | 1 Bed Suite | 1 |  | 1
| L10 | 1008 | 1B | Deluxe Room | 1 |  | 1
| L10 | 1009 | 4A | Junior Twin Suite | 1 |  | 1
| L11 | 1101 | 8A | 1 Bed Suite | 1 |  | 1
| L11 | 1102 | 2B | Deluxe Room | 1 |  | 1
| L11 | 1103 | 2C | Deluxe Room | 1 |  | 1
| L11 | 1106 | 2A | Deluxe Room | 1 |  | 1
| L11 | 1107 | 16A | Deluxe Room | 1 |  | 1
| L11 | 1108 | 1B | Deluxe Room | 1 |  | 1
| L11 | 1109 | 4A | Junior Twin Suite | 1 |  | 1
| L12 | 1201 | 10A | 1 Bed Suite | 1 |  | 1
| L12 | 1203 | 2B | Deluxe Room | 1 |  | 1
| L12 | 1204 | 11C | 1 Bed Suite | 1 |  | 1
| L12 | 1206 | 2B | Deluxe Room | 1 |  | 1
| L12 | 1207 | 11C | 1 Bed Suite | 1 |  | 1
| L12 | 1209 | 2A | Deluxe Room | 1 |  | 1
| L12 | 1210 | 9A | 1 Bed Suite | 1 |  | 1
| L12 | 1211 | 9B | 1 Bed Suite | 1 |  | 1
| L12 | 1212 | 1A | Deluxe Room | 1 |  | 1
| L12 | 1213 | 2F | Deluxe Room | 1 |  | 1
| L12 | 1216 | 2G | Deluxe Room | 1 |  | 1
| L12 | 1217 | 2E | Deluxe Room | 1 |  | 1
| L12 | 1218 | 5A | 1 Bed Suite | 1 |  | 1
| L13 | 1401 | 10A | 1 Bed Suite | 1 |  | 1
| L13 | 1403 | 2B | Deluxe Room | 1 |  | 1
| L13 | 1404 | 11C | 1 Bed Suite | 1 |  | 1
| L13 | 1406 | 2B | Deluxe Room | 1 |  | 1
| L13 | 1407 | 11C | 1 Bed Suite | 1 |  | 1
| L13 | 1409 | 2A | Deluxe Room | 1 |  | 1
| L13 | 1410 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L13 | 1411 | 19A | Deluxe Room | 1 |  | 1
| L13 | 1412 | 1A | Deluxe Room | 1 |  | 1
| L13 | 1413 | 2F | Deluxe Room | 1 |  | 1
| L13 | 1416 | 2G | Deluxe Room | 1 |  | 1
| L13 | 1417 | 2E | Deluxe Room | 1 |  | 1
| L13 | 1418 | 5A | 1 Bed Suite | 1 |  | 1
| L14 | 1501 | 10A | 1 Bed Suite | 1 |  | 1
| L14 | 1503 | 2B | Deluxe Room | 1 |  | 1
| L14 | 1504 | 11C | 1 Bed Suite | 1 |  | 1
| L14 | 1506 | 2B | Deluxe Room | 1 |  | 1
| L14 | 1507 | 11C | 1 Bed Suite | 1 |  | 1
| L14 | 1509 | 2A | Deluxe Room | 1 |  | 1
| L14 | 1510 | 1A | Deluxe Room | 1 |  | 1
| L14 | 1511 | 2F | Deluxe Room | 1 |  | 1
| L14 | 1510.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L14 | 1514 | 2G | Deluxe Room | 1 |  | 1
| L14 | 1515 | 2E | Deluxe Room | 1 |  | 1
| L14 | 1516 | 5A | 1 Bed Suite | 1 |  | 1
| L15 | 1601 | 10A | 1 Bed Suite | 1 |  | 1
| L15 | 1603 | 2B | Deluxe Room | 1 |  | 1
| L15 | 1604 | 11C | 1 Bed Suite | 1 |  | 1
| L15 | 1606 | 2B | Deluxe Room | 1 |  | 1
| L15 | 1607 | 11C | 1 Bed Suite | 1 |  | 1
| L15 | 1609 | 2A | Deluxe Room | 1 |  | 1
| L15 | 1610 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L15 | 1611 | 19A | Deluxe Room | 1 |  | 1
| L15 | 1612 | 1A | Deluxe Room | 1 |  | 1
| L15 | 1613 | 2F | Deluxe Room | 1 |  | 1
| L15 | 1616 | 2G | Deluxe Room | 1 |  | 1
| L15 | 1617 | 2E | Deluxe Room | 1 |  | 1
| L15 | 1618 | 5A | 1 Bed Suite | 1 |  | 1
| L16 | 1701 | 10A | 1 Bed Suite | 1 |  | 1
| L16 | 1702 | 11D | 1 Bed Suite | 1 |  | 1
| L16 | 1703 | 2C | Deluxe Room | 1 |  | 1
| L16 | 1706 | 2B | Deluxe Room | 1 |  | 1
| L16 | 1707 | 11C | 1 Bed Suite | 1 |  | 1
| L16 | 1709 | 2A | Deluxe Room | 1 |  | 1
| L16 | 1710.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L16 | 1710 | 1C | Deluxe Room | 1 |  | 1
| L16 | 1711 | 2H | Deluxe Room | 1 |  | 1
| L16 | 1714 | 2G | Deluxe Room | 1 |  | 1
| L16 | 1715 | 2E | Deluxe Room | 1 |  | 1
| L16 | 1716 | 5A | 1 Bed Suite | 1 |  | 1
| L07 | 701 | 8A | 1 Bed Suite | 1 |  | 1
| L07 | 702 | 2B | Deluxe Room | 1 |  | 1
| L07 | 703 | 2C | Deluxe Room | 1 |  | 1
| L07 | 706 | 2A | Deluxe Room | 1 |  | 1
| L07 | 707 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L07 | 708 | 19A | Deluxe Room | 1 |  | 1
| L07 | 709 | 1C | Deluxe Room | 1 |  | 1
| L07 | 710 | 4B | Junior Twin Suite | 1 |  | 1
| L19 | 2001 | 12A | 1 Bed Suite | 1 |  | 1
| L19 | 2002 | 17A | Presidential Suite | 1 |  | 1
| L19 | 2003 | 19A | Deluxe Room | 1 |  | 1
| L19 | 2004 | 6A | 1 Bed Suite | 1 |  | 1
| L20 | 2101 | 12A | 1 Bed Suite | 1 |  | 1
| L20 | 2102 | 2D | Deluxe Room | 1 |  | 1
| L20 | 2104 | 11B | 1 Bed Suite | 1 |  | 1
| L20 | 2105 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L20 | 2106 | 19A | Deluxe Room | 1 |  | 1
| L20 | 2107 | 6A | 1 Bed Suite | 1 |  | 1
| L21 | 2201 | 12A | 1 Bed Suite | 1 |  | 1
| L21 | 2202 | 2D | Deluxe Room | 1 |  | 1
| L21 | 2204 | 11B | 1 Bed Suite | 1 |  | 1
| L21 | 2205.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L21 | 2205 | 6A | 1 Bed Suite | 1 |  | 1
| L22 | 2301 | 12A | 1 Bed Suite | 1 |  | 1
| L22 | 2302 | 11A | 1 Bed Suite | 1 |  | 1
| L22 | 2304 | 2A | Deluxe Room | 1 |  | 1
| L22 | 2305 | 15A | 1 Bed Suite | 1 |  | 1
| L22 | 2306 | 6A | 1 Bed Suite | 1 |  | 1
| L23 | 2401 | 12A | 1 Bed Suite | 1 |  | 1
| L23 | 2402 | 2D | Deluxe Room | 1 |  | 1
| L23 | 2404 | 11B | 1 Bed Suite | 1 |  | 1
| L23 | 2405 | 16A | Deluxe Room | 1 |  | 1
| L23 | 2406 | 6A | 1 Bed Suite | 1 |  | 1
| L24 | 2501 | 13A | 1 Bed Suite | 1 |  | 1
| L24 | 2502 | 14A | 1 Bed Suite | 1 |  | 1
| L24 | 2503 | 2D | Deluxe Room | 1 |  | 1
| L24 | 2506 | 2B | Deluxe Room | 1 |  | 1
| L24 | 2507 | 11C | 1 Bed Suite | 1 |  | 1
| L24 | 2509 | 2A | Deluxe Room | 1 |  | 1
| L24 | 2510 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L24 | 2511 | 19A | Deluxe Room | 1 |  | 1
| L24 | 2512 | 1A | Deluxe Room | 1 |  | 1
| L24 | 2513 | 2F | Deluxe Room | 1 |  | 1
| L24 | 2516 | 2G | Deluxe Room | 1 |  | 1
| L24 | 2517 | 2E | Deluxe Room | 1 |  | 1
| L24 | 2518 | 5A | 1 Bed Suite | 1 |  | 1
| L25 | 2601 | 10B | 1 Bed Suite | 1 |  | 1
| L25 | 2602 | 14A | 1 Bed Suite | 1 |  | 1
| L25 | 2603 | 2D | Deluxe Room | 1 |  | 1
| L25 | 2606 | 2B | Deluxe Room | 1 |  | 1
| L25 | 2607 | 11C | 1 Bed Suite | 1 |  | 1
| L25 | 2609 | 2A | Deluxe Room | 1 |  | 1
| L25 | 2610.1 | 7A | 1 Bed Suite Duplex | 1 |  | 1
| L25 | 2610 | 1A | Deluxe Room | 1 |  | 1
| L25 | 2611 | 2F | Deluxe Room | 1 |  | 1
| L25 | 2614 | 2G | Deluxe Room | 1 |  | 1
| L25 | 2615 | 2E | Deluxe Room | 1 |  | 1
| L25 | 2616 | 5A | 1 Bed Suite | 1 |  | 1
| L26 | 2701 | 10B | 1 Bed Suite | 1 |  | 1
| L26 | 2702 | 14A | 1 Bed Suite | 1 |  | 1
| L26 | 2703 | 2D | Deluxe Room | 1 |  | 1
| L26 | 2705 | 11D | 1 Bed Suite | 1 |  | 1
| L26 | 2706 | 2C | Deluxe Room | 1 |  | 1
| L26 | 2708 | 18A | Royal Suite | 1 |  | 1
| L26 | 2709 | 1A | Deluxe Room | 1 |  | 1
| L26 | 2710 | 2F | Deluxe Room | 1 |  | 1
| L26 | 2713 | 2G | Deluxe Room | 1 |  | 1
| L26 | 2714 | 2E | Deluxe Room | 1 |  | 1
| L26 | 2715 | 5A | 1 Bed Suite | 1 |  | 1
| L27 | 2801 | 10B | 1 Bed Suite | 1 |  | 1
| L27 | 2802 | 14A | 1 Bed Suite | 1 |  | 1
| L27 | 2803 | 2D | Deluxe Room | 1 |  | 1
| L27 | 2806 | 2C | Deluxe Room | 1 |  | 1
| L27 | 2805 | 11D | 1 Bed Suite | 1 |  | 1
| L27 | 2808 | 11B | 1 Bed Suite | 1 |  | 1
| L27 | 2809 | 16A | Deluxe Room | 1 |  | 1
| L27 | 2810 | 1A | Deluxe Room | 1 |  | 1
| L27 | 2811 | 2F | Deluxe Room | 1 |  | 1
| L27 | 2814 | 2G | Deluxe Room | 1 |  | 1
| L27 | 2815 | 2E | Deluxe Room | 1 |  | 1
| L27 | 2816 | 5A | 1 Bed Suite | 1 |  | 1
[5 empty] | 173 |  | 173 | 173
| VO-011 | Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works |  |  | 173 | Nos | 245 | 42385
work down
| VO-011 | Cutting of gypsum ceiling, removing and replacing existing plywood supports to calcium silicate board & Painting works |  |  | 173 | Nos | 245 | 42385

## VO-12
PROJECT:Dorchestor Hotel & Residence
KHANSAHEB CIVIL ENGINEERING LLC
VALUATION OF VARIATION
PACKAGE: | Ceiling & Partitions
DATE: | 2022-08-30
VARIATION REF: | VO-012
DESCRIPTION: | External Ceiling Cutting and Finishing Works at Hoel Level -16
Item Ref | Description | BoQ Ref | Rate Ref | Quantity | Unit | Rate (AED) | Omission (AED) | Addition (AED) | Remarks
|  |  |  | Quantity | Unit
VO-012/1 | Removal & Disposal , Refixing Ceiling and Painting works |  |  | 89.5 | m2 | 192 |  | 17184
Measure
| AR-CI-SD--ML-60020 | Hotel | Level -16 | 89.5
| Sub Total | [5 empty] | 0 | 17184
| Grand Total | [6 empty] | 17184

## VO-16a
v | PROJECT | Dorchestor Plot BB. B03.018, Business Bay
v | CONTRACTOR | KCE
v | SUB CONTRACTOR | AL RAWDA
v | SUBJECT | VO-016a STAIRCASE
| Paint to Stairsace Wall |  |  |  |  | Quantity |  |  |  | Deduction |  | Net Total |  | Skim coat | Primer | Stucco | 1st cot Paint | Final coat | Paint
SN | DWG .NO | Level | Location | No. | Length | Height / Width | Total | Length | Height / Width | No. | Total | Wall Net Total |  | 100% | 20% | 30% | 30% | 20% | TOTAL QTY | Total Amount
1 | A-4101-4 | B2 to B1 | ST-01 | 1 | 19.46 | 9.1 | 177.086 | 1.1 | 2.1 | -1 | -2.31 | 174.776 |  | 174.776 | 34.9552 | 52.4328 | 52.4328 | 34.9552 | 174.776
|  | G.F | ST-01 | 1 | 19.95 | 1 | 19.95 |  |  |  |  | 19.95 |  | 19.95 | 3.99 | 5.985 | 5.985 | 3.99 | 19.95
0
| A-4101-4 | B2 to B1 | ST-02 | 1 | 18.95 | 10.88 | 206.176 | 1.1 | 2.1 | -2 | -4.62 | 201.556 |  | 201.556 | 40.3112 | 60.4668 | 60.4668 | 40.3112 | 201.556
| A-4101-4 | G.F | ST-02 | 1 | 31.65 | 3.05 | 96.5325 | 1.1 | 2.1 | -4 | -9.24 | 87.2925 |  | 87.2925 | 17.4585 | 26.1877 | 26.1877 | 17.4585 | 87.2925
| A-4101-4 | L2 | ST-02 | 1 | 18.95 | 3.05 | 57.7975 | 1.1 | 2.1 | -1 | -2.31 | 55.4875 |  | 55.4875 | 11.0975 | 16.6462 | 16.6462 | 11.0975 | 55.4875
| A-4101-4 | L3 | ST-02 | 1 | 25.95 | 4.25 | 110.2875 | 1.1 | 2.1 | -3 | -6.93 | 103.3575 |  | 103.3575 | 20.6715 | 31.0072 | 31.0072 | 20.6715 | 103.3575
| A-4102-5 | B2 to B1 | ST-03 | 1 | 21.06 | 11.2 | 235.872 | 1.2 | 2.1 | -2 | -5.04 | 230.832 |  | 230.832
[8 empty] | 1.1 | 2.1 | -2 | -4.62 | -4.62 |  | -4.62
| A-4102-5 | G.F | ST-03 | 1 | 31.48 | 4.57 | 143.8636 | 1.2 | 2.1 | -2 | -5.04 | 138.8236 |  | 138.8236
| A-4102-5 | L1 to L31 | ST-03 | 1 | 21.06 | 129 | 2716.74 | 1.2 | 2.1 | -29 | -73.08 | 2643.66 | L5-29 | 2114.928 | 422.9856 | 634.4784 | 634.4784 | 264.366 | 1956.3084 | L17-31
[8 empty] | 1.1 | 2.1 | -30 | -69.3 | -69.3 | L5-29 | -55.44 | -11.088 | -16.632 | -16.632 | -6.93 | -51.282 | L5-29
0
| A-4102-5 | B2 to B1 | ST-04 | 1 | 21.06 | 11.2 | 235.872 | 1.2 | 2.1 | -2 | -5.04 | 230.832 |  | 230.832 | 46.1664 | 69.2496 | 69.2496 |  | 184.6656
[8 empty] | 1.1 | 2.1 | -2 | -4.62 | -4.62 |  | -4.62 | -0.924 | -1.386 | -1.386 |  | -3.696
| A-4102-5 | G.F | ST-04 | 1 | 31.48 | 4.57 | 143.8636 | 1.2 | 2.1 | -2 | -5.04 | 138.8236 |  | 138.8236 | 27.7647 | 41.6471 | 41.6471 |  | 111.0589
| A-4102-5 | L1 to L31 | ST-04 | 1 | 21.06 | 129 | 2716.74 | 1.2 | 2.1 | -29 | -73.08 | 2643.66 |  | 1057.464 | 79.3098 | 118.9647 | 118.9647 |  | 317.2392 | L1-5 -15%
[8 empty] | 1.1 | 2.1 | -30 | -69.3 | -69.3 |  | -27.72 | -0.8316 | -1.2474 | -1.2474 |  | -3.3264 | L23-28
0
| A-4103-5 | B2 to B1 | ST-05 | 1 | 19.14 | 11.4 | 218.196 | 1.2 | 2.1 | -2 | -5.04 | 213.156 |  | 213.156 | 42.6312 | 63.9468 | 63.9468 | 42.6312 | 213.156
0
| A-4104-5 | B2 to B1 | ST-06 | 1 | 18.4 | 11.22 | 206.448 | 1.1 | 2.1 | -2 | -4.62 | 201.828 |  | 201.828 | 40.3656 | 60.5484 | 60.5484 |  | 161.4624
| A-4104-5 | G.F | ST-06 | 1 | 21.06 | 3.14 | 66.1284 | 1.1 | 2.1 | -2 | -4.62 | 61.5084 |  | 61.5084 | 12.3017 | 18.4525 | 18.4525 |  | 49.2067
| A-4104-5 | L2 to L28 | ST-06 | 1 | 18.4 | 105.24 | 1936.416 | 1.1 | 2.1 | -28 | -64.68 | 1871.736 |  | 187.1736 | 37.4347 | 56.1521 | 56.1521 |  | 149.7389
| A-4106-5 | B2 to B1 | ST-07 | 1 | 21.16 | 11.22 | 237.4152 | 1.1 | 2.1 | -2 | -4.62 | 232.7952 |  | 232.7952
| A-4106-5 | G.F | ST-07 | 1 | 37.24 | 6.5 | 242.06 | 1.1 | 2.1 | -2 | -4.62 | 237.44 |  | 225.568 | 47.488 | 71.232 | 71.232 |  |  | L7-29
| A-4106-5 | L2 to R | ST-07 | 1 | 21.16 | 112.4 | 2378.384 | 1.1 | 2.1 | -56 | -129.36 | 2249.024 | L2 to 29 | 2136.5728 | 427.3146 | 640.9718 | 640.9718 | 1602.4296 | 3311.6878 | L2-29
| A-4108-5 | B2 to B1 | ST-08 | 1 | 21.16 | 11.22 | 237.4152 | 1.1 | 2.1 | -2 | -4.62 | 232.7952 |  | 221.1554 | 46.559 | 69.8386 | 69.8386 |  | 186.2362
| A-4108-5 | G.F | ST-08 | 1 | 42 | 6.5 | 273 | 1.1 | 2.1 | -2 | -4.62 | 268.38 | [7 empty] | L7-29
| A-4108-5 | L2 to R | ST-08 | 1 | 21.16 | 112.4 | 2378.384 | 1.1 | 2.1 | -28 | -64.68 | 2313.704 | L19-28 | 1735.278 | 347.0556 | 520.5834 | 520.5834 | 1301.4585 | 2689.6809 | L7-18L19-29
L7-18
| A-4107-5 | B2 to G.F | ST-09 | 1 | 18.6 | 14.17 | 263.562 | 1.1 | 2.1 | -3 | -6.93 | 256.632 |  | 256.632 | 51.3264 | 76.9896 | 76.9896 | 51.3264 | 256.632
| A-4107-5 | B2 to G.F | ST-10 | 1 | 18.6 | 9.9 | 184.14 | 1.1 | 2.1 | -2 | -4.62 | 179.52 |  | 179.52 | 35.904 | 53.856 | 53.856 | 35.904 | 179.52
VO-16a/1 |  | Skim Coat Paint -Staircase Wall | [10 empty] | 16 | 10112.9101 | [5 empty] | 161806.5622
VO-16a/2 |  | Paint to Staircase wall | [10 empty] | 16 | [5 empty] | 10155.9821 | 162495.7133
| VO-16A Total Amount | [18 empty] | 324302.2755

## V.70 (hidden)
v | PROJECT |  |  | Dorchestor Hotel & Residence
v | CONTRACTOR |  |  | KHANSAHEB CIVIL ENGINEERING LLC
v | SUB CONTRACTOR |  |  | AL RAWDA GEN. MAINTANANCE & DECORATION CO. LLC
v | SUBJECT |  |  | PAINTING WORKS
VO.70 | Water meter room Shaft wall at G.F to 31 Residential
Quantity
SN | DWG .NO | BLG | Level | Room | No. | Length | Height / Width | Total | 1side board | final | Total | Remarks | WIR
[9 empty] | 60% | 40%
1 | Supply and Installation of Shaft Wall
| AR-CI-SD-ML-61038_01 | Res | 1 | Water meter room | 1 | 1.63 | 5.53 | 9.0139 | 5.4083 | 3.6056 | 6.3097 | 70%
| AR-CI-SD-ML-61038_01 | Res | 2 | Water meter room | 1 | 1.63 | 3.45 | 5.6235 | 3.3741 | 2.2494 | 3.9364 | 70%
| AR-CI-SD-ML-61038_01 | Res | 3 | Water meter room | 1 | 1.63 | 4.15 | 6.7645 |  |  | 0
| AR-CI-SD-ML-61038_01 | Res | 4 | Water meter room | 1 | 1.63 | 4.15 | 6.7645 | 4.0587 | 2.7058 | 4.7351 | 70%
| AR-CI-SD-ML-61038_01 | Res | 5 | Water meter room | 1 | 1.63 | 6.35 | 10.3505
| AR-CI-SD-ML-61038_01 | Res | 6 | Water meter room | 1 | 1.63 | 3.45 | 5.6235 | 3.3741 | 2.2494 | 5.0612 | 90% | ML-01675
| AR-CI-SD-ML-61038_01 | Res | 7 | Water meter room | 1 | 1.63 | 3.45 | 5.6235 | 3.3741 | 2.2494 | 5.0612 | 90% | ML-01675
| AR-CI-SD-ML-61038_01 | Res | 8 | Water meter room | 1 | 1.63 | 3.45 | 5.6235
| AR-CI-SD-ML-61038_01 | Res | 9 | Water meter room | 1 | 1.63 | 3.45 | 5.6235 | 3.3741 | 2.2494 | 5.0612 | 90% | ML-01675
| AR-CI-SD-ML-61038_01 | Res | 10 | Water meter room | 1 | 1.63 | 3.37 | 5.4931 | 3.2959 | 2.1972 | 4.9438 | 90% | ML-01675
| AR-CI-SD-ML-61038_01 | Res | 11 | Water meter room | 1 | 1.63 | 3.37 | 5.4931 | 3.2959 | 2.1972 | 4.9438 | 90% | ML-01675
| AR-CI-SD-ML-61038_01 | Res | 12 | Water meter room | 1 | 1.63 | 3.37 | 5.4931 | 3.2959 | 2.1972 | 4.9438 | 90% | ML-01676
| AR-CI-SD-ML-61038_01 | Res | 13 | Water meter room | 1 | 1.63 | 3.37 | 5.4931 | 3.2959 | 2.1972 | 4.9438 | 90% | ML-01676
| AR-CI-SD-ML-61038_01 | Res | 14 | Water meter room | 1 | 1.63 | 3.37 | 5.4931 | 3.2959 | 2.1972 | 4.9438 | 90% | ML-01676
| AR-CI-SD-ML-61038_01 | Res | 15 | Water meter room | 1 | 1.63 | 3.37 | 5.4931 | 3.2959 | 2.1972 | 4.9438 | 90% | ML-01677_
| AR-CI-SD-ML-61038_01 | Res | 16 | Water meter room | 1 | 1.63 | 3.55 | 5.7865 | 3.4719 | 2.3146 | 5.2079 | 90% | ML-01677_
| AR-CI-SD-ML-61038_01 | Res | 17 | Water meter room | 1 | 1.63 | 3.55 | 5.7865 | 3.4719 | 2.3146 | 5.2079 | 90% | ML-01677_
| AR-CI-SD-ML-61038_01 | Res | 18 | Water meter room | 1 | 1.63 | 3.5 | 5.705 | 3.423 | 2.282 | 5.1345 | 90% | ML-01677_
| AR-CI-SD-ML-61038_01 | Res | 19 to 21 | Water meter room | 3 | 1.63 | 3.45 | 16.8705 | 10.1223 | 6.7482 | 15.1835 | 90% | ML-01678_
| AR-CI-SD-ML-61038_01 | Res | 22 | Water meter room | 1 | 1.63 | 3.55 | 5.7865 | 3.4719 | 2.3146 | 5.2079 | 90% | L22-01692_
| AR-CI-SD-ML-61038_01 | Res | 23 | Water meter room | 1 | 1.63 | 5.7 | 9.291 | 5.5746 | 3.7164 | 8.3619 | 90% | ML-01676
| AR-CI-SD-ML-61038_01 | Res | 24 | Water meter room | 1 | 1.63 | 4.95 | 8.0685 | 4.8411 | 3.2274 | 7.2617 | 90% | ML-01691
| AR-CI-SD-ML-61038_01 | Res | 25 to 28 | Water meter room | 4 | 1.63 | 4.3 | 28.036 | 16.8216 | 11.2144 | 25.2324 | 90% | ML-01691
| AR-CI-SD-ML-61038_01 | Res | 29 | Water meter room | 1 | 1.63 | 4.95 | 8.0685 | 4.8411 | 3.2274 | 7.2617 | 90% | ML-01691
| AR-CI-SD-ML-61038_01 | Res | 30 | Water meter room | 1 | 1.63 | 4.3 | 7.009 | 4.2054 | 2.8036 | 6.3081 | 90% | ML-01691
| AR-CI-SD-ML-61038_01 | Res | 31 | Water meter room | 1 | 1.63 | 6.2 | 10.106
[9 empty] | rate | 290 | 150.1947 | 43556.4688 | 49775.31
2 | 600 x600 mm Gypsum tiles
| AR-CI-SD-ML-61038_01 | Res | G.F | Water meter room | 1 | 1.63 | 1.03 | 1.6789 | 1.0073 | 0.67156 | 1.1752 | 70%
| AR-CI-SD-ML-61038_01 | Res | 2 to 3 | Water meter room | 1 | 1.63 | 1.03 | 1.6789 | 1.0073 | 0.67156 | 1.1752 | 70%
| AR-CI-SD-ML-61038_01 | Res | 4 | Water meter room | 1 | 1.63 | 1.03 | 1.6789 | 1.0073 | 0.67156 | 1.1752 | 70%
| AR-CI-SD-ML-61038_01 | Res | 5 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 6 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 7 to 9 | Water meter room | 3 | 1.63 | 1.03 | 5.0367
| AR-CI-SD-ML-61038_01 | Res | 10 to 15 | Water meter room | 6 | 1.63 | 1.03 | 10.0734
| AR-CI-SD-ML-61038_01 | Res | 16 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 17 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 18 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 19 to 21 | Water meter room | 3 | 1.63 | 1.03 | 5.0367
| AR-CI-SD-ML-61038_01 | Res | 22 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 23 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 24 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 25 to 28 | Water meter room | 3 | 1.63 | 1.03 | 5.0367 | 3.022 |  | 1.511 | 50%
| AR-CI-SD-ML-61038_01 | Res | 29 | Water meter room | 1 | 1.63 | 1.03 | 1.6789 | 1.0073 |  | 0.50367 | 50%
| AR-CI-SD-ML-61038_01 | Res | 30 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
| AR-CI-SD-ML-61038_01 | Res | 31 | Water meter room | 1 | 1.63 | 1.03 | 1.6789
[10 empty] | 90 | 5.5404 | 498.6333
815.9454
44058.2021
Note on M11: Himal Kosala: No WIR for board
Note on M12: Himal Kosala: No WIR for board
Note on M14: Himal Kosala: No WIR for board
Note on M16: Himal Kosala: No WIR for final paint approval
Note on M17: Himal Kosala: No WIR for final paint approval
Note on M19: Himal Kosala: No WIR for final paint approval
Note on M20: Himal Kosala: No WIR for final paint approval
Note on M21: Himal Kosala: No WIR for final paint approval
Note on M22: Himal Kosala: No WIR for final paint approval
Note on M23: Himal Kosala: No WIR for final paint approval
Note on M24: Himal Kosala: No WIR for final paint approval
Note on M25: Himal Kosala: No WIR for final paint approval
Note on M26: Himal Kosala: No WIR for final paint approval
Note on M27: Himal Kosala: No WIR for final paint approval
Note on M28: Himal Kosala: No WIR for final paint approval
Note on M29: Himal Kosala: No WIR for final paint approval
Note on M30: Himal Kosala: No WIR for final paint approval
Note on M31: Himal Kosala: No WIR for final paint approval
Note on M32: Himal Kosala: No WIR for final paint approval
Note on M33: Himal Kosala: No WIR for final paint approval
Note on M34: Himal Kosala: No WIR for final paint approval
Note on M35: Himal Kosala: No WIR for final paint approval
Note on M42: Himal Kosala: No WIR for board
Note on M43: Himal Kosala: No WIR for board
Note on M44: Himal Kosala: No WIR for board
Note on M56: Himal Kosala: No WIR for board
Note on M57: Himal Kosala: No WIR for board

## Valuation (hidden)
DORCHESTER COLLECTION HOTEL & RESIDENCES (PLOT 18) |  |  |  |  | 2022-05-05
VALUATION OF REMAINING SUBCONTRACT WORKS |  |  |  |  | Ver. 2
Trade Package: | Partitions and Ceilings
Subcontractor: | Al Rawda General Maint. & Decoration Co. L.L.C.
Subcontract Ref: | 17001DH/SCA/D&B/40-4-5-ALRAWDA
17001DH/SCA/B/20-1-1-ALRAWDA
ORIGINAL SUBCONTRACT WORKS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
A | External cement sheet soffits | 2458680 | 79% | 1942357 | 516323
B | External coffered ceilings | 249750 | 38% | 94905 | 154845
C | External dry wall partitions | 450000 | 100% | 450000 | 0
D | Bulkheads and shadow gaps | 322285 | 73% | 235268 | 87017
E | BOH painting | 1416921 | 70% | 991845 | 425076
Sub-Totals |  | 4897636 | 75.84% | 3714375 | 1183261
VARIATIONS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| Guest room ceilings | 1287184 | 98.64% | 1269655 | 17529
| Guest room partitions | 2362610 | 100% | 2362610 | 0
| Guest room wall panels | 4451650 | 99.33% | 4421842 | 29808
| Internal painting | 626689 | 90.15% | 564936 | 61753
| External painting | 712504 | 80% | 570003 | 142501
| Corridor ceilings | 806420 | 77% | 620940 | 185480
| BOH painting to basement and staircases | 211500 | 88.99% | 188210 | 23290
| Gypsum shaft wall system to hotel tower L7-10 | 226200 | 100% | 226200 | 0
| Gypsum shaft wall system to hotel tower L11, L14 | 106494 | 100% | 106494 | 0
| Gypsum shaft wall system to hotel tower service areas L1 to roof | 211831 | 0% | 0 | 211831
| Gypsum demise wall system to hotel tower L11, L14 | 114342 | 100% | 114342 | 0
| Rockwool insulation above external soffits | 299390 | 66.8% | 200000 | 99390
| Temporary partitions and ceilings to site offices | 73000 | 100% | 73000 | 0
| Partitions and ceilings to sales suite corridor | 42684 | 100% | 42684 | 0
| Partitions and ceilings to guest room type 15A | 27505 | 100% | 27505 | 0
| Changes to ceilings to guest room types 7A, 15A | 16720 | 100% | 16720 | 0
| Wall preparation for wall paper | 73606 | 100% | 73606 | 0
Sub-Totals |  | 11650329 | 93.38% | 10878747 | 771582
MATERIALS ON SITE |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| None | 0 |  | 0 | 0
Sub-Totals |  | 0 |  | 0 | 0
Totals |  | 16547965 | 88.19% | 14593122 | 1954843
NOTES |  | NEW SUBCONTRACT
|  | Value of Remaining Subcontract Works |  |  | 1183261
1) The amount included at "Payments to Date" is subject to final validation by the Employer's Representative. The Subcontractor shall provide evidence substantiating the amount paid to date under the previous subcontract. 2) Payment of amounts due under the previous RPJV subcontract (including retention) will be made pursuant to the terms of the WFA between the Employer and the Subcontractor. 3) The subcontract shall provide security for its performance of the Subcontract Works in the amount of AED 1,654,797.00 in the form of an unconditional and irrevocable bank guarantee for the benefit of the Employer. |  | Value of Remaining Variation Works |  |  | 771582
|  | Less Value of Materials on Site at 28-Feb-22 |  |  | 0
|  | New Subcontract Price |  |  | 1954843
WORKS COMPLETED TO 28-FEB-22
|  | Value of Completed Subcontract Works |  |  | 3714375
|  | Value of Completed Variation Works |  |  | 10878747
|  | Value of Materials on Site at 28-Feb-22 |  |  | 0
|  | Value of Works Completed to 28-Feb-22 |  |  | 14593122
|  | Less Retention to 28-Feb-22 (10%) |  |  | -1459312.2
|  | Less Payments to Date (incl. Advance Payment) |  |  | -10980036
|  | Outstanding amount for Works Completed to 28-Feb-22 |  |  | 2153773.8
All amounts exclude VAT