## SUMMARY
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS | [7 empty] | 2023-01-01
SUMMARY | [7 empty] | KCE PC 12
No. | Description | Contract Amount | Work Done Under RPJV | New Subcontract Amount | WORK DONE UNDER KCE
[5 empty] | Previous | This Month | Cumulative - KCE
1 | Irrigation System | 1196825 | 563395 | 633430 | 523120.786 | 32293.577 | 87.68% | 555414.363 | 523120.786
2 | Landscape Area Pavers (Hardscape) | 558972 | 195640 | 363332 | 422483.9296 | 0 | 116.3% | 422483.9296 | 422483.9296
3 | Tree Anchoring | 0 | 0 | 0 |  | 0 | #DIV/0!
4 | Softscape | 4593498 | 1923038 | 2670460 | 978594.0612 | 108627.0296 | 40.71% | 1087221.0908 | 978594.0612
Deduction
5 | Advance Recovery for Material off Site |  | 1923038.44 | 576910.96 | 0 | 50881.0064 | 8.82% | 50881.0064
| TOTAL | 6349295 | 2682073 | 3667222 | 1924198.7768 | 90039.6002 | 54.93% | 2014238.377 | 1924198.7768
1890383.0379
33815.7389

## Irrigation
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE WORKS - IRRIGATION
FIONA ENVIRONS - PROGRESS
Item | Description | Qty. | Unit | Rate | Contract | Valuation | New Contract | Previous |  | Current Cumilative |  | This Month | This
[5 empty] | Amount-AED | WFA | Amount-AED | % | Amount | % | Amount | % | Amount
Irrigation tank and pump
A | GRP Tank | 1 | LS | 77750 | 77750 | 0 | 77750 | 100% | 77750 | 100% | 77750 | 0% | 0
B | Irrigation Pumps | 1 | LS | 125000 | 125000 | 0 | 125000 | 100% | 125000 | 100% | 125000 | 0% | 0
C | Sensors, Cabling, Valves | 1 | LS | 55501.54 | 55501.54 | 0 | 55501.54 | 90% | 49951.386 | 95% | 52726.463 | 5% | 2775.077
D | Design Fees | 1 | LS | 60273.46 | 60273.46 | 0 | 60273.46 | 100% | 60273.46 | 100% | 60273.46 | 0% | 0
| Irrigation network |  |  |  |  | 0 | 0
E | Delivery mains & submains | 1 | LS | 148000 | 148000 | 131234.56 | 16765.44 | 100% | 16765.44 | 100% | 16765.44 | 0% | 0
F | Electrical wire network | 1 | LS | 127400 |  | 0 | 0
| 1. Cable & Conduiting | 50% |  |  | 63700 | 47775 | 15925 | 100% | 15925 | 100% | 15925 | 0% | 0
| 2. Modules & Accessories | 30% |  |  | 38220 | 0 | 38220 | 30% | 11466 | 100% | 38220 | 70% | 26754
| 3. Software and Programming | 20% |  |  | 25480 | 0 | 25480 | 0% | 0 | 0% | 0 | 0% | 0
| Irrigation secondary network |  |  | 552900 |  | 0 | 0
G | Solenoid Valve | 10% | LS | 55290 | 55290 | 0 | 55290 | 85% | 46996.5 | 90% | 49761 | 5% | 2764.5
H | PVC Piping | 65% | LS | 359385 | 359385 | 359385 | 0 | 0% | 0 | 100% | 0 |  | 0
I | Dripline | 15% | LS | 82935 | 82935 | 0 | 82935 | 70% | 58054.5 | 70% | 58054.5 | 0% | 0
J | Drippers | 10% | LS | 55290 | 55290 | 0 | 55290 | 65% | 35938.5 | 65% | 35938.5 | 0% | 0
| Engineering and shop drawings |  |  |  |  | 0 | 0
K | Drawings | 1 | LS | 50000 | 50000 | 25000 | 25000 | 100% | 25000 | 100% | 25000 | 0% | 0
0
| Total |  |  |  | 1196825 | 563394.56 | 633430 |  | 523120.786 |  | 555414.363 |  | 32293.577
562914.36
7499.997

## Softscape
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS
SOFTSCAPE PACKAGE
Sr. No. | Scope | Original Value | Work Done Under RPJV | New Subcontract Amount | Previous | This Month | Cumulative
01 | Excavation and disposal at ground level | 27000 | 0 | 27000 | 0 | 0 | 0
02 | Sweet soil | 212640 | 0 | 212640 | 175501.3585 | 10389.8495 | 185891.208
03 | Palms, trees | 2969061 | 1929889.65 | 1039171.35 | 0 | 68343 | 68343
04 | Ground covers, grasses, climbers, shrubs, accent plants | 877015 | 570059.75 | 306955.25 | 0 | 9935.4714 | 9935.4714
05 | Maintenance (pre-completion) | 45000 | 0 | 45000 | 0 | 0 | 0
06 | Maintenance (DNP) | 180000 | 0 | 180000 | 0 | 0 | 0
07 | Drainage and geotextile | 282782 | 0 | 282782 | 226181.7427 | 19958.7087 | 246140.4514
08 | Unpaid MOS for Plants |  | -576910.96 | 576910.96 | 576910.96 | 0 | 576910.96
Variation
| Installation of tree anchoring system | 96330 | 0 | 96330 | 0 | 2671.5 | 2671.5
| TOTAL | 4593498 | 1923038.44 | 2670460 | 978594.0612 | 108627.0296 | 1087221.0908

## Irrigation System (hidden)
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS |  |  |  |  | 2023-01-01
IRRIGATION PACKAGE BREAKDOWN |  |  |  |  | KCE PC 12
SN | Item | Breakdown |  | % | Work Done
01 | GRP Tank | 77750 |  | 0% | 0
02 | Pumps | 125000 |  | 0% | 0
03 | Sensors, cabling | 55501.54 |  | 0% | 0
04 | Valves
05 | Dosing system
06 | Design Fees | 60273.46
| Irrigation tank and pump |  | 318525
07 | Dilivery main submain | 148000 |  | 90% | 133200
08 | Electrical wire network | 127400 |  | 50% | 63700
| Irrigation network |  | 275400
09 | Solenoid Valve | 552900 | 82935 |  | 0
10 | PVC Piping |  | 248805 | 95% | 236364.75
11 | Dripline |  | 82935 |  | 0
12 | Drippers |  | 138225 |  | 0
| Irrigation secondary network |  | 552900
13 | Drawings | 50000 | 50000 | 95% | 47500
| Engineering and shop drawings |  | 50000
| TOTAL | 1196825 | 1196825 | 40.17% | 480764.75
GRP Water Tank with internal partition 5m2x3mh=(135m3) 7mx6.5x3m)
Concrete Foundation (reinforced) 8 nO. 0.5x0.5x6.5m
Steel Channel frame 7mx100mm-channel x 6 No.
Tank Vent with insect screen - dia 2mm
Access Cover (lockable) 600x600mm
Inlet / out connections - dia3mm
Outlet - dia 3mm drain with 40mm isolation valve
Pipe & fitting dia-4m2 for pump suction
Filling line inlet 3 mm dia with motorized ball valve (back up)
Level Sensors and cabling only

## Hardscape
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS
IRRIGATION AND HARDSCAPE PACKAGES
Sr. No. | Scope | Original Value | Work Done Under RPJV | New Subcontract Amount | Previous | This Month | % | Cumulative
05 | Installation of concrete pavers (incl. grouting) | 558972 | 195640 | 363332 | 422483.9296 | 0 | 83.2% | 422483.9296
| TOTAL | 558972 | 195640 | 363332 | 422483.9296 | 0 |  | 422483.9296
464526.17
42042.2404

## Irrigation System Breakdown
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS
IRRIGATION PACKAGE - PROGRESS
Item | Description | Qty. | Unit | Rate | Amount | B1 | G.F | L-02 | L-04 | L-09 | L-10 | L-17 | L-23 | L-24 | L-25 | L-26 | L-27 | L-29 | L-30 | Progress % | Work Done
(Dhs.)
A | GRP Tank | 1 | LS | 77750 | 77750 | [14 empty] | 100% | 77750
B | Irrigation Pumps | 1 | LS | 125000 | 125000 | [14 empty] | 100% | 125000
C | Sensors, Cabling, Valves | 1 | LS | 55501.54 | 55501.54 | [14 empty] | 95% | 52726.463
D | Design Fees | 1 | LS | 60273.46 | 60273.46 | [14 empty] | 100% | 60273.46
E | Delivery mains & submains | 1 | LS | 148000 | 148000 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 148000
F | Electrical wire network | 1 | LS | 127400
| 1. Cable & Conduiting | 50% |  |  | 63700 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 63700
| 2. Modules & Accessories | 30% |  |  | 38220 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 38220
| 3. Software and Programming | 20% |  |  | 25480 | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0% | 0
G | Solenoid Valve | 1 | LS | 82935 | 55290 | [14 empty] | 90% | 49761
H | PVC Piping | 1 | LS | 248805 | 359385 | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 100% | 359385
I | Dripline | 1 | LS | 82935 | 82935 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 70% | 58054.5
J | Drippers | 1 | LS | 138225 | 55290 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 65% | 35938.5
K | Drawings | 1 | LS | 50000 | 50000 | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | 100% | 50000
1118808.923
| To Collection Dhs. |  |  |  | 1196825
78016.077

## Softscape Progress
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS
SOFTSCAPE PACKAGE - PROGRESS
S No | DESCRIPTION OF WORK | UNIT | QTY | SUPPLY RATE | SUPPLY COST | INSTALL RATE | INSTALL COST | COMPOSITE RATE | TOTAL BOQ AMOUNT | MATERIAL OFFSITE (65%) | KHANSAHEB | Previous | This Month |  | Cumulative
| SOIL, TREES, PALM & SHRUBS | [10 empty] | Amount | Amount | % | Amount
GROUND LEVEL
A | Planting engineered soil | m3 | 1548 | Not Priced
B | Sweet soil | m3 | 1548 | 45 | 69660 | 15 | 23220 | 60 | 92880 | 0 | 92880 | 87920.208 | 0 | 94.66% | 87920.208
| PALMS | [9 empty] | 0 |  | 0
C | Acoelorraphe wrightii (multi-stemmed), 1.0m Clear Trunk, 100-150 mm Caliper,2.0-3.0m Over All Heigh and 1.50 to 2 m Supply Spread (Replaced with Pitchadia Palm) | Nos | 10 | 1710 | 17100 | 300 | 3000 | 2010 | 20100 | 13065 | 7035 |  | 6030 | 30% | 6030
D | Butia capitata, 2m CT, 250-300mm Caliper, 3-4 m OAH & 2.50m-3m SS | Nos | 66 | 2160 | 142560 | 300 | 19800 | 2460 | 162360 | 105534 | 56826 |  | 8118 | 5% | 8118
E | Chamaerops humilis 'Vulcano - minimum 5 Trunks, 1-1.5 m CT,150-200 mm Caliper, 2-3 m OAH ad 1.50 -2 m SS (PC Rate at AED 1,611.21) | Nos | 4 | 3360 | 13440 | 300 | 1200 | 3660 | 14640 | 9516 | 5124 |  | 2928 | 20% | 2928
F | Livistona chinensis, 0.5-0.75m CT,250-300 mm Caliper, 2.0-3.0m OAH and 1.50 to 2 m SS | Nos | 31 | 1080 | 33480 | 300 | 9300 | 1380 | 42780 | 27807 | 14973 |  | 0
G | Trachycarpus fortunei, 1.0m CT,100-150 mm Caliper, 1.5-2.0m OAH,and 1.0 - 1.5 m SS | Nos | 6 | 1980 | 11880 | 300 | 1800 | 2280 | 13680 | 8892 | 4788 |  | 3420 | 25% | 3420
H | Washingtonia robusta 3-4m CT 350-400mm Cal,4- 5m OAH, 2.50-3m SS | Nos | 22 | 3960 | 87120 | 300 | 6600 | 4260 | 93720 | 60918 | 32802 |  | 0
| PALM MIXES | [8 empty] | 0 | 0 |  | 0
| PALMS MIX 1 | [9 empty] | 0 |  | 0
J | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT, 150-200 mm Caliper,2.0-3.0 m OAH and 1.50 -2 m SS (PC Rate at AED1,500) | Nos | 33 | 2880 | 95040 | 300 | 9900 | 3180 | 104940 | 68211 | 36729 |  | 20988 | 20% | 20988
K | Cycas revoluta, 0.5-0.6m CT 200-300mm Cal, 1-1.5m OAH 0.80m-1m SS | Nos | 52 | 990 | 51480 | 300 | 15600 | 1290 | 67080 | 43602 | 23478 |  | 6708 | 10% | 6708
| PALMS MIX 2 | [9 empty] | 0 |  | 0
L | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150 - 200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED1,500) | Nos | 43 | 2880 | 123840 | 300 | 12900 | 3180 | 136740 | 88881 | 47859 |  | 0
M | Ravenala madagascariensis (Travellers Palm),0.25 m CT,300 - 400 mm Caliper, 2.5-3.0m OAH, supply spread 1.50 - 2 m | Nos | 43 | 2880 | 123840 | 300 | 12900 | 3180 | 136740 | 88881 | 47859 |  | 6837 | 5% | 6837
N | Pritchardia pacifica, 1m CT 100-150mm Cal, 1.5-2.0m OAH & 1-1.5m SS | Nos | 43 | 1710 | 73530 | 300 | 12900 | 2010 | 86430 | 56179.5 | 30250.5 |  | 4321.5 | 5% | 4321.5
| GROUNDCOVERS | [9 empty] | 0 |  | 0
P | Alternanthera amoena, 0.1-0.2m OAH and 0.1 - 0.2 m SS | m2 | 1088 | 8 | 8704 | 50 | 54400 | 58 | 63104 | 41017.6 | 22086.4 |  | 0
Q | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | Nos | 21 | 21.6 | 453.6 | 25 | 525 | 46.6 | 978.6 | 636.09 | 342.51 |  | 0
R | Carissa macrocarpa 'Green Carpet' Natal Plum 0.2-0.3m OAH 0.2-0.3m SS | m2 | 179.33 | 28.8 | 5164.704 | 50 | 8966.5 | 78.8 | 14131.204 | 9185.2826 | 4945.9214 |  | 4945.9214 | 35% | 4945.9214
S | Ficus microcarpa 'Green Island' Dwarf ficus 0.3-0.4m OAH & 0.3-0.4m SS | m2 | 274.89 | 32.4 | 8906.436 | 50 | 13744.5 | 82.4 | 22650.936 | 14723.1084 | 7927.8276 |  | 3397.6404 | 15% | 3397.6404
A | Hymenocallis littoralis Beach Spiderlily 0.3-0.4m OAH and 0.3-0.4m SS | m2 | 116.75 | 21.6 | 2521.8 | 50 | 5837.5 | 71.6 | 8359.3 | 5433.545 | 2925.755 |  | 0
| GRASSES | [9 empty] | 0 |  | 0
B | Cyperus alternifolius, 0.5-0.6m OAH and 0.30 - 0.40 m SS | m2 | 213.26 | 18 | 3838.68 | 50 | 10663 | 68 | 14501.68 | 9426.092 | 5075.588 |  | 0
| CLIMBERS | [9 empty] | 0 |  | 0
C | Bougainvillea spectabilis 0.80 - 1 m OAH and 0.30 - 0.4 m SS | No | 11 | 27 | 297 | 25 | 275 | 52 | 572 | 371.8 | 200.2 |  | 0
D | Quisqualis indica white flower Rangoon creeper 1-1.5m OAH 0.5-0.6m SS | No | 13 | 32.4 | 421.2 | 25 | 325 | 57.4 | 746.2 | 485.03 | 261.17 |  | 0
| PALMS | [9 empty] | 0 |  | 0
F | Acoelorraphe wrightii (multi-stemmed), 1.0m CT, 100 -150 mm Caliper,2.0-3.0m OAH and 1.50 - 2 m SS (Replaced with Pitchadia Palm) | Nos | 3 | 1710 | 5130 | 300 | 900 | 2010 | 6030 | 3919.5 | 2110.5 |  | 2110.5 | 35% | 2110.5
G | Butia capitata, 2m CT, 250-300mm Caliper,3-4 m OAH & 2.50-3m SS | Nos | 5 | 2160 | 10800 | 300 | 1500 | 2460 | 12300 | 7995 | 4305 |  | 0
H | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150 -200 mm Caliper, 2.0-3.0m OAH and 1.5 - 2 m SS (PC Rate at AED 1,524.12) | Nos | 3 | 2880 | 8640 | 300 | 900 | 3180 | 9540 | 6201 | 3339 |  | 3339 | 35% | 3339
J | Livistona chinensis, 0.5-0.75m CT 250-300mm Cal, 2-3m OAH 1.50-2m SS | Nos | 4 | 1080 | 4320 | 300 | 1200 | 1380 | 5520 | 3588 | 1932 |  | 0
K | Trachycarpus fortunei 1m CT,100-150mm Cal 1.5-2.0m OAH 1-1.50m SS | Nos | 9 | 1980 | 17820 | 300 | 2700 | 2280 | 20520 | 13338 | 7182 |  | 2052 | 10% | 2052
L | Washingtonia robusta, 3-4m CT,350-400mm Cal 4-4.50m OAH 2.5-3m SS | Nos | 7 | 3960 | 27720 | 300 | 2100 | 4260 | 29820 | 19383 | 10437 |  | 1491 | 5% | 1491
| SHRUBS MIX 1 | [9 empty] | 0 |  | 0
M | Crinum asiaticum (Giant Spider Lily), o/a Ht 0.4-0.5m, SS 0.2-0.3m. | Nos | 79 | 10.8 | 853.2 | 25 | 1975 | 35.8 | 2828.2 | 1838.33 | 989.87 |  | 0
N | Cycas revoluta, 0.5-0.6m CT, 200-300mm Cal.0-1.5m OAH & 0.80-1m SS | Nos | 7 | 990 | 6930 | 300 | 2100 | 1290 | 9030 | 5869.5 | 3160.5 |  | 0
P | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 79 | 117 | 9243 | 50 | 3950 | 167 | 13193 | 8575.45 | 4617.55 |  | 0
Q | Asparagus densiflorous Meyersii, 0.2-0.3m OAH and 0.20-0.3 m SS | m2 | 19.66 | 32.4 | 636.984 | 50 | 983 | 82.4 | 1619.984 | 1052.9896 | 566.9944 |  | 323.9968 | 20% | 323.9968
R | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | m2 | 19.66 | 28.8 | 566.208 | 50 | 983 | 78.8 | 1549.208 | 1006.9852 | 542.2228 |  | 542.2228 | 35% | 542.2228
A | Hymenocallis littoralis Beach Spiderlily 0.3-0.4m OAH and 0.3-0.4m SS | m2 | 19.66 | 21.6 | 424.656 | 50 | 983 | 71.6 | 1407.656 | 914.9764 | 492.6796 |  | 0
| SHRUBS MIX 2 | [9 empty] | 0 |  | 0
B | Crinum asiaticum (Giant Spider Lily), o/a height 0.4-0.5m, SS 0.2-0.3m. | Nos | 11 | 10.8 | 118.8 | 25 | 275 | 35.8 | 393.8 | 255.97 | 137.83 |  | 0
C | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 11 | 117 | 1287 | 50 | 550 | 167 | 1837 | 1194.05 | 642.95 |  | 642.95 | 35% | 642.95
D | Asparagus densiflorous Meyersii, 0.2-0.3m OAH and 0.20 - 0.3 m SS | m2 | 3 | 32.4 | 97.2 | 50 | 150 | 82.4 | 247.2 | 160.68 | 86.52 |  | 0
E | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | m2 | 3 | 28.8 | 86.4 | 50 | 150 | 78.8 | 236.4 | 153.66 | 82.74 |  | 82.74 | 35% | 82.74
| LEVEL 2 | [11 empty] | 0
A | Planting engineered soil | m3 | 619 | Not priced | [6 empty] | 0 |  | 0
B | Sweet soil | m3 | 619 | 45 | 27855 | 15 | 9285 | 60 | 37140 |  | 37140 | 37140 | 0 | 100% | 37140
| PALMS | [9 empty] | 0 |  | 0
C | Acoelorraphe wrightii (multi-stemmed), 1.0m CT,100-150 mm caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (Replaced by Pitchadia Palm) | Nos | 9 | 1710 | 15390 | 300 | 2700 | 2010 | 18090 | 11758.5 | 6331.5 |  | 0
D | Copernicia alba, 1.5m CT, 200-250mm Cal,2.5-3.5m OAH 1-1.50m SS | Nos | 34 | 4500 | 153000 | 300 | 10200 | 4800 | 163200 | 106080 | 57120 |  | 0
E | Chamaerops humilis 'Vulcano' 1-1.50 m CT,150-200 mm Caliper, 2.0-3.0 m OAH and 1.50 - 2 m SS (PC Rate at AED 1,081.62) | Nos | 30 | 2880 | 86400 | 300 | 9000 | 3180 | 95400 | 62010 | 33390 |  | 0
F | Livistona chinensis, 0.5-0.75m CT 250-300mm Cal, 2-3m OAH 1.50-2m SS | Nos | 10 | 1080 | 10800 | 300 | 3000 | 1380 | 13800 | 8970 | 4830 |  | 0
G | Phoenix rebelenii,0.5 0.75 m CT,150-200 mm caliper, and 2-3 m OAH and 1.50 - 2 m SS | Nos | 16 | 504 | 8064 | 300 | 4800 | 804 | 12864 | 8361.6 | 4502.4 |  | 0
H | Rhapis excelsa (Min. 8 trunks),1-1.50 m CT,50-100 mm caliper,2-2.5 m OAH and 1-1.50 m SS | Nos | 7 | 252 | 1764 | 100 | 700 | 352 | 2464 | 1601.6 | 862.4 |  | 0
J | Trachycarpus fortunei 1.0m CT,100-150mm Cal 1.5-2.0m OAH 1-1.50m SS | Nos | 29 | 1980 | 57420 | 300 | 8700 | 2280 | 66120 | 42978 | 23142 |  | 0
K | Washingtonia robusta, 2.0-3.0m CT,300-350 mm Caliper, 3.0-4.0m OAH and 1.50 - 2 m SS | Nos | 18 | 2700 | 48600 | 300 | 5400 | 3000 | 54000 | 35100 | 18900 |  | 0
L | Washingtonia robusta (Medium), 1.5-2.0m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.50 - 2 m SS | Nos | 12 | 1800 | 21600 | 300 | 3600 | 2100 | 25200 | 16380 | 8820 |  | 0
| PALM MIXES | [9 empty] | 0 |  | 0
| PALMS MIX 1 | [9 empty] | 0 |  | 0
M | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150-200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED 1,500) | Nos | 41 | 2880 | 118080 | 300 | 12300 | 3180 | 130380 | 84747 | 45633 |  | 0
N | Cycas revoluta, 0.5-0.6m CT, 200-300mm Cal 1.0-1.5m OAH 0.80-1m SS | Nos | 53 | 990 | 52470 | 300 | 15900 | 1290 | 68370 | 44440.5 | 23929.5 |  | 0
| PALMS MIX 2 | [9 empty] | 0 |  | 0
P | Chamaerops humilis (Min. 3 trunks), 1.0-1.5mCT,150-200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED 1,500) | Nos | 7 | 2880 | 20160 | 300 | 2100 | 3180 | 22260 | 14469 | 7791 |  | 0
Q | Ravenala madagascariensis,0.25 m CT,300-400 mm Caliper, 2.5-3 m OAH and 1.50 - 2 m SS | Nos | 7 | 2880 | 20160 | 300 | 2100 | 3180 | 22260 | 14469 | 7791 |  | 0
R | Pritchardia pacifica, 1m CT, 100-150mm Cal,1.5-2.0m OAH & 1-1.50m SS | Nos | 7 | 1710 | 11970 | 300 | 2100 | 2010 | 14070 | 9145.5 | 4924.5 |  | 0
| GROUNDCOVERS | [5 empty] | 0 |  | 0 |  | 0 |  | 0
A | Alternanthera amoena, 0.1-0.2m OAH and 0.1 - 0.2 m SS | m2 | 163 | 8 | 1304 | 50 | 8150 | 58 | 9454 | 6145.1 | 3308.9 |  | 0
B | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | m2 | 23 | 86.4 | 1987.2 | 50 | 1150 | 136.4 | 3137.2 | 2039.18 | 1098.02 |  | 0
C | Carissa macrocarpa 'Boxwood Beauty', 0.15-0.2m OAH & 0.15 -0.2 m SS | m2 | 126 | 28.8 | 3628.8 | 50 | 6300 | 78.8 | 9928.8 | 6453.72 | 3475.08 |  | 0
D | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH, 0.2-0.3m SS | m2 | 31 | 28.8 | 892.8 | 50 | 1550 | 78.8 | 2442.8 | 1587.82 | 854.98 |  | 0
E | Hymenocallis littoralisBeach Spiderlily 0.3-0.4m OAH, 0.3-0.4m SS | m2 | 199 | 21.6 | 4298.4 | 50 | 9950 | 71.6 | 14248.4 | 9261.46 | 4986.94 |  | 0
| GRASSES | [9 empty] | 0 |  | 0
F | Cyperus alternifolius, 0.5-0.6m OAH and 0.3 -0.4 m SS | m2 | 107.31 | 18 | 1931.58 | 50 | 5365.5 | 68 | 7297.08 | 4743.102 | 2553.978 |  | 0
| SECRET GARDEN | [9 empty] | 0 |  | 0
| TREES | [9 empty] | 0 |  | 0
G | Ficus Benjamina Overall Height 1.5 Mtrs | Nos | 13 | 216 | 2808 | 100 | 1300 | 316 | 4108 | 2670.2 | 1437.8 |  | 0
| SHRUBS | [9 empty] | 0 |  | 0
H | Ficus microcarpa, hedge, 1.5m high | Nos | 78 | 135 | 10530 | 100 | 7800 | 235 | 18330 | 11914.5 | 6415.5 |  | 0
| GROUNDCOVERS | [9 empty] | 0 |  | 0
J | Alternanthera Brasiliana | m2 | 54.49 | 5.04 | 274.6296 | 50 | 2724.5 | 55.04 | 2999.1296 | 1949.4342 | 1049.6954 |  | 0
K | Ficus microcarpa 'Green Island Dwarf ficus 0.3-0.4m OAH , 0.3-0.4m SS | m2 | 11.2 | 32.4 | 362.88 | 50 | 560 | 82.4 | 922.88 | 599.872 | 323.008 |  | 0
| ACCENT PLANTS | [9 empty] | 0 |  | 0
L | Buxus microphylla 'Faulkner' (ball shape), 1.2m OAH | Nos | 12 | 270 | 3240 | 25 | 300 | 295 | 3540 | 2301 | 1239 |  | 0
M | Euonymus japonicus 'Green Rocket' (ball shape), 0.6m OAH | Nos | 40 | 135 | 5400 | 25 | 1000 | 160 | 6400 | 4160 | 2240 |  | 0
N | Westringia Fruticosa | Nos | 18 | 90 | 1620 | 25 | 450 | 115 | 2070 | 1345.5 | 724.5 |  | 0
P | Rosmarinus officinalis (ball shape) 0.35 m OAH | Nos | 41 | 288 | 11808 | 25 | 1025 | 313 | 12833 | 8341.45 | 4491.55 |  | 0
| LEVEL 4 - RESIDENTIAL POOL | [11 empty] | 0
A | Planting engineered soil | m3 | 834 | [7 empty] | 0 |  | 0
B | Sweet soil | m3 | 834 | 45 | 37530 | 15 | 12510 | 60 | 50040 |  | 50040 | 40232.1505 | 4803.8495 | 90% | 45036
| PALMS | [9 empty] | 0 |  | 0
C | Chamearops humilis, min 3 trunks, 1.0-1.5m CT -150-200 mm Caliper,2-3 m OAH and 1.5 - 2 m SS (PC Rate at AED 1,500) | Nos | 55 | 2880 | 158400 | 300 | 16500 | 3180 | 174900 | 113685 | 61215 |  | 0
D | Livingstonia chinensis - Chinese Fan Palm 0.5 - 0.75 m CT,250-300 mm Caliper, Height 2.0-3.0m,1.50-20m SS | Nos | 16 | 600 | 9600 | 300 | 4800 | 900 | 14400 | 9360 | 5040 |  | 0
E | Roystonea regia, 2.0-3.0m CT,300-350mm Cal,3-4m OAH & 1.5-2m SS | Nos | 34 | 8100 | 275400 | 300 | 10200 | 8400 | 285600 | 185640 | 99960 |  | 0
| TREES | [5 empty] | 0 |  | 0 |  | 0 |  | 0
F | Ficus nitida, 2-2.5m CT, 150-180mm caliper,3.5-4.5m OAH & 2 - 2.5 m SS | Nos | 7 | 2700 | 18900 | 300 | 2100 | 3000 | 21000 | 13650 | 7350 |  | 0
| PALMS | [9 empty] | 0 |  | 0
G | Chamaerops humilis 'Vulcano' (Compact), 0.75-1.0m OAH and 0.50 - 0.75 m SS (PC Rate at AED 1,081.62) | Nos | 115 | 2350 | 270250 | 300 | 34500 | 2650 | 304750 | 198087.5 | 106662.5 |  | 0
| TREES | [9 empty] | 0 |  | 0
H | Plumeria 'Singapore Dawrf" White,0.2 - 0.5 m CT,60-90mm Caliper, 1.5-2.0m OAH and 1-1.5 m SS | Nos | 93 | 225 | 20925 | 150 | 13950 | 375 | 34875 | 22668.75 | 12206.25 |  | 0
| SHRUBS, GROUNDCOVERS & SUCCULENTS | [9 empty] | 0 |  | 0
J | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | m2 | 128.33 | 86.4 | 11087.712 | 50 | 6416.5 | 136.4 | 17504.212 | 11377.7378 | 6126.4742 |  | 0
K | Ficus microcarpa, hedge, 1.5m OAH,0.4-0.6 m SS | Nos | 184 | 135 | 24840 | 25 | 4600 | 160 | 29440 | 19136 | 10304 |  | 0
L | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 411 | 117 | 48087 | 50 | 20550 | 167 | 68637 | 44614.05 | 24022.95 |  | 0
M | MIXED PLANTS | [9 empty] | 0 |  | 0
N | Cyperus alternifolius, 0.5-0.6m OAH,0.3-0.4 m SS | m2 | 20 | 18 | 360 | 50 | 1000 | 68 | 1360 | 884 | 476 |  | 0
P | Alternanthera veriscolor, 0.1-0.2m OAH, 0.1 - 0.2 m SS | m2 | 20 | 7.56 | 151.2 | 50 | 1000 | 57.56 | 1151.2 | 748.28 | 402.92 |  | 0
| GROUNDCOVERS | [9 empty] | 0 |  | 0
A | Alternanthera amoena, 0.1-0.2m OAH and 0.1-0.2m SS | m2 | 152 | 8 | 1216 | 50 | 7600 | 58 | 8816 | 5730.4 | 3085.6 |  | 0
B | Carissa macrocarpa 'Boxwood Beauty', 0.15-0.2m OAH & 0.15 - 0.2 m SS | m2 | 276 | 28.8 | 7948.8 | 50 | 13800 | 78.8 | 21748.8 | 14136.72 | 7612.08 |  | 0
C | Sesuvium portulacastrum, 0.1-0.2m OAH and 0.1-0.2m SS | m2 | 343 | 5.4 | 1852.2 | 50 | 17150 | 55.4 | 19002.2 | 12351.43 | 6650.77 |  | 0
| ACCENT PLANTS | [9 empty] | 0 |  | 0
D | Cycas revoluta, 0.5-0.6m CT,200-300mm Cal,1-1.50m OAH & 0.8-1m SS | Nos | 68 | 990 | 67320 | 300 | 20400 | 1290 | 87720 | 57018 | 30702 |  | 0
| LEVEL 4 - MEDITERRANEAN GARDEN | [11 empty] | 0
| TREES | [9 empty] | 0 |  | 0
A | Citrus Limon (Lemon Tree), 1 m CT,100 - 150 mm Caliper, o/a height 1.50-2.0m, and 1-1.5 m SS | Nos | 20 | 4500 | 90000 | 150 | 3000 | 4650 | 93000 | 60450 | 32550 |  | 0
B | Olea europea (Domestic Olive),1.5-2 m CT,200-250 mm Caliper, o/a height 3.50 -5 mm, and 2 -3 m SS | Nos | 26 | 6300 | 163800 | 300 | 7800 | 6600 | 171600 | 111540 | 60060 |  | 0
C | Olea europea (Domestic Olive), 1.5 - 2 m CT,100-150 mm Caliper,o/a height 2.5-3.5m, 1.5-2 m SS | Nos | 7 | 1980 | 13860 | 300 | 2100 | 2280 | 15960 | 10374 | 5586 |  | 0
D | Punica granatum (Pomegranate)1 m CT,100-120 mm Caliper,o/a height 1.5-2m, and 1 - 1.5 m SS Avail 30-40mm cal | Nos | 18 | 810 | 14580 | 150 | 2700 | 960 | 17280 | 11232 | 6048 |  | 0
| SHRUBS | [8 empty] | 0 | 0 |  | 0
E | Conocarpus erectus var sericeus(Silver-leaved Buttonwood) 1.5-2.0m OAH,1-1.5m SS | Nos | 220 | 450 | 99000 | 100 | 22000 | 550 | 121000 | 78650 | 42350 |  | 0
E1 | Ficus Microcarpa 40-60cm OAH | Nos | 104 | 10.8 | 1123.2 | 25 | 2600 | 35.8 | 3723.2 | 2420.08 | 1303.12 |  | 0
F | Rosmarinus officinalis (Rosemary),0.40-0.60m OAH,and 0.3-0.4 m SS | Nos | 212 | 21.6 | 4579.2 | 25 | 5300 | 46.6 | 9879.2 | 6421.48 | 3457.72 |  | 0
G | Rosmarinus officinalis 'Prostratus' .4 -0.6 m OAH,0.3 -0.4 m SS | Nos | 73 | 21.6 | 1576.8 | 25 | 1825 | 46.6 | 3401.8 | 2211.17 | 1190.63 |  | 0
| GROUNDCOVERS | [8 empty] | 0 | 0 |  | 0
J | Gazania pulchella 0.1 m - 0.2 m OAH,0.1 - 0.2 m SS | m2 | 2.13 | 12.96 | 27.6048 | 50 | 106.5 | 62.96 | 134.1048 | 87.1681 | 46.9367 |  | 0
K | Ocimum cinnamon 0.4 -0.5 m OAH,0.2m - 0.3 m SS | m2 | 22 | 32.4 | 712.8 | 50 | 1100 | 82.4 | 1812.8 | 1178.32 | 634.48 |  | 0
| PLANT MIXES | [8 empty] | 0 | 0 |  | 0
L | Vitex agnus-castus 0.8 m -1 m OAH,0.5-0.6 m SS | Nos | 66 | 21.6 | 1425.6 | 25 | 1650 | 46.6 | 3075.6 | 1999.14 | 1076.46 |  | 0
M | Alternanthera versicolor 0.1-0.2 m OAH, 0.1-0.2 m SS | m2 | 407 | 7.56 | 3076.92 | 50 | 20350 | 57.56 | 23426.92 | 15227.498 | 8199.422 |  | 0
| LEVEL 10 | [8 empty] | 0 | 0 |  | 0
| TALL PALMS | [8 empty] | 0 | 0 |  | 0
A | Planting engineered soil | m3 | 75 | [6 empty] | 0 | 0 |  | 0
B | Sweet soil | m3 | 75 | 45 | 3375 | 15 | 1125 | 60 | 4500 |  | 4500 |  | 225 | 5% | 225
C | Chamaerops humilis 'Vulcano', 0.75-1.0m OAH,0.5-0.75 m SS (PC Rate at AED 1,081.62) | Nos | 6 | 2250 | 13500 | 300 | 1800 | 2550 | 15300 | 9945 | 5355 |  | 0
D | Livistona chinensis, 0.5-0.75m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.5 - 2 m SS | Nos | 11 | 1080 | 11880 | 300 | 3300 | 1380 | 15180 | 9867 | 5313 |  | 0
E | Pritchardia pacifica, 1.0m CT,100-150mm Cal 1.5-2.0m OAH 1-1.5 m SS | Nos | 3 | 1710 | 5130 | 300 | 900 | 2010 | 6030 | 3919.5 | 2110.5 |  | 0
F | Trachycarpus fortunei, 1m CT,150-200mm Cal 1.5-2.0m OAH 1-1.50m SS | Nos | 9 | 1980 | 17820 | 300 | 2700 | 2280 | 20520 | 13338 | 7182 |  | 0
| SHRUBS182 | [8 empty] | 0 | 0 |  | 0
| Ficus Microcarpa (hedge) | Nos | 16 | 135 | 2160 | 100 | 1600 | 235 | 3760 | 2444 | 1316 |  | 0
| ACCENT PLANTS |  |  |  | 0 |  |  |  |  | 0 | 0 |  | 0
G | Zamia furfuracea Cardboard Palm, 0.5-0.6m OAH, supply spread 0.4-0.5m | Nos | 35 | 117 | 4095 | 50 | 1750 | 167 | 5845 | 3799.25 | 2045.75 |  | 0
| GOUND COVERS | [8 empty] | 0 | 0 |  | 0
H | Portulacaria afra, 0.2 3 -0.3 m OAH, 0.2 - 0.3 m SS | Nos | 470 | 4.5 | 2115 | 25 | 11750 | 29.5 | 13865 | 9012.25 | 4852.75 |  | 0
| LEVEL 17 | [11 empty] | 0
J | Planting engineered soil | m3 | 100 | [7 empty] | 0 |  | 0
K | Sweet soil | m3 | 100 | 45 | 4500 | 15 | 1500 | 60 | 6000 |  | 6000 |  | 0
| TREES | [9 empty] | 0 |  | 0
L | Butia capitata, 2m CT, 350-400 mm Caliper,3-4m OAH and 3 - 3.5 m SS | Nos | 6 | 2160 | 12960 | 300 | 1800 | 2460 | 14760 | 9594 | 5166 |  | 0
M | Ravenala madagascariensis (Travellers Palm),1m CT, 500mm Caliper, o/a Ht 5-6m, 3-3.5m SS (Spec 0.25 Clear Trunk; 2.5-3 Overall height) | Nos | 5 | 2880 | 14400 | 300 | 1500 | 3180 | 15900 | 10335 | 5565 |  | 0
N | Washingtonia filifera, 3.0m CT,500 mm Caliper, 5-6m OAH, and 3 m SS | Nos | 7 | 3240 | 22680 | 300 | 2100 | 3540 | 24780 | 16107 | 8673 |  | 0
| SHRUBS MIX 1 | [9 empty] | 0 |  | 0
P | Asparagus densiflorous sprengeri, 0.25-0.3m OAH, and 0.25 - 0.3 m SS | Nos | 182 | 8.1 | 1474.2 | 25 | 4550 | 33.1 | 6024.2 | 3915.73 | 2108.47 |  | 0
Q | Pennisetum alopecuroides, 0.5-0.6m OAH, and 0.4 - 0.5 m SS | Nos | 137 | 7.2 | 986.4 | 25 | 3425 | 32.2 | 4411.4 | 2867.41 | 1543.99 |  | 0
R | Euphorbia canariensis, 1.2-1.5m OAH,0.75 m - 0.9 m SS | Nos | 137 | 324 | 44388 | 25 | 3425 | 349 | 47813 | 31078.45 | 16734.55 |  | 0
| Sansevieria Cylindrica | Nos | 91 | 12.6 | 1146.6 | 25 | 2275 | 37.6 | 3421.6 | 2224.04 | 1197.56 |  | 0
T | Tichocerus Pasacana | Nos | 46 | 198 | 9108 | 25 | 1150 | 223 | 10258 | 6667.7 | 3590.3 |  | 0
| SHRUBS MIX 2 | [9 empty] | 0 |  | 0
A | Atriplex semibacatta, 0.15-0.2m OAH,0.15 - 0.2 m SS | Nos | 178 | 5.4 | 961.2 | 25 | 4450 | 30.4 | 5411.2 | 3517.28 | 1893.92 |  | 0
B | Cenchrus Ciliaris | Nos | 45 | 7.2 | 324 | 25 | 1125 | 32.2 | 1449 | 941.85 | 507.15 |  | 0
C | Agave attenata, 0.4m OAH and 0.5 m SS | Nos | 89 | 27 | 2403 | 25 | 2225 | 52 | 4628 | 3008.2 | 1619.8 |  | 0
D | Echinocactus grusonii, 0.25-0.3m OAH,0.25-0.3m SS | Nos | 59 | 81 | 4779 | 25 | 1475 | 106 | 6254 | 4065.1 | 2188.9 |  | 0
E | Opuntia basilaris | Nos | 45 | 45 | 2025 | 25 | 1125 | 70 | 3150 | 2047.5 | 1102.5 |  | 0
| SHRUBS MIX 3 | [9 empty] | 0 |  | 0
F | Aloe arborescens, 0.3-0.4m OAH,0.25-0.3 m SS | Nos | 36 | 12.6 | 453.6 | 25 | 900 | 37.6 | 1353.6 | 879.84 | 473.76 |  | 0
G | Atriplex Semibaccata 0.15-0.5 m OAH,0.15-0.2 m SS | Nos | 47 | 5.4 | 253.8 | 25 | 1175 | 30.4 | 1428.8 | 928.72 | 500.08 |  | 0
| GROUNDCOVERS | [9 empty] | 0 |  | 0
H | Asparagus densiflorous sprengeri, 0.2-0.3mOAH,0.25-0.3 m SS | Nos | 6 | 8.1 | 48.6 | 25 | 150 | 33.1 | 198.6 | 129.09 | 69.51 |  | 0
H1 | Atriplex Semibaccata 0 | Nos | 63 | 5.4 | 340.2 | 25 | 1575 | 30.4 | 1915.2 | 1244.88 | 670.32 |  | 0
| SUCCULANTS AND FEATURE PLANTS | [9 empty] | 0 |  | 0
J1 | Agave Attenuata | Nos | 8 | 27 | 216 | 25 | 200 | 52 | 416 | 270.4 | 145.6 |  | 0
J | Aloe arborescens, 0.3-0.4m OAH,0.25-0.3 m SS | Nos | 4 | 12.6 | 50.4 | 25 | 100 | 37.6 | 150.4 | 97.76 | 52.64 |  | 0
K | Euphorbia canariensis, 1.2-1.5m OAH,0.75-0.9 m SS | Nos | 16 | 324 | 5184 | 25 | 400 | 349 | 5584 | 3629.6 | 1954.4 |  | 0
L | Pachypodium lamerei | Nos | 18 | 153 | 2754 | 25 | 450 | 178 | 3204 | 2082.6 | 1121.4 |  | 0
M | Sansivieria cylindrica, 0.4-0.5m OAH,0.25-0.3 m SS | Nos | 6 | 12.6 | 75.6 | 25 | 150 | 37.6 | 225.6 | 146.64 | 78.96 |  | 0
N | Xanthorrhoea caespitosa (Replaced with Yucca Alternifolia) | Nos | 24 | 270 | 6480 | 25 | 600 | 295 | 7080 | 4602 | 2478 |  | 0
| LEVEL 23 MEMBERS LOUNGE | [11 empty] | 0
A | Planting engineered soil | m3 | 35 | [7 empty] | 0 |  | 0
B | Sweet soil | m3 | 35 | 45 | 1575 | 15 | 525 | 60 | 2100 |  | 2100 | 1155 | 735 | 90% | 1890
C | Ficus nitida, 2-2.5m CT, 150-180mm Cal ,3.5-4.5m OAH & 2-2.5m SS | Nos | 9 | 2700 | 24300 | 300 | 2700 | 3000 | 27000 | 17550 | 9450 |  | 0
D | Eunoymus japonicus, 0.6m OAH and 0.6 m SS | Nos | 114 | 21.6 | 2462.4 | 25 | 2850 | 46.6 | 5312.4 | 3453.06 | 1859.34 |  | 0
| LEVEL 24 TO LEVEL 29 RESIDENCE TOWER | [11 empty] | 0
E | Planting engineered soil | m3 | 300 | [7 empty] | 0 |  | 0
F | Sweet soil | m3 | 300 | 45 | 13500 | 15 | 4500 | 60 | 18000 |  | 18000 | 9054 | 2646 | 65% | 11700
| PALMS | [9 empty] | 0 |  | 0
H | Livistona chinensis, 0.5-0.75m CT 250-300mm Cal 2-3m OAH 1.50-2m SS | Nos | 15 | 1080 | 16200 | 300 | 4500 | 1380 | 20700 | 13455 | 7245 |  | 0
| SHRUBS | [8 empty] | 0 | 0 |  | 0
J | Ficus microcarpa, hedge, 1.5m OAH,0.4 - 0.6 m SS | Nos | 115 | 135 | 15525 | 100 | 11500 | 235 | 27025 | 17566.25 | 9458.75 |  | 0
| ACCENT PLANTS | [8 empty] | 0 | 0 |  | 0
K | Cycas revoluta, 0.5-0.6m CT,200-300mm Cal 1.0-1.5m OAH & 0.8-1m SS | Nos | 7 | 990 | 6930 | 300 | 2100 | 1290 | 9030 | 5869.5 | 3160.5 |  | 0
L | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 26 | 117 | 3042 | 50 | 1300 | 167 | 4342 | 2822.3 | 1519.7 |  | 0
| GROUNDCOVERS | [8 empty] | 0 | 0 |  | 0
M | Portulacaria afra 0.2 - 0.3 m OAH and 0.2 - 0.3 m SS | Nos | 307 | 4.5 | 1381.5 | 25 | 7675 | 29.5 | 9056.5 | 5886.725 | 3169.775 |  | 0
| LEVEL 29 HOTEL TOWER | [11 empty] | 0
N | Planting engineered soil | m3 | 33 | [7 empty] | 0 |  | 0
P | Sweet soil | m3 | 33 | 45 | 1485 | 15 | 495 | 60 | 1980 |  | 1980 |  | 1980 | 100% | 1980
| SHRUBS MIX 1 |  |  |  | 0 | [5 empty] | 0 |  | 0
| Zamia Furfuracea | Nos | 26 | 117 | 3042 | 50 | 1300 | 167 | 4342 | 2822.3 | 1519.7 |  | 0
| Carissa Green Carpet | Nos | 78 | 7.2 | 561.6 | 25 | 1950 | 32.2 | 2511.6 | 1632.54 | 879.06 |  | 0
| SHRUBS MIX 2 | [9 empty] | 0 |  | 0
| Zamia Furfuracea | Nos | 13 | 117 | 1521 | 50 | 650 | 167 | 2171 | 1411.15 | 759.85 |  | 0
| Carissa Green Carpet | Nos | 39 | 7.2 | 280.8 | 25 | 975 | 32.2 | 1255.8 | 816.27 | 439.53 |  | 0
| Asparagus Densiforous Meyersi | Nos | 39 | 8.1 | 315.9 | 25 | 975 | 33.1 | 1290.9 | 839.085 | 451.815 |  | 0
| ADDITIONAL ITEMS | [9 empty] | 0 |  | 0
A | Maintenance for Softscape (Upto December 2021) | Item | 1 | 45000 | 45000 |  |  |  | 45000 |  | 45000 |  | 0
A1 | Maintenance for Softscape post TOC (12 Months) | Item | 1 | 180000 | 180000 |  |  |  | 180000 |  | 180000 |  | 0
B | Excavation and disposal for planting areas at Ground Level | m3 | 600 | 45 | 27000 |  |  |  | 27000 |  | 27000 |  |  | 5% | 1350
| SUBTOTAL 1 - TOTAL TO SOFTSCAPE |  |  |  | 3561588.9944 |  | 749118.5 |  | 4310707.4944 | 2499943.8714 | 1810763.623 | 175501.3585 | 90018.3209 | 14.66% | 265519.6794
0
0
GROUND LEVEL
A | 30mm thk polypropylene drainage cell | m2 | 1056 |  |  |  |  | 46 | 48576 |  | 48576 | 46147.2 | 0 | 95% | 46147.2
B | Non woven needle punched polypropylene geotextile | m2 | 1056 |  |  |  |  | 7.25 | 7656 |  | 7656 | 7273.2 | 0 | 95% | 7273.2
C | Planter drain | Nos | 48 | [5 empty] | N/A |  | N/A |  | 0
LEVEL 02
D | 30mm thk polypropylene drainage cell | m2 | 1172 |  |  |  |  | 46 | 53912 |  | 53912 | 49599.04 | 1617.36 | 95% | 51216.4
E | Non woven needle punched polypropylene geotextile | m2 | 1172 |  |  |  |  | 7.25 | 8497 |  | 8497 | 7817.24 | 254.91 | 95% | 8072.15
F | Planter drain | Nos | 32 | [5 empty] | N/A |  | N/A |  | 0
LEVEL 04 RESIDENTIAL
G | 30mm thk polypropylene drainage cell | m2 | 2765 |  |  |  |  | 46 | 127190 |  | 127190 | 120830.5 | 0 | 95% | 120830.5
H | Non woven needle punched polypropylene geotextile | m2 | 2765 |  |  |  |  | 7.25 | 20046.25 |  | 20046.25 | 19043.9375 | 0 | 95% | 19043.9375
J | Planter drain | Nos | 138 | [5 empty] | N/A |  | N/A |  | 0
LEVEL 10
K | 30mm thk polypropylene drainage cell | m2 | 136 |  |  |  |  | 46 | 6256 |  | 6256 |  | 5317.6 | 85% | 5317.6 | 958
L | Non woven needle punched polypropylene geotextile | m2 | 136 |  |  |  |  | 7.25 | 986 |  | 986 |  | 838.1 | 85% | 838.1
LEVEL 17
M | 30mm thk polypropylene drainage cell | m2 | 550 |  |  |  |  | 46 | 25300 |  | 25300 |  | 2530 | 10% | 2530
N | Non woven needle punched polypropylene geotextile | m2 | 550 |  |  |  |  | 7.25 | 3987.5 |  | 3987.5 |  | 398.75 | 10% | 398.75
LEVEL 23
A | 30mm thk polypropylene drainage cell | m2 | 124 |  |  |  |  | 46 | 5704 |  | 5704 |  | 5704 | 100% | 5704
B | Non woven needle punched polypropylene geotextile | m2 | 124 |  |  |  |  | 7.25 | 899 |  | 899 |  | 899 | 100% | 899
LEVEL 24 to 29 RESIDENTIAL
C | 30mm thk polypropylene drainage cell | m2 | 298.43 |  |  |  |  | 46 | 13727.78 |  | 13727.78 | 10317.7994 | 1350.8136 | 85% | 11668.613
D | Non woven needle punched polypropylene geotextile | m2 | 298.43 |  |  |  |  | 7.25 | 2163.6175 |  | 2163.6175 | 1626.1749 | 212.9 | 85% | 1839.0749
LEVEL 29 HOTEL
E | 30mm thk polypropylene drainage cell | m2 | 148 |  |  |  |  | 46 | 6808 |  | 6808 | 6808 | 0 | 100% | 6808
F | Non woven needle punched polypropylene geotextile | m2 | 148 |  |  |  |  | 7.25 | 1073 |  | 1073 | 1073 | 0 | 100% | 1073
| To Summary | [7 empty] | 332782.1475 |  | 332782.1475 | 270536.0919 | 19123.4335 |  | 289659.5254
| Less Discount | [7 empty] | 49997.91 |  | 49997.91 | 40645.9279 | 2873.146 |  | 43519.0739
| SUBTOTAL 3 - TOTAL TO DRAINAGE GEOTEXTILE | [7 empty] | 282784.2375 |  | 282784.2375 | 226181.7427 | 19958.7087 |  | 246140.4514
No | DESCRIPTION OF WORK
GROUND LEVEL
D | Butia Capitata, 3-4 m OAH + Block work below | No. | 66 |  |  |  |  | 390 | 25740 |  | 25740 |  | 2574 | 10% | 2574
G | Butia Capitata, 3-4 m OAH + Block work below | No. | 5 |  |  |  |  | 390 | 1950 |  | 1950 |  | 97.5 | 5% | 97.5
LEVEL 2
F | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 10 |  |  |  |  | 390 | 3900 |  | 3900
G | Phoenix Rebelenii 2-3m OAH + Block work below | No. | 14 |  |  |  |  | 390 | 5460 |  | 5460
H | Olivia Europea 3.0m OAH + Block work below | No. | 7 |  |  |  |  | 390 | 2730 |  | 2730
LEVEL 4 Residential Pool
A | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 16 |  |  |  |  | 390 | 6240 |  | 6240
B | Roystonea Regia 3-4m OAH + Block work below | No. | 34 |  |  |  |  | 390 | 13260 |  | 13260
C | Ficus Nitida 3.5-4.5m OAH + Block work below | No. | 7 |  |  |  |  | 390 | 2730 |  | 2730
LEVEL 4 Mediterranean Garden
A | Olivia Europea 3.5-5.0m OAH + Block work below | No. | 26 |  |  |  |  | 420 | 10920 |  | 10920
B | Olivia Europea 2.5-3.5m OAH + Block work below | No. | 7 |  |  |  |  | 390 | 2730 |  | 2730
C | Butia Capitata, 3-4 m OAH + Block work below | No. | 6 |  |  |  |  | 390 | 2340 |  | 2340
LEVEL 10
A | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 11 |  |  |  |  | 390 | 4290 |  | 4290
G | Chamaerops humilis 'vulcano', | No. | 14 |  |  |  |  | 390 | 5460 |  | 5460
H | Pritchardia fortunei, 1.5-2.0m OAH+Block work below | No. | 3 |  |  |  |  | 390 | 1170 |  | 1170
LEVEL 23 MEMBERS LOUNGE
A | Ficus Nitida 3.5-4.5m OAH + Block work below | No. | 9 |  |  |  |  | 390 | 3510 |  | 3510
LEVEL 24 to LEVEL 29 RESIDENCE TOWER
A | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 10 |  |  |  |  | 390 | 3900 |  | 3900
| SUBTOTAL 4 - TOTAL TO TREE & PALM ANCHORING | [7 empty] | 96330 |  | 96330 |  | 2671.5 |  | 2671.5
1 | SUBTOTAL 1 - TOTAL TO SOFTSCAPE | [7 empty] | 4310707.4944 | 2499943.8714 | 1810763.623 | 175501.3585 | 90018.3209 |  | 265519.6794
3 | SUBTOTAL 3 - TOTAL TO DRAINAGE GEOTEXTILE | [7 empty] | 282784.2375 | 0 | 282784.2375 | 226181.7427 | 19958.7087 |  | 246140.4514
4 | SUBTOTAL 4 - TOTAL TO TREE & PALM ANCHORING | [7 empty] | 96330 | 0 | 96330 | 0 | 2671.5 |  | 2671.5
| TOTAL SUMMARY | [7 empty] | 4689821.7319 | 2499943.8714 | 2189877.8605 | 401683.1012 | 112648.5296 |  | 514331.6308
HARDSCAPE PAVERS
GROUND LEVEL + LEVEL 2
1 | Installation of Pavers Approx 6000 sq m | m2 | 6000 |  |  |  |  | 80.4255 | 482552.8 | 71540.0611 | 411012.7389 | 401483.9296 | 0 | 83.2% | 401483.9296
2 | Euro Grout with Application Approx 7000 sq m at AED12 per sq m | m2 | 7000 |  |  |  |  | 12 | 84000 | 12792 | 71208 | 21000 |  | 25% | 21000
| SUBTOTAL 5 - HARDSCAPE INSTALLATIONS | [7 empty] | 566552.8 | 84332.0611 | 482220.7389 | 422483.9296 | 0 |  | 422483.9296
Note on P216: Himal Kosala: only 5% no supporting
Note on P289: Himal Kosala: no supporting drawings or WIRs
Note on P290: Himal Kosala: no supporting drawings or WIRs

## Valuation (WFA)
DORCHESTER COLLECTION HOTEL & RESIDENCES (PLOT 18) |  |  |  |  | 2022-05-30
VALUATION OF REMAINING SUBCONTRACT WORKS |  |  |  |  | Ver. 3
Trade Package: | Soft Landscaping and Irrigation
Subcontractor: | Fiona Environs UAE
Subcontract Ref: | 17001DH/SCA/D&B/40-03-30-FE
ORIGINAL SUBCONTRACT WORKS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| Excavation and disposal at ground level | 27000 | 0% | 0 | 27000
| Sweet soil | 212640 | 0% | 0 | 212640
| Palms, trees | 2969061 | 0% | 0 | 2969061
| Ground covers, grasses, climbers, shrubs, accent plants | 877015 | 0% | 0 | 877015
| Maintenance (pre-completion) | 45000 | 0% | 0 | 45000
| Maintenance (DNP) | 180000 | 0% | 0 | 180000
| Drainage and geotextile | 282782 | 0% | 0 | 282782
Sub-Totals |  | 4593498 | 0% | 0 | 4593498
VARIATIONS |  | TOTAL VALUE OF SUBCONTRACT WORKS | VALUE OF WORKS COMPLETED TO 28-FEB-2022 |  | VALUE OF WORKS UNDER NEW SUBCONTRACT
| Irrigation tank and pump | 318525 | 0% | 0 | 318525
| Irrigation network | 275400 | 65% | 179010 | 96390
| Irrigation secondary network | 552900 | 65% | 359385 | 193515
| Engineering and shop drawings | 50000 | 50% | 25000 | 25000
| Installation of concrete pavers (incl. grouting) | 558972 | 35% | 195640 | 363332
| Installation of tree anchoring system | 96330 | 0% | 0 | 96330
Sub-Totals |  | 1852127 | 40.98% | 759035 | 1093092
MATERIALS ON SITE |  | TOTAL VALUE OF SUBCONTRACT WORKS |  | VALUE OF WORKS COMPLETED TO 28-FEB-2022 | VALUE OF WORKS UNDER NEW SUBCONTRACT
| Materials off Site (65% of BOQ value) | 0 |  | 1923038 | -1923038
Sub-Totals |  | 0 |  | 1923038 | -1923038
Totals |  | 6445625 | 41.61% | 2682073 | 3763552
NOTES |  | NEW SUBCONTRACT
|  | Value of Remaining Subcontract Works |  |  | 4593498
1) The amount included at "Payments to Date" is subject to final validation by the Employer's Representative. The Subcontractor shall provide evidence substantiating the amount paid to date under the previous subcontract. 2) Payment of amounts due under the previous RPJV subcontract (including retention) will be made pursuant to the terms of the WFA between the Employer and the Subcontractor. 3) The subcontract shall provide security for its performance of the Subcontract Works in the amount of AED 644,562.00 in the form of an unconditional and irrevocable bank guarantee for the benefit of the Employer. 4) The subcontract shall provide security against payment for trees/plants stored off site in the amount of AED 2,500,000.00 in the form of an unconditional and irrevocable bank guarantee for the benefit of the Employer. 5) The amount included above for material stored off site is subject to inspection and validation of trees/plants at the Subcontractor's nursery. |  | Value of Remaining Variation Works |  |  | 1093092
|  | Less Value of Materials on Site at 28-Feb-22 |  |  | -1923038
|  | New Subcontract Price |  |  | 3763552
WORKS COMPLETED TO 28-FEB-22
|  | Value of Completed Subcontract Works |  |  | 0
|  | Value of Completed Variation Works |  |  | 759035
|  | Value of Materials on Site at 28-Feb-22 |  |  | 1923038
|  | Value of Works Completed to 28-Feb-22 |  |  | 2682073
|  | Less Retention to 28-Feb-22 (10%) |  |  | -268207.3
|  | Less Payments to Date (incl. Advance Payment) |  |  | -1491330.36
|  | Outstanding amount for Works Completed to 28-Feb-22 |  |  | 922535.34
All amounts exclude VAT

## Hardscape Pavers Progress
PROJECT: PLOT 18 - DORCHESTER HOTEL & RESIDENCIES
LANDSCAPE PACKAGES BY: FIONA ENVIRONS
HARDSCAPE PAVERS - PROGRESS | [5 empty] | Progress | [9 empty] | #REF!
[6 empty] | Previous |  |  | This Month |  |  | Cumulative
Item | Description | Qty. | Unit | Rate | Amount | Qty. | % | Amount | Qty. | % | Amount | Qty. | % | Amount
[5 empty] | (Dhs.) |  |  | (Dhs.) |  |  | (Dhs.) |  |  | (Dhs.)
PAVING
GROUND LEVEL
A | Type HS -02-C; Granite paving band; 600x300x80mm, Black colour, honed finish | 129 | m | 235.5752 | 30389.2065 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 243.1 | #REF!
#REF!
B | Type HS -03-A, Precast concrete paving ; 600x300x60mm, white colour, diamond cut finish | 3148.49 | m2 | 117.7876 | 370853.1507 | 1660.9555 | 52.75% | 195640 | 764.78 | 24.29% | 90081.6177 | 2425.7355 | 77.04% | 285721.6177 |  |  | 121.55 | #REF!
#REF!
C | Type HS -03-B, Precast concrete paving band; 600x300x60mm, white colour, diamond cut finish | 39.61 | m | 90.6059 | 3588.8982 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 93.5 | #REF!
#REF!
D | Type HS -03-C, Precast concrete paving ; 600x300x60mm, white colour, diamond cut finish | 95.65 | m2 | 145.357 | 13903.397 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 150 | #REF!
#REF!
E | Type HS-04-A, Interlocking concrete paving; 200x100x80mm, grey colour, shot blast finish | 222.81 | m2 | 135.9088 | 30281.8386 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 140.25 | #REF!
#REF!
F | Type HS-04-B, Interlocking concrete paving; 200x100x80mm, grey colour, shot blast finish | 2.63 | m | 22.6515 | 59.5734 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 23.375 | #REF!
#REF!
H | Type HS -05-A, Interlocking concrete paving 200x100x80mm, grey colour, shot blast finish | 362.61 | m2 | 135.9088 | 49281.8881 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 140.25 | #REF!
#REF!
J | Type HS -05-B, Interlocking concrete paving band 200x100x80mm, grey colour, shot blast finish | 4.69 | m | 90.6059 | 424.9415 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 93.5 | #REF!
#REF!
K | HS-01-A, Flush Kerb, 300(W)x130mm thk, Honed, Black, Granite | 171.22 | m | 342.4902 | 58641.1657 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 353.43 | #REF!
#REF!
L | HS-01-B, Upstand Kerb, 300(W), Honed, Black, Granite | 173.68 | m | 342.4902 | 59483.6915 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 353.43 | #REF!
#REF!
M | HS-01-C, Upstand Kerb, 200(W), Honed, Black, Granite | 136.07 | m | 241.0116 | 32794.4479 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 248.71 | #REF!
#REF!
N | HS-01-C, P.C Transition Kerb, 300(W)x300x900mm, Honed, TH32 Black |  | m |  | 0 | [12 empty] | #REF!
#REF!
| Paving Type ST-01-A, Step Tread, 400mm wide | 33 | Lm | 332.6667 | 10978.0003 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 343.2927 | #REF!
| Paving Type ST-01-B, Step Riser, 150mm high | 33 | Lm | 176.001 | 5808.0324 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
| Paving Type ST-02-A, Step Tread, 320mm wide | 12.24 | Lm | 249.1661 | 3049.7934 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 257.125 | #REF!
| Paving Type ST-02-B, Step Riser, 165mm high | 10.2 | Lm | 184.3829 | 1880.7059 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 190.2725 | #REF!
| Paving Type ST-02-B, Step Riser, 175mm high | 2.04 | Lm | 189.3663 | 386.3072 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 195.415 | #REF!
| Paving Type ST-03-A, Step Tread, 300mm wide | 19.04 | Lm | 249.1661 | 4744.123 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 257.125 | #REF!
| Paving Type ST-03-B, Step Riser, 165mm high | 15.87 | Lm | 184.3829 | 2926.1571 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 190.2725 | #REF!
| Paving Type ST-03-B, Step Riser, 175mm high | 3.17 | Lm | 189.3663 | 600.291 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 195.415 | #REF!
| Paving Type ST-04-A, Step Tread, 280mm wide | 15 | Lm | 249.1661 | 3737.4919 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 257.125 | #REF!
| Paving Type ST-04-B, Step Riser, 170mm high | 15 | Lm | 189.3663 | 2840.4938 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 195.415 | #REF!
| Paving Type ST-07-A, Step Tread, 400mm wide | 20.09 | Lm | 32.8899 | 660.7587 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 33.9405 | #REF!
| Paving Type ST-07-B, Step Riser, 125mm high | 20.05 | Lm | 176.001 | 3528.8197 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
| Paving Type ST-07-B, Step Riser, 150mm high | 10.05 | Lm | 176.001 | 1768.8099 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
| Paving Type ST-08-A, Step Tread, 400mm wide | 20.1 | Lm | 332.6667 | 6686.6002 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 343.2927 | #REF!
| Paving Type ST-08-B, Step Riser, 125mm high | 20.05 | Lm | 176.001 | 3528.8197 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
| Paving Type ST-08-B, Step Riser, 150mm high | 10.06 | Lm | 176.001 | 1770.5699 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
| Paving Type ST-09-A, Step Tread, 400mm wide | 20.02 | Lm | 332.6667 | 6659.9868 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 343.2927 | #REF!
| Paving Type ST-09-B, Step Riser, 150mm high | 27.12 | Lm | 176.001 | 4773.1467 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
| Paving Type ST-10-A, Step Tread, 500mm wide | 3.03 | Lm | 348.8326 | 1056.9627 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 359.975 | #REF!
| Paving Type ST-10-B, Step Riser, 200mm high | 3.03 | Lm | 209.2995 | 634.1776 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 215.985 | #REF!
| Paving Type ST-11-A, Step Tread, (area) | 28.98 | m2 | 448.499 | 12997.5017 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 462.825 | #REF!
| Paving Type ST-11-B, Step Riser, 150mm high | 38.58 | Lm | 176.001 | 6790.1179 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 181.6228 | #REF!
[5 empty] | 0 | [12 empty] | #REF!
[5 empty] | 0 | [12 empty] | #REF!
#REF!
| To Collection Dhs. |  |  |  | 737509.8667 | [12 empty] | #REF!
#REF!
| PAVING (CONT'D) | [16 empty] | #REF!
#REF!
| OUTSIDE PLOT LIMIT | [16 empty] | #REF!
#REF!
A | 3 Layer sub base for Paving |  | m2 |  | 0 | [12 empty] | #REF!
#REF!
B | HS-01-B, Upstand Kerb, 300(W), Honed, Black, Granite | 303.42 | m | 342.4902 | 103918.3653 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 353.43 | #REF!
#REF!
C | Type HS -02-B, Precast concrete paving Granite; 600x300x80mm, black colour, diamond cut finish | 73.32 | m2 | 202.1236 | 14819.6994 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 208.5798 | #REF!
#REF!
D | Type HS -02-C, Precast concrete Granite paving band; 600x300x80mm, black colour, diamond cut finish | 11.88 | m | 60.6334 | 720.3253 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 62.5702 | #REF!
#REF!
E | Type HS -05-A, Interlocking concrete paving 200x100x80mm, grey colour, shot blast finish | 190.59 | m2 | 143.0576 | 27265.3475 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 147.6272 | #REF!
#REF!
F | Type HS -05-B, Interlocking concrete paving band 200x100x80mm, grey colour, shot blast finish | 327.8 | m | 65.0731 | 21330.9723 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 67.1517 | #REF!
#REF!
| LEVEL 02 | [16 empty] | #REF!
#REF!
G | Type HS -02-B; Basalt Precast concrete paving band; 600x300x80mm, Black colour, honed finish | 59.13 | m | 63.0526 | 3728.3014 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 65.0667 | #REF!
#REF!
H | Type HS -03-A, Precast concrete paving ; 600x300x60mm, white colour, diamond cut finish | 2114.01 | m2 | 135.9088 | 287312.5514 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 140.25 | #REF!
#REF!
J | Type HS -03-B, Precast concrete paving band; 600x200x60mm, white colour, diamond cut finish | 15.1 | m | 90.6059 | 1368.1485 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 93.5 | #REF!
[5 empty] | 0 | [12 empty] | #REF!
| Type HS -03-C, Precast concrete paving ; 600x300x60mm, white colour, diamond cut finish | 25.23 | m2 | 135.9088 | 3428.9789 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 140.25 | #REF!
#REF!
K | HS-04-C, Basalt banding, 600x300x50mm, black | 126.96 | m | 187.5541 | 23811.8732 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 193.545 | #REF!
#REF!
L | HS-04-D, Basalt kerb, 300mm wide, black | 92.25 | m | 384.1689 | 35439.5774 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 396.44 | #REF!
#REF!
M | Type HS -05-A, Interlocking concrete paving 200x100x80mm, grey colour, shot blast finish | 115.67 | m2 | 154.03 | 17816.6463 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 158.95 | #REF!
#REF!
N | Type HS -05-B, Interlocking concrete paving 200x100x80mm, grey colour, shot blast finish, 200mm wide band | 86.02 | m | 99.6664 | 8573.308 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 102.85 | #REF!
#REF!
P | HS-01-A, Basalt Precast concrete kerb, Black, 300mm wide | 74.92 | m | 384.1689 | 28781.931 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 396.44 | #REF!
#REF!
| Type HS -06-B, Basalt paving band 200x100x50mm, black colour, matt finish, | 34.33 | m | 86.0756 | 2954.9743 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 88.825 | #REF!
#REF!
Q | Type WF-02-A, 30mm thick basalt black colour polished floor finishes |  | m2 |  | 0 | [12 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
| To Collection Dhs. |  |  |  | 581271.0004 | [12 empty] | #REF!
#REF!
| PAVING (CONT'D) | [16 empty] | #REF!
#REF!
| LEVEL 04 RESIDENTIAL | [16 empty] | #REF!
#REF!
A | Paving Type ST, Step Tread, 250-400mm wide, 300mm length, 20mm thick, width as per plan (Size assumed) |  | m |  | 0 | [12 empty] | #REF!
#REF!
B | Paving Type ST, Step Tread, 1200mm wide, 600mm length, 20mm thick, width as per plan (length assumed) |  | m |  | 0 | [12 empty] | #REF!
#REF!
C | Paving Type ST, Step Tread, 2900mm wide, 600mm length, 20mm thick, width as per plan (length assumed) |  | m |  | 0 | [12 empty] | #REF!
#REF!
D | Paving Type ST, Step riser 100-200mm high, 20mm thick, 300mm length (Size assumed) |  | m |  | 0 | [12 empty] | #REF!
#REF!
| ST-02-A Lower Terrace Precast UHPC, honed finish, Stair tread, area m2 | 45.31 | m2 | 179.2736 | 8122.8883 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 185 | #REF!
| ST-02-B Lower Terrace Precast UHPC, honed finish, Stair riser, 150mm | 39.23 | m | 49.8332 | 1954.9574 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 51.425 | #REF!
| ST-03-A Lower Terrace Precast UHPC, honed finish, Stair tread, area m2 | 48.71 | m2 | 179.2736 | 8732.4187 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 185 | #REF!
| ST-03-A Lower Terrace Precast UHPC, honed finish, Stair tread, 400mm wide | 40.18 | m | 179.2736 | 7203.2146 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 185 | #REF!
| SR-01-A Lower Terrace Precast UHPC, honed finish, Step tread, to ramp area m2 | 31.71 | m2 | 179.2736 | 5684.7669 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 185 | #REF!
| SR-02-A Lower Terrace Precast UHPC, honed finish, Step tread, to ramp area m2 | 19.72 | m2 | 179.2736 | 3535.276 |  | 0% | 0 | 0 | 0% | 0 |  | 0% | 0 |  |  | 185 | #REF!
#REF!
#REF!
| LEVEL 17 - Provisional Sum converted to Lumpsum | [16 empty] | #REF!
#REF!
E | Paving Type HS-02-B, Gravel, crushed finish | [16 empty] | #REF!
| Type HS-02-C, River Pebble, dark grey, washed & tumble finish, 50mm dia | 31.45 | m2 | 408.9377 | Lumpsum | [11 empty] | 422 | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
| To Collection Dhs. |  |  |  | 35233.5219 | [12 empty] | #REF!
#REF!
| PAVING (CONT'D) | [16 empty] | #REF!
#REF!
| ADDITIONAL ITEMS | [16 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
| To Collection Dhs. |  |  |  | 0 | [12 empty] | #REF!
#REF!
| PAVING (CONT'D) | [16 empty] | #REF!
#REF!
| COLLECTION | [16 empty] | #REF!
#REF!
| Page 4/1 |  |  |  | 737509.8667 | [12 empty] | #REF!
#REF!
| Page 4/2 |  |  |  | 581271.0004 | [12 empty] | #REF!
#REF!
| Page 4/3 |  |  |  | 35233.5219 | [12 empty] | #REF!
#REF!
| Page 4/4 |  |  |  | 0 | [12 empty] | #REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
#REF!
| To Summary |  |  |  | 1354014.389 |  | 14.45% | 195640 |  | 6.653% | 90081.6177 |  | 21.1% | 285721.6177 | 195640

## KCE SUMMARY
PROJECT NO. 17001DH | [12 empty] | 65%
PROJECT NAME. Plot 18, Dorchester Hotel
TRADE PACKAGE: SOFTSCAPE
S No | DESCRIPTION OF WORK | UNIT | QTY | SUPPLY RATE | SUPPLY COST | INSTALL RATE | INSTALL COST | COMPOSITE RATE | TOTAL BOQ AMOUNT | WORK DONE PREVIOUSLY | KHANSAHEB
SOIL, TREES, PALM & SHRUBS
GROUND LEVEL
A | Planting engineered soil | m3 | 1548 | Not Priced
B | Sweet soil | m3 | 1548 | 45 | 69660 | 15 | 23220 | 60 | 92880 | 0 | 92880
| PALMS | [9 empty] | 0
C | Acoelorraphe wrightii (multi-stemmed), 1.0m Clear Trunk, 100-150 mm Caliper,2.0-3.0m Over All Heigh and 1.50 to 2 m Supply Spread (Replaced with Pitchadia Palm) | Nos | 10 | 1710 | 17100 | 300 | 3000 | 2010 | 20100 | 13065 | 7035
D | Butia capitata, 2m CT, 250-300mm Caliper, 3-4 m OAH & 2.50m-3m SS | Nos | 66 | 2160 | 142560 | 300 | 19800 | 2460 | 162360 | 105534 | 56826
E | Chamaerops humilis 'Vulcano - minimum 5 Trunks, 1-1.5 m CT,150-200 mm Caliper, 2-3 m OAH ad 1.50 -2 m SS (PC Rate at AED 1,611.21) | Nos | 4 | 3360 | 13440 | 300 | 1200 | 3660 | 14640 | 9516 | 5124
F | Livistona chinensis, 0.5-0.75m CT,250-300 mm Caliper, 2.0-3.0m OAH and 1.50 to 2 m SS | Nos | 31 | 1080 | 33480 | 300 | 9300 | 1380 | 42780 | 27807 | 14973
G | Trachycarpus fortunei, 1.0m CT,100-150 mm Caliper, 1.5-2.0m OAH,and 1.0 - 1.5 m SS | Nos | 6 | 1980 | 11880 | 300 | 1800 | 2280 | 13680 | 8892 | 4788
H | Washingtonia robusta 3-4m CT 350-400mm Cal,4- 5m OAH, 2.50-3m SS | Nos | 22 | 3960 | 87120 | 300 | 6600 | 4260 | 93720 | 60918 | 32802
| PALM MIXES | [8 empty] | 0 | 0
| PALMS MIX 1 | [9 empty] | 0
J | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT, 150-200 mm Caliper,2.0-3.0 m OAH and 1.50 -2 m SS (PC Rate at AED1,500) | Nos | 33 | 2880 | 95040 | 300 | 9900 | 3180 | 104940 | 68211 | 36729
K | Cycas revoluta, 0.5-0.6m CT 200-300mm Cal, 1-1.5m OAH 0.80m-1m SS | Nos | 52 | 990 | 51480 | 300 | 15600 | 1290 | 67080 | 43602 | 23478
| PALMS MIX 2 | [9 empty] | 0
L | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150 - 200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED1,500) | Nos | 43 | 2880 | 123840 | 300 | 12900 | 3180 | 136740 | 88881 | 47859
M | Ravenala madagascariensis (Travellers Palm),0.25 m CT,300 - 400 mm Caliper, 2.5-3.0m OAH, supply spread 1.50 - 2 m | Nos | 43 | 2880 | 123840 | 300 | 12900 | 3180 | 136740 | 88881 | 47859
N | Pritchardia pacifica, 1m CT 100-150mm Cal, 1.5-2.0m OAH & 1-1.5m SS | Nos | 43 | 1710 | 73530 | 300 | 12900 | 2010 | 86430 | 56179.5 | 30250.5
| GROUNDCOVERS | [9 empty] | 0
P | Alternanthera amoena, 0.1-0.2m OAH and 0.1 - 0.2 m SS | m2 | 1088 | 8 | 8704 | 50 | 54400 | 58 | 63104 | 41017.6 | 22086.4
Q | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | Nos | 21 | 21.6 | 453.6 | 25 | 525 | 46.6 | 978.6 | 636.09 | 342.51
R | Carissa macrocarpa 'Green Carpet' Natal Plum 0.2-0.3m OAH 0.2-0.3m SS | m2 | 179.33 | 28.8 | 5164.704 | 50 | 8966.5 | 78.8 | 14131.204 | 9185.2826 | 4945.9214
S | Ficus microcarpa 'Green Island' Dwarf ficus 0.3-0.4m OAH & 0.3-0.4m SS | m2 | 274.89 | 32.4 | 8906.436 | 50 | 13744.5 | 82.4 | 22650.936 | 14723.1084 | 7927.8276
A | Hymenocallis littoralis Beach Spiderlily 0.3-0.4m OAH and 0.3-0.4m SS | m2 | 116.75 | 21.6 | 2521.8 | 50 | 5837.5 | 71.6 | 8359.3 | 5433.545 | 2925.755
| GRASSES | [9 empty] | 0
B | Cyperus alternifolius, 0.5-0.6m OAH and 0.30 - 0.40 m SS | m2 | 213.26 | 18 | 3838.68 | 50 | 10663 | 68 | 14501.68 | 9426.092 | 5075.588
| CLIMBERS | [9 empty] | 0
C | Bougainvillea spectabilis 0.80 - 1 m OAH and 0.30 - 0.4 m SS | No | 11 | 27 | 297 | 25 | 275 | 52 | 572 | 371.8 | 200.2
D | Quisqualis indica white flower Rangoon creeper 1-1.5m OAH 0.5-0.6m SS | No | 13 | 32.4 | 421.2 | 25 | 325 | 57.4 | 746.2 | 485.03 | 261.17
| PALMS | [9 empty] | 0
F | Acoelorraphe wrightii (multi-stemmed), 1.0m CT, 100 -150 mm Caliper,2.0-3.0m OAH and 1.50 - 2 m SS (Replaced with Pitchadia Palm) | Nos | 3 | 1710 | 5130 | 300 | 900 | 2010 | 6030 | 3919.5 | 2110.5
G | Butia capitata, 2m CT, 250-300mm Caliper,3-4 m OAH & 2.50-3m SS | Nos | 5 | 2160 | 10800 | 300 | 1500 | 2460 | 12300 | 7995 | 4305
H | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150 -200 mm Caliper, 2.0-3.0m OAH and 1.5 - 2 m SS (PC Rate at AED 1,524.12) | Nos | 3 | 2880 | 8640 | 300 | 900 | 3180 | 9540 | 6201 | 3339
J | Livistona chinensis, 0.5-0.75m CT 250-300mm Cal, 2-3m OAH 1.50-2m SS | Nos | 4 | 1080 | 4320 | 300 | 1200 | 1380 | 5520 | 3588 | 1932
K | Trachycarpus fortunei 1m CT,100-150mm Cal 1.5-2.0m OAH 1-1.50m SS | Nos | 9 | 1980 | 17820 | 300 | 2700 | 2280 | 20520 | 13338 | 7182
L | Washingtonia robusta, 3-4m CT,350-400mm Cal 4-4.50m OAH 2.5-3m SS | Nos | 7 | 3960 | 27720 | 300 | 2100 | 4260 | 29820 | 19383 | 10437
| SHRUBS MIX 1 | [9 empty] | 0
M | Crinum asiaticum (Giant Spider Lily), o/a Ht 0.4-0.5m, SS 0.2-0.3m. | Nos | 79 | 10.8 | 853.2 | 25 | 1975 | 35.8 | 2828.2 | 1838.33 | 989.87
N | Cycas revoluta, 0.5-0.6m CT, 200-300mm Cal.0-1.5m OAH & 0.80-1m SS | Nos | 7 | 990 | 6930 | 300 | 2100 | 1290 | 9030 | 5869.5 | 3160.5
P | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 79 | 117 | 9243 | 50 | 3950 | 167 | 13193 | 8575.45 | 4617.55
Q | Asparagus densiflorous Meyersii, 0.2-0.3m OAH and 0.20-0.3 m SS | m2 | 19.66 | 32.4 | 636.984 | 50 | 983 | 82.4 | 1619.984 | 1052.9896 | 566.9944
R | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | m2 | 19.66 | 28.8 | 566.208 | 50 | 983 | 78.8 | 1549.208 | 1006.9852 | 542.2228
A | Hymenocallis littoralis Beach Spiderlily 0.3-0.4m OAH and 0.3-0.4m SS | m2 | 19.66 | 21.6 | 424.656 | 50 | 983 | 71.6 | 1407.656 | 914.9764 | 492.6796
| SHRUBS MIX 2 | [9 empty] | 0
B | Crinum asiaticum (Giant Spider Lily), o/a height 0.4-0.5m, SS 0.2-0.3m. | Nos | 11 | 10.8 | 118.8 | 25 | 275 | 35.8 | 393.8 | 255.97 | 137.83
C | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 11 | 117 | 1287 | 50 | 550 | 167 | 1837 | 1194.05 | 642.95
D | Asparagus densiflorous Meyersii, 0.2-0.3m OAH and 0.20 - 0.3 m SS | m2 | 3 | 32.4 | 97.2 | 50 | 150 | 82.4 | 247.2 | 160.68 | 86.52
E | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | m2 | 3 | 28.8 | 86.4 | 50 | 150 | 78.8 | 236.4 | 153.66 | 82.74
LEVEL 2
A | Planting engineered soil | m3 | 619 | Not priced | [6 empty] | 0
B | Sweet soil | m3 | 619 | 45 | 27855 | 15 | 9285 | 60 | 37140 |  | 37140
| PALMS | [9 empty] | 0
C | Acoelorraphe wrightii (multi-stemmed), 1.0m CT,100-150 mm caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (Replaced by Pitchadia Palm) | Nos | 9 | 1710 | 15390 | 300 | 2700 | 2010 | 18090 | 11758.5 | 6331.5
D | Copernicia alba, 1.5m CT, 200-250mm Cal,2.5-3.5m OAH 1-1.50m SS | Nos | 34 | 4500 | 153000 | 300 | 10200 | 4800 | 163200 | 106080 | 57120
E | Chamaerops humilis 'Vulcano' 1-1.50 m CT,150-200 mm Caliper, 2.0-3.0 m OAH and 1.50 - 2 m SS (PC Rate at AED 1,081.62) | Nos | 30 | 2880 | 86400 | 300 | 9000 | 3180 | 95400 | 62010 | 33390
F | Livistona chinensis, 0.5-0.75m CT 250-300mm Cal, 2-3m OAH 1.50-2m SS | Nos | 10 | 1080 | 10800 | 300 | 3000 | 1380 | 13800 | 8970 | 4830
G | Phoenix rebelenii,0.5 0.75 m CT,150-200 mm caliper, and 2-3 m OAH and 1.50 - 2 m SS | Nos | 16 | 504 | 8064 | 300 | 4800 | 804 | 12864 | 8361.6 | 4502.4
H | Rhapis excelsa (Min. 8 trunks),1-1.50 m CT,50-100 mm caliper,2-2.5 m OAH and 1-1.50 m SS | Nos | 7 | 252 | 1764 | 100 | 700 | 352 | 2464 | 1601.6 | 862.4
J | Trachycarpus fortunei 1.0m CT,100-150mm Cal 1.5-2.0m OAH 1-1.50m SS | Nos | 29 | 1980 | 57420 | 300 | 8700 | 2280 | 66120 | 42978 | 23142
K | Washingtonia robusta, 2.0-3.0m CT,300-350 mm Caliper, 3.0-4.0m OAH and 1.50 - 2 m SS | Nos | 18 | 2700 | 48600 | 300 | 5400 | 3000 | 54000 | 35100 | 18900
L | Washingtonia robusta (Medium), 1.5-2.0m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.50 - 2 m SS | Nos | 12 | 1800 | 21600 | 300 | 3600 | 2100 | 25200 | 16380 | 8820
| PALM MIXES | [9 empty] | 0
| PALMS MIX 1 | [9 empty] | 0
M | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150-200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED 1,500) | Nos | 41 | 2880 | 118080 | 300 | 12300 | 3180 | 130380 | 84747 | 45633
N | Cycas revoluta, 0.5-0.6m CT, 200-300mm Cal 1.0-1.5m OAH 0.80-1m SS | Nos | 53 | 990 | 52470 | 300 | 15900 | 1290 | 68370 | 44440.5 | 23929.5
| PALMS MIX 2 | [9 empty] | 0
P | Chamaerops humilis (Min. 3 trunks), 1.0-1.5mCT,150-200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED 1,500) | Nos | 7 | 2880 | 20160 | 300 | 2100 | 3180 | 22260 | 14469 | 7791
Q | Ravenala madagascariensis,0.25 m CT,300-400 mm Caliper, 2.5-3 m OAH and 1.50 - 2 m SS | Nos | 7 | 2880 | 20160 | 300 | 2100 | 3180 | 22260 | 14469 | 7791
R | Pritchardia pacifica, 1m CT, 100-150mm Cal,1.5-2.0m OAH & 1-1.50m SS | Nos | 7 | 1710 | 11970 | 300 | 2100 | 2010 | 14070 | 9145.5 | 4924.5
| GROUNDCOVERS | [5 empty] | 0 |  | 0 |  | 0
A | Alternanthera amoena, 0.1-0.2m OAH and 0.1 - 0.2 m SS | m2 | 163 | 8 | 1304 | 50 | 8150 | 58 | 9454 | 6145.1 | 3308.9
B | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | m2 | 23 | 86.4 | 1987.2 | 50 | 1150 | 136.4 | 3137.2 | 2039.18 | 1098.02
C | Carissa macrocarpa 'Boxwood Beauty', 0.15-0.2m OAH & 0.15 -0.2 m SS | m2 | 126 | 28.8 | 3628.8 | 50 | 6300 | 78.8 | 9928.8 | 6453.72 | 3475.08
D | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH, 0.2-0.3m SS | m2 | 31 | 28.8 | 892.8 | 50 | 1550 | 78.8 | 2442.8 | 1587.82 | 854.98
E | Hymenocallis littoralisBeach Spiderlily 0.3-0.4m OAH, 0.3-0.4m SS | m2 | 199 | 21.6 | 4298.4 | 50 | 9950 | 71.6 | 14248.4 | 9261.46 | 4986.94
| GRASSES | [9 empty] | 0
F | Cyperus alternifolius, 0.5-0.6m OAH and 0.3 -0.4 m SS | m2 | 107.31 | 18 | 1931.58 | 50 | 5365.5 | 68 | 7297.08 | 4743.102 | 2553.978
| SECRET GARDEN | [9 empty] | 0
| TREES | [9 empty] | 0
G | Ficus Benjamina Overall Height 1.5 Mtrs | Nos | 13 | 216 | 2808 | 100 | 1300 | 316 | 4108 | 2670.2 | 1437.8
| SHRUBS | [9 empty] | 0
H | Ficus microcarpa, hedge, 1.5m high | Nos | 78 | 135 | 10530 | 100 | 7800 | 235 | 18330 | 11914.5 | 6415.5
| GROUNDCOVERS | [9 empty] | 0
J | Alternanthera Brasiliana | m2 | 54.49 | 5.04 | 274.6296 | 50 | 2724.5 | 55.04 | 2999.1296 | 1949.4342 | 1049.6954
K | Ficus microcarpa 'Green Island Dwarf ficus 0.3-0.4m OAH , 0.3-0.4m SS | m2 | 11.2 | 32.4 | 362.88 | 50 | 560 | 82.4 | 922.88 | 599.872 | 323.008
| ACCENT PLANTS | [9 empty] | 0
L | Buxus microphylla 'Faulkner' (ball shape), 1.2m OAH | Nos | 12 | 270 | 3240 | 25 | 300 | 295 | 3540 | 2301 | 1239
M | Euonymus japonicus 'Green Rocket' (ball shape), 0.6m OAH | Nos | 40 | 135 | 5400 | 25 | 1000 | 160 | 6400 | 4160 | 2240
N | Westringia Fruticosa | Nos | 18 | 90 | 1620 | 25 | 450 | 115 | 2070 | 1345.5 | 724.5
P | Rosmarinus officinalis (ball shape) 0.35 m OAH | Nos | 41 | 288 | 11808 | 25 | 1025 | 313 | 12833 | 8341.45 | 4491.55
LEVEL 4 - RESIDENTIAL POOL
A | Planting engineered soil | m3 | 834 | [7 empty] | 0
B | Sweet soil | m3 | 834 | 45 | 37530 | 15 | 12510 | 60 | 50040 |  | 50040
| PALMS | [9 empty] | 0
C | Chamearops humilis, min 3 trunks, 1.0-1.5m CT -150-200 mm Caliper,2-3 m OAH and 1.5 - 2 m SS (PC Rate at AED 1,500) | Nos | 55 | 2880 | 158400 | 300 | 16500 | 3180 | 174900 | 113685 | 61215
D | Livingstonia chinensis - Chinese Fan Palm 0.5 - 0.75 m CT,250-300 mm Caliper, Height 2.0-3.0m,1.50-20m SS | Nos | 16 | 600 | 9600 | 300 | 4800 | 900 | 14400 | 9360 | 5040
E | Roystonea regia, 2.0-3.0m CT,300-350mm Cal,3-4m OAH & 1.5-2m SS | Nos | 34 | 8100 | 275400 | 300 | 10200 | 8400 | 285600 | 185640 | 99960
| TREES | [5 empty] | 0 |  | 0 |  | 0 |  |  |  | 640930
F | Ficus nitida, 2-2.5m CT, 150-180mm caliper,3.5-4.5m OAH & 2 - 2.5 m SS | Nos | 7 | 2700 | 18900 | 300 | 2100 | 3000 | 21000 | 13650 | 7350
| PALMS | [9 empty] | 0
G | Chamaerops humilis 'Vulcano' (Compact), 0.75-1.0m OAH and 0.50 - 0.75 m SS (PC Rate at AED 1,081.62) | Nos | 115 | 2350 | 270250 | 300 | 34500 | 2650 | 304750 | 198087.5 | 106662.5
| TREES | [9 empty] | 0
H | Plumeria 'Singapore Dawrf" White,0.2 - 0.5 m CT,60-90mm Caliper, 1.5-2.0m OAH and 1-1.5 m SS | Nos | 93 | 225 | 20925 | 150 | 13950 | 375 | 34875 | 22668.75 | 12206.25
| SHRUBS, GROUNDCOVERS & SUCCULENTS | [9 empty] | 0
J | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | m2 | 128.33 | 86.4 | 11087.712 | 50 | 6416.5 | 136.4 | 17504.212 | 11377.7378 | 6126.4742
K | Ficus microcarpa, hedge, 1.5m OAH,0.4-0.6 m SS | Nos | 184 | 135 | 24840 | 25 | 4600 | 160 | 29440 | 19136 | 10304
L | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 411 | 117 | 48087 | 50 | 20550 | 167 | 68637 | 44614.05 | 24022.95
M | MIXED PLANTS | [9 empty] | 0
N | Cyperus alternifolius, 0.5-0.6m OAH,0.3-0.4 m SS | m2 | 20 | 18 | 360 | 50 | 1000 | 68 | 1360 | 884 | 476
P | Alternanthera veriscolor, 0.1-0.2m OAH, 0.1 - 0.2 m SS | m2 | 20 | 7.56 | 151.2 | 50 | 1000 | 57.56 | 1151.2 | 748.28 | 402.92
| GROUNDCOVERS | [9 empty] | 0
A | Alternanthera amoena, 0.1-0.2m OAH and 0.1-0.2m SS | m2 | 152 | 8 | 1216 | 50 | 7600 | 58 | 8816 | 5730.4 | 3085.6
B | Carissa macrocarpa 'Boxwood Beauty', 0.15-0.2m OAH & 0.15 - 0.2 m SS | m2 | 276 | 28.8 | 7948.8 | 50 | 13800 | 78.8 | 21748.8 | 14136.72 | 7612.08
C | Sesuvium portulacastrum, 0.1-0.2m OAH and 0.1-0.2m SS | m2 | 343 | 5.4 | 1852.2 | 50 | 17150 | 55.4 | 19002.2 | 12351.43 | 6650.77
| ACCENT PLANTS | [9 empty] | 0
D | Cycas revoluta, 0.5-0.6m CT,200-300mm Cal,1-1.50m OAH & 0.8-1m SS | Nos | 68 | 990 | 67320 | 300 | 20400 | 1290 | 87720 | 57018 | 30702
LEVEL 4 - MEDITERRANEAN GARDEN
| TREES | [9 empty] | 0
A | Citrus Limon (Lemon Tree), 1 m CT,100 - 150 mm Caliper, o/a height 1.50-2.0m, and 1-1.5 m SS | Nos | 20 | 4500 | 90000 | 150 | 3000 | 4650 | 93000 | 60450 | 32550
B | Olea europea (Domestic Olive),1.5-2 m CT,200-250 mm Caliper, o/a height 3.50 -5 mm, and 2 -3 m SS | Nos | 26 | 6300 | 163800 | 300 | 7800 | 6600 | 171600 | 111540 | 60060
C | Olea europea (Domestic Olive), 1.5 - 2 m CT,100-150 mm Caliper,o/a height 2.5-3.5m, 1.5-2 m SS | Nos | 7 | 1980 | 13860 | 300 | 2100 | 2280 | 15960 | 10374 | 5586
D | Punica granatum (Pomegranate)1 m CT,100-120 mm Caliper,o/a height 1.5-2m, and 1 - 1.5 m SS Avail 30-40mm cal | Nos | 18 | 810 | 14580 | 150 | 2700 | 960 | 17280 | 11232 | 6048
| SHRUBS | [8 empty] | 0 | 0
E | Conocarpus erectus var sericeus(Silver-leaved Buttonwood) 1.5-2.0m OAH,1-1.5m SS | Nos | 220 | 450 | 99000 | 100 | 22000 | 550 | 121000 | 78650 | 42350
E1 | Ficus Microcarpa 40-60cm OAH | Nos | 104 | 10.8 | 1123.2 | 25 | 2600 | 35.8 | 3723.2 | 2420.08 | 1303.12
F | Rosmarinus officinalis (Rosemary),0.40-0.60m OAH,and 0.3-0.4 m SS | Nos | 212 | 21.6 | 4579.2 | 25 | 5300 | 46.6 | 9879.2 | 6421.48 | 3457.72
G | Rosmarinus officinalis 'Prostratus' .4 -0.6 m OAH,0.3 -0.4 m SS | Nos | 73 | 21.6 | 1576.8 | 25 | 1825 | 46.6 | 3401.8 | 2211.17 | 1190.63
| GROUNDCOVERS | [8 empty] | 0 | 0
J | Gazania pulchella 0.1 m - 0.2 m OAH,0.1 - 0.2 m SS | m2 | 2.13 | 12.96 | 27.6048 | 50 | 106.5 | 62.96 | 134.1048 | 87.1681 | 46.9367
K | Ocimum cinnamon 0.4 -0.5 m OAH,0.2m - 0.3 m SS | m2 | 22 | 32.4 | 712.8 | 50 | 1100 | 82.4 | 1812.8 | 1178.32 | 634.48
| PLANT MIXES | [8 empty] | 0 | 0
L | Vitex agnus-castus 0.8 m -1 m OAH,0.5-0.6 m SS | Nos | 66 | 21.6 | 1425.6 | 25 | 1650 | 46.6 | 3075.6 | 1999.14 | 1076.46
M | Alternanthera versicolor 0.1-0.2 m OAH, 0.1-0.2 m SS | m2 | 407 | 7.56 | 3076.92 | 50 | 20350 | 57.56 | 23426.92 | 15227.498 | 8199.422
| LEVEL 10 | [8 empty] | 0 | 0
| TALL PALMS | [8 empty] | 0 | 0
A | Planting engineered soil | m3 | 75 | [6 empty] | 0 | 0
B | Sweet soil | m3 | 75 | 45 | 3375 | 15 | 1125 | 60 | 4500 |  | 4500
C | Chamaerops humilis 'Vulcano', 0.75-1.0m OAH,0.5-0.75 m SS (PC Rate at AED 1,081.62) | Nos | 6 | 2250 | 13500 | 300 | 1800 | 2550 | 15300 | 9945 | 5355
D | Livistona chinensis, 0.5-0.75m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.5 - 2 m SS | Nos | 11 | 1080 | 11880 | 300 | 3300 | 1380 | 15180 | 9867 | 5313
E | Pritchardia pacifica, 1.0m CT,100-150mm Cal 1.5-2.0m OAH 1-1.5 m SS | Nos | 3 | 1710 | 5130 | 300 | 900 | 2010 | 6030 | 3919.5 | 2110.5
F | Trachycarpus fortunei, 1m CT,150-200mm Cal 1.5-2.0m OAH 1-1.50m SS | Nos | 9 | 1980 | 17820 | 300 | 2700 | 2280 | 20520 | 13338 | 7182
| SHRUBS182 | [8 empty] | 0 | 0
| Ficus Microcarpa (hedge) | Nos | 16 | 135 | 2160 | 100 | 1600 | 235 | 3760 | 2444 | 1316
| ACCENT PLANTS |  |  |  | 0 |  |  |  |  | 0 | 0
G | Zamia furfuracea Cardboard Palm, 0.5-0.6m OAH, supply spread 0.4-0.5m | Nos | 35 | 117 | 4095 | 50 | 1750 | 167 | 5845 | 3799.25 | 2045.75
| GOUND COVERS | [8 empty] | 0 | 0
H | Portulacaria afra, 0.2 3 -0.3 m OAH, 0.2 - 0.3 m SS | Nos | 470 | 4.5 | 2115 | 25 | 11750 | 29.5 | 13865 | 9012.25 | 4852.75
LEVEL 17
J | Planting engineered soil | m3 | 100 | [7 empty] | 0
K | Sweet soil | m3 | 100 | 45 | 4500 | 15 | 1500 | 60 | 6000 |  | 6000
| TREES | [9 empty] | 0
L | Butia capitata, 2m CT, 350-400 mm Caliper,3-4m OAH and 3 - 3.5 m SS | Nos | 6 | 2160 | 12960 | 300 | 1800 | 2460 | 14760 | 9594 | 5166
M | Ravenala madagascariensis (Travellers Palm),1m CT, 500mm Caliper, o/a Ht 5-6m, 3-3.5m SS (Spec 0.25 Clear Trunk; 2.5-3 Overall height) | Nos | 5 | 2880 | 14400 | 300 | 1500 | 3180 | 15900 | 10335 | 5565
N | Washingtonia filifera, 3.0m CT,500 mm Caliper, 5-6m OAH, and 3 m SS | Nos | 7 | 3240 | 22680 | 300 | 2100 | 3540 | 24780 | 16107 | 8673
| SHRUBS MIX 1 | [9 empty] | 0
P | Asparagus densiflorous sprengeri, 0.25-0.3m OAH, and 0.25 - 0.3 m SS | Nos | 182 | 8.1 | 1474.2 | 25 | 4550 | 33.1 | 6024.2 | 3915.73 | 2108.47
Q | Pennisetum alopecuroides, 0.5-0.6m OAH, and 0.4 - 0.5 m SS | Nos | 137 | 7.2 | 986.4 | 25 | 3425 | 32.2 | 4411.4 | 2867.41 | 1543.99
R | Euphorbia canariensis, 1.2-1.5m OAH,0.75 m - 0.9 m SS | Nos | 137 | 324 | 44388 | 25 | 3425 | 349 | 47813 | 31078.45 | 16734.55
| Sansevieria Cylindrica | Nos | 91 | 12.6 | 1146.6 | 25 | 2275 | 37.6 | 3421.6 | 2224.04 | 1197.56
T | Tichocerus Pasacana | Nos | 46 | 198 | 9108 | 25 | 1150 | 223 | 10258 | 6667.7 | 3590.3
| SHRUBS MIX 2 | [9 empty] | 0
A | Atriplex semibacatta, 0.15-0.2m OAH,0.15 - 0.2 m SS | Nos | 178 | 5.4 | 961.2 | 25 | 4450 | 30.4 | 5411.2 | 3517.28 | 1893.92
B | Cenchrus Ciliaris | Nos | 45 | 7.2 | 324 | 25 | 1125 | 32.2 | 1449 | 941.85 | 507.15
C | Agave attenata, 0.4m OAH and 0.5 m SS | Nos | 89 | 27 | 2403 | 25 | 2225 | 52 | 4628 | 3008.2 | 1619.8
D | Echinocactus grusonii, 0.25-0.3m OAH,0.25-0.3m SS | Nos | 59 | 81 | 4779 | 25 | 1475 | 106 | 6254 | 4065.1 | 2188.9
E | Opuntia basilaris | Nos | 45 | 45 | 2025 | 25 | 1125 | 70 | 3150 | 2047.5 | 1102.5
| SHRUBS MIX 3 | [9 empty] | 0
F | Aloe arborescens, 0.3-0.4m OAH,0.25-0.3 m SS | Nos | 36 | 12.6 | 453.6 | 25 | 900 | 37.6 | 1353.6 | 879.84 | 473.76
G | Atriplex Semibaccata 0.15-0.5 m OAH,0.15-0.2 m SS | Nos | 47 | 5.4 | 253.8 | 25 | 1175 | 30.4 | 1428.8 | 928.72 | 500.08
| GROUNDCOVERS | [9 empty] | 0
H | Asparagus densiflorous sprengeri, 0.2-0.3mOAH,0.25-0.3 m SS | Nos | 6 | 8.1 | 48.6 | 25 | 150 | 33.1 | 198.6 | 129.09 | 69.51
H1 | Atriplex Semibaccata 0 | Nos | 63 | 5.4 | 340.2 | 25 | 1575 | 30.4 | 1915.2 | 1244.88 | 670.32
| SUCCULANTS AND FEATURE PLANTS | [9 empty] | 0
J1 | Agave Attenuata | Nos | 8 | 27 | 216 | 25 | 200 | 52 | 416 | 270.4 | 145.6
J | Aloe arborescens, 0.3-0.4m OAH,0.25-0.3 m SS | Nos | 4 | 12.6 | 50.4 | 25 | 100 | 37.6 | 150.4 | 97.76 | 52.64
K | Euphorbia canariensis, 1.2-1.5m OAH,0.75-0.9 m SS | Nos | 16 | 324 | 5184 | 25 | 400 | 349 | 5584 | 3629.6 | 1954.4
L | Pachypodium lamerei | Nos | 18 | 153 | 2754 | 25 | 450 | 178 | 3204 | 2082.6 | 1121.4
M | Sansivieria cylindrica, 0.4-0.5m OAH,0.25-0.3 m SS | Nos | 6 | 12.6 | 75.6 | 25 | 150 | 37.6 | 225.6 | 146.64 | 78.96
N | Xanthorrhoea caespitosa (Replaced with Yucca Alternifolia) | Nos | 24 | 270 | 6480 | 25 | 600 | 295 | 7080 | 4602 | 2478
LEVEL 23 MEMBERS LOUNGE
A | Planting engineered soil | m3 | 35 | [7 empty] | 0
B | Sweet soil | m3 | 35 | 45 | 1575 | 15 | 525 | 60 | 2100 |  | 2100
C | Ficus nitida, 2-2.5m CT, 150-180mm Cal ,3.5-4.5m OAH & 2-2.5m SS | Nos | 9 | 2700 | 24300 | 300 | 2700 | 3000 | 27000 | 17550 | 9450
D | Eunoymus japonicus, 0.6m OAH and 0.6 m SS | Nos | 114 | 21.6 | 2462.4 | 25 | 2850 | 46.6 | 5312.4 | 3453.06 | 1859.34
LEVEL 24 TO LEVEL 29 RESIDENCE TOWER
E | Planting engineered soil | m3 | 300 | [7 empty] | 0
F | Sweet soil | m3 | 300 | 45 | 13500 | 15 | 4500 | 60 | 18000 |  | 18000
| PALMS | [9 empty] | 0
H | Livistona chinensis, 0.5-0.75m CT 250-300mm Cal 2-3m OAH 1.50-2m SS | Nos | 15 | 1080 | 16200 | 300 | 4500 | 1380 | 20700 | 13455 | 7245
| SHRUBS | [8 empty] | 0 | 0
J | Ficus microcarpa, hedge, 1.5m OAH,0.4 - 0.6 m SS | Nos | 115 | 135 | 15525 | 100 | 11500 | 235 | 27025 | 17566.25 | 9458.75
| ACCENT PLANTS | [8 empty] | 0 | 0
K | Cycas revoluta, 0.5-0.6m CT,200-300mm Cal 1.0-1.5m OAH & 0.8-1m SS | Nos | 7 | 990 | 6930 | 300 | 2100 | 1290 | 9030 | 5869.5 | 3160.5
L | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, SS 0.4-0.5m | Nos | 26 | 117 | 3042 | 50 | 1300 | 167 | 4342 | 2822.3 | 1519.7
| GROUNDCOVERS | [8 empty] | 0 | 0
M | Portulacaria afra 0.2 - 0.3 m OAH and 0.2 - 0.3 m SS | Nos | 307 | 4.5 | 1381.5 | 25 | 7675 | 29.5 | 9056.5 | 5886.725 | 3169.775
LEVEL 29 HOTEL TOWER
N | Planting engineered soil | m3 | 33 | [7 empty] | 0
P | Sweet soil | m3 | 33 | 45 | 1485 | 15 | 495 | 60 | 1980 |  | 1980
| SHRUBS MIX 1 |  |  |  | 0 | [5 empty] | 0
| Zamia Furfuracea | Nos | 26 | 117 | 3042 | 50 | 1300 | 167 | 4342 | 2822.3 | 1519.7
| Carissa Green Carpet | Nos | 78 | 7.2 | 561.6 | 25 | 1950 | 32.2 | 2511.6 | 1632.54 | 879.06
| SHRUBS MIX 2 | [9 empty] | 0
| Zamia Furfuracea | Nos | 13 | 117 | 1521 | 50 | 650 | 167 | 2171 | 1411.15 | 759.85
| Carissa Green Carpet | Nos | 39 | 7.2 | 280.8 | 25 | 975 | 32.2 | 1255.8 | 816.27 | 439.53
| Asparagus Densiforous Meyersi | Nos | 39 | 8.1 | 315.9 | 25 | 975 | 33.1 | 1290.9 | 839.085 | 451.815
| ADDITIONAL ITEMS | [9 empty] | 0
A | Maintenance for Softscape (Upto December 2021) | Item | 1 | 45000 | 45000 |  |  |  | 45000 |  | 45000
A1 | Maintenance for Softscape post TOC (12 Months) | Item | 1 | 180000 | 180000 |  |  |  | 180000 |  | 180000
B | Excavation and disposal for planting areas at Ground Level | m3 | 600 | 45 | 27000 |  |  |  | 27000 |  | 27000
| SUBTOTAL 1 - TOTAL TO SOFTSCAPE |  |  |  | 3561588.9944 |  | 749118.5 |  | 4310707.4944 | 2499943.8714 | 1810763.623
A | Tank and Pump |  |  |  |  | 4310707.4944 | 749118.5
1 | GRP Water Tank with internal partition 45m2x3mH=(135m3) 7mx6.5x3m) | item | 1 |  |  |  |  | 137750 | 137750
2 | Concrete foundation (reinforced) 8No. 0.5x.0.5x6.5m | item | 1 | [5 empty] | by others
3 | Steel channel frame 7mx100mm-channel x 6No. | m | 45 |  |  |  |  | 150 | 6750
4 | Tank vent with insect screen Ø2 | nos. | 2 |  |  |  |  | 350 | 700
5 | Access cover (lockable) 600x600mm | nos. | 2 |  |  |  |  | 1500 | 3000
6 | Inlet/out connections Ø3 | nos. | 4 |  |  |  |  | 250 | 1000
7 | Outlet Ø3 drain 40mm with isolation valve | nos. | 2 |  |  |  |  | 950 | 1900
8 | Pump suction outlet with isolation Ø4 valve | nos. | 3 |  |  |  |  | 2400 | 7200
9 | Pipe & fitting Ø4m2 for pump suction | m | 25 |  |  |  |  | 225 | 5625
10 | Filling line inlet 3Ø with motorized ball valve (back up) | nos. | 2 |  |  |  |  | 4000 | 8000
11 | Level sensors and cabling only to DDA & DDB | nos. | 8 |  |  |  |  | 1200 | 9600
12 | Cabling | item | 1 |  |  |  |  | 12000 | 12000
13 | Pump set - 1 duty standby with control panel VFD pressure vessel 200lt with all isolation valves etc. on (concrete foundation by others) | item | 1 |  |  |  |  | 125000 | 125000
[8 empty] | SUB-TOTAL (AED) | 318525 |  | 318525
B | Irrigation network
1 | Delivery Mainline & Submain | item | 1 |  |  |  |  | 148000 | 148000
2 | Control wire network and controllers | item | 1 |  |  |  |  | 127400 | 127400
[8 empty] | SUB-TOTAL (AED) | 275400 | 179010 | 96390
C | Secondary network
1 | Secondary Network including Solenoid valves (plastic), Pvc pipping and fittings, dripline, sleaves all as per details | item | 1 |  |  |  |  | 552900 | 552900
[8 empty] | SUB-TOTAL (AED) | 552900 | 359385 | 193515
D | Miscelleneous
1 | Shop drawing for irrigation only | item | 1 |  |  |  |  | 50000 | 50000
[8 empty] | SUB-TOTAL (AED) | 50000 | 17500 | 32500
| SUBTOTAL 2 - TOTAL TO IRRIGATION | [6 empty] | TOTAL AMOUNT | 1196825 | 555895 | 640930
GROUND LEVEL
A | 30mm thk polypropylene drainage cell | m2 | 1056 |  |  |  |  | 46 | 48576 |  | 48576
B | Non woven needle punched polypropylene geotextile | m2 | 1056 |  |  |  |  | 7.25 | 7656 |  | 7656
C | Planter drain | Nos | 48 | [5 empty] | N/A |  | N/A
LEVEL 02
D | 30mm thk polypropylene drainage cell | m2 | 1172 |  |  |  |  | 46 | 53912 |  | 53912
E | Non woven needle punched polypropylene geotextile | m2 | 1172 |  |  |  |  | 7.25 | 8497 |  | 8497
F | Planter drain | Nos | 32 | [5 empty] | N/A |  | N/A
LEVEL 04 RESIDENTIAL
G | 30mm thk polypropylene drainage cell | m2 | 2765 |  |  |  |  | 46 | 127190 |  | 127190
H | Non woven needle punched polypropylene geotextile | m2 | 2765 |  |  |  |  | 7.25 | 20046.25 |  | 20046.25
J | Planter drain | Nos | 138 | [5 empty] | N/A |  | N/A
LEVEL 10
K | 30mm thk polypropylene drainage cell | m2 | 136 |  |  |  |  | 46 | 6256 |  | 6256
L | Non woven needle punched polypropylene geotextile | m2 | 136 |  |  |  |  | 7.25 | 986 |  | 986
LEVEL 17
M | 30mm thk polypropylene drainage cell | m2 | 550 |  |  |  |  | 46 | 25300 |  | 25300
N | Non woven needle punched polypropylene geotextile | m2 | 550 |  |  |  |  | 7.25 | 3987.5 |  | 3987.5
LEVEL 23
A | 30mm thk polypropylene drainage cell | m2 | 124 |  |  |  |  | 46 | 5704 |  | 5704
B | Non woven needle punched polypropylene geotextile | m2 | 124 |  |  |  |  | 7.25 | 899 |  | 899
LEVEL 24 to 29 RESIDENTIAL
C | 30mm thk polypropylene drainage cell | m2 | 298.43 |  |  |  |  | 46 | 13727.78 |  | 13727.78
D | Non woven needle punched polypropylene geotextile | m2 | 298.43 |  |  |  |  | 7.25 | 2163.6175 |  | 2163.6175
LEVEL 29 HOTEL
E | 30mm thk polypropylene drainage cell | m2 | 148 |  |  |  |  | 46 | 6808 |  | 6808
F | Non woven needle punched polypropylene geotextile | m2 | 148 |  |  |  |  | 7.25 | 1073 |  | 1073
| To Summary | [7 empty] | 332782.1475 |  | 332782.1475
| Less Discount | [7 empty] | 49997.91 |  | 49997.91
| SUBTOTAL 3 - TOTAL TO DRAINAGE GEOTEXTILE | [7 empty] | 282784.2375 |  | 282784.2375
No | DESCRIPTION OF WORK
GROUND LEVEL
D | Butia Capitata, 3-4 m OAH + Block work below | No. | 66 |  |  |  |  | 390 | 25740 |  | 25740
G | Butia Capitata, 3-4 m OAH + Block work below | No. | 5 |  |  |  |  | 390 | 1950 |  | 1950
LEVEL 2
F | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 10 |  |  |  |  | 390 | 3900 |  | 3900
G | Phoenix Rebelenii 2-3m OAH + Block work below | No. | 14 |  |  |  |  | 390 | 5460 |  | 5460
H | Olivia Europea 3.0m OAH + Block work below | No. | 7 |  |  |  |  | 390 | 2730 |  | 2730
LEVEL 4 Residential Pool
A | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 16 |  |  |  |  | 390 | 6240 |  | 6240
B | Roystonea Regia 3-4m OAH + Block work below | No. | 34 |  |  |  |  | 390 | 13260 |  | 13260
C | Ficus Nitida 3.5-4.5m OAH + Block work below | No. | 7 |  |  |  |  | 390 | 2730 |  | 2730
LEVEL 4 Mediterranean Garden
A | Olivia Europea 3.5-5.0m OAH + Block work below | No. | 26 |  |  |  |  | 420 | 10920 |  | 10920
B | Olivia Europea 2.5-3.5m OAH + Block work below | No. | 7 |  |  |  |  | 390 | 2730 |  | 2730
C | Butia Capitata, 3-4 m OAH + Block work below | No. | 6 |  |  |  |  | 390 | 2340 |  | 2340
LEVEL 10
A | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 11 |  |  |  |  | 390 | 4290 |  | 4290
G | Chamaerops humilis 'vulcano', | No. | 14 |  |  |  |  | 390 | 5460 |  | 5460
H | Pritchardia fortunei, 1.5-2.0m OAH+Block work below | No. | 3 |  |  |  |  | 390 | 1170 |  | 1170
LEVEL 23 MEMBERS LOUNGE
A | Ficus Nitida 3.5-4.5m OAH + Block work below | No. | 9 |  |  |  |  | 390 | 3510 |  | 3510
LEVEL 24 to LEVEL 29 RESIDENCE TOWER
A | Livistona Chinesis, 2-3 m OAH + Block work below | No. | 10 |  |  |  |  | 390 | 3900 |  | 3900
| SUBTOTAL 4 - TOTAL TO TREE & PALM ANCHORING | [7 empty] | 96330 |  | 96330
GROUND LEVEL + LEVEL 2
1 | Installation of Pavers Approx 6000 sq m | m2 | 6000 |  |  |  |  | 80.4255 | 482552.8 | 71540.0611 | 411012.7389
2 | Euro Grout with Application Approx 7000 sq m at AED12 per sq m | m2 | 7000 |  |  |  |  | 12 | 84000 | 12792 | 71208
| SUBTOTAL 5 - HARDSCAPE INSTALLATIONS | [7 empty] | 566552.8 | 84332.0611 | 482220.7389 |  | 0.73889 | 0.0091868
Overall Summary
1 | SUBTOTAL 1 - TOTAL TO SOFTSCAPE | [7 empty] | 4310707.4944 | 2499943.8714 | 1810763.623 | 2189877.8605
2 | SUBTOTAL 2 - TOTAL TO IRRIGATION | [7 empty] | 1196825 | 555895 | 640930
3 | SUBTOTAL 3 - TOTAL TO DRAINAGE GEOTEXTILE | [7 empty] | 282784.2375 | 0 | 282784.2375
4 | SUBTOTAL 4 - TOTAL TO TREE & PALM ANCHORING | [7 empty] | 96330 | 0 | 96330
5 | SUBTOTAL 5 - HARDSCAPE INSTALLATIONS | [7 empty] | 566552.8 | 84332.0611 | 482220.7389
| TOTAL SUMMARY | [7 empty] | 6453199.5319 | 3140170.9325 | 3313028.5994

## Softscape BOQ (hidden)
PLOT-18
BILL OF QUANTITIES
BILL :- SOFTSCAPE - SOIL, TREES, PALM & SHRUBS | [9 empty] | PREVIOUS |  |  | THIS MONTH |  |  | CUMULATIVE
Item | Description | Qty. | Unit | Rate | Amount | Rate | Amount | Rate | Amount | QTY | % | Amount | QTY | % | Amount | QTY | % | Amount |  | Remarks
[5 empty] | (Dhs.) |  | (Dhs.)
SOIL, TREES, PALM & SHRUBS
| GROUND LEVEL | [21 empty] | reviewed and confirmed
A | Planting engineered soil | 1548 | m3 | 255.01 | 394755.48 |  |  | 180 | 278640 | [11 empty] | 394755.48 |  | increased
B | Sweet soil | 1548 | m3 | 73.62 | 113963.76 |  |  | 50 | 77400 | [11 empty] | 113963.76
| PALMS | [7 empty] | 0 | [11 empty] | 0
C | Acoelorraphe wrightii (multi-stemmed), 1.0m Clear Trunk, 100-150 mm Caliper,2.0-3.0m Over All Heigh and 1.50 to 2 m Supply Spread | 10 | Nos | 4470.75 | 44707.5 |  |  | 4470.75 | 44707.5 | [11 empty] | 44707.5
D | Butia capitata, 2 m CT,250-300 mm Caliper ,3-4 m OAH and 2.50 m to 3 m SS | 66 | Nos | 5573.92 | 367878.72 |  |  | 6967.4 | 459848.4 | [11 empty] | 367878.72
E | Chamaerops humilis 'Vulcano - minimum 5 Trunks, 1-1.5 m CT,150-200 mm Caliper, 2-3 m OAH ad 1.50 -2 m SS (PC Rate) | 4 | Nos |  |  |  |  | 1611.21 | 6444.84
F | Livistona chinensis, 0.5-0.75m CT,250-300 mm Caliper, 2.0-3.0m OAH and 1.50 to 2 m SS | 31 | Nos | 2033.13 | 63027.03 |  |  | 2033.13 | 63027.03 | [11 empty] | 63027.03
G | Trachycarpus fortunei, 1.0m CT,100-150 mm Caliper, 1.5-2.0m OAH,and 1.0 - 1.5 m SS | 6 | Nos | 1741.85 | 10451.1 |  |  | 1741.85 | 10451.1 | [11 empty] | 10451.1
H | Washingtonia robusta, 3.0-4.0m CT,350-400 mm Caliper,4- 5 m OAH, and 2.50 -3 m SS | 22 | Nos | 2419.24 | 53223.28 | 3750 |  | 2419.24 | 53223.28 | [11 empty] | 53223.28
| PALM MIXES | [7 empty] | 0 | [11 empty] | 0
| PALMS MIX 1 | [7 empty] | 0 | [11 empty] | 0
J | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT, 150-200 mm Caliper,2.0-3.0 m OAH and 1.50 -2 m SS (PC Rate at AED1,500) | 39 | Nos | 1527.94 | 59589.66 |  |  | 1500 | 58500 | [11 empty] | 59589.66
K | Cycas revoluta, 0.5-0.6m CT,200-300 mm Caliper, 1.0-1.5m OAH and 0.80m - 1 m SS | 52 | Nos | 938.66 | 48810.32 | 420 |  | 420 | 21840 | [11 empty] | 48810.32
| PALMS MIX 2 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
L | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150 - 200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED1,500) | 43 | Nos | 1527.94 | 65701.42 |  |  | 1500 | 64500 | [11 empty] | 65701.42
M | Ravenala madagascariensis (Travellers Palm),0.25 m CT,300 - 400 mm Caliper, 2.5-3.0m OAH, supply spread 1.50 - 2 m | 43 | Nos | 1432.89 | 61614.27 |  |  | 1576.179 | 67775.697 | [11 empty] | 61614.27
N | Pritchardia pacifica, 1.0m CT,100 - 150 mm Caliper, 1.5-2.0m OAH and 1 - 1.5 m SS | 43 | Nos | 1725.62 | 74201.66 |  |  | 1725.62 | 74201.66 | [11 empty] | 74201.66
| GROUNDCOVERS |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
P | Alternanthera amoena, 0.1-0.2m OAH and 0.1 - 0.2 m SS | 1088 | m2 | 28.29 | 30779.52 | 24 | 26112 | 24 | 26112 | [11 empty] | 30779.52
Q | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | 2 | m2 | 56.25 | 112.5 |  |  | 125 | 250 | [11 empty] | 112.5
R | Carissa macrocarpa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | 179.33 | m2 | 38.71 | 6941.8643 |  | 0 | 38.71 | 6941.8643 | [11 empty] | 6941.8643
S | Ficus microcarpa 'Green Island' Dwarf ficus 0.3-0.4m OAH and 0.3-0.4m SS | 274.89 | m2 | 48.38 | 13299.1782 |  |  | 48.38 | 13299.1782 | [11 empty] | 13299.1782
0
| To Collection Dhs |  |  |  | 1409057.2625 |  |  |  | 1327162.5495 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| GROUNDCOVERS (CONT'D) | [19 empty] | 0
A | Hymenocallis littoralis Beach Spiderlily 0.3-0.4m OAH and 0.3-0.4m SS | 116.75 | m2 | 96.77 | 11297.8975 |  |  | 96.77 | 11297.8975 | [11 empty] | 11297.8975
0
| GRASSES |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
B | Cyperus alternifolius, 0.5-0.6m OAH and 0.30 - 0.40 m SS | 213.26 | m2 | 133.53 | 28476.6078 | 160 |  | 133.53 | 28476.6078 | [11 empty] | 28476.6078
| CLIMBERS |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
C | Bougainvillea spectabilis 0.80 - 1 m OAH and 0.30 - 0.4 m SS | 11 | No |  | To be Priced | 25 |  | 25 | 275 | [10 empty] | New item | 0
D | Quisqualis indica (white flower), Rangoon creeper, 1.0-1.5m OAH, 0.5-0.6m SS | 13 | No |  | To be Priced | 25 |  | 50 | 650 | [10 empty] | New item | 0
0
| PALMS |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
F | Acoelorraphe wrightii (multi-stemmed), 1.0m CT, 100 -150 mm Caliper,2.0-3.0m OAH and 1.50 - 2 m SS | 3 |  | 4470.75 | 13412.25 |  |  | 4470.75 | 13412.25 | [11 empty] | 13412.25
G | Butia capitata, 2 m CT, 250 - 300 mm Caliper,3-4 m OAH and 2.50 - 3 m SS | 5 |  | 5573.92 | 27869.6 |  |  | 5573.92 | 27869.6 | [11 empty] | 27869.6
H | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150 -200 mm Caliper, 2.0-3.0m OAH and 1.5 - 2 m SS | 3 |  | 1527.94 | 4583.82 |  |  | 1604.337 | 4813.011 | [11 empty] | 4583.82
J | Livistona chinensis, 0.5-0.75m CT,250-300 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS | 4 |  | 2033.13 | 8132.52 |  |  | 2033.13 | 8132.52 | [11 empty] | 8132.52
K | Trachycarpus fortunei, 1.0m CT,100-150 mm Caliper, 1.5-2.0m OAH and 1- 1.50 m SS | 9 |  | 1741.85 | 15676.65 |  |  | 1741.85 | 15676.65 | [11 empty] | 15676.65
L | Washingtonia robusta, 3.0-4.0m CT,350-400 mm Caliper,4 - 4.50 m OAH and 2.5 - 3 m SS | 7 |  | 2419.24 | 16934.68 | 3750 |  | 2419.24 | 16934.68 | [6 empty] | 7 | 100% | 16934.68 |  |  | 16934.68
[5 empty] | 0 |  |  |  | 0 | [11 empty] | 0
| SHRUBS MIX 1 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
M | Crinum asiaticum (Giant Spider Lily), o/a height 0.4-0.5m, supply spread 0.2-0.3m. | 79 | Nos | 53.22 | 4204.38 |  |  | 53.22 | 4204.38 | [11 empty] | 4204.38
N | Cycas revoluta, 0.5-0.6m CT, 200-300 mm Caliper1.0-1.5m OAH and 0.80 - 1 m SS | 7 | Nos | 938.66 | 6570.62 | 420 |  | 420 | 2940 | [11 empty] | 6570.62
P | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, supply spread 0.4-0.5m | 79 | Nos | 67.74 | 5351.46 |  |  | 67.74 | 5351.46 | [6 empty] | 79 |  |  |  |  | 5351.46
Q | Asparagus densiflorous Meyersii, 0.2-0.3m OAH and 0.20-0.3 m SS | 19.66 |  | 56.25 | 1105.875 |  |  | 56.25 | 1105.875 | [11 empty] | 1105.875
R | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | 19.66 |  | 38.71 | 761.0386 |  |  | 38.71 | 761.0386 | [11 empty] | 761.0386
| To Collection Dhs |  |  |  | 144377.3989 |  |  |  | 141900.9699 |  |  | 0 |  |  | 0 |  |  | 16934.68 |  |  | 0
| SHRUBS MIX 1 (CONT'D) | [19 empty] | 0
A | Hymenocallis littoralis Beach Spiderlily 0.3-0.4m OAH and 0.3-0.4m SS | 19.66 | m2 | 96.77 | 1902.4982 |  |  | 96.77 | 1902.4982 | [11 empty] | 1902.4982
0
| SHRUBS MIX 2 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
B | Crinum asiaticum (Giant Spider Lily), o/a height 0.4-0.5m, supply spread 0.2-0.3m. | 11 | Nos | 53.22 | 585.42 |  |  | 53.22 | 585.42 | [11 empty] | 585.42
C | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, supply spread 0.4-0.5m | 11 | Nos | 67.74 | 745.14 |  |  | 67.74 | 745.14 | [6 empty] | 11 |  |  |  |  | 745.14
D | Asparagus densiflorous Meyersii, 0.2-0.3m OAH and 0.20 - 0.3 m SS | 3 | m2 | 56.25 | 168.75 |  |  | 56.25 | 168.75 | [11 empty] | 168.75
E | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH and 0.2-0.3m SS | 3 | m2 | 38.71 | 116.13 |  |  | 38.71 | 116.13 | [11 empty] | 116.13
0
0
0
0
0
0
0
0
0
0
0
0
| To Collection Dhs |  |  |  | 3517.9382 |  |  |  | 3517.9382 | [11 empty] | 0
| LEVEL 2 | [19 empty] | 0
A | Planting engineered soil | 619 | m3 | 255.01 | 157851.19 |  |  | 180 | 111420 | [11 empty] | 157851.19
B | Sweet soil | 619 | m3 | 73.62 | 45570.78 |  |  | 50 | 30950 | [11 empty] | 45570.78
| PALMS |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
C | Acoelorraphe wrightii (multi-stemmed), 1.0m CT,100-150 mm caliper, 2.0-3.0m OAH and 1.50 - 2 m SS | 9 | Nos | 5527.71 | 49749.39 |  |  | 5527.71 | 49749.39 | [11 empty] | 49749.39
D | Copernicia alba, 1.5m CT, 200-250 mm Caliper,2.5-3.5m OAH and 1 - 1.50 m SS | 34 | Nos | 3771.35 | 128225.9 |  |  | 3771.35 | 128225.9 | [11 empty] | 128225.9
E | Chamaerops humilis 'Vulcano' 1-1.50 m CT,150-200 mm Caliper, 2.0-3.0 m OAH and 1.50 - 2 m SS (PC Rate) | 30 | Nos | 1081.62 | 32448.6 |  |  | 1081.62 | 32448.6 | [11 empty] | 32448.6
F | Livistona chinensis, 0.5-0.75m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.5 - 2 m SS | 10 | Nos | 2014.74 | 20147.4 |  |  | 2014.74 | 20147.4 | [11 empty] | 20147.4
G | Phoenix rebelenii,0.5 0.75 m CT,150-200 mm caliper, and 2-3 m OAH and 1.50 - 2 m SS | 16 | Nos | 3762 | 60192 | 500 | 8000 | 500 | 8000 | [10 empty] | New item | 60192
H | Rhapis excelsa (Min. 8 trunks),1-1.50 m CT,50-100 mm caliper,2-2.5 m OAH and 1-1.50 m SS | 7 | Nos | 3573 | 25011 |  |  | 3573 | 25011 | [6 empty] | 7 | 100% |  |  |  | 25011
J | Trachycarpus fortunei, 1.0m CT,100 -150 mm Caliper, 1.5-2.0m OAH and 1 - 1.50 m SS | 29 | Nos | 1001.56 | 29045.24 |  |  | 1001.56 | 29045.24 | [11 empty] | 29045.24
K | Washingtonia robusta, 2.0-3.0m CT,300-350 mm Caliper, 3.0-4.0m OAH and 1.50 - 2 m SS | 18 | Nos | 2249.89 | 40498.02 | 850 | 15300 | 850 | 15300 | [10 empty] | Not shown in drawing,but listed in schedule | 40498.02
L | Washingtonia robusta (Medium), 1.5-2.0m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.50 - 2 m SS | 12 | Nos | 2014.74 | 24176.88 | 1000 |  |  | 12000 | [6 empty] | 12 | 100% | 12000 |  |  | 24176.88
| PALM MIXES |  |  |  | 0 | [15 empty] | 0
| PALMS MIX 1 |  |  |  | 0 | [15 empty] | 0
M | Chamaerops humilis (Min. 3 trunks), 1.0-1.5m CT,150-200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED 1,500) | 41 | Nos | 1527.94 | 62645.54 |  |  | 1500 | 61500 | [11 empty] | 62645.54
N | Cycas revoluta, 0.5-0.6m CT, 200-300 mm Caliper,1.0-1.5m OAH, and 0.80 - 1 m SS | 53 | Nos | 1205.63 | 63898.39 | 420 |  | 420 | 22260 | [11 empty] | 63898.39
| PALMS MIX 2 |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
P | Chamaerops humilis (Min. 3 trunks), 1.0-1.5mCT,150-200 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS (PC Rate at AED 1,500) | 7 | Nos | 1527.94 | 10695.58 |  |  | 1500 | 10500 | [11 empty] | 10695.58
Q | Ravenala madagascariensis,0.25 m CT,300-400 mm Caliper, 2.5-3 m OAH and 1.50 - 2 m SS | 7 | Nos | 1432.89 | 10030.23 |  |  | 1576.179 | 11033.253 | [11 empty] | 10030.23
R | Pritchardia pacifica, 1.0m CT, 100-150mm Caliper,1.5-2.0m OAH and 1 - 1.50 m SS | 7 | Nos | 1725.62 | 12079.34 |  |  | 1725.62 | 12079.34 | [11 empty] | 12079.34
0
| To Collection Dhs |  |  |  | 772265.48 |  |  |  | 579670.123 |  |  | 0 |  |  | 0 |  |  | 12000 |  |  | 0
0
| GROUNDCOVERS | [19 empty] | 0
A | Alternanthera amoena, 0.1-0.2m OAH and 0.1 - 0.2 m SS | 163 | m2 | 28.29 | 4611.27 |  |  | 28.29 | 4611.27 | [11 empty] | 4611.27
B | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | 23 | m2 | 56.25 | 1293.75 |  |  | 125 | 2875 | [11 empty] | 1293.75
C | Carissa macrocarpa 'Boxwood Beauty', 0.15-0.2m OAH and 0.15 -0.2 m SS | 126 | m2 | 86.41 | 10887.66 |  |  | 86.41 | 10887.66 | [11 empty] | 10887.66
D | Carissa 'Green Carpet' (Natal Plum) 0.2-0.3m OAH, 0.2-0.3m SS | 31 | m2 | 38.71 | 1200.01 |  |  | 38.71 | 1200.01 | [11 empty] | 1200.01
E | Hymenocallis littoralisBeach Spiderlily 0.3-0.4m OAH, 0.3-0.4m SS | 199 | m2 | 67.74 | 13480.26 |  |  | 67.74 | 13480.26 | [11 empty] | 13480.26
| GRASSES |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
F | Cyperus alternifolius, 0.5-0.6m OAH and 0.3 -0.4 m SS | 107.31 | m2 | 133.53 | 14329.1043 |  |  | 133.53 | 14329.1043 | [11 empty] | 14329.1043
| SECRET GARDEN |  |  |  | 0 | [15 empty] | 0
| TREES |  |  |  | 0 | [13 empty] | PROVISIONAL SUM |  | 0
G | Olive Tree | 7 | Nos |  | Excluded |  |  | 11000 | Lumpsum | [9 empty] | 77000 |  | 0
| SHRUBS | [19 empty] | 0
H | Ficus microcarpa, hedge, 1.5m high | 45 | Nos |  | Excluded |  |  | 20 | Lumpsum | [9 empty] | 900 |  | 0
| GROUNDCOVERS | [19 empty] | 0
J | Alternanthera amoena | 45 | m2 |  | Excluded |  |  | 24 | Lumpsum | [9 empty] | 1080 |  | 0
K | Ficus microcarpa 'Green Island'Dwarf ficus 0.3-0.4m OAH , 0.3-0.4m SS | 10 | m2 |  | Excluded |  |  | 48.38 | Lumpsum | [9 empty] | 483.8 |  | 0
| ACCENT PLANTS | [19 empty] | 0
L | Buxus microphylla 'Faulkner' (ball shape), 1.2m OAH | 10 | Nos |  | Excluded |  |  | 150 | Lumpsum | [9 empty] | 1500 |  | 0
M | Euonymus japonicus 'Green Rocket' (ball shape), 0.6m OAH | 20 | Nos |  | Excluded |  |  | 150 | Lumpsum | [9 empty] | 3000 |  | 0
N | Olea europaea (ball shape), 0.80m | 14 | Nos |  | Excluded |  |  | 150 | Lumpsum | [9 empty] | 2100 |  | 0
P | Rosmarinus officinalis (ball shape) 0.35 m OAH | 28 | Nos |  | Excluded |  |  | 150 | Lumpsum | [9 empty] | 4200 |  | 0
[19 empty] | 90263.8 |  | 0
| To Collection Dhs |  |  |  | 45802.0543 |  |  |  | 47383.3043 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| LEVEL 4 - RESIDENTIAL POOL | [19 empty] | 0
A | Planting engineered soil | 834 | m3 | 255.01 | 212678.34 |  |  | 180 | 150120 | [11 empty] | 212678.34
B | Sweet soil | 834 | m3 | 73.62 | 61399.08 |  |  | 50 | 41700 | [11 empty] | 61399.08
| PALMS | [7 empty] | 0 | [11 empty] | 0
C | Chamearops humilis, min 3 trunks, 1.0-1.5m CT -150-200 mm Caliper,2-3 m OAH and 1.5 - 2 m SS (PC Rate at AED 1,500) | 55 | Nos | 1527.94 | 84036.7 |  |  | 1500 | 82500 | [11 empty] | 84036.7
D | Livingstonia chinensis - Chinese Fan Palm 0.5 - 0.75 m CT,250-300 mm Caliper, Height 2.0-3.0m,1.50-20m SS | 16 | Nos | 2014.74 | 32235.84 |  |  | 2014.74 | 32235.84 | [11 empty] | 32235.84
E | Roystonea regia, 2.0-3.0m CT,300-350mm Caliper,3-4 m OAH and 1.5 - 2 m SS | 35 | Nos | 4429.14 | 155019.9 |  |  | 4429.14 | 155019.9 | [11 empty] | 155019.9
| TREES | [7 empty] | 0 | [11 empty] | 0
F | Ficus nitida, 2-2.5m CT, 150-180mm caliper,3.5-4.5m OAH and 2 - 2.5 m SS | 7 | Nos | 4624.51 | 32371.57 |  |  | 4624.51 | 32371.57 | [11 empty] | 32371.57
| INTERMEDIARY PLANTS | [7 empty] | 0 | [11 empty] | 0
| PALMS | [7 empty] | 0 | [11 empty] | 0
G | Chamaerops humilis 'Vulcano' (Compact), 0.75-1.0m OAH and 0.50 - 0.75 m SS (PC Rate) | 108 | Nos | 1081.62 | 116814.96 |  |  | 1081.62 | 116814.96 | [11 empty] | 116814.96
| TREES | [7 empty] | 0 | [11 empty] | 0
H | Plumeria 'Singapore Dawrf" White,0.2 - 0.5 m CT,60-90mm Caliper, 1.5-2.0m OAH and 1-1.5 m SS | 85 | Nos | 1192.2 | 101337 |  |  | 1192.2 | 101337 | [11 empty] | 101337
| SHRUBS, GROUNDCOVERS & SUCCULENTS | [19 empty] | 0
J | Rosmarinus officinalis, Common Rosemary, 0.4-0.6m OAH, 0.3-0.4m SS | 128.33 | m2 | 56.25 | 7218.5625 |  |  | 125 | 16041.25 | [11 empty] | 7218.5625
K | Ficus microcarpa, hedge, 1.5m OAH,0.4-0.6 m SS | 184 | Nos | 72.62 | 13362.08 |  |  | 72.62 | 13362.08 | [11 empty] | 13362.08
L | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, supply spread 0.4-0.5m | 411 | Nos | 61.74 | 25375.14 |  |  | 61.74 | 25375.14 | [6 empty] | 411 |  |  |  |  | 25375.14
M | MIXED PLANTS | [7 empty] | 0 | [11 empty] | 0
N | Cyperus alternifolius, 0.5-0.6m OAH,0.3-0.4 m SS | 20 | m2 | 25.16 | 503.2 |  |  | 25.16 | 503.2 | [11 empty] | 503.2
P | Alternanthera veriscolor, 0.1-0.2m OAH, 0.1 - 0.2 m SS | 20 | m2 | 42.82 | 856.4 | 24 |  | 42.82 | 856.4 | [11 empty] | 856.4
0
| To Collection Dhs |  |  |  | 843208.7725 |  |  |  | 768237.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| GROUNDCOVERS | [19 empty] | 0
A | Alternanthera amoena, 0.1-0.2m OAH and 0.1-0.2m SS | 152 | m2 | 28.29 | 4300.08 | 24 |  | 24 | 3648 | [11 empty] | 4300.08
B | Carissa macrocarpa 'Boxwood Beauty', 0.15-0.2m OAH and 0.15 - 0.2 m SS | 276 | m2 | 38.71 | 10683.96 |  |  | 38.71 | 10683.96 | [11 empty] | 10683.96
C | Sesuvium portulacastrum, 0.1-0.2m OAH and 0.1-0.2m SS | 343 | m2 | 38.71 | 13277.53 | 24 |  | 24 | 8232 | [11 empty] | 13277.53
| ACCENT PLANTS | [7 empty] | 0 | [11 empty] | 0
D | Cycas revoluta, 0.5-0.6m CT,200 -300 mm Caliper,1-1.50m OAH and 0.8 - 1 m SS | 68 | Nos | 987.05 | 67119.4 | 350 |  | 420 | 28560 | [11 empty] | 67119.4
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| To Collection Dhs |  |  |  | 95380.97 |  |  |  | 51123.96 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
| LEVEL 4 - MEDITERRANEAN GARDEN | [19 empty] | 0
| TREES | [19 empty] | 0
A | Citrus Limon (Lemon Tree), 1 m CT,100 - 150 mm Caliper, o/a height 1.50-2.0m, and 1-1.5 m SS | 21 | Nos | 3870.78 | 81286.38 |  |  | 4064.319 | 85350.699 | [11 empty] | 81286.38
B | Olea europea (Domestic Olive),1.5-2 m CT,200-250 mm Caliper, o/a height 3.50 -5 mm, and 2 -3 m SS | 26 | Nos | 10186.25 | 264842.5 |  |  | 10000 | 260000 | [9 empty] | 260000 |  | 264842.5
C | Olea europea (Domestic Olive), 1.5 - 2 m CT,100-150 mm Caliper,o/a height 2.5-3.5m, 1.5-2 m SS | 7 | Nos | 7639.69 | 53477.83 |  |  | 7500 | 52500 | [9 empty] | 52500 |  | 53477.83
D | Punica granatum (Pomegranate)1 m CT,100-120 mm Caliper,o/a height 1.5-2m, and 1 - 1.5 m SS | 18 | Nos | 1693.46 | 30482.28 |  |  | 2540.19 | 45723.42 | [11 empty] | 30482.28
| SHRUBS | [7 empty] | 0 | [11 empty] | 0
E | Conocarpus erectus var sericeus(Silver-leaved Buttonwood) 1.5-2.0m OAH,1-1.5m SS | 159 | Nos | 193.54 | 30772.86 | 40 |  | 60 | 9540 | [11 empty] | 30772.86
F | Rosmarinus officinalis (Rosemary),0.40-0.60m OAH,and 0.3-0.4 m SS | 203 | Nos | 43.34 | 8798.02 |  |  | 25 | 5075 | [11 empty] | 8798.02
G | Rosmarinus officinalis 'Prostratus' .4 -0.6 m OAH,0.3 -0.4 m SS | 76 | Nos | 43.34 | 3293.84 |  |  | 25 | 1900 | [11 empty] | 3293.84
H | Espalier Olive grove 0.90 m dia | 7 | Nos |  |  | 1500 |  | 1500 | 10500 | [10 empty] | Shown in drawing and not on LMS drawing | 0
| GROUNDCOVERS | [7 empty] | 0 | [11 empty] | 0
J | Gazania pulchella 0.1 m - 0.2 m OAH,0.1 - 0.2 m SS | 2.13 | m2 | 359.76 | 766.2888 |  |  | 359.76 | 766.2888 | [11 empty] | 766.2888
K | Ocimum cinnamon 0.4 -0.5 m OAH,0.2m - 0.3 m SS | 22 | m2 | 62.9 | 1383.8 |  |  | 62.9 | 1383.8 | [11 empty] | 1383.8
| PLANT MIXES | [7 empty] | 0 | [11 empty] | 0
L | Vitex agnus-castus 0.8 m -1 m OAH,0.5-0.6 m SS | 116 | Nos | 342.43 | 39721.88 |  |  | 342.43 | 39721.88 | [11 empty] | 39721.88
M | Alternanthera versicolor 0.1-0.2 m OAH, 0.1-0.2 m SS | 29.13 | m2 | 38.71 | 1127.6223 | 24 |  | 24 | 699.12 | [11 empty] | 1127.6223
0
0
0
| To Collection Dhs |  |  |  | 515953.3011 |  |  |  | 513160.2078 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
PLOT-18
BILL OF QUANTITIES
BILL :- SOFTSCAPE - SOIL, TREES, PALM & SHRUBS
Item | Description | Qty. | Unit | Rate | Amount | Rate | Amount | Rate | Amount | [10 empty] | Remarks
[5 empty] | (Dhs.) |  | (Dhs.)
SOIL, TREES, PALM & SHRUBS
| LEVEL 10 | [21 empty] | reviewed and confirmed
|  |  |  | 255.01 | 0 |  |  |  | 0 | [11 empty] | 0 |  | increased
| TALL PALMS |  |  | 73.62 | 0 |  |  |  | 0 | [11 empty] | 0
[9 empty] | 0 | [11 empty] | 0
A | Planting engineered soil | 75 | m3 | 4470.75 | 335306.25 |  |  | 180 | 13500 | [11 empty] | 335306.25
|  |  |  | 5573.92 | 0 |  |  |  | 0 | [11 empty] | 0
B | Sweet soil | 75 | m3 |  |  |  |  | 50 | 3750
|  |  |  | 2033.13 | 0 |  |  |  | 0 | [11 empty] | 0
C | Chamaerops humilis 'Vulcano', 0.75-1.0m OAH,0.5-0.75 m SS (PC Rate) | 7 | Nos | 2419.24 | 16934.68 | 3750 |  | 1081.62 | 7571.34 | [11 empty] | 16934.68
[9 empty] | 0 | [11 empty] | 0
D | Livistona chinensis, 0.5-0.75m CT, 250-300 mm Caliper,2.0-3.0m OAH and 1.5 - 2 m SS | 12 | Nos |  |  |  |  | 2014.74 | 24176.88 | [11 empty] | 0
|  |  |  | 1527.94 | 0 |  |  |  | 0 | [11 empty] | 0
E | Pritchardia pacifica, 1.0m CT,100-150 mm Caliper, 1.5-2.0m OAH and 1-1.5 m SS | 3 | Nos | 938.66 | 2815.98 | 420 |  | 1725.62 | 5176.86 | [11 empty] | 2815.98
[5 empty] | 0 |  |  |  | 0 | [11 empty] | 0
F | Trachycarpus fortunei, 1.0m CT,150 - 200 mm Caliper, 1.5-2.0m OAH and 1-1.50 m SS | 11 | Nos | 1527.94 | 16807.34 |  |  | 1741.85 | 19160.35 | [11 empty] | 16807.34
|  |  |  | 1432.89 | 0 |  |  |  | 0 | [11 empty] | 0
| ACCENT PLANTS |  |  | 1725.62 | 0 |  |  |  | 0 | [11 empty] | 0
[5 empty] | 0 |  |  |  | 0 | [11 empty] | 0
G | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m OAH, supply spread 0.4-0.5m | 48 | Nos | 28.29 | 1357.92 | 24 | 1152 | 67.74 | 3251.52 | [6 empty] | 48 |  |  |  |  | 1357.92
|  |  |  | 56.25 | 0 |  |  |  | 0 | [11 empty] | 0
| GOUND COVERS |  |  | 38.71 | 0 |  | 0 |  | 0 | [11 empty] | 0
H | Portulacaria afra, 0.2 3 -0.3 m OAH, 0.2 - 0.3 m SS | 46 | m2 | 48.38 | 2225.48 |  |  | 86.41 | 3974.86 | [11 empty] | 2225.48
0
| To Collection Dhs |  |  |  | 375447.65 |  |  |  | 80561.81 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| LEVEL 17 | [19 empty] | 0
J | Planting engineered soil | 100 | m3 |  |  |  |  | 180 | Lumpsum | [11 empty] | 0 | 18000
[21 empty] | 0 | 0
K | Sweet soil | 100 | m3 |  |  |  |  | 50 | Lumpsum | [11 empty] | 0 | 5000
[20 empty] | New item | 0 | 0
| TREES | [18 empty] | New item | 0 | 0
0
L | Butea capitata, 2m CT, 350-400 mm Caliper,3-4m OAH and 3 - 3.5 m SS | 6 | Nos |  |  |  |  | 6967.4 | Lumpsum | [11 empty] | 0 | 41804.4
[21 empty] | 0 | 0
M | Ravenala madagascariensis (Travellers Palm),1 m CT,500 mm Caliper, o/a height 5-6m, 3 - 3.5 m SS | 5 | Nos |  |  |  |  | 3152.36 | Lumpsum | [11 empty] | 0 | 15761.8
[21 empty] | 0 | 0
N | Washingtonia filifera, 3.0m CT,500 mm Caliper, 5-6m OAH, and 3 m SS | 7 | Nos |  |  |  |  | 1935.39 | Lumpsum | [11 empty] | 0 | 13547.73
[21 empty] | 0 | 0
| SHRUBS MIX 1 | [19 empty] | 0 | 0
[21 empty] | 0 | 0
P | Asparagus densiflorous sprengeri, 0.25-0.3m OAH, and 0.25 - 0.3 m SS | 19.16 | m2 |  |  |  |  | 56.25 | Lumpsum | [11 empty] | 0 | 1077.75
[21 empty] | 0 | 0
Q | Pennisetum alopecuroides, 0.5-0.6m OAH, and 0.4 - 0.5 m SS | 172 | Nos |  |  |  |  | 31.75 | Lumpsum | [11 empty] | 0 | 5461
[21 empty] | 0 | 0
R | Euphorbia canariensis, 1.2-1.5m OAH,0.75 m - 0.9 m SS | 172 | Nos |  |  |  |  | 55.17 | Lumpsum | [11 empty] | 0 | 9489.24
[21 empty] | 0 | 0
| To Collection Dhs |  |  |  | 0 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
[21 empty] | 0 | 0
| SOIL, TREES, PALM & SHRUBS (CONT'D) |  |  | 96.77 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
[9 empty] | 0 | [12 empty] | 0
| LEVEL 17 (CONT'D) |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0 | 0
|  |  |  | 53.22 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
T | Tichocerus Pasacana | 58 | Nos | 67.74 | 3928.92 |  |  | 80 | Lumpsum | [11 empty] | 3928.92 | 4640
| SHRUBS MIX 2 |  |  | 56.25 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
|  |  |  | 38.71 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
A | Atriplex semibacatta, 0.15-0.2m OAH,0.15 - 0.2 m SS | 13.08 | m2 |  |  |  |  | 70.3 | Lumpsum | [11 empty] | 0 | 919.524
B | Cenchrus Ciliaris | 39 | No |  |  |  |  | 8.4 | Lumpsum | [11 empty] | 0 | 327.6
[21 empty] | 0 | 0
C | Agave attenata, 0.4m OAH and 0.5 m SS | 78 | Nos |  |  |  |  | 67.59 | Lumpsum | [11 empty] | 0 | 5272.02
[21 empty] | 0 | 0
D | Echinocactus grusonii, 0.25-0.3m OAH,0.25-0.3m SS | 53 | Nos |  |  |  |  | 61.74 | Lumpsum | [12 empty] | 3272.22
0
E | Opuntia basilaris | 39 | No |  |  |  |  | 38.4 | Lumpsum | [12 empty] | 1497.6
| SHRUBS MIX 3 | [20 empty] | 0
0
F | Aloe arborescens, 0.3-0.4m OAH,0.25-0.3 m SS | 36 | Nos |  |  |  |  | 32.47 | Lumpsum | [12 empty] | 1168.92
[21 empty] | 0 | 0
G | Atriplex Semibaccata 0.15-0.5 m OAH,0.15-0.2 m SS | 4 | m2 |  |  |  |  | 70.3 | Lumpsum | [11 empty] | 0 | 281.2
| GROUNDCOVERS | [20 empty] | 0
H | Asparagus densiflorous sprengeri, 0.2-0.3mOAH,0.25-0.3 m SS | 1.4 | m2 |  |  |  |  | 56.25 | Lumpsum | [11 empty] | 0 | 78.75
0
0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
[21 empty] | 0 | 0
| To Collection Dhs |  |  |  | 3928.92 |  |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 0
[21 empty] | 0 | 0
| SOIL, TREES, PALM & SHRUBS (CONT'D) |  |  | 255.01 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
|  |  |  | 73.62 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
| LEVEL 17 (CONT'D) |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0 | 0
| SUCCULANTS AND FEATURE PLANTS |  |  | 5527.71 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
|  |  |  | 3771.35 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
J | Aloe arborescens, 0.3-0.4m OAH,0.25-0.3 m SS | 18 | Nos | 1081.62 | 19469.16 |  |  | 32.47 | Lumpsum | [11 empty] | 19469.16 | 584.46
|  |  |  | 2014.74 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
K | Euphorbia canariensis, 1.2-1.5m OAH,0.75-0.9 m SS | 16 | Nos | 3762 | 60192 | 500 | 8000 | 55.17 | Lumpsum | [10 empty] | New item | 60192 | 882.72
|  |  |  | 3573 | 0 |  |  |  | 0 | [11 empty] | 0 | 0
L | Pachypodium lamerei | 18 | Nos | 1001.56 | 18028.08 |  |  | 822.54 | Lumpsum | [11 empty] | 18028.08 | 14805.72
|  |  |  | 2249.89 | 0 | 850 | 0 |  | 0 | [10 empty] | Not shown in drawing,but listed in schedule | 0 | 0
M | Sansivieria cylindrica, 0.4-0.5m OAH,0.25-0.3 m SS | 15 | Nos | 2014.74 | 30221.1 | 1000 |  | 55.17 | Lumpsum | [11 empty] | 30221.1 | 827.55
[5 empty] | 0 | [15 empty] | 0 | 0
N | Xanthorrhoea caespitosa | 24 | Nos |  | 0 |  |  | 2025.27 | Lumpsum | [11 empty] | 0 | 48606.48
|  |  |  | 1527.94 | 0 |  |  |  | 0 | [11 empty] | 0
| LEVEL 23 MEMBERS LOUNGE |  |  | 1205.63 | 0 | 420 |  |  | 0 | [11 empty] | 0
[5 empty] | 0 |  |  |  | 0 | [11 empty] | 0
A | Planting engineered soil | 35 | m3 | 1527.94 | 53477.9 |  |  | 180 | 6300 | [11 empty] | 53477.9
|  |  |  | 1432.89 | 0 |  |  |  | 0 | [11 empty] | 0
B | Sweet soil | 35 | m3 | 1725.62 | 60396.7 |  |  | 50 | 1750 | [11 empty] | 60396.7
0
| To Collection Dhs |  |  |  | 241784.94 |  |  |  | 8050 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| SOIL, TREES, PALM & SHRUBS (CONT'D) | [19 empty] | 0
| LEVEL23 (CONT'D) |  |  | 28.29 | 0 |  |  |  | 0 | [11 empty] | 0
C | Ficus nitida, 2-2.5m CT, 150-180mm caliper,3.5-4.5 m OAH and 2-2.5 m SS | 9 | Nos | 56.25 | 506.25 |  |  | 4624.51 | 41620.59 | [11 empty] | 506.25
|  |  |  | 86.41 | 0 |  |  |  | 0 | [11 empty] | 0
D | Eunoymus japonicus, 0.6m OAH and 0.6 m SS | 104 | Nos | 38.71 | 4025.84 |  |  | 25.9 | 2693.6 | [11 empty] | 4025.84
|  |  |  | 67.74 | 0 |  |  |  | 0 | [11 empty] | 0
| LEVEL 24 TO LEVEL 29 RESIDENCE TOWER |  |  |  | 0 |  |  |  | 0 | [11 empty] | 0
|  |  |  | 133.53 | 0 |  |  |  | 0 | [11 empty] | 0
E | Planting engineered soil | 300 | m3 |  | 0 |  |  | 180 | 54000 | [11 empty] | 0
[5 empty] | 0 | [13 empty] | PROVISIONAL SUM |  | 0
F | Sweet soil | 300 | m3 |  | Excluded |  |  | 50 | 15000 | [9 empty] | 1500000 |  | 0
| PALMS | [19 empty] | 0
H | Livistona chinensis, 0.5-0.75m CT,250-300 mm Caliper, 2.0-3.0m OAH and 1.50 - 2 m SS | 15 | Nos |  | Excluded |  |  | 2014.74 | 30221.1 | [9 empty] | 300 |  | 0
0
| SHRUBS |  |  |  | Excluded | [13 empty] | 0 |  | 0
[5 empty] | Excluded | [13 empty] | 0 |  | 0
J | Ficus microcarpa, hedge, 1.5m OAH,0.4 - 0.6 m SS | 99 | Nos |  |  |  |  | 72.62 | 7189.38 | [11 empty] | 0
| ACCENT PLANTS |  |  |  | Excluded | [13 empty] | 0 |  | 0
[5 empty] | Excluded | [13 empty] | 0 |  | 0
K | Cycas revoluta, 0.5-0.6m CT,200-300 mm Cliper 1.0-1.5m OAH and 0.8-1 m SS | 7 | Nos |  | Excluded |  |  | 420 | 2940 | [9 empty] | 1050 |  | 0
[5 empty] | Excluded | [13 empty] | 0 |  | 0
L | Zamia furfuracea (Cardboard Palm), o/a height 0.5-0.6m, supply spread 0.4-0.5m | 26 | Nos |  |  |  |  | 67.74 | 1761.24 | [6 empty] | 26 |  |  | 1501350 |  | 0
| To Collection Dhs |  |  |  | 4532.09 |  |  |  | 155425.91 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| SOIL, TREES, PALM & SHRUBS (CONT'D) |  |  | 255.01 | 0 |  |  |  | 0 | [11 empty] | 0
| LEVEL24 to LEVEL 29 (CONT'D) |  |  | 73.62 | 0 |  |  |  | 0 | [11 empty] | 0
| GROUNDCOVERS | [7 empty] | 0 | [11 empty] | 0
|  |  |  | 1527.94 | 0 |  |  |  | 0 | [11 empty] | 0
M | Portulacaria afra 0.2 - 0.3 m OAH and 0.2 - 0.3 m SS | 19.14 | m2 | 2014.74 | 38562.1236 |  |  | 86.41 | 1653.8874 | [11 empty] | 38562.1236
|  |  |  | 4429.14 | 0 |  |  |  | 0 | [11 empty] | 0
| LEVEL 29 HOTEL TOWER | [7 empty] | 0 | [11 empty] | 0
|  |  |  | 4624.51 | 0 |  |  |  | 0 | [11 empty] | 0
N | Planting engineered soil | 33 | m3 |  |  |  |  | 180 | 5940 | [11 empty] | 0
[9 empty] | 0 | [11 empty] | 0
P | Sweet soil | 33 | m3 | 1081.62 | 35693.46 |  |  | 50 | 1650 | [11 empty] | 35693.46
[9 empty] | 0 | [11 empty] | 0
Q | Ficus microcarpa, hedge, 1.5m OAH,0.4 - 0.6 m SS | 30 | Nos | 1192.2 | 35766 |  |  | 72.62 | 2178.6 | [11 empty] | 35766
0
|  |  |  | 56.25 | 0 |  |  |  | 0 | [11 empty] | 0
|  |  |  | 72.62 | 0 |  |  |  | 0 | [11 empty] | 0
|  |  |  | 61.74 | 0 |  |  |  | 0 | [11 empty] | 0
[9 empty] | 0 | [11 empty] | 0
|  |  |  | 25.16 | 0 |  |  |  | 0 | [11 empty] | 0
|  |  |  | 42.82 | 0 | 24 |  |  | 0 | [11 empty] | 0
0
| To Collection Dhs |  |  |  | 110021.5836 |  |  |  | 11422.4874 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| SOIL, TREES, PALM & SHRUBS (CONT'D) | [19 empty] | 0
0
| ADDITIONAL ITEMS | [19 empty] | 0
0
A | Maintenance for Softscape | 1 | Item | 101862.54 | 101862.54 |  |  | 86862.54 | 86862.54 | [11 empty] | 101862.54
[9 empty] | 0 | [11 empty] | 0
A1 | Maintenance for Softscape post TOC | 1 | Item |  |  |  |  | 15000 | 15000
B | Excavation and disposal for planting areas at Ground Level | 600 | m3 | 29.55 | 17730 |  |  | 29.55 | 17730 | [11 empty] | 17730
0
C | Landscape lighting | 1 | Item | [17 empty] | 0
0
D | Irrigation system | 1 | Item | [17 empty] | 0
0
E | 100 mm thick comoacted aggregate base | 1 | Item | [17 empty] | 0
0
F | Internal rubber fire stone liner | 1 | Item | [17 empty] | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| To Collection Dhs. |  |  |  | 119592.54 |  |  |  | 119592.54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| SOIL, TREES, PALM & SHRUBS (CONT'D) | [19 empty] | 0
0
| COLLECTION | [19 empty] | 0
0
| Page 1/1 |  |  |  | 1409057.2625 |  |  |  | 1327162.5495 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/2 |  |  |  | 144377.3989 |  |  |  | 141900.9699 |  |  | 0 |  |  | 0 |  |  | 16934.68 |  |  | 0
0
| Page 1/3 |  |  |  | 3517.9382 |  |  |  | 3517.9382 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/4 | [7 empty] | 579670.123 |  |  | 0 |  |  | 0 |  |  | 12000 |  |  | 0
0
| Page 1/5 |  |  |  | 772265.48 |  |  |  | 47383.3043 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/6 |  |  |  | 45802.0543 |  |  |  | 768237.34 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/7 |  |  |  | 843208.7725 |  |  |  | 51123.96 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/8 |  |  |  | 95380.97 |  |  |  | 513160.2078 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/9 |  |  |  | 515953.3011 |  |  |  | 80561.81 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/10 |  |  |  | #REF! |  |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | 0
0
| Page 1/11 |  |  |  | #REF! |  |  |  | NA |  |  | NA |  |  | NA |  |  | NA |  |  | 0
0
| Page 1/11 |  |  |  | #REF! |  |  |  | 8050 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/12 |  |  |  | 119592.54 |  |  |  | 155425.91 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/12 | [7 empty] | 11422.4874 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
| Page 1/12 | [7 empty] | 119592.54 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
| To Summary |  |  |  | #REF! |  |  |  | 3807209.1401 |  |  | 0 |  |  | 0 |  |  | 28934.68 |  |  | 4684870.9011
2189877.8605
1617331.2796