## Cover (hidden)
Payment Application
Tax Registration Number : 100240059400003
Invoice Address:
Khansaheb Civil Engineering (KCE)
P.O.Box 2716
Dubai, UAE
To
Saman Kulasooriya
Invoice No. |  | Invoice Date | Job No.
201D22009/04/Feb/2023 |  | 2023-02-27 | 201D22009
Project : Dorchester Hotel & residances
S. No. | Description |  | Amount (Dhs.)
1 | We herewith invoicing you for the works carried out for the period ending February 2023 for the above-mentioned project as per the attached list. |  | 968682.1054
| Amount of this invoice (before VAT)..Dhs. |  | 968682.1054
UAE Six Hundred Sixty-three Thousand Two Hundred Eighteen and Fils (46/100) Only
THIS IS NOT A TAX INVOICE
Tax Invoice will be issued after the receipt of the corresponding payment certificate
for Khansaheb Civil Engineering L.L.C.
Archie Clift
Divisional Manager - Joinery Division

## Summary (hidden)
CONTRACTOR'S PAYMENT APPLICATION
Project No: |  | Project:
201D22009 |  | Dorchester - KCE |  |  |  | Contract Type: | Lumpsum
CONTRACT DETAILS | [5 empty] | Payment Application No. |  | 4
Grand Summary | [5 empty] | Interim / Final: |  | Iterim
Employer
Architect | [5 empty] | For Period Ending: |  | 2023-02-28
Consultant | [5 empty] | Issue Date: |  | 2023-02-27
Main Contractor
Contract Value |  | AED | 2105729.8665 |  |  | Commencement Date |  | 2022-10-14
Day Works |  | AED |  |  |  | Completion Date |  | 2023-03-31
Original Contract value |  | AED |  |  |  | EoT Awarded | Days
Variation Orders Issued |  | AED | 2983196.2754 |  |  | Revised Completion Date
Variations Submitted/ Agreed/Anticipated |  | AED | 610447.594
|  | AED | 5699373.7359 |  |  | Payment Due Date |  | 2023-04-28
PAYMENT DETAILS
This Application for payment is issued under the terms of the above mentioned Contract | [5 empty] | Cumulative (AED) | Previous claim | Interim (AED)
Gross Valuation of the Work
A | Cumulative Value of Work Done |  |  |  |  | 1037835.9306 | 574609.5823 | 463226.3483
B | Preliminaries
C | Variation Works |  |  |  |  | 829440.7243 | 81814.4408 | 747626.2835
D | Claims
[5 empty] | Sub-total ( E ) | 1867276.6549 | 656424.0231 | 1210852.6318
Add
E | Advance payment |  |  |  | 20% | 421145.9733 | 421145.9733 | 0
Less
F | Retention |  |  |  | 0%
G | Recovery of Advance Payment @ 20% of Sub-total ( E ) |  |  |  | 20% | 373455.331 | 131284.8046 | 242170.5264
[5 empty] | Sub-total ( H ) | 1914967.2972 | 946285.1918 | 968682.1054
J | AMOUNT FOR PAYMENT ON THIS CERTIFICATE (AED) |  |  |  |  | 968682.1054
Amount in words : |  | UAE Six Hundred Sixty-three Thousand Two Hundred Eighteen and Fils (46/100) Only
Position |  |  | Name | Date |  | Signature
Contractor - Khansaheb - Joinery
Quantity Surveyor |  |  | Renjini Andrews | 2023-02-27
Divisional Manager |  |  | Archie Clift | 2023-02-27

## Summary (2)
CONTRACTOR'S PAYMENT APPLICATION
Project No: |  | Project:
201D22009 |  | Dorchester - KCE |  |  |  | Contract Type: | Lumpsum
CONTRACT DETAILS | [5 empty] | Payment Application No. |  | 3
Grand Summary | [5 empty] | Interim / Final: |  | Advance
Employer
Architect | [5 empty] | For Period Ending: |  | 2023-01-31
Consultant | [5 empty] | Issue Date: |  | 2023-01-24
Main Contractor
Contract Value |  | AED | 2105729.8665 |  |  | Commencement Date |  | 2022-01-01
Day Works |  | AED |  |  |  | Completion Date |  | 2022-08-16
Original Contract value |  | AED |  |  |  | EoT Awarded | Days
Variation Orders Issued |  | AED | 2719104.0625 |  |  | Revised Completion Date
Variations Submitted/ Agreed/Anticipated |  | AED | 253979.4729
|  | AED | 5078813.4019 |  |  | Payment Due Date |  | 2022-12-23
PAYMENT DETAILS
This Application for payment is issued under the terms of the above mentioned Contract | [5 empty] | Cumulative (AED) | Previous claim | Interim (AED)
Gross Valuation of the Work
A | Cumulative Value of Work Done |  |  |  |  | 1037835.9306 | 810993.5956 | 226842.335
B | Preliminaries
C | Variation Works |  |  |  |  | 829440.7243 | 527631.6326 | 301809.0917
D | Claims
[5 empty] | Sub-total ( E ) | 1867276.6549 | 1338625.2282 | 528651.4267
Add
E | Advance payment |  |  |  | 20% | 421145.9733 | 421145.9733 | 0
Less
F | Retention |  |  |  | 0%
G | Recovery of Advance Payment @ 20% of Sub-total ( E ) |  |  |  | 20% | 373455.331 | 267725.0456 | 105730.2853
[5 empty] | Sub-total ( H ) | 1914967.2972 | 1492046.1558 | 422921.1414
J | AMOUNT FOR PAYMENT ON THIS CERTIFICATE (AED) |  |  |  |  | 422921.1414
Amount in words : |  | UAE Two Hundred Sixty-eight Thousand Five Hundred Thirty-seven and Fils (54/100) Only
Position |  |  | Name | Date |  | Signature
Contractor - Khansaheb - Joinery
Quantity Surveyor |  |  | Renjini Andrews | 2023-01-24
Divisional Manager |  |  | Archie Clift | 2023-01-24
[5 empty] | KCE Claim | 1609503.654 | 663218.464 | 3030101.31
[5 empty] | Difference | -117457.4982 | -240297.3226 | -1115134.0128

## Headboard & Wall paneling
BOQ Ref | Bill description | Qty | Unit | Rate | Amount | Previous Work done % | Previous Work done value | Current Work done % | Current Work done value | Current Claim | Remarks
1 | PRELIMINARIES |  |  |  | 44174.43 |  | 17669.772 |  | 17669.772 | 0
1/A | Supervision, Transportation, Drafting, | 1 | No | 44174.43 | 44174.43 |  | 17669.772 |  | 17669.772 | 0 | 40%
1 | HEADBOARD |  |  |  | 1464397.74 |  | 524260.9685 |  | 675884.2155 | 151623.247
1 | KING ROOM |  |  |  | 270658.5 |  | 79241.75 |  | 135329.25 | 56087.5
1/B | STANDARD KING ROOM 703 SCHEME BLUE Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-703-BE-02 (EXCLUDED LIGHTS & METAL FIXING) | 50 | Each | 3169.67 | 158483.5 | 50% | 79241.75 | 50% | 79241.75 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/C | Fabric FA-14 Futura Leathers | 500 | m2 | 224.35 | 112175 |  |  | 50% | 56087.5 | 56087.5 | MIR
1 | TWIN ROOM |  |  |  | 238179.48 |  | 69732.74 |  | 119089.74 | 49357
1/D | STANDARD TWIN ROOM 703 SCHEME - BLUE Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-703-BE-02 (EXCLUDED LIGHTS & METAL FIXING) | 44 | Each | 3169.67 | 139465.48 | 50% | 69732.74 | 50% | 69732.74 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/E | Fabric FA-14 Futura Leathers | 440 | m2 | 224.35 | 98714 |  |  | 50% | 49357 | 49357 | MIR
1 | STD KING ROOM |  |  |  | 302155.29 |  | 136295.81 |  | 151077.645 | 14781.835
1/F | STANDARD KING ROOM 704 SCHEME - PINK Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-704-BE-02 (EXCLUDED LIGHTS & METAL FIXING) | 57 | Each | 3169.67 | 180671.19 | 50% | 90335.595 | 50% | 90335.595 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/G | Fabric FA-19 Futura Leathers | 570 | m2 | 213.13 | 121484.1 |  | 45960.215 | 50% | 60742.05 | 14781.835 | MIR
1 | JUNIOR ROOM |  |  |  | 116621.34 |  | 45960.215 |  | 58310.67 | 12350.455
1/H | JUNIOR SUITE KING ROOM - 704 SCHEME - PINK Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-JUNIOR SUITE (EXCLUDED LIGHTS & METAL FIXING) | 22 | Each | 3169.67 | 69732.74 | 50% | 34866.37 | 50% | 34866.37 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/I | Fabric FA-19 Futura Leathers | 220 | m2 | 213.13 | 46888.6 |  | 11093.845 | 50% | 23444.3 | 12350.455 | MIR
1 | JUNIOR ROOM |  |  |  | 37106.79 |  | 19018.02 |  | 26477.57 | 7459.55
1/J | JUNIOR SUITE TWIN ROOM - 704 SCHEME - PINK Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-JUNIOR SUITE (EXCLUDED LIGHTS & METAL FIXING) | 7 | Each | 3169.67 | 22187.69 | 50% | 11093.845 | 50% | 11093.845 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/K | Fabric FA-19 Futura Leathers | 70 | m2 | 213.13 | 14919.1 |  |  | 50% | 7459.55 | 7459.55 | MIR
1 | 1 BED SUITE KING ROOM |  |  |  | 38036.04 |  | 19018.02 |  | 19018.02 | 0
1/L | 1 BED SUITE KING - NEW SCHEME (CREAM) WITH DINING Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-1 BEDROOM SUITE (EXCLUDED LIGHTS & METAL FIXING) | 12 | Each | 3169.67 | 38036.04 | 50% | 19018.02 | 50% | 19018.02 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/M | Fabric FA-39 Naturtex | 48 | Lm |  |  |  | 0 |  | 0 | 0 | EXCLUDED
1 | 1 BED SUITE TWIN ROOM |  |  |  | 15848.35 |  | 0 |  | 0 | 0
1/N | 1 BED SUITE TWIN - NEW SCHEME (CREAM) WITH DINING Size: 2900mm W x 100mm D x 1200mm H HEADBOARD DRG. GB-OMN-HTL-FFE-HEADBOARD-1 BEDROOM SUITE (EXCLUDED LIGHTS & METAL FIXING) | 5 | Each | 3169.67 | 15848.35 | 50% | 7924.175 | 50% | 7924.175 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
1/O | Fabric FA-39 Naturtex | 20 | Lm | [7 empty] | EXCLUDED
2 | SENIOR 1 BED SUITE KING ROOM |  |  |  | 349772.96 |  | 128826.499 |  | 128826.499 | 0
2/A | SENIOR 1 BED SUITE KING /1 BED DELUXE Size: (3950mm + 1000mm + 300mm) W x 50mm D x 1300mm H HEADBOARD. DRG. GB-OMN-HTL-ONE BED SUITE DELUXE (EXCLUDED LIGHTS) | 19 | Each | 7950.85 | 151066.15 | 50% | 75533.075 | 50% | 75533.075 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
2/B | Fabric FA-23 Fabrics (Bisson Bruneel) | 170 | Lm | 430.48 | 73181.6 | 72.82% | 53293.424 | 72.82% | 53293.424 | 0 | 123.80 Rm fabric received MIR
2/C | GL-04 Glass panel for above headboard | 19 | No | 6606.59 | 125525.21
2 | FEATUER SUITE KING ROOM |  |  |  | 68370.35 |  | 16490.8905 |  | 28077.7975 | 11586.907
2/D | FEATURE SUITES KING/1 BED DUPLEX Size: 3710mm H x 95mm D x 1340mm H HEADBOARD DRG. GB-OMN-HTL-ONE BED SUITE DELUXE (EXCLUDED LIGHTS & METAL FIXING) | 7 | Each | 5816.55 | 40715.85 | 35% | 14250.5475 | 35% | 14250.5475 | 0 | Cutting list issued, machining under progress.
2/E | Fabric HTL-FA-09 Fabrics | 50 | Lm | 553.09 | 27654.5 |  | 2240.343 | 50% | 13827.25 | 11586.907 | MIR
2 | ROYAL SUITE |  |  |  | 13655.92 |  | 4779.572 |  | 4779.572 | 0
2/F | ROYAL SUITE Headboard on Master Bedroom as detailed shown on DET. 01 - RS-2608-321 HEADBOARD. DRG. DET. 01 - RS-2608-321 (EXCLUDED METAL & WALL PAPER) (EXCLUDED LIGHTS) | 1 | Each | 6400.98 | 6400.98 | 35% | 2240.343 | 35% | 2240.343 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
2/G | Fabric FA-20 Fabrics (Dedar) | 9 | Lm | [7 empty] | EXCLUDED
2/H | ROYAL SUITE Twin Headboard on Secondary Bedroom as detailed shown on Dwg. No. - RS-2608-330, DET. 01 HEADBOARD (EXCLUDED LIGHTS) | 1 | Each | 7254.94 | 7254.94 | 35% | 2539.229 | 35% | 2539.229 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
2/I | Fabric FA-21 Fabrics (Dedar) | 14.5 | Lm | [7 empty] | EXCLUDED
2 | PRESIDENTIAL SUITE |  |  |  | 13992.72 |  | 4897.452 |  | 4897.452 | 0
2/J | PRESIDENTIAL SUITE Upholstered headboard on Master Bedroom as detailed shown on Dwg. No. - PRES-1902-200 SEC. AA,BB, 1902-204 SEC. MM,NN HEADBOARD (EXCLUDED LIGHTS) | 1 | Each | 7072.19 | 7072.19 | 35% | 2475.2665 | 35% | 2475.2665 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
2/K | Fabric FA-22 Fabrics (Nobilis) | 14.5 | Lm | [7 empty] | EXCLUDED
2/L | PRESIDENTIAL SUITE Upholstered headboard on Twin Bedroom as detailed shown on Dwg. No. - PRES-1902-208 HEADBOARD (EXCLUDED LIGHTS) | 1 | Each | 6920.53 | 6920.53 | 35% | 2422.1855 | 35% | 2422.1855 | 0 | First fix framing completed, activity % - framing-35%, Upholstery-45%(15%+30%) & site installation 20%.
2/M | Fabric FA-23 Fabrics (Nobilis) | 15 | Lm | [7 empty] | EXCLUDED
3 | PRELIMINARIES |  |  |  | 36145.6 |  | 0 |  | 0 | 0
3/A | Supervision,Transportation, Drafting, | 1 | No | 36145.6 | 36145.6
4 | WALL FINISHES |  |  |  | 321182.4744 |  | 141505.032 |  | 216724.12 | 75219.088
4 | PACKAGE -3 - ROYAL SUITE FIT-OUT |  |  |  | 9139.9144 |  | 0 |  | 0 | 0
4 | WALL FINISHES - LEFT WING
4 | Timber Wall Panel including all necessary framing, fitting, fixing, backing framing support, decoration, etc and the like all in accordance with drawings and specifications.
4 | Supply and fixing of Timber Cladding; Type HTL-WD-01
4/A | Living Room | 3.7 | m2 | 552.18 | 2043.066
4 | Supply and fixing of Timber Cladding; Type HTL-WD-19
4/B | Wood panel with frame at Entry Vestibule | 10.43 | m2 | 552.18 | 5759.2374
4 | Skirting
4 | Timber Skirting including all necessary timber support, framing, fittings, fixing accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
4/C | Supply and fixing of Timber Skirting; Type Baseboard HTL-WD-01; Walnut, 150mm high | 5.79 | m | 171.05 | 990.3795
4/D | Supply and fixing of Timber Skirting; Type Baseboard HTL-WD-19; US Walnut, 150mm high | 2.03 | m | 171.05 | 347.2315
4 | PACKAGE -4 - HOTEL GF LOBBY AND L1 CORRIDOR |  |  |  | 57487.58 |  | 34492.548 |  | 45990.064 | 11497.516
4 | Wall Panelling Works Supply and installation of Fluted Wall Panelling including all necessary framing, fitting, fixing, backing framing support, finishes, decoration, provision of the Niche etc and the like all in accordance with drawings and specifications.
4/E | Fluted Wall Panelling to GF Lobby including the finishes type; HTL-PT-04, White Paint, color All white N° 2005 - Matte finish | 47 | m2 | 1223.14 | 57487.58 | 60% | 34492.548 | 80% | 45990.064 | 11497.516 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
4 | PACKAGE -2 - LEVEL 01 BALL ROOM |  |  |  | 254554.98 |  | 107012.484 |  | 170734.056 | 63721.572
4 | Wall Finishes Wall finish including preparation of substrate, render, filler, primer, undercoat(s), finish coats, all necessary fittings, fixings accessories to complete all in accordance with the drawings and specifications
4 | Level 1
4 | Ball room
4/F | wall panel ; type HTL-WD-19 | 145 | m2 | 552.18 | 80066.1 | 40% | 32026.44 | 80% | 64052.88 | 32026.44 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
4/G | Wall panelling ; type HTL-WD-19 Meeting Room -02 | 28 | m2 | 552.18 | 15461.04 | 60% | 9276.624 | 80% | 12368.832 | 3092.208 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
4/H | Wall panelling; type HTL-WD-19 | 19 | m2 | 552.18 | 10491.42 | 60% | 6294.852 | 80% | 8393.136 | 2098.284 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
4 | Corridor
4/I | Wall panelling; type HTL-WD-19 | 89 | m2 | 552.18 | 49144.02 | 40% | 19657.608 | 40% | 19657.608 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%) | Location was not at the site
4 | Hall
4/J | Wall panelling ; type HTL-WD-19 | 50 | m2 | 552.18 | 27609 | 40% | 11043.6 | 60% | 16565.4 | 5521.8 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
4/K | Wall panelling ; type HTL-WD-19 | 92 | m2 | 552.18 | 50800.56 | 40% | 20320.224 | 65% | 33020.364 | 12700.14 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
4 | Storage
4/L | Wall panelling ; type HTL-WD-19 | 8 | m2 | 552.18 | 4417.44 | 40% | 1766.976 | 40% | 1766.976 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%) | Location was not at the site
4 | Break out space
4/M | Wall panelling; type HTL-WD-19 | 30 | m2 | 552.18 | 16565.4 | 40% | 6626.16 | 90% | 14908.86 | 8282.7 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5 | CEILING FINISHES |  |  |  | 239829.6221 |  | 127557.8231 |  | 127557.8231 | 0
5 | PACKAGE -3 - PRESIDENTIAL SUITE FIT-OUT - RIGHT WING |  |  |  | 12995.9765 |  | 2638.624 |  | 2638.624 | 0
5 | Supply and fixing of Timber Ceiling; Type cove light HTL-WD-02 incl. cornice; Smoked Oak, Smoked oak open grain - brushed - matte finish, 200mm wide
5/A | Vestibule | 6.42 | m | 465.53 | 2988.7026 | 40% | 1195.481 | 40% | 1195.481 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5/B | Vanity | 7.75 | m | 465.53 | 3607.8575 | 40% | 1443.143 | 40% | 1443.143 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5 | Supply and fixing of Timber Ceiling; Type cove light HTL-WD-19 incl. cornice; US Walnut, Satin brushed, 250mm wide
5/C | Twin Bathroom | 14.43 | m | 443.48 | 6399.4164
5 | PACKAGE -3 - PRESIDENTIAL SUITE FIT-OUT - LEFT WING |  |  |  | 22184.6116 |  | 8873.8446 |  | 8873.8446 | 0
5 | Suspended Ceiling System and Finishes
5 | Suspended Ceiling System including finishes, all necessary framing, fittings, fixing, corner bead, Cornice, accessories, shadow gaps, etc and the like all in accordance with drawings and specifications.
5 | Supply and fixing of Timber Ceiling; Type cove light HTL-WD-02 incl. cornice, bulkhead; Smoked Oak, Smoked oak open grain - brushed - matte finish, 250mm wide
5/D | Entry Vestibule | 9.55 | m | 465.53 | 4445.8115 | 40% | 1778.3246 | 40% | 1778.3246 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5/E | Study | 12.93 | m | 465.53 | 6019.3029 | 40% | 2407.7212 | 40% | 2407.7212 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5 | Supply and fixing of Timber Ceiling; Type cove light HTL-WD-19 incl. cornice, bulkhead; US Walnut, Satin brushed, 300mm wide
5/F | Master Bathroom | 12.28 | m | 488.69 | 6001.1132 | 40% | 2400.4453 | 40% | 2400.4453 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5 | Supply and fixing of Timber Ceiling Type HTL-WD-19 incl. light cove, cornice, bulkhead and etc; US Walnut, Satin brushed
5/G | Master Suite Vestibule | 5.6 | m2 | 1021.14 | 5718.384 | 40% | 2287.3536 | 40% | 2287.3536 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5 | PACKAGE -5 - Timber Ceiling to Hotel guest Rooms |  |  |  | 193408.924 |  | 116045.3544 |  | 116045.3544 | 0
5/H | Timber Ceiling (WD-07) | 113.72 | m2 | 1087.3 | 123647.756 | 60% | 74188.6536 | 60% | 74188.6536 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5/I | Timber Ceiling (WD-09) | 64.16 | m2 | 1087.3 | 69761.168 | 60% | 41856.7008 | 60% | 41856.7008 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
5 | ROYAL SUITE FIT-OUT - LEFT WING |  |  |  | 11240.11 |  | 0 |  | 0 | 0
5 | Supply and fixing of Timber Ceiling; Type cove light HTL-WD-02 incl. cornice, bulkhead; Smoked Oak, Smoked oak open grain - brushed - matte finish, 250mm wide
5/J | Master Bathroom | 17 | m | 465.53 | 7914.01
5 | Supply and fixing of Timber Ceiling; Type cove light HTL-WD-19 incl. cornice; US Walnut, Satin brushed, 250mm wide
5/K | Twin Bathroom | 7.5 | m | 443.48 | 3326.1
| Total |  |  |  | 2105729.8665 |  | 810993.5956 |  | 1037835.9306 | 226842.335 | 49.29%

## Misc. Joinery
Item | Bill description | Bill quantity | Unit | Rate | Amount | Previous Work done % | Previous Work done value | Current Work done % | Current Work done value | Current Claim | Remarks
E11-K158-KD-SR-336
6 | PRELIMINARIES |  |  |  | 196023.4 |  | 42744.4276 |  | 72506.23 | 29761.8024
6/A | Supervision,Transportation, Drafting, | 1 | No | 196023.4 | 196023.4 |  | 42744.4276 |  | 72506.23 | 29761.8024 | 36.99%
7 | PACKAGE -2 - LEVEL 01 BALL ROOM |  |  |  | 747029.99 |  | 320672.183 |  | 475112.8325 | 154440.6495
7 | BILL No. 3 - JOINERY |  |  |  | 747029.99 |  | 320672.183 |  | 475112.8325 | 154440.6495
7 | Built-in structures
7 | Supply and installation of Joinery Items as per the detail drawings & specifications.
7 | Level 1
7 | Ballroom
7/A | Wood cupboard;overall size 2050 mm x 530 mm x 2300 mm ; type HTL-WD-19 including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-325 (EXCLUDED STONE) | 1 | Item | 6584.08 | 6584.08
7/B | Backlit glass;overall size 2255 mm x 5000 mm; type HTL-GL-10 with metal frame in HTL-ME-03, including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-220 & L1-BALL-320 (Note: LED Folio system and Glass System is excluded). (INCLUDED GLASS & METAL. GLASS PANEL WILL HAVE JOINTS. EXCLUDED LIGHTING) | 3 | Item | 16193.1 | 48579.3 | 30% | 14573.79 | 40% | 19431.72 | 4857.93 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
7 | Hall
7/C | Soffit of architrave; type HTL-WD-19 | 27 | m2 | 657.65 | 17756.55 | 40% | 7102.62 | 60% | 10653.93 | 3551.31 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
7 | Meeting room 1
7/D | Soffit of architrave; type HTL-WD-19 | 38 | m2 | 657.65 | 24990.7 | 40% | 9996.28 | 85% | 21242.095 | 11245.815 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
7 | Meeting room 2
7/E | Soffit of architrave; type HTL-WD-19 | 33 | m2 | 657.65 | 21702.45 | 40% | 8680.98 | 80% | 17361.96 | 8680.98 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
7 | Lift lobby
7/F | Backlit mirror ; size 1200 mm x 2100 mm , including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-230 (Note: LED Folio system and Glass System is excluded). (INCLUDED GLASS & METAL EXCLUDED LIGHTING) | 1 | Item | 4921.87 | 4921.87 | [5 empty] | DOUG TO CHECK MIRROR
7 | Breakout space
7/G | Bar counter ; top in HTL-ST-36, sides in HTL-WD-19 , frame in HTL-ME-04,including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-309B (EXCLUDED STONE & INCLUDED METAL) | 1 | Item | 9399.1 | 9399.1 | 40% | 3759.64 | 40% | 3759.64 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
7/H | Back bar ; type HTL-WD-19 , bar top in HTL-ST-36 ,overall size 3035 mm x 685 mm x 2850 mm ;with mirror in HTL-GL-01 and size 1540mm x 1900mm; including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-204 (EXCLUDED STONE) | 1 | Item | 17841.08 | 17841.08
7/I | Soffit of architrave; type HTL-WD-19 | 48 | m2 | 657.65 | 31567.2 | 40% | 12626.88 | 80% | 25253.76 | 12626.88 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
8 | Ballroom male toilet
8/A | Vanity (curve), type in HTL-ST-38 top and front, size 9000 L x 580mm W x 680mm H, 100mm H recessed stone baseboard in HTL-ST-38, including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-204 7 (BALL-WC-D-100 & 200)(EXCLUDED STONE. INCLUDED METAL RING & METAL FRAME) | 1 | Item | 18982.15 | 18982.15 | 60% | 11389.29 | 90% | 17083.935 | 5694.645 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
8/B | Mirror, type HTL-GL-01, size 1720mm H x 1260mm W including metal frame in HTL-ME-04, including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-204 (INCLUDED MIRROR & METAL FRAME) | 5 | Item | 3011.7 | 15058.5 |  |  | 60% | 9035.1 | 9035.1
8/C | Mirror strips, type in HTL-GL-01, 1720mm H x 1600mm W including metal frame in HTL-ME-04, including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-204 (INCLUDED MIRROR & METAL FRAME) | 2 | Item | 3433.87 | 6867.74 |  |  | 60% | 4120.644 | 4120.644
8/D | Mirror, type in HTL-GL-01, 2450mm H x 240mm W including metal frame in HTL-ME-04, including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-204 (INCLUDED MIRROR & METAL FRAME) | 2 | Item | 1902.43 | 3804.86 |  |  | 60% | 2282.916 | 2282.916
8/E | Cupboard, jib doors type in HTL-WC-17 & baseboard in HTL-ST-38, push pull system with lock, size 2440mm L x 735mm W x 2400mm H, inside type in HTL-WD-09, including all necessary fittings, fixings and accessories in accordarce with the drawing and specifications, Detail drawing ref. L1-BALL-WC-D-309 (EXCLUDED STONE SKIRTING & SPECIAL PLASTER WC-17) | 1 | Item | 8078.73 | 8078.73 |  |  | 90% | 7270.857 | 7270.857
8/F | Infinity mirror, normal mirror 1180 mm L x 3045 mm H, two way mirror 1180 mm L x 3045 mm H, two back painted walls 435 mm L x 3045 mm H, back painted floor & ceiling 1180 mm L x 435 mm W, 150 mm H baseboard in HTL-ST-38, including all necessary fittings, fixings and accessories in accordance with the drawing and specifications, Detail drawing ref. L1-BALL-WC-D-312 & 311 (INCLUDED MIRROR. EXCLUDED STONE & LIGHTING) | 1 | Item | 6859.55 | 6859.55
8/G | Stone Shelf, type in HTL-ST-38, 1000 mm L x 100 mm W including all necessary fittings, fixings and accessories in accordance with the drawing and specifications, Detail drawing ref. L1-BALL-WC-D-307 (EXCLUDED STONE WORKS) | 6 | Nos | 327.79 | 1966.74
9 | Ballroom female toilet
9/A | Vanity, type in size 430 mm x 1930 mm x 740 mm, 150 mm H recessed metal baseboard in HTL-ME-04, backlit screen with mirror in HTL-GL-01 & metal frame in HTL-ME-04, including all necessary fittings, fixings and accessories in accordance with the drawing and specifications, Detail drawing ref. L1-BALL-WC-D-301 & WC-D-306 (INCLUDED METAL & SCREEN) | 1 | Item | 7383.15 | 7383.15 | 50% | 3691.575 | 50% | 3691.575 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
9/B | Vanity (curve) , type in HTL-ST-38 top and front, size xx L x 580 mm W x 780 mm H, 100 mm H recessed stone baseboard in HTL-ST-38, including all necessary fittings, fixings and accessories in accordance with the drawing and specifications, Detail drawing ref. L1-BALL-WC-D-305 & 306 (INCLUDED METAL & EXCLUDED STONE) | 1 | Item | 21583.69 | 21583.69 | 60% | 12950.214 | 90% | 19425.321 | 6475.107 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
9 | ADDITIONAL ITEMS
9 | The tenderer is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the Subcontractor fail to insert any items hereunder, it will be deemed that his lump sum price for the tender includes all works as required by the tender drawings and specification and no subsequent claim for any additional item will be entertained.
9 | Ballroom
9/C | Soffit of architrave; type HTL-WD-19 | 13 | m2 | 657.65 | 8549.45 |  |  | 40% | 3419.78 | 3419.78
10 | Ballroom female toilet
10/A | 1490mm L x 915mm high x 820mm W Built-in banquette seat in HTL-FA-WW including metal frame HTL-ME-04 - Detail drawing ref. L1-BALL-WC-D-300 (EXCLUDED WALL PAPER) | 2 | no. | 9476.96 | 18953.92 |  |  | 20% | 3790.784 | 3790.784
10/B | 6970mm L x 900mm H Backlit banquette in HTL-WD-19 + HTL-FA-XX (Detail drawing ref. L1-BALL-318) | 1 | no. | 27510.11 | 27510.11 |  |  | 40% | 11004.044 | 11004.044
10/C | Timber "L" beam HLT-WD-19 | 3 | m2 | 657.65 | 1972.95
10 | Corridor
10/D | Fluted wood panels; type HTL-WD-20 | 283 | m2 | 1248.25 | 353254.75 | 60% | 211952.85 | 75% | 264941.0625 | 52988.2125 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
10/E | 200 mm high Decorative lit beam; type HTL-WD-19 | 72 | m | 206.36 | 14857.92
10 | Hall
10/F | 200 mm high Decorative lit beam ; type HTL-WD-19 | 15 | m | 206.36 | 3095.4
10/G | Fluted wood panels ; type HTL-WD-20 | 26 | m2 | 1248.25 | 32454.5 | 60% | 19472.7 | 75% | 24340.875 | 4868.175 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
10 | Break out space
10/H | Fluted wood panels ; type HTL-WD-20 | 3 | m2 | 1248.25 | 3744.75 | 60% | 2246.85 | 90% | 3370.275 | 1123.425 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
10/I | Lit skirting 100 mm high; type HTL-ME-03 | 3 | m | 141.98 | 425.94 | 60% | 255.564 | 90% | 383.346 | 127.782 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
10/J | Wood beams ; type HTL-WD-19 | 5 | m2 | 657.65 | 3288.25 | 60% | 1972.95 | 90% | 2959.425 | 986.475 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
10 | Supply and fixing of Wooden Trim/Wooden Door Frame-Architrave; Type HTL-WD-02; Smoked Oak
10/K | Valet Box - (2.40+0.975+2.40) - 205mm wide | 1 | Nr | 1275.69 | 1275.69 | [5 empty] | NO DRG
10/L | Valet Box - (2.40+0.975+2.40) - 260mm wide | 1 | Nr | 1448.94 | 1448.94 |  |  | 20% | 289.788 | 289.788 | NO DRG
10 | Supply and fixing of Wooden Trim/Wooden Door Frame-Architrave; Type HTL-WD-19; US Walnut, Satin Brushed
10/M | Powder Room - (2.40+0.860+2.40) - 185mm wide | 1 | Nr | 1134.99 | 1134.99 | [5 empty] | NO DRG
10/N | Powder Room - (2.40+0.860+2.40) - 190mm wide | 1 | Nr | 1134.99 | 1134.99 | [5 empty] | NO DRG
11 | PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT |  |  |  | 271103.61 |  | 0 |  | 0 | 0
11 | CARPENTRY/JOINERY/STONE WORKS - RIGHT WING |  |  |  | 69705.23 |  | 0 |  | 0 | 0
11 | Wardrobe, Cabinet, Headboard, Vanity, Ledge
11 | Supply and Installation of Wardrobe, cabinets, etc. including supports, fixings, fittings, accessories,fabric panels at back, finishes, Doors, Ironmongeries, Metal Handle, Metal Frame, Metal Trim etc. and all like complete all in accordance with drawings and specifications.
11/A | Wood Wardrobe; Size 2220mm+2370mm (L) x 700mm (W) x 2650mm (H), Dressing Room 2 as detailed shown on Dwg. No. 1902-210, DET. II,JJ & 1902-212, SEC. 09,10 - Drg. L1-PRES-1902-314/315 (EXCLUDED STONE SKIRTING) | 1 | Nr | 24135.38 | 24135.38
11/B | Wood Valet Closet; Size 1100mm (L) x 650mm (W) x 2650mm (H), Valet Box as detailed shown on Dwg. No. 1902-210, DET. II,JJ & 1902-212, SEC. 09,10 - Drg. L1-PRES-1902-316 (EXCLUDED STONE SKIRTING) | 1 | Nr | 6439.78 | 6439.78
11/C | Wood drawers with stone top in HTL WD-09 & HTL-ST-35, Media Room as detailed shown on 1902-212, SEC. 09,10 1902-208 SEC. 01 & 02 & PRESI-1902-323 (EXCLUDED FABRIC PANELLING) | 1 | Nr | 16472.31 | 16472.31
11/D | Wood Cabinet incl. upper & lower cabinet, stone slab backsplash countertop, shelf & built-in wooden WD-07, Pantry as detailed shown on 1902-210 SEC II,JJ & 1902-213, SEC. 14 (Drg. L1-PRES-1902-130/213) (EXCLUDED STONE SKIRTING, TOP & SPLASHBACK) | 1 | Nr | 22657.76 | 22657.76
11/E | Stone Dresser HTL ST-21 & wooden drawers in HTL-WD-02 incl. wood screen and baseboard HTL-ME-01, Vanity as detailed shown on 1902-214 SEC. 15 & 16 | 1 | Nr |  | EXCLUDED | [5 empty] | PLEASE PROVIDE DETAILED DRAWING
12 | CARPENTRY WORKS (CONT'D)
12 | CARPENTRY/JOINERY/STONE WORKS - LEFT WING |  |  |  | 201398.38 |  | 0 |  | 0 | 0
12 | Wardrobe, Cabinet, Headboard, Vanity, Ledge
12 | Supply and Installation of Wardrobe, Cabinets, etc. including supports, fixings, fittings, accessories, fabric panels at back, finishes, Doors, Ironmongeries, Metal Handle, Metal Frame, Metal Trim etc. and all like complete all in accordance with drawings and specifications.
12/A | Upholstered banquette on Master Bedroom as detailed shown on Dwg. No. - PRES-1902-204 SEC. MM,NN - Drg. L1-PRES-1902-320 (EXCLUDED STONE SKIRTING & WALL PANEL ABOVE BANQUET UNIT FABRIC HTL-WC-31. INCLUDED PC RATE OF DHS 300/-LM FOR FABRIC DUE TO THE SPECIFICATION NOT AVAILABLE) | 1 | Nr | 21755.2 | 21755.2
12/B | Built-in desk / sideboard in HTL-ST-35 w/ metal feet HTL-ME-07 on Master Bedroom detailed shown on Dwg. No. - PRES-1902-200 SEC. AA,BB | 1 | Nr |  | EXCLUDED
12/C | Displays shelving unit w/ drawers on Master Bedroom detailed shown on Dwg. No. - PRES-1902-203 SEC. AA,BB Drg. L1-PRES-1902-321 (INCL. METAL & EXCLUDED UPHOLSTERY WALL PANEL) | 2 | Nr | 26337.28 | 52674.56
12/D | Wood Wardrobe (575+1095+755)x(690) + (930x755) on Dressing Room 1 as detailed shown on Dwg. No. 1902-203, SEC. KK,LL & 1902-212, SEC. 09,10 & 1902-205 SEC. OO,PP (SIZE CONSIDERED 875+1667mm Long - Drg. L1-PRES-1902-310) | 1 | Nr | 13023.51 | 13023.51
12/E | Wood Wardrobe (705+1735)x(755) on Dressing Room 1 as detailed shown on Dwg. No. 1902-203, SEC. KK,LL & 1902-212, SEC. 09,10 (SIZE CONSIDERED 2517mm Long - Drg. L1-PRES-1902-311) | 1 | Nr | 18170.59 | 18170.59
12/F | Wood Wardrobe (1095+575)x(690) on Dressing Room 1 as detailed shown on Dwg. No. 1902-203, SEC. KK,LL & 1902-212, SEC. 09,10 (SIZE CONSIDERED 2397mm Long - Drg. L1-PRES-1902-312) | 1 | Nr | 8807.31 | 8807.31
12/G | Wood Valet Closet; Size 950x690, Valet Box 1 as detailed shown on Dwg. No. 1902-205 SEC. RR - (Drg. L1-PRES-1902-312. EXCLUDED STONE SKIRTING) L1-PRES-1902-313 | 1 | Nr | 4940.14 | 4940.14
12/H | Wood Wardrobe w/ wood shelves (1620)x(645) on Corridor as detailed shown on Drg. L1-PRES-1902-317 (WE HAVE CONSIDERED SIZE 2175MM LONG. INCL. GLASS & EXCLUDED STONE) | 1 | Nr | 10954.32 | 10954.32
12/I | Wood shelf & wood drawers (700)x(570)x(2445) on Powder Room as detailed shown on Dwg. No. 1902-207, SEC. YY,ZZ (WE HAVE PRICED BASED ON DRG. Drg. L1-PRES-1902-335. EXCLUDED STONE & WOODEN DRAWER. INCLUDED METAL FRAME WORKS) | 1 | Nr | 2270.82 | 2270.82
13 | CARPENTRY WORKS - LEFT WING (CONT'D)
13 | Wood Shelf, Wooden Panelling/Frame, Vanity, Ledge
13/A | Make-up station with stone top and wood shelf, legs and wood panels on Dressing Room 1 as detailed shown on Dwg. No. 1902-203, SEC. LL | 1 | Nr |  | EXCLUDED | [5 empty] | NO FINISHES MENTIONED ON DRG. PLEASE PROVIDE
13 | Supply and Installation of Wooden Panelling w/ wood molding incl supports, fixings, fittings, accessories, finishes, etc. and all like complete all in accordance with drawings and specifications.
13/B | Study, HTL-WD-02 (Dwg. No. 1902-207 SEC. WW,XX & 1902-203 SEC. KK,LL) (WE HAVE PRICED BASED ON DRG. Drg. L1-PRES-1902-322. INCLUDED CABINET & EXCLUDED WALL PANELLING ALL AROUND STUDY ROOM) | 1 | Item | 41314.13 | 41314.13
13/C | Entry Vestibule, HTL-WD-19 (Dwg. No. 1902-206 SEC. UU,VV & 1902-203 SEC. LL) | 1 | Item | 11699.73 | 11699.73
13 | Supply and Installation of Wood frame (WD-19) with mirror panel (GL-14) incl. supports, fixings, fittings, accessories, finishes, etc. and all like complete all in accordance with drawings and specifications as shown in Dwg. No. 1902-202 SEC. II,JJ
13/D | Master Suite Vestibule (EXCLUDED STONE KICKER) | 1 | Item | 15788.07 | 15788.07
14 | PACKAGE -3 - ROYAL SUITE FIT-OUT |  |  |  | 186150.93 |  | 0 |  | 0 | 0
14 | CARPENTRY/JOINERY/STONE WORKS - RIGHT WING |  |  |  | 186150.93 |  | 0 |  | 0 | 0
14 | Built-in Cupboard, Lockers and Storage
14 | Supply and Installation of Built-in Cupboard, Lockers and Storage including supports, fixings, fittings, accessories, finishes, Doors, Ironmongeries, Stone Skirting, Metal Handle, Metal Frame, Metal Trim etc. and all like complete all in accordance with drawings and specifications.
14/A | Twin Desk on Secondary Bedroom as detailed shown on Dwg. No.- RS-2608-331, DET. 01 (DRG.RS-2608-331) - (EXCLUDED STONE) | 1 | Nr | 4405.06 | 4405.06
14/B | Cupboard; Size 4010mm (L) x 710mm (W) x 2490mm (H), Dressing 2 as detailed shown on Dwg. No. RS-2608-332, DET. 01 (HTL-WC-30) (EXCLUDED FABRIC) | 1 | Nr | 20455.96 | 20455.96
14/C | Cupboard on Dressing 2 as detailed shown on Dwg. No. - RS-2608-333, DET. 01 (HTL-WC-30) (EXCLUDED FABRIC) | 1 | Nr | 9413.38 | 9413.38
14/D | Cupboard; Size 620mm (L) x 540mm (W) x 2490/2690mm (H), Valet Box 2 as detailed shown on RS-2608-338 (HTL-WC-28) (EXCLUDED FABRIC) | 1 | Nr | 5096.89 | 5096.89
15 | CARPENTRY/JOINERY/STONE WORKS - LEFT WING
15 | Built-in Cupboard, Lockers and Storage
15 | Supply and Installation of Built-in Cupboard, Lockers and Storage including supports, fixings, fittings, accessories, finishes, Doors, Ironmongeries, Stone Skirting, Metal Handle, Metal Frame, Metal Trim etc. and all like complete all in accordance with drawings and specifications.
15/A | Headboard on Master Bedroom Sofa as detailed shown on DET. 01 - RS-2608-322 (EXCLUDED METAL TRIM, STONE SKIRTING/CLADDING & WALL COVERING HTL-WC-25) | 1 | Nr | 6160.12 | 6160.12
15/B | Shelf / Desk on Master Bedroom as detailed shown on DET. 01 - RS-2608-323 (INCLUDED METAL TRIM. EXCLUDED WALL PANEL & STONE SKIRTING) | 1 | Nr | 13861.45 | 13861.45
15/C | Cupboard on Master Dressing 1 as detailed shown on DET. 01 - RS-2608-314 (EXCLUDED STONE SKIRTING) | 1 | Nr | 9534.03 | 9534.03
15/D | Cupboard on Master Dressing 1 as detailed shown on DET. 02 - RS-2608-314 (EXCLUDED STONE SKIRTING) | 1 | Nr | 9829.39 | 9829.39
15/E | Cupboard on Master Dressing 1 as detailed shown on DET. 01 - RS-2608-315 (EXCLUDED STONE SKIRTING) | 1 | Nr | 14566.25 | 14566.25
15/F | Shelf on Master Dressing 1 as detailed shown on DET. 01 - RS-2608-316 (EXCLUDED STONE SKIRTING & TOP) | 1 | Nr | 8124.55 | 8124.55
15/G | Cupboard on Master Dressing 1 as detailed shown on DET. 01 - RS-2608-317 (HTL-WC-28) (EXCLUDED STONE SKIRTING) & TOP | 1 | Nr | 9472.7 | 9472.7
15/H | Cupboard; Size 620mm (L) x 540mm (W) x 2490/2690mm (H), Valet Box 1 as detailed shown on RS-2608-338 (EXCLUDED STONE SKIRTING) | 1 | Nr | 4795.17 | 4795.17
15/I | Pantry Cabinet as detailed shown on DET. 01 - RS-2608-324 (EXCLUDED STONE) | 1 | Nr | 15916.68 | 15916.68
15/J | Entrance Display as detailed shown on DET. 01 - RS-2608-325 (INCLUDED METAL & MIRROR. EXCLUDED STONE) | 1 | Nr | 6227.74 | 6227.74
15/K | Entrance Display as detailed shown on DET. 02 - RS-2608-325 (INCLUDED METAL & MIRROR. EXCLUDED STONE) | 1 | Nr | 8768.03 | 8768.03
16 | Built-in Cupboard, Lockers and Storage
16 | Supply and Installation of Built-in Cupboard, Lockers and Storage including supports, fixings, fittings, accessories, finishes, Doors, Ironmongeries, Stone Skirting, Metal Handle, Metal Frame, Metal Trim etc. and all like complete all in accordance with drawings and specifications.
16/A | Dining Sideboard as detailed shown on DET. 01 - RS-2608-326 (STONE SKIRTING EXCLUDED) | 1 | Nr | 12860.45 | 12860.45
16/B | Mini Bar as detailed shown on DET. 01 - RS-2608-327 (INCLUDED GLASS WITH METAL SHELF. EXCLUDED ALL STONE WORKS) | 1 | Nr | 5614.46 | 5614.46
16/C | Living Room Desk Niche as detailed shown on DET. 01 - RS-2608-328 (EXCLUDED STONE) | 1 | Nr | 5906.32 | 5906.32
16/D | Living Room Library Shelves as detailed shown on DET. 01 - RS-2608-329 (EXCLUDED STONE) | 1 | Nr | 15142.3 | 15142.3
17 | PACKAGE -4 - HOTEL LEVEL 01:- PRAYER ROOM & ABLUTION |  |  |  | 10768.26 |  | 2692.065 |  | 5384.13 | 2692.065
17 | TIMBER WORKS
17 | Prayer Room Recess, Shoe Bench, Shelf
17 | Supply and Installation of Prayer Room Recess, including necessary framing, fittings, backing support, fixing board, PT-03 frame, ST-12 recess etc and the like all in accordance with drawings and specifications. As detailed shown on Dwg. IDR-HL1-101A-120
17/A | Male Prayer Room | 1 | Nr |  | EXCLUDED
17/B | Female Prayer Room | 1 | Nr |  | EXCLUDED
17 | Supply and Installation of Prayer Room Shoe Bench, including necessary framing, fittings, backing support, fixing board, upholstered cushion, wooden structure, metal strip if any, etc and the like all in accordance with drawings and specifications. As detailed shown on Dwg. IDR-HL1-101A-121
17/C | Male Ablution | 1 | Nr | 4570.39 | 4570.39 | 25% | 1142.5975 | 50% | 2285.195 | 1142.5975 | Cutting list under progress
17/D | Female Ablution | 1 | Nr | 4570.39 | 4570.39 | 25% | 1142.5975 | 50% | 2285.195 | 1142.5975 | Cutting list under progress
17 | Supply and Installation of Prayer Room Shelf, including necessary framing, fittings, backing support, fixing board, wooden structure, etc and the like all in accordance with drawings and specifications. As detailed shown on Dwg. IDR-HL1-101A-122
17/E | Male Prayer Room | 1 | Nr | 813.74 | 813.74 | 25% | 203.435 | 50% | 406.87 | 203.435 | Cutting list under progress
17/F | Female Prayer Room | 1 | Nr | 813.74 | 813.74 | 25% | 203.435 | 50% | 406.87 | 203.435 | Cutting list under progress
18 | PACKAGE -4 - HOTEL - GYM - L28 |  |  |  | 0 |  | 0 |  | 0
18 | JOINERY WORKS
18 | HOTEL - GYM - L28
18 | Note: The Sub-contractor is referred to the Specifications and Drawings for all details related to this Section of the Works and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the item description.
18 | Built-in Closets including fixings, fittings, accessories, finishes, etc. supplied and installed complete (supply and installation of timber skirting and stone finishes by others)
18/A | Storage Closet interior in HTL-PT-04, including removable shelves in HTL-PT-04, jib doors in HTL-WC-14 (wall covering measured elseware) invisible hinges SOSS type, discreet door nob in HTL-MT-05, door stopper in HTL-PT-04 overall size 1044mmL x 580mmW x 2667mmH, (ref drawing L28-GYM-DD-302) | 1 | No |  | EXCLUDED
19 | PACKAGE -5 - Cupboard and Side Table |  |  |  | 71853 |  | 0 |  | 0 | 0
19/A | Supply and Installation of Side Table Size : 1826 X650X 445mm Material MDF with Oak Veneered Finish in High Gloss/ Matte Finish with Stone Top of Viola Marble - Drg. D1BS-707-335 (EXCLUDED STONE) | 10 | No | 3811.31 | 38113.1 | [5 empty] | DOUG TO CHECK STONE TOP
19/B | Supply and Installation of Cupboard with overhead Niche Size : 933 X 530 X 2505mm Material MDF with Oak Veneered Finish in High Gloss/ Tulle Print | 10 | No | 3373.99 | 33739.9
19/C | Supply and Installation of Side Table Size : 700 X 670X 445 mm Material MDF with Oak Veneered Finish in High Gloss/ Matte Finish with Stone Top of ST-21 | 5 | No |  | EXCLUDED
| Total |  |  |  | 1482929.19 |  | 366108.6756 |  | 553003.1925 | 186894.5169 |  | 37.29%

## Timber doors
BOQ Ref | Bill description | Qty | Unit | Rate | Amount | Discount % | Revised rate | Revised Amount | Previous Work done % | Previous Work done value | Current Work done % | Current Work done value | Current Claim | Remarks
E11-K158-KD-SR-336
20 | PACKAGE 2 - BALL ROOMS - DOORS AND WINDOWS |  |  |  | 450940.27 |  |  | 425300.2137 |  | 73275.9952 |  | 175718.9793 | 102442.9842 |  | 155528.8393 | 356820.3843 | 43.59%
20 | PRELIMINARIES |  |  |  | 72608.27 |  |  | 68479.8294 |  | 5588.8474 |  | 20190.14 | 14601.2926
20/A | Preliminaries | 1 | Item | 72608.27 | 72608.27 | 5.686% | 68479.8294 | 68479.8294 |  | 5588.8474 |  | 20190.14 | 14601.2926
20 | Timber doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications .
20 | Level 1 Ballroom |  |  |  | 221458 |  |  | 208866.0982 |  |  |  | 82201.709 | 82201.709
20/B | Wood door ;overall size 4115 mm x 5000 mm ; type HTL-WD-19+HTL-WD-20 - Drg 924 & 925 (25) - Non Fire Rated (EXCLUDED HTL-ME-03) | 1 | Nr | 31891.5 | 31891.5 | 5.686% | 30078.1781 | 30078.1781 |  |  | 30% | 9023.4534 | 9023.4534 | SHOP DRAWING CHANGED TO BEECH WOOD STAINED TO WALNUT FINISHED
20/C | Wood door ;overall size 4115 mm x 5000 mm ; type HTL-WD-19+HTL-WD-20 - Drg 924 & 925 (36) - Non Fire Rated (EXCLUDED HTL-ME-03) | 1 | Nr | 36966.5 | 36966.5 | 5.686% | 34864.6182 | 34864.6182 |  |  | 30% | 10459.3855 | 10459.3855
20/D | Wood door ;overall size 2000 mm x 5000 mm ; type HTL-WD-19+HTL-WD-20 - Drg 920 & 921 (26, 27, 28 & 29) - Non Fire Rated (EXCLUDED HTL-ME-03) | 4 | Nr | 15575 | 62300 | 5.686% | 14689.4196 | 58757.6783 |  |  | 50% | 29378.8391 | 29378.8391
20/E | Wood door ;overall size 2000 mm x 5000 mm ; type HTL-WD-19+HTL-WD-20 - Drg 920 & 921 - (35, 34, 33 & 32) - Non Fire Rated -(EXCLUDED HTL-ME-03) | 4 | Nr | 15575 | 62300 | 5.686% | 14689.4196 | 58757.6783 |  |  | 50% | 29378.8391 | 29378.8391
20/F | Wood door; overall size 1800 mm x 5000 mm; type HTL-WD-19+HTL-WD-20 - Drg 920 & 921 (30 & 31) - Non Fire Rated - (EXCLUDED HTL-ME-03) | 2 | Nr | 14000 | 28000 | 5.686% | 13203.9726 | 26407.9453 |  |  | 15% | 3961.1918 | 3961.1918
20 | Meeting room 1 |  |  |  | 24100 |  |  | 22729.6958 |  | 4602.5276 |  | 10242.5102 | 5639.9826
20/G | Jib door ;overall size 955 mm x 2200 mm; type HTL-WD-19 (EXCLUDED STONE & IRONMONGERY) - Drg 918 & 919 (3 & 10) - 1 HR Fire Rated - 35DB | 2 | Nr | 6100 | 12200 | 5.686% | 5753.1595 | 11506.319 | 40% | 4602.5276 | 50% | 5753.1595 | 1150.6319 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
20/H | Jib door ;overall size 620 mm x 2200 mm; type HTL-WD-19. (EXCLUDED STONE & IRONMONGERY) - Drg 916 & 917 (4 & 9) - 1HR Fire Rated - 35DB | 2 | Nr | 5950 | 11900 | 5.686% | 5611.6884 | 11223.3768 |  |  | 40% | 4489.3507 | 4489.3507
20 | Meeting room 2 |  |  |  | 24100 |  |  | 22729.6958 |  | 4602.5276 |  | 4602.5276 | 0
20/I | Jib door ;overall size 955 mm x 2200 mm; type HTL-WD-19 - Drg 918 & 919 (12 & 18) - 1HR Fire Rated - 35DB | 2 | Nr | 6100 | 12200 | 5.686% | 5753.1595 | 11506.319 | 40% | 4602.5276 | 40% | 4602.5276 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
20/J | Jib door ;overall size 620 mm x 2200 mm; type HTL-WD-19 - Drg 916 & 917 (17 & 21) - 1 HR Fire Rated - 35DB | 2 | Nr | 5950 | 11900 | 5.686% | 5611.6884 | 11223.3768 |  |  |  | 0 | 0
20 | Corridor |  |  |  | 0
20/K | Entrance door; overall size 3750 mm x 2400 mm - (EXCLUDED NO DETAILS AVAILABLE) | 1 | Nr |  | EXCLUDED
20/L | Wood door; overall size 900 mm x 2400 mm; type HTL-WD-19 & HTL-ST-36 (EXCLUDED NO DETAILS AVAILABLE) | 1 | Nr |  | EXCLUDED
20 | Hall |  |  |  | 11900 |  |  | 11223.3768 |  |  |  | 0
20/M | Jib door ;overall size 620 mm x 2200 mm ; type HTL-WD-19 - Drg 916 & 917 (23 & 19) - 1 Hr Fire Rated - 35DB | 2 | Nr | 5950 | 11900 | 5.686% | 5611.6884 | 11223.3768 |  |  |  | 0
20 | Pre-function space |  |  |  | 0
20/N | Jiib door; overall size 900 mm x 2200 mm; type HTL-WC-21 including base board in HTL-PT-08 - (EXCLUDED NO DETAILS AVAILABLE) | 3 | Nr |  | EXCLUDED
20 | Ballroom male toilet |  |  |  | 46738 |  |  | 44080.5195 |  | 33646.2688 |  | 33646.2688 | 0
21/A | Wooden door; overall size(900 mm x 2400 mm); type HTL-WD-19; finish type HTL-PT-12 - Drg 928 & 929 (39 & Urinal Door) - Non Fire Rated | 2 | Nr | 5466 | 10932 | 5.686% | 5155.2082 | 10310.4164 | 80% | 8248.3331 | 80% | 8248.3331 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
21/B | Wooden door ;overall size (775 mm x 2400 mm); type HTL-WD-19; finish type HTL-PT-12 - Drg 928 & 929 (40, 41, 42, 43, 44 & 46) - Non Fire Rated | 6 | Nr | 5014.5 | 30087 | 5.686% | 4729.3801 | 28376.2804 | 80% | 22701.0243 | 80% | 22701.0243 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
21/C | Door ;overall size (1020 mm x 2400 mm); type HTL-WD-19 - Drg 930 (45) - Non Fire Rated | 1 | Nr | 5719 | 5719 | 5.686% | 5393.8228 | 5393.8228 | 50% | 2696.9114 | 50% | 2696.9114 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
21 | Ballroom female toilet |  |  |  | 50036 |  |  | 47190.9982 |  | 24835.8237 |  | 24835.8237 | 0
21/D | Wooden door; overall size(900 mm x 2400 mm); type HTL-WD-19; type HTL-PT-12 - Drg 928 & 929 (51 & 54) - Non Fire Rated | 2 | Nr | 5466 | 10932 | 5.686% | 5155.2082 | 10310.4164 | 80% | 8248.3331 | 80% | 8248.3331 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
21 | Timber doors complete with frames, sub frames (Cont'd)
21 | Ballroom female toilet (Cont'd)
21/E | Wooden door ;overall size (780 mm x 2400 mm); type HTL-WD-19; finish type HTL-PT-11 - Drg 928 & 929 (49, 50, 54 & 53) - Non Fire Rated | 4 | Nr | 5025 | 20100 | 5.686% | 4739.283 | 18957.1322 | 80% | 15165.7057 | 80% | 15165.7057 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
21 | ADDITIONAL ITEMS
21 | Ballroom female toilet
21/F | Wooden door ;overall size (780 mm x 2400 mm); type HTL-WD-19; finish type HTL-PT-11 - Drg 930 (48) - Non Fire Rated | 1 | Nr | 5025 | 5025 | 5.686% | 4739.283 | 4739.283 | 30% | 1421.7849 | 30% | 1421.7849 | 0 | Fabrication 80% (30%+20%+30%)+ Installation 20% (10%+10%)
21 | Corridor
21/G | Wood door; overall size 1800 mm x 2400 mm; type HTL-WD-19 (EXCLUDED, NO DRAWINGS AVAILABLE) | 1 | Nr |  | EXCLUDED
21 | Near toilet
21/H | Wooden door; overall size(1000 mm x 2400 mm); type HTL-WD-19 - Drg. 914 & 915 (38 & 47) - Non Fire Rated | 2 | Nr | 6989.5 | 13979 | 5.686% | 6592.0833 | 13184.1667 |  |  |  | 0
21 | Near ballroom area
21/I | Wooden door; overall size(1000 mm x 2400 mm); type HTL-WD-19 (EXCLUDED, NO DRAWINGS AVAILABLE) | 2 | Nr |  | EXCLUDED
21/J | Wooden door; overall size(1200 mm x 2400 mm); type HTL-WD-19 (EXCLUDED, NO DRAWINGS AVAILABLE) | 1 | Nr |  | EXCLUDED
21 | PACKAGE -3 - HOTEL LEVEL 19 |  |  |  | 277121 |  |  | 261364.1503 |  | 0 |  | 0 | 0
21 | PRESIDENTIAL SUITE FIT-OUT - RIGHT WING |  |  |  | 67350 |  |  | 63520.5399 |  | 0 |  | 0 | 0
21 | DOORS, DOOR FRAMES AND IRONMONGERIES -
21 | Doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications.
21 | Wood Double Door w/ metal door lever in HTL-WD-19
21/K | Corridor . Drg.342 (RA-1) - Non Fire Rated | 3 | Nr | 7200 | 21600 | 5.686% | 6790.6145 | 20371.8435 |  |  |  | 0
21/L | Twin Bedroom - Drg. 342 (RA-2) Non Fire Rated | 1 | Nr | 7200 | 7200 | 5.686% | 6790.6145 | 6790.6145 |  |  |  | 0
22/A | Vestibule - Drg. 342 (RA-3) - Non Fire Rated | 1 | Nr | 7200 | 7200 | 5.686% | 6790.6145 | 6790.6145 |  |  |  | 0
22 | Additional
22/B | Sliding Door with Mirror - Drg. 344 - Non Fire Rated | 3 | Nr | 10450 | 31350 | 5.686% | 9855.8224 | 29567.4673 |  |  |  | 0 |  | ADDITIONAL
22 | PRESIDENTIAL SUITE FIT-OUT - LEFT WING |  |  |  | 90597 |  |  | 85445.7364 |  | 0 |  | 0 | 0
22 | Doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications.
22 | Wood Double Door w/ metal door lever in HTL-WD-19
22/C | Entry Vestibule - Drg. 340 (LA-1) - 60 Minutes 40 db | 1 | Nr | 14000 | 14000 | 5.686% | 13203.9726 | 13203.9726 |  |  |  | 0
22/D | Corridor - Drg.342 (LA-2) - Non Fire Rated | 2 | Nr | 7200 | 14400 | 5.686% | 6790.6145 | 13581.229 |  |  |  | 0
22 | Wood Door w/ invisible hinges in HTL-WD-19
22/E | Master Bathroom - Drg. 343 (LB1) - Non Fire Rated | 1 | Nr | 5772.5 | 5772.5 | 5.686% | 5444.2809 | 5444.2809 |  |  |  | 0
22/F | Dressing Room - Drg.343 (LB2) - Non Fire Rated | 1 | Nr | 5772.5 | 5772.5 | 5.686% | 5444.2809 | 5444.2809 |  |  |  | 0
22/G | Powder Room - Drg.341 (LB3) - Non Fire Rated | 1 | Nr | 5944 | 5944 | 5.686% | 5606.0295 | 5606.0295 |  |  |  | 0
22 | Concealed Door w/ invisible hinges
22/H | Powder Room - Drg.345 (LE1) - Non Fire Rated | 1 | Nr | 5944 | 5944 | 5.686% | 5606.0295 | 5606.0295 |  |  |  | 0
22/I | Valet Box - Drg.348 - 60 Minutes - 40 DB | 3 | Nr | 7500 | 22500 | 5.686% | 7073.5568 | 21220.6703 |  |  |  | 0 |  | FR ISSUE STONE FRAME
22 | Concealed wood door with wood molding and metal base board in HTL-WD-02 and HTL-ME-01
22/J | Powder Room - Drg.345 (LC1) - Non Fire Rated | 1 | Nr | 5814 | 5814 | 5.686% | 5483.4212 | 5483.4212 |  |  |  | 0
22/K | Sliding Door with Mirror - Drg. 344 - Non Fire Rated | 1 | Nr | 10450 | 10450 | 5.686% | 9855.8224 | 9855.8224 |  |  |  | 0
22 | ROYAL SUITE - RIGHT WING |  |  |  | 37074 |  |  | 34966.0059 |  | 0 |  | 0 | 0
22 | DOORS, DOOR FRAMES AND IRONMONGERIES
22 | Doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications.
22/L | Door and finishes as per ref dwg;- RS-2608-132 & RS-2608-311, Detail 01 - (EXCLUDED FABRIC PANELS) - Non Fire Rated | 1 | Nr | 5700 | 5700 | 5.686% | 5375.9032 | 5375.9032 |  |  |  | 0
22/M | Door and finishes as per ref dwg;- RS-2608-132 & RS-2608-311, Detail 05 (EXCLUDED FABRIC PANELS) - Non Fire Rated | 1 | Nr | 5900 | 5900 | 5.686% | 5564.5313 | 5564.5313 |  |  |  | 0
22/N | Door and finishes as per ref dwg;- RS-2608-132 & RS-2608-312, Detail 01 (EXCLUDED FABRIC PANELS) - Non Fire Rated | 1 | Nr | 6050 | 6050 | 5.686% | 5706.0025 | 5706.0025 |  |  |  | 0
22/O | Door and finishes as per ref dwg;- RS-2608-132 & RS-2608-312, Detail 06 (EXCLUDED FABRIC PANELS) - Non Fire Rated | 1 | Nr | 5900 | 5900 | 5.686% | 5564.5313 | 5564.5313 |  |  |  | 0
23/A | Door and finishes as per ref dwg;- RS-2608-132 & RS-2608-313, Detail 01 - Non Fire Rated | 1 | Nr | 5900 | 5900 | 5.686% | 5564.5313 | 5564.5313 |  |  |  | 0
23/B | Door and finishes as per ref dwg;- RS-2608-132 & RS-2608-313, Detail 04 - 60 Minutes - 40 DB | 1 | Nr | 7624 | 7624 | 5.686% | 7190.5062 | 7190.5062 |  |  |  | 0 |  | DK TO CHANGE IN DOOR BOQ
23 | ROYAL SUITE - LEFT WING |  |  |  | 82100 |  |  | 77431.8682 |  | 0 |  | 0 | 0
23 | DOORS, DOOR FRAMES AND IRONMONGERIES
23 | Doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications.
23/C | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-303, Detail 01 60 min FR, 39 STC Rating | 1 | Nr | 11200 | 11200 | 5.686% | 10563.1781 | 10563.1781 |  |  |  | 0 |  | FR ISSUE MIRROR & METAL FRAME
23/D | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-304, Detail 01 - Non Fire Rated | 1 | Nr | 5850 | 5850 | 5.686% | 5517.3743 | 5517.3743 |  |  |  | 0
23/E | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-304, Detail 07 - Non Fire Rated | 1 | Nr | 5850 | 5850 | 5.686% | 5517.3743 | 5517.3743 |  |  |  | 0
23/F | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-305, Detail 01 - Non Fire Rated | 1 | Nr |  | EXCLUDED | [8 empty] | THIS IS METAL & GLASS DOOR
23/G | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-305, Detail 07 - Non Fire Rated | 1 | Nr | 8000 | 8000 | 5.686% | 7545.1272 | 7545.1272 |  |  |  | 0
23/H | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-306, Detail 01 - Non Fire Rated | 1 | Nr | 8200 | 8200 | 5.686% | 7733.7554 | 7733.7554 |  |  |  | 0
23/I | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-307, Detail 01 - Non Fire Rated | 1 | Nr | 7800 | 7800 | 5.686% | 7356.499 | 7356.499 |  |  |  | 0
23/J | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-308, Detail 01 - Non Fire Rated | 1 | Nr | 8900 | 8900 | 5.686% | 8393.954 | 8393.954 |  |  |  | 0
23/K | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-309, Detail 01 - Non Fire Rated | 1 | Nr | 6100 | 6100 | 5.686% | 5753.1595 | 5753.1595 |  |  |  | 0
23/L | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-310, Detail 01 - Non Fire Rated (EXCLUDED WALL COVERING & IRONMONGERY) | 1 | Nr | 5800 | 5800 | 5.686% | 5470.2172 | 5470.2172 |  |  |  | 0
23/M | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-310, Detail 05 60 min FR, 40DB | 1 | Nr | 7200 | 7200 | 5.686% | 6790.6145 | 6790.6145 |  |  |  | 0
23/N | Door and finishes as per ref dwg;- RS-2608-122 & RS-2608-310, Detail 05 - 60 min FR | 1 | Nr | 7200 | 7200 | 5.686% | 6790.6145 | 6790.6145 |  |  |  | 0
23 | PACKAGE -4 - HOTEL LEVEL 01 |  |  |  | 151305.5 |  |  | 142702.406 |  | 0 |  | 18207.5238 | 18207.5238
23 | PRAYER ROOM & ABLUTION |  |  |  | 28781.5 |  |  | 27145.0099 |  | 0 |  | 18207.5238 | 18207.5238
23 | DOORS, DOOR FRAMES AND IRONMONGERIES
23 | TIMBER DOORS Timber doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications.
23/O | Timber door and finishes as per ref dwg;- IDR-H-L1-101A-124 - Non FR, 35 STC rating | 2 | Nr | 5816.5 | 11633 | 5.686% | 5485.7791 | 10971.5581 |  |  | 80% | 8777.2465 | 8777.2465 | NON FR, 35 RATING BUT DOOR FRAME STONE
23/P | Timber door and finishes as per ref dwg;- IDR-H-L1-101A-125 - Non FR, 35 STC rating | 2 | Nr | 6200 | 12400 | 5.686% | 5847.4736 | 11694.9472 |  |  | 50% | 5847.4736 | 5847.4736 | NON FR, 35 RATING BUT DOOR FRAME STONE
23/Q | Door and finishes as per ref dwg;- IDR-H-L1-101A-126 - Non FR | 1 | Nr | 4748.5 | 4748.5 | 5.686% | 4478.5046 | 4478.5046 |  |  | 80% | 3582.8037 | 3582.8037
23 | PACKAGE - 4 - HOTEL GF LOBBY AND L1 CORRIDOR DOORS |  |  |  | 117924 |  |  | 111218.9479 |  | 0 |  | 0 | 0
24 | TIMBER DOORS Supply and installation of Timber doors complete with frames, sub frames, transoms, stops, ironmongeries, insulation, protective and decorative coatings all in accordance with the drawings and specifications.
24/A | Fluted hidden door with push-catch release to GF Lobby including the finishes type HTL-PT-04, White Paint, color All white N° 2005 - Matte finish (Drg. P18-IDR-H-L0-101C-001 & 011 - Non Fire Rated | 1 | nr | 6624 | 6624 | 5.686% | 6247.3653 | 6247.3653 |  |  |  | 0
24/B | Double leaf doors including finishes to L1 Corridor; refer section 4 in drawing P18-IDR-H-L1-101B-015, 001.1 & 126 - 60 min FR, 35 STC Rating - 1944x2510 | 1 | nr | 14050 | 14050 | 5.686% | 13251.1297 | 13251.1297 |  |  |  | 0
24/C | Double leaf doors including finishes to Lift Lobby in L1 Corridor - 60 min FR, 35 STC Rating - AHK-ID-SD-L1-01555 & 01522 | 1 | nr | 14050 | 14050 | 5.686% | 13251.1297 | 13251.1297 |  |  |  | 0
24/D | Single leaf doors including finishes to L1 Corridor; refer section 2 in drawing P18-IDR-H-L1-101B-013 - 40db Rating - 90 Minutes - Door Type HO-TB-23 - Drg. P18-IDR-H-AL-BDR-127, A-1504 & 013 (EXCLUDED WALL COVERING) | 2 | nr | 9200 | 18400 | 5.686% | 8676.8963 | 17353.7926 |  |  |  | 0 |  | DB RATING FOR 90 MINUTE REQURIRE 40DB NOT POSSIBLE. ALSO STONE FRAME ISSUE
24/E | Single leaf doors including finishes to L1 Corridor; refer section 5 in drawing P18-IDR-H-L1-101B-015 - 60 min FR (CANCELLED) | 1 | nr |  | EXCLUDED
24/F | Single leaf doors including finishes to L1 Corridor; refer section 6 in drawing P18-IDR-H-L1-101B-015 - 90 Minutes - Door Type HO-TB-23 - Drg. P18-IDR-H-AL-BDR-127, A-1504 & 013 (EXCLUDED WALL COVERING) | 8 | nr | 8100 | 64800 | 5.686% | 7639.4413 | 61115.5305 |  |  |  | 0 |  | DB RATING FOR 90 MINUTE REQURIRE 40DB NOT POSSIBLE. ALSO STONE FRAME ISSUE
24 | PACKAGE -4 - HOTEL-GYM-L28 |  |  |  | 4600 |  |  | 4338.4482 |  | 0 |  | 0 | 0
24 | TIMBER DOORS HOTEL - GYM - L28 Note: The Contractor is referred to the Specifications and Drawings for all details related to this Section of the Works and he is to include for complying with all the requirements contained therein, whether or not they are specifically mentioned within the item description. DOORS Supply and installation of timber doors complete with frames, sub frames, transoms, stops, insulation, sealant, protective and decorative coatings all in accordance with the drawings and specifications (ironmongeries included elsewhere)
24/G | Jib Door ; 970mm x 2470mmH, refer to RFI 008 response of client drg. No. AHK-ID-SD-L28-01430, 01445 - Non Fire Rated | 1 | No | 4600 | 4600 | 5.686% | 4338.4482 | 4338.4482 |  |  |  | 0
| Total |  |  |  | 879366.77 |  |  | 829366.77 |  | 73275.9952 |  | 193926.5031 | 120650.5079

## Daybed
Item | Bill description | Bill quantity | Unit | Rate | Amount | Previous Work done % | Previous Work done value | Current Work done % | Current Work done value | Current Claim | Remarks
E11-K158-KD-SR-372
25 | Level 4 Residential Pool |  |  |  | 86902.2 |  |  |  | 0
25/A | Daybed Booth Size 2250x2250x1200mm | 4 | No | 21725.55 | 86902.2 |  |  |  | 0
| Total |  |  |  | 86902.2 |  | 0 |  | 0 | 0

## Additional Joinery works
Item | Bill description | Bill quantity | Unit | Rate | Amount | Previous Work done % | Previous Work done value | Current Work done % | Current Work done value | Current Claim | Remarks
E11-K158-KD-SR-348
| Backing frame & Shelves |  |  |  | 81875.0182 |  | 0 |  | 0 | 0
26 | Room Type-07A
26/A | Supply & installation of 18mm MR MDF backing for HTL-WC-11 above the vanity counter with 40x40m mm Meranti wood framing including opening for Mirror cabinets. Overall size 4566x300x1370mm. Excluding HTL-WC-11. | 5 | Nos | 4608.5011 | 23042.5056 |  |  |  | 0 | 0
26/B | Supply & installation of 18mm MR MDF backing for HTL-WC-11 below the vanity counter with 40x40m mm Meranti wood framing. Overall size 4566x300x600mm. Excluding HTL-WC-11. | 5 | Nos | 3212.2579 | 16061.2895 |  |  |  | 0 | 0
26/C | Mirror cabinet with 18mm MR MDF in veneer finish. Size 800x327x1245mm. Excluding metal HTL-ME-04, Backlighted mirror, LED & MEP works. | 10 | Nos | 1435.4665 | 14354.6645 |  |  |  | 0 | 0
27 | Room Type-15A
27/A | Supply & installation of 18mm MR MDF backing for HTL-WC-11 above the vanity counter with 40x40m mm Meranti wood framing including opening for Mirror cabinets. Overall size 3650x300x1370mm. Excluding HTL-WC-11. | 2 | Nos | 3713.6169 | 7427.2338 |  |  |  | 0 | 0
27/B | Supply & installation of 18mm MR MDF backing for HTL-WC-11 below the vanity counter with 40x40m mm Meranti wood framing. Overall size 3650x300x600mm. Excluding HTL-WC-11. | 2 | Nos | 2564.7991 | 5129.5983 |  |  |  | 0 | 0
27/C | Mirror cabinet with 18mm MR MDF in veneer finish. Size 600x327x1245mm. Excluding HTL-ME-04, Backlighted mirror, LED & MEP works. | 4 | Nos | 1357.4915 | 5429.9662 |  |  |  | 0 | 0
27/D | HTL-WD-02 shelf with 18mm MR MDF in veneer finish. Size 285x1958mm. Excluding HTL-ME-04 frames. | 2 | Nos | 968.1323 | 1936.2646 |  |  |  | 0 | 0
27/E | Vanity base metal unit with 20mm SS tube in HTL-ME-04 finish. Size 2000x328x600mm | 2 | Nos | 4246.7479 | 8493.4958 |  |  |  | 0 | 0
E11-K158-SK-SR-411
28 | Supply & installation GF Lift lobby mirror panel |  |  |  | 8356.2768 |  | 0 |  | 0 | 0
28/A | Supply & installation 6mm (HTL-GL-01) mirror with 12mm ply backing & require timber supports. | 1 | Item | 8356.2768 | 8356.2768 |  |  |  | 0 | 0
E11-K158-SK-SR-411
29 | Supply & installation of FHC doors |  |  |  | 7351.4438 |  | 0 |  | 0 | 0
29/A | FHC type-15 with 18mm FR MDF excluding wall covering HTL-WC-20 finish. Size 800x1600mm | 1 | Nos | 1260.0551 | 1260.0551 |  |  |  | 0 | 0
29/B | FHC type-04 with 18mm FR MDF shutter in HTL-WD-20 finish. Size 800x1600mm | 2 | Nos | 3045.6944 | 6091.3887 |  |  |  | 0 | 0
E11-K158-SK-mv-415
30 | Shelves in the Janitor room at Hotel Level 10, 16, 22 & 25 |  |  |  | 7923.1375 |  | 5546.1963 |  | 5546.1963 | 0
30 | Supply & installation of Shelves in the Janitor room with 18mm MR MDF in veneer finish with hidden metal sleeves(GI). Size 1280x350x60mm
30/A | Level 10 | 2 | Nos | 990.3922 | 1980.7844 | 70% | 1386.5491 | 70% | 1386.5491 | 0 | Under Progress
30/B | Level 16 | 2 | Nos | 990.3922 | 1980.7844 | 70% | 1386.5491 | 70% | 1386.5491 | 0 | Under Progress
30/C | Level 22 | 2 | Nos | 990.3922 | 1980.7844 | 70% | 1386.5491 | 70% | 1386.5491 | 0 | Under Progress
30/D | Level 25 | 2 | Nos | 990.3922 | 1980.7844 | 70% | 1386.5491 | 70% | 1386.5491 | 0 | Under Progress
E11-K158-SK-mv-415
31 | Supply & installation of Pantry cabinet |  |  |  | 13694.9313 |  | 13694.9313 |  | 13694.9313 | 0
31/A | Pantry base cabinet with 18mm white MF MDF (MR) with 20mm stone top including 40mm Fascia & 100mm high metal legs. Excluding sinks, taps & all other sanitary fittings. Size (1590+580)x600x900mm | 1 | No | 10601.2094 | 10601.2094 | 100% | 10601.2094 | 100% | 10601.2094 | 0 | Completed
31/B | Overhead cabinet with 18mm white MF MDF (MR). Size 2190x450x900mm | 1 | No | 3093.7219 | 3093.7219 | 100% | 3093.7219 | 100% | 3093.7219 | 0 | Completed
32 | Secret Garden |  |  |  | 154141.16 |  |  |  | 0
32 | Small Room |  |  |  | 10435.44 |  |  |  | 0
32 | Joinery |  |  |  | 10435.44 |  |  |  | 0
32/A | Upper Wall Cabinet - Size 1610x400x1100mm (EXCLUDING LIGHTS). Dwg OMN-HTL-TB-205 | 1 | No | 4168.3 | 4168.3 |  |  |  | 0
32/B | Base Cabinet - Size 1610x600x900mm (EXCLUDING STONE). Dwg OMN-HTL-TB-205 | 1 | No | 6267.14 | 6267.14 |  |  |  | 0
32 | Large Room |  |  |  | 78277.74 |  |  |  | 0
32 | Wall |  |  |  | 14287.2 |  |  |  | 0
32/C | Wall Trim - Drawing TB-300 - Detail-02 | 19 | Lm | 197.51 | 3752.69 |  |  |  | 0
32/D | Timber and Mirror Back Wall Finish. Dwg OMN-HTL-TB-203 | 7 | m2 | 1504.93 | 10534.51 |  |  |  | 0
32 | Joinery |  |  |  | 50263.79 |  |  |  | 0
32 | Back Bar
32/E | Back Bar - Size 6030x600x900mm h (EXCLUDING STONE & LIGHTS). Dwg OMN-HTL-TB-203 & 304 | 1 | No | 11851.36 | 11851.36 |  |  |  | 0
32/F | Back Bar Bottles Display - Size 6030x600x900mm h (EXCLUDING STONE & LIGHTS). Dwg OMN-HTL-TB-203 & 304 | 1 | No | 12525.92 | 12525.92 |  |  |  | 0
32 | Front Bar
32/G | Front Bar - Size 6030x730x900mm h (EXCLUDING STONE). Dwg OMN-HTL-TB-200, 204 & 205 | 1 | No | 9654.65 | 9654.65 |  |  |  | 0
32/H | Folding doors - Size 6030x1615mm (EXCLUDING POWDER COATING METAL TRELLIS). Dwg OMN-HTL-TB-200 | 1 | Set | 16231.86 | 16231.86 |  |  |  | 0
32 | Doors |  |  |  | 13726.75 |  |  |  | 0
32/I | Entry Door - Size 900x2580x310mm (EXCLUDING IRONMONGERY & METAL TRELLIS). Dwg OMN-HTL-TB-301 | 1 | No | 5373.29 | 5373.29 |  |  |  | 0
32/J | Arch - Size 900x2160x250mm. Dwg OMN-HTL-TB-301 | 1 | No | 2897.93 | 2897.93 |  |  |  | 0
32/K | Back Door - Size 900x2160x250mm (EXCLUDING IRONMONGERY). Dwg OMN-HTL-TB-301 | 1 | No | 5455.53 | 5455.53 |  |  |  | 0
32 | EXTERNAL |  |  |  | 65427.98 |  |  |  | 0
32 | Wall |  |  |  | 65427.98 |  |  |  | 0
32/L | 25mm Painted wood panels. Dwg OMN-HTL-TB-202 | 33 | m2 | 674.29 | 22251.57 |  |  |  | 0
32/M | Timber Trims 50mm. Dwg OMN-HTL-TB-202 | 62 | lm | 231.28 | 14339.36 |  |  |  | 0
32/N | Timber Trim 150mm. Dwg OMN-HTL-TB-202 | 31 | lm | 325.19 | 10080.89 |  |  |  | 0
32/O | Painted Ply & Timber Trim Column Panel 455x3600mm | 10 | No | 1187.62 | 11876.2 |  |  |  | 0
32/P | Mirror - Size 900x2500mm Shape. Dwg OMN-HTL-TB-200 | 2 | No | 3439.98 | 6879.96 |  |  |  | 0
32/Q | Ply Framing Rate | 0 | m2 | 388.27 | Rate only
| E11-K158-KD-mv-464 |  |  |  | 29675.594 |  |  |  | 0
33 | Gym Cabinet |  |  |  | 29675.594 |  |  |  | 0
33/A | Supply & installation of Gym cabinet with 18mm MDF in the ash olive finish including 6mm clear mirror, open shelving, drawers, and bins with flap doors. Size 2065x780x2560mm | 1 | No | 29675.594 | 29675.594 |  |  |  | 0
| Supply & installation of MFD louver shutter |  |  |  | 16888.3409 |  |  |  | 0
34 | Supply & installation of MDF louvers in wallpaper finish including necessary fittings. Size 770x720mm. Excluding wallpaper finish & edge trim.
34/A | Level 7 to 11 | 3 | Nos | 938.2412 | 2814.7235 |  |  |  | 0
34/B | Level 12 to 16 | 6 | Nos | 938.2412 | 5629.447 |  |  |  | 0
34/C | Level 19 to 23 | 3 | Nos | 938.2412 | 2814.7235 |  |  |  | 0
34/D | Level 24 to 27 | 6 | Nos | 938.2412 | 5629.447 |  |  |  | 0

## M12
201A22002 - DORCHESTER HOTEL & RESIDENCES (COMPLETION WORKS) | [16 empty] | 2023-04-18
M12
Sl No | VO. NO | KJD VO | Date Issued | E11 Ref No. | KCE Ref No. | Subcontractors | Package | Instruction Description | Budget | Submitted | KJD submission | Final Amount (AED) | Work Approval % | Previous Work done value | Cumulative Work done | Current Work done value | Remarks
1 | 336 | 1V | 2022-10-18 | 336 | K158 | KJD | Timber Works | Timber Doors & Misc Joinery Work - ballroom, Royal , Pres, Gym, Prayer, GF &l1 |  | 2312295.96 |  | 2312295.96 | PS-23 R2 | 439384.6707 | 746929.6956 | 307545.0249 |  |  | 73275.9952 | 193926.5031 | 120650.5079
2 | 348 | 2V | 2022-10-19 | 348 | K158 | KJD | Timber Works | Additional Joinery Works to vanity Counter Type 7A & 15A (Scope Gap in ASI) |  | 81875.0182 |  | 81875.0182 | C0-82 | [5 empty] | 366108.6756 | 553003.1925 | 186894.5169
3 | 372 | 3V | 2022-10-25 | 372 | K158 | KJD | Timber Works | Supply & Installation of Daybed Booth |  | 86902.2 |  | 86902.2 | CO-77
4 | 388 | 4V | 2022-10-27 | 388 | K158 | KJD | Timber Works | Fabrication, supply & installation of removable mdf louver panels to Hotel Corridors L7-27 as per below OME confirmation and details on RFI |  | 16888.3409 |  | 16888.3409 |  |  |  |  | OME confirmation & details on attached RFI ref KCE-ID-RFI-ML-000262 Rev1 & sketch KCE-SK-024
5 | 411 | 5V | 2022-11-07 | 411 | K158 | KJD | Timber Works | GF Lift Mirror Panel & FHC Doors |  | 15707.7206 |  | 15707.7206 | PS-023 Rev 03 |  |  |  | KJD Ref - KJD-201D22007-AC-QS-vf-QTN-22-163
6 | 415 | 6V | 2022-11-07 | 415 | K158 | KJD | Timber Works | Supply & installation of Shelves in Janitor room at Hotel Level 10, 16, 22 & 25 Supply & installation of Pantry cabinet at Hotel Level 3 |  | 21618.0688 |  | 21618.0688 |  | 19241.1276 | 19241.1276 | 0 | KJD Ref - KJD-201D22007-AC-QS-vf-QTN-22-161 & KJD-201D22009-AC-QS-vf-QTN-22-167
7 |  | 7V | 2022-11-24 | 464 |  | KJD | Timber Works | Gym cabinet |  | 29675.594 |  | 29675.59 |  |  |  |  | KJD Ref - KJD-201D22009-AC-QS-vf-QTN-22-174 dated 11/11/2022
8 |  | 8V | 2022-11-22 |  |  | KJD | Timber Works | Secret Garden |  | 154141.16 |  | 154141.16 |  |  |  |  | Awaiting confirmation from KCE
9 |  | 9V | 2022-12-28 | 574 |  |  |  | Supply & installation of beach wood skirting in white PU paint finish. |  | 27948.99 |  | 27948.99 | 90% | 25154.091 | 25154.091 | 0 | Variation balance to submit, Final Qty need to be agreed with KCE, H26a for 220 Rm issued to production | Only 90% approved until submit the WIR
10 |  | 10V | [5 empty] | Additional Qty of guest room ceiling | [8 empty] | Additional Qty of ceiling, issues with tender Qty. H26a ssued to production
11 |  | 11V | 2023-01-10 | 479 |  | KJD | Timber Works | ELV box |  | 24473.9429 |  | 24473.9429 | 90% | 22026.5487 | 18355.46 | -3671.0887 | KJD Ref - KJD-201D22009-AC-QS-vf-QTN-22-204 | Only 90% approved until submit the WIR
12 |  | 12V | 2023-01-10 | 555 |  | KJD | Timber Works | Ballroom Bar Bi fold door |  | 24075.33 |  | 24075.33 |  |  |  |  | KJD Ref - KJD-201D22009-AC-QS-vf-QTN-23-001
13 |  | 13V | 2023-01-10 | 555 |  | KJD | Timber Works | Sliding Doors @ Level 23 GYM Disable Toilet | 6500 | [7 empty] | VO Balance to submit, awaiting details from Mr. Sukesh
14 |  | 14V | [5 empty] | Temporary doors for electrical room (KJD-201D22009-AC-QS-vf-QTN-22-178) |  |  | 19273.8543 | 19273.8543 | 90% | 17346.4688 | 17346.4688 | 0 | VO Submitted, Option-1 for 79,093.93 & Option-2 for AED110,009.17, Confirmation received from KCE for 5 Nos 90Mins doors | Only 90% approved until submit the WIR
15 |  | 15V | [5 empty] | BOH Lobby Cupboards Level 7 to 27 (KJD-201D22009-AC-QS-vf-QTN-22-183 & 184) | [8 empty] | Budget of AED 555,754 for VE option, AED 642,334.12 for original Laminate option, Awaiting confirmation from KCE
16 |  | 16V | 2023-01-17 | 631 |  |  |  | Pocket Doors for Movable Partitions (KJD-201D22009-AC-QS-vf-QTN-22-197) |  | 104898.33 |  | 104898.33 | 30% |  | 31469.499 | 31469.499 | VO Submitted (KJD-201D22009-AC-QS-vf-QTN-22-197)
17 |  | 17V | 2023-01-10 | 609 |  |  |  | L23 - Lift lobbies - Washroom Mirror |  | 27217.38 |  | 27217.38 |  |  |  |  | VO Submitted, Ref KJD/201D22009/AC/QS-vf/QTN/23/006/R01
18 |  | 18V | 2023-02-16 | 752 |  | KJD | Timber Works | L23 Pantry (KJD-201D22009-AC-QS-vf-QTN-22-182-R01) |  | 55478.24 |  | 55478.24 |  |  |  |  | VO submitted (KJD-201D22009-AC-QS-vf-QTN-22-182-R01)
19 |  | 19V |  |  |  | KJD | Timber Works | Additional mirrors |  |  | 17836.25 | 17836.25 |  |  |  |  | VO submitted, awaiting confirmation from KCE
20 |  | 20V |  |  |  | KJD | Timber Works | Additional timber door based on KCE-AX-RFI-GF-00150_B | 10000 | [7 empty] | VO balance to submit
21 |  | 21V |  |  |  | KJD | Timber Works | Door frame thickness change based on KJD-ID-RFI-GF-00003_00_R | 25000 | [7 empty] | VO balance to submit
22 |  | 22V | [5 empty] | Lift car panels |  |  | 21090.01 | 21090.01 |  |  |  |  | KJD VO - KJD/201D22009/AC/QS-vf/QTN/23/026. Awaiting confirmation from KCE
23 |  | 23V | 2023-01-17 | 631 |  |  |  | Additional fabrics order on behalf of KCE (Dedar) |  |  | 70116.0698 | 70116.0698 | 90% | 63104.4628 | 63104.4628 | 0 | VO balance to submit | Please submit the supportings (supplier's quotations or other)
24 |  | 24V | 2023-01-19 | 639 |  |  |  | Additional 1No access door & 2 Nos FHC door | [8 empty] | VO balance to submit
25 |  | 25V | 2023-01-19 | 639 |  |  |  | Ground floor ADA lift access door | [8 empty] | VO balance to submit
26 |  | 26V | 2023-01-30 | 681 |  |  |  | Additional FHC door in paint finish | [8 empty] | VO balance to submit
27 |  | 27V | 2023-02-01 | 693 |  |  |  | MDF wall cladding in PU paint finish backing for WC-21 @ BOH area | [8 empty] | VO balance to submit
28 |  | 28V |  | 730 |  |  |  | MR MDF backing for ME-06 metal cladding | [8 empty] | VO balance to submit
29 |  | 29V | 2023-02-13 | 742 |  |  |  | MDF backing for ballroom metal ceiling | [8 empty] | VO balance to submit
30 |  | 30V | 2023-02-21 | 760 |  |  |  | Access panels on stone walls with ball catchers (Male 7 Nos & Female 6Nos) | [8 empty] | VO balance to submit
31 |  | 31V | 23.02.23 | 773 |  |  |  | Prefuction area additional timber panelling above door | [8 empty] | VO balance to submit
32 |  | 32V | 23.02.23 | 780 |  |  |  | Ballroom, Meeting room 1 & 2 additional doors & windows |  |  | 482131.41 | 482131.41 |  |  |  |  | KJD-201D22009-AC-QS-vf-QTN-23-031 Provisional proposal submitted, revised proposal under progress
[8 empty] | Total Amount [AED] | 41500 | 2983196.2754 | 610447.594 | 3593643.8655 |  | 527631.6326 | 829440.7243 | 301809.0917 | 90% only until Variation approved by OME