## March summary
M/s Khansaheb Civil Engineering LLC |  |  | our ref: ARS/1294/0123
Dubai, UAE |  |  | date: 28/02/2023
PROJECT: Plot 18 BB - Dorchester Hotel
Reference No: ARM/KCE-DHR/010
SI | DESCRIPTION | Previous | Current | Cumulative
I. | Hardlandscape Stoneworks
1 | Work Done Hardlandscape stoneworks | 1469466.6261 | 264181.0826 | 1733647.7087
2 | Variations - Roberts | 499789.6006 | 152525.7067 | 652315.3073
3 | Material on Site | 975313.0246 | -239649.3368 | 735663.6878
| Sub-total Amount (A) | 2944569.2514 | 177057.4525 | 3121626.7038
II. | Variations
1 | Variations - KCE | 1363601.2759 | 503896.5819 | 1867497.8578
| Sub-total Amount (B) | 1363601.2759 | 503896.5819 | 1867497.8578
III. | Grand Total: A+B=C | 4308170.5272 | 680954.0344 | 4989124.5616
IV. | Less Retention: Cx20% | -861634.1054 | -136190.8069 | -997824.9123
V. | Advance payment
1 | Stoneworks in Ballroom, Royal, Presidential Suit, Gym, Prayer Room, Lobbies | 216955.15 | 0 | 216955.15
2 | Stoneworks at GF and Level 02 Hardlandscape areas due to design change | 126189 | 0 | 126189
VI. | Less Advance payment recovery 10%
1 | Stoneworks in Ballroom, Royal, Presidential Suit, Gym, Prayer Room, Lobbies | -56644.164 | -10222.8536 | -66867.0176
2 | Stoneworks at GF and Level 02 Hardlandscape areas due to design change | -15680 | -37632 | -53312
| Total Net claim amount | 3717356.4078 | 496908.3739 | 4214264.7817

## Summary
Plot-18
IPC-Al Reem- February 2023 |  |  |  | Date: 27/02/2023 |  | Al Reem Claim |  |  | Variance
Invoice No: ARM-KCE-DHR-011
Item | Description | Amount | Previous - Certified | This Month Claim | Cumulative | Previous - Claim | This Month | Cumulative
1 | Ground Floor | 1060613.5 | 413255.41 | 247087.25 | 660342.66
2 | Level 02 | 673208.1555 | 498258.5576 | 0 | 498258.5576
3 | Level 04 | 295974.2543 | 231305.42 | 13609.6806 | 244915.1006
4 | Level 10 | 45666.68 | 0 | 0 | 0
5 | Level 17 | 2641.8 | 0 | 0 | 0
6 | Level 24 | 83370.7749 | 83371.5629 | 0 | 83371.5629
7 | Level 25 | 89567.1029 | 85695.8229 | 0 | 85695.8229
8 | Level 26 | 79999.26 | 9983.96 | 0 | 9983.96
9 | Level 27 | 81316.2646 | 77445.7726 | 3484.152 | 80929.9246
10 | Level 29 | 86942.1549 | 70150.12 | 0 | 70150.12
11 | Level 29 RTP | 853401.7526 | 0 | 0 | 0
|  | 3352701.6998 | 1469466.6261 | 264181.0826 | 1733647.7087 | 1061914.8776 | 292653.9029 | 1354568.7806 | 379078.9281 | 232806.5976 | Ok - cobbles Level 02 | ok | 2385963.016 | 177057.4525
| Variations | [7 empty] | 0
| Roberts | [7 empty] | 0
1 | Revisied stone size L29 | 84491.83 | 0 | 13118.592 | 13118.592
2 | Revisied Omani stone to pool | 76358.7091 | 46665.1545 | 0 | 46665.1545
3 | Stone work to L17 terraces | 202707.3 | 0 | 0 | 0
4 | Change for granite | 164129.8266 | 41686.51 | 11289.95 | 52976.46
5 | Change for granite cobbles | 711678.45 | 426211.8 | 132625.85 | 558837.65
6 | Discount | -35584 | -14773.8639 | -4508.6853 | -19282.5492
|  | 1203782.1157 | 499789.6006 | 152525.7067 | 652315.3073 | 369940.4965 | 108357.9165 | 478298.413 | 174016.8943 |  |  | ok
0
1 | Material on Site |  | 975313.0246 | -239649.3368 | 735663.6878 | -573687.44 | -158198.968 | 1055952.9126 | -320289.2248 |  |  | ok
0
| Variation - KCE | [7 empty] | 0
1 | ARM-AR-A-VAR-001, Change in Design of Level 02 Water Feature | 4165.4331 | 4160.8917 | 0 | 4160.8917 |  |  | 4160.89 | 0.0017
2 | ARM-AR-A-VAR-008, Supply and Installation of Omani flooring at Level 04 Pool area | 125306.361 | 67650 | 4510 | 72160 |  |  | 67250 | 4910
3 | ARS-1201-0922, Supply and installation of pool overflow channel stone support | 164783.0952 | 160184.0592 | 0 | 160184.0592 |  |  | 160184.06 | -0.0008
4 | ARM-AR-A-VAR-009, Supply and installation of 400mmL plate SS coping support at Level 24,25,27 & 29 | 98788.9305 | 98788.9305 | 0 | 98788.9305 |  |  | 98788.93 | 0.00046559
5 | Supply and installation of additional 10x10x5cm black granite cobbles at LPG Truck Delivery | 74930 | 74930 | 0 | 74930 |  |  | 74930 | 0
6 | Demolition of GF due to design enhancement | 72577.96 | 72577.96 | 0 | 72577.96 |  |  | 54756 | 17821.96
7 | Demolition of existing floor tiles (white granix tile 50mm thick) and tile bed at Level 2 | 8310.64 | 8310.64 | 0 | 8310.64
8 | Stoneworks at GF and Level 02 Hardlandscape areas due to design change E11/K114/SK/mv/597 | 1261894.844 | 156800 | 376320 | 533120 | [9 empty] | Advance paid to Reem
9 | Installation of tiles in Hotel balcony as per E11/K114/SK/mv/581 | 26597.55 | 26597.55 | 45167.115 | 71764.665
|  |  |  | 26775 | 26775 |  |  |  | 26775
7 | Supply and Installation of Hardlandscape Tiling works at Levels GF,2,4,23 & 29RTP | 534254 | 278670.8574 | 4884.44 | 283555.2974 | 43200 | 153648.0574 | 196848.0574 | 86707.24
9 | Stoneworks in Ballroom, Royal, Presidential Suit, Gym, Prayer Room, Lobbies (AHK Balance) | 2169551.48 | 566441.64 | 102228.536 | 668670.176 | 107012.16 | 337354.73 | 444366.89 | 224303.286 | [5 empty] | Advance paid to Reem
0
0
|  | 4541160.2938 | 1363601.2759 | 559885.091 | 1867497.8578 | [9 empty] | Only paid 90% Until VO approval
| Cumulative Works Done - Feb 2023 |  | 4308170.5272 | 736942.5435 | 4989124.5616 |  | 733815.6388

## BILL - FEB 23
Item | Description | Qty | Unit | Supply Rate | Install Rate | Amount | Previous Qty | Current Qty | Cumulative | Previous Amount | Current Amount | Cumulative Amount
| Ground Floor | [8 empty] | 0 | 0 | 0
| Paving | [8 empty] | 0 | 0 | 0
| Type HS-01 | [8 empty] | 0 | 0 | 0
1 | Type HS-01-A; Flush Kerb, 300x130mm, Black Granite | 247.5 | m | 337 | 84 | 104197.5 | 63 | 24.85 | 87.85 | 26523 | 10461.85 | 36984.85
2 | Type HS-01-C; Upstand Kerb, 200x330mm, Black Granite | 270.8 | m | 470 | 113 | 157876.4 | 0 |  | 0 | 0 | 0 | 0
| Type HS-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
3 | Type HS-02-A; Field Pattern, 100x100x50mm, Granite Cobble | 1574.6 | m2 | 190 | 200 | 614094 | 942 | 475.14 | 1417.14 | 367380 | 185304.6 | 552684.6 | 1417.14 | 475.14
4 | Type HS-02-B; Field Pattern, 600x300x80mm, Black Granite | 72.5 | m2 | 663 | 218 | 63872.5 | 0 |  | 0 | 0 | 0 | 0
5 | Type HS-02-C; Banding, 600x300x80mm, Black Granite | 224.3 | m | 207 | 80 | 64374.1 | 67.43 | 88.97 | 156.4 | 19352.41 | 25534.39 | 44886.8
| Type HS-04 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
6 | Type HS-04-A; Field Pattern, 100x100x50mm, Granite cobble | 144.1 | m2 | 190 | 200 | 56199 | 0 | 66.119 | 66.119 | 0 | 25786.41 | 25786.41
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
7 | Type HS-02-A; Field Pattern; 100x100x50mm; Granite cobble | 388.47 | m2 | 190 | 200 | 151503.3 | 0 |  | 0 | 0 | 0 | 0
8 | Type HS-02-B; Banding; 600x300x80mm; Basalt | 30.56 | m | 238 | 85 | 9870.88 | 0 |  | 0 | 0 | 0 | 0
| Type HS-04 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
9 | Type HS-04-A; Driveway Field Pattern; 100x100x50mm; Granite cobble | 708.62 | m2 | 190 | 200 | 276361.8 | 708.62 | 0 | 708.62 | 276361.8 | 0 | 276361.8
10 | Type HS-04-B; Brass Inlay; 35x10mm; Solid Brass | 19 | m | 1025.2941 | 74.1176 | 20888.8235 | 12.38 | 0 | 12.38 | 13610.7176 | 0 | 13610.7176
11 | Type HS-04-C; Banding; 600x300x50mm; Basalt | 123.57 | m | 123 | 68 | 23601.87 | 123.57 | 0 | 123.57 | 23601.87 | 0 | 23601.87
12 | Type HS-04-D; Upstand Kerb; 300x300mm; Basalt | 46.63 | m | 929 | 143 | 49987.36 | 46.63 |  | 46.63 | 49987.36 | 0 | 49987.36
13 | Type HS-04-E; Field Pattern; 100x100x50mm; Granite cobble | 89.02 | m2 | 190 | 200 | 34717.8 | 89.02 | 0 | 89.02 | 34717.8 | 0 | 34717.8
| Type HS-06 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
14 | Type HS-06-B; Banding; 200x100x50mm; Basalt | 25.14 | m | 54.22 | 38.78 | 2338.02 | 0 |  | 0 | 0 | 0 | 0
| Water Feature | [5 empty] | 0 |  | 0 | 0 | 0 | 0
15 | WF-02-A; Ledge coping, 1300x900x90-30mm (cut to fit in radius), Basalt | 18.67 | m2 | 2223 | 874.4853 | 57830.05 | 18.67 | 0 | 18.67 | 57830.05 | 0 | 57830.05
16 | WF-02-B; Suspended Floor, 550x1100x20mm, Basalt | 34.15 | m2 | 456 | 147 | 20592.45 | 34.15 | 0 | 34.15 | 20592.45 | 0 | 20592.45
17 | WF-02-C; External Wall Cladding, 380x300x20mm, Basalt | 8.8218 | m² | 456 | 189 | 5690.061 | 8.82 | 0 | 8.82 | 5688.9 | 0 | 5688.9
18 | WF-02-D; Overflow Channel Coping, 300x300x50mm, Black Granite cobble | 24.58 | m | 123 | 107 | 5653.4 | 7.37 | 0 | 7.37 | 1695.1 | 0 | 1695.1
19 | WF-02-E; Internal Wall & Floor, 300x300x5mm, Ceramic mosaic (fixing only, material to be supplied by Contractor) | 52.539 | m² |  | 169 | 8879.091 | 52.54 | 0 | 52.54 | 8879.26 | 0 | 8879.26
20 | Buzon Pedestal | 34.15 | m2 | 155 |  | 5293.25 | 34.15 | 0 | 34.15 | 5293.25 | 0 | 5293.25
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 04 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving (Hotel) | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
21 | Type HS-02-A; Ornamental Gravel; 10-30mm; Sandstone | 52.67 | m2 | 144.8382 | 24.7059 | 8929.8887 | 0 |  | 0 | 0 | 0 | 0
| Type HS-03 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
22 | Type HS-03-A; Ornamental Gravel; 10-30mm; Sandstone | 16.86 | m2 | 144.8382 | 24.7059 | 2858.5138 | 0 |  | 0 | 0 | 0 | 0
| Paving (Resi) | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type BS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
23 | Type BS-01-A; Wall Cladding; Sandstone | 4.74 | m2 | 221 | 182 | 1910.22 | 0 |  | 0 | 0 | 0 | 0
24 | Type BS-01-B; Seat Finish; 20mm; Light Grey Omani marble | 2.928 | m2 | 268 | 198 | 1364.448 | 0 |  | 0 | 0 | 0 | 0
| Type BS-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
25 | Type BS-02-A; Wall claddding; Sandstone | 3.7584 | m2 | 221 | 182 | 1514.6352 | 0 |  | 0 | 0 | 0 | 0
26 | Type BS-02-B; Seat Finish; 20mm Ligth Grey Omani Marble | 7.9344 | m2 | 268 | 198 | 3697.4304 | 0 |  | 0 | 0 | 0 | 0
| Type EC-03 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
27 | Type EC-03-A; Wall Cladding; Sandstone | 8.6506 | m2 | 221 | 182 | 3486.1918 | 0 |  | 0 | 0 | 0 | 0
| Type EC-10 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
28 | Type EC-10-B; Wall Coping; 200x20mm; Omani Marble | 14.31 | m | 66 | 48 | 1631.34 | 0 |  | 0 | 0 | 0 | 0
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
29 | SP-04-A; Overflow Coping, 300mmWx20mmm, Omani Limestone | 71 | m | 103 | 62 | 11715 | 71 | 0 | 71 | 11715 | 0 | 11715
30 | SP-04-B; Wall FInish, 20mm, Omani Limestone | 95.28 | m2 | 232 | 182 | 39445.92 | 95.28 | 0 | 95.28 | 39445.92 | 0 | 39445.92
31 | SP-04-C; Floor FInish, 20mm, Omani Limestone | 174 | m2 | 220 | 174 | 68556 | 174 | 0 | 174 | 68556 | 0 | 68556
32 | SP-04-D; Step Tread, 420mmWx20mm, Omani Limestone | 7 | m | 135 | 81 | 1512 | 7 | 0 | 7 | 1512 | 0 | 1512
33 | SP-04-E; Step Riser, 130mmHx20mm, Omani Limestone | 8.75 | m | 45 | 27 | 630 | 8.75 | 0 | 8.75 | 630 | 0 | 630
34 | SP-04-F; Overflow Pool Wall, 20mm, Omani Limestone | 31.59 | m2 | 232 | 182 | 13078.26 | 31.59 | 0 | 31.59 | 13078.26 | 0 | 13078.26
35 | SP-04-G; Overflow channel coping, Porcelaine Tile (Fixing Only, material to be supplied by Contractor) | 66 | m |  | 755.8788 | 49888 | 66 | 0 | 66 | 49888 | 0 | 49888
36 | SP-04-H; Overflow channel wall & floor; Omani Limestone | 19.5 | m2 | 262 | 183 | 8677.5 | 19.5 | 0 | 19.5 | 8677.5 | 0 | 8677.5
| Water Feature | [5 empty] | 64 | 0 | 64 | 0 | 0 | 0
37 | WF-04B-A; Chef's Table Coping, 13900x1400x20mm, Silestone | 1 | no | 5497 | 5921 | 11418 | 0 |  | 0 | 0 | 0 | 0
38 | WF-04B-B; Wall & Floor Finish,20mm, Natural Stone | 44.621 | m² | 221 | 182 | 17982.263 | 44.62 | 0 | 44.62 | 17981.86 | 0 | 17981.86
39 | WF-04B-D; Wall Cladding,20mm, Natural Stone | 41.96 | m² | 221 | 251.3756 | 19820.88 | 41.96 | 0 | 41.96 | 19820.88 | 0 | 19820.88
40 | WF-04B-E; Water Drain Channel Wall & Floor, 20mm, Natural Stone | 18.91 | m² | 221 | 358.2655 | 10953.91 | 0 | 17.019 | 17.019 | 0 | 9858.519 | 9858.519
41 | WF-04B-F; Water Drain Channel Top, 20mm, Natural Stone | 2.736 | m² | 221 | 1300.1523 | 4161.8119 | 0 | 2.466 | 2.466 | 0 | 3751.1616 | 3751.1616
42 | WF-04B-C; Stainless Steel Water Channel 225x225x225x3mm as per drawing no. LA-LD-L4-3204 detail 303 | 15.17 | m |  | 839.95 | 12742.0415 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 10 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
43 | SP-10-A; Overflow Coping, 300mmWx20mmm, Omani Limestone | 28 | m | 107 | 65 | 4816 | 0 |  | 0 | 0 | 0 | 0
44 | SP-10-B; Wall FInish, 20mm, Omani Limestone | 79 | m2 | 232 | 182 | 32706 | 0 |  | 0 | 0 | 0 | 0
45 | SP-10-D; Step Tread, 420mmWx20mm, Omani Limestone | 17 | m | 169 | 76 | 4165 | 0 |  | 0 | 0 | 0 | 0
46 | SP-10-E; Step Riser, 130mmHx20mm, Omani Limestone | 20.4 | m | 52 | 27 | 1611.6 | 0 |  | 0 | 0 | 0 | 0
47 | SP-10-F; Overflow Pool Wall, 20mm, Omani Limestone | 5.72 | m2 | 232 | 182 | 2368.08 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 17 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
48 | Type HS-01-A; Crazy Cut Floor, Bluestone 20mm thick | 538 | m2 | 200 | 142 | Rate only | 0 |  | 0 | 0 | 0 | 0
49 | Levl 17- 50mm dia Type HS-02-C, River Pebble, Dark Grey, Washed & tumble finish, 50mm dia (rates taken from Al Reem L29) | 31.45 | m2 | 60 | 24 | 2641.8 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 24 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
50 | Type HS-01-B; Pool Deck; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 220 | 174 | 4223.68 | 10.72 | 0 | 10.72 | 4223.68 | 0 | 4223.68
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Landscape | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type EC-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
51 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 220 | 174 | 2942.392 | 7.47 | 0 | 7.47 | 2943.18 | 0 | 2943.18
52 | Shadow gap - C type; 20x60x20x10mm | 17.36 | m | 178 | 45 | 3871.28 | 17.36 | 0 | 17.36 | 3871.28 | 0 | 3871.28
| Type ST-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
53 | Type ST-01-A; Step Tread; 660x20mm; Omani marble | 13.32 | m | 193 | 83 | 3676.32 | 13.32 | 0 | 13.32 | 3676.32 | 0 | 3676.32
54 | Type ST-01-B; Step Riser; 170x20mm; Omani marble | 13.32 | m | 52 | 27 | 1052.28 | 13.32 | 0 | 13.32 | 1052.28 | 0 | 1052.28
55 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS C channel | 40.45 | m | 187.7647 | 46.9412 | 9493.8529 | 40.45 | 0 | 40.45 | 9493.8529 | 0 | 9493.8529
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
56 | Type SP-24-A; Rim flow channel sloped coping; 600x20mm; Omani marble | 31.1 | m | 185 | 577.8971 | 23726.1 | 31.1 | 0 | 31.1 | 23726.1 | 0 | 23726.1
57 | Type SP-24-B; Wall & Floor finish; 20mm; Omani marble | 51.76 | m2 | 232 | 295.6592 | 27311.64 | 51.76 | 0 | 51.76 | 27311.64 | 0 | 27311.64
58 | Type SP-24-D; Step Tread; 620Wx20mm; Omani marble | 6.12 | m | 193 | 83 | 1689.12 | 6.12 | 0 | 6.12 | 1689.12 | 0 | 1689.12
59 | Type SP-24-E; Step Riser; 200Htx20mm; Omani marble | 8.16 | m | 52 | 27 | 644.64 | 8.16 | 0 | 8.16 | 644.64 | 0 | 644.64
60 | Type SP-24-F; Overflow channel wall & floor; 25x25x5mm; Ceramic Mosaic tile | 17.11 | m² | 105 | 172 | 4739.47 | 17.11 | 0 | 17.11 | 4739.47 | 0 | 4739.47
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 25 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
61 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 16.72 | m2 | 220 | 174 | 6587.68 | 16.72 | 0 | 16.72 | 6587.68 | 0 | 6587.68
| Landscape | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type EC-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
62 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.47 | m2 | 220 | 174 | 2943.18 | 7.47 | 0 | 7.47 | 2943.18 | 0 | 2943.18
63 | Shadow gap - C type; 20x60x20x10mm | 17.36 | m | 178 | 45 | 3871.28 | 0 |  | 0 | 0 | 0 | 0
| Type ST-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
64 | Type ST-01-A; Outdoor Terrace Stair; 600x20mm; Omani marble | 13.32 | m | 193 | 83 | 3676.32 | 13.32 | 0 | 13.32 | 3676.32 | 0 | 3676.32
65 | Type ST-01-B; Outdoor Terrace Stair; 170x20mm; Omani marble | 13.32 | m | 52 | 27 | 1052.28 | 13.32 | 0 | 13.32 | 1052.28 | 0 | 1052.28
66 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS C channel | 40.45 | m | 187.7647 | 46.9412 | 9493.8529 | 40.45 |  | 40.45 | 9493.8529 | 0 | 9493.8529
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
67 | Type SP-25-A; Rim flow channel coping; 600x20mm; omani marble | 31.56 | m | 185 | 577.897 | 24077.03 | 31.56 | 0 | 31.56 | 24077.03 | 0 | 24077.03
68 | Type SP-25-B; wall & floor finish; 1200x600x20mm; omani marble | 60 | m2 | 232 | 280.05 | 30723 | 60 | 0 | 60 | 30723 | 0 | 30723
69 | Type SP-25-D; Step Tread; 600Wx20mm; omani marble | 6.12 | m | 193 | 83 | 1689.12 | 6.12 | 0 | 6.12 | 1689.12 | 0 | 1689.12
70 | Type SP-25-E; Step Riser; 200Htx20mm; omani marble | 8.16 | m | 52 | 27 | 644.64 | 8.16 | 0 | 8.16 | 644.64 | 0 | 644.64
71 | Type SP-25F; Overflow channel wall & floor; 25x25x5mm ceramic mosaic tile | 17.36 | m² | 105 | 172 | 4808.72 | 17.36 | 0 | 17.36 | 4808.72 | 0 | 4808.72
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 26 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
72 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 25.34 | m2 | 220 | 174 | 9983.96 | 25.34 | 0 | 25.34 | 9983.96 | 0 | 9983.96
| Landscape | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type EC-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
73 | Type EC-02-A; Wall Coping; 1200x600x20mm; Omani marble | 3.91 | m2 | 220 | 174 | 1540.54 | 0 |  | 0 | 0 | 0 | 0
74 | Type EC-02-B; Wall Cladding ; 1200x600x20mm; Omani Marble | 19.53 | m2 | 220 | 174 | 7694.82 | 0 |  | 0 | 0 | 0 | 0
| Type EC-03 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
75 | Type EC-03-A; Wall Coping; 1200x600x20mm; Omani marble | 5.69 | m2 | 220 | 174 | 2241.86 | 0 |  | 0 | 0 | 0 | 0
76 | Type EC-03-B; Wall Cladding ; 1200x600x20mm; Omani Marble | 48.51 | m2 | 220 | 174 | 19112.94 | 0 |  | 0 | 0 | 0 | 0
| Type ST-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
77 | Type ST-01-A; Step Tread; 620x20mm; Omani marble | 11 | m | 193 | 83 | 3036 | 0 |  | 0 | 0 | 0 | 0
78 | Type ST-01-B; Step Riser; 150x20mm; Omani marble | 11 | m | 52 | 27 | 869 | 0 |  | 0 | 0 | 0 | 0
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
79 | Type SP-26-A; coping; 535x20mm; Omani marble | 14 | m | 185 | 433.8414 | 8663.78 | 0 |  | 0 | 0 | 0 | 0
80 | Type SP-26-B; wall & floor finish; 1200x600x20mm; omani marble | 45.94 | m2 | 232 | 241.9216 | 21771.96 | 0 |  | 0 | 0 | 0 | 0
81 | Type SP-26-D; Step Tread; 600x600x20mm; omani marble | 7.5 | m | 193 | 83 | 2070 | 0 |  | 0 | 0 | 0 | 0
82 | Type SP-26-E; Step Riser; 600x200x20mm; omani marble | 7.5 | m | 52 | 27 | 592.5 | 0 |  | 0 | 0 | 0 | 0
83 | Type SP-26-F; Upstand wall finish; 20mm; omani marble | 5.85 | m2 | 232 | 182 | 2421.9 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 27 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
84 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 220 | 174 | 4223.68 | 10.72 | 0 | 10.72 | 4223.68 | 0 | 4223.68
| Landscape | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type EC-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
85 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 220 | 174 | 2942.392 | 7.47 | 0 | 7.47 | 2943.18 | 0 | 2943.18
86 | Shadow gap -C Type 20x60x20x10mm | 17.36 | m | 178 | 45 | 3871.28 | 0 | 15.624 | 15.624 | 0 | 3484.152 | 3484.152
| Type ST-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
87 | Type ST-01-A; Step Tread; 660x20mm; Omani marble | 13.32 | m | 193 | 83 | 3676.32 | 13.32 | 0 | 13.32 | 3676.32 | 0 | 3676.32
88 | Type ST-01-B; Step Riser; 170x20mm; Omani marble | 13.32 | m | 52 | 27 | 1052.28 | 13.32 | 0 | 13.32 | 1052.28 | 0 | 1052.28
89 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS Cchannel | 40.45 | m | 187.76 | 46.9412 | 9493.6626 | 40.45 |  | 40.45 | 9493.6626 | 0 | 9493.6626
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
90 | Type SP-27-A; Rim flow channel coping; 600x20mm; omani marble | 31.56 | m | 185 | 577.897 | 24077.03 | 31.56 | 0 | 31.56 | 24077.03 | 0 | 24077.03
91 | Type SP-27-B; Wall & floor finish; 1200x600x20mm; omani marble | 46.48 | m2 | 232 | 311.5318 | 25263.36 | 46.48 | 0 | 46.48 | 25263.36 | 0 | 25263.36
92 | Type SP-27-D; Step Tread; 600Wx20mm; omani marble | 6.15 | m | 193 | 83 | 1697.4 | 6.15 | 0 | 6.15 | 1697.4 | 0 | 1697.4
93 | Type SP-27-E; Step Riser; 200Htx20mm; omani marble | 8.2 | m | 52 | 27 | 647.8 | 8.2 | 0 | 8.2 | 647.8 | 0 | 647.8
94 | Type SP-27-F; Overflow channel wall & floor; 25x25x5mm; ceramic mosaic tile | 15.78 | m² | 105 | 172 | 4371.06 | 15.78 | 0 | 15.78 | 4371.06 | 0 | 4371.06
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 29 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
95 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 220 | 174 | 4223.68 | 10.72 | 0 | 10.72 | 4223.68 | 0 | 4223.68
| Landscape | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type EC-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
96 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 220 | 174 | 2942.392 | 7.47 | 0 | 7.47 | 2943.18 | 0 | 2943.18
97 | Shadow gap -C Type 20x60x20x10mm | 17.36 | m | 178 | 45 | 3871.28 | 0 |  | 0 | 0 | 0 | 0
| Type ST-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
98 | Type ST-01-A; Step Tread; 660mmWx20mm; Omani marble | 13.32 | m | 193 | 83 | 3676.32 | 4.39 | 0 | 4.39 | 1211.64 | 0 | 1211.64
99 | Type ST-01-B; Step Riser; 170mmHx20mm; Omani marble | 13.32 | m | 52 | 27 | 1052.28 | 1.13 | 0 | 1.13 | 89.27 | 0 | 89.27
100 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS Cchannel | 40.45 | m | 187.7647 | 46.9412 | 9493.8529 | 0 |  | 0 | 0 | 0 | 0
| Swimming Pool | [5 empty] | 0 |  | 0 | 0 | 0 | 0
101 | Type SP-29-A; Rim flow channel coping; 20mm thick; omani marble | 31.56 | m | 185 | 577.897 | 24077.03 | 31.56 | 0 | 31.56 | 24077.03 | 0 | 24077.03
102 | Type SP-29-B; Wall & floor finish; 1200x600x20mm; omani marble | 59.28 | m2 | 232 | 283.5628 | 30562.56 | 59.28 | 0 | 59.28 | 30562.56 | 0 | 30562.56
103 | Type SP-29-D; Step Tread; 600x400x20mm; omani marble | 6.12 | m | 193 | 83 | 1689.12 | 6.12 | 0 | 6.12 | 1689.12 | 0 | 1689.12
104 | Type SP-29-E; Step Riser; 600x200x20mm; omani marble | 8.16 | m | 52 | 27 | 644.64 | 8.16 | 0 | 8.16 | 644.64 | 0 | 644.64
105 | Type SP-29-F; Overflow channel wall & floor; 25x25x5mm; ceramic mosai tile | 17 | m² | 105 | 172 | 4709 | 17 | 0 | 17 | 4709 | 0 | 4709
| RTP Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type HS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
106 | Type HS-01-A; Field Pattern; 600x300x20mm; Omani marble 1200x600mm | 610.29 | m2 | 150 | 177 | 199564.83 | 0 |  | 0 | 0 | 0 | 0
| Type HS-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
107 | Type HS-02-A; Field Pattern; 600x300x20mm; Omani marble 1200x600mm | 55 | m2 | 150 | 177 | 17985 | 0 |  | 0 | 0 | 0 | 0
| RTP Paving | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Type BS-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
108 | Type BS-01-A; Bar countertop; 635Wx20mm; Calacatta Gold | 1 | no. | 31077 | 5246 | 36323 | 0 |  | 0 | 0 | 0 | 0
109 | Type BS-01-B; Bar counter wall cladding; 20mm thick; Calacatta Gold | 17.33 | m2 | 2040 | 266 | 39962.98 | 0 |  | 0 | 0 | 0 | 0
110 | Type BS-01-C; Wall coping; 600W; Light Grey | 1 | no. | 10543 | 1990 | 12533 | 0 |  | 0 | 0 | 0 | 0
| Type EC-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
111 | Type EC-01-A; wall coping; 200mmWx20mm; Omani marble | 24.7 | m | 69 | 47 | 2865.2 | 0 |  | 0 | 0 | 0 | 0
112 | Type EC-01-B; wall cladding; 600x300x20mm; Omani marble | 148.44 | m2 | 163 | 192 | 52696.2 | 0 |  | 0 | 0 | 0 | 0
| Type ST-01 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
113 | Type ST-01-A; Step Tread; 295mmWx20mm; omani marble | 7.23 | m | 88.3436 | 37.988 | 913.3769 | 0 |  | 0 | 0 | 0 | 0
114 | Type ST-01-B; Step Riser; 150mmHx20mm omani marble | 7.23 | m | 46.8706 | 24.2912 | 514.4996 | 0 |  | 0 | 0 | 0 | 0
| Type ST-02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
115 | Type ST-02-A; Step Tread; 295mmWx20mm; omani marble | 7.94 | m | 88.3436 | 37.988 | 1003.0722 | 0 |  | 0 | 0 | 0 | 0
116 | Type ST-02-B; Step Riser; 150mmHx20mm; omani marble | 11.71 | m | 46.8706 | 24.2912 | 833.3043 | 0 |  | 0 | 0 | 0 | 0
117 | Type ST-02-A; Step landing; 20mm thick; omani marble | 18.95 | m2 | 220 | 174 | 7466.3 | 0 |  | 0 | 0 | 0 | 0
118 | Type ST-02-B; Step Riser; 450mHx20mm omani marble | 17.7 | m | 140.6118 | 72.8735 | 3778.6897 | 0 |  | 0 | 0 | 0 | 0
| Type ST-06 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
119 | Type ST-06-A; Step tread; 520mmW; omani marble | 45.25 | m | 253 | 98 | 15882.75 | 0 |  | 0 | 0 | 0 | 0
120 | Type ST-06-B; Step Riser; 90mmH x 20mm; omani marble | 45.25 | m | 28 | 23 | 2307.75 | 0 |  | 0 | 0 | 0 | 0
| Type SP-29A | [5 empty] | 0 |  | 0 | 0 | 0 | 0
121 | Type SP-29A-A; Pool coping; 200mmW; Light grey omani limestone | 86.3 | m | 69 | 47 | 10010.8 | 0 |  | 0 | 0 | 0 | 0
122 | Type SP-29A-B; Wall finish; 25x25x10mm; Sky blue natural stone mosaic | 453 | m2 | 210 | 161 | 168063 | 0 |  | 0 | 0 | 0 | 0
123 | Type SP-29A-C; Floor finish; 25x25x10mm; Sky blue natural stone mosaic | 407 | m2 | 210 | 143 | 143671 | 0 |  | 0 | 0 | 0 | 0
124 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 600mmWx10mm | 158.8 | m | 143 | 87 | 36524 | 0 |  | 0 | 0 | 0 | 0
125 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 1200mmWx10mm | 29.7 | m | 279 | 175 | 13483.8 | 0 |  | 0 | 0 | 0 | 0
126 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 400mmWx10mm | 21.5 | m | 97 | 58 | 3332.5 | 0 |  | 0 | 0 | 0 | 0
127 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 300mmWx10mm | 6.2 | m | 75 | 44 | 737.8 | 0 |  | 0 | 0 | 0 | 0
128 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 450mmWx10mm | 95 | m | 109 | 66 | 16625 | 0 |  | 0 | 0 | 0 | 0
129 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 1600mmWx10mm | 6.7 | m | 371 | 233 | 4046.8 | 0 |  | 0 | 0 | 0 | 0
130 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 70mm ht x 10mm | 19 | m | 16 | 8 | 456 | 0 |  | 0 | 0 | 0 | 0
131 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 130mm ht x 10mm | 95 | m | 30 | 14 | 4180 | 0 |  | 0 | 0 | 0 | 0
132 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 200mm ht x 10mm | 23.4 | m | 45 | 22 | 1567.8 | 0 |  | 0 | 0 | 0 | 0
133 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 370mm ht x 10mm | 68.4 | m | 84 | 40 | 8481.6 | 0 |  | 0 | 0 | 0 | 0
134 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 420mm ht x 10mm | 31 | m | 96 | 46 | 4402 | 0 |  | 0 | 0 | 0 | 0
135 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 450mm ht x 10mm | 27.8 | m | 102 | 49 | 4197.8 | 0 |  | 0 | 0 | 0 | 0
136 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic ,470mm ht x 10mm | 72 | m | 107 | 51 | 11376 | 0 |  | 0 | 0 | 0 | 0
137 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 500mm ht x 10mm | 16.9 | m | 114 | 55 | 2856.1 | 0 |  | 0 | 0 | 0 | 0
138 | Type SP-29A-G; Overflow channel coping; 250mmW x 20mm ; porcelain rakeen (fixing only, material to be supplied by Contractor | 131 | m |  | 169 | 22139 | 0 |  | 0 | 0 | 0 | 0
139 | Type SP-29A-H; Decorative pebble; 50mm dia; river stone Excluding Type SP-29A-F - GRP pool Table & Coping Support | 31.2 | m2 | 60 | 24 | 2620.8 | 0 |  | 0 | 0 | 0 | 0
| Total |  |  |  |  | 3352701.6998 |  |  |  | 1469466.6261 | 264181.0826 | 1733647.7087
Note on J8: Himal Kosala: only 95% done, 90% until total area WIR approval
Note on I65: Himal Kosala: only 90%
Note on I66: Himal Kosala: only 90%
Note on I150: Himal Kosala: only 90%
Note on I182: Himal Kosala: No Supporting

## Variation
Item | Description | Qty | Unit | Supply Rate | Install Rate | Amount | Previous Qty | Current Qty | Cumulative | Previous Amount | Current Amount | Cumulative Amount
| Roberts Variation | [8 empty] | 0 | 0 | 0
[10 empty] | 0 |  | 0
| Level 29 | [8 empty] | 0 |  | 0
1 | Type HS-01-A; Field Pattern; 600x300x20mm; Omani marble 1200x600mm | 610.29 | m2 | 127 | 0 | 77506.83 |  | 103.296 | 103.296 | 0 | 13118.592 | 13118.592
2 | Type HS-02-A; Field Pattern; 600x300x20mm; Omani marble 1200x600mm | 55 | m2 | 127 | 0 | 6985 |  |  |  | 0 |  | 0
[10 empty] | 0 |  | 0
| Level 04 | [8 empty] | 0 |  | 0
3 | Type BS-01-B; Seat Finish; 20mm; Light Grey Omani marble | 2.928 | m2 | 46 | 0 | 134.688 |  |  |  | 0 |  | 0
4 | Type BS-02-B; Seat Finish; 20mm Ligth Grey Omani Marble | 7.9344 | m2 | 46 | 0 | 364.9824 |  |  |  | 0 |  | 0
5 | Type EC-10-B; Wall Coping; 200x20mm; Omani Marble | 14.31 | m | 14.2 | 0 | 203.202 |  |  |  | 0 |  | 0
6 | SP-04-A; Overflow Coping, 300mmWx20mmm, Omani Limestone | 71 | m | 22.22 | 0 | 1577.62 | 71 |  | 71 | 1577.62 | 0 | 1577.62
7 | SP-04-B; Wall FInish, 20mm, Omani Limestone | 95.28 | m2 | 57 | 0 | 5430.96 | 95.28 |  | 95.28 | 5430.96 | 0 | 5430.96
8 | SP-04-C; Floor FInish, 20mm, Omani Limestone | 174 | m2 | 57 | 0 | 9918 | 174 |  | 174 | 9918 | 0 | 9918
9 | SP-04-D; Step Tread, 420mmWx20mm, Omani Limestone | 7 | m | 28.46 | 0 | 199.22 | 7 |  | 7 | 199.22 | 0 | 199.22
10 | SP-04-E; Step Riser, 130mmHx20mm, Omani Limestone | 8.75 | m | 10.45 | 0 | 91.4375 | 8.75 |  | 8.75 | 91.4375 | 0 | 91.4375
11 | SP-04-F; Overflow Pool Wall, 20mm, Omani Limestone | 31.59 | m2 | 57 | 0 | 1800.63 | 31.59 |  | 31.59 | 1800.63 | 0 | 1800.63
12 | SP-04-H; Overflow channel wall & floor; Omani Limestone | 19.5 | m2 | 58 | 0 | 1131 | 19.5 |  | 19.5 | 1131 | 0 | 1131
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 10 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
13 | SP-10-A; Overflow Coping, 300mmWx20mmm, Omani Limestone | 28 | m | 21.96 |  | 614.88 | 0 |  | 0 | 0 | 0 | 0
14 | SP-10-B; Wall FInish, 20mm, Omani Limestone | 79 | m2 | 57 |  | 4503 | 0 |  | 0 | 0 | 0 | 0
15 | SP-10-D; Step Tread, 420mmWx20mm, Omani Limestone | 17 | m | 36.02 |  | 612.34 | 0 |  | 0 | 0 | 0 | 0
16 | SP-10-E; Step Riser, 130mmHx20mm, Omani Limestone | 20.4 | m | 12.5 |  | 255 | 0 |  | 0 | 0 | 0 | 0
17 | SP-10-F; Overflow Pool Wall, 20mm, Omani Limestone | 5.72 | m2 | 57 |  | 326.04 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 24 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
18 | Type HS-01-B; Pool Deck; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 57 |  | 611.04 | 10.72 |  | 10.72 | 611.04 | 0 | 611.04
19 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 57 |  | 425.676 | 7.47 |  | 7.47 | 425.79 | 0 | 425.79
20 | Type ST-01-A; Step Tread; 660x20mm; Omani marble | 13.32 | m | 39.7 |  | 528.804 | 13.32 |  | 13.32 | 528.804 | 0 | 528.804
21 | Type ST-01-B; Step Riser; 170x20mm; Omani marble | 13.32 | m | 12.5 |  | 166.5 | 13.32 |  | 13.32 | 166.5 | 0 | 166.5
22 | Type SP-24-A; Rim flow channel sloped coping; 600x20mm; Omani marble | 31.1 | m | 36 |  | 1119.6 | 31.1 |  | 31.1 | 1119.6 | 0 | 1119.6
23 | Type SP-24-B; Wall & Floor finish; 20mm; Omani marble | 51.76 | m2 | 57 |  | 2950.32 | 51.76 |  | 51.76 | 2950.32 | 0 | 2950.32
24 | Type SP-24-D; Step Tread; 620Wx20mm; Omani marble | 6.12 | m | 39.7 |  | 242.964 | 6.12 |  | 6.12 | 242.964 | 0 | 242.964
25 | Type SP-24-E; Step Riser; 200Htx20mm; Omani marble | 8.16 | m | 12.5 |  | 102 | 8.16 |  | 8.16 | 102 | 0 | 102
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 25 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
26 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 16.72 | m2 | 57 | 0 | 953.04 | 16.72 |  | 16.72 | 953.04 | 0 | 953.04
27 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.47 | m2 | 57 | 0 | 425.79 | 7.47 |  | 7.47 | 425.79 | 0 | 425.79
28 | Type ST-01-A; Outdoor Terrace Stair; 600x20mm; Omani marble | 13.32 | m | 39.7 | 0 | 528.804 | 13.32 |  | 13.32 | 528.804 | 0 | 528.804
29 | Type ST-01-B; Outdoor Terrace Stair; 170x20mm; Omani marble | 13.32 | m | 12.5 | 0 | 166.5 | 13.32 |  | 13.32 | 166.5 | 0 | 166.5
30 | Type SP-25-A; Rim flow channel coping; 600x20mm; omani marble | 31.56 | m | 36 | 0 | 1136.16 | 31.56 |  | 31.56 | 1136.16 | 0 | 1136.16
31 | Type SP-25-B; wall & floor finish; 1200x600x20mm; omani marble | 60 | m2 | 57 | 0 | 3420 | 60 |  | 60 | 3420 | 0 | 3420
32 | Type SP-25-D; Step Tread; 600Wx20mm; omani marble | 6.12 | m | 39.7 | 0 | 242.964 | 6.12 |  | 6.12 | 242.964 | 0 | 242.964
33 | Type SP-25-E; Step Riser; 200Htx20mm; omani marble | 8.16 | m | 12.5 | 0 | 102 | 8.16 |  | 8.16 | 102 | 0 | 102
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 26 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
34 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 25.34 | m2 | 57 | 0 | 1444.38 | 25.34 |  | 25.34 | 1444.38 | 0 | 1444.38
35 | Type EC-02-A; Wall Coping; 1200x600x20mm; Omani marble | 3.91 | m2 | 57 | 0 | 222.87 | 0 |  | 0 | 0 | 0 | 0
36 | Type EC-02-B; Wall Cladding ; 1200x600x20mm; Omani Marble | 19.53 | m2 | 57 | 0 | 1113.21 | 0 |  | 0 | 0 | 0 | 0
37 | Type EC-03-A; Wall Coping; 1200x600x20mm; Omani marble | 5.69 | m2 | 57 | 0 | 324.33 | 0 |  | 0 | 0 | 0 | 0
38 | Type EC-03-B; Wall Cladding ; 1200x600x20mm; Omani Marble | 48.51 | m2 | 57 | 0 | 2765.07 | 0 |  | 0 | 0 | 0 | 0
39 | Type ST-01-A; Step Tread; 620x20mm; Omani marble | 11 | m | 39.7 | 0 | 436.7 | 0 |  | 0 | 0 | 0 | 0
40 | Type ST-01-B; Step Riser; 150x20mm; Omani marble | 11 | m | 12.5 | 0 | 137.5 | 0 |  | 0 | 0 | 0 | 0
41 | Type SP-26-A; coping; 535x20mm; Omani marble | 14 | m | 36 | 0 | 504 | 0 |  | 0 | 0 | 0 | 0
42 | Type SP-26-B; wall & floor finish; 1200x600x20mm; omani marble | 45.94 | m2 | 57 | 0 | 2618.58 | 0 |  | 0 | 0 | 0 | 0
43 | Type SP-26-D; Step Tread; 600x600x20mm; omani marble | 7.5 | m | 39.7 | 0 | 297.75 | 0 |  | 0 | 0 | 0 | 0
44 | Type SP-26-E; Step Riser; 600x200x20mm; omani marble | 7.5 | m | 12.5 | 0 | 93.75 | 0 |  | 0 | 0 | 0 | 0
45 | Type SP-26-F; Upstand wall finish; 20mm; omani marble | 5.85 | m2 | 57 | 0 | 333.45 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 27 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
46 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 57 | 0 | 611.04 | 10.72 |  | 10.72 | 611.04 | 0 | 611.04
47 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 57 | 0 | 425.676 | 7.47 |  | 7.47 | 425.79 | 0 | 425.79
48 | Type ST-01-A; Step Tread; 660x20mm; Omani marble | 13.32 | m | 39.7 | 0 | 528.804 | 13.32 |  | 13.32 | 528.804 | 0 | 528.804
49 | Type ST-01-B; Step Riser; 170x20mm; Omani marble | 13.32 | m | 12.5 | 0 | 166.5 | 13.32 |  | 13.32 | 166.5 | 0 | 166.5
50 | Type SP-27-A; Rim flow channel coping; 600x20mm; omani marble | 31.56 | m | 36 | 0 | 1136.16 | 31.56 |  | 31.56 | 1136.16 | 0 | 1136.16
51 | Type SP-27-B; Wall & floor finish; 1200x600x20mm; omani marble | 46.48 | m2 | 57 | 0 | 2649.36 | 46.48 |  | 46.48 | 2649.36 | 0 | 2649.36
52 | Type SP-27-D; Step Tread; 600Wx20mm; omani marble | 6.15 | m | 39.7 | 0 | 244.155 | 6.15 |  | 6.15 | 244.155 | 0 | 244.155
53 | Type SP-27-E; Step Riser; 200Htx20mm; omani marble | 8.2 | m | 12.5 | 0 | 102.5 | 8.2 |  | 8.2 | 102.5 | 0 | 102.5
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 29 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
54 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 57 | 0 | 611.04 | 10.72 |  | 10.72 | 611.04 | 0 | 611.04
55 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 57 | 0 | 425.676 | 7.47 |  | 7.47 | 425.79 | 0 | 425.79
56 | Type ST-01-A; Step Tread; 660mmWx20mm; Omani marble | 13.32 | m | 39.7 | 0 | 528.804 | 4.39 |  | 4.39 | 174.283 | 0 | 174.283
57 | Type ST-01-B; Step Riser; 170mmHx20mm; Omani marble | 13.32 | m | 12.5 | 0 | 166.5 | 1.13 |  | 1.13 | 14.125 | 0 | 14.125
58 | Type SP-29-A; Rim flow channel coping; 20mm thick; omani marble | 31.56 | m | 36 | 0 | 1136.16 | 31.56 |  | 31.56 | 1136.16 | 0 | 1136.16
59 | Type SP-29-B; Wall & floor finish; 1200x600x20mm; omani marble | 59.28 | m2 | 57 | 0 | 3378.96 | 59.28 |  | 59.28 | 3378.96 | 0 | 3378.96
60 | Type SP-29-D; Step Tread; 600x400x20mm; omani marble | 6.12 | m | 39.7 | 0 | 242.964 | 6.12 |  | 6.12 | 242.964 | 0 | 242.964
61 | Type SP-29-E; Step Riser; 600x200x20mm; omani marble | 8.16 | m | 12.5 | 0 | 102 | 8.16 |  | 8.16 | 102 | 0 | 102
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 29 RTP | [5 empty] | 0 |  | 0 | 0 | 0 | 0
62 | Type BS-01-C; Wall coping; 600W; Light Grey | 1 | no. | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
63 | Type EC-01-A; wall coping; 200mmWx20mm; Omani marble | 24.7 | m | 14.88 | 0 | 367.536 | 0 |  | 0 | 0 | 0 | 0
64 | Type EC-01-B; wall cladding; 600x300x20mm; Omani marble | 148.44 | m2 | 47 | 0 | 6976.68 | 0 |  | 0 | 0 | 0 | 0
65 | Type ST-01-A; Step Tread; 295mmWx20mm; omani marble | 7.23 | m | 18.2564 | 0 | 131.9941 | 0 |  | 0 | 0 | 0 | 0
66 | Type ST-01-B; Step Riser; 150mmHx20mm omani marble | 7.23 | m | 11.3094 | 0 | 81.767 | 0 |  | 0 | 0 | 0 | 0
67 | Type ST-02-A; Step Tread; 295mmWx20mm; omani marble | 7.94 | m | 18.2564 | 0 | 144.9561 | 0 |  | 0 | 0 | 0 | 0
68 | Type ST-02-B; Step Riser; 150mmHx20mm; omani marble | 11.71 | m | 11.3094 | 0 | 132.4332 | 0 |  | 0 | 0 | 0 | 0
69 | Type ST-02-A; Step landing; 20mm thick; omani marble | 18.95 | m2 | 57 | 0 | 1080.15 | 0 |  | 0 | 0 | 0 | 0
70 | Type ST-02-B; Step Riser; 450mHx20mm omani marble | 17.7 | m | 29.9182 | 0 | 529.5528 | 0 |  | 0 | 0 | 0 | 0
71 | Type ST-06-A; Step tread; 520mmW; omani marble | 45.25 | m | 50.68 | 0 | 2293.27 | 0 |  | 0 | 0 | 0 | 0
72 | Type ST-06-B; Step Riser; 90mmH x 20mm; omani marble | 45.25 | m | 6.7 | 0 | 303.175 | 0 |  | 0 | 0 | 0 | 0
73 | Type SP-29A-A; Pool coping; 200mmW; Light grey omani limestone | 86.3 | m | 14.88 | 0 | 1284.144 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Stone Work | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 17 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
74 | Supply and installation of stoneworks at Level 17 terraces | 545 | m2 | 223 | 148.94 | 202707.3 | 0 |  | 0 | 0 | 0 | 0
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Extraover for Granite | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Ground Floor | [5 empty] | 0 |  | 0 | 0 | 0 | 0
75 | Type HS-01-A; Flush Kerb, 300x130mm, Black Granite | 247.5 | m | 146 | 4 | 37125 | 63 | 24.85 | 87.85 | 9450 | 3727.5 | 13177.5
76 | Type HS-01-C; Upstand Kerb, 200x330mm, Black Granite | 270.8 | m | 209 | 6 | 58222 | 0 |  | 0 | 0 | 0 | 0
77 | Type HS-02-B; Field Pattern, 600x300x80mm, Black Granite | 72.5 | m2 | 265 | 12 | 20082.5 | 0 |  | 0 | 0 | 0 | 0
78 | Type HS-02-C; Banding, 600x300x80mm, Black Granite | 224.3 | m | 81 | 4 | 19065.5 | 67.43 | 88.97 | 156.4 | 5731.55 | 7562.45 | 13294
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
79 | Type HS-02-B; Banding; 600x300x80mm; Basalt | 30.56 | m | 46 | 4 | 1528 | 0 |  | 0 | 0 | 0 | 0
80 | Type HS-04-C; Banding; 600x300x50mm; Basalt | 123.57 | m | 19 | 2 | 2594.97 | 123.57 |  | 123.57 | 2594.97 | 0 | 2594.97
81 | Type HS-04-D; Upstand Kerb; 300x300mm; Basalt | 46.63 | m | 195 | 5 | 9326 | 46.63 |  | 46.63 | 9326 | 0 | 9326
82 | Type HS-06-B; Banding; 200x100x50mm; Basalt | 25.14 | m | 8.78 | 2.22 | 276.54 | 0 |  | 0 | 0 | 0 | 0
83 | WF-02-A; Ledge coping, 1300x900x90-30mm (cut to fit in radius), Basalt | 18.67 | m2 | 533 | 17.5147 | 10278.11 | 18.67 |  | 18.67 | 10278.11 | 0 | 10278.11
84 | WF-02-B; Suspended Floor, 550x1100x20mm, Basalt | 34.15 | m2 | 82 | 5 | 2971.05 | 34.15 |  | 34.15 | 2971.05 | 0 | 2971.05
85 | WF-02-C; External Wall Cladding, 380x300x20mm, Basalt | 8.8218 | m² | 82 | 5 | 767.4966 | 8.82 |  | 8.82 | 767.34 | 0 | 767.34
86 | WF-02-D; Overflow Channel Coping, 300x300x50mm, Black Granite cobble | 24.58 | m | 70 | 7 | 1892.66 | 7.37 |  | 7.37 | 567.49 | 0 | 567.49
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Extraover for Granite Cobbles | [5 empty] | 0 |  | 0 | 0 | 0 | 0
| Ground Floor | [5 empty] | 0 |  | 0 | 0 | 0 | 0
87 | Type HS-02-A; Field Pattern, 100x100x50mm, Granite Cobble | 1574.6 | m2 | 239 | 6 | 385777 | 942 | 475.14 | 1417.14 | 230790 | 116409.3 | 347199.3
88 | Type HS-04-A; Field Pattern, 100x100x50mm, Granite cobble | 144.1 | m2 | 239 | 6 | 35304.5 | 0 | 66.19 | 66.19 | 0 | 16216.55 | 16216.55
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Level 02 | [5 empty] | 0 |  | 0 | 0 | 0 | 0
89 | Type HS-02-A; Field Pattern; 100x100x50mm; Granite cobble | 388.47 | m2 | 239 | 6 | 95175.15 | 0 |  | 0 | 0 | 0 | 0
90 | Type HS-04-A; Driveway Field Pattern; 100x100x50mm; Granite cobble | 708.62 | m2 | 239 | 6 | 173611.9 | 708.62 |  | 708.62 | 173611.9 | 0 | 173611.9
91 | Type HS-04-E; Field Pattern; 100x100x50mm; Granite cobble | 89.02 | m2 | 239 | 6 | 21809.9 | 89.02 |  | 89.02 | 21809.9 | 0 | 21809.9
[7 empty] | 0 |  | 0 | 0 | 0 | 0
| Discount |  |  |  |  | -35584 |  |  |  | -13204.33 | -5815.76 | -19020.09
[10 empty] | 0 |  | 0
| Total Roberts |  |  |  |  | 1203782.1157 |  |  |  | 501359.1345 | 151218.632 | 652577.7665
Note on I5: Himal Kosala: 80% only, no WIR, some of the areas incompleted

## Material OffSite
Item | Description | Qty | Unit | Rate | Amount | Used Qty | Balance Qty | Material Offsite Amount | Current Amount | Cumulative Amount
| Ground Floor | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
1 | Type HS-01-A; Flush Kerb, 300x130mm, Black Granite | 131.7 | m | 269.6 | 35506.32 | 87.85 | 43.85 | 11821.96
2 | Type HS-01-C; Upstand Kerb, 200x330mm, Black Granite | 292 | m | 376 | 109792 | 0 | 292 | 109792
| Type HS-02 | [6 empty] | 0
3 | Type HS-02-A; Field Pattern, 100x100x50mm, Granite Cobble | 1574.6 | m2 | 343.2 | 540402.72 | 1417.14 | 157.46 | 54040.272
4 | Type HS-02-B; Field Pattern, 600x300x80mm, Black Granite | 72.5 | m2 | 530.4 | 38454 | 0 | 72.5 | 38454
5 | Type HS-02-C; Banding, 600x300x80mm, Black Granite | 60.65 | m | 530.4 | 32168.76 | 156.4 | -95.75 | -50785.8
| Type HS-04 | [6 empty] | 0
6 | Type HS-04-A; Field Pattern, 100x100x50mm, Granite cobble | 144.1 | m2 | 343.2 | 49455.12 | 66.119 | 77.981 | 26763.0792
0
| Level 02 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-02 | [6 empty] | 0
7 | Type HS-02-A; Field Pattern; 100x100x50mm; Granite cobble | 388.47 | m2 | 343.2 | 133322.904 | 0 | 388.47 | 133322.904
8 | Type HS-02-B; Banding; 600x300x80mm; Basalt | 30.56 | m | 190.4 | 5818.624 | 0 | 30.56 | 5818.624
| Type HS-04 | [6 empty] | 0
9 | Type HS-04-A; Driveway Field Pattern; 100x100x50mm; Granite cobble | 708.62 | m2 | 343.2 | 243198.384 | 708.62 |  | 0
10 | Type HS-04-B; Brass Inlay; 35x10mm; Solid Brass | [6 empty] | 0
11 | Type HS-04-C; Banding; 600x300x50mm; Basalt | 119.57 | m | 98.4 | 11765.688 | 123.57 | -4 | -393.6
12 | Type HS-04-D; Upstand Kerb; 300x300mm; Basalt | 48 | m | 743.2 | 35673.6 | 46.63 | 1.37 | 1018.184
13 | Type HS-04-E; Field Pattern; 100x100x50mm; Granite cobble | 84.69 | m2 | 343.2 | 29065.608 | 89.02 | -4.33 | -1486.056
| Type HS-06 | [6 empty] | 0
14 | Type HS-06-B; Banding; 200x100x50mm; Basalt | 25.14 | m | 43.376 | 1090.4726 | 0 | 25.14 | 1090.4726
| Water Feature | [6 empty] | 0
15 | WF-02-A; Ledge coping, 1300x900x90-30mm (cut to fit in radius), Basalt | [6 empty] | 0
16 | WF-02-B; Suspended Floor, 550x1100x20mm, Basalt | [6 empty] | 0
17 | WF-02-C; External Wall Cladding, 380x300x20mm, Basalt | [6 empty] | 0
18 | WF-02-D; Overflow Channel Coping, 300x300x50mm, Black Granite cobble | [6 empty] | 0
19 | WF-02-E; Internal Wall & Floor, 300x300x5mm, Ceramic mosaic (fixing only, material to be supplied by Contractor) | [6 empty] | 0
20 | Buzon Pedestal | [6 empty] | 0
0
| Level 04 | [6 empty] | 0
| Paving (Hotel) | [6 empty] | 0
| Type HS-02 | [6 empty] | 0
21 | Type HS-02-A; Ornamental Gravel; 10-30mm; Sandstone | [6 empty] | 0
| Type HS-03 | [6 empty] | 0
22 | Type HS-03-A; Ornamental Gravel; 10-30mm; Sandstone | [6 empty] | 0
| Paving (Resi) | [6 empty] | 0
| Type BS-01 | [6 empty] | 0
23 | Type BS-01-A; Wall Cladding; Sandstone | [6 empty] | 0
24 | Type BS-01-B; Seat Finish; 20mm; Light Grey Omani marble | [6 empty] | 0
| Type BS-02 | [6 empty] | 0
25 | Type BS-02-A; Wall claddding; Sandstone | [6 empty] | 0
26 | Type BS-02-B; Seat Finish; 20mm Ligth Grey Omani Marble | [6 empty] | 0
| Type EC-03 | [6 empty] | 0
27 | Type EC-03-A; Wall Cladding; Sandstone | [6 empty] | 0
| Type EC-10 | [6 empty] | 0
28 | Type EC-10-B; Wall Coping; 200x20mm; Omani Marble | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
29 | SP-04-A; Overflow Coping, 300mmWx20mmm, Omani Limestone |  |  | 176 |  | 71 | -71 | -12496
30 | SP-04-B; Wall FInish, 20mm, Omani Limestone | 95.28 | m2 | 176 | 16769.28 | 95.28 | 0 | 0
31 | SP-04-C; Floor FInish, 20mm, Omani Limestone | 174 | m2 | 176 | 30624 | 174 | 0 | 0
32 | SP-04-D; Step Tread, 420mmWx20mm, Omani Limestone |  |  | 176 |  | 7 | -7 | -1232
33 | SP-04-E; Step Riser, 130mmHx20mm, Omani Limestone |  |  | 176 |  | 8.75 | -8.75 | -1540
34 | SP-04-F; Overflow Pool Wall, 20mm, Omani Limestone | 31.59 | m2 | 176 | 5559.84 | 31.59 | 0 | 0
35 | SP-04-G; Overflow channel coping, Porcelaine Tile (Fixing Only, material to be supplied by Contractor) | [6 empty] | 0
36 | SP-04-H; Overflow channel wall & floor; Omani Limestone | 19.5 | m2 | 176 | 3432 | 19.5 | 0 | 0
| Water Feature | [6 empty] | 0
37 | WF-04B-A; Chef's Table Coping, 13900x1400x20mm, Silestone | [6 empty] | 0
38 | WF-04B-B; Wall & Floor Finish,20mm, Natural Stone | [6 empty] | 0
39 | WF-04B-D; Wall Cladding,20mm, Natural Stone | [6 empty] | 0
40 | WF-04B-E; Water Drain Channel Wall & Floor, 20mm, Natural Stone | [6 empty] | 0
41 | WF-04B-F; Water Drain Channel Top, 20mm, Natural Stone | [6 empty] | 0
42 | WF-04B-C; Stainless Steel Water Channel 225x225x225x3mm as per drawing no. LA-LD-L4-3204 detail 303 | [6 empty] | 0
0
| Level 10 | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
43 | SP-10-A; Overflow Coping, 300mmWx20mmm, Omani Limestone | [6 empty] | 0
44 | SP-10-B; Wall FInish, 20mm, Omani Limestone | 79 | m2 | 176 | 13904 | 0 | 79 | 13904
45 | SP-10-D; Step Tread, 420mmWx20mm, Omani Limestone | [6 empty] | 0
46 | SP-10-E; Step Riser, 130mmHx20mm, Omani Limestone | [6 empty] | 0
47 | SP-10-F; Overflow Pool Wall, 20mm, Omani Limestone | 5.72 | m2 | 176 | 1006.72 | 0 | 5.72 | 1006.72
0
| Level 17 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
48 | Type HS-01-A; Crazy Cut Floor, Bluestone 20mm thick | [6 empty] | 0
49 | Levl 17- 50mm dia Type HS-02-C, River Pebble, Dark Grey, Washed & tumble finish, 50mm dia (rates taken from Al Reem L29) | [6 empty] | 0
0
| Level 24 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
50 | Type HS-01-B; Pool Deck; 1200x600x20mm; Light Grey Omani marble | 10.72 | m2 | 176 | 1886.72 | 10.72 |  | 0
0
| Landscape | [6 empty] | 0
| Type EC-02 | [6 empty] | 0
51 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 7.468 | m2 | 176 | 1314.368 | 7.47 | -0.002 | -0.352
52 | Shadow gap - C type; 20x60x20x10mm | [6 empty] | 0
| Type ST-01 | [6 empty] | 0
53 | Type ST-01-A; Step Tread; 660x20mm; Omani marble |  |  | 176 |  | 13.32 | -13.32 | -2344.32
54 | Type ST-01-B; Step Riser; 170x20mm; Omani marble |  |  | 176 |  | 13.32 | -13.32 | -2344.32
55 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS C channel | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
56 | Type SP-24-A; Rim flow channel sloped coping; 600x20mm; Omani marble |  |  | 176 |  | 31.1 | -31.1 | -5473.6
57 | Type SP-24-B; Wall & Floor finish; 20mm; Omani marble | 51.76 | m2 | 176 | 9109.76 | 51.76 | 0 | 0
58 | Type SP-24-D; Step Tread; 620Wx20mm; Omani marble |  |  | 176 |  | 6.12 | -6.12 | -1077.12
59 | Type SP-24-E; Step Riser; 200Htx20mm; Omani marble |  |  | 176 |  | 8.16 | -8.16 | -1436.16
60 | Type SP-24-F; Overflow channel wall & floor; 25x25x5mm; Ceramic Mosaic tile | [6 empty] | 0
0
| Level 25 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
61 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 16.72 | m2 | 176 | 2942.72 | 16.72 | 0 | 0
| Landscape | [6 empty] | 0
| Type EC-02 | [6 empty] | 0
62 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | 1.41 | m2 | 176 | 248.16 | 7.47 | -6.06 | -1066.56
63 | Shadow gap - C type; 20x60x20x10mm | [6 empty] | 0
| Type ST-01 | [6 empty] | 0
64 | Type ST-01-A; Outdoor Terrace Stair; 600x20mm; Omani marble | [6 empty] | 0
65 | Type ST-01-B; Outdoor Terrace Stair; 170x20mm; Omani marble | [6 empty] | 0
66 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS C channel | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
67 | Type SP-25-A; Rim flow channel coping; 600x20mm; omani marble | [6 empty] | 0
68 | Type SP-25-B; wall & floor finish; 1200x600x20mm; omani marble | 60 | m2 | 176 | 10560 | 60 |  | 0
69 | Type SP-25-D; Step Tread; 600Wx20mm; omani marble | [6 empty] | 0
70 | Type SP-25-E; Step Riser; 200Htx20mm; omani marble | [6 empty] | 0
71 | Type SP-25F; Overflow channel wall & floor; 25x25x5mm ceramic mosaic tile | [6 empty] | 0
0
| Level 26 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
72 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | 21.53 | m2 | 176 | 3789.28 | 25.34 | -3.81 | -670.56
| Landscape | [6 empty] | 0
| Type EC-02 | [6 empty] | 0
73 | Type EC-02-A; Wall Coping; 1200x600x20mm; Omani marble | 3.91 | m2 | 176 | 688.16 | 0 | 3.91 | 688.16
74 | Type EC-02-B; Wall Cladding ; 1200x600x20mm; Omani Marble | 6.95 | m2 | 176 | 1223.2 | 0 | 6.95 | 1223.2
| Type EC-03 | [6 empty] | 0
75 | Type EC-03-A; Wall Coping; 1200x600x20mm; Omani marble | [6 empty] | 0
76 | Type EC-03-B; Wall Cladding ; 1200x600x20mm; Omani Marble | [6 empty] | 0
| Type ST-01 | [6 empty] | 0
77 | Type ST-01-A; Step Tread; 620x20mm; Omani marble | [6 empty] | 0
78 | Type ST-01-B; Step Riser; 150x20mm; Omani marble | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
79 | Type SP-26-A; coping; 535x20mm; Omani marble | [6 empty] | 0
80 | Type SP-26-B; wall & floor finish; 1200x600x20mm; omani marble | [6 empty] | 0
81 | Type SP-26-D; Step Tread; 600x600x20mm; omani marble | [6 empty] | 0
82 | Type SP-26-E; Step Riser; 600x200x20mm; omani marble | [6 empty] | 0
83 | Type SP-26-F; Upstand wall finish; 20mm; omani marble | [6 empty] | 0
0
| Level 27 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
84 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | [6 empty] | 0
| Landscape | [6 empty] | 0
| Type EC-02 | [6 empty] | 0
85 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | [6 empty] | 0
86 | Shadow gap -C Type 20x60x20x10mm | [6 empty] | 0
| Type ST-01 | [6 empty] | 0
87 | Type ST-01-A; Step Tread; 660x20mm; Omani marble | [6 empty] | 0
88 | Type ST-01-B; Step Riser; 170x20mm; Omani marble | [6 empty] | 0
89 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS Cchannel | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
90 | Type SP-27-A; Rim flow channel coping; 600x20mm; omani marble | [6 empty] | 0
91 | Type SP-27-B; Wall & floor finish; 1200x600x20mm; omani marble | [6 empty] | 0
92 | Type SP-27-D; Step Tread; 600Wx20mm; omani marble | [6 empty] | 0
93 | Type SP-27-E; Step Riser; 200Htx20mm; omani marble | [6 empty] | 0
94 | Type SP-27-F; Overflow channel wall & floor; 25x25x5mm; ceramic mosaic tile | [6 empty] | 0
0
| Level 29 | [6 empty] | 0
| Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
95 | Type HS-01-B; Field Pattern; 1200x600x20mm; Light Grey Omani marble | [6 empty] | 0
| Landscape | [6 empty] | 0
| Type EC-02 | [6 empty] | 0
96 | Type EC-02-A; Pool Deck Wall; 1200x600x20mm; Omani marble | [6 empty] | 0
97 | Shadow gap -C Type 20x60x20x10mm | [6 empty] | 0
| Type ST-01 | [6 empty] | 0
98 | Type ST-01-A; Step Tread; 660mmWx20mm; Omani marble | [6 empty] | 0
99 | Type ST-01-B; Step Riser; 170mmHx20mm; Omani marble | [6 empty] | 0
100 | Type ST-01-C; SS U-type bottom support; 20x60x20x5mm; SS Cchannel | [6 empty] | 0
| Swimming Pool | [6 empty] | 0
101 | Type SP-29-A; Rim flow channel coping; 20mm thick; omani marble | [6 empty] | 0
102 | Type SP-29-B; Wall & floor finish; 1200x600x20mm; omani marble | [6 empty] | 0
103 | Type SP-29-D; Step Tread; 600x400x20mm; omani marble | [6 empty] | 0
104 | Type SP-29-E; Step Riser; 600x200x20mm; omani marble | [6 empty] | 0
105 | Type SP-29-F; Overflow channel wall & floor; 25x25x5mm; ceramic mosai tile | [6 empty] | 0
| RTP Paving | [6 empty] | 0
| Type HS-01 | [6 empty] | 0
106 | Type HS-01-A; Field Pattern; 600x300x20mm; Omani marble 1200x600mm | 276.24 | m2 | 176 | 48618.24 | 0 | 276.24 | 48618.24
| Type HS-02 | [6 empty] | 0
107 | Type HS-02-A; Field Pattern; 600x300x20mm; Omani marble 1200x600mm | [6 empty] | 0
| RTP Paving | [6 empty] | 0
| Type BS-01 | [6 empty] | 0
108 | Type BS-01-A; Bar countertop; 635Wx20mm; Calacatta Gold | 30.02 | no. | 1632 | 48992.64 | 0 | 30.02 | 48992.64
109 | Type BS-01-B; Bar counter wall cladding; 20mm thick; Calacatta Gold | 17.33 | m2 | 1632 | 28282.56 | 0 | 17.33 | 28282.56
110 | Type BS-01-C; Wall coping; 600W; Light Grey | [6 empty] | 0
| Type EC-01 | [6 empty] | 0
111 | Type EC-01-A; wall coping; 200mmWx20mm; Omani marble | [6 empty] | 0
112 | Type EC-01-B; wall cladding; 600x300x20mm; Omani marble | [6 empty] | 0
| Type ST-01 | [6 empty] | 0
113 | Type ST-01-A; Step Tread; 295mmWx20mm; omani marble | [6 empty] | 0
114 | Type ST-01-B; Step Riser; 150mmHx20mm omani marble | [6 empty] | 0
| Type ST-02 | [6 empty] | 0
115 | Type ST-02-A; Step Tread; 295mmWx20mm; omani marble | [6 empty] | 0
116 | Type ST-02-B; Step Riser; 150mmHx20mm; omani marble | [6 empty] | 0
117 | Type ST-02-A; Step landing; 20mm thick; omani marble | [6 empty] | 0
118 | Type ST-02-B; Step Riser; 450mHx20mm omani marble | [6 empty] | 0
| Type ST-06 | [6 empty] | 0
119 | Type ST-06-A; Step tread; 520mmW; omani marble | [6 empty] | 0
120 | Type ST-06-B; Step Riser; 90mmH x 20mm; omani marble | [6 empty] | 0
| Type SP-29A | [6 empty] | 0
121 | Type SP-29A-A; Pool coping; 200mmW; Light grey omani limestone | [6 empty] | 0
122 | Type SP-29A-B; Wall finish; 25x25x10mm; Sky blue natural stone mosaic | 453 | m2 | 168 | 76104 | 0 | 453 | 76104
123 | Type SP-29A-C; Floor finish; 25x25x10mm; Sky blue natural stone mosaic | 407 | m2 | 168 | 68376 | 0 | 407 | 68376
124 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 600mmWx10mm | 95.28 | m | 168 | 16007.04 | 0 | 95.28 | 16007.04
125 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 1200mmWx10mm | 35.64 | m | 168 | 5987.52 | 0 | 35.64 | 5987.52
126 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 400mmWx10mm | 8.6 | m | 168 | 1444.8 | 0 | 8.6 | 1444.8
127 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 300mmWx10mm | 1.86 | m | 168 | 312.48 | 0 | 1.86 | 312.48
128 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 450mmWx10mm | 42.75 | m | 168 | 7182 | 0 | 42.75 | 7182
129 | Type SP-29A-D; Pool step tread; 600mmWx10mm; sky blue natural stone mosaic, 1600mmWx10mm | 10.72 | m | 168 | 1800.96 | 0 | 10.72 | 1800.96
130 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 70mm ht x 10mm | 1.33 | m | 168 | 223.44 | 0 | 1.33 | 223.44
131 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 130mm ht x 10mm | 12.35 | m | 168 | 2074.8 | 0 | 12.35 | 2074.8
132 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 200mm ht x 10mm | 4.68 | m | 168 | 786.24 | 0 | 4.68 | 786.24
133 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 370mm ht x 10mm | 25.31 | m | 168 | 4252.08 | 0 | 25.31 | 4252.08
134 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 420mm ht x 10mm | 13.02 | m | 168 | 2187.36 | 0 | 13.02 | 2187.36
135 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 450mm ht x 10mm | 12.51 | m | 168 | 2101.68 | 0 | 12.51 | 2101.68
136 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic ,470mm ht x 10mm | 33.84 | m | 168 | 5685.12 | 0 | 33.84 | 5685.12
137 | Type SP-29A-E; Pool step riser 70mm htx10mm; Sky blue natural stone mosaic, 500mm ht x 10mm | 8.45 | m | 168 | 1419.6 | 0 | 8.45 | 1419.6
138 | Type SP-29A-G; Overflow channel coping; 250mmW x 20mm ; porcelain rakeen (fixing only, material to be supplied by Contractor | [6 empty] | 0
139 | Type SP-29A-H; Decorative pebble; 50mm dia; river stone Excluding Type SP-29A-F - GRP pool Table & Coping Support | [6 empty] | 0
| Variation |  |  |  | 0 |  |  | 0
| Supply and installation of stoneworks at Level 17 terraces | 545 |  | 178.4 | 97228 | 0 | 545 | 97228
| Total |  |  |  | 1787838.9686 |  |  | 735663.6878 | 0 | 0
[8 empty] | -27943.52 |  | 0.41148
707720.1678

## Variation KCE
VO Ref | Description | Qty | Unit | Rate | Amount | Qty |  |  | Amount
[6 empty] | Previous | Current | Cummulative | Previous | Current | Cummulative
ARM-AR-A-VAR-001 | Change in Design of Level 02 Water Feature |  |  |  | 4165.4331 |  |  |  | 4160.8917 | 0 | 4160.8917
| WF-02-A; Ledge coping, 1300x900x90-30mm (cut to fit in radius) including SS support | -18.67 | m2 | 3097.49 | -57830.1383 | -18.67 |  | -18.67 | -57830.1383 | 0 | -57830.1383
| WF-02-B; Suspended Floor, 550x1100x20mm | -34.15 | m2 | 603 | -20592.45 | -34.15 |  | -34.15 | -20592.45 | 0 | -20592.45
| WF-02-C; External Wall Cladding, 380x300x20mm | -8.8218 | m² | 645 | -5690.061 | -8.82 |  | -8.82 | -5688.9 | 0 | -5688.9
| Radial coping 300mmWX30mmT chamfered | 22.4824 | m | 463 | 10409.3512 | 22.48 |  | 22.48 | 10408.24 | 0 | 10408.24
| Radial Flooring 3cmT | 34.1946 | m2 | 1165 | 39836.709 | 34.19 |  | 34.19 | 39831.35 | 0 | 39831.35
| Chiselled Wall 30mmT Black Absoluto | 13.4894 | m² | 1371 | 18494.0222 | 13.49 |  | 13.49 | 18494.79 | 0 | 18494.79
| Stainless steel support at overflow 250x200x5mm flat stainless support | 1 | Set | 19538 | 19538 | 1 |  | 1 | 19538 | 0 | 19538
ARM-AR-A-VAR-008 | Supply and Installation of Omani flooring at Level 04 Pool area |  |  |  | 125306.361 |  |  |  | 67650 | 4510 | 72160
| Supply and installation of Omani flooring 1200x600x20mm at Level 4 Pool Area | 259.011 | m2 | 451 | 116813.961 | 150 | 10 | 160 | 67650 | 4510 | 72160
| Supply and installation of Stair Thread 400mmWx1700mmL ,Omani 2cmT | 25.2 | m | 233 | 5871.6 |  |  | 0 | 0 | 0 | 0
| Supply and installation of Stair Riser 400mmW x 144mmH, ,Omani 2cmT | 28.8 | m | 91 | 2620.8 |  |  | 0 | 0 | 0 | 0
ARS-1201-0922 | Supply and installation of pool overflow channel stone support as per KCE-LX-RFI-PW-000146 |  |  |  | 164783.0952 |  |  |  | 160184.0592 | 0 | 160184.0592
Tender
| Level 04 SP-04-A L-shaped 300x200x100x5mm | -64 | m | 699.06 | -44739.84 | -64 |  | -64 | -44739.84 | 0 | -44739.84
| Level 04 WF-04-B-A L-shaped 300x300x300x5mm | -7.8 | m | 619.74 | -4833.972 |  |  | 0 | 0 | 0 | 0
| Level 24 SS Coping support L-shaped 300x150x100x5mm | -31.1 | m | 491.9 | -15298.09 | -31.1 |  | -31.1 | -15298.09 | 0 | -15298.09
| Level 25 SS Coping support L-shaped 300x150x100x5mm | -31.56 | m | 491.9 | -15524.364 | -31.56 |  | -31.56 | -15524.364 | 0 | -15524.364
| Level 27 SS Coping support L-shaped 300x150x100x5mm | -31.56 | m | 491.9 | -15524.364 | -31.56 |  | -31.56 | -15524.364 | 0 | -15524.364
| Level 29 SS Coping support L-shaped 300x150x100x5mm | -31.56 | m | 491.9 | -15524.364 | -31.56 |  | -31.56 | -15524.364 | 0 | -15524.364
Revised Design 5mm to 10mm
| Level 04 SP-04-A T-shaped 200x550x100x10mm | 64 | m | 2080.45 | 133148.8 | 64 |  | 64 | 133148.8 | 0 | 133148.8
| Level 04 WF-04-B-A L-shaped 200x450x210x10mm | 7.8 | m | 1209.36 | 9433.008 |  |  | 0 | 0 | 0 | 0
| Level 24 SS Coping support Straight shaped 200x450x10mm | 31.1 | m | 1062.54 | 33044.994 | 31.1 |  | 31.1 | 33044.994 | 0 | 33044.994
| Level 25 SS Coping support Straight shaped 200x450x10mm | 31.56 | m | 1062.54 | 33533.7624 | 31.56 |  | 31.56 | 33533.7624 | 0 | 33533.7624
| Level 27 SS Coping support Straight shaped 200x450x10mm | 31.56 | m | 1062.54 | 33533.7624 | 31.56 |  | 31.56 | 33533.7624 | 0 | 33533.7624
| Level 29 SS Coping support Straight shaped 200x450x10mm | 31.56 | m | 1062.54 | 33533.7624 | 31.56 |  | 31.56 | 33533.7624 | 0 | 33533.7624
ARM-AR-A-VAR-009 | Supply and installation of 400mmL plate SS coping support at Level 24,25,27 & 29 as per WIR ref. ARM-AX-WR-L24-00017 Rev 0 |  |  |  | 98788.9305 |  |  |  | 98788.9305 | 0 | 98788.9305
Refer to claim under EI-244
| Suppply and installation of Straight shaped 200mmLx450mmWx10mm at Level 24 Swimming Pool SS coping support | -31.1 | m | 1062.54 | -33044.994 | -31.1 |  | -31.1 | -33044.994 | 0 | -33044.994
| Suppply and installation of Straight shaped 200mmLx450mmWx10mm at Level 25 Swimming Pool SS coping support | -31.56 | m | 1062.54 | -33533.7624 | -31.56 |  | -31.56 | -33533.7624 | 0 | -33533.7624
| Suppply and installation of Straight shaped 200mmLx450mmWx10mm at Level 27 Swimming Pool SS coping support | -31.56 | m | 1062.54 | -33533.7624 | -31.56 |  | -31.56 | -33533.7624 | 0 | -33533.7624
| Suppply and installation of Straight shaped 200mmLx450mmWx10mm at Level 29 Swimming pool SS coping support | -31.56 | m | 1062.54 | -33533.7624 | -31.56 |  | -31.56 | -33533.7624 | 0 | -33533.7624
Revised claim as per EI-447
| Suppply and installation of Straight shaped 400mmLx450mmWx10mm at Level 24 Swimming Pool SS coping support | 31.1 | m | 1847.9505 | 57471.26 | 31.1 |  | 31.1 | 57471.26 | 0 | 57471.26
| Suppply and installation of Straight shaped 400mmLx450mmWx10mm at Level 25 Swimming Pool SS coping support | 31.56 | m | 1847.9505 | 58321.3172 | 31.56 |  | 31.56 | 58321.3172 | 0 | 58321.3172
| Suppply and installation of Straight shaped 400mmLx450mmWx10mm at Level 27 Swimming Pool SS coping support | 31.56 | m | 1847.9505 | 58321.3172 | 31.56 |  | 31.56 | 58321.3172 | 0 | 58321.3172
| Suppply and installation of Straight shaped 400mmLx450mmWx10mm at Level 29 Swimming pool SS coping support | 31.56 |  | 1847.9505 | 58321.3172 | 31.56 |  | 31.56 | 58321.3172 | 0 | 58321.3172
ARM-AR-A-VAR-009 | Supply and installation of additional 10x10x5cm black granite cobbles at LPG Truck Delivery as per KCE-LX-RFI-GF-00332 Rev 00 | 118 | m2 | 635 | 74930 | 118 |  | 118 | 74930 | 0 | 74930
ARM-AR-A-VAR-014 | Demolition of existing floor tiles (White Granix tile 50mm thick) and tile bed due to design changes at GF & Level 2 as per the areas highlighted in the attached sketches | 1395.73 | m2 | 52 | 72577.96 | 1395.73 |  | 1395.73 | 72577.96 | 0 | 72577.96 | 322.22
ARM-AR-A-VAR-015 | Demolition of existing floor tiles (white granix tile 50mm thick) and tile bed at Level 2 | 159.82 | m2 | 52 | 8310.64 | 159.82 |  | 159.82 | 8310.64 | 0 | 8310.64 | 158.1
ARS.1274.1222 | Stoneworks at GF and Level 02 Hardlandscape areas due to design change E11/K114/SK/mv/597 |  |  |  | 1261894.844 |  |  |  | 156800 | 376320 | 533120
| Supply and installation of Omani Beige 600x300x30mm Sandblasted Finish at GF and Level 02 Hardlandscape | 2026 | m2 | 490 | 992740 | 320 | 768 | 1088 | 156800 | 376320 | 533120
| Supply and installation of Omani Straight Stair Tread & Riser 30mm | 96.89 | m2 | 726 | 70342.14 | 0 |  | 0 | 0 | 0 | 0
| Supply and installation of Omani Curved Stair Tread & Riser 30mm | 88.042 | m2 | 862 | 75892.204 | 0 |  | 0 | 0 | 0 | 0
| Supply and installation of Omani Beige coping 30mm |  |  |  | 0 | 0 |  | 0 | 0 | 0 | 0
| ; 150mmWx30mmT | 4.25 | m | 114 | 484.5 | 0 |  | 0 | 0 | 0 | 0
| ; 200mmWx30mmT | 242 | m | 152 | 36784 | 0 |  | 0 | 0 | 0 | 0
| ; 250mmWx30mmT | 92 | m | 190 | 17480 | 0 |  | 0 | 0 | 0 | 0
| ; 300mmWx30mmT | 187 | m | 228 | 42636 | 0 |  | 0 | 0 | 0 | 0
| ; 400mmWx30mmT | 84 | m | 304 | 25536 | 0 |  | 0 | 0 | 0 | 0
| Installation of floor tiles at various locations as per highlighted markup drawing including grouting adhesive, trims, accesories , etc... to complete the works - Balcony areas | 253.31 | m2 |  | 75798.45 |  |  |  | 26597.55 | 45167.115 | 71764.665
| Hotel balcony area (m2) | 329.89 | m2 | 105 | 34638.45 | 253.31 | 76.58 | 329.89 | 26597.55 | 8040.9 | 34638.45
| Residential Swimming pool surround Levels 24,25 & 27 (m2) | 392 | m2 | 105 | 41160 |  | 353.583 | 353.583 | 0 | 37126.215 | 37126.215
| Installation of bespoke kerbstone for hardscape works and work as per WIR ref. ARM-AX-WR-L24-00017 Rev 0 as per EI 445 | 175 | m | 170 | 29750 |  | 157.5 | 157.5 | 0 | 26775 | 26775
| Total |  |  |  | 1886555.7138 |  |  |  | 670000.0314 | 452772.115 | 1122772.1464
Note on J46: Himal Kosala: 80% only grouting not done and WIR not approved
Note on I57: Himal Kosala: 90% until WIR approval
Note on I58: Himal Kosala: 90% until WIR approval

## Hardlandscape Variation
Item | Description | Qty | Unit | Supply Rate | Install Rate | Amount | Material @ Site Rate | Material Qty | Material Balance Qty | Material @ Site Amount | Previous Qty | Current Qty | Cumulative | Previous Amount | Current Amount | Cumulative Amount
Supply and Installation of Hardlandscape Tiling works at Levels GF,2,4,23 & 29RTP
GF | Type-HS-06-A; Field Pattern, 100x300x20mm, Porcelain Black HNT 208 | 233.6 | m2 | 315 | 117 | 100915.2 | 252 | 233.6 | 133.6 | 33667.2 | 100 | 0 | 100 | 43200 | 0 | 43200
GF | Type HS-06-B; Kerb, 200x300x20mm, Porcelain Black HNT 208 | 24.8 | m | 101 | 36 | 3397.6 | 80.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 02 | WF-02-E; Internal Wall & Floor, 300x300x5mm, Ceramic mosaic Ceramic black mosaic | 52.539 | m2 | 248.31 |  | 13045.9591 | 198.648 |  | 0 | 0 | 52.54 | 0 | 52.54 | 13046.2074 | 0 | 13046.2074
Level 04 | Type HS-01-A; Field Pattern; 1200x600x10mm; Porcelain Avorio Strutturato Rettificato | 439.78 | m2 |  | 131 | 57611.18 | 0 |  | 0 | 0 |  | 439.78 | 439.78 | 0 | 57611.18 | 57611.18
Level 04 | Type HS-01-A; Upper & Lower Terrace; 1200x600x10mm; Porcelain Avorio Strutturato Rettificato | 877.542 | m2 |  | 131 | 114958.002 | 0 |  | 0 | 0 | 922.45 | -424.54 | 497.91 | 120840.95 | -55614.74 | 65226.21
Level 04 | Type BS-01-C; Wall coping; 10mm; Porcelain Ivory Coem largos | 5.78 | m2 |  | 220 | 1271.6 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type BS-02-C; Wall Cladding; 10mm; Porcelain Tile Avorio Strutturato Rettificato | 6.68 | m2 |  | 220 | 1469.6 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type EC-03-B; Wall Coping; 10mm; Porcelain Ivory Coem largos | 2.34 | m2 |  | 220 | 514.8 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-01-A; Step Tread; 420x10mm; Porcelain Avorio Strutturato Rettificato | 16.5 | m |  | 102 | 1683 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-01-B; Step Riser; 125x10mm; Porcelain Avorio Strutturato Rettificato | 16.5 | m |  | 42 | 693 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-02-A; Step Tread; 320x10mm; Porcelain Avorio Strutturato Rettificato | 48 | m |  | 78 | 3744 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-02-B; Step Riser; 188x10mm; Porcelain Avorio Strutturato Rettificato | 48 | m |  | 63 | 3024 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-03-A; Step Tread; 430x10mm; Porcelain Avorio Strutturato Rettificato | 2.4 | m |  | 102 | 244.8 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-03-B; Step Riser; 150x10mm; Porcelain Avorio Strutturato Rettificato | 2.4 | m |  | 50 | 120 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-04-A; Step Tread; 420x10mm; Porcelain Avorio Strutturato Rettificato | 70.75 | m |  | 102 | 7216.5 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-04-B; Step Riser; 150x10mm; Porcelain Avorio Strutturato Rettificato | 70.75 | m |  | 50 | 3537.5 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-05-A; Step Tread; 420x10mm; Porcelain Avorio Strutturato Rettificato | 27 | m |  | 102 | 2754 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-05-B; Step Riser; 150x10mm; Porcelain Avorio Strutturato Rettificato | 27 | m |  | 50 | 1350 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-06-A; Step Tread; 420x10mm; Porcelain Avorio Strutturato Rettificato | 6.75 | m |  | 50 | 337.5 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-06-B; Step Riser; 150x10mm; Porcelain Avorio Strutturato Rettificato | 6.75 | m |  | 50 | 337.5 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 04 | Type ST-01A-A; Upper Terrace Stair; 420x10mm; Porcelain Avorio Strutturato Rettificato | 14.44 | m |  | 50 | 722 | 0 |  | 0 | 0 |  | 14.44 | 14.44 | 0 | 722 | 722
Level 04 | Type ST-01A-B; Upper Terrace Stair; 144x10mm; Porcelain Avorio Strutturato Rettificato | 14.44 | m |  | 50 | 722 | 0 |  | 0 | 0 |  | 14.44 | 14.44 | 0 | 722 | 722
Level 04 | Type ST-01B-A; Lower Terrace Stair; 420x10mm; Porcelain Avorio Strutturato Rettificato | 14.44 | m |  | 50 | 722 | 0 |  | 0 | 0 |  | 14.44 | 14.44 | 0 | 722 | 722
Level 04 | Type ST-01B-B; Lower Terrace Stair; 144x10mm; Porcelain Avorio Strutturato Rettificato | 14.44 | m |  | 50 | 722 | 0 |  | 0 | 0 |  | 14.44 | 14.44 | 0 | 722 | 722
Level 04 | SP-04-G; Overflow channel coping, Porcelain Avorio Strutturato Rettificato Rates for supply and install of tile | 39.6 | m2 |  | 178 | 7048.8 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type HS-01-A; Field Pattern; 1200x600x10mm; Porcelain; White; Rakeen Collection |  | m2 |  | 154 | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type HS-01-B; Field Pattern; 1200x600x10mm; Porcelain; White; Rakeen Collection | 155.53 | m2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type BS-02-A; Wall Finish; 1200x600x10mm; Porcelain; White Rakeen Collection | 8.2 | m2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type BS-02-B; Seat Finish; 1200x600x10mm; Porcelain; White Rakeen Collection | 5.86 | m2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type EC-02-A; Top Wall Finish; 1200x600x10mm; Porcelain; White Rakeen Collection | 8.97 | m2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type EC-02-B; Wall Finish; 1200x600x10mm; Porcelain; White Rakeen Collection | 19.96 | m2 |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type ST-01-A; Step Tread; 410x10mm; Porcelain; White Rakeen Collection | 15.07 | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 10 | Type ST-01-B; Step Riser; 150x10mm; Porcelain; White Rakeen Collection | 15.07 | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type HS-01-A; Field Pattern; 1200x600x10mm; Porcelain; White; Rakeen Collection | 717.43 | m2 |  | 131 | 93983.33 | 0 |  | 0 | 0 | 157 | 0 | 157 | 20567 | 0 | 20567
Level 23 | Type BS-01-A; Bench Seat Finish; Ivory 10mm Porcelain | 8.7 | m2 |  | 243 | 2114.1 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type BS-01-B; Seat Finish; Ivory 10mm Porcelain | 9 | m2 |  | 204 | 1836 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type BS-02-A; Wall Finish; Ivory 10mm Porcelain | 8.4 | m2 |  | 256 | 2150.4 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type BS-02-B; Bench Seat Finish; Ivory 10mm Porcelain | 11.48 | m2 |  | 204 | 2341.92 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type BS-03-A; External Wall cladding 1200x600x10mm; Ivory Porcelain | 17.76 | m2 |  | 256 | 4546.56 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type BS-03-B; Bench Seat Finish; Ivory 10mm Porcelain | 13.28 | m2 |  | 206 | 2735.68 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type EC-01-A; Coping 600x400x10mm; Ivory Porcelain | 17.76 | m |  | 88 | 1562.88 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type EC-01-B; Wall cladding 1200x600x10mm; Ivory Porcelain | 47.44 | m2 |  | 148 | 7021.12 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | PVC Plaster Stop (Below Bench Seat), 20x20x3mm | 28 |  | 18.6 | 7.6 | 733.6 | 14.88 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type ST-01-A; Step Tread; 400x10mm; Porcelain; White Rakeen Collection |  | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type ST-01-B; Step Riser; 165x10mm; Porcelain; White Rakeen Collection |  | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type ST-02-A; Step Tread; 200x10mm; Porcelain; White Rakeen Collection |  | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type ST-02-B; Step Riser; 165x10mm; Porcelain; White Rakeen Collection |  | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type ST-03-A; Step Tread; 200x10mm; Porcelain; White Rakeen Collection |  | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Type ST-03-B; Step Riser; 165x10mm; Porcelain; White Rakeen Collection |  | m |  |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23A-A; Coping, 400mmWx10mmm, Ivory | 33.9 | m |  | 88 | 2983.2 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23A-A; Coping, 350mmWx10mmm, Ivory | 12.7 | m |  | 85 | 1079.5 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23A-A; Coping, 200mmWx10mmm, Ivory | 13.5 | m |  | 78 | 1053 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23A-B;Cladding, 1200x600x10mm, Ivory | 68.8 | m2 |  | 148 | 10182.4 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23A-C;Flooring, 1200x600x10mm, Black AQ002 | 41.18 | m2 | 169 | 106 | 11324.5 | 135.2 |  | 0 | 0 | 41.18 | 0 | 41.18 | 11324.5 | 0 | 11324.5
Level 23 | WF-23A-D;External Wall Cladding, 1200x600x10mm, Ivory | 9 | m2 |  | 148 | 1332 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Corner Bead SS 316 Y Style, 35x30x30x2mm | 92.25 | m | 33 | 12 | 4151.25 | 26.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | PVC Plaster Stop (Below Bench Seat), 20x20x3mm | 33.65 | m | 19 | 7 | 874.9 | 15.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23B-A; Coping, 400mmWx10mmm, Ivory | 47.98 | m |  | 88 | 4222.24 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23B-B;Cladding, 1200x600x10mm, Ivory | 70.33 | m2 |  | 148 | 10408.84 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23B-C;Flooring, 1200x600x10mm, Black AQ002 | 50 | m2 | 169 | 106 | 13750 | 135.2 |  | 0 | 0 | 50 | 0 | 50 | 13750 | 0 | 13750
Level 23 | WF-23B-D;External Wall Cladding, 1200x600x10mm, Ivory | 15.33 | m2 |  | 148 | 2268.84 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | Corner Bead SS 316 Y Style, 35x30x30x2mm | 91 | m | 33 | 12 | 4095 | 26.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | PVC Plaster Stop (Below Bench Seat), 20x20x3mm | 33.85 | m | 19 | 7 | 880.1 | 15.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23C-A; Coping, 400mmWx10mmm, Ivory | 67.6 | m |  | 88 | 5948.8 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23C-B;Cladding, 1200x600x10mm, Ivory | 52.24 | m2 |  | 148 | 7731.52 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | WF-23C-C;Flooring, 1200x600x10mm, Black AQ002 | 81 | m2 | 169 | 106 | 22275 | 135.2 |  | 0 | 0 | 81 | 0 | 81 | 22275 | 0 | 22275
Level 23 | Corner Bead SS 316 Y Style, 35x30x30x2mm | 116.5 | m | 33 | 12 | 5242.5 | 26.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 23 | PVC Plaster Stop (Below Bench Seat), 20x20x3mm | 16.6 | m | 19 | 7 | 431.6 | 15.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Level 29 RTP | Type BS-01-D; Interior wall cladding; 5mm thickness; Magnolia from shading bleds 20 - Excluded | 19.68 | m2 | 1540 | 236 | 34951.68 | 1232 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
[6 empty] | 592375.0011 |  |  |  | 33667.2 |  |  |  | 245003.6574 | 4884.44 | 249888.0974
Note on M36: Himal Kosala: No supporting
Note on M52: Himal Kosala: No supporting
Note on M53: Himal Kosala: No supporting
Note on M54: Himal Kosala: No supporting
Note on M55: Himal Kosala: No supporting
Note on M57: Himal Kosala: No supporting
Note on M60: Himal Kosala: No supporting
Note on M61: Himal Kosala: No supporting
Note on M63: Himal Kosala: No supporting
Note on M66: Himal Kosala: No supporting
Note on M67: Himal Kosala: No supporting

## AHK Balance
Item | Description | Qty | Unit | Supply Rate | Install Rate | Amount | Material @ Site Rate | Material Qty | Material Balance Qty | Material @ Site Amount | Previous Qty | Current Qty | Cumulative | Previous Amount | Current Amount | Cumulative Amount
Stoneworks in Ballroom, Royal, Presidential Suit, Gym, Prayer Room, Lobbies (AHK Balance) | [11 empty] | 0 |  | 0 | 0 | 0
PACKAGE -3 - ROYAL SUITE FIT-OUT
FLOOR FINISHES - RIGHT WING
Stone Works
Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications.
Supply and fixing of Stone flooring; Type HTL-ST-50, Crystal White, Honed + Wet Floor Treatment
A | Secondary Bathroom | 9.23 | m2 | 450 | 200 | 5999.5 | 360 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
B | Vestibule | 0.27 | m2 | 450 | 200 | 175.5 | 360 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone flooring with Herringbone pattern; Type HTL-ST-52
C | Secondary Bathroom - Light Travertine | 7.655 | m2 | 357 | 216 | 4386.315 | 285.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone border/flooring with Herringbone pattern; Type HTL-ST-47, Arabescato Marble, Honed + Wet Floor Treatment
D | Vestibules, Secondary Bedroom | 9.87 | m2 | 851 | 219 | 10560.9 | 680.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Threshold
E | Supply and fixing of Stone Threshold, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications.
1 | 175mm wide; Type ST-47,Arabescato Marble, Honed | 0.75 | m | 153 | 45 | 148.5 | 122.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2 | 180mm wide; Type ST-47,Arabescato Marble, Honed | 0.815 | m | 157 | 45 | 164.63 | 125.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
3 | 200mm wide; Type ST-47,Arabescato Marble, Honed | 0.9 | m | 173 | 46 | 197.1 | 138.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
4 | 285mm wide; Type ST-47,Arabescato Marble, Honed | 0.75 | m | 241 | 57 | 223.5 | 192.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Metal Works
Floor Joint/Metal Trim
Metal Trim laid on cement and sand screed including all backing support fixing, movement joints,polishing, decoration, adhesive etc and the like all in accordance with drawings and specifications.
B | Metal Trim divider of Type HTL-ME-01 | 46.135 | m | 208 | 21 | 10564.915 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
FLOOR FINISHES - LEFT WING
Stone Works
Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications.
Supply and fixing of Stone flooring; Type HTL-ST-01, Crystal White, Polished
A | Pantry | 3.42 | m2 | 450 | 200 | 2223 | 360 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone border; Type HTL-ST-10, Saint Laurent Marble, Polished, 85mm wide
B | Powder Room | 6 | m | 29 | 29 | 348 | 23.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone flooring with Herringbone pattern; Type HTL-ST-21, Viola Marble, Polished
C | Living Room & Corridor | 13.79 | m2 | 1448 | 278 | 23801.54 | 1158.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone flooring/border; Type HTL-ST-21, Viola Marble, Polished
D | Master Bathroom, Master Suite Corridor, Dressing 1 & Entry Vestibule | 21.25 | m2 | 1502 | 268 | 37612.5 | 1201.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone flooring/border; Type HTL-ST-22, Taj Mahal Quartzite, Honed + Water Treatment
E | Master Bedroom | 9.86 | m2 | 407 | 212 | 6103.34 | 325.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone flooring with Herringbone pattern; Type HTL-ST-50, Crystal White, Honed + Wet Floor Treatment
F | Master Bathroom | 6.102 | m2 | 440 | 219 | 4021.218 | 352 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
G | Powder Room | 1.59 | m2 | 440 | 219 | 1047.81 | 352 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone flooring with Herringbone pattern; Type HTL-ST-51, Crystal White, Honed
H | Entry Vestibule | 2.19 | m2 | 1057 | 237 | 2833.86 | 845.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Threshold
E | Supply and fixing of Stone Threshold, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications.
1 | 150mm wide; Type ST-01, Crystal White, Polished | 0.9 | m | 76 | 40 | 104.4 | 60.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2 | 200mm wide; Type ST-10, Saint Laurent Marble, Polished | 0.81 | m | 74 | 40 | 92.34 | 59.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
3 | 110mm wide; Type ST-21, Viola Marble, Polished | 0.9 | m | 170 | 42 | 190.8 | 136 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
4 | 160mm wide; Type ST-21, Viola Marble, Polished | 3.561 | m | 241 | 45 | 1018.446 | 192.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
5 | 190mm wide; Type ST-21, Viola Marble, Polished | 2.06 | m | 284 | 47 | 681.86 | 227.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
6 | 220mm wide; Type ST-21, Viola Marble, Polished | 1.205 | m | 326 | 48 | 450.67 | 260.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
7 | 230mm wide; Type ST-21, Viola Marble, Polished | 0.9 | m | 340 | 48 | 349.2 | 272 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
8 | 235mm wide; Type ST-21, Viola Marble, Polished | 1.25 | m | 348 | 48 | 495 | 278.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
9 | 240mm wide; Type ST-21, Viola Marble, Polished | 1.25 | m | 355 | 49 | 505 | 284 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
10 | 250mm wide; Type ST-21, Viola Marble, Polished | 0.9 | m | 372 | 49 | 378.9 | 297.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
11 | 270mm wide; Type ST-21, Viola Marble, Polished | 0.9 | m | 400 | 53 | 407.7 | 320 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
12 | 435mm wide; Type ST-21, Viola Marble, Polished | 1.29 | m | 637 | 74 | 917.19 | 509.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Metal Works
Floor Joint/Metal Trim
Metal Trim laid on cement and sand screed including all backing support fixing, movement joints,polishing, decoration, adhesive etc and the like all in accordance with drawings and specifications.
A | Metal Trim divider of Type HTL-ME-01 | 110.06 | m | 208 | 21 | 25203.74 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
WALL FINISHES - RIGHT WING
Stone Works
Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche etc and the like all in accordance with drawings and specifications.
Supply and fixing of Stone Wall Cladding; Type HTL-ST-37
A | Secondary Bathroom | 32.9 | m2 | 426 | 191 | 20299.3 | 340.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone Wall Cladding; Type HTL-ST-51
B | Secondary Bathroom | 12.05 | m2 | 462 | 185 | 7796.35 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
C | Secondary Bedroom | 2.33 | m2 | 462 | 185 | 1507.51 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Wall Finishes including all necessary framing, fitting, fixing, backing framing support, decoration, etc and the like all in accordance with drawings and specifications.
E | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-22 |  | m2
F | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-24 |  | m2
G | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-29 |  | m2
| Supply and fixing of Wall Panel System including the finishes type; HTL-WC-23 |  | m2
Skirting
Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing, polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications.
H | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-47; 150mm high | 27.55 | m | 141 | 26 | 4600.85 | 112.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
WALL FINISHES - LEFT WING
Stone Works
Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche etc and the like all in accordance with drawings and specifications.
Supply and fixing of Stone Wall Cladding; Type HTL-ST-01, Crystal White, Polished
A | Living Room | 12.18 | m2 | 462 | 223 | 8343.3 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone Wall Cladding; Type HTL-ST-10, Saint Laurent Marble, Polished
B | Powder Room | 10.23 | m2 | 365 | 182 | 5595.81 | 292 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone Wall Cladding; Type HTL-ST-21, Viola Marble, Polished
C | Master Bathroom | 26.73 | m2 | 1582 | 219 | 48140.73 | 1265.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone Wall Cladding; Type HTL-ST-23, Taj Mahal Quartzite, Polished
D | Master Bedroom | 14.75 | m2 | 420 | 230 | 9587.5 | 336 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
Supply and fixing of Stone Wall Cladding; Type HTL-ST-51, Crystal White, Honed
E | Dining Room | 1.53 | m2 | 462 | 223 | 1048.05 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
F | Master Bathroom | 4.4 | m2 | 462 | 223 | 3014 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
G | Supply and fixing of Stone Pilaster; Type Frame HTL-ST-51;
1 | 130 x 2500mm high |  | nos.
2 | 170 x 2650mm high @ dining room as per elev. PP2 | 1 | nos. | 270 | 131 | 401 | 216 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
3 | 300 x 2500mm high |  | nos.
4 | 310 x 2500 2650mm high @ dining room as per elev. 002 | 2 | nos. | 435 | 237 | 1344 | 348 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
5 | 400 x 2500 2650mm high @ corridor as per elev. ZZ1 & XX1 | 4 | nos. | 612 | 301 | 3652 | 489.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
6 | 575 x 2500mm high |  | nos.
7 | 310 x 6350mm high @ living room as per elev SS2 & RR2 | 5 | nos. | 1043 | 567 | 8050 | 834.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
8 | 565 x 6350mm high |  | nos.
9 | (375+80) x 6350mm high @ living room as per elev. RR 2 | 2 | nos. | 1466 | 836 | 4604 | 1172.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
H | Supply and fixing of Stone Trim / Door Frame; Type HTL-ST-51; Crystal White, Honed |  | nos.
1 | 145 x 1290mm long |  | nos.
2 | 220 x 1250mm long |  | nos.
3 | 425 x 2330mm high |  | nos.
4 | 220 x 2650mm high @ Master Suite Corridor as per elev TT1 & VV1 | 2 | nos. | 411 | 180 | 1182 | 328.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
5 | 390 x 2650mm high |  | nos.
| Wall Finishes including all necessary framing, fitting, fixing, backing framing support, decoration, etc and the like all in accordance with drawings and specifications. |  | nos.
| Supply and fixing of Wall Panel System including the finishes type; HTL-WC-24 |  | nos.
C | Dining Room |  | nos.
| Supply and fixing of Wall Panel System including the finishes type; HTL-WC-25 |  | nos.
D | Master Bedroom |  | nos.
E | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-26 |  | nos.
1 | Dressing 1 |  | nos.
2 | Valet Box 1 |  | nos.
3 | Master Suite Corridor |  | nos.
| Supply and fixing of Wall Panel System including the finishes type; HTL-WC-27 |  | nos.
F | Living Room |  | nos.
| Skirting |  | nos.
C | Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing, polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications. |  | nos.
1 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-10; Saint Laurent Marble, 150mm high | 6.21 | m | 46 | 23 | 428.49 | 36.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-21; Viola Marble, 150mm high | 22.04 | m | 129 | 25 | 3394.16 | 103.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
3 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-23; Taj Mahal Quartzite, 150mm high | 15.429 | m | 75 | 25 | 1542.9 | 60 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
4 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-51; Crystal White, 150mm high | 24.97 | m | 52 | 23 | 1872.75 | 41.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
ADDITIONAL ITEMS
1 | Supply & fixing of stone wall cladding; type HTL-ST-51, Crystal White Honed
| A. Living Room | 31.04 | m2 | 462 | 223 | 21262.4 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
| B. Corridor | 1.34 | m2 | 462 | 223 | 917.9 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
| C. Entry Vestibule | 0.69 | m2 | 462 | 223 | 472.65 | 369.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2 | Supply & fixing of stone door frame Type HTL-ST-51 at Master Suit corridor as per drawing no. RS-2608-307 | 1 | nos. | 1107 | 578 | 1685 | 885.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
3 | Supply & fixing of stone pilaster; type frame HTL-ST-51
| A. 375x2650mm @ corridor as per elev ZZ1 & XX1 | 4 | nos. | 596 | 289 | 3540 | 476.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
| B. 200x2325mm @ master bathroom as per elev. KK1 & II1 | 6 | nos. | 279 | 135 | 2484 | 223.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
| C. 221x2325 @ master bathroom as per elev. II1 | 1 | nos. | 308 | 149 | 457 | 246.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
| D. 177 x 2325 @ master bathroom as per elev. II1 | 1 | nos. | 247 | 120 | 367 | 197.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
4 | Additional supply & fix of metal support for stone pilaster, baseboard & door frame. |  | L/S |  |  | 73458.9 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT
FLOOR FINISHES - RIGHT WING
Stone Works
Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications.
A | Supply and fixing of Stone flooring; Type HTL-ST-01, Crystal White, Polished
1 | Pantry | 6.33 | m2 | 450 | 200 | 4114.5 | 360 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
B | Supply and fixing of Stone flooring with Chevron pattern; Type HTL-ST-21, Viola Marble, Polished
1 | Twin Bathroom | 7.11 | m2 | 1509 | 251 | 12513.6 | 1207.2 |  | 0 | 0 |  | 5.688 | 5.688 | 0 | 10010.88 | 10010.88 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Stone flooring Type HTL-ST-21, Viola Marble, Polished
1 | Twin Bathroom | 4.02 | m2 | 1563 | 278 | 7400.82 | 1250.4 |  | 0 | 0 |  | 3.216 | 3.216 | 0 | 5920.656 | 5920.656 | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone flooring Type HTL-ST-37, Calacatta Paonazzo
1 | Open Kitchen | 6.7 | m2 | 405 | 215 | 4154 | 324 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
2 | Vanity | 2.29 | m2 | 405 | 215 | 1419.8 | 324 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
E | Supply and fixing of Stone flooring Type HTL-ST-48, Pinta Verde, Honed + Wet Floor Treatment
1 | Twin Bedroom | 3.25 | m2 | 324 | 210 | 1735.5 | 259.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0
F | Supply and fixing of Stone border/flooring Type HTL-ST-50, Crystal White, Honed + Wet Floor Treatment
1 | Twin Bathroom | 5.81 | m2 | 450 | 200 | 3776.5 | 360 |  | 0 | 0 |  | 4.648 | 4.648 | 0 | 3021.2 | 3021.2 | 80% only until WIR approval, and balance work completion
| Threshold & Borders | [15 empty] | 80% only until WIR approval, and balance work completion
G | Supply and fixing of Stone Threshold & Borders, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 165mm wide; Type ST-37 Threshold | 1.16 | m | 74 | 45 | 138.04 | 59.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | 200mm wide; Type ST-37 Threshold | 0.9 | m | 90 | 47 | 123.3 | 72 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | 315 345mm wide; Type ST-37 Threshold (as per detail shown in drawing no. 1902-132) | 1.16 | m | 155 | 54 | 242.44 | 124 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | 330mm wide; Type ST-37 Threshold | 2.32 | m | 148 | 44 | 445.44 | 118.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
5 | 255mm wide; Type ST-50 Threshold | 0.915 | m | 127 | 42 | 154.635 | 101.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
6 | 260 265mm wide; Type ST-50 Threshold (as per detail shown in drawing no. 1902-132) | 0.915 | m | 132 | 44 | 161.04 | 105.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
7 | 250mm wide; Type ST-48 Border | 22.7 | m | 85 | 47 | 2996.4 | 68 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
8 | 330mm wide; Type ST-48 Border | 7.48 | m | 112 | 51 | 1219.24 | 89.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
9 | 350mm wide; Type ST-48 Border | 5.44 | m | 119 | 51 | 924.8 | 95.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
10 | 200mm wide; Type ST-50 Border | 7.81 | m | 92 | 36 | 999.68 | 73.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Metal Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Floor Joint/Metal Trim | [15 empty] | 80% only until WIR approval, and balance work completion
E | Metal Trim laid on cement and sand screed including all backing support fixing, movement joints,polishing, decoration, adhesive etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Metal Trim divider of Type HTL-ME-04; Brass, Brushed-matte vernish | 62.05 | m | 208 | 21 | 14209.45 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| FLOOR FINISHES - LEFT WING | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone flooring Type HTL-ST-21, Viola Marble, Polished | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Powder Room | 2.2 | m2 | 1516 | 269 | 3927 | 1212.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone flooring with Chevron pattern; Type HTL-ST-35, Arabescato Marble, Acid Wash | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Master Bathroom | 6.17 | m2 | 937 | 234 | 7225.07 | 749.6 |  | 0 | 0 |  | 4.936 | 4.936 | 0 | 5780.056 | 5780.056 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Stone flooring Type HTL-ST-35, Arabescato Marble, Acid Wash | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Master Bathroom | 3.26 | m2 | 903 | 220 | 3660.98 | 722.4 |  | 0 | 0 |  | 15.856 | 15.856 | 0 | 17806.288 | 17806.288 | 80% only until WIR approval, and balance work completion
2 | Master Bedroom | 19.82 | m2 | 903 | 220 | 22257.86 | 722.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone flooring; Type HTL-ST-37, Calacatta Paonazzo | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Living Room, Corridor, Entry Vestibule | 24.93 | m2 | 406 | 214 | 15456.6 | 324.8 |  | 0 | 0 |  | 9.972 | 9.972 | 0 | 6182.64 | 6182.64 | 80% only until WIR approval, and balance work completion
E | Supply and fixing of Stone flooring/border; Type HTL-ST-50, Crystal White, Honed + Water Treatment | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Master Bathroom | 4.83 | m2 | 450 | 204 | 3158.82 | 360 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Threshold & Borders | [15 empty] | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone Threshold & Border, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 225mm wide; Type ST-37 Threshold | 1.16 | m | 96 | 45 | 163.56 | 76.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | 315mm wide; Type ST-37 Threshold | 1.16 | m | 135 | 62 | 228.52 | 108 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | 520mm wide; Type ST-37 Threshold | 1.16 | m | 223 | 103 | 378.16 | 178.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | 125mm wide; Type ST-37 Threshold | 0.88 | m | 54 | 43 | 85.36 | 43.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
5 | 155mm wide; Type ST-37 Threshold | 0.56 | m | 66 | 45 | 62.16 | 52.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
6 | 175mm wide; Type ST-37 Threshold | 0.82 | m | 75 | 46 | 99.22 | 60 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
7 | 190mm wide; Type ST-37 Threshold | 0.82 | m | 81 | 46 | 104.14 | 64.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
8 | 175mm wide; Type ST-01 Border | 11.22 | m | 74 | 30 | 1166.88 | 59.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
9 | 350mm wide; Type ST-35 Border | 4.29 | m | 298 | 56 | 1518.66 | 238.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
10 | 240mm wide; Type ST-50 Border | 4.27 | m | 104 | 34 | 589.26 | 83.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
11 | 200mm wide; Type WD-02 Border |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
12 | 100mm wide; Type WD-06 Border |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
13 | 200mm wide; Type WD-06 Border |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
14 | 260mm wide; Type WD-06 Border |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
15 | 265mm wide; Type WD-06 Border |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
16 | 325mm wide; Type WD-06 Border |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
17 | 90mm wide; Type WD-06 Threshold |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Metal Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Floor Joint/Metal Trim | [15 empty] | 80% only until WIR approval, and balance work completion
A | Metal Trim laid on cement and sand screed including all backing support fixing, movement joints,polishing, decoration, adhesive etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Metal Trim divider of Type HTL-ME-04; Brass, Brushed-matte vernish (qty indicated is only items related to stone works) | 76.28 | m | 208 | 21 | 17468.12 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| WALL FINISHES - RIGHT WING | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche if any, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone Wall Cladding; Type HTL-ST-37, Calacatta Paonazzo | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Corridor, Dining Room, Media Room, Twin Bathroom | 65.28 | m2 | 441 | 230 | 43802.88 | 352.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone Wainscotting, 1300mm high; Type HTL-ST-37, Calacatta Paonazzo, Twin Bathroom | 8.733 | m2 | 460 | 192 | 5693.916 | 368 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Stone Wall Cladding; Type HTL-ST-48, Pinta Verde, Honed + Wet Floor Treatment, Twin Bedroom | 6.75 | m2 | 355 | 228 | 3935.25 | 284 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone Wainscotting, 300mm high; Type HTL-ST-48, Pinta Verde, Honed + Wet Floor Treatment, Twin Bedroom | 2.91 | m2 | 368 | 228 | 1734.36 | 294.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Wall Finishes including all necessary framing, fitting, fixing, backing framing support, decoration, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
G | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-22 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Skirting | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing, polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone Skirting; Type Removable Baseboard HTL-ST-16; 150mm high | 5.99 | m | 66 | 24 | 539.1 | 52.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-37; 150mm high | 47.61 | m | 68 | 25 | 4427.73 | 54.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Stone Trim/Stone Door Frame/Architrave; Type HTL-ST-37; Calacatta Paonazzo | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Pantry - (2.40+0.975+2.40) - 195mm wide | 2 | nos. | 817 | 370 | 2374 | 653.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Vanity - (2.40+1.26+2.40) - 220mm wide | 1 | nos. | 936 | 434 | 1370 | 748.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Twin Bedroom - (2.40+1.26+2.40) - 225mm wide | 1 | nos. | 992 | 464 | 1456 | 793.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | Corridor - (2.40+1.26+2.40) - 370mm wide | 2 | nos. | 1435 | 710 | 4290 | 1148 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
5 | Vestibule - (2.40+1.26+2.40) - 385mm wide | 1 | nos. | 1490 | 740 | 2230 | 1192 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone Trim / Stone Door Frame/Architrave; Type HTL-ST-51; Crystal White, Honed | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Dressing Room 2 - (2.40+0.975+2.40) - 265mm wide | 1 | nos. | 1359 | 488 | 1847 | 1087.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Twin Bathroom - (2.40+0.975+2.40) - 250mm wide | 1 | nos. | 1273 | 443 | 1716 | 1018.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| WALL FINISHES - LEFT WING | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and fixing of Stone Wainscotting; Type HTL-ST-21, Viola Marble, Polished, 1050mm high | [15 empty] | 80% only until WIR approval, and balance work completion
A | Powder Room | 9.24 | m2 | 1595 | 219 | 16761.36 | 1276 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Supply and fixing of Stone Wall Cladding; Type HTL-ST-35, Arabescato Marble, Acid Wash | [15 empty] | 80% only until WIR approval, and balance work completion
B | Master Bathroom | 30.47 | m2 | 916 | 199 | 33974.05 | 732.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Stone Wainscotting; Type HTL-ST-35, Arabescato Marble, Acid Wash | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 300mm high, Master Bedroom | 2.65 | m2 | 916 | 237 | 3055.45 | 732.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | 1300mm high, Master Bathroom | 6.686 | m2 | 916 | 237 | 7708.958 | 732.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone Wall Cladding; Type HTL-ST-37, Calacatta Paonazzo | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Living Room, Corridor, Study, Entry Vestibule | 23.8 | m2 | 441 | 230 | 15969.8 | 352.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
F | Wall Finishes including all necessary framing, fitting, fixing, backing framing support, decoration, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-32 |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
2 | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-22 |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
3 | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-23 |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
4 | Supply and fixing of Wall Panel System including the finishes type; HTL-WC-31 |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
| Skirting |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
A | Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing, polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications. |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
1 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-21; 150mm high | 8.85 | m | 123 | 25 | 1309.8 | 98.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-35; 150mm high | 31.86 | m | 77 | 24 | 3217.86 | 61.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Supply and fixing of Stone Skirting; Type Baseboard HTL-ST-37; 150mm high | 29.59 | m | 68 | 25 | 2751.87 | 54.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone Trim/Stone Door Frame/Architrave; Type HTL-ST-37; Calacatta Paonazzo | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Valet Box - (2.40+0.975+2.40) - 200mm wide | 1 | nos. | 1429 | 388 | 1817 | 1143.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Valet Box - (2.40+0.975+2.40) - 200mm wide | 1 | nos. | 1429 | 388 | 1817 | 1143.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Master Bathroom - (2.40+0.950+2.40) - 250mm wide | 1 | nos. | 1560 | 467 | 2027 | 1248 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | Dressing Room 1 - (2.40+0.950+2.40) - 260mm wide | 1 | nos. | 1588 | 482 | 2070 | 1270.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
5 | Master Bedroom - (2.40+1.26+2.40) - 280mm wide | 1 | nos. | 1745 | 545 | 2290 | 1396 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
6 | Corridor - (2.40+1.26+2.40) - 560mm wide | 1 | nos. | 2686 | 1066 | 3752 | 2148.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Metal Trim/Metal Door Frame-Architrave; Type HTL-WD-19; US Walnut, Satin Brushed | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Entry Vestibule - (2.40+1.425+2.40) - 220mm wide | [15 empty] | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
| RIGHT WING - FLOOR FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fix of stone threshold as per detail shown in drawing no. 1902-132. | [15 empty] | 80% only until WIR approval, and balance work completion
| Vestibule | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 180mm wide; Type HTL-ST-37 | 1.16 | m2 | 85 | 46 | 151.96 | 68 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Twin Bathroom | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 180mm wide; Type HTL-ST-50 | 2.64 | m2 | 81 | 29 | 290.4 | 64.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| RIGHT WING - WALL FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
B | Supply and fix of stone wall cladding; Type HTL-ST-16 as per detail shown in drawing no. 1902-210 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Pantry | 5.48 | m2 | 440 | 212 | 3572.96 | 352 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Open Kitchen | 2.41 | m2 | 440 | 212 | 1571.32 | 352 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Supply and fix of stone skirting; Type baseboad HTL-ST-48; 150mm high as per detail shown in drawing no. 1902-215 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Twin bedroom | 10.22 | m | 80 | 25 | 1073.1 | 64 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Supply and fix of stone dado; Type HTL-ST-37; 35mm width as per detail shown in drawing no. 1902-210 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Twin bathroom | 6.78 | m | 60 | 30 | 610.2 | 48 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
E | Supply & fix of stone trim/stone door frame/architrave; Type HTL-ST-37 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Open kitchen (2.43+2.715+2.43)-290mm wide; as detailed shown on dwg no. 1902-346, Det. 01 | 1 | nos. | 4694 | 634 | 5328 | 3755.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Dining Room (2.43+2.715+2.43)-290mm wide; as detailed shown on dwg no. 1902-346, Det. 01 | 1 | nos. | 4694 | 634 | 5328 | 3755.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Media Room (2.43+2.715+2.43)-290mm wide; as detailed shown on dwg no. 1902-346, Det. 01 | 1 | nos. | 4694 | 634 | 5328 | 3755.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | Dressing Room (2.43+0.975+2.43)-265mm; as detailed shown on dwg no. 1902-344, Det. 01. | 1 | nos. | 3169 | 433 | 3602 | 2535.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| LEFT WING - WALL FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply & fix of stone bulkhead cladding; Type HTL-ST-35 as per detail shown in drawing no. 1902-201 & 1902-302 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Masterbathroom | 2.34 | m2 | 916 | 237 | 2698.02 | 732.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Supply & fix of stone dado; Type HTL-ST-37; 35mm | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Master bathroom (as per drawing no. 1902-205) | 5.16 | m | 80 | 34 | 588.24 | 64 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Powder Room (as per drawingno. .1902-207) | 8.85 | m | 80 | 34 | 1008.9 | 64 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Supply & fix of stone trim/stone door frame/architrave; Type HTL-ST-37 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Corridor (2.43+2.245+2.43)-260mm wide; as detailed shown on Dwg. No. 1902-350, Det. 01 | 2 | nos. | 4694 | 634 | 10656 | 3755.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Corridor (2.43+2.375+2.43)-260mm wide; as detailed shown on Dwg. No. 1902-350, Det. 01 | 1 | nos. | 4694 | 634 | 5328 | 3755.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Corridor (2.43+2.230+2.43)-26mm wide; as detailed shown on Dwg. No. 1902-350; Det. 01 | 1 | nos. | 4694 | 634 | 5328 | 3755.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | Corridor (2.43+1.16+2.43)-370mm wide; as detailed shown on Dwg. No. 1902-342, Det. 01 | 1 | nos. | 4907 | 739 | 5646 | 3925.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| ADDITIONAL METAL SUPPORT | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Additional supply & fix of metal support for stone pilaster, baseboard & door frame. |  | L/S |  |  | 82621.8 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
PACKAGE -4 - HOTEL - GYM - L28 | [16 empty] | 80% only until WIR approval, and balance work completion
| STONE WORKS (WALLS AND FLOORS) | [15 empty] | 80% only until WIR approval, and balance work completion
| Wall Finishes | [15 empty] | 80% only until WIR approval, and balance work completion
B | Wall baseboard : Taj Mahal Quartzite polished stone type HTL-ST-23, 200mm high | 33 | m | 241 | 35 | 9108 | 192.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Piller baseboard :Taj Mahal Quartzite polished stone type HTL-ST-23, 200mm high | 8.31 | m | 241 | 35 | 2293.56 | 192.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Stone To Doors | [15 empty] | 80% only until WIR approval, and balance work completion
| ADDITIONAL WORKS | [15 empty] | 80% only until WIR approval, and balance work completion
| The tenderer is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the tendered fail to insert any items hereunder, it will be deemed that his lump sum price for the tender includes all works as required by the tender drawings and specification and no subsequent claim for any additional item will be entertained. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Stone; threshold (assume type HTL-ST-25) 150mm width, refer to RFI 008 response of client | 1.5 | m | 215 | 45 | 390 | 172 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Supply and installation architrave Calacatta Vagli Marble type in HTL-ST-25 total size of 240mm by 2700mm H x 1000mm, refer to RFI 008 response of client | 1 | Item | 2582 | 443 | 3025 | 2065.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
| DISABLED TOILET | [15 empty] | 80% only until WIR approval, and balance work completion
C | Stone Floor: Type HTL-ST-08 as detail shown in drawing no. AHK-ID-SD-L28-01431 | 5.33 | m2 | 459 | 210 | 3565.77 | 367.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Stone Wall Cladding: Type-HTL-ST-27 as detail shown in drawing no. AHK-ID-SD-L28-01446 | 18 | m2 | 485 | 195 | 12240 | 388 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
E | Stone Skirting: Type-HTL-ST-07 as detail shown in drawing no. AHK-ID-SD-L28-01446 | 8.72 | m | 43 | 23 | 575.52 | 34.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
F | Stone Dado: Type-HTL-ST-07 as detail shown in drawing no. AHK-ID-SD-L28-01446 | 8.72 | m | 50 | 22 | 627.84 | 40 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
PACKAGE -4 - HOTEL LEVEL 01:- PRAYER ROOM & ABLUTION | [16 empty] | 80% only until WIR approval, and balance work completion
| FLOOR FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone flooring; Type HTL-ST-08, "Pierre de Bourgogne" or travertin, Anti-gliss Treatment | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Ablution | 8.78 | m2 | 455 | 200 | 5750.9 | 364 |  | 0 | 0 | 8.78 | 0 | 8.78 | 5750.9 | 0 | 5750.9 | 80% only until WIR approval, and balance work completion
2 | Female Ablution | 10.55 | m2 | 455 | 200 | 6910.25 | 364 |  | 0 | 0 | 10.55 | 0 | 10.55 | 6910.25 | 0 | 6910.25 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone Seating; Type HTL-ST-16, Volakas Marble, Honed | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Ablution | 1.63 | m2 | 516 | 183 | 1139.37 | 412.8 |  | 0 | 0 | 1.63 | 0 | 1.63 | 1139.37 | 0 | 1139.37 | 80% only until WIR approval, and balance work completion
2 | Female Ablution | 1.09 | m2 | 516 | 183 | 761.91 | 412.8 |  | 0 | 0 | 1.09 | 0 | 1.09 | 761.91 | 0 | 761.91 | 80% only until WIR approval, and balance work completion
C | Supply and fixing of Stone Upstand; Type HTL-ST-16, Volakas Marble, Honed | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Ablution | 2.1 | m2 | 490 | 208 | 1465.8 | 392 |  | 0 | 0 | 2.1 | 0 | 2.1 | 1465.8 | 0 | 1465.8 | 80% only until WIR approval, and balance work completion
2 | Female Ablution | 1.4 | m2 | 490 | 208 | 977.2 | 392 |  | 0 | 0 | 1.4 | 0 | 1.4 | 977.2 | 0 | 977.2 | 80% only until WIR approval, and balance work completion
| Threshold | [15 empty] | 80% only until WIR approval, and balance work completion
D | Supply and fixing of Stone Threshold, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 200mm wide; Type ST-08, Pierre de Bourgogne, Anti-gliss treatment | 2.4 | m | 98 | 41 | 333.6 | 78.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | 250mm wide; Type ST-08, Pierre de Bourgogne, Anti-gliss treatment | 2.4 | m | 118 | 42 | 384 | 94.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Skirting | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Skirting including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing, polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone Skirting; Type HTL-ST-07; 100mm high | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Ablution | 7.39 | m | 42 | 23 | 480.35 | 33.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Female Ablution | 7.76 | m | 42 | 23 | 504.4 | 33.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| WALL FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration,provision of the Niche etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone Wall Cladding; Type HTL-0T-07 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Ablution | 13.54 | m2 | 436 | 178 | 8313.56 | 348.8 |  | 0 | 0 | 13.54 | 0 | 13.54 | 8313.56 | 0 | 8313.56 | 80% only until WIR approval, and balance work completion
2 | Female Ablution | 7.31 | m2 | 436 | 178 | 4488.34 | 348.8 |  | 0 | 0 | 7.31 | 0 | 7.31 | 4488.34 | 0 | 4488.34 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone Wall Recess; Type HTL-ST-24 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Ablution | 2.34 | m2 | 696 | 234 | 2176.2 | 556.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Female Ablution | 1.38 | m2 | 696 | 234 | 1283.4 | 556.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
| WALL FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply & fix of stone wall recess; Type HTL-ST-12; as per drawing no. P18-IDR-H-L1-101A-120 | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Male Prayer Room | 2.15 | m2 | 1532 | 258 | 3848.5 | 1225.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Femal Prayer Room | 2.15 | m2 | 1532 | 258 | 3848.5 | 1225.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
PACKAGE - 4 - HOTEL GF LOBBY AND L1 CORRIDOR | [16 empty] | 80% only until WIR approval, and balance work completion
| FLOOR FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and installation of Stone flooring laid on cement and sand screed including grouting, movement joints,pointing, polishing, decoration, dry set mortar or adhesive and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Dark Granite flooring to GF Lobby, subject to sample approval (considered chelmsford Grey) | 25 | m2 | 549 | 140 | 17225 | 439.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Light Granite flooring to GF Lobby, subject to sample approval (considered Saudi Bianco) | 13 | m2 | 372 | 134 | 6578 | 297.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Stone flooring to L1 Corridor; Type HTL-ST-01; Crystal White; Polished | 8 | m2 | 473 | 201 | 5392 | 378.4 |  | 0 | 0 | 8 | 0 | 8 | 5392 | 0 | 5392 | 80% only until WIR approval, and balance work completion
| Threshold | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and installation of Stone Threshold, including necessary grouting, polishing, decoration, adhesives, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
4 | Threshold of various sizes to GF Lobby | 1 | Item | 898 | 329 | 1227 | 718.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Metal Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and installation of Metal works in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
7 | Metal trim to GF Lobby; Type HTL-ME-03; Mirror Polished Stainless Steel | 21 | m | 208 | 21 | 4809 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
8 | Metal trim to L1 Corridor; Type HTL-ME-03; Mirror Polished Stainless Steel | 21 | m | 208 | 21 | 4809 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Skirting | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and installation of Skirting finishes including all necessary backing support, framing, fittings, fixing, accessories,grouting, movement joints,pointing, polishing, decoration shadow gaps, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
11 | Light Marble Skirting to GF Lobby; subject to sample approval; 150mm high (considered Saudi Bianco) | 22 | m | 56 | 23 | 1738 | 44.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
12 | Stone Skirting to L1 Corridor; Type HTL-ST-01; Crystal White; Polished | 120 | m | 56 | 23 | 9480 | 44.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| WALL FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Works | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and installation of Stone finishes including all necessary framing, fitting, fixing, backing framing support, decoration, provision of the Niche etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Stone Wall Cladding and architrave to L1 Corridor; Type HTL-ST-01, Crystal White, Polished | 17 | m2 | 542 | 226 | 13056 | 433.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
PACKAGE -2 - LEVEL 01 BALL ROOM | [16 empty] | 80% only until WIR approval, and balance work completion
| MARBLE FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
| Floor Finishes | [15 empty] | 80% only until WIR approval, and balance work completion
| Floor finishes including preparation of substrate, cement and sand render, bedding or screed or any underlayment for fitted carpets, grout with all necessary fittings, fixings accessories to complete all in accordance with the drawings and specifications | [15 empty] | 80% only until WIR approval, and balance work completion
| Level 1 | [15 empty] | 80% only until WIR approval, and balance work completion
| Ballroom | [15 empty] | 80% only until WIR approval, and balance work completion
A | Stone floor ; type HTL-ST-36 | 138 | m2 | 305 | 202 | 69966 | 244 |  | 0 | 0 | 100 | 10.4 | 110.4 | 50700 | 5272.8 | 55972.8 | 80% only until WIR approval, and balance work completion
| Meeting Room (1 & 2), Break Out Space, Hall, Corridor and Hallways | [15 empty] | 80% only until WIR approval, and balance work completion
B | Stone floor ; type HTL-ST-36 | 307.65 | m2 | 305 | 202 | 155978.55 | 244 |  | 0 | 0 | 307.65 | 0 | 307.65 | 155978.55 | 0 | 155978.55 | 80% only until WIR approval, and balance work completion
| Lift Lobby | [15 empty] | 80% only until WIR approval, and balance work completion
C | Stone floor ; type HTL-ST-36 | 21 | m2 | 305 | 202 | 10647 | 244 |  | 0 | 0 | 21 | 0 | 21 | 10647 | 0 | 10647 | 80% only until WIR approval, and balance work completion
| Ballroom male toilet | [15 empty] | 80% only until WIR approval, and balance work completion
D | Stone floor; herringbone pattern; type HTL-ST-01 | 54 | m2 | 301 | 215 | 27864 | 240.8 |  | 0 | 0 | 54 | 0 | 54 | 27864 | 0 | 27864 | 80% only until WIR approval, and balance work completion
D | 7mm wide Brass Strip insert in brushed finish with top layer brass coat (HTL-ME-04) | 61.33 | m | 206 | 20 | 13860.58 | 164.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Ballroom female toilet | [15 empty] | 80% only until WIR approval, and balance work completion
E | Stone floor; herringbone pattern; type HTL-ST-01 | 61.49 | m2 | 317 | 175 | 30253.08 | 253.6 |  | 0 | 0 | 61.49 | 0 | 61.49 | 30253.08 | 0 | 30253.08 | 80% only until WIR approval, and balance work completion
D | 7mm wide Brass Strip insert in brushed finish with top layer brass coat (HTL-ME-04) | 60 | m | 206 | 20 | 13560 | 164.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Wall Finishes | [15 empty] | 80% only until WIR approval, and balance work completion
| Wall finish including preparation of substrate, render, filler, primer, undercoat(s), finish coats, all necessary fittings, fixings accessories to complete all in accordance with the drawings and specifications | [15 empty] | 80% only until WIR approval, and balance work completion
A | Supply and fixing of Stone Wall Cladding; Type HTL-ST-36 | 10 | m2 | 317 | 175 | 4920 | 253.6 |  | 0 | 0 |  | 8 | 8 | 0 | 3936 | 3936 | 80% only until WIR approval, and balance work completion
B | Supply and fixing of Stone Wall Cladding; Type HTL-ST-10 | 20.79 | m2 | 353 | 176 | 10997.91 | 282.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Toilet | [15 empty] | 80% only until WIR approval, and balance work completion
C | Supply and fixing of stone in female toilet; type HTL-ST-37 | 98.38 | m2 | 1356 | 206 | 153669.56 | 1084.8 |  | 0 | 0 | 98.38 | 0 | 98.38 | 153669.56 | 0 | 153669.56 | 80% only until WIR approval, and balance work completion
D | Supply and fixing of stone in male toilet; type HTL-ST-38 | 145 | m2 | 373 | 176 | 79605 | 298.4 |  | 0 | 0 | 145 | 0 | 145 | 79605 | 0 | 79605 | 80% only until WIR approval, and balance work completion
| Skirting Finishes | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone skirting including all necessary backing support, framing, fittings, fixing, accessories, grouting, movement joints, pointing, polishing, decoration shadow gaps, etc. and the like all in accordance with drawings and specifications | [15 empty] | 80% only until WIR approval, and balance work completion
E | Supply and fixing of stone skirting; type stone baseboard HTL-ST-36 | 114 | m | 59 | 39 | 11172 | 47.2 |  | 0 | 0 |  | 55.2 | 55.2 | 0 | 5409.6 | 5409.6 | 80% only until WIR approval, and balance work completion
F | Supply and fixing of stone skirting; type stone baseboard HTL-ST-10 | 60 | m | 128 | 81 | 12540 | 102.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
G | Supply and fixing of stone skirting; 150mm high; type stone baseboard HTL-ST-37 to female toilet | 106 | m | 132 | 28 | 16960 | 105.6 |  | 0 | 0 | 106 | 0 | 106 | 16960 | 0 | 16960 | 80% only until WIR approval, and balance work completion
H | Supply and fixing of stone skirting; 150mm high; type stone baseboard HTL-ST-38 to male toilet | 59.84 | m | 67 | 26 | 5565.12 | 53.6 |  | 0 | 0 | 59.84 | 0 | 59.84 | 5565.12 | 0 | 5565.12 | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
| The tenderer is to detail below any additional items with quantities and rates not previously included to complete the build up of the lump sum tender price for this section of the works. Should the Subcontractor fail to insert any items hereunder, it will be deemed that his lump sum price for the tender includes all works as required by the tender drawings and specification and no subsequent claim for any additional item will be entertained. | [15 empty] | 80% only until WIR approval, and balance work completion
A | Stone Treads; to steps, HTL-ST-36, 500mm wide | 24 | m | 180 | 74 | 6096 | 144 |  | 0 | 0 |  | 19.2 | 19.2 | 0 | 4876.8 | 4876.8 | 80% only until WIR approval, and balance work completion
B | Stone Risers; to steps, HTL-ST-36, 160mm high | 24 | m | 61 | 35 | 2304 | 48.8 |  | 0 | 0 |  | 19.2 | 19.2 | 0 | 1843.2 | 1843.2 | 80% only until WIR approval, and balance work completion
C | Stone vanity counter to female toilet, curved, HTL-ST-37, overall size 2580 x 2185 x 880mm high as per Dwg Ref L1-BALL-WC-D-305 & L1-BALL-WC-D-306 | 1 | nos. | 6274 | 3893 | 10167 | 5019.2 |  | 0 | 0 |  | 0.8 | 0.8 | 0 | 8133.6 | 8133.6 | 80% only until WIR approval, and balance work completion
D | Stone architrave, 150mm wide, HTL-ST-37 to female toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01A | 17.28 | m | 122 | 70 | 3317.76 | 97.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
E | Stone architrave, 210mm wide, HTL-ST-37 to female toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01 | 23 | m | 141 | 70 | 4853 | 112.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
F | Stone architrave, 200mm wide, HTL-ST-38 to male toilet urinal as per Dwg Ref L1-BALL-WC-D-307 Detail Top view 1 | 39 | m | 149 | 70 | 8541 | 119.2 |  | 0 | 0 |  | 31.2 | 31.2 | 0 | 6832.8 | 6832.8 | 80% only until WIR approval, and balance work completion
G | Stone Architrave, 905mm wide, HTL-ST-38 to male toilets | 7 | m | 379 | 310 | 4823 | 303.2 |  | 0 | 0 |  | 5.6 | 5.6 | 0 | 3858.4 | 3858.4 | 80% only until WIR approval, and balance work completion
H | Stone Architrave, 150mm wide, HTL-ST-38 to male toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01A | 11.52 | m | 113 | 69 | 2096.64 | 90.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
A | Stone Architrave, 210mm wide, HTL-ST-38 to male toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01 | 34 | m | 153 | 71 | 7616 | 122.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Stone Urinal shelf, 100mm wide, HTL-ST-38 to male toilet as per Dwg Ref L1-BALL-WC-D-307 | 6 | m | 270 | 119 | 2334 | 216 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Stone Vanity Counter to male toilet, curved, HTL-ST-38, overall size 8775 x 1040 x 880mm high as per Dwg Ref L1-BALL-WC-D-302 & L1-BALL-WC-D-303 | 1 | nos. | 7155 | 4194 | 11349 | 5724 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Stone Architrave around Disable Lift Doors, 230mm wide, HTL-ST-36 | 11 | m | 146 | 90 | 2596 | 116.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
E | Stone Bar Counter, in fluted HTL-ST-36 stone, overall size 1650 x 840 x 1100mm high | 1 | nos. | 1403 | 881 | 2284 | 1122.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
F | Stone Back Bar Counter, in HTL-ST-36 stone, overall size 2970 x 640 | 1 | nos. | 720 | 502 | 1222 | 576 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
G | Stone Architrave around BOH Doors. 240mm wide, HTL-ST-36 | 6 | m | 137 | 89 | 1356 | 109.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
H | Stone Architrave to Lift Lobby, HTL-ST-36 stone | 8.18 | m2 | 365 | 299 | 5431.52 | 292 |  | 0 | 0 |  | 6.544 | 6.544 | 0 | 4345.216 | 4345.216 | 80% only until WIR approval, and balance work completion
I | Stone Architrave to Lift Doors, 465mm wide, HTL-ST-36 stone | 37 | m | 200 | 104 | 11248 | 160 |  | 0 | 0 |  | 29.6 | 29.6 | 0 | 8998.4 | 8998.4 | 80% only until WIR approval, and balance work completion
J | Supply and fixing of Stone Architrave; Type HTL-ST-10, size 770+440 550 x 20mm for Ballroom | 73 | m | 453 | 261 | 52122 | 362.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
K | Supply and fixing of Stone Architrave; Type HTL-ST-10, size 540+770+615 x 20mm for Ballroom | 73 | m | 666 | 471 | 83001 | 532.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| FRAMING SUPPORT | [15 empty] | 80% only until WIR approval, and balance work completion
A | Stone vanity counter to female toilet, curved, HTL-ST-37, overall size 2580 x 2185 x 880mm high as per Dwg Ref L1-BALL-WC-D-305 & L1-BALL-WC-D-306 | 1 | nos. |  |  | 9499.5 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Stone architrave, 150mm wide, HTL-ST-37 to female toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01A | 17.28 | m |  |  | 13825.73 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Stone architrave, 210mm wide, HTL-ST-37 to female toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01 | 23 | m |  |  | 20700 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Stone architrave, 200mm wide, HTL-ST-38 to male toilet urinal as per Dwg Ref L1-BALL-WC-D-307 Detail Top view 1 |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
E | Stone Architrave, 905mm wide, HTL-ST-38 to male toilets | 7 | m |  |  | 6678 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
F | Stone Architrave, 150mm wide, HTL-ST-38 to male toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01A | 11.52 | m |  |  | 9850 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| FRAMING SUPPORT |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
A | Stone Architrave, 210mm wide, HTL-ST-38 to male toilet doors as per Dwg Ref L1-BALL-WC-D-310 Detail 01 | 34 | m |  |  | 30600 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Stone Urinal shelf, 100mm wide, HTL-ST-38 to male toilet as per Dwg Ref L1-BALL-WC-D-307 |  | nos. | [13 empty] | 80% only until WIR approval, and balance work completion
C | Stone Vanity Counter to male toilet, curved, HTL-ST-38, overall size 8775 x 1040 x 880mm high as per Dwg Ref L1-BALL-WC-D-302 & L1-BALL-WC-D-303 | 1 | nos. |  |  | 11500.2 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
D | Stone Architrave around Disable Lift Doors, 230mm wide, HTL-ST-36 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
G | Stone Architrave around BOH Doors. 240mm wide, HTL-ST-36 | 6 | m |  |  | 5400 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
H | Stone Architrave to Lift Lobby, HTL-ST-36 stone |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
I | Stone Architrave to Lift Doors, 465mm wide, HTL-ST-36 stone |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
J | Supply and fixing of Stone Architrave; Type HTL-ST-10, size 770+440 550 x 20mm for Ballroom | 73 | m |  |  | 65700 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
K | Supply and fixing of Stone Architrave; Type HTL-ST-10, size 540 550+770+615 x 20mm for Ballroom | 73 | m |  |  | 65700 | 0 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| INTERNAL FINISHES | [15 empty] | 80% only until WIR approval, and balance work completion
| Floor Finishes | [15 empty] | 80% only until WIR approval, and balance work completion
| Floor finishes including preparation of substrate, cement and sand render, bedding or screed or any underlayment for fitted carpets, grout with all necessary fittings, fixings accessories to complete all in accordance with the drawings and specifications | [15 empty] | 80% only until WIR approval, and balance work completion
| Level 1 | [15 empty] | 80% only until WIR approval, and balance work completion
| Ballroom | [15 empty] | 80% only until WIR approval, and balance work completion
C | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
D | Metal trim ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Meeting Room 1 | [15 empty] | 80% only until WIR approval, and balance work completion
J | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
K | Metal strip; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
L | Stone threshold; type HTL-ST-36 , width 150 mm |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Meeting Room 2 | [15 empty] | 80% only until WIR approval, and balance work completion
N | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
Q | Metal trim ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Corridor | [15 empty] | 80% only until WIR approval, and balance work completion
B | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
D | Metal trim ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
E | Metal trim ; type HTL-ME-03 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Disable lift lobby | [15 empty] | 80% only until WIR approval, and balance work completion
H | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Hall | [15 empty] | 80% only until WIR approval, and balance work completion
M | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
N | Metal floor ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Lift Lobby | [15 empty] | 80% only until WIR approval, and balance work completion
Q | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
S | Metal floor ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| To Collection Dhs. | [15 empty] | 80% only until WIR approval, and balance work completion
| Pre-function space | [15 empty] | 80% only until WIR approval, and balance work completion
B | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
C | Metal trim ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Breakout space | [15 empty] | 80% only until WIR approval, and balance work completion
F | Stone floor ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
G | Metal trim ; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Ballroom male toilet | [15 empty] | 80% only until WIR approval, and balance work completion
J | Stone floor; type HTL-ST-01 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
K | Stone floor; herringbone pattern; type HTL-ST-01 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
M | Brass strip ; type HTL-ME-04 | 68 | m | 208 | 21 | 15572 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Ballroom female toilet | [15 empty] | 80% only until WIR approval, and balance work completion
Q | Stone floor; herringbone pattern; type HTL-ST-01 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
T | 7 mm brass strip ; type HTL-ME-04 | 59 | m | 208 | 21 | 13511 | 166.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Wall Finishes | [15 empty] | 80% only until WIR approval, and balance work completion
| Wall finish including preparation of substrate, render, filler, primer, undercoat(s), finish coats, all necessary fittings, fixings accessories to complete all in accordance with the drawings and specifications | [15 empty] | 80% only until WIR approval, and balance work completion
| Level 1 | [15 empty] | 80% only until WIR approval, and balance work completion
| Ball room | [15 empty] | 80% only until WIR approval, and balance work completion
J | 400 mm high Stone baseboard ; type HTL-ST-10 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
K | Stone wall; type HTL-ST-10 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
P | Moveable partition; type HTL-WC-20/ HTL-ME-03 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Meeting Room -01 | [15 empty] | 80% only until WIR approval, and balance work completion
A | Metal " C" Beam 100 x 200 mm; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
B | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
D | 200 mm height Stone baseboard; type HTL-ST-36 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
G | Metal strip 20 mm wide; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Meeting Room -02 | [15 empty] | 80% only until WIR approval, and balance work completion
K | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
L | Metal "U" Beam 100 x 200 mm; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
M | 200 mm height Stone baseboard ; type HTL-ST-36 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Corridor | [15 empty] | 80% only until WIR approval, and balance work completion
S | Lit skirting 100 mm high; type HTL-ME-03 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
T | Stringer at staircase side; type HTL-ME-04 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
U | 200 mm high Stone baseboard; type HTL-ST-36 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
W | 200 mm high Decorative lit beam; type HTL-WD-19 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Hall | [15 empty] | 80% only until WIR approval, and balance work completion
C | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Hall | [15 empty] | 80% only until WIR approval, and balance work completion
D | Stone wall ; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Hall | [15 empty] | 80% only until WIR approval, and balance work completion
G | Stone baseboard 200 mm height; type HTL-ST-36 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Hall | [15 empty] | 80% only until WIR approval, and balance work completion
K | Stone baseboard 200 mm height; type HTL-ST-10 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Lift lobby | [15 empty] | 80% only until WIR approval, and balance work completion
L | 200 mm high Stone baseboard ; type HTL-ST-36 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
M | Stone wall; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Prefunction | [15 empty] | 80% only until WIR approval, and balance work completion
P | Metal " L" Beam 130 x 130 mm; type HTL-ME-06 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
Q | 200 mm height Stone baseboard ; type HTL-ST-10 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
R | 400 mm height Stone baseboard ; type HTL-ST-10 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
S | Stone wall; type HTL-ST-10 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Break out space | [15 empty] | 80% only until WIR approval, and balance work completion
D | 200 mm high Stone baseboard ; type HTL-ST-10 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
E | Stone back bar; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Ballroom male toilet | [15 empty] | 80% only until WIR approval, and balance work completion
M | Wainscotting ; type HTL-ST-38 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
N | Stone baseboard ; type HTL-ST-38, 150 mm H |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| Ballroom female toilet | [15 empty] | 80% only until WIR approval, and balance work completion
Q | Stone wall; HTL -ST -37 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
S | 150 mm Stone baseboard; type HTL-ST-37 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
T | Metal baseboard; HTL -ME -04 |  | m | [13 empty] | 80% only until WIR approval, and balance work completion
| BOH | [15 empty] | 80% only until WIR approval, and balance work completion
C | 200 mm height Stone baseboard HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
D | Stone wall; type HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| Storage | [15 empty] | 80% only until WIR approval, and balance work completion
H | 200 mm height Stone baseboard HTL-ST-36 |  | m2 | [13 empty] | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
A | Ballroom Male Toilet | [15 empty] | 80% only until WIR approval, and balance work completion
| ST-01; 205mmW Threshold | 6.91 | m | 102 | 34 | 939.76 | 81.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
B | Ballroom Female Toilet | [15 empty] | 80% only until WIR approval, and balance work completion
| ST-01; 205mmW Threshold | 5.13 | m | 102 | 34 | 697.68 | 81.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| PACKAGE -3 - HOTEL LEVEL 19:- PRESIDENTIAL SUITE FIT-OUT | [15 empty] | 80% only until WIR approval, and balance work completion
| Vanity | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and Installation of vanity with wash hand basin cutout including supporting HDF frame, decoration and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
B | Stone custom sink and stone top in HTL-ST-37 with wood drawer box at Twin Bathroom, as detailed shown on Dwg. No. 1902-210, SEC. II | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 1000mm length | 1 | Nr | 5087 | 318 | 5405 | 4069.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | 2000mm length | 1 | Nr | 5408 | 494 | 5902 | 4326.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
C | Stone Bench; Type HTL-ST-37, as detailed shown on Dwg No. 1902-211, SEC. 08 | 1 | Nr | 645 | 377 | 1022 | 516 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Stone Ledge Top | [15 empty] | 80% only until WIR approval, and balance work completion
D | Supply and Installation of Stone Ledge Top at WC cistern, including necessary framing, backing board to receive wall tiles, fittings, etc., complete as per Drawings and Specifications | [15 empty] | 80% only until WIR approval, and balance work completion
1 | 230mm wide;Type HTL-ST-35 Stone Ledge Top at WC cistern | 1 | Nr | 353 | 72 | 425 | 282.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
11 | Built-in metal drawers w/ stone top and fabric panel at back in metal continuous frame, Study Room as detailed shown on Dwg. No. 1902-120, 1902-203 SEC. KK,LL | 1 | Nr | 1124 | 262 | 1386 | 899.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Wood Shelf, Wooden Panelling/Frame, Vanity, Ledge | [15 empty] | 80% only until WIR approval, and balance work completion
A | Make-up station with stone top and wood shelf, legs and wood panels on Dressing Room 1 as detailed shown on Dwg. No. 1902-203, SEC. LL | 1 | Nr | 1221 | 284 | 1505 | 976.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Vanity | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and Installation of vanity with wash hand basin cutout including supporting HDF frame, decoration and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
D | Custom stone sink and stone vanity in HTL-ST-35 with wood drawer box, wood shelf at Master Bathroom, as detailed shown on Dwg. No. 1902-200 SEC. AA,BB & 1902-205 SEC. OO,PP | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Master Bathroom | 2 | Nr | 2327 | 665 | 5984 | 1861.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
E | Custom stone sink and stone vanity in HTL-ST-21 at Powder Room, as detailed shown on Dwg. No. 1902-203 SEC. KK,LL & 1902-207 SEC. YY | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Powder Room | 1 | Nr | 2566 | 443 | 3009 | 2052.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
E | Stone Bench; Type HTL-ST-35, as detailed shown on Dwg No. 1902-201, SEC. CC,DD | 1 | Nr | 323 | 359 | 682 | 258.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Stone Ledge Top | [15 empty] | 80% only until WIR approval, and balance work completion
F | Supply and Installation of Stone Ledge Top at WC cistern, including necessary framing, backing board to receive wall tiles, fittings, etc., complete as per Drawings and Specifications, Type: HTL-ST-35; 230mm wide | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Master Bathroom | 1 | Nr | 356 | 72 | 428 | 284.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Powder Room | 1 | Nr | 356 | 72 | 428 | 284.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Custom stone sink and stone vanity with backsplash in HTL-ST-52 at Open Kitchen as detailed shown on dwg no. 1902-324; Det. 01 | 1 | Nr | 2197 | 1133 | 3330 | 1757.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Custom stone sink and stone vanity with backsplash in HTL-ST-16 at Pantry | 1 | Nr. | 2487 | 1275 | 3762 | 1989.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Stone Island at Open Kitchen: Type HTL-ST-37, as detailed shown on dwg. No. 1902-325, det. 01: Type HTL-ST-37 | 1 | Nr. | 3658 | 1772 | 5430 | 2926.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | Wooden drawers with stone top on Media Room, as detailed shown on Dwg. No. 1902-323. Det.01, Type HTL-ST-35 | 1 | Nr. | 2097 | 381 | 2478 | 1677.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
5 | Wooden wardrobe with stone top and backsplash on Dressing Room 2, as detailed shown on Dwg. No. 1902-315, Det. 01; Tpe HTL-ST-35 | 1 | Nr. | 2701 | 646 | 3347 | 2160.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
6 | Wooden wardrobe with stone top and backsplash on Dressing Room 1, as detailed shown on Dwg. No. 1902-311, Det. 01; Type HTL-ST-35 | 1 | Nr. | 2858 | 681 | 3539 | 2286.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
7 | Wooden wardrobe with stone top and backsplash on Dressing room 1, as detailed shown on Dwg. No. 1902-310,Det.01; Type HTL-ST-35 | 1 | Nr. | 1090 | 181 | 1271 | 872 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| PACKAGE -3 - ROYAL SUITE FIT-OUT | [15 empty] | 80% only until WIR approval, and balance work completion
| Stone Vanity | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and Installation Stone vanity with wash hand basin cutout including supporting HDF frame, decoration and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
F | Backlit Stone Vanity - Secondary Bathroom, as detailed shown on Dwg. No. RS-2608-334, DET. 01 | 1 | Nr | 5407 | 494 | 5901 | 4325.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
G | Stone Bench; Type HTL-ST-37, as detailed shown on Dwg No. RS-2608-336, DET. 02 | 1 | Nr | 457 | 376 | 833 | 365.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Stone Ledge Top | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and Installation of Stone Ledge Top at WC cistern, including necessary framing, backing board to receive wall tiles, fittings, etc., complete as per Drawings and Specifications | [15 empty] | 80% only until WIR approval, and balance work completion
H | 250mm wide;Type HTL-ST-21 Stone Ledge Top at WC cistern | 1.32 | m | 388 | 50 | 578.16 | 310.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Stone Vanity | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and Installation Stone vanity with wash hand basin cutout including supporting HDF frame, decoration and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
E | Backlit Stone Vanity - Master Bathroom, as detailed shown on Dwg. No. RS-2608-318, DET. 01 | 2 | Nr | 1310 | 655 | 3930 | 1048 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
F | Stone Bench; Type HTL-ST-21, as detailed shown on Dwg No. RS-2608-318, DET. 02 | 1 | Nr | 328 | 362 | 690 | 262.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Stone Ledge Top | [15 empty] | 80% only until WIR approval, and balance work completion
| Supply and Installation of Stone Ledge Top at WC cistern, including necessary framing, backing board to receive wall tiles, fittings, etc., complete as per Drawings and Specifications | [15 empty] | 80% only until WIR approval, and balance work completion
G | 250mm wide;Type HTL-ST-21 Stone Ledge Top at WC cistern | 1.2 | m | 395 | 50 | 534 | 316 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Supply and Installation of Wash Basin, including necessary framing, backing board to receive wall tiles, fittings, etc and the like all in accordance with drawings and specifications. | [15 empty] | 80% only until WIR approval, and balance work completion
H | Supply and fixing of Wash Basin;Type HTL-ST-51, as detailed shown on Dwg No. RS-2608-337, DET. 01 | 1 | Nr | 323 | 359 | 682 | 258.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
Add | Bathtub top - size 1950 x 1020mm ST-37 | 1 | Nr | 2067 | 773 | 2840 | 1653.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| ADDITIONAL ITEMS | [15 empty] | 80% only until WIR approval, and balance work completion
1 | Supply & installation of stone at Master Dressing as per drawing no. RS-2608-314; Type ST-21 | 1 | Nr. | 2656 | 418 | 3074 | 2124.8 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
2 | Supply & installation of stone at Master Dressing as per drawing no. RS-2608-315; Type ST-21 | 1 | Nr. | 2653 | 408 | 3061 | 2122.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
3 | Supply & installation of stone at Master Dressing as per drawing no. RS-2608-316; Type ST-21 | 1 | Nr. | 2488 | 390 | 2878 | 1990.4 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
4 | Supply & installation of stone at Master Dressing as per drawing no. RS-2608-317; Type ST-21 | 1 | Nr. | 3017 | 764 | 3781 | 2413.6 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
5 | Supply & instalaltion of stone at Pantry as per drawing no. RS-2608-324; Type ST-16 | 1 | Nr. | 2230 | 880 | 3110 | 1784 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
6 | Supply & installation of stone at dining sideboard as per drawing no. RS-2608-326; Top Type ST-21 & wall type ST-51 | 1 | Nr. | 2605 | 561 | 3166 | 2084 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
7 | Supply & installation of stone at minibars as per drawing no. RS-2608-327; Type ST-21 | 2 | Nos. | 2029 | 300 | 4658 | 1623.2 |  | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 80% only until WIR approval, and balance work completion
| Grand total |  |  |  |  | 2169551.483 |  |  |  | 0 |  |  |  | 566441.64 | 102228.536 | 668670.176

## VO register (hidden)
Project: Dorchester Plot 18
Subject: Variation order register
Item no. | Reference | Description | EI Ref | Aconex Ref | Date of Submission | Amount
| ORIGINAL CONTRACT | Supply and installation of hardlandscape Stoneworks |  |  |  | 4556481
Variation Order
1 | ARM-AR-A-VAR-001 | Change in Design of Level 02 Water Feature | E11-K114-SK-dm-151 |  | 2022-04-08 | 4165.46
2 | ARS-1139-0622 | Addition Support for Level 29 Pool Bar Counter | E11-K114-SK-dm-051 |  | 28/06/2022
3 | ARM-AR-A-VAR-002 | Additional Black Absoluto Banding at Level 02 Drop Off as per KCE-LX-RFI-L2-00073 | E11/K114/SN/dm/183 | ARMG-SUBCONLET-000078 | 15/9/2022
4 | ARS-1182-0822 | Stoneworks in Ballroom, Royal, Presidential Suit, Gym, Prayer Room, Lobbies | E11-K114-SK-SR-206 |  | 15/9/2022 | 1787839.32
5 | ARS-1157-0822 | Supply and installation of Omani stone 20mm thick cladding for Daybed booth at Level 04 Residential Swimming pool as per mark-up drawing LA-LD-L4-3421. | E11/K114/SK/MV/243 & 244 |  | 2022-08-08 | 12288
6 | ARS-1201-0922 | Supply and installation of pool overflow channel stone support as per KCE-LX-RFI-PW-000146 |  |  | 21/09/2022 | 164783.47
7 | ARM-AR-A-VAR-003 | Submittal of variation order ARM-AR-A-VAR-003 – Supply and installation of Omani stone 20mm thick planter cladding at Levels 10,24,25, 26,27 & 29 as per EI-303_R0,R1&R2 | E11K114SCdm303 r0, r1 & r2 | ARMG-SUBCONLET-000106 | 31/10/2022 | 91055.68
8 | ARM-AR-A-VAR-004_R1 | Supply and installation of additional cobbles, banding and benches at Level 02 drop off as per revised design | E11/K114/SC/dm/367 | ARMG-SUBCONLET-000137 | 2022-08-12 | 112777
9 | ARM-AR-A-VAR-005 | Supply and installation of additional Tribeca Sanded Crazy cut HS-01A at Level 17 as per EI-373 | E11/K114/SC/dm/373 | ARMG-SUBCONLET-000109 | 2022-01-11
10 | ARM-AR-A-VAR-006_R4 | Supply and Installation of Hardlandscape Tiling works as per EI 306 & 338 | E11/K114/SC/dm/306 & 338 | ARMG-SUBCONLET-000133 | 2022-06-12 | 534254
11 | ARM-AR-A-VAR-007 | Supply and Installation of Omani flooring and stair cladding 20mmT at Level 10 as per EI 306R1 | E11/K114/SC/dm/306_r1 | ARMG-SUBCONLET-000113 | 2022-03-11 | 98371
12 | ARM-AR-A-VAR-008_R1 | Supply and Installation of Omani flooring at Level 04 Pool area | E11-K114-SC-MV-438 | ARMG-SUBCONLET-000128 | 28/11/2022 | 125306
13 | ARM-AR-A-VAR-009 | Supply and installation of 400mmL plate SS coping support at Level 24,25,27 & 29 as per WIR ref. ARM-AX-WR-L24-00017 Rev 0 | E11/K114/AS/dm/447 | ARMG-SUBCONLET-000130 | 2022-05-12 | 98788
14 | ARM-AR-A-VAR-010 | Supply and installation of 10x10x5cm cobbles stone at LPG delivery truck way; Work as per RFI ref. KCE-LX-RFI-GF-00332 Rev 00 | E11/K114/NA/dm/490 | ARMG-SUBCONLET-000132 | 2022-05-12 | 74930
15 | ARM-AR-A-VAR-011 | Supply and installation of 20mm thick black tile to Level 23 (WF-23A-C-WF-23B-C, WF-23C-C) as per the attached material apporval ref ARM-LX-MT-ET-00045 dated 07.11.22 | E11-K114-SK-mv-562 | ARMG-SUBCONLET-000145 | 2023-02-01 | 17683.73
16 | ARM-AR-A-VAR-012 | Level 17 revised drawing | E11/K114/SC/mv/427 | ARMG-SUBCONLET-000154 | 25/01/2023 | 153872.2
17 |  | Supply and installation of Stone/Tile at Level 23 Disabled Toilet | E11-K114-SN-SR-499 |  |  | 14758
18 | ARS.1272.1222 | Stoneworks at Secret Garden |  | E11/K114/SK/mv/597 | 27/12/2022 | 428553
19 | ARS.1274.1222 | Cost estimate for stoneworks at GF and Level 02 Hardlandscape areas due to design change |  |  | 28/12/2022 | 1261894.84
20 | ARM-AR-A-VAR-013 | Supply and installation of Level 29 Bar counter as per revised ID design | E11-K114-SN-dm-498 |  |  | 95912.33
21 | ARM-AR-A-VAR-014 | Demolition of existing floor tiles (White Granix tile 50mm thick) and tile bed due to design changes at GF & Level 2 as per the areas highlighted in the attached sketches | E11/K114/KD/sk/565 | ARMG-SUBCONLET-000168 | 23/02/2023 | 72577
22 | ARM-AR-A-VAR-015 | Demolition of existing floor tiles (white granix tile 50mm thick) and tile bed at Level 2 | E11/K114/HN/MV/701 | ARMG-SUBCONLET-000169 | 23/02/2023 | 8310
23 |  | installation of floor tiles at various locations as per highlighted markup drawing including grouting adhesive, trims, accesories , etc... to complete the works - Balcony areas | E11/K114/SK/mv/581
24 |  | Omani beige tile at highlighted step on drawing ref. ARM-TL-SD-L4-00410 Rev 00 | E11/K114/SC/dm/603
25 |  | Supply and installation of granite kerb at GF to L2 ramp | E11/K114/SK/SC/646
26 |  | Lift 12 & 13 internal floor stone finish | E11/K114/SN/dm/698
27 |  | Demolition of existing floor tiles (white granix tile 50mm thick) and tile bed at Level 2 | E11/K114/HN/MV/701
28 |  | Installation of tiling at Level 03 | E11/K114/SK/SR/724
29 |  | Installation of bespoke kerbstone for hardscape works and work as per WIR ref. ARM-AX-WR-L24-00017 Rev 0 | E11/K114/AS/dm/445
30 |  | Works at GF Ballroom prefunction & GF paving as per Client email | E11/K114/AK/dm/774 & 778
| Total amount - VO |  |  |  |  | 5158119.03
Quotations issued to KCE
1 | ARS/1311/0223 | Quotation for Lift 12 & 3 stone flooring, border and skirting |  |  | 2023-10-02 | 3877.08
2 | ARS/1319/0223 | Additional stoneworks for L02 Secret Garden inside terrace bar flooring |  | ARMG-SUBCONLET-000166 | 15/2/2023 | 15120
| Total amount quotation |  |  |  |  | 18997.08
| Grand Total |  |  |  |  | 9733597.11