## Sheet1
P-287 | KHANSAHEB CIVIL ENGINEERING L.L.C
KHANSAHEB LOP
[7 empty] | 0.8 |  | 0.2 |  |  | 0.8 |  | 0.2
[6 empty] | Material Delivery 80% |  | Installation 20% |  | TOTAL | Material Delivery 80% |  | Installation 20%
SL | DESCRIPTION | UNIT | QTY | RATE |  | QTY | AMOUNT | QTY | AMOUNT | AMOUNT | QTY | AMOUNT | QTY | AMOUNT
WALL FINISHES
-1 | Type RES-WD-06; Wooden panelling to cloakroom including framing RES-WD-02 (refer Drawing 301) - (MDF with Veneer Finish) | m² | 25 | 357 | 8925 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-2 | Type RES-WD-06; Wooden panelling to concierge including framing RES-WD-02 - (MDF with Veneer Finish) | m² | 32 | 357 | 11424 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-1 | Type RES-WD-08; Stiles and rails 40mm wide horizontally to corridor (refer Drawing 306) (Solid Wood) | m | 63 | 134 | 8442 |  | 0 | 37 | 991.6 | 991.6 |  | 0 | 37 | 892.44
-2 | Type RES-WD-08; Stiles and rails 40mm wide vertically to corridor (refer Drawing 306) (Solid Wood) | m | 77 | 134 | 10318 |  | 0 | 51 | 1366.8 | 1366.8 |  | 0 | 51 | 1230.12
-3 | Type RES-WD-15; Vertical wall planks to fitness room (refer Drawing 330 and 331) (Solid Wood) | m² | 57 | 402 | 22914 |  | 0 | 32 | 2572.8 | 2572.8 |  | 0 | 32 | 2315.52
-4 | Type RES-WD-15; Vertical wall planks to yoga room (refer Drawing 330 and 331) (Solid Wood) | m² | 24 | 402 | 9648 |  | 0 | 12 | 964.8 | 964.8 |  | 0 | 12 | 868.32
-5 | Type RES-WD-16; Stiles and rails 40mm wide horizontally to corridor (refer Drawing 338) (Solid Wood) | m | 76 | 134 | 10184 |  | 0 | 41 | 1098.8 | 1098.8 |  | 0 |  | 0
-6 | Type RES-WD-16; Stiles and rails 40mm wide vertically to corridor (refer Drawing 338) (Solid Wood) | m | 145 | 134 | 19430 |  | 0 | 100 | 2680 | 2680 |  | 0 |  | 0
| Total Wall Finish |  |  |  | 0 |  | 0 |  | 9674.8 | 9674.8 |  | 0 |  | 5306.4
| SKIRTING |  |  |  | 0
-9 | Type RES-WD-08; Wooden skirting 250mm high to corridor (refer Detail 01 of Drawing 301) | m | 25 | 80 | 2000 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-10 | Type RES-WD-16; Wooden skirting 200mm high to fitness room (refer Detail 05 of Drawing 301) | m | 20 | 80 | 1600 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-11 | Type RES-WD-16; Wooden skirting 200mm high to yoga room (refer Detail 06 of Drawing 301) | m | 10 | 80 | 800 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-12 | Type RES-WD-08; Wooden skirting 250mm high to corridor (refer Detail 01 of Drawing 301) | m | 2 | 80 | 160 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-13 | Type RES-WD-16; Wooden skirting 200mm high to Yoga Room (refer Detail 01 of Drawing 301) | m | 2 | 80 | 160 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-14 | Type RES-WD-07; Wooden skirting 150mm high to cloakrooms (refer Detail 03 of Drawing 336) | m | 11 | 80 | 880 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-15 | Type RES-WD-16; Wooden skirting 250mm high to corridor (refer Detail 01 of Drawing 336) | m | 43 | 80 | 3440 |  | 0 |  | 0 | 0 |  | 0 |  | 0
| Total Skirting |  |  |  | 0 |  | 0 |  | 0 | 0 |  | 0 |  | 0
| CEILING FINISHES |  |  |  | 0
-16 | Type RES-WD-02; Double wood lit cornice size 500mm wide x 300mm high to lift lobby (Client TBC) | m | 21 | 407 | 8547 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-17 | Type RES-WD-02; Double wood lit cornice size 500mm wide x 300mm high to lift lobby (Client TBC) | m | 21 | 407 | 8547 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-18 | Type RES-WD-02; Double wood lit cornice size 500mm wide x 300mm high to corridor (refer Detail 09 of Drawing 300) | m | 36 | 407 | 14652 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-19 | Type RES-WD-02; Double wood lit cornice size 500mm wide x 300mm high to lift lobby (refer Detail 09 of Drawing 300) | m | 21 | 407 | 8547 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-20 | Type RES-WD-02; Wood ceiling border size 500mm wide x 300mm high to corridor (refer Detail 08 of Drawing 300) | m | 26 | 407 | 10582 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-21 | Type RES-WD-02; Wood lit cornice size 300mm wide x 150mm high to lobby (refer Detail 04 of Drawing 300) | m | 42 | 232 | 9744 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-22 | Type RES-WD-02; Wood lit cornice size 300mm wide x 150mm high to lift lobby (refer Detail 04 of Drawing 300) | m | 18 | 232 | 4176 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-23 | Type RES-WD-02; Wood lit cornice size 300mm wide x 150mm high to lift lobby (Client TBC) | m | 18 | 232 | 4176 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-7 | Type RES-WD-01; Suspended/ Openable Wood Ceiling (Point de hongir" pattern to lift Car | m² | 9 | 491 | 4419 | 6.28 | 2466.784 | 6.28 | 616.696 | 3083.48 |  | 0 |  | 0
-25 | Type RES-WD-01; Suspended/ Openable Wood Ceiling (Point de hongir" pattern to lift Car | m² | 3 | 491 | 1473 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-26 | Type RES-WD-02; Double wood lit cornice size 390mm wide x 120mm high to meeting/dining room (refer Detail 08 of Drawing 336) | m | 14 | 232 | 3248 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-27 | Type RES-WD-02; Double wood lit cornice size 390mm wide x 170mm high to meeting/dining room (refer Detail 09 of Drawing 336) | m | 13 | 232 | 3016 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-28 | Type RES-WD-02; Double wood lit cornice size 390mm wide x 120mm high to multifunction room (refer Detail 08 of Drawing 336) | m | 13 | 232 | 3016 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-29 | Type RES-WD-02; Double wood lit cornice size 390mm wide x 170mm high to multifunction room (refer Detail 09 of Drawing 336) | m | 13 | 232 | 3016 |  | 0 |  | 0 | 0 |  | 0 |  | 0
-30 | Type RES-WD-02; Wood lit cornice size 300mm wide x 150mm high to lift lobby (Client TBC) | m | 18 | 232 | 4176 |  | 0 |  | 0 | 0 |  | 0 |  | 0
| Total Ceiling |  |  |  | 0 |  | 2466.784 |  | 616.696 | 3083.48 |  | 0 |  | 0
| ARCHITRAVE FINISHES |  |  |  | 0
-8 | Type RES-WD-08; Wooden architrave size 1180mm wide to lift lobby (refer Drawing 308) | m | 10 | 353 | 3530 | 10 | 2824 | 10 | 706 | 3530 |  | 0 |  | 0
-9 | Type RES-WD-08; Wooden architrave size 890mm wide to corridor (refer Drawing 343) | m | 9 | 322 | 2898 | 9 | 2318.4 | 9 | 579.6 | 2898 |  | 0 |  | 0
-10 | Type RES-WD-16; Wooden architrave size 1140mm wide to lift lobby (refer Drawing 340) | m | 10 | 353 | 3530 | 10 | 2824 | 10 | 706 | 3530 |  | 0 |  | 0
| Total Architraves |  |  |  | 0 |  | 7966.4 |  | 1991.6 | 9958 |  | 0 |  | 0
| Wooden Doors - Including subframes |  |  |  | 0
-11 | Single leaf storage door overall size 1370 x 2215mm high (refer Dwg. 304) Frame: WD-02 / Shutter: WD-06 | No | 1 | 2023 | 2023 |  | 0 | 1 | 404.6 | 404.6 |  | 0 |  | 0
-12 | Double leaf electromagnetic lift lobby door overall size 2700 x 2400mm high Frame/Shutter: WD-06 - 60Mins FR - Electromagnetic lock / Ironmongeries are excluded | No | 1 | 5398 | 5398 | 1 | 4318.4 | 1 | 1079.6 | 5398 |  | 0 |  | 0
-13 | Single leaf men's changing room main door overall size 900 x 2400mm high (refer Drawing 314) (Frame/Shutter: WD-08 with metal casing | No | 1 | 2234 | 2234 | 1 | 1787.2 | 1 | 446.8 | 2234 |  | 0 |  | 0
-14 | Single leaf women's changing room main door overall size 900 x 2400mm high (refer Drawing 309) - (Frame/Shutter: WD-08 with metal casing | No | 1 | 2234 | 2234 | 1 | 1787.2 | 1 | 446.8 | 2234 |  | 0 |  | 0
-15 | Single leaf men's changing room doors overall size 950 x 2400mm high (refer Drawing 309) (Frame/Shutter: WD-08 with metal casing- | No | 4 | 2234 | 8936 | 4 | 7148.8 | 4 | 1787.2 | 8936 | 4 | 7148.8 |  | 0
-16 | Single leaf women's changing room doors overall size 900 x 2400mm high (refer Drawing 320) Frame/Shutter: WD-07 | No | 4 | 1826 | 7304 | 4 | 5843.2 | 4 | 1460.8 | 7304 | 4 | 5843.2 |  | 0
-17 | Double leaf lift lobby pivot door overall size 3200 x 3470mm high (refer Drawing 307 and 308) Frame/Shutter: WD-16 - 60Mins FR | No | 1 | 5585 | 5585 | 1 | 4468 | 1 | 1117 | 5585 |  | 0 |  | 0
-18 | Double leaf fitness room pivot door overall size 1790 x 3450mm high with finish Type RES-WD-16 (refer Drawing 323 and 324) Frame/Shutter: WD-16 | No | 1 | 3256 | 3256 | 1 | 2604.8 | 1 | 651.2 | 3256 |  | 0 |  | 0
-19 | Double leaf yoga room pivot door overall size 1900 x 3450mm high with finish Type RES-WD-16 (refer Drawing 330 and 331) Frame: WD-15 / Shutter: WD-16 | No | 1 | 3256 | 3256 | 1 | 2604.8 | 1 | 651.2 | 3256 |  | 0 |  | 0
-20 | Single leaf storage/cloakroom door overall size 850 x 2400mm high (refer Drawing 359) - Frame / Shutter: WD-07 on one side & WC-02 on the other side with Metal Trim - | No | 2 | 1826 | 3652 | 2 | 2921.6 | 2 | 730.4 | 3652 | 2 | 2921.6 |  | 0
-21 | Single leaf men's restrooms door overall size 950 x 2900mm high (refer Drawing 353) - Frame / Shutter: WD-07 on one side & PT-03 on the other side with Metal Casing | No | 4 | 2237 | 8948 | 4 | 7158.4 | 4 | 1789.6 | 8948 |  | 0 |  | 0
-22 | Single leaf women's restrooms door overall size 950 x 2900mm high (refer Drawing 353) -- Frame / Shutter: WD-07 on one side & PT-03 on the other side with Metal Casing | No | 4 | 2237 | 8948 | 4 | 7158.4 | 4 | 1789.6 | 8948 |  | 0 |  | 0
-23 | Double leaf corridor door overall size 1700 x 2400mm high w/ finish Type RES-WD-16 (refer Drawing 341) Frame/Shutter: WD-16 | No | 1 | 3256 | 3256 | 1 | 2604.8 | 1 | 651.2 | 3256 |  | 0 |  | 0
-24 | Double leaf corridor door overall size 2050 x 3470mm high with finish Type RES-WD-16 (refer Drawing 343 and 345) Frame/Shutter: WD-16 | No | 1 | 3351 | 3351 | 1 | 2680.8 | 1 | 670.2 | 3351 |  | 0 |  | 0
-25 | Double leaf lift lobby pivot door overall size 3200 x 3470mm high with finish Type RES-WD-16 (refer Drawing 339 and 340) Frame/Shutter: WD-16 - 60Mins FR | No | 1 | 5585 | 5585 | 1 | 4468 | 1 | 1117 | 5585 |  | 0 |  | 0
-26 | Double leaf meeting/dining room pivot door overall size 3700 x 3460mm high with finish Type RES-WD-16 (refer Drawing 346 to 348) Frame/Shutter: WD-16 | No | 1 | 3637 | 3637 | 1 | 2909.6 | 1 | 727.4 | 3637 |  | 0 |  | 0
-27 | Double leaf mulfunction room pivot door overall size 3700 x 3470mm high (refer Drawing 346) Frame/Shutter: WD-16 | No | 1 | 3637 | 3637 | 1 | 2909.6 | 1 | 727.4 | 3637 |  | 0 |  | 0
| Total Doors |  |  |  | 0 |  | 63373.6 |  | 16248 | 79621.6 |  | 15913.6 |  | 0
| JOINERY WORKS |  |  |  | 0
-28 | Concierge station; overall size 1370mm (L) x 720mm (W) x 2215mm (H) (refer Drawing 303) | No | 1 | 2681 | 2681 |  | 0 | 1 | 536.2 | 536.2 |  |  |  | 0
-29 | Concierge desk; overall size 3000mm (L) x 600mm (W) x 1100mm (H) (refer Drawing 302) | No | 1 | 8042 | 8042 | 1 | 6433.6 | 1 | 1608.4 | 8042 | 1 | 5790.24 |  | 0
-30 | Welcome desk; overall size 1300mm (L) x 500mm (W) x 1100mm (H) (refer Drawing 303 to 305) | No | 1 | 3351 | 3351 | 1 | 2680.8 | 1 | 670.2 | 3351 |  | 0 |  | 0
-31 | Refreshment cabinet; overall size 2205mm (L) x 505mm (W) x 1150mm (H) to fitness room (refer Drawing 326 and 327) | No | 1 | 5362 | 5362 | 1 | 4289.6 | 1 | 1072.4 | 5362 | 1 | 3860.64 |  | 0
-32 | Storage cabinet; overall size 2725mm (L) x 600mm (W) x 2400mm (H) to storage/cloakrooms | No | 2 | 5172 | 10344 | 2 | 8275.2 | 2 | 2068.8 | 10344 | 2 | 7447.68 |  | 0
-33 | Meeting room cupboard; overall size 8310mm (L) x varies width x 3600mm (H) including fixed panels (refer Drawing 349 to 351) | No | 1 | 17202 | 17202 | 1 | 13761.6 | 1 | 3440.4 | 17202 |  | 0 |  | 0
-34 | Multifunction room cupboard; overall size 8150mm (L) x varies width x 3600mm (H) including fixed panels (refer Drawing 350 to 352) | No | 1 | 17202 | 17202 | 1 | 13761.6 | 1 | 3440.4 | 17202 |  | 0 |  | 0
-35 | Cupboard including; overall size 1185mm (L) x 670mm (W) x 2200mm (H) at fitness room (refer Drawing 328) | No | 1 | 1340 | 1340 | 1 | 1072 | 1 | 268 | 1340 | 1 | 964.8 |  | 0
-36 | Yoga props cupboard; overall size 4600mm (L) x 780mm (W) x 2200mm (H) (refer Drawing 332 to 335) | No | 1 | 5362 | 5362 | 1 | 4289.6 | 1 | 1072.4 | 5362 | 1 | 3860.64 |  | 0
-37 | Lockers including underlit bench; overall size 1105mm (L) x 390 / 500mm (W) x 500 / 3590mm (H) including fixed panel above to men's changing room (refer Drawing 321) | No | 1 | 3128 | 3128 | 1 | 2502.4 | 1 | 625.6 | 3128 | 1 | 2252.16 |  | 0
-38 | Lockers including underlit bench; overall size 1105mm (L) x 390 / 500mm (W) x 500 / 3590mm (H) including fixed panel above to women's changing room (refer Drawing 321) | No | 1 | 3128 | 3128 | 1 | 2502.4 | 1 | 625.6 | 3128 | 1 | 2252.16 |  | 0
| Total Joinery | [5 empty] | 59568.8 |  | 15428.4 | 74997.2 |  | 26428.32 |  | 0
[7 empty] | 133375.584 |  | 43959.496 | 177335.08 |  | 42341.92 |  | 5306.4
| Cumulative Workdone | [5 empty] | 47648.32
| Previous Certified | [5 empty] | 28243.2
| Cumulative Workdone | [5 empty] | 19405.12
| Historic Debt | [5 empty] | 102424
150072.32
Note on Q12: Himal Kosala: 90% only until WIR raise and approve
Note on Q13: Himal Kosala: 90% only until WIR raise and approve
Note on Q14: Himal Kosala: 90% only until WIR raise and approve
Note on Q15: Himal Kosala: 90% only until WIR raise and approve
Note on N71: Himal Kosala: 90% until MIR apprv
Note on N73: Himal Kosala: 90% until MIR apprv
Note on N74: Himal Kosala: 90% until MIR apprv
Note on N77: Himal Kosala: 90% until MIR apprv
Note on N78: Himal Kosala: 90% until MIR apprv
Note on N79: Himal Kosala: 90% until MIR apprv
Note on N80: Himal Kosala: 90% until MIR apprv