## BOQ (hidden)
INVENTURE METAL PRODUCTS INDUSTRIES LLC
MAIN CONTRACTOR : KHANSAHEEB
PROJECT : DORCHESTER
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO:6 - BALANCE BALUSTRADE WORKS
AS PER LPO
Items | Description | Qty | Unit | Rate | Amount | Previous | Present | Cumulative | %
Balance balustrade work has been categories as type 1,2,3,4 amd 5 in acordance with the avaialble material on site contractor should price for verify free of defects,collect,store,handling,transporting(within the site)installation such free issued material
Type 1-Complete supply and installation by contractor
Supply & installation of 1200mm high Glass balustrade comprising with bottom rail,glass panels and stainless steel top U channel fixed to the concerte slab,Glass panels to be furnished 10+152.10mm Low iron clear Heat Strengthend Laminated Glass with polished Edge to be fixed with 15mm glass to glass clear gap,all as per the drawing and specification.
A | Glass Balstrade Type EWS - 102 | 130 | m | 1600 | 208000 | 628640 | 32926.4 | 661566.4 | 318.1%
B | Ditto Curved | 20 | m | 2600 | 52000 | 795166.58 | 8185.45 | 803352.03 | 1545%
Type 2 - Glass and Bottom rails supplied by Employer
Collect free issued glass panles,bottom rails and installation of thr compleate balustrade as stated above(under type-1).Top Channel and all other neessary fittings,fixtures and accessories shall be supply and installed by the contractor
C | Glass Balustrade type EWS - 102 | 575 | m | 300 | 172500 | 164255.55 | 0 | 164255.55 | 95.22%
D | Ditto, Curved | 25 | m | 400 | 10000 | 28100 | 0 | 28100 | 281%
Type 3- Glass Supplied by Employer
Collect free issued glass panels and installation of the compleate balustrade as stated above (under type-1).bottom reil,stainless steel top channel and all other necessary fitting,fixtures and accessories shall be supply and installed by the contractor.
E | Glass Balustrade Type EWS -102 | 350 | m | 950 | 332500 | 45837.5 | - | 45837.5 | 13.79%
F | Ditto, Curved | 90 | m | 1100 | 99000
Type 4-Top Channel Supply installation
Supply and installation of stainless steel top U channels to installed glass balustrde including welded joints
G | Balustrade top channel supply - Stright | 110 | m | 150 | 16500 | 21765 | 669.375 | 22434.375 | 136%
H | Ditto , Curved | 15 | m | 200 | 3000
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.1 - STAR RAILS AND PROTECTION RAILS
Type 5 -Top Channeld installation only
Collect free issued top channel and installation(Including welded joints) to installed glass balustrade
J | Top U Channel - Stright | 90 | m | 75 | 6750
STAIR RAILS
Supply & Installation of 1200mm high glass balustarde comprising with bottom rail,glass panles and stainless steel top U Channel fixed to the concrete slab,glass panles to be furnished 10+1.2+10mm Low-Iron Clear hear Strengthened Laminated Glass with Polished edge and to be fixed with 15mm glass clear gap,all as per the drawing A-4123 abd A-4124 Specifications.
Plaza Stair Handrail
A | Glass Balustrade Type EWS - 10 & Handrail | 45 | m | 1750 | 78750 |  | 28350 | 28350 | 36%
B | Ditto , Curved | 10 | m | 2750 | 27500
Retails Stair Handrail
C | Glass Balustrade Type EWS - 102 & Handrail | 30 | m | 1750 | 52500 | 13125 | 7087.5 | 20212.5 | 38.5%
D | Ditto,Curved | 5 | m | 2750 | 13750 | 3437.5 | 1856.25 | 5293.75 | 38.5%
WALL PROTECTION RAILS
Protection gurad/rails fixed to walk in kitchen and housekeeping area compleate with necessary fittings fixing accessories in accordance with the drawing and the specification
E | Supply and fixed of WP1:-1.5mm thick stainless steel 30 grad brush finish r Size: - 150mm high *20mm depth,2mm thick bracket,as per the typical detail drawing,1614.TYP.100 details 'C'. | 410 | m |  | Excluded
CORNER GUARDS
F | Supply and fixed of corner guard -1.5mm thick stainless steel 304 grade brush finish angle with necessary male female brackets.Stainless steel screws and Epoxy Grout Size-50*50*1800mm high
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.3 - GLASS/ALUMINIUM DOORS AND WINDOWS
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications
A | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB243 and LB244) | 2 | Nr | 42750 | 85500
B | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB1129 and LB1130) | 2 | Nr | 42750 | 85500
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications.
Basement Level 01
C | Type-01 Size: 1200*1500mm | 1 | Nr |  | Excluded
D | Type-01 Size: 1500*1500mm | 4 | Nr |  | Excluded
E | Type-02 Size: 3250*1500mm | 1 | Nr |  | Excluded
F | Type-03 Size: 1250*1500mm | 2 | Nr |  | Excluded
G | Type-03 Size: 2150*1500mm | 1 | Nr |  | Excluded
H | Type-04 Size: 1500*1200mm | 1 | Nr |  | Excluded
J | Type-04 Size: 2100*1200mm | 1 | Nr |  | Excluded
LOUVERS
Louver compleate with frames,sub frames,transoms,stops,ironmoongeries,insulation,protective and decorative coatings all in accordance with the drawing and specifications
K | LW - 6 Size 6500*4200mm | 1 | Nr | 30030 | 30030 | 30030 | 0 | 30030
L | LW-7 Size: 1150*4200mm | 1 | Nr | 5313 | 5313 | 5313 | 0 | 5313
M | LW-8 Size 6000*2000mm | 1 | Nr | 13200 | 13200 | 13200 | 0 | 13200
N | LW-9 Size 6000*4000mm | 1 | Nr | 26400 | 26400 | 26400 | 0 | 26400
P | LW-10 Size:3000*4000mm | 1 | Nr | 13200 | 13200 | 13200 | 0 | 13200
[5 empty] | 1331893 | 1788470.13 | 79074.975 | 1867545.105
0

## QUANTITY DETAILS (hidden)
INVENTURE METAL PRODUCTS INDUSTRIES LLC
MAIN CONTRACTOR : KHANSAHEEB
PROJECT : DORCHESTER
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO1 - BALANCE BALUSTRADE WORKS
|  | AS PER LPO |  |  |  |  | AS PER SITE
[6 empty] | MATERIAL DELIVERY |  |  |  |  | INSTALLATION
[6 empty] | MATERIAL DELIVERED | MATERIAL DELIVERY |  |  | MATERIAL | INSTALLATION | INSTALLATION |  |  | INSTALLATION | TOTAL
Items | Description | Qty | Unit | Rate | Amount | % | Previous | Present | To Date | AMOUNT | % | Previous | Present | To Date | AMOUNT
Balance balustrade work has been categories as type 1,2,3,4 amd 5 in acordance with the avaialble material on site contractor should price for verify free of defects,collect,store,handling,transporting(within the site)installation such free issued material
Type 1-Complete supply and installation by contractor
Supply & installation of 1200mm high Glass balustrade comprising with bottom rail,glass panels and stainless steel top U channel fixed to the concerte slab,Glass panels to be furnished 10+152.10mm Low iron clear Heat Strengthend Laminated Glass with polished Edge to be fixed with 15mm glass to glass clear gap,all as per the drawing and specification.
A | Glass Balstrade Type EWS - 102 | 130 | m | 1600 | 208000
| Bottom Channel | 40% |  |  |  | 25% | 420 | 0 | 420 | 168000 | 15% | 316 | 29 | 345 | 82800 | 250800
| Glass | 50% |  |  |  | 35% | 283 | 229 | 512 | 286720 | 15% |  | 80 | 80 | 19200 | 305920
| Top Rail | 10% |  |  |  | 5% | 500 | 512 | 1012 | 80960 | 5% | 448 | 190.178 | 638.178 | 51054.24 | 132014.24
B | Ditto Curved | 20 | m | 2600 | 52000
| Bottom Channel | 40% |  |  |  | 25% | 184 | 44.57 | 228.57 | 148570.5 | 15% | 184 | 0 | 184 | 71760 | 220330.5
| Glass | 50% |  |  |  | 35% | 190 | 73.16 | 263.16 | 239475.6 | 15% |  | 238 | 238 | 92820 | 332295.6
| Top Rail | 10% |  |  |  | 5% | 66 | 102 | 168 | 21840 | 5% |  | 11 | 11 | 1430 | 23270
Type 2 - Glass and Bottom rails supplied by Employer
Collect free issued glass panles,bottom rails and installation of thr compleate balustrade as stated above(under type-1).Top Channel and all other neessary fittings,fixtures and accessories shall be supply and installed by the contractor
C | Glass Balustrade type EWS - 102 | 575 | m | 300 | 172500
| Bottom Channel | 40% | [8 empty] | 40% | 402 | 0 | 402 | 48240 | 48240
| Glass | 50% | [8 empty] | 50% | 640 | 0 | 640 | 96000 | 96000
| Top Rail | 10% | [8 empty] | 10% | 199 | 0 | 199 | 5970 | 5970
D | Ditto, Curved | 25 | m | 400 | 10000
| Bottom Channel | [9 empty] | 40% | 138 | 0 | 138 | 22080 | 22080
| Glass | [9 empty] | 50% | 17.38 | 0 | 17.38 | 3476 | 3476
| Top Rail | [9 empty] | 10% | 15.1 | 0 | 15.1 | 604 | 604
Type 3- Glass Supplied by Employer
Collect free issued glass panels and installation of the compleate balustrade as stated above (under type-1).bottom reil,stainless steel top channel and all other necessary fitting,fixtures and accessories shall be supply and installed by the contractor.
E | Glass Balustrade Type EWS -102 | 350 | m | 950 | 332500
F | Ditto, Curved | 90 | m | 1100 | 99000
Type 4-Top Channel Supply installation
Supply and installation of stainless steel top U channels to installed glass balustrde including welded joints
G | Balustrade top channel supply - Stright | 110 | m | 150 | 16500
H | Ditto , Curved | 15 | m | 200 | 3000
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.1 - STAR RAILS AND PROTECTION RAILS
Type 5 -Top Channeld installation only
Collect free issued top channel and installation(Including welded joints) to installed glass balustrade
J | Top U Channel - Stright | 90 | m | 75 | 6750
STAIR RAILS
Supply & Installation of 1200mm high glass balustarde comprising with bottom rail,glass panles and stainless steel top U Channel fixed to the concrete slab,glass panles to be furnished 10+1.2+10mm Low-Iron Clear hear Strengthened Laminated Glass with Polished edge and to be fixed with 15mm glass clear gap,all as per the drawing A-4123 abd A-4124 Specifications.
Plaza Stair Handrail
A | Glass Balustrade Type EWS - 10 & Handrail | 45 | m | 1750 | 78750
B | Ditto , Curved | 10 | m | 2750 | 27500
Retails Stair Handrail
C | Glass Balustrade Type EWS - 102 & Handrail | 30 | m | 1750 | 52500
D | Ditto,Curved | 5 | m | 2750 | 13750
WALL PROTECTION RAILS
Protection gurad/rails fixed to walk in kitchen and housekeeping area compleate with necessary fittings fixing accessories in accordance with the drawing and the specification
E | Supply and fixed of WP1:-1.5mm thick stainless steel 30 grad brush finish r Size: - 150mm high *20mm depth,2mm thick bracket,as per the typical detail drawing,1614.TYP.100 details 'C'. | 410 | m |  | Excluded
CORNER GUARDS
F | Supply and fixed of corner guard -1.5mm thick stainless steel 304 grade brush finish angle with necessary male female brackets.Stainless steel screws and Epoxy Grout Size-50*50*1800mm high
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.3 - GLASS/ALUMINIUM DOORS AND WINDOWS
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications
A | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB243 and LB244) | 2 | Nr | 42750 | 85500
B | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB1129 and LB1130) | 2 | Nr | 42750 | 85500
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications.
Basement Level 01
C | Type-01 Size: 1200*1500mm | 1 | Nr |  | Excluded
D | Type-01 Size: 1500*1500mm | 4 | Nr |  | Excluded
E | Type-02 Size: 3250*1500mm | 1 | Nr |  | Excluded
F | Type-03 Size: 1250*1500mm | 2 | Nr |  | Excluded
G | Type-03 Size: 2150*1500mm | 1 | Nr |  | Excluded
H | Type-04 Size: 1500*1200mm | 1 | Nr |  | Excluded
J | Type-04 Size: 2100*1200mm | 1 | Nr |  | Excluded
LOUVERS
Louver compleate with frames,sub frames,transoms,stops,ironmoongeries,insulation,protective and decorative coatings all in accordance with the drawing and specifications
K | LW - 6 Size 6500*4200mm | 1 | Nr | 30030 | 30030 | 65% | 1 | 0 | 1 | 19519.5 | 35% | 1 | 0 | 1 | 10510.5 | 30030 | 6.5 | 4.2 | 27.3
L | LW-7 Size: 1150*4200mm | 1 | Nr | 5313 | 5313 | 65% | 1 | 0 | 1 | 3453.45 | 35% | 1 | 0 | 1 | 1859.55 | 5313 | 1.15 | 4.2 | 4.83
M | LW-8 Size 6000*2000mm | 1 | Nr | 13200 | 13200 | 65% | 1 | 0 | 1 | 8580 | 35% | 1 | 0 | 1 | 4620 | 13200 | 6 | 2 | 12
N | LW-9 Size 6000*4000mm | 1 | Nr | 26400 | 26400 | 65% | 1 | 0 | 1 | 17160 | 35% | 1 | 0 | 1 | 9240 | 26400 | 6 | 4 | 24
P | LW-10 Size:3000*4000mm | 1 | Nr | 13200 | 13200 | [11 empty] | 3 | 4 | 12
[5 empty] | 1331893 |  |  |  |  | 994279.05 |  |  |  |  | 521664.29 | 1515943.34
0

## QUANTITY BREAK UP (hidden)
A | Glass Balstrade Type EWS - 102 | [5 empty] | B | Ditto Curved | [5 empty] | C | Glass Balustrade type EWS - 102 | [5 empty] | D | Ditto Curved
BOQ QTY | 130 | [5 empty] | BOQ QTY | 20 | [5 empty] | BOQ QTY | 575 | [5 empty] | BOQ QTY | 25
| QTY |  |  | DRAWING REFERENCE |  |  |  | QTY |  |  | DRAWING REFERENCE |  |  |  | QTY |  |  | DRAWING REFERENCE |  |  |  | QTY |  |  | DRAWING REFERENCE
Floor | Bottom Channel | Glass | Toprail | Bottom Channel | Glass | Toprail | Floor | Bottom Channel | Glass | Toprail | Bottom Channel | Glass | Toprail | Floor | Bottom Channel | Glass | Toprail | Bottom Channel | Glass | Toprail | Floor | Bottom Channel | Glass | Toprail | Bottom Channel | Glass | Toprail
BASEMENT 3 | [6 empty] | BASEMENT 3 | [6 empty] | BASEMENT 3 | [6 empty] | BASEMENT 3
BASEMENT 2 | [6 empty] | BASEMENT 2 | [6 empty] | BASEMENT 2 | [6 empty] | BASEMENT 2
BASEMENT 1 | [6 empty] | BASEMENT 1 | [6 empty] | BASEMENT 1 | [6 empty] | BASEMENT 1
GF | [6 empty] | GF | [6 empty] | GF | [6 empty] | GF
1st Floor | [6 empty] | 1st Floor | [6 empty] | 1st Floor | [6 empty] | 1st Floor
2nd Floor | [6 empty] | 2nd Floor | [6 empty] | 2nd Floor | [6 empty] | 2nd Floor
3rd Floor | [6 empty] | 3rd Floor | [6 empty] | 3rd Floor | [6 empty] | 3rd Floor
4th Floor | [6 empty] | 4th Floor | [6 empty] | 4th Floor | [6 empty] | 4th Floor
5th Floor | [6 empty] | 5th Floor | [6 empty] | 5th Floor | [6 empty] | 5th Floor
6th Floor | [6 empty] | 6th Floor | [6 empty] | 6th Floor | [6 empty] | 6th Floor
7th Floor | [6 empty] | 7th Floor | [6 empty] | 7th Floor | [6 empty] | 7th Floor
8th Floor | [6 empty] | 8th Floor | [6 empty] | 8th Floor | [6 empty] | 8th Floor
9th Floor | [6 empty] | 9th Floor | [6 empty] | 9th Floor | [6 empty] | 9th Floor
10th Floor | [6 empty] | 10th Floor | [6 empty] | 10th Floor | [6 empty] | 10th Floor
11th Floor | [6 empty] | 11th Floor | [6 empty] | 11th Floor | [6 empty] | 11th Floor
12th Floor | [6 empty] | 12th Floor | [6 empty] | 12th Floor | [6 empty] | 12th Floor
13th Floor | [6 empty] | 13th Floor | [6 empty] | 13th Floor | [6 empty] | 13th Floor
14th Floor | [6 empty] | 14th Floor | [6 empty] | 14th Floor | [6 empty] | 14th Floor
15th Floor | [6 empty] | 15th Floor | [6 empty] | 15th Floor | [6 empty] | 15th Floor
16th Floor | [6 empty] | 16th Floor | [6 empty] | 16th Floor | [6 empty] | 16th Floor
17th Floor | [6 empty] | 17th Floor | [6 empty] | 17th Floor | [6 empty] | 17th Floor
18th Floor | [6 empty] | 18th Floor | [6 empty] | 18th Floor | [6 empty] | 18th Floor
19th Floor | [6 empty] | 19th Floor | [6 empty] | 19th Floor | [6 empty] | 19th Floor
20th Floor | [6 empty] | 20th Floor | [6 empty] | 20th Floor | [6 empty] | 20th Floor
Total | 0 | 0 | 0 |  |  |  | Total | 0 | 0 | 0 |  |  |  | Total | 0 | 0 | 0 |  |  |  | Total | 0 | 0 | 0

## Summary
Inventure Progress Assessment
No | Description | Amount
|  | Previous | This Month | Cumulative
| Original Scope | 1790234.58 | 77310.525 | 1867545.105
| Variation | 178335.2 | 86814.8 | 265150
| Total | 1968569.78 | 164125.325 | 2132695.105
| Advance | 66594.65 | 0 | 66594.65
| Advance Recovery | -66594.65 | 0 | -66594.65
|  | 1968569.78 | 164125.325 | 2132695.105

## QUANTITY DETAILS (2)
INVENTURE METAL PRODUCTS INDUSTRIES LLC
MAIN CONTRACTOR : KHANSAHEEB
PROJECT : DORCHESTER
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO:6 - BALANCE BALUSTRADE WORKS
|  | AS PER LPO |  |  |  |  | AS PER SITE
[6 empty] | MATERIAL DELIVERY |  |  |  |  | INSTALLATION
[6 empty] | MATERIAL DELIVERED | MATERIAL DELIVERY |  |  | MATERIAL | INSTALLATION | INSTALLATION |  |  | INSTALLATION | TOTAL
Items | Description | Qty | Unit | Rate | Amount | % | Previous | Present | To Date | AMOUNT | % | Previous | Present | To Date | AMOUNT
Balance balustrade work has been categories as type 1,2,3,4 amd 5 in acordance with the avaialble material on site contractor should price for verify free of defects,collect,store,handling,transporting(within the site)installation such free issued material
Type 1-Complete supply and installation by contractor
667
Supply & installation of 1200mm high Glass balustrade comprising with bottom rail,glass panels and stainless steel top U channel fixed to the concerte slab,Glass panels to be furnished 10+152.10mm Low iron clear Heat Strengthend Laminated Glass with polished Edge to be fixed with 15mm glass to glass clear gap,all as per the drawing and specification.
A | Glass Balstrade Type EWS - 102 | 130 | m | 1600 | 208000
| Bottom Channel | 40% |  |  |  | 25% | 420 |  | 420 | 168000 | 15% | 390 | 9 | 399 | 95760 | 263760 | 168000 | 0 | 82800 | 12960 |  |  | 9
| Glass | 50% |  |  |  | 35% | 420 | 16 | 436 | 244160 | 15% | 202 | 90.86 | 292.86 | 70286.4 | 314446.4 | 286720 | -42560 | 19200 | 51086.4 |  |  | 92.6
| Top Rail | 10% |  |  |  | 5% | 841 |  | 841 | 67280 | 5% | 201 | 0 | 201 | 16080 | 83360 | 80960 | -13680 | 51054.24 | -34974.24 |  |  | 0
B | Ditto Curved | 20 | m | 2600 | 52000 | [12 empty] | 0 |  | 0
| Bottom Channel | 40% |  |  |  | 25% | 314.535 | 0 | 314.535 | 204447.75 | 15% | 201.238 | 0 | 201.238 | 78482.82 | 282930.57 | 148570.5 | 55877.25 | 71760 | 6722.82
| Glass | 50% |  |  |  | 35% | 358.751 | 6.22 | 364.971 | 332123.61 | 15% | 317.34 | 6.475 | 323.815 | 126287.85 | 458411.46 | 239475.6 | 92648.01 | 92820 | 33467.85 |  |  | 6.475
| Top Rail | 10% |  |  |  | 5% | 221 | 0 | 221 | 28730 | 5% | 256 | 0 | 256 | 33280 | 62010 | 21840 | 6890 | 1430 | 31850
| Type 2 - Glass and Bottom rails supplied by Employer | [19 empty] | 454.936
[21 empty] | 470.936 | 178.076
| Collect free issued glass panles,bottom rails and installation of thr compleate balustrade as stated above(under type-1).Top Channel and all other neessary fittings,fixtures and accessories shall be supply and installed by the contractor | [15 empty] | 122.577 | 143.14 | 120 |  | -34.936
-41.156
C | Glass Balustrade type EWS - 102 | 575 | m | 300 | 172500
| Bottom Channel | 40% | [8 empty] | 40% | 402 | 0 | 402 | 48240 | 48240 |  |  | 48240 | 0
| Glass | 50% | [8 empty] | 50% | 646.237 | 0 | 646.237 | 96935.55 | 96935.55 |  | 23.14 | 96000 | 935.55 |  |  | 226.237
| Top Rail | 10% | [8 empty] | 10% | 636 | 0 | 636 | 19080 | 19080 |  |  | 5970 | 13110
D | Ditto, Curved | 25 | m | 400 | 10000 | [14 empty] | 0
| Bottom Channel | [9 empty] | 40% | 138 | 0 | 138 | 22080 | 22080 |  |  | 22080 | 0
| Glass | [9 empty] | 50% | 27.08 | 0 | 27.08 | 5416 | 5416 |  |  | 3476 | 1940
| Top Rail | [9 empty] | 10% | 15.1 | 0 | 15.1 | 604 | 604 |  |  | 604 | 0
Type 3- Glass Supplied by Employer
| Collect free issued glass panels and installation of the compleate balustrade as stated above (under type-1).bottom reil,stainless steel top channel and all other necessary fitting,fixtures and accessories shall be supply and installed by the contractor. | [16 empty] | 205
E | Glass Balustrade Type EWS -102 | 350 | m | 950 | 332500
| Bottom Channel | 40% |  |  |  | 25% | 193 |  | 193 | 45837.5 | 15% |  |  |  |  | 45837.5
| Glass | 50% |  |  |  | 35% |  |  |  |  | 15% |  |  |  |  | 0
| Top Rail | 10% |  |  |  | 5% |  |  |  |  | 5% |  |  |  |  | 0
F | Ditto, Curved | 90 | m | 1100 | 99000
Bottom Channel
Glass
| Top Rail | [21 empty] | 56525
Type 4-Top Channel Supply installation
Supply and installation of stainless steel top U channels to installed glass balustrde including welded joints
G | Balustrade top channel supply - Stright | 110 | m | 150 | 16500 | 65% | 171 |  |  | 16672.5 | 35% | 97 | 12.75 | 109.75 | 5761.875 | 22434.375 | [6 empty] | 669.375
H | Ditto , Curved | 15 | m | 200 | 3000 | 65% |  |  |  |  | 35%
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.1 - STAR RAILS AND PROTECTION RAILS
Type 5 -Top Channeld installation only
Collect free issued top channel and installation(Including welded joints) to installed glass balustrade
J | Top U Channel - Stright | 90 | m | 75 | 6750
STAIR RAILS
Supply & Installation of 1200mm high glass balustarde comprising with bottom rail,glass panles and stainless steel top U Channel fixed to the concrete slab,glass panles to be furnished 10+1.2+10mm Low-Iron Clear hear Strengthened Laminated Glass with Polished edge and to be fixed with 15mm glass clear gap,all as per the drawing A-4123 abd A-4124 Specifications.
Plaza Stair Handrail
A | Glass Balustrade Type EWS - 10 & Handrail | 45 | m | 1750 | 78750 | 25% |  | 40.5 | 40.5 | 17718.75 | 15% |  | 40.5 | 40.5 | 10631.25 | 28350 | [6 empty] | 24806.25
[6 empty] | 35% |  |  |  |  | 15%
[6 empty] | 5% |  |  |  |  | 5%
B | Ditto , Curved | 10 | m | 2750 | 27500
[6 empty] | 25% |  |  |  |  | 15%
[6 empty] | 35% |  |  |  |  | 15%
[6 empty] | 5% |  |  |  |  | 5%
Retails Stair Handrail
C | Glass Balustrade Type EWS - 102 & Handrail | 30 | m | 1750 | 52500
| Bottom Channel |  |  |  |  | 25% | 30 | 0 | 30 | 13125 | 15% |  | 27 | 27 | 7087.5 | 20212.5 | [6 empty] | 7875
| Glass |  |  |  |  | 35% |  |  |  |  | 15%
| Top Rail |  |  |  |  | 5% |  |  |  |  | 5%
D | Ditto,Curved | 5 | m | 2750 | 13750
| Bottom Channel | 40% |  |  |  | 25% | 5 | 0 | 5 | 3437.5 | 15% |  | 4.5 | 4.5 | 1856.25 | 5293.75 | [6 empty] | 2062.5
| Glass | 50% |  |  |  | 35% |  |  |  |  | 15%
| Top Rail | 10% |  |  |  | 5% |  |  |  |  | 5%
WALL PROTECTION RAILS
Protection gurad/rails fixed to walk in kitchen and housekeeping area compleate with necessary fittings fixing accessories in accordance with the drawing and the specification
E | Supply and fixed of WP1:-1.5mm thick stainless steel 30 grad brush finish r Size: - 150mm high *20mm depth,2mm thick bracket,as per the typical detail drawing,1614.TYP.100 details 'C'. | 410 | m |  | Excluded
CORNER GUARDS
F | Supply and fixed of corner guard -1.5mm thick stainless steel 304 grade brush finish angle with necessary male female brackets.Stainless steel screws and Epoxy Grout Size-50*50*1800mm high
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.3 - GLASS/ALUMINIUM DOORS AND WINDOWS
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications
A | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB243 and LB244) | 2 | Nr | 42750 | 85500
B | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB1129 and LB1130) | 2 | Nr | 42750 | 85500
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications.
Basement Level 01
C | Type-01 Size: 1200*1500mm | 1 | Nr |  | Excluded
D | Type-01 Size: 1500*1500mm | 4 | Nr |  | Excluded
E | Type-02 Size: 3250*1500mm | 1 | Nr |  | Excluded
F | Type-03 Size: 1250*1500mm | 2 | Nr |  | Excluded
G | Type-03 Size: 2150*1500mm | 1 | Nr |  | Excluded
H | Type-04 Size: 1500*1200mm | 1 | Nr |  | Excluded
J | Type-04 Size: 2100*1200mm | 1 | Nr |  | Excluded
LOUVERS
Louver compleate with frames,sub frames,transoms,stops,ironmoongeries,insulation,protective and decorative coatings all in accordance with the drawing and specifications
K | LW - 6 Size 6500*4200mm | 1 | Nr | 30030 | 30030 | 65% | 1 | 0 | 1 | 19519.5 | 35% | 1 | 0 | 1 | 10510.5 | 30030 | 6.5 | 4.2 | 27.3
L | LW-7 Size: 1150*4200mm | 1 | Nr | 5313 | 5313 | 65% | 1 | 0 | 1 | 3453.45 | 35% | 1 | 0 | 1 | 1859.55 | 5313 | 1.15 | 4.2 | 4.83
M | LW-8 Size 6000*2000mm | 1 | Nr | 13200 | 13200 | 65% | 1 | 0 | 1 | 8580 | 35% | 1 | 0 | 1 | 4620 | 13200 | 6 | 2 | 12
N | LW-9 Size 6000*4000mm | 1 | Nr | 26400 | 26400 | 65% | 1 | 0 | 1 | 17160 | 35% | 1 | 0 | 1 | 9240 | 26400 | 6 | 4 | 24
P | LW-10 Size:3000*4000mm | 1 | Nr | 13200 | 13200 | 65% |  | 1 | 1 | 8580 | 35% | 1 |  | 1 | 4620 | 13200 | 3 | 4 | 12
[5 empty] | 1331893 |  |  |  |  | 1198825.56 |  |  |  |  | 668719.545 | 1867545.105

## VARIATION
CONTRACTOR : KHANSAHEB
PROJECT : DORCHESTER
Item No | Description | REFERENCE | SIZE |  | Qty | Unit | Rate | Amount | Previous | Present | To Date | Previous | Present | Cumulative | %
VARIATION
IMPI/DXB/13299A/2022
1 | QUOTATION FOR SHIFTING OF GLASS –E11/K128/AK/dm/090
a | Shifting of Glass from Hotel Building to allotted location |  |  |  | 43 | Nos | 120 | 5160 | 43 | 0 | 43 | 5160 | 0 | 5160 | 100%
b | Shifting of Glass from Podium to allotted location |  |  |  | 80 | Nos | 120 | 9600 | 80 | 0 | 80 | 9600 | 0 | 9600 | 100%
c | Shifting of Glass from Residence Building to allotted location |  |  |  | 67 | Nos | 120 | 8040 | 67 | 0 | 67 | 8040 | 0 | 8040 | 100%
d | Shifting of Glass from GF to allotted location |  |  |  | 45 | Nos | 120 | 5400 | 45 | 0 | 45 | 5400 | 0 | 5400 | 100%
e | Supply of Ratchet Belts to hold the glass |  |  |  | 30 | Nos | 100 | 3000 | 30 | 0 | 30 | 3000 | 0 | 3000 | 100%
f | Cleaning of Glass ( Removal of Dust/mud ) |  |  |  | 235 | Nos | 50 | 11750 | 235 | 0 | 235 | 11750 | 0 | 11750 | 100%
IMPI/DXB/13266/2022
2 | Fabrication, supply and installation of three leaf sandwich panel door non fire rated 3200 x 2000 |  | 3200 | 2000 | 4 | Nos | 8000 | 32000
IMPI/DXB/13273A/2022
3 | SUPPLY AND INSTALLATION OF ALUMINIUM LOUVER | E11/K128/AK/DM/145
a | Fabrication, supply and installation of powder coated non fire rated aluminium fix louver (L31-B1) |  |  |  | 9.4 | M2 | 1100 | 10340 | 9.4 | 0 | 9.4 | 10340 | 0 | 10340 | 100%
b | Installation charge of existing louver |  |  |  | 46.4 | M2 | 250 | 11600 | 46.4 |  | 46.4 | 11600 |  | 11600 | 100%
c | Additional bottom profile and fixing screws |  |  |  | 1 | item | 700 | 700 | 1 |  | 1 | 700 |  | 700 | 100%
IMPI/DXB/13282A/2022
4 | QUOTATION FOR SUPPLY AND INSTALLATION OF WINDOWS | E11/K128/AK/DM/114
a | Fabrication, supply and installation of fix window 900 x 900 |  |  |  | 5 | NOS | 1250 | 6250
b | Installation charge of single leaf door |  |  |  | 1 | NOS | 750 | 750
c | Installation charge of Double leaf door |  |  |  | 1 | NOS | 1500 | 1500 | 1 |  | 1 | 1500 |  | 1500 | 100%
IMPI/DXB/13296A/2022
5 | FABRICATION, SUPPLY AND INSTALLATION OF GLASS RAILING AT LVL 30 & 31
a | Fabrication, supply and installation of glass balustrade at Level 30 and 31
i) | Qty : Level 30 – 18.1Lm
ii) | Qty : Level 31 – 20.3Lm
iii) | Total Qty: 38.4Lm |  |  |  | 38.4 | Lm | 1600 | 61440
| IMPI/DXB/13292/2022 | E11/K128/AK/DM/113
6 | Fabrication,Supply and Installation of Fix Window |  | 900 | 450 | 5 | Nos | 1000 | 5000 | 5 |  | 5 | 5000 |  | 5000 | 100%
IMPI/DXB/13319/2022
7 | QUOTATION PAINTING ON EXISTING RAILING
| Cleaning of surface, Putty where required, one coat painting and protection. |  |  |  | 1 | LM | 325 | RATE ONLY
a | Floor mounted railing |  |  |  | 1 | LM | 150 | RATE ONLY
b | Wall mounted railing
8 | IMPI/DXB/13333A/2022
a | Supply and Installation of Bottom Gasket for Glass Handrail |  |  |  | 2715 | LM | 40 | 108600 | 1885 | 372 | 2257 | 75400 | 14880 | 90280 | 83.13% | 75400
b | Removal and Refixing of Existing Glass and Top rail of Balcony Handrail from Level 10 to Level 29 |  |  |  | 32 | LM | 750 | 24000 | 32 | 0 | 0 | 32250 | 0 | 32250 | 50%
9 | TOP RAIL POLISHING & Removal & Reinstatement of Glass for GRC Installation
a | Removal of Stains cleaning /Polishing of Stainless Steel Top Rail of Existing Handrail | E11-K128-JA-AK-570 |  |  |  | LM | 60 | 0 |  | 1175.5 | 0 |  | 70530 | 70530
b | Removal & reinstatement of glass for GRC installation | E11-K128-SK-AK-552 |  |  |  |  | 750 |  |  | 0 | 0 |  | 0 | 0
| VARIATION | [6 empty] | 305130 |  |  |  | 179740 | 85410 | 265150 |  | #REF!
Note on K50: Himal Kosala: no supporting for this claim

## BRACKET INSTALLATION
DORCHESTER - RESIDENTIAL,HOTEL & PODIUM - WORK COMPLETION AS PER WIR APPROOVAL- JANUARY MONTH-2023 - BRACKET INSTALLATION
SR NO | LEVEL | LOCATION | QTY (M) |  | WIR REFERANCE NO. |  |  |  | NEW | DESCRIPTON | REMARKS
|  |  | STRAIGHT | CURVE
1 | 23 | RESIDENTIAL | 9 | - | INV-AX-WR-L23-00158 |  |  |  | IMPI | BRACKET INSTALLATION | APPROOVE
2 | GF | STAIR RETAIL | 27 | 4.5 | INV-AX-WR-GF-00165 |  |  |  | IMPI | BRACKET INSTALLATION | APPROOVE
3 | GF | STAIR PLAZA | 40.5 | - | INV-AX-WR-GF-00182 |  |  |  | IMPI | BRACKET INSTALLATION | -
|  |  | 84 | 4.5
TOTAL | INSTALLATION BY IMPI AND APPROOVE |  |  |  |  | TOTAL QTY | STRAIGHT | CURVE | ALL APPROOVE
[7 empty] | 84 | 4.5
88.5
Note on D8: Himal Kosala: WIR not approved
Note on E8: Himal Kosala: WIR not approved
Note on D9: Himal Kosala: WIR not approved

## GLASS INSTALLATION
DORCHESTER - RESIDENTIAL,HOTEL & PODIUM - WORK COMPLETION AS PER WIR APPROOVAL- JANUARY MONTH-2023 - GLASS INSTALLATION
SR NO | LEVEL | LOCATION | QTY (R/M) |  | WIR REFERANCE NO. |  | NEW | DESCRIPTON | REMARKS
|  |  | STRAIGHT | CURVE
1 | 8 | HOTEL | 11.3 |  | INV-AX-WR-L08-00147 |  | IMPI | GLASS INSTALLATION | APPROOVE
2 | 2 | PODIUM | 10 |  | INV-AX-WR-L02-00151 |  | IMPI | GLASS INSTALLATION | APPROOVE
3 | 4 | PODIUM | 22 |  | INV-AX-WR-L04-00152 |  | IMPI | GLASS INSTALLATION | APPROOVE
4 | 31 | RESIDENTIAL | 20 |  | INV-AX-WR-L31-00155 |  | IMPI | GLASS INSTALLATION | APPROOVE
5 | 27 | RESIDENTIAL | 0.7 |  | INV-AX-WR-L27-00156 |  | IMPI | GLASS INSTALLATION | APPROOVE
6 | 26 | RESIDENTIAL | 2.7 |  | INV-AX-WR-L26-00157 |  | IMPI | GLASS INSTALLATION | APPROOVE
7 | 7 | HOTEL | 1.5 | 1.375 | INV-AX-WR-L07-00159 |  | IMPI | GLASS INSTALLATION | APPROOVE
8 | 4 | PODIUM |  | 5.1 | INV-AX-WR-L04-00161 |  | IMPI | GLASS INSTALLATION | APPROOVE
9 | 23 | RESIDENTIAL | 7 |  | INV-AX-WR-L23-00171 |  | IMPI | GLASS INSTALLATION | APPROOVE
10 | 23 | RESIDENTIAL | 8.64 |  | INV-AX-WR-L23-00176 |  | IMPI | GLASS INSTALLATION | APPROOVE
11 | 17 | HOTEL | 7.02 |  | INV-AX-WR-L17-00177 |  | IMPI | GLASS INSTALLATION | APPROOVE
|  |  | 90.86 | 6.475 |  |  |  |  | APPROOVE
TOTAL | INSTALLATION BY IMPI AND APPROOVE |  |  |  |  | STRAIGHT - 92.06 R/M CURVE- 6.475 R/M | ALL APPROOVE
Note on D16: Himal Kosala: WIR not approved
Note on D17: Himal Kosala: WIR not approved

## TOP RAIL INSTALLATION
DORCHESTER - RESIDENTIAL,HOTEL & PODIUM - WORK COMPLETION AS PER WIR APPROOVAL- JANUARY MONTH-2023 - TOP RAIL INSTALLATION WITH ALIGNMENT
SR NO | LEVEL | LOCATION | QTY (M) |  | WIR REFERANCE NO. |  | NEW | DESCRIPTON | REMARKS
|  |  | STRAIGHT | CURVE
1 | 8 | HOTEL | 12 |  | INV-AX-WR-L08-00153 |  | IMPI | TOP RAIL INSTALLATION | APPROOVE
2 | 22 | RESIDENCE | 0.75 |  | INV-AX-WR-L22-00164 |  | IMPI | TOP RAIL INSTALLATION | APPROOVE
12.75
TOTAL | INSTALLATION BY IMPI AND APPROOVE |  |  |  |  | STRAIGHT - 14 R/M | ALL APPROOVE
Note on D8: Himal Kosala: WIR not approved, location not correct

## GASKET INSTALLATION
DORCHESTER - RESIDENTIAL,HOTEL & PODIUM - WORK COMPLETION AS PER WIR APPROOVAL- JANUARY MONTH-2023 -GASKET INSTALLATION
SR NO | LEVEL | LOCATION | QTY (M) | WIR REFERANCE NO. |  | NEW | DESCRIPTON | REMARKS
1 | 25 | RESDIENTIAL | 28 | INV-AX-WR-L25-00166 |  | IMPI | GASKET INSTALLATION | APPROOVE
2 | 23 | RESDIENTIAL | 140 | INV-AX-WR-L23-00167 |  | IMPI | GASKET INSTALLATION | APPROOVE
3 | 24 | RESDIENTIAL | 43 | INV-AX-WR-L24-00168 |  | IMPI | GASKET INSTALLATION | APPROOVE
4 | 26 | RESDIENTIAL | 70 | INV-AX-WR-L26-00172 |  | IMPI | GASKET INSTALLATION | APPROOVE
5 | 27 | RESDIENTIAL | 91 | INV-AX-WR-L27-00173 |  | IMPI | GASKET INSTALLATION | APPROOVE
TOTAL |  |  | 372
TOTAL | INSTALLATION BY IMPI AND APPROOVE |  |  |  | 372 R/M | ALL APPROOVE

## TOP RAIL POLISHING
DORCHESTER - RESIDENTIAL,HOTEL & PODIUM - WORK COMPLETION AS PER WIR APPROOVAL- JANUARY MONTH-2023 - TOP RAIL POLISHING
SR NO | LEVEL | LOCATION | QTY (R/M) | WIR REFERANCE NO. |  | NEW | DESCRIPTON | REMARKS
1 | 7 | HOTEL | 100 | INV-AX-WR-L07-00160 |  | IMPI | TOP RAIL POLISHING | APPROOVE
2 | 22 | RESIDENCE | 55 | INV-AX-WR-L22-00162 |  | IMPI | TOP RAIL POLISHING | APPROOVE
3 | 16 | RESIDENCE | 61 | INV-AX-WR-L16-00163 |  | IMPI | TOP RAIL POLISHING | APPROOVE
4 | 21 | RESIDENCE | 163 | INV-AX-WR-L21-00169 |  | IMPI | TOP RAIL POLISHING | APPROOVE
5 | 22 | RESIDENCE | 68 | INV-AX-WR-L22-00170 |  | IMPI | TOP RAIL POLISHING | APPROOVE
6 | 8 | HOTEL | 89 | INV-AX-WR-L08-00174 |  | IMPI | TOP RAIL POLISHING | APPROOVE
7 | 9 | HOTEL | 122 | INV-AX-WR-L09-00175 |  | IMPI | TOP RAIL POLISHING | APPROOVE
8 | 11 | HOTEL | 89.1 | INV-AX-WR-L11-00178 |  | IMPI | TOP RAIL POLISHING | APPROOVE
9 | 12 | HOTEL | 158.4 | INV-AX-WR-L12-00179 |  | IMPI | TOP RAIL POLISHING | APPROOVE
10 | 10 | HOTEL | 111.6 | INV-AX-WR-L10-00180 |  | IMPI | TOP RAIL POLISHING | APPROOVE
11 | 13 | HOTEL | 158.4 | INV-AX-WR-L13-00181 |  | IMPI | TOP RAIL POLISHING | APPROOVE
TOTAL |  |  | 1175.5
TOTAL | INSTALLATION BY IMPI AND APPROOVE |  |  |  | QTY-1238 R/M | ALL APPROOVE
Note on D14: Himal Kosala: WIR not approved
Note on D15: Himal Kosala: WIR not approved
Note on D16: Himal Kosala: WIR not approved
Note on D17: Himal Kosala: WIR not approved

## QUANTITY DETAILS (3) (hidden)
INVENTURE METAL PRODUCTS INDUSTRIES LLC
MAIN CONTRACTOR : KHANSAHEEB
PROJECT : DORCHESTER
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO1 - BALANCE BALUSTRADE WORKS
|  | AS PER LPO |  |  |  |  | AS PER SITE
[6 empty] | MATERIAL DELIVERY |  |  |  |  | INSTALLATION
[6 empty] | MATERIAL DELIVERED | MATERIAL DELIVERY |  |  | MATERIAL | INSTALLATION | INSTALLATION |  |  | INSTALLATION | TOTAL
Items | Description | Qty | Unit | Rate | Amount | % | Previous | Present | To Date | AMOUNT | % | Previous | Present | To Date | AMOUNT
Balance balustrade work has been categories as type 1,2,3,4 amd 5 in acordance with the avaialble material on site contractor should price for verify free of defects,collect,store,handling,transporting(within the site)installation such free issued material
Type 1-Complete supply and installation by contractor
667
Supply & installation of 1200mm high Glass balustrade comprising with bottom rail,glass panels and stainless steel top U channel fixed to the concerte slab,Glass panels to be furnished 10+152.10mm Low iron clear Heat Strengthend Laminated Glass with polished Edge to be fixed with 15mm glass to glass clear gap,all as per the drawing and specification.
A | Glass Balstrade Type EWS - 102 | 130 | m | 1600 | 208000
| Bottom Channel | 40% |  |  |  | 25% | 420 |  | 420 | 168000 | 15% | 206 |  | 206 | 49440 | 217440 | 168000 | 0 | 82800 | -33360
| Glass | 50% |  |  |  | 35% | 420 |  | 420 | 235200 | 15% | 80 | 126.869 | 206.869 | 49648.56 | 284848.56 | 286720 | -51520 | 19200 | 30448.56
| Top Rail | 10% |  |  |  | 5% | 420 |  | 420 | 33600 | 5% | 176.657 | 29.343 | 206 | 16480 | 50080 | 80960 | -47360 | 51054.24 | -34574.24
B | Ditto Curved | 20 | m | 2600 | 52000 | [12 empty] | 0 |  | 0
| Bottom Channel | 40% |  |  |  | 25% | 249.07 | 65.465 | 314.535 | 204447.75 | 15% | 291 | 23.895 | 314.895 | 122809.05 | 327256.8 | 148570.5 | 55877.25 | 71760 | 51049.05
| Glass | 50% |  |  |  | 35% | 355.16 | 3.591 | 358.751 | 326463.41 | 15% | 238 | 76.6146 | 314.6146 | 122699.694 | 449163.104 | 239475.6 | 86987.81 | 92820 | 29879.694
| Top Rail | 10% |  |  |  | 5% | 206 | 53 | 259 | 33670 | 5% | 11 | 247.63 | 258.63 | 33621.9 | 67291.9 | 21840 | 11830 | 1430 | 32191.9
| Type 2 - Glass and Bottom rails supplied by Employer | [19 empty] | 460.5454
[21 empty] | 460.5454 | 253.6764
| Collect free issued glass panles,bottom rails and installation of thr compleate balustrade as stated above(under type-1).Top Channel and all other neessary fittings,fixtures and accessories shall be supply and installed by the contractor | [15 empty] | 23.6146 | 213.131 | 120 |  | -40.5454
-44.1364
C | Glass Balustrade type EWS - 102 | 575 | m | 300 | 172500
| Bottom Channel | 40% | [8 empty] | 40% | 402 | 0 | 402 | 48240 | 48240 |  |  | 48240 | 0
| Glass | 50% | [8 empty] | 50% | 395.76 | 6.237 | 401.997 | 60299.55 | 60299.55 |  | 93.131 | 96000 | -35700.45
| Top Rail | 10% | [8 empty] | 10% | 392.296 | 9.704 | 402 | 12060 | 12060 |  |  | 5970 | 6090
D | Ditto, Curved | 25 | m | 400 | 10000 | [14 empty] | 0
| Bottom Channel | [9 empty] | 40% | 138 | 0 | 138 | 22080 | 22080 |  |  | 22080 | 0
| Glass | [9 empty] | 50% | 17.38 | 0 | 17.38 | 3476 | 3476 |  |  | 3476 | 0
| Top Rail | [9 empty] | 10% | 15.1 | 0 | 15.1 | 604 | 604 |  |  | 604 | 0
Type 3- Glass Supplied by Employer
| Collect free issued glass panels and installation of the compleate balustrade as stated above (under type-1).bottom reil,stainless steel top channel and all other necessary fitting,fixtures and accessories shall be supply and installed by the contractor. | [16 empty] | 18
E | Glass Balustrade Type EWS -102 | 350 | m | 950 | 332500
| Bottom Channel | 40% |  |  |  | 25% | 238 |  | 238 | 56525 | 15% | 178 | 60 | 238 | 25365 | 81890
| Glass | 50% |  |  |  | 35% | 238 |  | 238 | 79135 | 15% | 238 |  | 238 | 33915 | 113050
| Top Rail | 10% |  |  |  | 5% | 238 |  | 238 | 11305 | 5% | 238 |  | 238 | 11305 | 22610
F | Ditto, Curved | 90 | m | 1100 | 99000
Bottom Channel
Glass
Top Rail
Type 4-Top Channel Supply installation
Supply and installation of stainless steel top U channels to installed glass balustrde including welded joints
G | Balustrade top channel supply - Stright | 110 | m | 150 | 16500 | 65% | 324 |  |  | 31590 | [5 empty] | 31590
H | Ditto , Curved | 15 | m | 200 | 3000
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.1 - STAR RAILS AND PROTECTION RAILS
Type 5 -Top Channeld installation only
Collect free issued top channel and installation(Including welded joints) to installed glass balustrade
J | Top U Channel - Stright | 90 | m | 75 | 6750
STAIR RAILS
Supply & Installation of 1200mm high glass balustarde comprising with bottom rail,glass panles and stainless steel top U Channel fixed to the concrete slab,glass panles to be furnished 10+1.2+10mm Low-Iron Clear hear Strengthened Laminated Glass with Polished edge and to be fixed with 15mm glass clear gap,all as per the drawing A-4123 abd A-4124 Specifications.
Plaza Stair Handrail
A | Glass Balustrade Type EWS - 10 & Handrail | 45 | m | 1750 | 78750
B | Ditto , Curved | 10 | m | 2750 | 27500
Retails Stair Handrail
C | Glass Balustrade Type EWS - 102 & Handrail | 30 | m | 1750 | 52500
| Bottom Channel |  |  |  |  | 25% |  | 25 | 25 | 10937.5 | [5 empty] | 10937.5
| Glass |  |  |  |  | 35%
| Top Rail |  |  |  |  | 5%
D | Ditto,Curved | 5 | m | 2750 | 13750
| Bottom Channel | 40% |  |  |  | 25% |  | 7.3 | 7.3 | 5018.75 | [5 empty] | 5018.75
| Glass | 50% |  |  |  | 35%
| Top Rail | 10% |  |  |  | 5%
WALL PROTECTION RAILS
Protection gurad/rails fixed to walk in kitchen and housekeeping area compleate with necessary fittings fixing accessories in accordance with the drawing and the specification
E | Supply and fixed of WP1:-1.5mm thick stainless steel 30 grad brush finish r Size: - 150mm high *20mm depth,2mm thick bracket,as per the typical detail drawing,1614.TYP.100 details 'C'. | 410 | m |  | Excluded
CORNER GUARDS
F | Supply and fixed of corner guard -1.5mm thick stainless steel 304 grade brush finish angle with necessary male female brackets.Stainless steel screws and Epoxy Grout Size-50*50*1800mm high
BILLS OF QUANTITIES -BALASTRADES AND ACCESSORIES
BILL NO.3 - GLASS/ALUMINIUM DOORS AND WINDOWS
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications
A | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB243 and LB244) | 2 | Nr | 42750 | 85500
B | Type D-24,Size 1900mm*2500mm.insulated,One hour fire rated with vision panel,(LB1129 and LB1130) | 2 | Nr | 42750 | 85500
GLASS/ALUMINIUM DOORS
Aluminum/Glass doors complete with frames,sub frames,transoms,stops,ironmonogeries,insulation,protective and decorative coating all in accordance with the draing and specifications.
Basement Level 01
C | Type-01 Size: 1200*1500mm | 1 | Nr |  | Excluded
D | Type-01 Size: 1500*1500mm | 4 | Nr |  | Excluded
E | Type-02 Size: 3250*1500mm | 1 | Nr |  | Excluded
F | Type-03 Size: 1250*1500mm | 2 | Nr |  | Excluded
G | Type-03 Size: 2150*1500mm | 1 | Nr |  | Excluded
H | Type-04 Size: 1500*1200mm | 1 | Nr |  | Excluded
J | Type-04 Size: 2100*1200mm | 1 | Nr |  | Excluded
LOUVERS
Louver compleate with frames,sub frames,transoms,stops,ironmoongeries,insulation,protective and decorative coatings all in accordance with the drawing and specifications
K | LW - 6 Size 6500*4200mm | 1 | Nr | 30030 | 30030 | 65% | 1 | 0 | 1 | 19519.5 | 35% | 1 | 0 | 1 | 10510.5 | 30030 | 6.5 | 4.2 | 27.3
L | LW-7 Size: 1150*4200mm | 1 | Nr | 5313 | 5313 | 65% | 1 | 0 | 1 | 3453.45 | 35% | 1 | 0 | 1 | 1859.55 | 5313 | 1.15 | 4.2 | 4.83
M | LW-8 Size 6000*2000mm | 1 | Nr | 13200 | 13200 | 65% | 1 | 0 | 1 | 8580 | 35% | 1 | 0 | 1 | 4620 | 13200 | 6 | 2 | 12
N | LW-9 Size 6000*4000mm | 1 | Nr | 26400 | 26400 | 65% | 1 | 0 | 1 | 17160 | 35% | 1 | 0 | 1 | 9240 | 26400 | 6 | 4 | 24
P | LW-10 Size:3000*4000mm | 1 | Nr | 13200 | 13200 | 65% |  | 1 | 1 | 8580 | 35% |  | 1 | 1 | 4620 | 13200 | 3 | 4 | 12
[5 empty] | 1331893 |  |  |  |  | 1253185.36 |  |  |  |  | 642893.804 | 1896079.164
2161229.164

## Sheet2 (hidden)
19.213
11.11